## Sheet1
project number | Sub agency | project category | project priorty | current cost | post payment | approved payments | paid payments | contractor id | is there any pulled contractor | total payment for prev contract | prev contractor etimad ref | project status | progress measure | current progress | planned progress | actual start date | original end date | planned end date | excpected end date | actual end date (first phase) | actual end date (last phase) | main reason of failure | prosedure | longtitude | latitude | final project status | dept | percentage %
2100074992 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 10000000 | 500000 | 8707681 | 8707681 | 1010143807 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-11-11 | 2021-05-04 | 2022-10-10 | 2022-10-10 | 2021-05-04 |  |  |  | 46.6827 | 24.7032 | منجز | No
2200226811 | أمانة / حفر الباطن | تشييد | ذات اولوية عالية | 386400 | 19320 | 386400 | 386400 | 1010288411 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2022-02-24 | 2023-02-14 | 2022-08-01 | 2022-08-01 | 2023-02-14 |  |  |  | 45.9627 | 28.3784 | منجز | No
2100195160 | رئاسة أمن الدولة / ديوان رئاسة أمن الدولة | تشييد | ذات اولوية عالية وعاجلة | 1262264.85 | 63113.2425 | 1262264.85 | 1262264.85 | 1010238249 | لا | 0 | 191101345885 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-05-10 | 2021-10-31 | 2021-10-31 | 2021-10-31 | 2021-10-31 |  |  |  | 46.6761 | 24.6988 | منجز | No
2100037575 | وزارة الصحة / التجمع الاول | تشييد | ذات اولوية عالية | 270790802 | 13539540.1 | 241756666.42 | 241756666.42 | 1010119820 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 98 | 100 | 2007-10-28 | 2010-09-24 | 2010-10-09 | 2010-10-09 | 2010-09-24 |  | ضعف كفاءة المقاول الفنية |  | 46.6894 | 24.6274 | منجز | No
2200213032 | وزارة الحرس الوطني / وكالة الشؤون الفنية | توريد وتركيب | ذات اولوية عالية | 496725.25 | 24836.2625 | 157936.4 | 157936.4 | 1010216372 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 43 | 100 | 2021-11-16 | 2022-02-10 | 2023-03-01 | 2023-03-01 |  |  |  | تم إنذار المقاول كتابيا | 46.9084 | 24.6916 | Failed | No
2100195156 | رئاسة أمن الدولة / ديوان رئاسة أمن الدولة | تشييد | ذات اولوية عالية وعاجلة | 7017614.1 | 350880.705 | 5858953.8 | 5858953.8 | 5855007433 | لا | 0 | 190501148415 | جاري | الكميات التي تم تركيبها | 90 | 100 | 2019-05-21 | 2019-08-20 | 2022-08-31 | 2022-08-31 |  |  |  |  | 39.2149 | 21.4376 | Failed | No
2200225901 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 90275543.86 | 4513777.193 | 522503.24 | 522503.24 | 4031008077 | نعم | 505173000 |  | جاري | الكميات التي تم تركيبها | 3 | 12.95 | 2021-12-29 | 2025-11-15 | 2025-11-15 | 2025-11-15 |  |  |  |  | 39.9732 | 21.3416 | متأخر | No
2200212936 | وزارة الصحة / الجوف | ترميم | ذات اولوية عالية | 2852952 | 142647.6 | 197604.77 | 0 | 3400012083 | لا | 0 | 220301227230 | جاري | الكميات التي تم تركيبها | 25 | 63 | 2022-04-10 | 2023-01-19 | 2023-04-30 | 2023-04-30 |  |  |  | تم تمديد الجدول الزمني | 38.2234 | 30.4942 | Failed | Yes
2200233656 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 18700000 | 935000 | 6422464.55 | 6422464.55 | 4031019772 | لا | 0 |  | جاري | تكلفة العمل المنجز | 34.34 | 34.34 | 2021-02-14 | 2023-01-23 | 2023-01-23 | 2023-01-23 |  |  |  |  | 39.8579 | 21.3891 | منتظم | No
2200234010 | أمانة / عسير | تشييد | ذات اولوية عالية | 772800 | 38640 | 0 | 0 | 5850031232 | لا | 0 |  | جاري | تكلفة العمل المنجز | 90 | 100 | 2022-06-13 | 2023-06-20 | 2023-06-20 | 2023-06-20 |  |  |  |  | 42.1351 | 19.1255 | متأخر | No
2100004690 | رئاسة أمن الدولة / ديوان رئاسة أمن الدولة | تشييد | ذات اولوية عالية وعاجلة | 18220737.78 | 911036.889 | 18189078.1 | 18189078.1 | 1010243700 | لا | 0 | 200301131371 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2020-03-12 | 2020-09-05 | 2022-03-17 | 2022-03-17 | 2020-09-05 |  | أوامر تغيير |  | 39.2169 | 21.4626 | منجز | No
2100025281 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 15981315 | 799065.75 | 14880554 | 14880554 | 1010269830 | لا | 0 | 190201046854 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-06-12 | 2020-06-11 | 2022-02-28 | 2022-02-28 | 2020-06-11 |  | ضعف كفاءة المقاول الفنية |  | 46.6704 | 24.7057 | منجز | No
2100067944 | أمانة / جازان | تشييد | ذات اولوية عالية | 1962786 | 98139.3 | 1904883.4 | 1904883.4 | 5906012983 | لا | 0 | 180909111386 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-09-14 | 2016-08-29 | 2019-06-06 | 2019-06-06 | 2016-08-29 |  | اخرى |  | 42.6249 | 17.1514 | منجز | No
2100059205 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 846090 | 42304.5 | 846090 | 846090 | 4031071448 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2019-01-29 | 2019-05-29 | 2019-07-12 | 2019-07-12 | 2019-05-29 |  | اخرى |  | 21.3355 | 39.9652 | منجز | No
2100050772 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 15854475 | 792723.75 | 14618253 | 14618253 | 1010269830 | لا | 0 | 190301026920 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-06-12 | 2020-06-11 | 2020-02-28 | 2020-02-28 | 2020-06-11 |  |  |  | 46.6869 | 24.7082 | منجز | No
2100062064 | وزارة الداخلية / مديرية الأمن العام | تشييد | ذات اولوية متوسطة | 2297361.86 | 114868.093 | 2173108.16 | 2173108.16 | 1010250698 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-08-26 | 2020-08-25 | 2020-08-25 | 2020-08-25 | 2020-08-25 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 43.9505 | 23.3989 | منجز | No
2100024264 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 21596388 | 1079819.4 | 5653075.61 | 5653075.61 | 5950013263 | لا | 0 | 180909073640 | مسحوب | تكلفة العمل المنجز | 79 | 80 | 2015-08-03 | 2021-06-29 | 2021-06-29 | 2021-06-29 |  |  | ضعف كفاءة المقاول الفنية |  | 44.1966 | 17.5765 | مسحوب | No
2100106746 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية وعاجلة | 596768698.88 | 29838434.944 | 493958129.2 | 493958129.2 | 1010004739 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2014-05-01 | 2016-04-20 | 2019-12-31 | 2019-12-31 | 2016-04-20 |  | تأخرصرف المستحقات المالية |  | 24.8806 | 46.9328 | منجز | No
2100103585 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 2626940 | 131347 | 1380870 | 1380870 | 1010354377 | لا | 0 |  | جاري | اخرى | 95 | 100 | 2018-11-10 | 2019-09-16 | 2021-12-31 | 2021-12-31 |  |  | تأخرصرف المستحقات المالية |  |  |  | Failed | No
2100032955 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 19266036.36 | 963301.818 | 12254755 | 9669431 | 1010076960 | لا | 0 | 201009018029 | جاري | الكميات التي تم تركيبها | 65 | 100 | 2018-08-27 | 2020-08-26 | 2022-05-09 | 2022-05-09 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 46.6759 | 24.7057 | Failed | No
2100066894 | أمانة / جازان | تشييد | ذات اولوية عالية | 2699800 | 134990 | 555529.04 | 555529.04 | 5901008401 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 82 | 100 | 2018-08-26 | 2019-08-22 | 2019-08-27 | 2019-08-27 | 2019-08-22 |  | ضعف كفاءة المقاول الفنية |  | 42.5822 | 16.8903 | منجز | No
2100100704 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 24313181.13 | 1215659.0565 | 6703554 | 3743714 | 1010076960 | لا | 0 | 190801084168 | جاري | الكميات التي تم تركيبها | 35 | 72 | 2019-12-11 | 2021-12-10 | 2023-09-11 | 2023-09-11 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 46.6745 | 24.7069 | Failed | No
2100020753 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 2712620 | 135631 | 2056720 | 2056720 | 4030071125 | لا | 0 |  | جاري | اخرى | 75.82 | 100 | 2018-02-08 | 2020-04-11 | 2020-04-11 | 2020-04-11 |  |  |  |  | 26.3204 | 50.1431 | Failed | No
2200233682 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 17581073.5 | 879053.675 | 5058281 | 5058281 | 4031046580 | لا | 0 |  | جاري | تكلفة العمل المنجز | 17.75 | 17.75 | 2022-05-18 | 2023-05-18 | 2023-05-18 | 2023-05-18 |  |  |  |  | 39.8579 | 21.3891 | منتظم | No
2100019014 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية | 27494495 | 1374724.75 | 18745530.97 | 18745530.97 | 1010267848 | لا | 0 | 181001214358 | جاري | منهجية القيمة المكتسبة | 80.74 | 100 | 2017-12-19 | 2020-11-16 | 2023-03-31 | 2023-03-31 |  |  | اخرى |  | 39.6282 | 24.394 | متأخر | No
2100023100 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية | 5760730 | 288036.5 | 419326.21 | 419326.21 | 1116002556 | لا | 0 |  | مسحوب | منهجية القيمة المكتسبة | 44.05 | 100 | 2014-09-25 | 2017-08-23 | 2022-12-31 | 2022-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 40.3658 | 23.0235 | مسحوب | No
2100036153 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية وعاجلة | 54349981.73 | 2717499.0865 | 9300848.91 | 7639614.09 | 1010031532 | لا | 0 | 180301001085 | جاري | منهجية القيمة المكتسبة | 20.33 | 69.63 | 2018-09-25 | 2021-08-23 | 2023-12-31 | 2023-12-31 |  |  | لا يوجد تأخير |  | 39.0003 | 24.3337 | Failed | No
2100022621 | أمانة / عسير | دراسات هندسية | ذات اولوية عالية | 6615000 | 330750 | 1653750 | 0 | 1010259772 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 27 | 100 | 2019-10-16 | 2020-04-13 | 2023-10-01 | 2023-10-01 |  |  | عدم اكتمال أو ضعف أعمال التصميم والدراسات |  |  |  | مسحوب | Yes
2100073500 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية عالية | 290496113.5 | 14524805.675 | 215536174.4 | 215536174.4 | 1116000094 | لا | 0 | 4046308 | جاري | تكلفة العمل المنجز | 74.2 | 74.2 | 2011-05-26 | 2014-05-26 | 2019-06-05 | 2019-06-05 |  |  | ضعف كفاءة المقاول الفنية | أخرى | 39.8508 | 21.362 | Failed | No
2100047121 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية عالية | 14075250 | 703762.5 | 8872120.92 | 8872120.92 | 4031038849 | لا | 0 | 4046266 | جاري | تكلفة العمل المنجز | 63.03 | 63.03 | 2019-03-31 | 2021-03-30 | 2023-08-30 | 2023-08-30 |  |  |  | أخرى | 39.8418 | 21.3765 | Failed | No
2100078842 | شركة المياه الوطنية / منطقة الباحة | إشراف | ذات اولوية عالية وعاجلة | 7497400 | 374870 | 5250793.08 | 5250793.08 | 1010421976 | لا | 0 | 190301020733 | جاري | التكلفة المفوترة | 77.29 | 100 | 2019-04-10 | 2022-04-10 | 2022-04-10 | 2022-04-10 |  |  | لا يوجد تأخير |  | 41.49 | 19.9989 | خدمات عامة | No
2100056906 | شركة المياه الوطنية / منطقة الباحة | إشراف | ذات اولوية عالية | 4993920 | 249696 | 4552527.98 | 4552527.98 | 1131052240 | لا | 0 | 190709013385 | منجز – استلام ابتدائي | التكلفة المفوترة | 95.36 | 100 | 2017-12-14 | 2020-12-13 | 2021-12-13 | 2021-12-13 | 2020-12-13 |  | لا يوجد تأخير |  | 41.2887 | 20.1141 | منجز | No
2200233693 | وزارة النقل والخدمات اللوجستية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 88735358.96 | 4436767.948 | 10149390.14 | 10149390.14 | 2060024520 | لا | 0 |  | جاري | تكلفة العمل المنجز | 20.97 | 18.33 | 2022-02-05 | 2024-01-13 | 2024-01-13 | 2024-01-13 |  |  |  |  | 49.8602 | 26.7659 | منتظم | No
2100013193 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 6177220 | 308861 | 5559480 | 0 | 1010064540 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 90 | 100 | 2015-02-23 | 2017-02-12 | 2019-10-28 | 2019-10-28 | 2017-02-12 |  | ضعف كفاءة المقاول الفنية |  | 46.6754 | 24.7181 | منجز | Yes
2100059732 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية | 19597544.6 | 979877.23 | 11844756 | 11844756 | 1132002394 | لا | 0 | 181009157545 | جاري | منهجية القيمة المكتسبة | 67.05 | 100 | 2012-11-03 | 2015-10-01 | 2022-12-31 | 2022-12-31 |  |  | لا يوجد تأخير |  | 40.6569 | 23.322 | Failed | No
2100095771 | أمانة / عسير | دراسات هندسية | ذات اولوية عالية | 27447500 | 1372375 | 1837500 | 840000 | 4030283265 | لا | 0 |  | جاري | تكلفة العمل المنجز | 97 | 100 | 2019-01-21 | 2021-01-10 | 2023-03-31 | 2023-03-31 |  |  | عدم اكتمال أو ضعف أعمال التصميم والدراسات |  |  |  | خدمات عامة | No
2100000475 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية وعاجلة | 169081695.24 | 8454084.762 | 127062184.65 | 127062184.65 | 1010004739 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2015-10-20 | 2017-10-10 | 2020-08-24 | 2020-08-24 | 2017-10-10 |  | تأخرصرف المستحقات المالية |  | 16.9872 | 42.5667 | منجز | No
2100104484 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 17474916.12 | 873745.806 | 15549671.22 | 15549671.22 | 4031069720 | لا | 0 | 180709030574 | جاري | تكلفة العمل المنجز | 98.15 | 100 | 2017-10-24 | 2018-10-13 | 2022-12-31 | 2022-12-31 |  |  | تأخرصرف المستحقات المالية |  | 39.1677 | 21.5008 | منتظم | No
2100005633 | أمانة / العاصمة المقدسة | دراسة بيئية | ذات اولوية متوسطة | 2877250 | 143862.5 | 2877250 | 2877250 | 2050003582 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2018-02-11 | 2020-02-10 | 2020-02-10 | 2020-02-10 | 2020-02-10 | 2020-02-18 | اخرى |  |  |  | منجز | No
2100021361 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية وعاجلة | 22468397.23 | 1123419.8615 | 3503474.68 | 3503474.68 | 1010031532 | لا | 0 | 190301005272 | جاري | منهجية القيمة المكتسبة | 20.34 | 25.05 | 2019-06-09 | 2022-05-07 | 2023-12-31 | 2023-12-31 |  |  | لا يوجد تأخير |  | 39.6005 | 24.4595 | منتظم | No
2100043326 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية | 22605563.04 | 1130278.152 | 11639365.04 | 11639365.04 | 4650011120 | لا | 0 | 181009158723 | جاري | منهجية القيمة المكتسبة | 76.76 | 100 | 2013-09-01 | 2016-07-30 | 2022-12-31 | 2022-12-31 |  |  | لا يوجد تأخير |  | 37.9533 | 26.5665 | Failed | No
2100093822 | أمانة / جازان | تشييد | ذات اولوية عالية | 46698750 | 2334937.5 | 9218449.08 | 9218449.08 | 5900000115 | لا | 0 | 190401064816 | جاري | اخرى | 20 | 100 | 2019-09-23 | 2021-09-12 | 2021-09-13 | 2021-09-13 |  |  | ضعف كفاءة المقاول الفنية |  | 42.632 | 16.8843 | Failed | No
2100024065 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2371610 | 118580.5 | 2109338.2 | 0 | 1010219044 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 89 | 100 | 2015-05-26 | 2016-08-18 | 2016-10-28 | 2016-10-28 | 2016-08-18 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 46.6754 | 24.7044 | منجز | Yes
2100040121 | شركة المياه الوطنية / منطقة نجران | تشييد | ذات اولوية عالية | 66472851.4 | 3323642.57 | 62316473.44 | 62316473.44 | 5950005891 | لا | 0 | 180709033245 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2014-11-09 | 2017-10-06 | 2019-09-19 | 2019-09-19 | 2017-10-06 | 2021-07-11 | لا يوجد تأخير |  | 44.2341 | 17.5757 | منجز | No
2100019504 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 7937500 | 396875 | 10000 | 10000 | 4031041927 | لا | 0 |  | جاري | التكلفة المفوترة | 0.52 | 0.52 | 2019-06-11 | 2022-08-24 | 2022-08-24 | 2022-08-24 |  |  |  |  | 39.3829 | 21.9002 | متأخر | No
2100099385 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية وعاجلة | 30000000 | 1500000 | 5726667.94 | 5726667.94 | 1010262459 | لا | 0 | 180201000167 | مسحوب | منهجية القيمة المكتسبة | 32.73 | 100 | 2018-04-11 | 2021-03-09 | 2022-09-20 | 2022-09-20 |  |  | لا يوجد تأخير |  | 39.6921 | 24.5225 | مسحوب | No
2100202510 | شركة المياه الوطنية / منطقة نجران | تشييد | ذات اولوية عالية وعاجلة | 25805270 | 1290263.5 | 11292240.9 | 11292240.9 | 5950002185 | لا | 0 | 180709021709 | جاري | منهجية القيمة المكتسبة | 43.75 | 51.37 | 2021-05-20 | 2022-11-02 | 2023-01-31 | 2023-01-31 |  |  |  |  | 47.1167 | 17.485 | متأخر | No
2100084383 | وزارة الداخلية / مديرية الأمن العام | تشييد | ذات اولوية متوسطة | 2269150.8 | 113457.54 | 1996998 | 1996998 | 1010250698 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-10-29 | 2020-10-29 | 2021-01-29 | 2021-01-29 | 2020-10-29 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 41.2742 | 30.8313 | منجز | No
2100048720 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 79096639.58 | 3954831.979 | 32286240.93 | 31802275.34 | 4030157663 | لا | 0 | 180709032087 | جاري | تكلفة العمل المنجز | 49 | 63 | 2015-03-09 | 2016-08-22 | 2024-12-31 | 2024-12-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.1677 | 21.5008 | متأخر | No
2100075320 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 95075376.82 | 4753768.841 | 72377066.56 | 72377066.56 | 1010154882 | لا | 0 | 180809057528 | جاري | الكميات التي تم تركيبها | 75.041 | 94 | 2014-09-05 | 2015-11-21 | 2020-02-11 | 2020-02-11 |  |  | التنسيق مع أصحاب المصلحه (خدمات |  | 46.6786 | 24.7082 | Failed | No
2100073312 | المؤسسة العامة لتحلية المياه المالحة | تشييد | ذات اولوية عالية | 5278840584 | 263942029.2 | 4743104537.97 | 4743104537.97 | 1010440093 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 98.8 | 100 | 2017-05-17 | 2024-03-31 | 2024-03-31 | 2024-03-31 |  |  | تأخرصرف المستحقات المالية |  | 39.5274 | 20.6832 | منتظم | No
2100018200 | وزارة البيئة والمياة والزراعة | دراسات هندسية | ذات اولوية متوسطة | 441000 | 22050 | 441000 | 441000 | 1010441731 | لا | 0 | 190301084791 | جاري | تكلفة العمل المنجز | 100 | 100 | 2019-05-25 | 2019-05-26 | 2019-05-26 | 2019-05-26 |  |  |  |  | 46.7564 | 24.7218 | خدمات عامة | No
2100041602 | أمانة / الرياض | دراسات هندسية | ذات اولوية متوسطة | 9990000 | 499500 | 9990000 | 8846482 | 1010468431 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-10-07 | 2018-10-06 | 2018-10-06 | 2018-10-06 | 2018-10-06 |  | اخرى |  |  |  | منجز | No
2100018211 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية وعاجلة | 22016163.31 | 1100808.1655 | 10566201.86 | 10566201.86 | 4650011120 | لا | 0 | 181009153555 | مسحوب | منهجية القيمة المكتسبة | 56 | 100 | 2013-01-27 | 2015-12-26 | 2024-04-03 | 2024-04-03 |  |  | ضعف كفاءة المقاول الفنية |  | 39.2916 | 25.703 | مسحوب | No
2100074970 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 8828052 | 441402.6 | 7360458.5 | 0 | 1128001788 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-09-24 | 2017-09-08 | 2020-04-21 | 2020-04-21 | 2017-09-08 |  | ضعف كفاءة المقاول الفنية |  | 46.6843 | 24.7075 | منجز | Yes
2100010054 | أمانة / عسير | تشييد | ذات اولوية عالية | 1508350 | 75417.5 | 776080 | 776080 | 5858041259 | لا | 0 |  | جاري | تكلفة العمل المنجز | 65 | 100 | 2015-08-16 | 2016-02-12 | 2023-03-31 | 2023-03-31 |  |  | تأخرصرف المستحقات المالية |  | 42.7302 | 18.3003 | Failed | No
2100087231 | شركة المياه الوطنية / منطقة نجران | تشييد | ذات اولوية عالية | 153126982.32 | 7656349.116 | 110733453 | 110733453 | 5950000060 | لا | 0 | 180709028288 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2014-11-16 | 2017-04-20 | 2021-02-13 | 2021-02-13 | 2017-04-20 |  | لا يوجد تأخير |  | 44.2341 | 17.5757 | منجز | No
2100045975 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 24512021 | 1225601.05 | 19950584 | 19950584 | 1010005046 | لا | 0 | 181209545147 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 95 | 100 | 2014-08-06 | 2019-03-30 | 2019-03-30 | 2019-03-30 |  |  |  |  | 46.6759 | 24.7082 | Failed | No
2100073430 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 11688460 | 584423 | 10176929.35 | 10176929.35 | 4030044382 | لا | 0 | 180909105878 | منجز – استلام نهائي | تكلفة العمل المنجز | 95.5 | 95.5 | 2015-12-08 | 2018-05-11 | 2020-05-22 | 2020-05-22 | 2018-05-11 | 2022-03-07 |  |  | 39.869 | 21.3731 | منجز | No
2100066861 | أمانة / جازان | تشييد | ذات اولوية عالية | 21029450.5 | 1051472.525 | 21029450.5 | 21029450.5 | 5900007895 | لا | 0 | 180809051671 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 96 | 100 | 2014-03-26 | 2015-09-17 | 2019-12-31 | 2019-12-31 | 2015-09-17 |  | اخرى |  | 42.8484 | 16.9651 | منجز | No
2100035582 | أمانة / جازان | تشييد | ذات اولوية عالية | 13409260 | 670463 | 12068334 | 12068334 | 1010193433 | لا | 0 | 181109368381 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-09-06 | 2016-02-28 | 2020-02-02 | 2020-02-02 | 2016-02-28 |  | ضعف كفاءة المقاول الفنية |  | 42.8445 | 16.9682 | منجز | No
2100033865 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 7764000 | 388200 | 7233974 | 0 | 1012001538 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 85 | 100 | 2015-08-19 | 2017-08-08 | 2017-08-08 | 2017-08-08 | 2017-08-08 |  | ضعف كفاءة المقاول الفنية |  | 46.7111 | 24.7094 | منجز | Yes
2100060642 | شركة المياه الوطنية / منطقة نجران | تشييد | ذات اولوية عالية | 32416750 | 1620837.5 | 27112213 | 25737289.13 | 5950000060 | لا | 0 | 180709028153 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 94.4 | 100 | 2014-12-18 | 2017-05-22 | 2022-03-11 | 2022-03-11 | 2017-05-22 |  | تأخرصرف المستحقات المالية |  | 44.2341 | 17.5757 | منجز | No
2100019401 | شركة المياه الوطنية / منطقة نجران | تشييد | ذات اولوية عالية | 72987450 | 3649372.5 | 44178517.49 | 44178517.49 | 5850025975 | لا | 0 | 180701023912 | ايقاف كلي | منهجية القيمة المكتسبة | 68.1 | 82.45 | 2018-02-04 | 2021-01-02 | 2022-04-12 | 2022-04-12 |  |  | لا يوجد تأخير |  | 44.2341 | 17.5757 | Failed | No
2200233726 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 147939001.5 | 7396950.075 | 22260167.01 | 22260167.01 | 4031042604 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 16.2 | 37.4 | 2022-02-20 | 2023-11-03 | 2023-11-03 | 2023-11-03 |  |  |  |  | 46.6736 | 24.6258 | متأخر | No
2200212984 | المؤسسة العامة للتقاعد | تشييد | ذات اولوية عالية | 28500000 | 1425000 | 0 | 0 | 4032025725 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 30 | 16.82 | 2022-01-30 | 2023-01-30 | 2023-01-30 | 2023-01-30 |  |  |  |  | 39.1266 | 21.7249 | منتظم | No
2100092934 | أمانة / الرياض | دراسات هندسية | ذات اولوية متوسطة | 14800000 | 740000 | 14800000 | 13515990 | 1010433483 | لا | 0 |  | منجز – استلام نهائي | التكلفة المفوترة | 100 | 100 | 2015-07-22 | 2019-04-22 | 2019-04-22 | 2019-04-22 |  | 2019-04-22 | اخرى |  |  |  | منجز | No
2100199500 | جامعة شقراء | تشييد | ذات اولوية عالية وعاجلة | 69299292.92 | 3464964.646 | 43633153.27 | 43633153.27 | 1116003807 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 70 | 100 | 2018-09-13 | 2019-07-10 | 2023-04-01 | 2023-04-01 |  |  |  |  | 42.9208 | 23.9167 | Failed | No
2100092234 | شركة المياه الوطنية / منطقة نجران | تشييد | ذات اولوية عالية | 68924783 | 3446239.15 | 61630322.6 | 61630322.6 | 5950009827 | لا | 0 | 190409065333 | جاري | منهجية القيمة المكتسبة | 93 | 100 | 2018-04-08 | 2020-03-17 | 2022-06-01 | 2022-06-01 |  |  | لا يوجد تأخير |  | 44.2341 | 17.5757 | Failed | No
2100080603 | أمانة / الرياض | تشييد | ذات اولوية عالية | 252859918.42 | 12642995.921 | 21812760 | 21812760 | 1010044185 | لا | 0 | 190601011671 | جاري | الكميات التي تم تركيبها | 90.19 | 94.9 | 2019-08-25 | 2023-07-31 | 2023-07-31 | 2023-07-31 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6759 | 24.7007 | منتظم | No
2100001293 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية وعاجلة | 31767129 | 1588356.45 | 10981905.99 | 4628306.34 | 4030087384 | لا | 0 | 181009152412 | جاري | منهجية القيمة المكتسبة | 23.2 | 26.9 | 2020-06-07 | 2023-05-05 | 2023-05-05 | 2023-05-05 |  |  | لا يوجد تأخير |  | 38.1161 | 25.0633 | منتظم | No
2100038441 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | لم تعد تحتاجها الجهة | 13474997.37 | 673749.8685 | 986110.92 | 986110.92 | 1010196247 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 7.32 | 7.32 | 2013-10-24 | 2015-10-01 | 2015-10-01 | 2015-10-01 |  |  | اخرى |  | 39.9177 | 21.4247 | مسحوب | No
2100037332 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1965175 | 98258.75 | 1730000 | 0 | 1010276830 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 87 | 100 | 2015-10-07 | 2016-12-30 | 2019-09-14 | 2019-09-14 | 2016-12-30 |  | ضعف كفاءة المقاول الفنية |  | 46.669 | 24.7152 | منجز | Yes
2100101393 | شركة المياه الوطنية / منطقة نجران | تشييد | ذات اولوية عالية وعاجلة | 66585192 | 3329259.6 | 20755516.33 | 14729368.33 | 5950005891 | لا | 0 | 190501111280 | جاري | منهجية القيمة المكتسبة | 68.5 | 54.36 | 2019-10-13 | 2022-03-17 | 2024-01-27 | 2024-01-27 |  |  | تصاريح أعمال التنفيذ |  | 44.3204 | 17.534 | منتظم | No
2100001842 | مدينة الملك فهد الطبية | تشييد | ذات اولوية عالية | 13191962.28 | 659598.114 | 13153712.36 | 13153712.36 | 1010217074 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-08-27 | 2020-02-27 | 2021-02-14 | 2021-02-14 | 2020-02-27 |  |  |  | 46.702 | 24.686 | منجز | No
2100008271 | المؤسسة العامة لتحلية المياه المالحة | تشييد | ذات اولوية عالية | 1471182285 | 73559114.25 | 1332677359.41 | 1332677359.41 | 4030289014 | لا | 0 | 181201517830 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 98.4 | 100 | 2019-01-13 | 2021-12-30 | 2022-08-15 | 2022-08-15 | 2021-12-30 |  | لا يوجد تأخير |  | 39.3551 | 22.4796 | منجز | No
2100079914 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية وعاجلة | 9297598 | 464879.9 | 6863068.4 | 6863068.4 | 4030163543 | لا | 0 | 180709033690 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 84.93 | 100 | 2014-12-20 | 2017-11-17 | 2019-03-12 | 2019-03-12 |  | 2017-11-17 | لا يوجد تأخير |  | 39.6005 | 24.4595 | منجز | No
2100089935 | شركة المياه الوطنية / منطقة نجران | تشييد | ذات اولوية عالية وعاجلة | 139999995 | 6999999.75 | 13566324.56 | 13566324.56 | 5950008379 | لا | 0 | 191201069835 | مسحوب | منهجية القيمة المكتسبة | 15.34 | 99.66 | 2018-11-06 | 2021-10-05 | 2024-08-23 | 2024-08-23 |  |  | اخرى |  | 44.2341 | 17.5757 | مسحوب | No
2100087835 | جامعة نجران | تشييد | ذات اولوية عالية وعاجلة | 440146398 | 22007319.9 | 396131758 | 396131758 | 1010175494 | لا | 0 | 211109259928 | جاري | التكلفة المفوترة | 99 | 100 | 2012-03-13 | 2016-03-03 | 2022-12-21 | 2022-12-21 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 44.2341 | 17.5757 | متأخر | No
2100055123 | رئاسة الحرس الملكي | تشييد | ذات اولوية عالية وعاجلة | 8686051.41 | 434302.5705 | 8686051.41 | 8686051.41 | 1010235877 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-05-31 | 2020-05-20 | 2020-12-02 | 2020-12-02 | 2020-05-20 |  |  |  | 39.1469 | 21.536 | منجز | No
2100002262 | أمانة / حائل | تشييد | ذات اولوية عالية وعاجلة | 24789632 | 1239481.6 | 24537579.41 | 24537579.41 | 1010069549 | لا | 0 | 180909067364 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-07-07 | 2018-12-29 | 2020-06-30 | 2020-06-30 | 2018-12-29 |  |  |  | 41.6911 | 27.5175 | منجز | No
2200233741 | أمانة / الرياض | الخدمات الاستشارية | ذات اولوية متوسطة | 14986786.54 | 749339.327 | 3787997.54 | 3787997.54 | 1010348048 | لا | 0 |  | جاري | اخرى | 5.35 | 10 | 2022-03-23 | 2023-11-03 | 2023-11-03 | 2023-11-03 |  |  |  |  | 46.6736 | 24.6258 | خدمات عامة | No
2100024566 | وزارة الرياضة | تشييد | ذات اولوية عالية | 125822728.83 | 6291136.4415 | 34853314 | 34853314 | 1010016736 | نعم | 700019.77 | 180909096663 | جاري | الكميات التي تم تركيبها | 67 | 100 | 2012-07-14 | 2015-07-15 | 2019-01-30 | 2019-01-30 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | Failed | No
2100043433 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية وعاجلة | 6821425 | 341071.25 | 4902197.55 | 4902197.55 | 4040068130 | لا | 0 | 190701021212 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-10-03 | 2021-09-11 | 2021-08-24 | 2021-08-24 | 2021-09-11 |  | لا يوجد تأخير |  | 39.6005 | 24.4595 | منجز | No
2100104543 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية وعاجلة | 509511072 | 25475553.6 | 414715785.49 | 372804638 | 1010052129 | لا | 0 | 181009152732 | مسحوب | منهجية القيمة المكتسبة | 87.2 | 100 | 2009-07-15 | 2012-06-12 | 2021-12-31 | 2021-12-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 37.857 | 26.1287 | مسحوب | No
2200233752 | أمانة / الرياض | الخدمات الاستشارية | ذات اولوية متوسطة | 14986786.54 | 749339.327 | 4238419.92 | 4238419.92 | 1010348048 | لا | 0 |  | جاري | اخرى | 28.38 | 33.47 | 2022-01-30 | 2023-11-24 | 2023-11-24 | 2023-11-24 |  |  |  |  | 46.6736 | 24.6258 | خدمات عامة | No
2100094231 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية | 6993944 | 349697.2 | 4338477.36 | 3606296.97 | 4030087384 | لا | 0 | 180201000172 | جاري | منهجية القيمة المكتسبة | 75.77 | 82.97 | 2018-04-08 | 2021-03-06 | 2022-12-31 | 2022-12-31 |  |  | اخرى |  | 39.3119 | 24.6383 | متأخر | No
2100023715 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية وعاجلة | 27104740 | 1355237 | 25679490.5 | 25679490.5 | 1010231237 | لا | 0 | 180909066232 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 98.7 | 2015-10-08 | 2018-03-13 | 2021-06-28 | 2021-06-28 | 2018-03-13 |  | لا يوجد تأخير |  | 39.6565 | 24.4713 | منجز | No
2100191144 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية وعاجلة | 30053640 | 1502682 | 5717089.35 | 3514310.35 | 5855010714 | لا | 0 | 201101049509 | جاري | منهجية القيمة المكتسبة | 41.9 | 45.3 | 2021-06-08 | 2022-11-22 | 2022-11-22 | 2022-11-22 |  |  |  |  | 41.4865 | 19.7112 | منتظم | No
2100028302 | رئاسة الحرس الملكي | تشييد | ذات اولوية عالية وعاجلة | 34632700 | 1731635 | 27559435.68 | 27559435.68 | 1128004627 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 84 | 85 | 2019-05-27 | 2021-05-26 | 2023-06-10 | 2023-06-10 |  |  |  |  | 46.6972 | 24.6554 | منتظم | No
2100086656 | المؤسسة العامة لتحلية المياه المالحة | تشييد | ذات اولوية عالية | 368012249.57 | 18400612.4785 | 331211025.35 | 331211025.35 | 1010012911 | لا | 0 | 190501016525 | جاري | منهجية القيمة المكتسبة | 97.5 | 97.4 | 2019-07-22 | 2023-09-09 | 2023-09-09 | 2023-09-09 |  |  | تأخرصرف المستحقات المالية |  | 45.5629 | 27.9068 | منتظم | No
2100091910 | المؤسسة العامة لتحلية المياه المالحة | تشييد | ذات اولوية عالية | 1178000000 | 58900000 | 703444001.42 | 703444001.42 | 1010004739 | لا | 0 | 190801047447 | جاري | منهجية القيمة المكتسبة | 78.5 | 100 | 2020-08-04 | 2022-08-04 | 2022-08-04 | 2022-08-04 |  |  | اخرى |  | 50.2073 | 26.179 | متأخر | No
2100104285 | جامعة جازان | تشييد | ذات اولوية متوسطة | 3589484 | 179474.2 | 1810934.96 | 1810934.96 | 4030133619 | لا | 0 | 181109307359 | جاري | الكميات التي تم تركيبها | 50 | 100 | 2017-09-06 | 2018-09-11 | 2023-12-31 | 2023-12-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.8052 | 16.9507 | Failed | No
2100014125 | أمانة / جازان | تشييد | ذات اولوية عالية | 785950.9 | 39297.545 | 667437.73 | 667437.73 | 2050069840 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-06-17 | 2019-06-10 | 2019-06-10 | 2019-06-10 | 2019-06-10 |  | اخرى |  | 42.596 | 16.9549 | منجز | No
2200233763 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 128817645.6 | 6440882.28 | 18208250.05 | 18208250.05 | 1010010506 | لا | 0 |  | جاري | اخرى | 4.95 | 25.34 | 2022-05-29 | 2024-02-21 | 2024-01-21 | 2024-01-21 |  |  |  |  | 46.6736 | 24.6258 | متأخر | No
2100103294 | جامعة جازان | تشييد | ذات اولوية متوسطة | 202552002.7 | 10127600.135 | 144008269.31 | 142644302.35 | 4030154193 | لا | 0 | 181009161888 | جاري | الكميات التي تم تركيبها | 78 | 96 | 2013-01-07 | 2016-06-20 | 2024-01-01 | 2024-01-01 |  |  | تأخرصرف المستحقات المالية |  | 42.5497 | 16.9761 | متأخر | No
2100000372 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية وعاجلة | 24937457 | 1246872.85 | 19039538.16 | 19039538.16 | 4030007856 | لا | 0 | 181101368650 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 96 | 100 | 2018-12-23 | 2021-11-21 | 2022-04-30 | 2022-04-30 | 2021-11-21 |  | لا يوجد تأخير |  | 39.6005 | 24.4595 | منجز | No
2100042416 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية منخفضة | 94876996.55 | 4743849.8275 | 85299906.41 | 85263317.55 | 1116000094 | لا | 0 | 180809055348 | مسحوب | منهجية القيمة المكتسبة | 90.7 | 100 | 2011-10-15 | 2014-09-12 | 2024-12-31 | 2024-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 41.2405 | 19.951 | مسحوب | No
2100065295 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 609600 | 30480 | 41468 | 0 | 1010129395 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 80 | 100 | 2013-12-28 | 2015-03-23 | 2022-01-19 | 2022-01-19 |  |  | ضعف كفاءة المقاول الفنية |  | 45.28 | 24.066 | مسحوب | Yes
2100092153 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 22040003.91 | 1102000.1955 | 0 | 0 | 5900013632 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 1 | 100 | 2015-10-03 | 2017-03-27 | 2017-03-28 | 2017-03-28 |  |  | اخرى |  | 42.5487 | 16.8599 | مسحوب | No
2200233774 | أمانة / الأحساء | توريد وتركيب | ذات اولوية متوسطة | 1695146 | 84757.3 | 805977.5 | 805977.5 | 2050018628 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 24 | 20 | 2022-08-07 | 2023-08-02 | 2023-08-02 | 2023-08-02 |  |  |  |  | 49.5651 | 25.3718 | منتظم | No
2100194062 | وزارة الداخلية / المديرية العامة لحرس الحدود | تشييد | ذات اولوية عالية | 24214429.4 | 1210721.47 | 21694092.9 | 21694092.9 | 4030140033 | لا | 0 | 190601039824 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 93 | 100 | 2019-10-27 | 2022-01-17 | 2022-12-18 | 2022-12-18 |  |  |  |  | 42.5547 | 16.8729 | Failed | No
2100061095 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية وعاجلة | 17200965 | 860048.25 | 15629453.95 | 15629453.95 | 4650043888 | لا | 0 | 190409010379 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2014-12-22 | 2016-11-30 | 2019-12-09 | 2019-12-09 |  | 2016-11-30 | لا يوجد تأخير |  | 39.6571 | 24.4058 | منجز | No
2100039303 | وزارة الداخلية / مديرية الأمن العام | تشييد | ذات اولوية عالية | 1854573 | 92728.65 | 1854573 | 1854573 | 4031190271 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-10-13 | 2020-10-13 | 2020-10-13 | 2020-10-13 | 2020-10-13 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.2487 | 21.4986 | منجز | No
2100059920 | جامعة جازان | تشييد | ذات اولوية عالية وعاجلة | 193827568.3 | 9691378.415 | 63465188.21 | 60545905.01 | 1010094890 | لا | 0 | 191001287293 | جاري | الكميات التي تم تركيبها | 34 | 83 | 2020-06-18 | 2022-04-17 | 2025-01-07 | 2025-01-07 |  |  | اخرى |  | 42.5471 | 16.9776 | Failed | No
2100060130 | جامعة جازان | تشييد | ذات اولوية عالية | 171161324.01 | 8558066.2005 | 113989790.69 | 108551599.84 | 1010233574 | لا | 0 | 181109360697 | جاري | الكميات التي تم تركيبها | 83 | 96 | 2012-12-30 | 2016-06-12 | 2024-01-01 | 2024-01-01 |  |  | تأخرصرف المستحقات المالية |  | 42.5545 | 16.9813 | متأخر | No
2200233796 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 18616200 | 930810 | 142500 | 0 | 2060023127 | لا | 0 |  | جاري | تكلفة العمل المنجز | 5 | 5 | 2022-09-04 | 2024-02-26 | 2024-02-26 | 2024-02-26 |  |  |  |  | 49.6964 | 25.4092 | منتظم | Yes
2100018340 | أمانة / الجوف | دراسة الجدوى | ذات اولوية متوسطة | 846000 | 42300 | 846000 | 846000 | 3400011727 | لا | 0 | 190201033397 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-10-14 | 2019-10-10 | 2019-11-10 | 2019-11-10 | 2019-10-10 |  | اخرى |  | 38.2216 | 30.5155 | منجز | No
2100191122 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية وعاجلة | 64401300.69 | 3220065.0345 | 2849313.1 | 2061774.95 | 4030021112 | لا | 0 | 200909007954 | جاري | منهجية القيمة المكتسبة | 21.73 | 21.55 | 2020-12-24 | 2022-12-03 | 2023-08-31 | 2023-08-31 |  |  |  |  | 41.4519 | 19.7506 | منتظم | No
2100075880 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 851335 | 42566.75 | 555428 | 0 | 1010258205 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 18 | 2019-02-06 | 2021-03-27 | 2021-03-27 | 2021-03-27 | 2021-03-27 |  |  |  | 45.4924 | 25.0808 | منجز | Yes
2100016575 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2857664 | 142883.2 | 0 | 0 | 4650020435 | لا | 0 |  | لم يبدأ | التكلفة المفوترة | 0 | 100 | 2016-08-22 | 2017-11-15 | 2024-06-15 | 2024-06-15 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.6005 | 24.4595 | Failed | No
2100021125 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 4570907.5 | 228545.375 | 2870555 | 2870555 | 1010151477 | لا | 0 |  | مسحوب | التكلفة المفوترة | 28 | 100 | 2005-12-30 | 2007-10-08 | 2007-10-08 | 2007-10-08 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | مسحوب | No
2200233800 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 23988351.4 | 1199417.57 | 1343200 | 1343200 | 2060023127 | لا | 0 |  | جاري | تكلفة العمل المنجز | 8 | 8 | 2022-09-04 | 2024-02-26 | 2024-02-26 | 2024-02-26 |  |  |  |  | 49.5919 | 25.3565 | منتظم | No
2100041554 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية عالية وعاجلة | 14891176.85 | 744558.8425 | 13091916.82 | 13091916.82 | 1010199999 | لا | 0 | 191009198685 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 99 | 100 | 2019-01-03 | 2020-09-02 | 2021-05-06 | 2021-05-06 |  |  | لا يوجد تأخير |  | 46.1365 | 24.5973 | Failed | No
2100107715 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 521001541.01 | 26050077.0505 | 267258652.86 | 250683987.18 | 4030008659 | لا | 0 |  | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2013-09-09 | 2015-09-08 | 2022-08-30 | 2022-08-30 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال | أخرى | 39.1677 | 21.5008 | Failed | No
2100093542 | شركة المياه الوطنية / منطقة المدينة المنورة | إشراف | ذات اولوية عالية وعاجلة | 13240000 | 662000 | 12654366.69 | 10473366.69 | 4030283265 | لا | 0 | 180709036109 | جاري | تكلفة العمل المنجز | 0 | 0 | 2011-12-18 | 2017-08-16 | 2022-02-16 | 2022-02-16 |  |  | لا يوجد تأخير |  | 39.5891 | 24.5454 | خدمات عامة | No
2100097285 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية وعاجلة | 5416032 | 270801.6 | 5415959.96 | 5415959.96 | 5855021983 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-11-22 | 2020-10-31 | 2020-10-26 | 2020-10-26 | 2020-10-31 |  | لا يوجد تأخير |  | 41.4374 | 19.7864 | منجز | No
2100041753 | شركة المياه الوطنية / منطقة حائل | إشراف | ذات اولوية عالية | 2991500 | 149575 | 7492239.87 | 7458639.87 | 1131052239 | لا | 0 | 180709022138 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-06-02 | 2017-06-02 | 2021-10-05 | 2021-10-05 | 2017-06-02 |  | لا يوجد تأخير |  | 41.739 | 27.3029 | منجز | No
2100102815 | شركة المياه الوطنية / منطقة الباحة | إشراف | ذات اولوية عالية وعاجلة | 2151607.5 | 107580.375 | 1963022.07 | 1963022.07 | 4031087359 | لا | 0 | 191201124110 | منجز – استلام ابتدائي | التكلفة المفوترة | 96.34 | 100 | 2020-03-30 | 2021-09-30 | 2022-03-31 | 2022-03-31 | 2021-09-30 |  | لا يوجد تأخير |  | 41.4712 | 20.0154 | منجز | No
2100194036 | وزارة الداخلية / المديرية العامة لحرس الحدود | تشييد | ذات اولوية عالية | 1046155.9 | 52307.795 | 1046155.9 | 1046155.9 | 7016389111 | لا | 0 | 210201082798 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2021-01-20 | 2022-01-20 | 2022-01-20 | 2022-01-20 | 2022-01-20 |  |  |  | 39.1075 | 21.5845 | منجز | No
2100192242 | جامعة جازان | توريد وتركيب | ذات اولوية متوسطة | 1922739 | 96136.95 | 0.01 | 0.01 | 5855027386 | لا | 0 | 200701033809 | لم يبدأ | الكميات التي تم تركيبها | 0.1 | 0.1 | 2022-01-01 | 2022-10-30 | 2023-10-30 | 2023-10-30 |  |  |  |  | 42.543 | 16.9643 | متأخر | No
2100085385 | أمانة / الجوف | إشراف | ذات اولوية عالية وعاجلة | 4563317.14 | 228165.857 | 4563317.14 | 4563317.14 | 1010325651 | لا | 0 | 191101345243 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-10-15 | 2021-10-02 | 2022-01-31 | 2022-01-31 | 2021-10-02 |  | اخرى |  | 40.1043 | 29.878 | منجز | No
2100000593 | جامعة نجران | تشييد | ذات اولوية عالية | 56986984 | 2849349.2 | 46749683 | 46749683 | 2066001761 | لا | 0 | 181109339657 | جاري | الكميات التي تم تركيبها | 98 | 100 | 2013-06-14 | 2015-11-18 | 2021-12-31 | 2021-12-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 44.2341 | 17.5757 | Failed | No
2100105906 | جامعة نجران | تشييد | ذات اولوية عالية وعاجلة | 55000000 | 2750000 | 49499718 | 49499718 | 5950009827 | لا | 0 | 181209511340 | جاري | الكميات التي تم تركيبها | 96 | 100 | 2014-12-21 | 2017-11-17 | 2021-12-15 | 2021-12-15 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 44.2341 | 17.5757 | Failed | No
2100007405 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية وعاجلة | 47640405.74 | 2382020.287 | 29349878.34 | 27355134.74 | 4650049275 | لا | 0 | 180709025749 | جاري | منهجية القيمة المكتسبة | 91.98 | 98.8 | 2018-12-04 | 2021-11-01 | 2022-10-25 | 2022-10-25 |  |  | عدم واقعية الجدول الزمني |  | 41.2405 | 19.951 | متأخر | No
2200213043 | وزارة الحرس الوطني / وكالة الشؤون الفنية | أخرى | ذات اولوية عالية | 3023690.4 | 151184.52 | 2712786.75 | 2712786.75 | 4030171296 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2021-11-02 | 2022-11-01 | 2022-11-01 | 2022-11-01 | 2022-11-01 |  |  |  | 46.8839 | 24.6562 | منجز | No
2200233811 | أمانة / الأحساء | توريد وتركيب | ذات اولوية متوسطة | 15490787.85 | 774539.3925 | 432450 | 432450 | 2060023127 | لا | 0 |  | جاري | تكلفة العمل المنجز | 4 | 4 | 2022-09-04 | 2023-08-30 | 2023-08-30 | 2023-08-30 |  |  |  |  | 49.6922 | 25.4073 | منتظم | No
2100090893 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 31957182.6 | 1597859.13 | 0 | 0 | 1113001164 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 43 | 100 | 2019-07-25 | 2022-01-21 | 2022-01-22 | 2022-01-22 |  |  |  |  | 45.2565 | 25.2397 | Failed | No
2100014980 | وزارة الداخلية / مديرية الأمن العام | تشييد | ذات اولوية متوسطة | 2197249.53 | 109862.4765 | 2197249.53 | 2197249.53 | 1010250698 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-01-08 | 2021-01-08 | 2021-01-08 | 2021-01-08 | 2021-01-08 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 47.5511 | 25.1013 | منجز | No
2100192253 | جامعة جازان | إشراف | ذات اولوية عالية وعاجلة | 12804741.51 | 640237.0755 | 11561790.47 | 9889051.04 | 5900032159 | لا | 0 | 191101066255 | جاري | الكميات التي تم تركيبها | 86 | 86 | 2020-03-05 | 2022-03-05 | 2023-06-04 | 2023-06-04 |  |  |  |  | 42.5489 | 16.9771 | خدمات عامة | No
2100028173 | جامعة جازان | تشييد | ذات اولوية عالية وعاجلة | 127257446.4 | 6362872.32 | 114425942.26 | 114425942.26 | 1010317864 | لا | 0 | 181009162116 | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 100 | 100 | 2012-11-13 | 2016-04-26 | 2020-10-12 | 2020-10-12 |  |  | تأخرصرف المستحقات المالية |  | 42.5532 | 16.9778 | Failed | No
2100084803 | وزارة الداخلية / المديرية العامة لحرس الحدود | تشييد | ذات اولوية عالية | 615075500 | 30753775 | 610483413.31 | 610483413.31 | 1010039430 | لا | 0 | 180709023828 | جاري | تكلفة العمل المنجز | 88 | 90 | 2015-06-18 | 2023-03-30 | 2023-03-30 | 2023-03-30 |  |  | تغيرات في نطاق المشروع |  | 52.0189 | 19.0602 | منتظم | No
2100023800 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية | 36619777.55 | 1830988.8775 | 31087329.61 | 23960428.77 | 4030156606 | لا | 0 | 180709020807 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 92.55 | 100 | 2015-04-29 | 2017-04-07 | 2021-06-28 | 2021-06-28 | 2017-04-07 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 40.8361 | 26.419 | منجز | No
2200213054 | المؤسسة العامة للتقاعد | تشييد | ذات اولوية عالية | 2173913.04 | 108695.652 | 108695.65 | 108695.65 | 2050104662 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 69.33 | 100 | 2021-09-09 | 2022-08-03 | 2022-08-03 | 2022-08-03 |  |  |  |  | 39.1266 | 21.7257 | Failed | No
2100026552 | أمانة / الرياض | تشييد | ذات اولوية عالية | 1129532 | 56476.6 | 1129532 | 0 | 1010258205 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-07-24 | 2018-12-26 | 2018-12-26 | 2018-12-26 | 2018-12-26 |  |  |  | 46.0956 | 25.1158 | منجز | Yes
2100194014 | وزارة الداخلية / المديرية العامة لحرس الحدود | تشييد | ذات اولوية عالية | 2696509.2 | 134825.46 | 808333.76 | 808333.76 | 1010393545 | لا | 0 | 201209030069 | مسحوب | تكلفة العمل المنجز | 35 | 35 | 2019-12-22 | 2020-03-21 | 2020-03-21 | 2020-03-21 |  |  | ضعف كفاءة المقاول الفنية |  | 43.5119 | 17.6657 | مسحوب | No
2100199861 | الجامعة الاسلامية بالمدينة المنورة | ترميم | ذات اولوية عالية | 6999300 | 349965 | 1816874.65 | 1816874.65 | 4650002701 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 35 | 37 | 2022-07-25 | 2023-11-13 | 2023-11-13 | 2023-11-13 |  |  |  |  | 39.5654 | 24.4807 | منتظم | No
2100032196 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 281336065.3 | 14066803.265 | 244725750.67 | 244725750.67 | 1010074413 | لا | 0 | 180809057582 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-03-03 | 2017-03-02 | 2021-06-20 | 2021-06-20 | 2017-03-02 |  |  |  | 46.6841 | 24.7032 | منجز | No
2100057875 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية وعاجلة | 48648945 | 2432447.25 | 42978018.25 | 41600131 | 1010184370 | لا | 0 | 180809055233 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 96.51 | 100 | 2014-04-01 | 2016-03-10 | 2021-08-08 | 2021-08-08 | 2016-03-10 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.3171 | 26.7909 | منجز | No
2100191096 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية وعاجلة | 4013040 | 200652 | 2568526.44 | 2568526.44 | 2050003475 | لا | 0 | 201101365581 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 80 | 99.54 | 2021-01-04 | 2021-06-01 | 2021-07-28 | 2021-07-28 | 2021-06-01 |  |  |  | 41.6635 | 20.2843 | منجز | No
2100035884 | أمانة / جازان | تشييد | ذات اولوية عالية | 3348286 | 167414.3 | 2394920 | 2394920 | 5907014307 | لا | 0 | 180801053116 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-07-09 | 2019-07-03 | 2019-07-07 | 2019-07-07 | 2019-07-03 |  | اخرى |  | 42.9372 | 16.6011 | منجز | No
2100080264 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 643333 | 32166.65 | 640300 | 0 | 1017000955 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-07-17 | 2018-09-30 | 2018-10-01 | 2018-10-01 | 2018-09-30 |  |  |  | 46.5615 | 22.008 | منجز | Yes
2100060421 | المؤسسة العامة لتحلية المياه المالحة | تشييد | ذات اولوية عالية | 228589554 | 11429477.7 | 129949591.17 | 129949591.17 | 1010011560 | لا | 0 | 200201034819 | جاري | منهجية القيمة المكتسبة | 93.7 | 100 | 2020-05-31 | 2021-09-30 | 2022-09-30 | 2022-09-30 |  |  | اخرى |  | 41.0903 | 19.1259 | متأخر | No
2100191052 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية وعاجلة | 10735043.86 | 536752.193 | 8448161 | 8448161 | 1010130068 | لا | 0 | 200401065385 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 87.6 | 100 | 2020-07-09 | 2021-07-09 | 2021-07-13 | 2021-07-13 | 2021-07-09 |  |  |  | 41.4473 | 19.9567 | منجز | No
2100090241 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية عالية | 7998586.4 | 399929.32 | 7995550.95 | 7995550.95 | 1010210389 | لا | 0 | 180301001124 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-02-21 | 2021-01-29 | 2020-06-08 | 2020-06-08 |  | 2021-01-29 | لا يوجد تأخير |  | 43.526 | 19.539 | منجز | No
2100105114 | شركة المياه الوطنية | تشييد | ذات اولوية عالية وعاجلة | 551505800 | 27575290 | 479278894.51 | 479278894.51 | 1010012911 | نعم | 11645077.5 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 98.89 | 100 | 2017-07-04 | 2019-04-19 | 2021-12-11 | 2021-12-11 | 2019-04-19 |  | لا يوجد تأخير |  | 40.0549 | 29.8587 | منجز | No
2100025723 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2081660 | 104083 | 144200 | 144200 | 4650026523 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 7 | 100 | 2009-05-25 | 2010-05-10 | 2023-12-15 | 2023-12-15 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.6005 | 24.4595 | مسحوب | No
2100087684 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية | 25610550 | 1280527.5 | 15586154 | 11131857.66 | 5860008190 | لا | 0 | 180201000304 | جاري | منهجية القيمة المكتسبة | 85.79 | 100 | 2018-10-18 | 2021-09-16 | 2022-12-15 | 2022-12-15 |  |  | اخرى |  | 41.482 | 20.0136 | متأخر | No
2100191262 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية عالية | 13999177 | 699958.85 | 13997285.51 | 12612985.51 | 5855028463 | لا | 0 | 191201146741 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2020-07-16 | 2021-07-05 | 2021-07-01 | 2021-07-01 | 2021-07-05 |  |  |  | 41.9263 | 18.3537 | منجز | No
2100038345 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية وعاجلة | 7503573 | 375178.65 | 8762762.88 | 7152722.74 | 4650198974 | لا | 0 | 180901075321 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-10-14 | 2020-09-22 | 2020-12-29 | 2020-12-29 | 2020-09-22 |  | لا يوجد تأخير |  | 39.6005 | 24.4595 | منجز | No
2100049685 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية وعاجلة | 7781650 | 389082.5 | 7763489.02 | 7763489.02 | 4650009299 | لا | 0 | 181009152852 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99.24 | 96.25 | 2014-12-24 | 2016-12-01 | 2020-01-29 | 2020-01-29 | 2016-12-01 |  | لا يوجد تأخير |  | 39.5671 | 24.339 | منجز | No
2100082342 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 21411275.2 | 1070563.76 | 5146574.2 | 5146574.2 | 3400011750 | لا | 0 | 190301031655 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-11-15 | 2021-11-05 | 2022-06-09 | 2022-06-09 | 2021-11-05 |  |  |  | 38.6739 | 31.6729 | منجز | No
2100046944 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4851135 | 242556.75 | 41405 | 0 | 1118000832 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 80 | 100 | 2014-01-20 | 2019-03-25 | 2019-03-24 | 2019-03-24 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6713 | 24.7131 | مسحوب | Yes
2100090031 | المؤسسة العامة لتحلية المياه المالحة | تشييد | ذات اولوية عالية | 84869200 | 4243460 | 80727072 | 80727072 | 1010018980 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 97.6 | 100 | 2019-11-28 | 2022-08-30 | 2022-08-30 | 2022-08-30 | 2022-08-30 |  | تأخرصرف المستحقات المالية |  | 42.6565 | 17.6668 | منجز | No
2100089132 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية وعاجلة | 14711760 | 735588 | 10856940.49 | 10856940.49 | 4031045263 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 80.8 | 100 | 2015-08-04 | 2017-07-13 | 2020-04-06 | 2020-04-06 |  | 2017-07-13 | لا يوجد تأخير |  | 41.4374 | 19.7864 | منجز | No
2100033773 | شركة المياه الوطنية / منطقة حائل | إشراف | ذات اولوية عالية | 7261000 | 363050 | 7206407.68 | 7206407.68 | 1010314421 | لا | 0 | 181201507959 | منجز – استلام ابتدائي | التكلفة المفوترة | 99.25 | 100 | 2019-01-24 | 2022-01-25 | 2022-01-23 | 2022-01-23 | 2022-01-25 |  | لا يوجد تأخير |  | 41.5391 | 27.0622 | منجز | No
2100103342 | شركة المياه الوطنية / منطقة الرياض | دراسات هندسية | ذات اولوية عالية | 13125125 | 656256.25 | 13125119.38 | 13125119.38 | 1010348048 | لا | 0 |  | منجز – استلام نهائي | تكلفة العمل المنجز | 99.98 | 100 | 2018-11-24 | 2020-11-24 | 2022-03-01 | 2022-03-01 |  | 2020-11-24 | لا يوجد تأخير |  | 46.7222 | 24.7031 | منجز | No
2100056420 | شركة المياه الوطنية / منطقة الباحة | إشراف | ذات اولوية عالية | 6350400 | 317520 | 6350400 | 6350400 | 1131052239 | لا | 0 | 180709023955 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2017-05-18 | 2019-05-17 | 2019-05-18 | 2019-05-18 | 2019-05-17 |  | لا يوجد تأخير |  | 41.4797 | 20.0179 | منجز | No
2100091475 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2060270 | 103013.5 | 1760783.8993 | 0 | 1116010244 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 87 | 100 | 2015-06-13 | 2016-06-07 | 2018-09-12 | 2018-09-12 | 2016-06-07 |  | ضعف كفاءة المقاول الفنية |  | 46.1254 | 25.3378 | منجز | Yes
2100192452 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 31256550.41 | 1562827.5205 | 27274477.66 | 27274477.66 | 1010196414 | لا | 0 | 181101270842 | جاري | تكلفة العمل المنجز | 98 | 99.25 | 2018-07-01 | 2019-10-08 | 2023-12-31 | 2023-12-31 |  |  |  |  | 39.2391 | 21.4933 | منتظم | No
2200233785 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 17503000 | 875150 | 0 | 0 | 4030148791 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 4 | 4 | 2022-10-02 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  |  | 49.5609 | 25.6564 | منتظم | No
2100074093 | شركة المياه الوطنية / منطقة مكة المكرمة | إشراف | ذات اولوية متوسطة | 4894560 | 244728 | 4643515.28 | 4643515.28 | 1010326770 | لا | 0 |  | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 1 | 100 | 2019-05-08 | 2021-05-07 | 2021-09-21 | 2021-09-21 | 2021-05-07 |  | لا يوجد تأخير |  | 39.784 | 21.5517 | منجز | No
2100061670 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية | 40371917 | 2018595.85 | 33775974.37 | 33775974.37 | 4650015928 | لا | 0 | 181009160158 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 98 | 2014-09-25 | 2017-08-23 | 2021-01-25 | 2021-01-25 | 2017-08-23 |  | لا يوجد تأخير |  | 40.6859 | 23.3652 | منجز | No
2100193642 | صندوق التنمية الزراعية | تشييد | ذات اولوية متوسطة | 1513951.4 | 75697.57 | 938446.26 | 938446.26 | 2050069840 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 100 | 100 | 2020-10-25 | 2021-06-19 | 2021-12-14 | 2021-12-14 |  |  |  |  | 50.0201 | 26.518 | Failed | No
2100063593 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 7725851 | 386292.55 | 2662032.775 | 0 | 1010234015 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 86.82 | 100 | 2015-03-28 | 2017-03-17 | 2020-06-12 | 2020-06-12 | 2017-03-17 |  | ضعف كفاءة المقاول الفنية |  | 46.6788 | 24.7063 | منجز | Yes
2100040633 | وزارة الصحة / بيشة | تشييد | ذات اولوية عالية | 3149468.5 | 157473.425 | 1490538.2 | 1233115.25 | 4030190342 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 63 | 100 | 2015-05-20 | 2018-09-16 | 2022-11-15 | 2022-11-15 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.8635 | 19.7585 | مسحوب | No
2100042991 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 8208600 | 410430 | 39811 | 0 | 1010154882 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 56 | 100 | 2011-09-06 | 2013-04-28 | 2020-10-22 | 2020-10-22 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6891 | 24.7231 | مسحوب | Yes
2100080780 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 11799785 | 589989.25 | 1942107.75 | 0 | 1010056094 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 46.9 | 100 | 2015-08-05 | 2017-07-25 | 2020-12-17 | 2020-12-17 | 2017-07-25 |  | ضعف كفاءة المقاول الفنية |  | 46.4791 | 22.0843 | منجز | Yes
2200233925 | أمانة / الأحساء | دراسة الجدوى | ذات اولوية متوسطة | 2461000 | 123050 | 0 | 0 | 1010600030 | لا | 0 |  | جاري | تكلفة العمل المنجز | 1 | 1 | 2022-06-22 | 2023-09-23 | 2022-09-23 | 2022-09-23 |  |  |  |  | 49.5604 | 25.3897 | خدمات عامة | No
2100041683 | شركة المياه الوطنية / منطقة حائل | إشراف | ذات اولوية عالية | 7028000 | 351400 | 18481861.1 | 18370894.44 | 1010314421 | لا | 0 | 181209451598 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-10-26 | 2016-10-26 | 2021-10-05 | 2021-10-05 | 2016-10-26 |  | لا يوجد تأخير |  | 40.1902 | 27.6075 | منجز | No
2100059172 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية وعاجلة | 118274146.5 | 5913707.325 | 34693190 | 34693190 | 1116000094 | لا | 0 | 180709028251 | مسحوب | منهجية القيمة المكتسبة | 37.62 | 100 | 2014-05-22 | 2017-04-20 | 2017-07-14 | 2017-07-14 |  |  | ضعف كفاءة المقاول الفنية |  | 41.4374 | 19.7864 | مسحوب | No
2100056630 | شركة المياه الوطنية / منطقة عسير | إشراف | ذات اولوية عالية | 3192000 | 159600 | 2168187.35 | 2168187.35 | 2050099301 | لا | 0 | 180901089062 | منجز – استلام ابتدائي | التكلفة المفوترة | 71.27 | 100 | 2018-10-04 | 2020-07-15 | 2020-07-15 | 2020-07-15 | 2020-07-15 |  | لا يوجد تأخير |  | 42.4964 | 19.932 | منجز | No
2100030575 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1463200 | 73160 | 0 | 0 | 1115001965 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 14 | 2019-04-17 | 2020-10-08 | 2020-10-08 | 2020-10-08 | 2020-10-08 |  |  |  | 46.6933 | 24.7069 | منجز | No
2100029120 | أمانة / الرياض | تشييد | ذات اولوية عالية | 29811250 | 1490562.5 | 20206006.95 | 0 | 1116002021 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 100 | 2013-04-05 | 2014-09-27 | 2019-09-15 | 2019-09-15 | 2014-09-27 |  | ضعف كفاءة المقاول الفنية |  | 44.4366 | 24.5025 | منجز | Yes
2200233332 | الهيئة العامة للموانئ | تصميم وتشييد | ذات اولوية عالية | 43700000 | 2185000 | 0 | 0 | 2050050438 | لا | 0 |  | جاري | تكلفة العمل المنجز | 0 | 10.42 | 2022-10-13 | 2024-10-13 | 2024-10-13 | 2024-10-13 |  |  |  |  | 49.6652 | 27.0239 | متأخر | No
2200233914 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 9503667.15 | 475183.3575 | 737160.23 | 737160.23 | 4031054258 | لا | 0 |  | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2014-12-11 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2017-11-08 | 2022-10-11 |  |  | 39.8579 | 21.3891 | منجز | No
2100019736 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 13274961.69 | 663748.0845 | 13270961.69 | 11946488 | 1010183025 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 98.77 | 99.64 | 2016-09-25 | 2018-09-25 | 2021-09-26 | 2021-09-26 | 2018-09-25 |  | لا يوجد تأخير |  | 39.8012 | 21.3647 | منجز | No
2100062204 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية | 16952824 | 847641.2 | 9635843.68 | 8919944 | 4031045263 | لا | 0 | 180709022013 | جاري | منهجية القيمة المكتسبة | 65.82 | 100 | 2015-08-05 | 2017-07-14 | 2022-01-14 | 2022-01-14 |  |  | أوامر تغيير |  | 41.2825 | 20.1612 | Failed | No
2100009940 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية وعاجلة | 19579510 | 978975.5 | 19579088.52 | 19579088.52 | 4700009877 | لا | 0 | 181109308215 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-01-07 | 2020-12-05 | 2020-11-22 | 2020-11-22 | 2020-12-05 |  | لا يوجد تأخير |  | 40.1587 | 23.2568 | منجز | No
2100102911 | شركة المياه الوطنية / منطقة عسير | إشراف | ذات اولوية عالية | 6040000 | 302000 | 4082904.5 | 4082904.5 | 4030283265 | لا | 0 | 180809044745 | منجز – استلام ابتدائي | التكلفة المفوترة | 67.5 | 100 | 2017-12-05 | 2020-05-10 | 2020-05-12 | 2020-05-12 | 2020-05-10 |  | لا يوجد تأخير |  | 42.5393 | 18.1926 | منجز | No
2100058273 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية | 37828445.1 | 1891422.255 | 23626574.75 | 22026238.75 | 4030156606 | لا | 0 | 180709022870 | مسحوب | منهجية القيمة المكتسبة | 57.06 | 100 | 2015-03-12 | 2017-02-18 | 2022-12-30 | 2022-12-30 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.6821 | 26.7798 | مسحوب | No
2100070055 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 287775000 | 14388750 | 228976062.14 | 228976062.14 | 1010054406 | لا | 0 | 181109363878 | جاري | الكميات التي تم تركيبها | 85.19 | 89.07 | 2013-10-22 | 2017-09-07 | 2023-02-20 | 2023-02-20 |  |  |  |  | 39.4384 | 21.4514 | منتظم | No
2100106116 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية وعاجلة | 10907662 | 545383.1 | 10126108.47 | 10126108.47 | 1010267848 | لا | 0 | 181009133329 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99.54 | 100 | 2016-02-01 | 2018-01-09 | 2021-03-14 | 2021-03-14 | 2018-01-09 |  | لا يوجد تأخير |  | 39.553 | 24.4194 | منجز | No
2100026331 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية عالية | 24885400 | 1244270 | 21615487.84 | 18693088.39 | 5855010714 | لا | 0 | 190401076867 | جاري | منهجية القيمة المكتسبة | 90 | 98.21 | 2019-07-03 | 2022-05-30 | 2023-03-31 | 2023-03-31 |  |  | اخرى |  | 42.8019 | 18.1626 | متأخر | No
2100104451 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية | 51241754 | 2562087.7 | 2932399.59 | 2932399.59 | 4030068284 | لا | 0 | 180709023681 | مسحوب | منهجية القيمة المكتسبة | 5.84 | 100 | 2015-03-02 | 2018-01-28 | 2026-09-15 | 2026-09-15 |  |  | ضعف كفاءة المقاول الفنية |  | 41.2825 | 20.1612 | مسحوب | No
2100020915 | وزارة الشـؤون الاسلامية والدعوة والارشاد | تشييد | ذات اولوية عالية | 1588889.6 | 79444.48 | 1222100 | 0 | 1155000117 | لا | 0 | 181109283281 | جاري | الكميات التي تم تركيبها | 99 | 100 | 2017-12-31 | 2019-04-20 | 2019-04-20 | 2019-04-20 |  |  | تأخرصرف المستحقات المالية |  | 43.076 | 25.8543 | Failed | Yes
2100065715 | أمانة / الجوف | تشييد | ذات اولوية منخفضة | 392000 | 19600 | 392000 | 352800 | 3401014820 | لا | 0 | 200609073672 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-10-15 | 2020-04-11 | 2021-02-01 | 2021-02-01 | 2020-04-11 |  |  |  | 39.8661 | 29.8084 | منجز | No
2100191085 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية وعاجلة | 2990047.5 | 149502.375 | 1065687.4 | 974053.25 | 7007465839 | لا | 0 | 200901006924 | جاري | منهجية القيمة المكتسبة | 79.54 | 100 | 2020-11-01 | 2021-10-21 | 2022-07-04 | 2022-07-04 |  |  |  |  | 41.4731 | 20.0038 | Failed | No
2100079951 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية وعاجلة | 90607586.98 | 4530379.349 | 83144223.55 | 83144223.55 | 1010187733 | لا | 0 | 180909078590 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 97.62 | 2015-04-09 | 2018-03-08 | 2019-12-29 | 2019-12-29 |  | 2018-03-08 | لا يوجد تأخير |  | 39.6004 | 24.4621 | منجز | No
2100007302 | شركة المياه الوطنية / منطقة الباحة | إشراف | ذات اولوية عالية وعاجلة | 2988000 | 149400 | 1886870.31 | 1886870.31 | 4031087359 | لا | 0 | 181001168875 | ايقاف كلي | التكلفة المفوترة | 60.12 | 100 | 2018-10-28 | 2021-06-27 | 2023-01-01 | 2023-01-01 |  |  | لا يوجد تأخير |  | 41.482 | 20.0339 | Failed | No
2100102060 | وزارة الصحة / عسير | تشييد | لم تعد تحتاجها الجهة | 37188646.24 | 1859432.312 | 26422388.84 | 19285042.44 | 4030052981 | لا | 0 | 181009123532 | مسحوب | تكلفة العمل المنجز | 90 | 100 | 2013-09-27 | 2015-03-27 | 2021-07-21 | 2021-07-21 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال | تم إعادة ترسيته | 42.5238 | 18.2024 | مسحوب | No
2100020683 | شركة المياه الوطنية / منطقة المدينة المنورة | إشراف | ذات اولوية عالية | 13088880 | 654444 | 10157703.57 | 9224417.14 | 2050087924 | لا | 0 | 190201045699 | جاري | تكلفة العمل المنجز | 80.96 | 0 | 2019-08-05 | 2022-10-14 | 2022-10-14 | 2022-10-14 |  |  | لا يوجد تأخير |  | 39.5615 | 24.5085 | خدمات عامة | No
2100105534 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية وعاجلة | 167950751 | 8397537.55 | 151143664.31 | 151143664.31 | 2050003475 | لا | 0 | 180809056184 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 96.75 | 100 | 2014-03-25 | 2017-08-16 | 2020-01-22 | 2020-01-22 | 2017-08-16 |  | لا يوجد تأخير |  | 41.8041 | 27.6021 | منجز | No
2100025966 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية | 23748141.7 | 1187407.085 | 19542333.19 | 19542333.19 | 1132002394 | لا | 0 | 181009163830 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 94 | 2012-06-16 | 2015-05-15 | 2021-01-28 | 2021-01-28 | 2015-05-15 |  | لا يوجد تأخير |  | 40.5248 | 24.8638 | منجز | No
2100008116 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 17598750 | 879937.5 | 15114000 | 0 | 1010163813 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-04-01 | 2017-03-21 | 2021-06-14 | 2021-06-14 | 2017-03-21 |  | ضعف كفاءة المقاول الفنية |  | 47.3183 | 24.1524 | منجز | Yes
2100191380 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية | 124966032.03 | 6248301.6015 | 29098008.31 | 24647890.83 | 1010210667 | لا | 0 | 200701179365 | جاري | منهجية القيمة المكتسبة | 42.2 | 51.64 | 2020-12-20 | 2023-11-19 | 2023-11-18 | 2023-11-18 |  |  |  |  | 41.6579 | 27.516 | متأخر | No
2100056696 | وزارة التجارة | دراسة الجدوى | ذات اولوية عالية وعاجلة | 3117480 | 155874 | 2191334.46 | 2191334.46 | 1010348048 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 79 | 88 | 2018-07-11 | 2021-01-10 | 2023-01-13 | 2023-01-13 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  |  |  | خدمات عامة | No
2100061154 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية وعاجلة | 6244518 | 312225.9 | 4979536 | 4979536 | 4650025559 | لا | 0 | 180909083856 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 99.5 | 2014-12-31 | 2017-11-27 | 2019-11-27 | 2019-11-27 |  | 2017-11-27 | لا يوجد تأخير |  | 39.6005 | 24.4595 | منجز | No
2200227651 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 65159750 | 3257987.5 | 0 | 0 | 5855021168 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 0 | 0 | 2022-05-16 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  |  |  |  | 40.4947 | 21.4103 | منتظم | No
2200233951 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 33638951.5 | 1681947.575 | 25992582.42 | 25992582.42 | 4031030163 | لا | 0 |  | جاري | تكلفة العمل المنجز | 80.75 | 80.75 | 2015-04-12 | 2017-10-10 | 2021-06-02 | 2021-06-02 |  |  |  |  | 39.8579 | 21.3891 | Failed | No
2200234135 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 5000000 | 250000 | 0 | 0 | 4031019772 | لا | 0 |  | جاري | تكلفة العمل المنجز | 0 | 0 | 2021-07-31 | 2022-05-31 | 2022-05-31 | 2022-05-31 |  |  |  |  | 39.8579 | 21.3891 | Failed | No
2100005740 | شركة المياه الوطنية / منطقة الحدود الشمالية | إشراف | ذات اولوية عالية | 6838000 | 341900 | 6838000 | 6838000 | 1010314421 | لا | 0 | 180709033810 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-11-01 | 2018-10-31 | 2021-01-14 | 2021-01-14 | 2018-10-31 |  | لا يوجد تأخير |  | 41.0008 | 30.9838 | منجز | No
2100099234 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية وعاجلة | 125514698.5 | 6275734.925 | 59655859.24 | 59655859.24 | 4030004451 | لا | 0 |  | مسحوب | منهجية القيمة المكتسبة | 32.4 | 100 | 2012-05-28 | 2015-04-26 | 2024-12-28 | 2024-12-28 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6526 | 24.3389 | مسحوب | No
2100017780 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 545665 | 27283.25 | 42015 | 0 | 1010045486 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 36 | 100 | 2015-07-04 | 2016-07-18 | 2021-06-20 | 2021-06-20 |  |  | ضعف كفاءة المقاول الفنية |  | 45.9 | 25.2869 | مسحوب | Yes
2200213382 | أمانة / الجوف | دعم فني | ذات اولوية عالية وعاجلة | 818550 | 40927.5 | 818550 | 818550 | 3400010235 | لا | 0 | 210101030899 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-12-02 | 2021-05-31 | 2021-07-13 | 2021-07-13 | 2021-05-31 |  |  |  | 40.1043 | 29.878 | منجز | No
2100011745 | وزارة الحرس الوطني / وكالة الشؤون الفنية | تشييد | ذات اولوية متوسطة | 1409318.45 | 70465.9225 | 1399990.54 | 1233927.14 | 1010495829 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2020-01-27 | 2021-07-08 | 2022-03-01 | 2022-03-01 | 2021-07-08 |  |  |  | 43.9301 | 26.3839 | منجز | No
2200233962 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 227781898.76 | 11389094.938 | 11389094.94 | 11389094.94 | 2051030141 | لا | 0 |  | لم يبدأ | منهجية القيمة المكتسبة | 0 | 0 |  |  |  | 2025-09-16 |  |  |  |  | 49.4629 | 26.9627 | منتظم | No
2100104823 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية | 35488893.42 | 1774444.671 | 19521701.07 | 18744168.45 | 1010043648 | لا | 0 | 190401117386 | جاري | منهجية القيمة المكتسبة | 76.15 | 100 | 2019-11-12 | 2021-10-21 | 2022-10-21 | 2022-10-21 |  |  | اخرى |  | 41.764 | 27.6425 | متأخر | No
2100078912 | شركة المياه الوطنية / منطقة الباحة | إشراف | ذات اولوية عالية | 1665000 | 83250 | 1665000 | 1539347.05 | 1010417238 | لا | 0 | 190301005322 | منجز – استلام ابتدائي | التكلفة المفوترة | 92.45 | 100 | 2018-10-25 | 2020-06-25 | 2020-06-25 | 2020-06-25 | 2020-06-25 |  | لا يوجد تأخير |  | 41.4511 | 19.7633 | منجز | No
2100191155 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 14949385.25 | 747469.2625 | 8217107.05 | 8217107.05 | 4031057370 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 91 | 100 | 2020-10-06 | 2021-04-06 | 2021-10-07 | 2021-10-07 | 2021-04-06 |  |  |  | 39.9059 | 21.4017 | منجز | No
2100061320 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية وعاجلة | 7730733.5 | 386536.675 | 6878013.61 | 6878013.61 | 4650034676 | لا | 0 | 180809047674 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-11-14 | 2019-04-30 | 2020-01-02 | 2020-01-02 |  | 2019-04-30 | لا يوجد تأخير |  | 39.6005 | 24.4595 | منجز | No
2100003474 | شركة المياه الوطنية / منطقة الحدود الشمالية | تشييد | ذات اولوية عالية | 17363802.5 | 868190.125 | 14426763.17 | 14426763.17 | 1010009352 | نعم | 0.01 | 181001182399 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-12-19 | 2020-11-27 | 2021-12-05 | 2021-12-05 | 2020-11-27 |  | لا يوجد تأخير |  | 44.3266 | 29.1427 | منجز | No
2100003220 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية | 85745093.4 | 4287254.67 | 69552992.64 | 69552992.64 | 1010184370 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 93.5 | 100 | 2013-03-03 | 2015-02-10 | 2020-02-10 | 2020-02-10 | 2015-02-10 |  | لا يوجد تأخير |  | 41.4779 | 20.0185 | منجز | No
2200233973 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 75425278 | 3771263.9 | 1624257.02 | 1624257.02 | 2050022617 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 5 | 5 | 2022-04-07 | 2025-04-03 | 2025-04-03 | 2025-04-03 |  |  |  |  | 49.4728 | 26.9686 | منتظم | No
2100189976 | وزارة البيئة والمياة والزراعة | تحديث وتوريد | ذات اولوية متوسطة | 942246.75 | 47112.3375 | 800561.8 | 800561.8 | 1010273396 | لا | 0 | 201101309292 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2021-01-21 | 2021-08-15 | 2021-08-16 | 2021-08-16 | 2021-08-15 |  |  |  | 49.5949 | 25.3371 | منجز | No
2200233984 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 25000000 | 1250000 | 24263391.29 | 24263391.29 | 4031008077 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 97.05 | 97.05 | 2014-01-01 | 2016-06-04 | 2019-07-10 | 2019-07-10 | 2016-06-04 |  |  |  | 39.8579 | 21.3891 | منجز | No
2100106072 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 59116325 | 2955816.25 | 43158650.55 | 43158650.55 | 2050003475 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99.33 | 100 | 2016-12-15 | 2018-12-15 | 2019-12-02 | 2019-12-02 | 2018-12-15 |  | لا يوجد تأخير |  | 39.8373 | 21.4561 | منجز | No
2100104812 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية | 37933000 | 1896650 | 22844298.95 | 20163477.95 | 5860008190 | لا | 0 | 181109260291 | جاري | منهجية القيمة المكتسبة | 88.17 | 100 | 2018-04-05 | 2021-03-02 | 2022-12-15 | 2022-12-15 |  |  | لا يوجد تأخير |  | 41.482 | 20.0136 | Failed | No
2100073242 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية وعاجلة | 29780846 | 1489042.3 | 26937948.72 | 26937948.72 | 4650052854 | لا | 0 | 181009164639 | جاري | منهجية القيمة المكتسبة | 90 | 100 | 2011-03-15 | 2014-02-10 | 2022-06-30 | 2022-06-30 |  |  | لا يوجد تأخير |  | 38.2583 | 23.3597 | Failed | No
2100043573 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 838850 | 41942.5 | 741100 | 0 | 1010257811 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 95 | 2015-07-29 | 2017-07-18 | 2020-03-31 | 2020-03-31 | 2017-07-18 |  | ضعف كفاءة المقاول الفنية |  | 46.6809 | 24.7069 | منجز | Yes
2100010161 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 27024409 | 1351220.45 | 21717463 | 21717463 | 1010178838 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-04-25 | 2019-03-21 | 2019-05-02 | 2019-05-02 | 2019-03-21 |  |  |  | 39.6005 | 24.4595 | منجز | No
2200234150 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 13784085 | 689204.25 | 1099208.3 | 1099208.3 | 4031033277 | لا | 0 |  | جاري | تكلفة العمل المنجز | 7.97 | 7.97 | 2019-10-29 | 2022-04-16 | 2022-07-15 | 2022-07-15 |  |  |  |  | 39.8579 | 21.3891 | متأخر | No
2200233995 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 198018374.65 | 9900918.7325 | 9900918.73 | 9900918.73 | 2051013824 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 0 | 2 | 2022-08-03 | 2026-05-19 | 2026-05-19 | 2026-05-19 |  |  |  |  | 49.4596 | 26.9635 | منتظم | No
2200234146 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 2899250 | 144962.5 | 704533.8 | 704533.8 | 4032045419 | لا | 0 |  | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 29.91 | 29.91 | 2015-04-13 | 2016-09-26 | 2017-04-27 | 2017-04-27 |  |  |  |  | 39.8579 | 21.3891 | Failed | No
2100032642 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 1684770 | 84238.5 | 1516363 | 0 | 5950012263 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-04-13 | 2019-12-06 | 2019-12-06 | 2019-12-06 | 2019-12-06 |  | اخرى |  | 44.1524 | 17.6538 | منجز | Yes
2100103633 | وزارة الدفاع / الإدارة الهندسية والاشغال بالخدمات الصحية | تشييد | ذات اولوية متوسطة | 4486000 | 224300 | 4486000 | 4486000 | 4030187641 | لا | 0 | 181209475653 | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-10-16 | 2019-10-04 | 2022-08-31 | 2022-08-31 |  |  | عدم وجود مبالغ في البنود تغطي الأعمال المرصودة |  | 40.4776 | 21.2422 | متأخر | No
2100190864 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 3102640 | 155132 | 2537509.19 | 2537509.19 | 4031059045 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 92.75 | 100 | 2020-12-06 | 2021-06-07 | 2022-01-31 | 2022-01-31 | 2021-06-07 |  |  |  | 39.8953 | 21.44 | منجز | No
2100080135 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية وعاجلة | 313579876.12 | 15678993.806 | 245352207.41 | 245352207.41 | 1010054406 | لا | 0 | 180709029945 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99.7 | 96.87 | 2011-08-13 | 2014-07-10 | 2021-08-03 | 2021-08-03 | 2014-07-10 |  | لا يوجد تأخير |  | 39.5962 | 24.555 | منجز | No
2100191951 | شركة المياه الوطنية / منطقة مكة المكرمة | إشراف | ذات اولوية متوسطة | 3416400 | 170820 | 2554981.54 | 2282781.54 | 7014063510 | لا | 0 |  | جاري | مدفوعات ساعات العمل | 0.5 | 0.6 | 2021-01-04 | 2023-01-04 | 2023-01-04 | 2023-01-04 |  |  |  |  | 39.9051 | 21.3959 | خدمات عامة | No
2100105792 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية وعاجلة | 26582400 | 1329120 | 23492695.48 | 23492695.48 | 5810001890 | لا | 0 | 180301000997 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 90.14 | 100 | 2019-02-14 | 2020-07-30 | 2021-05-26 | 2021-05-26 | 2020-07-30 |  | تصاريح أعمال التنفيذ |  | 41.482 | 20.0136 | منجز | No
2200234006 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 1974000 | 98700 | 843297.12 | 843297.12 | 4031064664 | لا | 0 |  | جاري | تكلفة العمل المنجز | 42.72 | 42.72 | 2020-03-18 | 2021-03-18 | 2021-12-20 | 2021-12-20 |  |  |  |  | 39.8579 | 21.3891 | Failed | No
2100041613 | شركة المياه الوطنية / منطقة المدينة المنورة | إشراف | ذات اولوية عالية وعاجلة | 10999700 | 549985 | 11325410.93 | 10962298.43 | 2050101543 | لا | 0 | 180501009663 | جاري | تكلفة العمل المنجز | 0 | 0 | 2018-09-13 | 2021-09-12 | 2022-03-12 | 2022-03-12 |  |  | لا يوجد تأخير |  | 39.5735 | 24.502 | خدمات عامة | No
2100061202 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 113780500 | 5689025 | 94584227.2 | 94584227.2 | 1010026934 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 92 | 100 | 2019-06-27 | 2021-06-27 | 2021-08-31 | 2021-08-31 | 2021-06-27 |  | لا يوجد تأخير |  | 39.882 | 21.4976 | منجز | No
2100022466 | شركة المياه الوطنية / منطقة المدينة المنورة | مساحة | ذات اولوية عالية وعاجلة | 8871492 | 443574.6 | 5559877.02 | 5559877.02 | 4650047424 | لا | 0 | 190501078093 | جاري | مدفوعات ساعات العمل | 67.8 | 0 | 2019-10-17 | 2021-04-18 | 2022-07-31 | 2022-07-31 |  |  | لا يوجد تأخير |  | 39.6129 | 24.4747 | خدمات عامة | No
2200234021 | أمانة / عسير | تشييد | ذات اولوية عالية | 8159420 | 407971 | 0 | 0 | 5859000601 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 98 | 100 | 2013-11-17 | 2015-11-24 | 2015-11-24 | 2015-11-24 |  |  |  |  | 42.1667 | 18.9547 | مسحوب | No
2100089655 | شركة المياه الوطنية / منطقة الباحة | إشراف | ذات اولوية متوسطة | 4050000 | 202500 | 4050000 | 4050000 | 1010420649 | لا | 0 | 180709026298 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-05-20 | 2017-05-22 | 2017-05-22 | 2017-05-22 | 2017-05-22 |  | لا يوجد تأخير |  | 41.4616 | 19.9812 | منجز | No
2100106164 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية | 51815320 | 2590766 | 41952058.1 | 41952058.1 | 4650052854 | لا | 0 | 180709032323 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 98 | 2013-01-21 | 2015-12-20 | 2020-08-12 | 2020-08-12 | 2015-12-20 |  | لا يوجد تأخير |  | 40.6887 | 23.3625 | منجز | No
2100104915 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 126950000 | 6347500 | 103823802.93 | 103823802.93 | 1010012911 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99 | 100 | 2013-02-06 | 2016-02-04 | 2020-11-25 | 2020-11-25 | 2016-02-04 |  | لا يوجد تأخير |  | 39.8297 | 21.3605 | منجز | No
2100023601 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية | 24688381 | 1234419.05 | 16841445.98 | 16841445.98 | 1010328073 | لا | 0 | 181101341193 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-02-13 | 2020-02-13 | 2020-06-07 | 2020-06-07 |  | 2020-02-13 | لا يوجد تأخير |  | 39.3449 | 25.5379 | منجز | No
2100049755 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية وعاجلة | 371520271.09 | 18576013.5545 | 131871226.68 | 131871226.68 | 1010014578 | لا | 0 | 180909089093 | جاري | مدفوعات ساعات العمل | 55.26 | 99.93 | 2010-06-28 | 2013-06-11 | 2024-12-31 | 2024-12-31 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | Failed | No
2200227706 | أمانة / حفر الباطن | تشييد | ذات اولوية عالية | 2519535 | 125976.75 | 1910849 | 1910849 | 1010008188 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2021-11-14 | 2022-11-14 | 2022-11-14 | 2022-11-14 | 2022-11-14 |  |  |  | 45.9627 | 28.3784 | منجز | No
2100087673 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية وعاجلة | 33976586 | 1698829.3 | 19438120 | 18386904.21 | 4030159820 | لا | 0 | 190601035814 | جاري | منهجية القيمة المكتسبة | 82.96 | 96.06 | 2019-11-14 | 2022-10-13 | 2023-06-10 | 2023-06-10 |  |  | اخرى |  | 41.2468 | 19.9434 | متأخر | No
2100085875 | شركة المياه الوطنية / منطقة مكة المكرمة | إشراف | ذات اولوية متوسطة | 5832000 | 291600 | 4306677.41 | 4306677.41 | 1131035992 | لا | 0 |  | جاري | مدفوعات ساعات العمل | 98 | 100 | 2019-06-19 | 2021-06-18 | 2022-06-18 | 2022-06-18 |  |  | لا يوجد تأخير |  | 39.7753 | 21.3823 | خدمات عامة | No
2100019692 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية متوسطة | 20024613 | 1001230.65 | 15189199.07 | 15189199.07 | 1010048595 | لا | 0 | 200309089672 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 87.41 | 100 | 2015-07-30 | 2017-07-08 | 2021-08-02 | 2021-08-02 | 2017-07-08 |  | لا يوجد تأخير |  | 38.4864 | 27.6176 | منجز | No
2200234076 | أمانة / عسير | أخرى | ذات اولوية عالية | 1909346 | 95467.3 | 664848.53 | 477000 | 5852001934 | لا | 0 |  | جاري | تكلفة العمل المنجز | 37 | 100 | 2020-12-13 | 2022-12-13 | 2022-12-13 | 2022-12-13 |  |  |  |  | 42.2343 | 18.7664 | خدمات عامة | No
2200213393 | أمانة / الجوف | أخرى | ذات اولوية عالية وعاجلة | 167707 | 8385.35 | 150936.12 | 150936.12 | 3407008162 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-12-23 | 2021-06-21 | 2022-09-21 | 2022-09-21 | 2021-06-21 |  |  |  | 40.1043 | 29.878 | منجز | No
2100100155 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية وعاجلة | 6980400 | 349020 | 6980400 | 6160308 | 1010210389 | لا | 0 | 190301027864 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-10-22 | 2020-10-22 | 2021-03-28 | 2021-03-28 | 2020-10-22 |  | لا يوجد تأخير |  | 41.7115 | 19.8989 | منجز | No
2100002601 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية وعاجلة | 7000000 | 350000 | 7000000 | 5950000 | 1010210389 | لا | 0 | 190301031532 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2020-03-23 | 2021-03-12 | 2021-06-08 | 2021-06-08 | 2021-03-12 |  | لا يوجد تأخير |  | 39.5739 | 24.4791 | منجز | No
2200234065 | أمانة / عسير | أخرى | ذات اولوية عالية | 2582828 | 129141.4 | 0 | 0 | 2051035036 | لا | 0 |  | جاري | تكلفة العمل المنجز | 65 | 100 | 2020-09-06 | 2021-09-15 | 2021-09-15 | 2021-09-15 |  |  |  |  | 42.2343 | 18.7664 | خدمات عامة | No
2100049184 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية وعاجلة | 48543186.28 | 2427159.314 | 28036778.15 | 28036778.15 | 2051003203 | لا | 0 | 180709016427 | مسحوب | تكلفة العمل المنجز | 73 | 100 | 2014-03-31 | 2016-02-29 | 2024-12-31 | 2024-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 40.3447 | 26.8523 | مسحوب | No
2200234220 | أمانة / العاصمة المقدسة | إشراف | ذات اولوية متوسطة | 1564849.99 | 78242.4995 | 1564850 | 1564850 | 4030229175 | لا | 0 |  | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2020-06-01 | 2022-06-01 | 2022-06-01 | 2022-06-01 | 2022-06-01 | 2022-06-01 |  |  | 39.8579 | 21.3891 | منجز | No
2200210851 | المؤسسة العامة للحبوب | تصميم وتشييد | ذات اولوية عالية | 3953010 | 197650.5 | 0 | 0 | 3400011596 | لا | 0 |  | لم يبدأ | الكميات التي تم تركيبها | 1 | 1 | 2022-03-01 | 2023-02-01 | 2024-02-01 | 2024-02-01 |  |  |  |  | 39.3295 | 29.8723 | منتظم | No
2100191181 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية وعاجلة | 1820392.5 | 91019.625 | 1404390.41 | 1404390.41 | 5855254826 | لا | 0 | 210201020978 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 92.643 | 100 | 2021-04-04 | 2022-03-25 | 2022-11-30 | 2022-11-30 | 2022-03-25 |  |  |  | 41.4673 | 20.0226 | منجز | No
2100002715 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية وعاجلة | 1982921 | 99146.05 | 1982920.77 | 1982920.77 | 5801004548 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-05-02 | 2020-05-02 | 2020-09-03 | 2020-09-03 |  | 2020-05-02 | تصاريح أعمال التنفيذ |  | 41.5686 | 19.8801 | منجز | No
2100105151 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية | 25057635 | 1252881.75 | 20813625.2 | 20130066.51 | 1134000066 | لا | 0 | 180709030025 | مسحوب | منهجية القيمة المكتسبة | 84.63 | 100 | 2014-01-28 | 2016-01-07 | 2023-08-01 | 2023-08-01 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.363 | 26.2863 | مسحوب | No
2200234242 | جامعة تبوك | تشييد | ذات اولوية عالية وعاجلة | 139979996.28 | 6998999.814 | 1472245.79 | 1472245.79 | 1010210566 | لا | 0 |  | جاري | تكلفة العمل المنجز | 2 | 10 | 2022-07-18 | 2024-01-08 | 2024-01-08 | 2024-01-08 |  |  |  |  | 36.4878 | 28.3937 | متأخر | No
2100056722 | أمانة / الرياض | دراسة الجدوى | ذات اولوية متوسطة | 3088575 | 154428.75 | 2611482 | 0 | 1010312946 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-04-09 | 2018-08-05 | 2018-08-05 | 2018-08-05 | 2018-08-05 |  | اخرى |  |  |  | منجز | Yes
2100016682 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية وعاجلة | 64978650 | 3248932.5 | 51671215.95 | 50849537.45 | 5860008190 | لا | 0 | 190709039334 | جاري | منهجية القيمة المكتسبة | 96.5 | 98.5 | 2018-07-16 | 2022-06-02 | 2022-08-27 | 2022-08-27 |  |  | تأخرصرف المستحقات المالية |  | 41.5686 | 19.8801 | منتظم | No
2200234080 | أمانة / عسير | أخرى | ذات اولوية عالية | 3427590 | 171379.5 | 2122258 | 0 | 2051035036 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 76 | 100 | 2015-05-10 | 2017-05-16 | 2015-05-16 | 2015-05-16 |  |  |  |  | 41.9114 | 19.7487 | مسحوب | Yes
2200234091 | أمانة / عسير | أخرى | ذات اولوية عالية | 1096750 | 54837.5 | 0 | 0 | 5852003252 | لا | 0 |  | جاري | تكلفة العمل المنجز | 55 | 100 | 2021-10-31 | 2022-12-28 | 2022-12-28 | 2022-12-28 |  |  |  |  | 42.3326 | 18.6258 | خدمات عامة | No
2100008330 | جامعة القصيم | تشييد | ذات اولوية عالية وعاجلة | 7021198 | 351059.9 | 6438849.8 | 6438849.8 | 1010186040 | لا | 0 | 200409028965 | جاري | تكلفة العمل المنجز | 99 | 99 | 2019-04-28 | 2020-01-23 | 2023-11-08 | 2023-11-08 |  |  | تأخرصرف المستحقات المالية |  | 43.8579 | 26.3006 | منتظم | No
2100006031 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية وعاجلة | 132171765 | 6608588.25 | 89007305.95 | 78899485.67 | 4030139128 | لا | 0 | 190709013385 | جاري | منهجية القيمة المكتسبة | 75.59 | 100 | 2015-04-01 | 2019-02-17 | 2023-04-25 | 2023-04-25 |  |  | اخرى |  | 41.2825 | 20.1612 | متأخر | No
2100075423 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3823840 | 191192 | 41780 | 0 | 1114000037 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 8 | 100 | 2014-10-13 | 2016-04-05 | 2023-08-02 | 2023-08-02 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6816 | 24.7038 | مسحوب | Yes
2100042921 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 9935171.54 | 496758.577 | 5119943.58 | 5119943.58 | 3350003498 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-09-07 | 2016-05-29 | 2022-06-15 | 2022-06-15 | 2016-05-29 |  | ضعف كفاءة المقاول الفنية |  | 38.097 | 24.0836 | منجز | No
2200234102 | أمانة / عسير | أخرى | ذات اولوية عالية | 1654275 | 82713.75 | 0 | 0 | 5850031121 | لا | 0 |  | ايقاف جزئي | تكلفة العمل المنجز | 0 | 100 | 2020-09-13 | 2022-12-27 | 2022-12-27 | 2022-12-27 |  |  |  |  | 42.05 | 19.3798 | Failed | No
2100033460 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 10432935 | 521646.75 | 9110046.47 | 9110046.47 | 2050018628 | لا | 0 | 181009119901 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 90.11 | 100 | 2014-03-19 | 2021-03-20 | 2021-03-30 | 2021-03-30 | 2021-03-20 |  | اخرى |  | 44.248 | 17.5488 | منجز | No
2100001363 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية | 45708301 | 2285415.05 | 3942803.2 | 3942803.2 | 5801003664 | لا | 0 |  | لم يبدأ | منهجية القيمة المكتسبة | 0 | 100 | 2016-01-03 | 2019-03-30 | 2023-01-08 | 2023-01-08 |  |  | ضعف كفاءة المقاول الفنية |  | 41.482 | 20.0136 | Failed | No
2100102782 | شركة المياه الوطنية / منطقة الباحة | الخدمات الاستشارية | ذات اولوية عالية وعاجلة | 12996000 | 649800 | 12935024.91 | 11290419.65 | 1010421282 | لا | 0 | 190301020733 | جاري | التكلفة المفوترة | 99.56 | 99.56 | 2018-10-18 | 2021-10-18 | 2022-04-20 | 2022-04-20 |  |  | لا يوجد تأخير |  | 41.4744 | 20.0103 | خدمات عامة | No
2200213076 | شركة المياه الوطنية / منطقة الرياض | إشراف | ذات اولوية عالية | 4482000 | 224100 | 2415275.81 | 2415275.81 | 1010314421 | لا | 0 |  | جاري | التكلفة المفوترة | 60.54 | 60.54 | 2021-10-14 | 2022-10-15 | 2022-10-15 | 2022-10-15 |  |  |  |  | 46.795 | 24.6531 | خدمات عامة | No
2100103386 | وزارة العدل | تشييد | ذات اولوية عالية وعاجلة | 324517277 | 16225863.85 | 121456026.36 | 121456026.36 | 1010078624 | لا | 0 | 180809061008 | جاري | تكلفة العمل المنجز | 71.26 | 100 | 2014-12-11 | 2017-08-10 | 2023-03-29 | 2023-03-29 |  |  | تأخرصرف المستحقات المالية |  | 39.6623 | 24.4604 | Failed | No
2100046340 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 46700000 | 2335000 | 41841991 | 299424.62 | 5950009827 | لا | 0 | 220601025060 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-02-19 | 2017-01-27 | 2022-02-21 | 2022-02-21 | 2017-01-27 |  |  |  | 44.1804 | 17.5943 | منجز | No
2200234286 | أمانة / العاصمة المقدسة | إشراف | ذات اولوية متوسطة | 866250 | 43312.5 | 718437.5 | 718437.5 | 4031070328 | لا | 0 |  | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 88.62 | 88.62 | 2020-01-04 | 2020-12-23 | 2020-12-23 | 2020-12-23 |  |  |  |  | 39.8579 | 21.3891 | Failed | No
2100191612 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية وعاجلة | 1538796 | 76939.8 | 1473887.71 | 1473887.71 | 2051041977 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2020-05-03 | 2020-08-03 | 2020-10-14 | 2020-10-14 |  | 2020-08-03 |  |  | 46.9053 | 24.3523 | منجز | No
2100030424 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3213432 | 160671.6 | 3060609.6 | 0 | 1131015382 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 100 | 2014-09-19 | 2018-06-02 | 2018-06-02 | 2018-06-02 | 2018-06-02 |  |  |  | 45.2138 | 25.3217 | منجز | Yes
2100074863 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1108294 | 55414.7 | 345250 | 0 | 1010258205 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 44 | 2019-01-20 | 2020-04-14 | 2020-01-15 | 2020-01-15 | 2020-04-14 |  |  |  | 46.7249 | 22.294 | منجز | Yes
2100189884 | الجامعة السعودية الالكترونية | ترميم | ذات اولوية متوسطة | 1559915.4 | 77995.77 | 248798.48 | 248798.48 | 1010216984 | لا | 0 | 201001026619 | جاري | تكلفة العمل المنجز | 75 | 100 | 2020-11-10 | 2021-03-10 | 2023-03-31 | 2023-03-31 |  |  | نزع الملكيات |  | 49.734 | 25.2835 | Failed | No
2100030623 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4550000 | 227500 | 2748976.07 | 0 | 1113000601 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 67 | 100 | 2014-08-10 | 2016-02-01 | 2020-02-09 | 2020-02-09 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6713 | 24.7044 | مسحوب | Yes
2100193605 | وزارة الحرس الوطني / الشؤون الفنية بالقطاع الشرقي | تشييد | ذات اولوية عالية | 5038135.61 | 251906.7805 | 3875943.21 | 3203641.02 | 2051027134 | لا | 0 | 180701016129 | جاري | تكلفة العمل المنجز | 98 | 100 | 2018-08-12 | 2019-02-05 | 2023-03-01 | 2023-03-01 |  |  |  |  | 49.5198 | 25.4491 | Failed | No
2200234312 | أمانة / العاصمة المقدسة | تصميم | ذات اولوية متوسطة | 3335000 | 166750 | 876605.9 | 876605.9 | 1010336184 | لا | 0 |  | جاري | تكلفة العمل المنجز | 26.29 | 26.29 | 2022-05-08 | 2024-05-07 | 2024-05-07 | 2024-05-07 |  |  |  |  | 39.8579 | 21.3891 | منتظم | No
2100019961 | الجامعة السعودية الالكترونية | تصميم | ذات اولوية متوسطة | 236250 | 11812.5 | 236250 | 236250 | 1010421940 | لا | 0 | 191101309267 | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2019-05-23 | 2019-07-01 | 2019-07-01 | 2019-07-01 | 2019-07-01 |  |  |  | 39.5254 | 24.4082 | منجز | No
2100018141 | أمانة / الرياض | تشييد | ذات اولوية عالية | 148000000 | 7400000 | 12228124.39 | 12228124.39 | 1010048595 | لا | 0 | 190301022776 | جاري | الكميات التي تم تركيبها | 19 | 19 | 2019-06-13 | 2021-10-16 | 2020-11-25 | 2020-11-25 |  |  |  |  | 46.6731 | 24.7107 | Failed | No
2100020591 | رئاسة أمن الدولة / القيادة العامة لطيران الأمن | تشييد | ذات اولوية عالية وعاجلة | 60202607.9 | 3010130.395 | 0 | 0 | 1010150014 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 1 | 1 | 2019-07-21 | 2020-03-05 | 2020-05-03 | 2020-05-03 |  |  | التنسيق مع أصحاب المصلحه (خدمات |  | 46.7334 | 24.7476 | مسحوب | No
2100071610 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 12441625 | 622081.25 | 39811 | 0 | 1011000444 | لا | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 6 | 100 | 2014-09-29 | 2016-09-18 | 2021-06-24 | 2021-06-24 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 46.6727 | 24.7044 | Failed | Yes
2200213426 | أمانة / الجوف | تشييد | ذات اولوية عالية وعاجلة | 2211550 | 110577.5 | 1577400 | 1577400 | 3400016537 | لا | 0 | 200101052169 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-12-24 | 2020-12-18 | 2022-09-22 | 2022-09-22 | 2020-12-18 |  |  |  | 40.3803 | 30.1147 | منجز | No
2100087080 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 16219140.68 | 810957.034 | 2324327.74 | 2324327.74 | 1011008214 | لا | 0 |  | مسحوب | التكلفة المفوترة | 30 | 100 | 2014-06-04 | 2016-05-24 | 2022-05-18 | 2022-05-18 |  |  | ضعف كفاءة المقاول الفنية |  | 38.0093 | 24.1366 | مسحوب | No
2100101522 | جامعة القصيم | تشييد | ذات اولوية عالية | 13079913 | 653995.65 | 12160511.01 | 12160511.01 | 1134000719 | لا | 0 | 200409027536 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-12-25 | 2019-09-21 | 2021-09-30 | 2021-09-30 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 43.8579 | 26.3006 | Failed | No
2100025443 | شركة المياه الوطنية / منطقة الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 20506506.97 | 1025325.3485 | 13204702.73 | 13204702.73 | 4030021112 | نعم | 3862806.3 | 180901073277 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 94.01 | 100 | 2019-04-22 | 2020-10-04 | 2021-09-26 | 2021-09-26 | 2020-10-04 |  | لا يوجد تأخير |  | 40.9308 | 31.0057 | منجز | No
2100107380 | الرئاسة العامة لهيئة الأمر بالمعروف والنهي عن المنكر | تشييد | ذات اولوية متوسطة | 19869176 | 993458.8 | 11726011.41 | 11726011.41 | 1010220472 | لا | 0 | 180609013131 | جاري | الكميات التي تم تركيبها | 75 | 80 | 2014-09-08 | 2016-04-30 | 2022-09-30 | 2022-09-30 |  |  | ضعف كفاءة المقاول الفنية | مخطط لسحبه وإعادة ترسيته | 45.3613 | 25.9064 | Failed | No
2100016855 | جامعة الطائف | تشييد | ذات اولوية متوسطة | 98844998.92 | 4942249.946 | 79075999.06 | 79075999.06 | 1010028011 | لا | 0 | 180809055791 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2010-09-03 | 2011-08-24 | 2018-08-13 | 2018-08-13 | 2011-08-24 |  | اخرى |  | 40.4868 | 21.3265 | منجز | No
2100018082 | جامعة شقراء | تصميم وإشراف | ذات اولوية عالية | 8632800 | 431640 | 8632800 | 8090832 | 1010322156 | لا | 0 | 181101373635 | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2019-01-27 | 2021-02-04 | 2022-01-31 | 2022-01-31 | 2021-02-04 |  | لا يوجد تأخير |  | 45.1409 | 25.1729 | منجز | No
2100205995 | وزارة الحرس الوطني / كلية الملك خالد العسكرية | ترميم | ذات اولوية عالية وعاجلة | 2797260 | 139863 | 1181970 | 1181970 | 1010356776 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 83.5 | 83.5 | 2021-12-21 | 2022-06-15 | 2022-08-04 | 2022-08-04 |  |  |  |  | 46.8908 | 24.7413 | Failed | No
2100102222 | وزارة الصحة / جدة | تشييد | ذات اولوية عالية | 84000000 | 4200000 | 67225000 | 67225000 | 1010136286 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-04-01 | 2017-12-09 | 2018-01-01 | 2018-01-01 | 2017-12-09 |  |  |  | 40.8795 | 20.4487 | منجز | No
2100080555 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 9695975 | 484798.75 | 2516835 | 0 | 1010272521 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 48 | 100 | 2015-11-28 | 2017-11-05 | 2023-04-14 | 2023-04-14 |  |  | تأخرصرف المستحقات المالية |  | 46.6706 | 24.7025 | Failed | Yes
2100061843 | وزارة التعليم | تشييد | ذات اولوية عالية | 4566525 | 228326.25 | 3460295.5 | 3460295.5 | 4030128372 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 95 | 100 | 2014-12-17 | 2015-12-07 | 2022-09-15 | 2022-09-15 | 2015-12-07 |  | ضعف كفاءة المقاول الفنية |  | 38.0623 | 24.0861 | منجز | No
2200213684 | وزارة البيئة والمياة والزراعة | ترميم | ذات اولوية متوسطة | 226233 | 11311.65 | 226233 | 226233 | 5950018887 | لا | 0 | 200101051608 | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2020-06-16 | 2020-10-18 | 2020-10-18 | 2020-10-18 | 2020-10-18 |  |  |  | 42.8638 | 19.0969 | منجز | No
2100012574 | أمانة / الرياض | تشييد | ذات اولوية عالية وعاجلة | 1745841512.47 | 87292075.6235 | 583089902.57 | 559412602.67 | 1010010506 | لا | 0 | 190301099926 | جاري | تكلفة العمل المنجز | 37.31 | 64.3 | 2019-07-21 | 2023-12-31 | 2023-12-31 | 2023-12-31 |  |  |  |  | 46.6759 | 24.7007 | Failed | No
2200213135 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية وعاجلة | 39641453.12 | 1982072.656 | 9698991.73 | 8783554.23 | 1118000259 | لا | 0 |  | جاري | تكلفة العمل المنجز | 23.63 | 15.16 | 2021-10-10 | 2024-04-10 | 2024-04-10 | 2024-04-10 |  |  |  |  | 46.8284 | 24.6783 | منتظم | No
2100031835 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 66058527.13 | 3302926.3565 | 59936975.07 | 56372908.26 | 1010014477 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 91.01 | 100 | 2018-06-20 | 2019-06-20 | 2022-12-30 | 2022-12-30 |  |  | أوامر تغيير |  | 46.7098 | 24.6275 | Failed | No
2100081126 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 845800 | 42290 | 421.23 | 0 | 1123002388 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 50 | 100 | 2015-10-13 | 2016-10-07 | 2020-02-13 | 2020-02-13 |  |  | ضعف كفاءة المقاول الفنية |  | 45.8644 | 25.261 | مسحوب | Yes
2100007766 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 10766792.08 | 538339.604 | 4010134.91 | 4010134.91 | 1116004360 | لا | 0 |  | مسحوب | التكلفة المفوترة | 34 | 100 | 2013-04-23 | 2015-04-13 | 2023-08-22 | 2023-08-22 |  |  | ضعف كفاءة المقاول الفنية |  | 38.0623 | 24.0861 | مسحوب | No
2100004922 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 65000000 | 3250000 | 59611920.37 | 59611920.37 | 5950010121 | لا | 0 | 180501008086 | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2018-08-27 | 2020-08-05 | 2021-08-08 | 2021-08-08 | 2020-08-05 | 2022-08-04 |  |  | 42.6894 | 21.719 | منجز | No
2100087732 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية | 136714700 | 6835735 | 94418239.51 | 94418239.51 | 1131018844 | لا | 0 | 181109273820 | مسحوب | منهجية القيمة المكتسبة | 77 | 100 | 2014-01-06 | 2016-06-10 | 2022-09-30 | 2022-09-30 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.6968 | 27.506 | مسحوب | No
2100102616 | شركة المياه الوطنية / منطقة الباحة | إشراف | ذات اولوية عالية وعاجلة | 2322054 | 116102.7 | 2322054 | 2322054 | 1131052239 | لا | 0 | 190301018398 | جاري | التكلفة المفوترة | 100 | 100 | 2019-01-15 | 2022-01-16 | 2022-01-16 | 2022-01-16 |  |  | لا يوجد تأخير |  | 41.6054 | 19.9786 | خدمات عامة | No
2100018911 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1016077.25 | 50803.8625 | 420.66 | 0 | 1017000694 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 40 | 100 | 2015-07-29 | 2016-10-21 | 2021-07-04 | 2021-07-04 |  |  | ضعف كفاءة المقاول الفنية |  | 45.5711 | 20.4614 | Failed | Yes
2100059555 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية | 18744264 | 937213.2 | 14245486.29 | 14245486.29 | 2050003338 | لا | 0 | 180801052954 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 84.29 | 100 | 2018-06-24 | 2020-06-02 | 2021-06-21 | 2021-06-21 | 2020-06-02 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.4135 | 27.8986 | منجز | No
2200213150 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 4693643.48 | 234682.174 | 4693643.48 | 4693643.48 | 1010016228 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2021-09-01 | 2021-11-28 | 2021-11-09 | 2021-11-09 | 2021-11-28 |  |  |  | 45.5736 | 24.2095 | منجز | No
2100065936 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2000000 | 100000 | 41991 | 0 | 2051047076 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 100 | 2015-04-14 | 2016-10-05 | 2017-02-03 | 2017-02-03 | 2016-10-05 |  |  |  | 45.3695 | 25.8859 | منجز | Yes
2100066511 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 16847250 | 842362.5 | 16847250 | 16742844 | 2060024520 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2019-07-06 | 2020-12-19 | 2020-12-19 | 2020-12-19 | 2020-12-19 |  |  |  | 50.0756 | 26.3722 | منجز | No
2200234360 | أمانة / العاصمة المقدسة | دراسات هندسية | ذات اولوية متوسطة | 7969557.96 | 398477.898 | 7660580 | 7660580 | 2051060068 | لا | 0 |  | منجز – استلام نهائي | تكلفة العمل المنجز | 96.12 | 96.12 | 2020-06-28 | 2022-06-08 | 2022-06-08 | 2022-06-08 | 2022-06-08 | 2022-07-20 |  |  | 39.8579 | 21.3891 | منجز | No
2100041565 | وزارة التعليم | تشييد | ذات اولوية عالية | 9449518.54 | 472475.927 | 6418080.16 | 6418080.16 | 1010182874 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2013-09-04 | 2015-08-25 | 2022-08-09 | 2022-08-09 | 2015-08-25 |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.5802 | منجز | No
2100097860 | وزارة الدفاع / الإدارة الهندسية والاشغال بقوات الدفاع الجوي | تشييد | ذات اولوية متوسطة | 2948143.78 | 147407.189 | 2948143.78 | 489981.5 | 1010156182 | لا | 0 | 190901035196 | فسخ العقد | الكميات التي تم تركيبها | 17 | 100 | 2019-09-24 | 2021-08-22 | 2022-02-28 | 2022-02-28 |  |  | أوامر سامية |  | 46.6772 | 24.7069 | مسحوب | No
2100066220 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1016077.25 | 50803.8625 | 606991 | 0 | 1017000694 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 40 | 95 | 2015-07-29 | 2016-10-21 | 2019-07-06 | 2019-07-06 |  |  | ضعف كفاءة المقاول الفنية |  | 45.5822 | 20.4667 | Failed | Yes
2100023284 | وزارة التعليم | تشييد | لم تعد تحتاجها الجهة | 3249673.57 | 162483.6785 | 0 | 0 | 1160086590 | لا | 0 |  | مسحوب | التكلفة المفوترة | 1 | 100 | 2015-11-15 | 2017-05-08 | 2019-07-31 | 2019-07-31 |  |  | ضعف كفاءة المقاول الفنية |  | 46.1235 | 24.6048 | مسحوب | No
2100018476 | جامعة المجمعة | تشييد | ذات اولوية عالية وعاجلة | 4548609 | 227430.45 | 4548609 | 4472130.02 | 1010165175 | لا | 0 | 200101017392 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2020-05-03 | 2021-12-31 | 2022-03-31 | 2022-03-31 | 2021-12-31 |  | عدم واقعية الجدول الزمني |  | 45.4151 | 25.8724 | منجز | No
2100049210 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 34033763.1 | 1701688.155 | 22393459.1 | 22393459.1 | 1010231237 | لا | 0 | 180809065123 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 94.66 | 100 | 2014-01-07 | 2016-12-05 | 2021-03-10 | 2021-03-10 | 2016-12-05 |  | لا يوجد تأخير |  | 47.3078 | 24.1522 | منجز | No
2100191730 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 111973000 | 5598650 | 2251915.82 | 2251915.82 | 1010122914 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 5.17 | 5.06 | 2021-04-29 | 2023-04-29 | 2023-04-29 | 2023-04-29 |  |  |  |  | 46.5315 | 24.5743 | منتظم | No
2100103353 | وزارة الدفاع / الإدارة الهندسية والاشغال بقوات الدفاع الجوي | تشييد | ذات اولوية متوسطة | 2755221 | 137761.05 | 2755221 | 1217532.16 | 1010177619 | لا | 0 | 200201023612 | جاري | الكميات التي تم تركيبها | 85 | 100 | 2020-02-27 | 2021-02-15 | 2021-12-31 | 2021-12-31 |  |  | أوامر سامية |  | 46.6924 | 24.7146 | Failed | No
2100055952 | أمانة / الرياض | دراسة الجدوى | ذات اولوية متوسطة | 2725000 | 136250 | 0 | 0 | 1010434689 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-01-04 | 2017-12-19 | 2017-12-19 | 2017-12-19 | 2017-12-19 |  | اخرى |  |  |  | منجز | No
2100004631 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية وعاجلة | 17266345.81 | 863317.2905 | 13484720.81 | 13318497.1 | 1010289236 | لا | 0 | 180709023472 | فسخ العقد | تكلفة العمل المنجز | 88 | 100 | 2015-01-17 | 2016-04-11 | 2024-12-31 | 2024-12-31 |  |  | لا يوجد تأخير |  | 42.6516 | 17.1668 | مسحوب | No
2100069381 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 59038778.7 | 2951938.935 | 28946961.11 | 28946961.11 | 1010014477 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 92.55 | 100 | 2019-03-07 | 2021-03-08 | 2022-07-31 | 2022-07-31 |  |  | لا يوجد تأخير |  | 46.7098 | 24.6275 | Failed | No
2100020554 | شركة المياه الوطنية / منطقة الرياض | تصميم | ذات اولوية عالية | 984000 | 49200 | 984000 | 984000 | 2050101543 | لا | 0 | 181209428853 | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2018-12-23 | 2019-04-22 | 2019-04-22 | 2019-04-22 |  | 2019-04-22 | لا يوجد تأخير |  | 44.831 | 20.4565 | منجز | No
2100070125 | شركة المياه الوطنية / منطقة الرياض | دراسات هندسية | ذات اولوية عالية | 27024500 | 1351225 | 18941986.76 | 17101071.66 | 1010407685 | لا | 0 |  | جاري | تكلفة العمل المنجز | 96.5 | 100 | 2019-07-21 | 2021-01-21 | 2022-04-01 | 2022-04-01 |  |  | لا يوجد تأخير |  | 46.7944 | 24.6528 | خدمات عامة | No
2100029820 | أمانة / الرياض | تشييد | ذات اولوية عالية | 12895665 | 644783.25 | 5841249.11 | 0 | 1116005202 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 96 | 100 | 2013-06-08 | 2015-05-29 | 2019-10-21 | 2019-10-21 | 2015-05-29 |  | ضعف كفاءة المقاول الفنية |  | 44.6256 | 23.9007 | منجز | Yes
2100042545 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 5590932.62 | 279546.631 | 359763.45 | 359763.45 | 1010142553 | لا | 0 |  | مسحوب | التكلفة المفوترة | 12 | 100 | 2016-09-26 | 2018-03-20 | 2019-10-26 | 2019-10-26 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | مسحوب | No
2100191752 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 17403750 | 870187.5 | 9797492.95 | 9797492.95 | 1010227442 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 57.08 | 45.67 | 2021-06-09 | 2023-06-09 | 2023-06-08 | 2023-06-08 |  |  |  |  | 46.5408 | 24.755 | منتظم | No
2100061423 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 13630550 | 681527.5 | 13554872.2 | 12202159.6 | 1010275506 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 99.92 | 100 | 2018-12-27 | 2020-12-28 | 2020-12-27 | 2020-12-27 |  | 2020-12-28 | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100042932 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية وعاجلة | 30000000 | 1500000 | 11702027.64 | 11332757.47 | 2051001250 | لا | 0 | 181001151982 | جاري | منهجية القيمة المكتسبة | 53.88 | 84.53 | 2019-01-15 | 2021-01-15 | 2023-02-20 | 2023-02-20 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 49.9973 | 26.5769 | Failed | No
2100032675 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 15959500 | 797975 | 41794 | 0 | 1010056094 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 70 | 100 | 2015-01-06 | 2016-12-26 | 2021-01-24 | 2021-01-24 |  |  | ضعف كفاءة المقاول الفنية |  | 46.683 | 24.7038 | Failed | Yes
2100044704 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 16348233 | 817411.65 | 9586631.45 | 0 | 1116005202 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 94.59 | 100 | 2014-09-19 | 2016-09-08 | 2020-10-11 | 2020-10-11 | 2016-09-08 |  | ضعف كفاءة المقاول الفنية |  | 46.6644 | 24.6757 | منجز | Yes
2200234404 | أمانة / العاصمة المقدسة | إشراف | ذات اولوية متوسطة | 4180848 | 209042.4 | 871010 | 871010 | 4031070328 | لا | 0 |  | جاري | تكلفة العمل المنجز | 20.83 | 20.83 | 2022-05-29 | 2024-06-09 | 2024-06-09 | 2024-06-09 |  |  |  |  | 39.8579 | 21.3891 | خدمات عامة | No
2100086671 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 53817671.99 | 2690883.5995 | 49265126.4 | 49265126.4 | 1010210667 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-11-27 | 2019-07-25 | 2020-05-05 | 2020-05-05 | 2019-07-25 | [5 empty] | منجز | No
2100041156 | أمانة / العاصمة المقدسة | تصميم | ذات اولوية متوسطة | 5460000 | 273000 | 5449400 | 5449400 | 2051060068 | لا | 0 |  | منجز – استلام نهائي | اخرى | 100 | 100 | 2018-05-07 | 2020-05-06 | 2020-05-06 | 2020-05-06 | 2020-05-06 | 2020-05-20 | اخرى |  |  |  | منجز | No
2100096880 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 9696909.3 | 484845.465 | 4571182.61 | 4315858.02 | 1010138875 | نعم | 1746923.65 | 180809055409 | جاري | منهجية القيمة المكتسبة | 92 | 100 | 2015-08-16 | 2017-07-24 | 2023-02-15 | 2023-02-15 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 45.8688 | 25.2426 | متأخر | No
2100199883 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية وعاجلة | 39170230 | 1958511.5 | 16990707 | 16990707 | 2057001166 | لا | 0 | 181001139762 | جاري | منهجية القيمة المكتسبة | 48.78 | 62.16 | 2021-04-19 | 2023-04-19 | 2023-04-19 | 2023-04-19 |  |  |  |  | 46.0207 | 28.3645 | متأخر | No
2100056884 | شركة المياه الوطنية / منطقة الرياض | إشراف | ذات اولوية عالية | 20742480 | 1037124 | 16462370.34 | 16462370.34 | 1010323435 | لا | 0 |  | جاري | تكلفة العمل المنجز | 92.87 | 100 | 2019-11-03 | 2022-05-04 | 2022-05-04 | 2022-05-04 |  |  | لا يوجد تأخير |  | 46.7943 | 24.653 | خدمات عامة | No
2100102572 | أمانة / الرياض | دراسات هندسية | ذات اولوية متوسطة | 13850000 | 692500 | 13653053 | 13653053 | 1010425026 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2010-11-22 | 2019-01-30 | 2019-01-30 | 2019-01-30 | 2019-01-30 |  | ضعف اداء الاستشاري |  |  |  | منجز | No
2100061681 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 14865600 | 743280 | 13135291.3 | 13135291.3 | 1010275506 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 98.52 | 100 | 2019-01-29 | 2020-07-29 | 2020-09-05 | 2020-09-05 |  | 2020-07-29 | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100091711 | شركة المياه الوطنية / منطقة الرياض | إشراف | ذات اولوية عالية | 8560000 | 428000 | 4707990.31 | 4707990.31 | 1010314421 | لا | 0 |  | جاري | مدفوعات ساعات العمل | 55 | 97.47 | 2019-03-21 | 2022-03-22 | 2022-07-28 | 2022-07-28 |  |  | لا يوجد تأخير |  | 46.7943 | 24.653 | خدمات عامة | No
2100192264 | جامعة المجمعة | تشييد | ذات اولوية عالية وعاجلة | 40757418.38 | 2037870.919 | 34998832.7 | 34998832.7 | 1010005046 | لا | 0 | 180909072773 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-09-04 | 2021-08-14 | 2021-08-14 | 2021-08-14 | 2021-08-14 |  |  |  | 45.4211 | 25.8779 | منجز | No
2100056851 | شركة المياه الوطنية / منطقة حائل | إشراف | لم تعد تحتاجها الجهة | 4904000 | 245200 | 5852068.46 | 5852068.46 | 3350040777 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2012-01-14 | 2015-01-14 | 2020-07-15 | 2020-07-15 | 2015-01-14 |  | لا يوجد تأخير |  | 42.4095 | 27.8764 | منجز | No
2200213743 | شركة المياه الوطنية / منطقة حائل | إشراف | ذات اولوية عالية وعاجلة | 7700400 | 385020 | 13593798.99 | 3051162.15 | 2050101543 | لا | 0 | 210701046872 | جاري | التكلفة المفوترة | 52.03 | 45.7 | 2021-10-24 | 2023-04-24 | 2023-04-24 | 2023-04-24 |  |  |  |  | 41.7164 | 27.5069 | خدمات عامة | No
2100104790 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 717856181.28 | 35892809.064 | 368978362.21 | 361309815.43 | 1010004249 | لا | 0 |  | ايقاف كلي | منهجية القيمة المكتسبة | 68.17 | 81.98 | 2011-09-14 | 2014-08-12 | 2023-05-31 | 2023-05-31 |  |  | لا يوجد تأخير |  | 46.7098 | 24.6275 | Failed | No
2100061316 | وزارة الرياضة | تشييد | ذات اولوية متوسطة | 60130381.06 | 3006519.053 | 14692563 | 14692563 | 1010006362 | نعم | 348565.36 |  | مسحوب | الكميات التي تم تركيبها | 65 | 100 | 2012-08-29 | 2015-01-31 | 2021-12-31 | 2021-12-31 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | مسحوب | No
2200234485 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | دراسات هندسية | ذات اولوية عالية | 173592.5 | 8679.625 | 0 | 0 | 1010430162 | لا | 0 | 221001052531 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2022-10-10 | 2022-11-23 | 2023-02-28 | 2023-02-28 |  |  |  |  | 39.1925 | 21.4858 | منتظم | No
2100000545 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية | 46427800 | 2321390 | 41439253.97 | 41404253.97 | 1134000066 | لا | 0 | 180709025804 | مسحوب | منهجية القيمة المكتسبة | 91.62 | 100 | 2014-06-18 | 2016-05-27 | 2023-08-01 | 2023-08-01 |  |  | ضعف كفاءة المقاول الفنية |  | 41.3171 | 26.7909 | مسحوب | No
2100056755 | أمانة / الرياض | دراسة الجدوى | ذات اولوية متوسطة | 840000 | 42000 | 39572 | 0 | 1010103658 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2011-09-06 | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 |  | اخرى |  |  |  | منجز | Yes
2100064315 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2296150 | 114807.5 | 42067 | 0 | 2050051754 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 15 | 100 | 2015-07-29 | 2016-10-21 | 2023-08-23 | 2023-08-23 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | مسحوب | Yes
2100199290 | وزارة الداخلية / المديرية العامة لحرس الحدود | تشييد | ذات اولوية عالية | 2958716.55 | 147935.8275 | 2958716.55 | 2958716.55 | 4030209372 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2021-09-09 | 2022-03-04 | 2022-03-05 | 2022-03-05 | 2022-03-04 |  |  |  | 37.2517 | 25.0447 | منجز | No
2100058553 | وزارة التعليم | تشييد | ذات اولوية عالية | 16124279 | 806213.95 | 2643528.85 | 2643528.85 | 1010142553 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 16 | 100 | 2014-11-23 | 2017-02-10 | 2017-06-07 | 2017-06-07 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 46.7098 | 24.6275 | مسحوب | No
2100060023 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 1225650.29 | 61282.5145 | 0 | 0 | 1010276834 | لا | 0 |  | جاري | التكلفة المفوترة | 1 | 100 | 2012-04-15 | 2013-06-09 | 2013-07-06 | 2013-07-06 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | Failed | No
2100074406 | جامعة الملك سعود | تشييد | ذات اولوية متوسطة | 55767878.29 | 2788393.9145 | 32977185.04 | 32977185.04 | 1010420564 | لا | 0 | 200309013292 | جاري | تكلفة العمل المنجز | 73 | 100 | 2019-06-09 | 2020-06-09 | 2022-12-31 | 2022-12-31 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 46.7098 | 24.6275 | Failed | No
2100049980 | أمانة / الجوف | تشييد | ذات اولوية عالية | 27491230 | 1374561.5 | 27491230 | 27491230 | 1134000444 | لا | 0 | 181201445108 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-02-05 | 2020-07-29 | 2020-07-29 | 2020-07-29 | 2020-07-29 |  |  |  | 40.135 | 29.872 | منجز | No
2100190573 | شركة المياه الوطنية / منطقة الرياض | تصميم | ذات اولوية عالية | 8523800 | 426190 | 7006432.22 | 7006432.22 | 2050101543 | لا | 0 |  | جاري | التكلفة المفوترة | 82.2 | 82.2 | 2020-09-17 | 2022-09-17 | 2022-09-17 | 2022-09-17 |  |  |  |  | 46.7942 | 24.6533 | منتظم | No
2100191225 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 3809523.81 | 190476.1905 | 2670476.4 | 2670476.4 | 1010276827 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2020-04-23 | 2020-10-23 | 2022-02-28 | 2022-02-28 | 2020-10-23 |  | التنسيق مع أصحاب المصلحه (خدمات |  | 39.9051 | 21.3994 | منجز | No
2100087205 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية منخفضة | 8600000 | 430000 | 2963628.47 | 2963628.47 | 2251045738 | لا | 0 | 181009153709 | مسحوب | منهجية القيمة المكتسبة | 46 | 100 | 2018-02-25 | 2020-02-25 | 2023-06-14 | 2023-06-14 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 50.168 | 26.3214 | مسحوب | No
2100006694 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 6963999.71 | 348199.9855 | 5414007.65 | 5414007.65 | 1131003889 | لا | 0 | 190209011105 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2013-08-12 | 2015-02-03 | 2021-12-30 | 2021-12-30 | 2015-02-03 |  |  |  | 40.0549 | 29.8587 | منجز | No
2100009601 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1768975 | 88448.75 | 41639 | 0 | 1116009614 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 57.77 | 100 | 2014-11-04 | 2015-10-20 | 2019-10-27 | 2019-10-27 |  |  | ضعف كفاءة المقاول الفنية |  | 44.3935 | 24.5062 | Failed | Yes
2100002030 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية | 38714500 | 1935725 | 38714500 | 38714500 | 5855021168 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-03-27 | 2020-08-29 | 2020-07-23 | 2020-07-23 |  | 2020-08-29 | لا يوجد تأخير |  | 40.3222 | 26.8621 | منجز | No
2100191376 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية وعاجلة | 13734524.75 | 686726.2375 | 1376300 | 0 | 1010147422 | لا | 0 | 201101285677 | جاري | منهجية القيمة المكتسبة | 21.97 | 100 | 2021-03-25 | 2021-12-25 | 2022-09-01 | 2022-09-01 |  |  |  |  | 41.8046 | 27.6192 | Failed | Yes
2100013926 | أمانة / الرياض | تشييد | ذات اولوية عالية | 930050 | 46502.5 | 41196 | 0 | 1118001032 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 88.2 | 100 | 2013-05-06 | 2014-07-30 | 2014-07-30 | 2014-07-30 |  |  | ضعف كفاءة المقاول الفنية |  | 43.8311 | 25.019 | مسحوب | Yes
2100060782 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 6994238.03 | 349711.9015 | 2414072.63 | 0 | 4650020435 | لا | 0 |  | مسحوب | التكلفة المفوترة | 47 | 100 | 2013-12-29 | 2015-12-20 | 2023-06-15 | 2023-06-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | Yes
2200234533 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | توريد وتركيب | ذات اولوية متوسطة | 1004819.48 | 50240.974 | 0 | 0 | 1010499889 | لا | 0 | 220701116674 | جاري | تكلفة العمل المنجز | 100 | 100 | 2022-10-02 | 2022-12-30 | 2023-02-28 | 2023-02-28 |  |  |  |  | 47.1167 | 17.485 | منتظم | No
2100086682 | شركة المياه الوطنية / منطقة الحدود الشمالية | تشييد | ذات اولوية عالية | 61092330 | 3054616.5 | 57876944 | 57876944 | 1010171599 | لا | 0 | 180709020798 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2015-06-01 | 2018-04-30 | 2020-12-22 | 2020-12-22 |  | 2018-04-30 | لا يوجد تأخير |  | 40.9991 | 30.992 | منجز | No
2100081900 | هيئة تطوير بوابة الدرعية | تشييد | ذات اولوية عالية | 4654003 | 232700.15 | 4654003 | 4654003 | 1010079992 | لا | 0 |  | جاري | اخرى | 100 | 100 | 2019-05-22 | 2021-10-27 | 2020-07-16 | 2020-07-16 | [6 empty] | Failed | No
2200214200 | أمانة / الأحساء | أخرى | ذات اولوية عالية وعاجلة | 8750798.005 | 437539.9003 | 3813037 | 3813037 | 1010193266 | نعم | 0.1 | 220209137742 | جاري | الكميات التي تم تركيبها | 45 | 50 | 2021-11-07 | 2023-05-01 | 2023-05-01 | 2023-05-01 |  |  |  |  | 49.5398 | 25.4257 | خدمات عامة | No
2100189604 | الهيئة الملكية للجبيل وينبع / مدينة جازان للصناعات الأساسية والتحويلية | تصميم وتشييد | ذات اولوية عالية وعاجلة | 437533598.83 | 21876679.9415 | 126994675.4 | 126994675.4 | 2054000121 | لا | 0 | 191001132509 | جاري | اخرى | 3.56 | 86.4 | 2020-07-15 | 2023-07-15 | 2025-10-01 | 2025-10-01 |  |  |  | تم تمديد الجدول الزمني | 42.405 | 17.3218 | Failed | No
2100006974 | جامعة الطائف | تشييد | ذات اولوية متوسطة | 99867947 | 4993397.35 | 84944538.73 | 78452042.03 | 1010070634 | لا | 0 | 181109364841 | جاري | تكلفة العمل المنجز | 83 | 85 | 2019-01-11 | 2020-08-31 | 2023-09-18 | 2023-09-18 |  |  | لا يوجد تأخير |  | 40.4877 | 21.3275 | منتظم | No
2100056943 | شركة المياه الوطنية / منطقة الحدود الشمالية | إشراف | ذات اولوية عالية | 2898000 | 144900 | 2350076.31 | 2350076.31 | 1010406370 | لا | 0 | 181109306877 | منجز – استلام ابتدائي | التكلفة المفوترة | 98 | 100 | 2014-02-17 | 2016-02-16 | 2021-12-18 | 2021-12-18 | 2016-02-16 |  | لا يوجد تأخير |  | 38.665 | 31.6665 | منجز | No
2200228023 | أمانة / المنطقة الشرقية | تصميم وتشييد | ذات اولوية متوسطة | 5970225 | 298511.25 | 5356740 | 5356740 | 2062016958 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 90 | 95 | 2021-08-29 | 2022-08-29 | 2022-08-29 | 2022-08-29 | 2022-08-29 |  |  |  | 50.0888 | 26.4207 | منجز | No
2200228045 | أمانة / المنطقة الشرقية | تصميم وتشييد | ذات اولوية عالية | 8883175 | 444158.75 | 6628365 | 6628365 | 2062016958 | لا | 0 |  | جاري | التكلفة المفوترة | 81 | 93 | 2021-10-27 | 2022-10-27 | 2022-10-27 | 2022-10-27 |  |  |  |  | 50.0888 | 26.4207 | متأخر | No
2100014033 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 6418388 | 320919.4 | 6386487 | 6386487 | 2060023127 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2019-05-23 | 2020-05-11 | 2020-05-11 | 2020-05-11 | 2020-05-11 |  |  |  | 50.2097 | 26.2823 | منجز | No
2100102104 | وزارة الصحة / حائل | تشييد | ذات اولوية عالية | 4999670 | 249983.5 | 2250185.82 | 2250185.82 | 3350009207 | لا | 0 | 190901003004 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-09-29 | 2022-09-01 | 2022-09-01 | 2022-09-01 | 2022-09-01 |  | ضعف كفاءة المقاول الفنية |  | 41.6964 | 27.5096 | منجز | No
2100085326 | أمانة / الرياض | دراسات هندسية | ذات اولوية متوسطة | 38671500 | 1933575 | 17524810 | 14903366.56 | 1010468431 | لا | 0 |  | جاري | التكلفة المفوترة | 90 | 100 | 2019-01-24 | 2021-07-12 | 2022-03-15 | 2022-03-15 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  |  |  | خدمات عامة | No
2100043842 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية متوسطة | 23059450 | 1152972.5 | 23197006.94 | 23197006.94 | 1129000025 | لا | 0 | 180709019768 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 99.97 | 100 | 2012-04-22 | 2014-09-25 | 2020-01-06 | 2020-01-06 |  | 2014-09-25 | لا يوجد تأخير |  | 43.9544 | 26.3504 | منجز | No
2100190470 | شركة المياه الوطنية / منطقة الرياض | إشراف | ذات اولوية عالية | 15888000 | 794400 | 8920158.74 | 8920158.74 | 2050101543 | لا | 0 | 190701123831 | جاري | التكلفة المفوترة | 88.7 | 88.7 | 2020-01-26 | 2023-01-26 | 2023-01-27 | 2023-01-27 |  |  |  |  | 46.576 | 24.6385 | خدمات عامة | No
2100043175 | شركة المياه الوطنية / منطقة الحدود الشمالية | تشييد | ذات اولوية عالية | 5115518.44 | 255775.922 | 5115518.44 | 5115518.44 | 1010239020 | لا | 0 | 181001165924 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-07-03 | 2020-06-11 | 2020-09-01 | 2020-09-01 |  | 2020-06-11 | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 38.6525 | 31.6739 | منجز | No
2100048915 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية | 7999050 | 399952.5 | 8397712.92 | 8397712.92 | 1010022543 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-10-08 | 2019-09-17 | 2020-03-10 | 2020-03-10 |  | 2019-09-17 | لا يوجد تأخير |  | 43.4988 | 25.8709 | منجز | No
2100024113 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 47025000 | 2351250 | 44934650 | 44934650 | 1010012911 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 87.95 | 100 | 2016-12-11 | 2018-12-11 | 2019-10-22 | 2019-10-22 | 2018-12-11 |  | لا يوجد تأخير |  | 40.2136 | 21.9877 | منجز | No
2100093085 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 2695080 | 134754 | 2369635 | 2369635 | 2511104587 | لا | 0 |  | جاري | اخرى | 100 | 100 | 2020-01-13 | 2020-12-12 | 2020-12-12 | 2020-12-12 |  |  | اخرى |  |  |  | Failed | No
2100050374 | أمانة / جازان | تشييد | ذات اولوية عالية | 882250 | 44112.5 | 422147 | 422147 | 5903030625 | لا | 0 | 191201009220 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 96 | 100 | 2018-08-29 | 2019-08-14 | 2021-08-30 | 2021-08-30 | 2019-08-14 |  | ضعف كفاءة المقاول الفنية |  | 42.0255 | 17.7183 | منجز | No
2100192706 | البريد السعودي | تصميم وإشراف | ذات اولوية عالية | 1352505 | 67625.25 | 134610 | 0.01 | 2050093025 | لا | 0 | 190409004432 | جاري | تكلفة العمل المنجز | 75 | 75 | 2018-05-08 | 2022-12-30 | 2022-12-31 | 2022-12-31 |  |  |  |  | 46.7129 | 24.9284 | منتظم | No
2100074336 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1865843 | 93292.15 | 1030622 | 1030622 | 1118001885 | لا | 0 |  | مسحوب | التكلفة المفوترة | 90 | 100 | 2011-04-02 | 2012-06-24 | 2022-05-31 | 2022-05-31 |  |  | ضعف كفاءة المقاول الفنية |  | 42.9095 | 23.8972 | مسحوب | No
2100091836 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 6913500 | 345675 | 40828 | 0 | 1128001203 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2012-03-16 | 2015-01-20 | 2015-01-20 | 2015-01-20 | 2015-01-20 |  |  |  | 47.3196 | 24.1352 | منجز | Yes
2100108942 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 3492603.45 | 174630.1725 | 2439278.6 | 2439278.6 | 4032003067 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2020-08-27 | 2020-10-03 | 2021-07-27 | 2021-07-27 | 2020-10-03 | [5 empty] | منجز | No
2200234566 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | أخرى | ذات اولوية متوسطة | 709624.75 | 35481.2375 | 0 | 0 | 5950014853 | لا | 0 | 220501174461 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2022-08-21 | 2022-11-17 | 2023-02-28 | 2023-02-28 | 2022-11-17 |  |  |  | 47.1167 | 17.485 | منتظم | No
2100020230 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 500661 | 25033.05 | 500661 | 500661 | 5951126918 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2019-06-30 | 2020-02-01 | 2020-02-01 | 2020-02-01 | 2020-02-01 |  | لا يوجد تأخير |  |  |  | منجز | No
2100084696 | هيئة تطوير بوابة الدرعية | تصميم |  | 52486350 | 2624317.5 | 0 | 0 | 0 |  | 0 |  | جاري | التكلفة المفوترة | 6 | 6 | 2020-03-14 21:00 | 2024-09-14 21:00 |  |  |  |  | لا يوجد تأخير |  |  |  | منتظم | No
2100092864 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 713120 | 35656 | 366421 | 366421 | 5908005820 | لا | 0 | 181109358971 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 98 | 100 | 2018-09-19 | 2019-09-18 | 2021-07-11 | 2021-07-11 | 2019-09-18 |  | ضعف كفاءة المقاول الفنية |  | 42.6099 | 16.9248 | منجز | No
2100081012 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1583400 | 79170 | 0.01 | 0.01 | 1010211585 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-12-12 | 2019-06-10 | 2020-06-04 | 2020-06-04 | 2019-06-10 |  | ضعف كفاءة المقاول الفنية |  |  |  | منجز | No
2100105486 | جامعة الإمام عبدالرحمن بن فيصل | تشييد | ذات اولوية عالية وعاجلة | 54284028 | 2714201.4 | 47084228 | 47084228 | 2050022550 | لا | 0 | 180709034795 | جاري | تكلفة العمل المنجز | 94.99 | 96.7 | 2013-05-01 | 2015-10-03 | 2022-03-23 | 2022-03-23 |  |  | اخرى |  | 50.1928 | 26.3815 | متأخر | No
2200228303 | وزارة الصحة / المدينة المنورة | ترميم | ذات اولوية متوسطة | 227400 | 11370 | 0 | 0 | 4659100139 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2022-07-04 | 2022-11-03 | 2022-11-03 | 2022-11-03 | 2022-11-03 |  |  |  | 39.5608 | 24.4952 | منجز | No
2100103106 | شركة المياه الوطنية / منطقة مكة المكرمة | إشراف | ذات اولوية عالية وعاجلة | 5736000 | 286800 | 5353040.21 | 5353040.21 | 1131035992 | لا | 0 |  | جاري | التكلفة المفوترة | 100 | 100 | 2019-10-20 | 2021-10-19 | 2022-02-21 | 2022-02-21 |  |  | لا يوجد تأخير |  | 40.4509 | 21.3518 | خدمات عامة | No
2100103784 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية | 53120038 | 2656001.9 | 32394840.12 | 32394840.12 | 1010184370 | لا | 0 | 180709031911 | مسحوب | منهجية القيمة المكتسبة | 94 | 100 | 2014-01-28 | 2015-07-14 | 2022-12-01 | 2022-12-01 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 40.4731 | 26.0049 | مسحوب | No
2100026456 | أمانة / الرياض | تشييد | ذات اولوية عالية | 12284230 | 614211.5 | 1573238 | 0 | 1017000207 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 97 | 100 | 2015-05-20 | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 |  | ضعف كفاءة المقاول الفنية |  | 46.7315 | 22.3063 | منجز | Yes
2200228281 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 1432895 | 71644.75 | 1432894.6 | 1432894.6 | 2056001462 | لا | 0 |  | جاري | تكلفة العمل المنجز | 100 | 56 | 2022-05-23 | 2023-03-19 | 2022-11-07 | 2022-11-07 |  |  |  |  | 48.4957 | 27.4692 | منتظم | No
2100108614 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 2199440 | 109972 | 2199440 | 2199440 | 2511104587 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2019-06-23 | 2019-11-17 | 2020-01-17 | 2020-01-17 | 2019-11-17 |  | لا يوجد تأخير |  |  |  | منجز | No
2100018653 | شركة المياه الوطنية / منطقة الرياض | الخدمات الاستشارية | ذات اولوية عالية | 3465600 | 173280 | 2113876.64 | 2050701.64 | 1010314421 | لا | 0 |  | جاري | التكلفة المفوترة | 73.81 | 66.03 | 2019-12-26 | 2021-12-25 | 2023-03-09 | 2023-03-09 |  |  | لا يوجد تأخير |  | 46.7943 | 24.6528 | خدمات عامة | No
2100199920 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية وعاجلة | 9000000 | 450000 | 3098655.19 | 3098655.19 | 2050060197 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 93 | 98.73 | 2021-08-29 | 2022-08-18 | 2022-11-30 | 2022-11-30 |  |  |  |  | 49.5586 | 25.2653 | متأخر | No
2100078164 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية متوسطة | 2724050 | 136202.5 | 2723950 | 2723950 | 5850022870 | لا | 0 | 180701016861 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-07-15 | 2019-10-01 | 2019-09-25 | 2019-09-25 |  | 2019-10-01 | لا يوجد تأخير |  | 42.4989 | 18.2169 | منجز | No
2100074793 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية | 21470000 | 1073500 | 19239825.6 | 19239825.6 | 1118000259 | لا | 0 | 180201000140 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 98.5 | 100 | 2018-04-25 | 2021-03-22 | 2021-11-21 | 2021-11-21 | 2021-03-22 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.6969 | 27.506 | منجز | No
2100085993 | جامعة الإمام عبدالرحمن بن فيصل | تشييد | ذات اولوية عالية وعاجلة | 36958504 | 1847925.2 | 19647986 | 19647986 | 2055002293 | لا | 0 | 180809040711 | ايقاف كلي | تكلفة العمل المنجز | 52 | 90.7 | 2014-09-07 | 2017-02-08 | 2022-12-29 | 2022-12-29 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 50.1931 | 26.3956 | Failed | No
2100087312 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 50914650 | 2545732.5 | 29757853.55 | 29488357.55 | 4030032844 | لا | 0 | 181001150787 | جاري | منهجية القيمة المكتسبة | 78.07 | 88.02 | 2019-01-07 | 2021-07-07 | 2023-01-30 | 2023-01-30 |  |  | اخرى |  | 50.0392 | 26.3819 | متأخر | No
2100028862 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2094775 | 104738.75 | 2094775 | 0 | 1010298824 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-08-05 | 2018-09-16 | 2021-06-16 | 2021-06-16 | 2018-09-16 |  | تأخرصرف المستحقات المالية |  | 46.5427 | 24.7418 | منجز | Yes
2100034871 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 20484964.1 | 1024248.205 | 16516722.23 | 0 | 4650020435 | لا | 0 |  | جاري | التكلفة المفوترة | 92 | 100 | 2010-04-16 | 2011-10-09 | 2023-03-15 | 2023-03-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | Failed | Yes
2200228336 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 2110484.025 | 105524.2012 | 2110484.025 | 2110484.025 | 2056001352 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2022-05-25 | 2023-03-21 | 2023-03-21 | 2023-03-21 | 2023-03-21 |  |  |  | 48.4957 | 27.4692 | منجز | No
2100103180 | جامعة الإمام عبدالرحمن بن فيصل | تشييد | ذات اولوية عالية وعاجلة | 69261011 | 3463050.55 | 24805722.17 | 24805722.17 | 2055002293 | لا | 0 | 180709036261 | ايقاف كلي | تكلفة العمل المنجز | 50 | 90 | 2014-04-08 | 2017-03-06 | 2022-12-29 | 2022-12-29 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 50.2005 | 26.3976 | Failed | No
2100083753 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية متوسطة | 7991216.61 | 399560.8305 | 7991216.61 | 7991216.61 | 1010076960 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-05-26 | 2017-01-18 | 2017-08-18 | 2017-08-18 | 2017-01-18 | [5 empty] | منجز | No
2100025546 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 17495650 | 874782.5 | 17495650 | 17495650 | 2050056172 | لا | 0 | 180901069724 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99.15 | 100 | 2018-10-29 | 2021-10-28 | 2021-08-03 | 2021-08-03 | 2021-10-28 |  | لا يوجد تأخير |  | 49.988 | 26.3906 | منجز | No
2100061762 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 12560651 | 628032.55 | 9905918.62 | 9905918.62 | 1123002388 | لا | 0 | 181109288076 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 97.5 | 100 | 2018-06-14 | 2020-11-16 | 2020-09-10 | 2020-09-10 | 2020-11-16 |  | ضعف كفاءة المقاول الفنية |  | 45.3525 | 25.8912 | منجز | No
2100017684 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية وعاجلة | 4885755 | 244287.75 | 4653100 | 4653100 | 1010016228 | لا | 0 | 190801022182 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-11-27 | 2021-05-13 | 2020-12-14 | 2020-12-14 |  | 2021-05-13 | لا يوجد تأخير |  | 44.4412 | 24.5406 | منجز | No
2200228340 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 270000 | 13500 | 270000 | 270000 | 1010094436 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2022-05-15 | 2022-08-13 | 2022-08-13 | 2022-08-13 | 2022-08-13 |  |  |  | 48.8755 | 25.9585 | منجز | No
2100042906 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية منخفضة | 9207294.84 | 460364.742 | 2513481.41 | 2513481.41 | 2050055733 | لا | 0 | 180809037950 | مسحوب | منهجية القيمة المكتسبة | 32.45 | 100 | 2013-07-07 | 2014-09-23 | 2023-03-11 | 2023-03-11 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 49.6145 | 27.007 | مسحوب | No
2200228266 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 657225 | 32861.25 | 467550 | 467550 | 2056001462 | لا | 0 |  | جاري | تكلفة العمل المنجز | 81 | 77 | 2022-07-06 | 2023-03-03 | 2023-03-03 | 2023-03-03 |  |  |  |  | 48.2846 | 26.7644 | منتظم | No
2100043540 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1376100 | 68805 | 1376100 | 0 | 1010246223 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2017-11-05 | 2019-07-01 | 2019-07-01 | 2019-07-01 | 2019-07-01 |  |  |  | 46.6768 | 24.7181 | منجز | Yes
2100070840 | وزارة الموارد البشرية والتنمية الإجتماعية | إشراف | ذات اولوية منخفضة | 3312000 | 165600 | 7509198.33 | 7509198.33 | 1010348048 | لا | 0 | 181109262353 | مسحوب | مدفوعات ساعات العمل | 82 | 100 | 2013-06-29 | 2016-05-27 | 2021-10-13 | 2021-10-13 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 50.0602 | 26.4614 | مسحوب | No
2100061353 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية وعاجلة | 52845998 | 2642299.9 | 47560547 | 44318597 | 1010014082 | نعم | 15215243 | 180901081829 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-06-16 | 2021-05-25 | 2022-06-30 | 2022-06-30 | 2021-05-25 |  | لا يوجد تأخير |  | 41.7456 | 27.5063 | منجز | No
2100054666 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 41756062.68 | 2087803.134 | 18097439.82 | 18097439.82 | 2050022550 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 43 | 100 | 2013-10-22 | 2015-04-15 | 2018-07-07 | 2018-07-07 |  |  | ضعف كفاءة المقاول الفنية |  | 46.8329 | 24.6678 | مسحوب | No
2100199194 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 10507040 | 525352 | 5008920 | 5008920 | 1010158780 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 60.41 | 64.36 | 2021-06-17 | 2022-12-17 | 2022-12-17 | 2022-12-17 |  |  |  |  | 46.7941 | 24.6529 | منتظم | No
2100107833 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 17037777.78 | 851888.889 | 1388412.65 | 0 | 4650020435 | لا | 0 |  | مسحوب | التكلفة المفوترة | 11 | 100 | 2013-02-25 | 2014-11-17 | 2024-01-15 | 2024-01-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | Yes
2100053071 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تصميم وتشييد | ذات اولوية عالية وعاجلة | 29626291.25 | 1481314.5625 | 23243499.612 | 23243499.612 | 1010140330 | لا | 0 | 180809059311 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2014-12-03 | 2016-11-30 | 2020-07-04 | 2020-07-04 | 2016-11-30 |  | لا يوجد تأخير |  | 49.5844 | 27.0813 | منجز | No
2100199990 | جامعة الملك سعود | تشييد | ذات اولوية متوسطة | 279531653.26 | 13976582.663 | 97291881.67 | 97291881.67 | 1010254468 | لا | 0 | 200309015199 | مسحوب | تكلفة العمل المنجز | 28 | 100 | 2012-08-25 | 2014-02-07 | 2014-02-07 | 2014-02-07 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6186 | 24.7308 | مسحوب | No
2200234625 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | دراسات هندسية | ذات اولوية عالية وعاجلة | 14037332.5 | 701866.625 | 0 | 0 | 2051047662 | لا | 0 |  | جاري | تكلفة العمل المنجز | 0 | 0 | 2022-10-04 | 2027-04-16 | 2027-10-12 | 2027-10-12 |  |  |  |  | 49.1918 | 27.4934 | خدمات عامة | No
2100016030 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية وعاجلة | 21613025 | 1080651.25 | 15671770.13 | 14745507.4 | 1010013226 | لا | 0 | 180709021273 | مسحوب | منهجية القيمة المكتسبة | 90 | 100 | 2014-12-14 | 2017-05-18 | 2022-08-31 | 2022-08-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 43.6378 | 26.4981 | مسحوب | No
2100067841 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 5996000 | 299800 | 2599992.9 | 2599992.9 | 4031058457 | لا | 0 |  | جاري | تكلفة العمل المنجز | 43.25 | 43.25 | 2015-09-06 | 2018-09-04 | 2021-09-04 | 2021-09-04 |  |  | ضعف كفاءة المقاول الفنية |  | 39.8255 | 21.3581 | متأخر | No
2100191940 | وزارة الصحة / جازان | تشييد | ذات اولوية عالية وعاجلة | 19655336.2 | 982766.81 | 19655336.2 | 0.01 | 4030145720 | لا | 0 | 210301180766 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2020-10-27 | 2021-05-31 | 2021-05-31 | 2021-05-31 | 2021-05-31 |  |  |  | 42.6255 | 16.9951 | منجز | No
2100074561 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 6485524.73 | 324276.2365 | 2571717.69 | 2571717.69 | 1010090099 | لا | 0 |  | مسحوب | التكلفة المفوترة | 50 | 100 | 2012-03-17 | 2014-08-20 | 2023-12-15 | 2023-12-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | No
2200228373 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 6990735 | 349536.75 | 6428900 | 6428900 | 2050018628 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2021-03-15 | 2022-12-13 | 2022-12-13 | 2022-12-13 | 2022-12-13 |  |  |  | 49.9667 | 26.3855 | منجز | No
2100086041 | وزارة التعليم | تشييد | لم تعد تحتاجها الجهة | 16731636 | 836581.8 | 1567191.21 | 1567191.21 | 1010142553 | لا | 0 |  | مسحوب | التكلفة المفوترة | 18 | 100 | 2014-12-11 | 2017-06-02 | 2019-08-28 | 2019-08-28 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | مسحوب | No
2200228465 | المؤسسة العامة للحبوب | تصميم وتشييد | ذات اولوية عالية | 1024075 | 51203.75 | 614445 | 1 | 4030147825 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 80 | 80 | 2022-07-24 | 2023-01-17 | 2023-01-17 | 2023-01-17 |  |  |  |  | 39.1867 | 21.4826 | منتظم | No
2100061180 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 268676853.57 | 13433842.6785 | 243587936.03 | 231073451.1 | 1010004249 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 94.85 | 100 | 2017-06-11 | 2019-06-11 | 2021-11-19 | 2021-11-19 | 2019-06-11 |  | لا يوجد تأخير |  | 50.2028 | 26.2461 | منجز | No
2100019880 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية وعاجلة | 17955000 | 897750 | 15976634.73 | 15976634.73 | 2050003475 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 98.5 | 100 | 2017-11-23 | 2019-11-02 | 2019-11-02 | 2019-11-02 | 2019-11-02 |  | لا يوجد تأخير |  | 49.6569 | 25.3613 | منجز | No
2100035114 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 572260 | 28613 | 286500 | 286500 | 3550027826 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 50 | 50 | 2013-06-09 | 2014-02-04 | 2020-04-05 | 2020-04-05 |  |  | اخرى |  | 36.5566 | 28.4015 | مسحوب | No
2200228395 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 18392000 | 919600 | 18392000 | 18392000 | 2050018628 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-11-18 | 2022-05-03 | 2022-05-03 | 2022-05-03 | 2022-05-03 |  |  |  | 50.0089 | 26.5586 | منجز | No
2200214605 | جامعة الملك سعود | تشطيب | ذات اولوية عالية | 330708.95 | 16535.4475 | 330704.12 | 330704.12 | 1010351290 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2022-01-24 | 2022-03-11 | 2022-06-30 | 2022-06-30 | 2022-03-11 |  |  |  | 46.6237 | 24.7252 | منجز | No
2100026482 | أمانة / الجوف | تشييد | ذات اولوية عالية وعاجلة | 17400000 | 870000 | 13947251.08 | 13947251.08 | 3450009076 | لا | 0 | 190401091807 | جاري | الكميات التي تم تركيبها | 91 | 100 | 2019-10-10 | 2021-09-30 | 2023-02-15 | 2023-02-15 |  |  |  |  | 37.3796 | 31.325 | متأخر | No
2100097694 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 32944641 | 1647232.05 | 28110634.53 | 28110634.53 | 1010026934 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 96.1 | 100 | 2018-01-28 | 2019-07-28 | 2020-12-26 | 2020-12-26 |  | 2019-07-28 | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100049475 | أمانة / جازان | تشييد | ذات اولوية عالية | 5541911 | 277095.55 | 2262233.43 | 2262233.43 | 5907007322 | لا | 0 | 180701033185 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-09-18 | 2020-03-11 | 2021-06-03 | 2021-06-03 | 2020-03-11 |  | ضعف كفاءة المقاول الفنية |  | 42.9251 | 16.6156 | منجز | No
2200228406 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 4139520 | 206976 | 3158214 | 3158214 | 1010137467 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-08-12 | 2021-10-29 | 2021-10-29 | 2021-10-29 | 2021-10-29 |  |  |  | 46.9781 | 27.2349 | منجز | No
2100034451 | أمانة / جازان | تشييد | ذات اولوية عالية | 2997000 | 149850 | 2738635 | 2738635 | 5901015523 | لا | 0 | 191001112790 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-05-28 | 2020-05-28 | 2021-09-27 | 2021-09-27 | 2020-05-28 |  | ضعف كفاءة المقاول الفنية |  | 42.9369 | 16.7082 | منجز | No
2100075552 | أمانة / تبوك | تشييد | ذات اولوية عالية | 1697666.25 | 84883.3125 | 1697666.25 | 0 | 3550123598 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-09-23 | 2020-09-17 | 2021-04-30 | 2021-04-30 | 2020-09-17 |  | ضعف كفاءة المقاول الفنية |  | 36.5424 | 28.3913 | منجز | Yes
2200228476 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 14038231 | 701911.55 | 14832095.544 | 13656207.72 | 2050018628 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 95 | 100 | 2020-05-03 | 2021-11-02 | 2022-08-15 | 2022-08-15 | 2021-11-02 |  |  |  | 50.0888 | 26.4207 | منجز | No
2200234651 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 117337475.65 | 5866873.7825 | 0 | 0 | 2050004983 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 0 | 0 |  | 2024-10-17 | 2024-10-17 | 2025-04-16 |  |  |  |  | 49.0257 | 27.4211 | منتظم | No
2100091733 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 19770520 | 988526 | 14564091.02 | 14337170.06 | 2252010279 | لا | 0 | 181001131761 | جاري | منهجية القيمة المكتسبة | 76.87 | 99.95 | 2018-12-13 | 2021-11-14 | 2022-12-13 | 2022-12-13 |  |  | اخرى |  | 45.9493 | 28.3684 | متأخر | No
2100026261 | وزارة الصحة / جازان | تشييد | ذات اولوية عالية | 13056168 | 652808.4 | 6450000 | 2488055.85 | 1010215470 | نعم | 6450000 | 181009134962 | مسحوب | تكلفة العمل المنجز | 75 | 100 | 2016-08-06 | 2018-08-06 | 2022-04-30 | 2022-04-30 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.8112 | 17.0963 | مسحوب | No
2100195646 | جامعة أم القرى | تشييد | ذات اولوية متوسطة | 4159533 | 207976.65 | 1034553.28 | 1034553.28 | 4030215478 | لا | 0 | 200201130292 | جاري | تكلفة العمل المنجز | 27 | 100 | 2020-02-16 | 2020-08-13 | 2023-06-30 | 2023-06-30 |  |  |  | مخطط لفسخ العقد | 39.9453 | 21.3282 | Failed | No
2100028534 | وزارة الصحة / ديوان الوزارة | تشييد | ذات اولوية عالية | 24405826 | 1220291.3 | 24405826 | 22001876 | 1010220966 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 100 | 100 | 2018-07-17 | 2020-07-16 | 2022-02-28 | 2022-02-28 |  |  | أوامر تغيير |  | 42.9405 | 16.6064 | Failed | No
2100096876 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 14832201 | 741610.05 | 4379014.82 | 4379014.82 | 1010230019 | لا | 0 | 181001179715 | مسحوب | منهجية القيمة المكتسبة | 40.32 | 100 | 2018-12-30 | 2020-12-31 | 2022-06-12 | 2022-06-12 |  |  | لا يوجد تأخير |  | 49.65 | 25.4411 | مسحوب | No
2100191645 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 9174330 | 458716.5 | 7504688.46 | 6302201.38 | 1010070634 | لا | 0 |  | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 99.52 | 82.31 | 2020-09-21 | 2022-09-21 | 2022-10-30 | 2022-10-30 |  |  |  |  | 46.732 | 24.602 | منتظم | No
2200225982 | وزارة الداخلية / المديرية العامة لحرس الحدود | تشييد | ذات اولوية عالية | 2497300 | 124865 | 743200 | 743200 | 4030168691 | لا | 0 | 220601242049 | جاري | تكلفة العمل المنجز | 70 | 88 | 2022-05-11 | 2023-02-11 | 2023-02-11 | 2023-02-11 |  |  |  |  | 41.0787 | 19.1281 | متأخر | No
2100066662 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 273000 | 13650 | 59850 | 59850 | 2066002549 | لا | 0 | 191101088264 | فسخ العقد | تكلفة العمل المنجز | 21 | 100 | 2019-09-15 | 2020-03-13 | 2020-12-21 | 2020-12-21 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5885 | 25.382 | مسحوب | No
2100093030 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 3280955 | 164047.75 | 2678955 | 2678955 | 2511105361 | لا | 0 |  | جاري | اخرى | 97 | 100 | 2020-01-01 | 2021-07-01 | 2021-07-01 | 2021-07-01 | [6 empty] | Failed | No
2100085540 | أمانة / الرياض | دراسات هندسية | ذات اولوية متوسطة | 23972550 | 1198627.5 | 21102533 | 21102533 | 1010326466 | لا | 0 |  | جاري | التكلفة المفوترة | 93 | 100 | 2018-12-20 | 2021-03-03 | 2022-09-15 | 2022-09-15 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  |  |  | خدمات عامة | No
2100040983 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 104087489 | 5204374.45 | 19774129.44 | 9083391.87 | 2050022550 | لا | 0 | 210109014785 | مسحوب | منهجية القيمة المكتسبة | 9.704 | 100 | 2013-07-02 | 2017-05-19 | 2025-12-19 | 2025-12-19 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 44.4236 | 24.5207 | مسحوب | No
2100191741 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 4900000 | 245000 | 4900000 | 4900000 | 1010257051 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2020-05-19 | 2021-01-19 | 2020-12-22 | 2020-12-22 |  | 2021-01-19 |  |  | 47.5403 | 25.0981 | منجز | No
2100040762 | وزارة الصحة / جازان | تشييد | ذات اولوية عالية | 8794688.32 | 439734.416 | 6109378 | 1805541 | 4030145720 | لا | 0 | 191001026270 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-04-04 | 2021-04-04 | 2022-01-04 | 2022-01-04 | 2021-04-04 |  |  |  | 42.9405 | 16.6064 | منجز | No
2200228432 | أمانة / المنطقة الشرقية | أخرى | ذات اولوية منخفضة | 6930320 | 346516 | 4551318 | 0 | 2050020378 | لا | 0 |  | جاري | التكلفة المفوترة | 66 | 73 | 2020-11-05 | 2023-11-05 | 2023-11-05 | 2023-11-05 |  |  |  |  | 50.0888 | 26.4207 | خدمات عامة | Yes
2100055230 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 51760897.8 | 2588044.89 | 51759708.72 | 47927292.22 | 1118000259 | لا | 0 | 180809052477 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2013-09-09 | 2016-08-06 | 2020-11-11 | 2020-11-11 |  | 2016-08-06 | تأخرصرف المستحقات المالية |  | 44.4412 | 24.5406 | منجز | No
2200221023 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 9900000 | 495000 | 2785730 | 2785730 | 5850022870 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 61.31 | 61.7 | 2022-02-20 | 2022-08-21 | 2022-08-21 | 2022-08-21 |  |  |  |  | 39.8769 | 21.4063 | منتظم | No
2100022374 | وزارة الصحة / الطائف | تشييد | ذات اولوية عالية وعاجلة | 11039018 | 551950.9 | 2545304.38 | 2545304.38 | 1131020503 | لا | 0 | 200209119086 | جاري | تكلفة العمل المنجز | 65 | 100 | 2015-04-07 | 2016-09-19 | 2022-02-01 | 2022-02-01 |  |  | تأخرصرف المستحقات المالية |  | 41.3548 | 22.6242 | Failed | No
2100028630 | أمانة / العاصمة المقدسة | ترميم | ذات اولوية متوسطة | 2737927 | 136896.35 | 2607550 | 2607550 | 4650047424 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2019-06-05 | 2020-04-24 | 2020-05-30 | 2020-05-30 |  | 2020-04-24 | اخرى |  | 39.1677 | 21.5007 | منجز | No
2100015713 | شركة المياه الوطنية / منطقة الرياض | إشراف | ذات اولوية عالية | 12592800 | 629640 | 12534419.34 | 12534419.34 | 1131035992 | لا | 0 |  | منجز – استلام نهائي | التكلفة المفوترة | 99.53 | 100 | 2015-10-18 | 2018-10-17 | 2020-07-15 | 2020-07-15 |  | 2018-10-17 | لا يوجد تأخير |  | 46.794 | 24.6531 | منجز | No
2100091593 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 23230171.05 | 1161508.5525 | 22719489.42 | 22719489.42 | 1010219753 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-05-06 | 2020-11-07 | 2022-07-30 | 2022-07-30 | 2020-11-07 |  | لا يوجد تأخير |  | 46.3601 | 24.4054 | منجز | No
2100006812 | وزارة التعليم | تشييد | ذات اولوية عالية | 14694896 | 734744.8 | 12483594.6 | 0 | 1010060469 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2017-10-04 | 2019-09-25 | 2021-09-21 | 2021-09-21 | 2019-09-25 |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | منجز | Yes
2200225993 | شركة المياه الوطنية / منطقة حائل | تصميم | لم تعد تحتاجها الجهة | 4987500 | 249375 | 4275000 | 4275000 | 1010348048 | لا | 0 |  | جاري | التكلفة المفوترة | 85.71 | 100 | 2018-12-26 | 2019-07-26 | 2023-05-01 | 2023-05-01 |  |  |  |  | 41.6576 | 27.5162 | Failed | No
2100105000 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية | 17129500 | 856475 | 16045881.45 | 16045881.45 | 4030032844 | لا | 0 | 180301001401 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 91.8 | 100 | 2018-08-09 | 2020-07-18 | 2021-11-02 | 2021-11-02 | 2020-07-18 |  | اخرى |  | 43.9553 | 26.3508 | منجز | No
2100079623 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 168343835 | 8417191.75 | 112638495.77 | 110010320.9 | 2060010281 | لا | 0 | 180809053798 | جاري | منهجية القيمة المكتسبة | 74.7 | 79.14 | 2018-02-21 | 2021-02-21 | 2023-06-30 | 2023-06-30 |  |  | لا يوجد تأخير |  | 40.0297 | 29.233 | منتظم | No
2100040471 | وزارة الصحة / الطائف | تشييد | ذات اولوية عالية وعاجلة | 2991460.5 | 149573.025 | 0 | 0 | 4030185377 | لا | 0 | 190901207755 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-02-23 | 2020-05-22 | 2021-05-22 | 2021-05-22 | 2020-05-22 |  | تأخرصرف المستحقات المالية |  | 40.3734 | 21.2678 | منجز | No
2200234721 | جامعة القصيم | تشييد | ذات اولوية عالية وعاجلة | 1200738 | 60036.9 | 721805 | 720805 | 2050030952 | لا | 0 |  | جاري | تكلفة العمل المنجز | 93 | 100 | 2022-03-30 | 2022-07-28 | 2022-11-30 | 2022-11-30 |  |  |  |  | 44.0791 | 26.1137 | Failed | No
2200234710 | أمانة / الجوف | تشييد | ذات اولوية عالية | 1861850 | 93092.5 | 1499997.9 | 1499997.9 | 1134000444 | لا | 0 | 220239488048 | جاري | تكلفة العمل المنجز | 92 | 67 | 2022-07-24 | 2023-03-21 | 2023-03-21 | 2023-03-21 |  |  |  |  | 40.3717 | 30.1254 | منتظم | No
2100008536 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 1541160 | 77058 | 0 | 0 | 2050041707 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-07-19 | 2020-06-17 | 2020-06-16 | 2020-06-16 | 2020-06-17 |  | لا يوجد تأخير |  | 48.5359 | 27.448 | منجز | No
2100105501 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية وعاجلة | 707110430.15 | 35355521.5075 | 496640730.16 | 496640730.16 | 1010004739 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 99.06 | 100 | 2014-03-12 | 2016-03-01 | 2022-12-31 | 2022-12-31 |  |  | تأخرصرف المستحقات المالية | أخرى | 24.9863 | 46.9306 | منتظم | No
2100072516 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 8950987.5 | 447549.375 | 0 | 0 | 2050027937 | لا | 0 | 190909071535 | مسحوب | تكلفة العمل المنجز | 6 | 100 | 2019-06-09 | 2021-02-01 | 2021-01-17 | 2021-01-17 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 49.5505 | 25.3995 | مسحوب | No
2100056210 | وزارة الصحة / الرياض | تشييد | ذات اولوية متوسطة | 2620620 | 131031 | 2214372 | 2214372 | 1010255931 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 95 | 2015-12-05 | 2016-09-04 | 2018-04-10 | 2018-04-10 | 2016-09-04 |  | تأخرصرف المستحقات المالية |  | 46.6775 | 24.6976 | منجز | No
2200234732 | جامعة القصيم | تشييد | ذات اولوية عالية وعاجلة | 490000 | 24500 | 0 | 0 | 3450009369 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2022-09-25 | 2022-11-24 | 2022-11-24 | 2022-11-24 | 2022-11-24 |  |  |  | 43.5387 | 25.8774 | منجز | No
2100041930 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية وعاجلة | 469500000 | 23475000 | 114510704.87 | 75473873.38 | 1010271502 | لا | 0 |  | مسحوب | منهجية القيمة المكتسبة | 35.81 | 100 | 2015-06-21 | 2017-02-21 | 2024-09-27 | 2024-09-27 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 46.7098 | 24.6275 | مسحوب | No
2200228572 | شركة المياه الوطنية | دراسات هندسية | ذات اولوية عالية | 4299000 | 214950 | 4299000 | 4299000 | 1010407685 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-06-08 | 2021-12-09 | 2021-12-09 | 2021-12-09 | 2021-12-09 |  |  |  | 46.6836 | 24.6876 | منجز | No
2100040456 | وزارة الصحة / الطائف | تشييد | ذات اولوية عالية وعاجلة | 61589670 | 3079483.5 | 53611213.05 | 53611213.05 | 1010054305 | لا | 0 | 181001133847 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 99 | 100 | 2018-02-20 | 2018-10-15 | 2019-09-02 | 2019-09-02 | 2018-10-15 |  | تأخرصرف المستحقات المالية |  | 40.3738 | 21.2678 | منجز | No
2100089445 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية | 2004190168.89 | 100209508.4445 | 3078443.7 | 3078443.7 | 1010609431 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 0.16 | 52.81 | 2015-01-08 | 2018-12-17 | 2026-12-31 | 2026-12-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 49.9313 | 26.3156 | Failed | No
2100082471 | أمانة / الأحساء | تشييد | ذات اولوية عالية وعاجلة | 15200291.992 | 760014.5996 | 11109211 | 10051163 | 4030032844 | لا | 0 | 190401086767 | جاري | تكلفة العمل المنجز | 80 | 85 | 2019-06-15 | 2020-12-06 | 2022-12-09 | 2022-12-09 |  |  |  |  | 49.573 | 25.4246 | منتظم | No
2200213146 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية وعاجلة | 4742220.4 | 237111.02 | 3674552.54 | 3674552.54 | 1010149483 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 90.35 | 100 | 2021-10-10 | 2022-01-10 | 2022-06-30 | 2022-06-30 | 2022-01-10 |  |  |  | 47.3099 | 24.0529 | منجز | No
2100061025 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 124500000 | 6225000 | 99600000 | 97351568 | 2251029078 | لا | 0 | 190301062442 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 99.52 | 98.15 | 2019-04-29 | 2021-10-28 | 2023-02-14 | 2023-02-14 |  |  |  |  | 38.3155 | 23.9301 | منتظم | No
2100021534 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية وعاجلة | 955500 | 47775 | 920195.5 | 920195.5 | 1010158780 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 96.31 | 100 | 2020-04-15 | 2020-07-15 | 2021-01-25 | 2021-01-25 |  | 2020-07-15 | لا يوجد تأخير |  | 47.5412 | 25.1013 | منجز | No
2100106621 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 37451797.75 | 1872589.8875 | 37347421.6 | 37347421.6 | 2050002732 | لا | 0 | 180709031651 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-01-10 | 2019-06-15 | 2021-04-18 | 2021-04-18 | 2019-06-15 |  | لا يوجد تأخير |  | 50.0104 | 26.464 | منجز | No
2100055285 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 941000 | 47050 | 835979.05 | 835979.05 | 1010296759 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-10-14 | 2019-10-14 | 2019-10-14 | 2019-10-14 |  | 2019-10-14 | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100063781 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات الجوية | دراسات هندسية | ذات اولوية عالية | 32627700 | 1631385 | 32627700 | 32627700 | 1010459572 | لا | 0 | 200509015223 | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2020-03-04 | 2020-09-05 | 2020-10-29 | 2020-10-29 | 2020-09-05 |  | لا يوجد تأخير |  | 40.1034 | 29.8797 | منجز | No
2200228594 | شركة المياه الوطنية | دراسات هندسية | ذات اولوية عالية | 3745120 | 187256 | 2996100 | 1872562.5 | 1010348048 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2020-04-21 | 2021-11-18 | 2021-11-18 | 2021-11-18 | 2021-11-18 |  |  |  | 46.6836 | 24.6876 | منجز | No
2100062182 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 19691874 | 984593.7 | 19636132.68 | 19636132.68 | 2050003475 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-01-01 | 2020-01-01 | 2019-11-24 | 2019-11-24 |  | 2020-01-01 | لا يوجد تأخير |  | 46.8214 | 24.7686 | منجز | No
2100005386 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 74102600 | 3705130 | 69246961.3 | 69246961.3 | 1010074413 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 94.95 | 100 | 2015-03-29 | 2017-03-29 | 2019-12-03 | 2019-12-03 |  | 2017-03-29 | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2200210431 | وزارة الصحة / بيشة | ترميم | ذات اولوية عالية | 14891150 | 744557.5 | 2500467.63 | 1456160.3 | 1010230446 | لا | 0 | 200201085975 | جاري | تكلفة العمل المنجز | 28.3 | 100 | 2020-01-30 | 2022-07-20 | 2022-12-06 | 2022-12-06 |  |  |  |  | 42.6132 | 20.0345 | Failed | No
2100101791 | وزارة الصحة / الطائف | تشييد | ذات اولوية عالية وعاجلة | 1207725 | 60386.25 | 599040 | 0 | 4035000994 | لا | 0 | 190801097554 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 95 | 100 | 2019-09-14 | 2020-01-14 | 2022-05-31 | 2022-05-31 | 2020-01-14 |  | تأخرصرف المستحقات المالية |  | 40.8428 | 20.7416 | منجز | Yes
2100043455 | وزارة الحرس الوطني / الشؤون الصحية | تشييد | ذات اولوية عالية | 50862205.54 | 2543110.277 | 18607011.4 | 8619974.4 | 4030166491 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 47 | 100 | 2019-08-25 | 2021-12-23 | 2023-07-31 | 2023-07-31 |  |  | تصاريح أعمال التنفيذ |  | 39.3625 | 21.4223 | Failed | No
2100022142 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 7362341.75 | 368117.0875 | 1611393.75 | 0 | 4030288443 | لا | 0 |  | مسحوب | التكلفة المفوترة | 35 | 100 | 2015-04-08 | 2017-03-29 | 2023-12-15 | 2023-12-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | Yes
2200226004 | وزارة الداخلية / المديرية العامة لحرس الحدود | ترميم | ذات اولوية عالية | 3261980 | 163099 | 2174788 | 2174788 | 4030168691 | لا | 0 |  | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 89 | 100 | 2022-04-18 | 2022-10-18 | 2022-12-03 | 2022-12-03 |  |  |  |  | 39.1925 | 21.4858 | متأخر | No
2100031426 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 2444680 | 122234 | 2189960 | 2189960 | 4650040767 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 89 | 100 | 2013-01-28 | 2014-01-16 | 2014-01-16 | 2014-01-16 |  |  | ضعف كفاءة المقاول الفنية |  | 39.5746 | 24.5223 | مسحوب | No
2100199931 | وزارة الصحة / الباحة | ترميم | ذات اولوية متوسطة | 3916230 | 195811.5 | 1556606.08 | 1556606.08 | 5810014239 | لا | 0 | 191001075541 | جاري | الكميات التي تم تركيبها | 80 | 100 | 2019-11-10 | 2022-02-23 | 2023-03-15 | 2023-03-15 |  |  |  |  | 41.4387 | 20.0634 | Failed | No
2100002446 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية منخفضة | 5224050 | 261202.5 | 4697914.78 | 4530500.33 | 3550025982 | لا | 0 | 180709033813 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99.5 | 96.89 | 2017-11-19 | 2020-10-18 | 2020-05-10 | 2020-05-10 | 2020-10-18 |  | لا يوجد تأخير |  | 36.5775 | 28.3528 | منجز | No
2100087570 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 14201025 | 710051.25 | 14054478.58 | 14054478.58 | 1010311911 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 99.88 | 100 | 2018-12-25 | 2020-06-25 | 2020-08-04 | 2020-08-04 |  | 2020-06-25 | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100199846 | الجامعة الاسلامية بالمدينة المنورة | توريد وتركيب | ذات اولوية عالية | 500388 | 25019.4 | 394365.32 | 394365.32 | 1010299555 | لا | 0 | 191001093944 | جاري | الكميات التي تم تركيبها | 100 | 100 | 2020-02-20 | 2020-07-19 | 2022-10-31 | 2022-10-31 |  |  |  |  | 39.5654 | 24.4807 | Failed | No
2100061412 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 15000000 | 750000 | 15000000 | 14166708 | 2251029920 | لا | 0 | 180809040847 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2017-12-13 | 2019-06-06 | 2021-08-31 | 2021-08-31 | 2019-06-06 |  | اخرى |  | 49.5545 | 25.6632 | منجز | No
2100094006 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 15270057 | 763502.85 | 13703104 | 13703104 | 2251027860 | لا | 0 | 180709020348 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-12-04 | 2016-11-23 | 2022-11-30 | 2022-11-30 | 2016-11-23 |  | ضعف كفاءة المقاول الفنية |  | 49.7172 | 25.417 | منجز | No
2100088852 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 3053266.94 | 152663.347 | 1713758.64 | 1713758.64 | 1010164501 | لا | 0 |  | مسحوب | التكلفة المفوترة | 56 | 100 | 2015-02-24 | 2016-02-19 | 2021-04-02 | 2021-04-02 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 46.7098 | 24.5895 | مسحوب | No
2100048252 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية متوسطة | 41891496 | 2094574.8 | 5935057.2 | 5935057.2 | 1010260620 | لا | 0 | 180909072579 | مسحوب | منهجية القيمة المكتسبة | 24.7 | 100 | 2013-08-22 | 2015-02-04 | 2023-08-25 | 2023-08-25 |  |  | ضعف كفاءة المقاول الفنية |  | 36.4674 | 28.4823 | مسحوب | No
2100037645 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 4956475.24 | 247823.762 | 4808962.08 | 4671377.16 | 1010010506 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-05-05 | 2019-11-01 | 2020-03-09 | 2020-03-09 | 2019-11-01 | [5 empty] | منجز | No
2200228631 | الجمارك السعودية | تشييد | ذات اولوية عالية | 10418861.11 | 520943.0555 | 3568294.42 | 3568294.42 | 1010132551 | لا | 0 |  | جاري | تكلفة العمل المنجز | 51 | 100 | 2022-03-20 | 2022-12-03 | 2023-03-30 | 2023-03-30 |  |  |  |  | 55.434 | 22.1606 | Failed | No
2100088723 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 11174734.51 | 558736.7255 | 9040567.07 | 9040567.07 | 1010081451 | لا | 0 |  | جاري | التكلفة المفوترة | 88 | 100 | 2013-11-10 | 2015-10-31 | 2022-01-25 | 2022-01-25 |  |  | ضعف كفاءة المقاول الفنية |  | 46.5746 | 24.6261 | Failed | No
2100096036 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية وعاجلة | 17890000 | 894500 | 12164820.87 | 12164820.87 | 2055006347 | لا | 0 | 180809053397 | مسحوب | منهجية القيمة المكتسبة | 79.5 | 100 | 2018-03-03 | 2020-03-03 | 2022-09-07 | 2022-09-07 |  |  | لا يوجد تأخير |  | 50.1201 | 26.1534 | مسحوب | No
2100002155 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 22320422 | 1116021.1 | 2375535.72 | 2375535.72 | 2050011871 | لا | 0 | 180809053942 | مسحوب | منهجية القيمة المكتسبة | 21.3 | 100 | 2017-12-20 | 2020-06-20 | 2022-11-06 | 2022-11-06 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 50.0648 | 26.5856 | مسحوب | No
2100064330 | الهيئة الملكية للجبيل وينبع / مدينة جازان للصناعات الأساسية والتحويلية | توريد وتركيب | ذات اولوية عالية | 20616750 | 1030837.5 | 13601524.9 | 12027756.8 | 2050004110 | لا | 0 | 200509021421 | جاري | تكلفة العمل المنجز | 71.16 | 79.46 | 2017-11-22 | 2022-11-21 | 2023-04-17 | 2023-04-17 |  |  | تأخرصرف المستحقات المالية |  | 42.3739 | 17.3181 | متأخر | No
2200226074 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية وعاجلة | 5863480 | 293174 | 0 | 0 | 1010227442 | لا | 0 |  | جاري | تكلفة العمل المنجز | 16.1 | 1.6 | 2022-05-05 | 2023-01-05 | 2023-01-05 | 2023-01-05 |  |  |  |  | 46.6126 | 24.6587 | منتظم | No
2100059511 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 79282538 | 3964126.9 | 63174055.79 | 63174055.79 | 1010317283 | لا | 0 | 180709023942 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 96.46 | 100 | 2015-02-22 | 2019-01-09 | 2020-08-18 | 2020-08-18 | 2019-01-09 |  | لا يوجد تأخير |  | 46.8944 | 23.5058 | منجز | No
2100002623 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 5620574.3 | 281028.715 | 0 | 0 | 1010121536 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0 | 100 | 2007-11-23 | 2009-11-13 | 2023-06-12 | 2023-06-12 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.5429 | 16.8808 | مسحوب | No
2200234861 | جامعة الملك خالد | تشييد | ذات اولوية عالية وعاجلة | 85000005.2 | 4250000.26 | 9607150 | 9607150 | 1010434398 | لا | 0 |  | جاري | تكلفة العمل المنجز | 9.9 | 9.9 | 2022-07-17 | 2025-01-02 | 2025-01-02 | 2025-01-02 |  |  |  |  | 42.7162 | 18.0913 | منتظم | No
2100105195 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 39107344 | 1955367.2 | 27557372.51 | 27557372.51 | 1010090968 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 96.89 | 100 | 2018-01-01 | 2020-07-01 | 2020-06-29 | 2020-06-29 |  | 2020-07-01 | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100010216 | وزارة النقل والخدمات اللوجستية / منطقة القصيم | تشييد | ذات اولوية متوسطة | 150866048.5 | 7543302.425 | 135779442.82 | 135779442.82 | 1010132469 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2009-10-31 | 2012-04-03 | 2022-10-15 | 2022-10-15 | 2012-04-03 |  |  |  | 43.9306 | 26.2366 | منجز | No
2100002343 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 6867077.64 | 343353.882 | 6724299.72 | 6724299.72 | 4030170755 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-07-24 | 2020-01-20 | 2020-01-20 | 2020-01-20 | 2020-01-20 | [5 empty] | منجز | No
2200226026 | وزارة الداخلية / المديرية العامة لحرس الحدود | تشييد | ذات اولوية عالية | 1296372 | 64818.6 | 482091.5 | 482091.5 | 5855340104 | لا | 0 | 220401115098 | جاري | تكلفة العمل المنجز | 65 | 73 | 2022-04-17 | 2023-04-17 | 2023-04-17 | 2023-04-17 |  |  |  |  | 42.8638 | 19.0969 | متأخر | No
2100088933 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 10960319.76 | 548015.988 | 9486152.04 | 9486152.04 | 1010081451 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 98 | 100 | 2013-12-19 | 2015-12-09 | 2021-10-15 | 2021-10-15 | 2015-12-09 |  | ضعف كفاءة المقاول الفنية |  | 46.5746 | 24.6261 | منجز | No
2200234894 | جامعة الملك خالد | تشييد | ذات اولوية عالية وعاجلة | 59856486.85 | 2992824.3425 | 0 | 0 | 4031038849 | لا | 0 |  | جاري | تكلفة العمل المنجز | 0 | 0 | 2022-09-06 | 2025-02-08 | 2025-02-08 | 2025-02-08 |  |  |  |  | 42.7329 | 18.0749 | منتظم | No
2100094544 | هيئة تطوير بوابة الدرعية | تشييد | ذات اولوية متوسطة | 945787 | 47289.35 | 633678 | 633678 | 1010348048 | لا | 0 |  | جاري | اخرى | 67 | 67 | 2019-11-27 | 2020-05-25 | 2021-02-28 | 2021-02-28 | [6 empty] | Failed | No
2100040154 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 58800000 | 2940000 | 43604837.77 | 37560962.71 | 1010010506 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 84.51 | 100 | 2013-01-01 | 2016-01-01 | 2019-12-16 | 2019-12-16 |  | 2016-01-01 | لا يوجد تأخير |  | 46.7693 | 24.8236 | منجز | No
2100019725 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية وعاجلة | 8498490 | 424924.5 | 5749602.42 | 5749602.42 | 1010147422 | لا | 0 | 181201454563 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 95 | 100 | 2019-02-24 | 2021-02-25 | 2022-02-28 | 2022-02-28 | 2021-02-25 |  | لا يوجد تأخير |  | 49.9925 | 26.5913 | منجز | No
2100064105 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 8424558 | 421227.9 | 2416472.88 | 1855946.64 | 4030052981 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 19 | 100 | 2014-04-01 | 2016-03-21 | 2023-12-29 | 2023-12-29 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.5429 | 16.8808 | مسحوب | No
2100105243 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 7148665 | 357433.25 | 7052262.05 | 7052262.05 | 2050056172 | لا | 0 | 181201400025 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-03-03 | 2020-09-03 | 2020-08-31 | 2020-08-31 | 2020-09-03 |  | لا يوجد تأخير |  | 49.8036 | 26.8454 | منجز | No
2100107214 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 18796829.22 | 939841.461 | 14441776.74 | 14441776.74 | 2251012445 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2016-12-15 | 2019-03-05 | 2020-01-29 | 2020-01-29 | 2019-03-05 |  |  |  | 49.5604 | 25.3897 | منجز | No
2100027075 | أمانة / الرياض | تشييد | ذات اولوية عالية | 6501600 | 325080 | 6501600 | 0 | 1113000219 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-02-01 | 2018-09-10 | 2018-09-10 | 2018-09-10 | 2018-09-10 |  |  |  | 45.5263 | 25.2931 | منجز | Yes
2100106131 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية وعاجلة | 848335673.12 | 42416783.656 | 483420471.78 | 476843141.11 | 1010152417 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 90.27 | 100 | 2014-11-02 | 2016-10-22 | 2023-06-29 | 2023-06-29 |  |  | تأخرصرف المستحقات المالية | أخرى | 24.7843 | 46.8591 | متأخر | No
2100022724 | وزارة الداخلية / ديوان وزارة الداخلية | تصميم وتشييد | ذات اولوية عالية وعاجلة | 11500000000 | 575000000 | 7463413200.82 | 7456162180.82 | 1010081126 | لا | 0 |  | ايقاف كلي | منهجية القيمة المكتسبة | 58.92 | 100 | 2012-05-19 | 2015-05-18 | 2022-09-25 | 2022-09-25 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  |  |  | Failed | No
2100080091 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 14622590 | 731129.5 | 13158430 | 13158430 | 4030087384 | لا | 0 | 180909066895 | جاري | منهجية القيمة المكتسبة | 99.94 | 99.94 | 2017-08-16 | 2019-07-27 | 2022-03-31 | 2022-03-31 |  |  | لا يوجد تأخير |  | 48.4939 | 28.4386 | Failed | No
2200226030 | وزارة الداخلية / المديرية العامة لحرس الحدود | تشييد | ذات اولوية عالية | 264500 | 13225 | 0 | 0 | 1010230481 | لا | 0 | 220701080357 | مسحوب | تكلفة العمل المنجز | 1 | 95 | 2022-06-23 | 2022-12-17 | 2022-12-17 | 2022-12-17 |  |  |  |  | 44.2289 | 17.5656 | مسحوب | No
2100078794 | وزارة الموارد البشرية والتنمية الإجتماعية | إشراف | ذات اولوية منخفضة | 934491.6 | 46724.58 | 1441584 | 1441584 | 1010440712 | لا | 0 | 190501069520 | مسحوب | الكميات التي تم تركيبها | 39 | 100 | 2019-01-10 | 2020-07-03 | 2021-12-31 | 2021-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 43.9921 | 26.0802 | مسحوب | No
2100103202 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 18891448.48 | 944572.424 | 8777321.53 | 8777321.53 | 2050023659 | لا | 0 | 180809050332 | مسحوب | منهجية القيمة المكتسبة | 80.6 | 100 | 2009-05-09 | 2012-04-06 | 2022-12-08 | 2022-12-08 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 50.0083 | 26.5645 | مسحوب | No
2100007991 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية وعاجلة | 94999989 | 4749999.45 | 65057660.54 | 49747144.54 | 1131014852 | لا | 0 | 200301078375 | ايقاف جزئي | منهجية القيمة المكتسبة | 70.11 | 63.61 | 2020-06-24 | 2023-05-23 | 2023-05-22 | 2023-05-22 |  |  | لا يوجد تأخير |  | 38.1237 | 24.1257 | منتظم | No
2200226085 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية وعاجلة | 94372880 | 4718644 | 0 | 0 | 2050007224 | لا | 0 |  | جاري | تكلفة العمل المنجز | 1e-15 | 1e-15 | 2022-06-15 | 2024-06-15 | 2024-06-15 | 2024-06-15 |  |  |  |  | 46.5219 | 24.8319 | منتظم | No
2100205030 | وزارة الصحة / تجمع الشرقية | ترميم | ذات اولوية عالية | 1733599.8 | 86679.99 | 964725.52 | 964725.52 | 2050069840 | لا | 0 | 201001199233 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2021-01-24 | 2021-07-24 | 2021-12-28 | 2021-12-28 | 2021-07-24 |  |  |  | 49.9982 | 26.5765 | منجز | No
2100189781 | الهيئة الملكية لمحافظة العلا | تصميم وتشييد | ذات اولوية عالية وعاجلة | 144616254.71 | 7230812.7355 | 101231378.3 | 101231378.3 | 2051008235 | لا | 0 |  | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 100 | 100 | 2020-07-01 | 2022-08-31 | 2023-02-28 | 2023-02-28 |  |  |  |  | 37.8687 | 26.7383 | متأخر | No
2200226041 | وزارة الداخلية / المديرية العامة لحرس الحدود | ترميم | ذات اولوية عالية | 2678091.25 | 133904.5625 | 403916.8 | 403916.8 | 5855340104 | لا | 0 |  | جاري | تكلفة العمل المنجز | 50 | 72 | 2022-04-20 | 2023-04-20 | 2023-04-20 | 2023-04-20 |  |  |  |  | 42.9733 | 16.5279 | متأخر | No
2200228782 | وزارة المالية | إشراف | ذات اولوية عالية | 36930064.82 | 1846503.241 | 28803298.9 | 28803298.9 | 4650061777 | لا | 0 |  | جاري | مدفوعات ساعات العمل | 73.83 | 75 | 2014-08-17 | 2015-05-17 | 2024-04-30 | 2024-04-30 |  |  |  |  | 39.7445 | 24.435 | خدمات عامة | No
2200228793 | وزارة المالية | تحديث وتوريد | ذات اولوية عالية | 1071802298.85 | 53590114.9425 | 0 | 0 | 4030068284 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 5.2 | 20.39 | 2022-03-01 | 2024-11-30 | 2024-11-30 | 2024-11-30 |  |  |  |  | 39.6112 | 24.4672 | متأخر | No
2100098022 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 4499740 | 224987 | 4389845.23 | 4389845.23 | 1010210667 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-12-24 | 2020-06-21 | 2020-06-21 | 2020-06-21 | 2020-06-21 |  | أوامر تغيير |  |  |  | منجز | No
2100073286 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 12062600 | 603130 | 12013532 | 12013532 | 4030087384 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 99.06 | 100 | 2017-11-14 | 2019-10-24 | 2020-08-27 | 2020-08-27 |  | 2019-10-24 | لا يوجد تأخير |  | 48.4982 | 28.4391 | منجز | No
2100098453 | وزارة التعليم | تشييد | ذات اولوية عالية | 13388065 | 669403.25 | 4923965 | 4777436 | 4031033277 | لا | 0 |  | مسحوب | التكلفة المفوترة | 85 | 100 | 2015-04-12 | 2017-04-03 | 2022-12-15 | 2022-12-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | No
2200212973 | المؤسسة العامة للتقاعد | تشييد | ذات اولوية عالية | 29455044.34 | 1472752.217 | 6786441.54 | 6786441.54 | 1010200098 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 74.14 | 100 | 2021-10-09 | 2022-09-05 | 2022-09-05 | 2022-09-05 |  |  |  |  | 39.1267 | 21.7263 | Failed | No
2100205225 | وزارة الصحة / تجمع الشرقية | تشييد | ذات اولوية عالية | 491452.5 | 24572.625 | 40467.94 | 40467.94 | 2051044592 | لا | 0 | 200401103610 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-10-11 | 2021-01-11 | 2021-12-28 | 2021-12-28 | 2021-01-11 |  |  |  | 49.9679 | 26.5253 | منجز | No
2100091582 | الهيئة الملكية للجبيل وينبع / مدينة جازان للصناعات الأساسية والتحويلية | دراسات هندسية | ذات اولوية متوسطة | 9998459.6 | 499922.98 | 2514132.3 | 2514132.3 | 2050107656 | لا | 0 | 181201470591 | جاري | مدفوعات ساعات العمل | 26.95 | 26.95 | 2019-01-30 | 2024-01-29 | 2024-01-29 | 2024-01-29 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.3708 | 17.3428 | خدمات عامة | No
2100012375 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 17273540 | 863677 | 15678118.5275 | 15678118.5275 | 4650050716 | لا | 0 |  | جاري | تكلفة العمل المنجز | 91 | 100 | 2018-02-27 | 2023-09-06 | 2021-09-09 | 2021-09-09 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.6083 | 24.4742 | متأخر | No
2100007055 | المؤسسة العامة للتقاعد | تشييد | ذات اولوية عالية | 16383385 | 819169.25 | 2747039.38 | 2747039.38 | 4030154608 | نعم | 3052266 |  | مسحوب | التكلفة المفوترة | 18 | 100 | 2014-12-02 | 2016-01-06 | 2021-02-16 | 2021-02-16 |  |  | ضعف كفاءة المقاول الفنية |  | 39.7085 | 24.483 | مسحوب | No
2100193255 | وزارة الحرس الوطني / الشؤون الفنية بالقطاع الغربي | تشييد | ذات اولوية عالية | 1398442.5 | 69922.125 | 0 | 0 | 1010070662 | لا | 0 | 201101248059 | ايقاف كلي | تكلفة العمل المنجز | 30 | 30 | 2021-02-08 | 2022-02-07 | 2023-05-20 | 2023-05-20 |  |  |  |  | 42.7821 | 16.9255 | Failed | No
2100052986 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 11303250 | 565162.5 | 11010454.55 | 11010454.55 | 4031041927 | لا | 0 | 200209130285 | منجز – استلام ابتدائي | التكلفة المفوترة | 97.44 | 97.44 | 2019-06-10 | 2020-05-29 | 2022-01-23 | 2022-01-23 | 2020-05-29 |  |  |  | 39.8665 | 21.3329 | منجز | No
2100048580 | وزارة الصحة / تجمع الشرقية | تشييد | ذات اولوية عالية | 5280000 | 264000 | 0 | 0 | 2051060090 | لا | 0 | 191001003631 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-07-21 | 2022-03-21 | 2022-03-21 | 2022-03-21 | 2022-03-21 |  | تصاريح أعمال التنفيذ |  | 50.105 | 26.4072 | منجز | No
2100091420 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2913487.5 | 145674.375 | 41889 | 0 | 1010108475 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-12-30 | 2016-06-22 | 2019-10-10 | 2019-10-10 | 2016-06-22 |  | ضعف كفاءة المقاول الفنية |  | 45.9927 | 24.3299 | منجز | Yes
2100063626 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1207500 | 60375 | 600000 | 0 | 1010129381 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 90 | 2018-11-25 | 2020-01-19 | 2020-01-19 | 2020-01-19 | 2020-01-19 |  |  |  | 46.6782 | 24.7069 | منجز | Yes
2100104123 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 23499883.56 | 1174994.178 | 19971122.25 | 19971122 | 1010225750 | لا | 0 |  | مسحوب | التكلفة المفوترة | 85 | 100 | 2012-05-22 | 2014-05-14 | 2023-01-15 | 2023-01-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | No
2100071632 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 319646.5 | 15982.325 | 319646.5 | 319646.5 | 3350023776 | لا | 0 | 190501009281 | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 92 | 100 | 2019-03-21 | 2020-03-14 | 2020-03-15 | 2020-03-15 |  |  |  |  | 42.4404 | 27.1928 | Failed | No
2100079693 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية | 67138863.91 | 3356943.1955 | 13848423.04 | 13848423.04 | 1010007606 | نعم | 10064960.3 | 180709023801 | جاري | تكلفة العمل المنجز | 25 | 100 | 2015-08-25 | 2016-12-17 | 2025-12-31 | 2025-12-31 |  |  | تأخرصرف المستحقات المالية |  | 42.0825 | 19.2061 | Failed | No
2100096666 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية وعاجلة | 51077320.65 | 2553866.0325 | 16651330.97 | 16651330.97 | 1010154653 | نعم | 36664214.62 |  | مسحوب | تكلفة العمل المنجز | 84 | 100 | 2016-05-29 | 2018-08-22 | 2026-12-31 | 2026-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7211 | 24.6588 | مسحوب | No
2200226096 | شركة المياه الوطنية / منطقة الرياض | تصميم وتشييد | ذات اولوية عالية | 8935000 | 446750 | 0 | 0 | 1010259673 | لا | 0 |  | جاري | تكلفة العمل المنجز | 1e-34 | 1e-41 | 2022-06-23 | 2023-12-24 | 2023-12-24 | 2023-12-24 |  |  |  |  | 46.7401 | 24.6819 | منتظم | No
2100060443 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية وعاجلة | 7133484 | 356674.2 | 4727164.13 | 4727164.13 | 1010074764 | لا | 0 | 180301000634 | جاري | منهجية القيمة المكتسبة | 76.2 | 100 | 2018-07-10 | 2021-07-10 | 2022-08-03 | 2022-08-03 |  |  | لا يوجد تأخير |  | 50.0091 | 26.5773 | Failed | No
2100010791 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 11319124.59 | 565956.2295 | 11185253.54 | 9971595.32 | 1010060469 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2016-02-01 | 2018-04-22 | 2019-07-21 | 2019-07-21 | 2018-04-22 |  |  |  | 39.6005 | 24.4595 | منجز | No
2100020823 | جامعة نجران | تشييد | ذات اولوية عالية وعاجلة | 60000000 | 3000000 | 24265810 | 24265810 | 5855000147 | لا | 0 | 180709024469 | جاري | الكميات التي تم تركيبها | 85 | 100 | 2015-11-04 | 2018-10-01 | 2023-01-01 | 2023-01-01 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 47.1167 | 17.4861 | Failed | No
2100000906 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية | 64359924.1 | 3217996.205 | 46281253.04 | 46071673.04 | 1010175465 | لا | 0 | 180709022390 | جاري | تكلفة العمل المنجز | 91 | 97 | 2014-09-10 | 2016-08-10 | 2023-05-01 | 2023-05-01 |  |  | اخرى |  | 46.1024 | 24.4548 | متأخر | No
2100073732 | جامعة القصيم | تشييد | ذات اولوية عالية | 616687498 | 30834374.9 | 407325854.5 | 407325854.5 | 2051030201 | لا | 0 | 200409032066 | جاري | تكلفة العمل المنجز | 65 | 96 | 2011-10-24 | 2014-04-11 | 2023-12-25 | 2023-12-25 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 43.8579 | 26.3006 | Failed | No
2100027510 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 23128331.87 | 1156416.5935 | 21142781.91 | 21142781.91 | 1010224518 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99.94 | 100 | 2019-02-28 | 2021-03-01 | 2021-06-08 | 2021-06-08 | 2021-03-01 |  | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100196825 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 49655235 | 2482761.75 | 42359206.37 | 42359206.37 | 2050031898 | لا | 0 | 180809043629 | منجز – استلام ابتدائي | التكلفة المفوترة | 85 | 100 | 2013-11-20 | 2015-08-02 | 2016-07-02 | 2016-07-02 | 2015-08-02 |  |  |  | 50.0888 | 26.4207 | منجز | No
2100095130 | الهيئة الملكية للجبيل وينبع / مدينة جازان للصناعات الأساسية والتحويلية | تصميم وإشراف | ذات اولوية متوسطة | 68764732.5 | 3438236.625 | 54142996.03 | 54142996.03 | 2051060090 | لا | 0 | 181201494285 | جاري | مدفوعات ساعات العمل | 83.78 | 87.31 | 2019-03-04 | 2024-03-02 | 2024-03-02 | 2024-03-02 |  |  | تأخرصرف المستحقات المالية |  | 42.3669 | 17.3459 | منتظم | No
2100083580 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 13394152 | 669707.6 | 13394152 | 13394152 | 2251032617 | لا | 0 | 180801054422 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-11-05 | 2020-10-26 | 2021-06-21 | 2021-06-21 | 2020-10-26 |  |  |  | 49.5875 | 25.3736 | منجز | No
2100190455 | وزارة البيئة والمياة والزراعة | توريد وتركيب | ذات اولوية عالية وعاجلة | 498072.75 | 24903.6375 | 498072.75 | 498072.75 | 7007119667 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2021-05-03 | 2021-10-27 | 2021-10-27 | 2021-10-27 | 2021-10-27 |  |  |  | 44.2415 | 17.5563 | منجز | No
2200233892 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 17607275.1 | 880363.755 | 6222597 | 6222597 | 4031046580 | لا | 0 |  | جاري | تكلفة العمل المنجز | 35.34 | 35.34 | 2022-05-18 | 2023-05-18 | 2023-05-18 | 2023-05-18 |  |  |  |  | 39.8579 | 21.3891 | منتظم | No
2200233936 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 25622500 | 1281125 | 11066666.5 | 11066666.5 | 4031008077 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 53.48 | 53.48 | 2014-08-06 | 2017-08-06 | 2019-01-12 | 2019-01-12 | 2017-08-06 |  |  |  | 39.8579 | 21.3891 | منجز | No
2100190934 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 28008440 | 1400422 | 25207536.55 | 25207536.55 | 4030021112 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2020-02-16 | 2020-12-17 | 2021-03-13 | 2021-03-13 | 2020-12-17 |  |  |  | 39.7114 | 21.2553 | منجز | No
2100036234 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 18061800 | 903090 | 16196633.8 | 16196633.8 | 1010224518 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 93.39 | 100 | 2019-02-11 | 2020-02-11 | 2020-02-11 | 2020-02-11 |  | 2020-02-11 | لا يوجد تأخير |  | 46.5756 | 24.7675 | منجز | No
2100019762 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 11502821.4 | 575141.07 | 11368008.04 | 11368008.04 | 1010185409 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-11-11 | 2020-09-21 | 2021-05-12 | 2021-05-12 | 2020-09-21 |  | أوامر تغيير | أخرى |  |  | منجز | No
2100193281 | وزارة الحرس الوطني / الشؤون الفنية بالقطاع الغربي | توريد وتركيب | ذات اولوية عالية | 9884505 | 494225.25 | 9265670 | 8118585 | 4030171572 | لا | 0 | 220109092271 | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 99.5 | 100 | 2020-09-20 | 2022-03-07 | 2023-01-30 | 2023-01-30 |  |  | اخرى |  | 39.3716 | 21.4301 | Failed | No
2100009310 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 17963925 | 898196.25 | 14600924.43 | 14526126.87 | 1010039430 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-10-30 | 2020-08-25 | 2020-08-09 | 2020-08-09 | 2020-08-25 |  | أوامر تغيير |  |  |  | منجز | No
2100069613 | المؤسسة العامة للري | تشييد | ذات اولوية عالية | 3330994.42 | 166549.721 | 3330994.42 | 3330994.42 | 2252028812 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2019-09-25 | 2020-05-18 | 2022-06-09 | 2022-06-09 | 2020-05-18 |  | لا يوجد تأخير |  | 49.6248 | 25.3896 | منجز | No
2100091781 | أمانة / جدة | الخدمات الاستشارية | ذات اولوية متوسطة | 2468620 | 123431 | 2525435 | 2185996 | 4650047424 | لا | 0 | 181109339412 | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 99 | 2015-06-28 | 2016-12-10 | 2022-05-02 | 2022-05-02 | 2016-12-10 | 2022-02-01 | أوامر سامية |  |  |  | منجز | No
2100058041 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1895980 | 94799 | 757801.6 | 757800 | 4034100039 | لا | 0 | 190509064655 | مسحوب | تكلفة العمل المنجز | 48 | 100 | 2018-05-28 | 2019-11-19 | 2022-06-30 | 2022-06-30 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6211 | 21.2076 | مسحوب | No
2200221583 | شركة المياه الوطنية / منطقة الحدود الشمالية | إشراف | ذات اولوية عالية وعاجلة | 7888230 | 394411.5 | 1774715.42 | 0 | 1010949106 | لا | 0 | 210101030262 | جاري | التكلفة المفوترة | 41 | 45 | 2021-07-12 | 2023-07-12 | 2023-07-12 | 2023-07-12 |  |  |  |  | 40.9172 | 30.9931 | خدمات عامة | Yes
2100065391 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 3666600 | 183330 | 1442670 | 1442670 | 2050048409 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 40 | 100 | 2012-02-18 | 2013-08-11 | 2019-02-17 | 2019-02-17 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5673 | 25.3893 | مسحوب | No
2100055650 | جامعة القصيم | تشييد | ذات اولوية عالية وعاجلة | 15623031 | 781151.55 | 15932649.45 | 15527547.3 | 1131012139 | لا | 0 | 210609041506 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2017-11-06 | 2018-09-02 | 2021-06-15 | 2021-06-15 | 2018-09-02 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 44.1667 | 26.7346 | منجز | No
2100107505 | هيئة تطوير منطقة المدينة المنورة | تشييد | ذات اولوية عالية | 53360860 | 2668043 | 32258753 | 32258753 | 2050024197 | لا | 0 | 190309071752 | جاري | تكلفة العمل المنجز | 75 | 100 | 2018-04-03 | 2021-04-02 | 2023-02-19 | 2023-02-19 |  |  | ضعف كفاءة المقاول الفنية |  | 39.5796 | 24.4848 | Failed | No
2200234345 | أمانة / العاصمة المقدسة | تصميم | ذات اولوية متوسطة | 3200000 | 160000 | 3200000 | 3200000 | 1010326466 | لا | 0 |  | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2021-11-07 | 2022-07-08 | 2022-07-08 | 2022-07-08 | 2022-07-08 | 2022-07-28 |  |  | 39.8579 | 21.3891 | منجز | No
2100199216 | شركة المياه الوطنية / منطقة الرياض | دراسات هندسية | ذات اولوية عالية | 2010000 | 100500 | 1092119.37 | 1092119.37 | 1010348048 | لا | 0 |  | جاري | التكلفة المفوترة | 74.55 | 74.55 | 2021-07-08 | 2022-10-08 | 2022-10-08 | 2022-10-08 |  |  |  |  | 46.7939 | 24.6531 | خدمات عامة | No
2100191450 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 21903800 | 1095190 | 19084909.88 | 19084909.88 | 1010257051 | لا | 0 | 200709052696 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 97 | 100 | 2020-06-30 | 2021-03-30 | 2022-02-28 | 2022-02-28 |  |  |  |  | 39.2018 | 21.3585 | Failed | No
2100043142 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 54998758.29 | 2749937.9145 | 14016006.84 | 10116975.67 | 1010031532 | لا | 0 | 180201000289 | جاري | منهجية القيمة المكتسبة | 36.13 | 36.13 | 2018-12-11 | 2022-10-29 | 2023-09-21 | 2023-09-21 |  |  | لا يوجد تأخير |  | 45.6166 | 25.5958 | منتظم | No
2100190853 | شركة المياه الوطنية / منطقة الجوف | تشييد | ذات اولوية عالية وعاجلة | 5881589.7 | 294079.485 | 5235063.15 | 4017117.42 | 3400011750 | لا | 0 | 200501102919 | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2020-10-01 | 2021-09-21 | 2021-09-18 | 2021-09-18 | 2021-09-21 | 2022-09-11 |  |  | 40.2066 | 29.9707 | منجز | No
2100001831 | جامعة طيبة | تشييد | ذات اولوية عالية | 128858882 | 6442944.1 | 79399496.58 | 79399496.58 | 2050022550 | لا | 0 | 181109361470 | جاري | تكلفة العمل المنجز | 61.62 | 100 | 2013-06-05 | 2017-04-09 | 2017-04-10 | 2017-04-10 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال | مخطط لسحبه وإعادة ترسيته | 39.6005 | 24.4595 | Failed | No
2100063136 | مستشفى الملك فيصل التخصصي ومركز الأبحاث | إشراف | ذات اولوية عالية | 49704110 | 2485205.5 | 37212982.84 | 37212982.84 | 4030216250 | لا | 0 | 181101309386 | جاري | مدفوعات ساعات العمل | 72 | 74 | 2019-01-08 | 2022-01-07 | 2024-04-30 | 2024-04-30 |  |  |  |  | 39.1726 | 21.7434 | خدمات عامة | No
2200226122 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية عالية | 32909700 | 1645485 | 0 | 0 | 5855010714 | لا | 0 | 210901071287 | جاري | منهجية القيمة المكتسبة | 0 | 0 | 2022-06-05 | 2024-06-05 | 2024-06-05 | 2024-06-05 |  |  |  |  | 42.815 | 18.0974 | منتظم | No
2100191236 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية عالية | 23939831.75 | 1196991.5875 | 10534736 | 10249030 | 5855020873 | لا | 0 | 200301072353 | جاري | منهجية القيمة المكتسبة | 51.59 | 100 | 2020-12-01 | 2022-05-17 | 2023-05-31 | 2023-05-31 |  |  |  |  | 42.8538 | 18.2789 | Failed | No
2100191774 | شركة المياه الوطنية / منطقة الرياض | إشراف | ذات اولوية عالية | 6232800 | 311640 | 3749967.03 | 3749967.03 | 1010326770 | لا | 0 |  | جاري | التكلفة المفوترة | 60.17 | 60.17 | 2021-02-20 | 2023-02-20 | 2023-02-20 | 2023-02-20 |  |  |  |  | 46.8525 | 24.7946 | خدمات عامة | No
2100108953 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية وعاجلة | 66204730 | 3310236.5 | 52698366.76 | 29792221 | 2050018730 | لا | 0 | 180709033112 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 80.47 | 100 | 2011-05-23 | 2013-04-30 | 2019-01-31 | 2019-01-31 | 2013-04-30 |  | لا يوجد تأخير |  | 42.5241 | 17.3714 | منجز | No
2200235012 | وزارة الرياضة | ترميم | ذات اولوية عالية | 2669265 | 133463.25 | 0 | 0 | 1010188861 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 20 | 20 | 2022-09-19 | 2023-09-18 | 2023-09-18 | 2023-09-18 |  |  |  |  | 39.1925 | 21.4858 | منتظم | No
2100022982 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية وعاجلة | 39250150 | 1962507.5 | 39250149.96 | 38851257.06 | 1010179797 | لا | 0 | 180709025041 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 99.6 | 100 | 2015-06-17 | 2018-05-16 | 2020-02-23 | 2020-02-23 |  | 2018-05-16 | لا يوجد تأخير |  | 42.5429 | 16.8808 | منجز | No
2100059533 | شركة المياه الوطنية / منطقة الحدود الشمالية | تشييد | ذات اولوية عالية | 23482240 | 1174112 | 19369174 | 18484996.6 | 5950014087 | لا | 0 | 181001218317 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 90.88 | 99.5 | 2019-05-23 | 2021-10-24 | 2022-07-15 | 2022-07-15 |  |  | اخرى |  | 38.6644 | 31.6517 | متأخر | No
2100019832 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية متوسطة | 79417151.44 | 3970857.572 | 79204503.27 | 79204503.27 | 1010219753 | لا | 0 | 180709019599 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2016-06-23 | 2018-06-02 | 2020-12-21 | 2020-12-21 |  | 2018-06-02 | لا يوجد تأخير |  | 43.9553 | 26.3508 | منجز | No
2100016472 | وزارة التعليم | تشييد | ذات اولوية عالية | 2742008 | 137100.4 | 1616197 | 1616197 | 1010240933 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-08-27 | 2016-05-19 | 2016-05-19 | 2016-05-19 | 2016-05-19 |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | منجز | No
2100017485 | وزارة الصحة / التجمع الاول | تشييد | ذات اولوية عالية | 74197300 | 3709865 | 40990471 | 40990471 | 1010007936 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 99 | 95 | 2017-09-27 | 2019-07-02 | 2019-07-02 | 2019-07-02 | 2019-07-02 |  | تأخرصرف المستحقات المالية |  | 46.6894 | 24.6274 | منجز | No
2100061110 | شركة المياه الوطنية / منطقة الحدود الشمالية | تشييد | ذات اولوية عالية | 56940470 | 2847023.5 | 56940470 | 51210912.65 | 2054001027 | لا | 0 | 181009137162 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-02-22 | 2021-01-19 | 2021-03-29 | 2021-03-29 |  | 2021-01-19 | لا يوجد تأخير |  | 41.0226 | 30.9583 | منجز | No
2200226133 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية عالية | 24164289.8 | 1208214.49 | 0 | 0 | 5855023504 | لا | 0 | 211001006145 | جاري | منهجية القيمة المكتسبة | 0 | 0 | 2022-06-05 | 2024-06-05 | 2024-06-05 | 2024-06-05 |  |  |  |  | 42.5117 | 18.2465 | منتظم | No
2100092083 | شركة المياه الوطنية / منطقة الحدود الشمالية | توريد وتركيب | ذات اولوية عالية | 4769299.5 | 238464.975 | 2655140.95 | 2655140.95 | 1010216415 | لا | 0 | 190701201899 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-12-25 | 2019-12-16 | 2019-12-02 | 2019-12-02 | 2019-12-16 |  | لا يوجد تأخير |  | 40.9165 | 30.9926 | منجز | No
2100072085 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 20800696 | 1040034.8 | 20800696 | 20800696 | 2050041707 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2019-06-22 | 2021-05-31 | 2021-05-31 | 2021-05-31 | 2021-05-31 |  |  |  | 50.2219 | 26.3223 | منجز | No
2100094172 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية | 11012949.05 | 550647.4525 | 10073396.21 | 10073396.21 | 1010279791 | لا | 0 | 180709019610 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 99.91 | 100 | 2015-10-18 | 2018-09-15 | 2020-12-09 | 2020-12-09 |  | 2018-09-15 | لا يوجد تأخير |  | 44.2014 | 25.8831 | منجز | No
2100191811 | شركة المياه الوطنية / منطقة حائل | إشراف | لم تعد تحتاجها الجهة | 2992470.72 | 149623.536 | 2967539.62 | 2967539.62 | 3400011727 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-05-19 | 2016-07-19 | 2017-02-04 | 2017-02-04 | 2016-07-19 |  |  |  | 42.4113 | 27.8755 | منجز | No
2100027613 | وزارة الصحة / التجمع الاول | تشييد | ذات اولوية عالية | 8288224.36 | 414411.218 | 2956086.97 | 2956086.97 | 2050004344 | لا | 0 | 181009122128 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 80 | 98 | 2018-03-01 | 2018-10-23 | 2018-10-25 | 2018-10-25 | 2018-10-23 |  | اخرى |  | 46.6894 | 24.6274 | منجز | No
2100013403 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 25979994 | 1298999.7 | 2579084 | 0 | 1010160688 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 94.63 | 14 | 2019-03-23 | 2021-03-12 | 2021-03-12 | 2021-03-12 | 2021-03-12 |  |  |  | 46.6727 | 24.7144 | منجز | Yes
2100052006 | وزارة الصحة / حائل | تشييد | ذات اولوية عالية | 4642050 | 232102.5 | 3408824 | 3408824 | 1010075656 | لا | 0 | 200201002883 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-02-17 | 2021-04-22 | 2021-04-22 | 2021-04-22 | 2021-04-22 |  | ضعف كفاءة المقاول الفنية |  | 41.6966 | 27.5075 | منجز | No
2200221056 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 3008709 | 150435.45 | 0 | 0 | 1010263725 | نعم | 9139886.07 |  | جاري | منهجية القيمة المكتسبة | 7 | 42.6 | 2022-01-11 | 2023-01-11 | 2023-01-11 | 2023-01-11 |  |  |  |  | 39.2285 | 21.5514 | Failed | No
2100028501 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 6025295 | 301264.75 | 5400625 | 0 | 1010007322 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 95 | 100 | 2008-01-28 | 2009-09-20 | 2023-01-15 | 2023-01-15 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.6005 | 24.4595 | مسحوب | Yes
2100044015 | أمانة / الجوف | تشييد | ذات اولوية متوسطة | 886430 | 44321.5 | 886430 | 886430 | 3400111080 | لا | 0 | 180909094816 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-07-29 | 2019-09-05 | 2019-09-05 | 2019-09-05 | 2019-09-05 |  | تأخرصرف المستحقات المالية |  | 39.8856 | 29.7982 | منجز | No
2200226052 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 362000 | 18100 | 302000 | 0 | 4031072977 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 94 | 100 | 2022-03-01 | 2022-07-01 | 2022-07-01 | 2022-07-01 |  |  |  |  | 39.8809 | 21.4118 | متأخر | Yes
2100068795 | أمانة / القصيم | تشييد | ذات اولوية متوسطة | 552300000 | 27615000 | 358618538.4965 | 358618538.4965 | 1010011560 | لا | 0 | 18080103897 | جاري | تكلفة العمل المنجز | 66 | 69 | 2018-11-10 | 2023-10-12 | 2023-10-13 | 2023-10-13 |  |  | ضعف كفاءة المقاول الفنية |  | 43.9818 | 26.3592 | منتظم | No
2100098151 | رئاسة أمن الدولة / القيادة العامة لطيران الأمن | تشييد | ذات اولوية عالية وعاجلة | 25000000 | 1250000 | 5547549.9 | 5547549.9 | 1010119469 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 20 | 20 | 2019-10-20 | 2020-10-20 | 2020-10-10 | 2020-10-10 |  |  | التنسيق مع أصحاب المصلحه (خدمات |  | 46.7342 | 24.7475 | مسحوب | No
2100031441 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3176000 | 158800 | 41717 | 0 | 1113000490 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-01-11 | 2016-07-04 | 2020-02-22 | 2020-02-22 | 2016-07-04 |  | ضعف كفاءة المقاول الفنية |  | 45.5239 | 25.2972 | منجز | Yes
2100040681 | وزارة الصحة / حائل | تشييد | ذات اولوية منخفضة | 389820 | 19491 | 389820 | 389820 | 3350020084 | لا | 0 | 191201146927 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-11-05 | 2020-02-12 | 2021-05-29 | 2021-05-29 | 2020-02-12 |  | ضعف كفاءة المقاول الفنية |  | 41.6852 | 27.5704 | منجز | No
2200235141 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 235192561 | 11759628.05 | 52282730 | 52282730 | 4030023505 | نعم | 210898790 |  | جاري | منهجية القيمة المكتسبة | 34.7 | 41.17 | 2022-02-20 | 2024-05-05 | 2024-05-24 | 2024-05-24 |  |  |  |  | 38.19 | 24.0232 | متأخر | No
2100103025 | شركة المياه الوطنية / منطقة الحدود الشمالية | إشراف | ذات اولوية عالية وعاجلة | 29999904 | 1499995.2 | 29899915.24 | 29899915.24 | 2051011487 | لا | 0 |  | منجز – استلام نهائي | مدفوعات ساعات العمل | 99.63 | 100 | 2017-01-01 | 2018-12-10 | 2018-12-10 | 2018-12-10 |  | 2018-12-10 | لا يوجد تأخير |  | 38.9397 | 31.6773 | منجز | No
2100012725 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 15829600 | 791480 | 15829600 | 15829600 | 1010006004 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-11-25 | 2022-02-06 | 2021-10-22 | 2021-10-22 | 2022-02-06 |  | ضعف كفاءة المقاول الفنية |  | 39.5709 | 24.523 | منجز | No
2200226063 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 55000000 | 2750000 | 0 | 0 | 1010012911 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 1 | 1 | 2022-04-28 | 2024-04-29 | 2024-04-29 | 2024-04-29 |  |  |  |  | 39.803 | 21.3572 | منتظم | No
2100062930 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 16999998 | 849999.9 | 3840613.5334 | 0 | 1114000037 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 95 | 100 | 2013-09-01 | 2019-03-25 | 2019-03-26 | 2019-03-26 |  |  | ضعف كفاءة المقاول الفنية |  | 46.672 | 24.7001 | مسحوب | Yes
2100040165 | وزارة الصحة / بيشة | تشييد | ذات اولوية عالية | 2000000 | 100000 | 1141915.2 | 418810 | 5852002706 | نعم | 970996.89 | 202101152094 | جاري | تكلفة العمل المنجز | 95 | 100 | 2020-12-20 | 2021-12-09 | 2022-12-15 | 2022-12-15 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 21 | 19 | Failed | No
2100061364 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية | 114678210 | 5733910.5 | 53327601.55 | 53327601.55 | 1116000082 | نعم | 53616614.65 | 181209508521 | مسحوب | منهجية القيمة المكتسبة | 48.16 | 100 | 2012-11-12 | 2014-10-21 | 2022-02-28 | 2022-02-28 |  |  | ضعف كفاءة المقاول الفنية |  | 43.1153 | 17.2761 | مسحوب | No
2100105674 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية عالية | 59590500 | 2979525 | 53613513 | 53613513 | 4030082735 | لا | 0 | 180901068860 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-10-02 | 2021-03-06 | 2021-12-09 | 2021-12-09 | 2021-03-06 |  | لا يوجد تأخير |  | 42.4989 | 18.2169 | منجز | No
2100064444 | أمانة / عسير | تشييد | ذات اولوية عالية | 4089960 | 204498 | 490795 | 490795 | 5860005901 | لا | 0 | 191001131040 | مسحوب | تكلفة العمل المنجز | 80 | 100 | 2019-09-08 | 2020-09-08 | 2021-12-30 | 2021-12-30 |  |  | ضعف كفاءة المقاول الفنية |  | 41.95 | 19.5769 | مسحوب | No
2100000556 | جامعة نجران | تشييد | ذات اولوية متوسطة | 2000000 | 100000 | 1800000 | 1800000 | 1001032384 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 82 | 100 | 2012-01-12 | 2016-06-30 | 2023-08-31 | 2023-08-31 |  |  | عدم وجود مبالغ في البنود تغطي الأعمال المرصودة |  | 44.2341 | 17.5757 | Failed | No
2200235163 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 8067899.75 | 403394.9875 | 1215484 | 806789.58 | 4700004138 | نعم | 125859423 |  | جاري | منهجية القيمة المكتسبة | 33.46 | 79.35 | 2022-03-31 | 2023-03-30 | 2023-08-16 | 2023-08-16 |  |  |  |  | 38.19 | 24.0232 | Failed | No
2100029735 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1294650 | 64732.5 | 1294650 | 1294650 | 4032025656 | لا | 0 | 181209462185 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-10-28 | 2019-04-26 | 2019-04-26 | 2019-04-26 | 2019-04-26 |  |  |  | 40.4038 | 21.2651 | منجز | No
2100001315 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 37037000 | 1851850 | 19911783 | 19911783 | 2050007224 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-03-13 | 2019-02-19 | 2019-06-17 | 2019-06-17 |  | 2019-02-19 | لا يوجد تأخير |  | 39.1491 | 21.5827 | منجز | No
2100002166 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 36740000 | 1837000 | 31610057.29 | 31610057.29 | 5800004747 | لا | 0 | 180809052296 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 98.08 | 100 | 2014-12-25 | 2017-05-29 | 2021-02-28 | 2021-02-28 | 2017-05-29 |  | لا يوجد تأخير |  | 45.3525 | 25.8912 | منجز | No
2200235572 | أمانة / القصيم | تشييد | ذات اولوية عالية | 2949850 | 147492.5 | 2359880 | 2359880 | 1161100455 | لا | 0 |  | جاري | تكلفة العمل المنجز | 81 | 81 | 2020-06-29 | 2023-06-10 | 2023-06-10 | 2023-06-10 |  |  |  |  | 43.2796 | 26.028 | منتظم | No
2100189626 | الهيئة الملكية للجبيل وينبع / مدينة جازان للصناعات الأساسية والتحويلية | تشييد | ذات اولوية متوسطة | 43273599.14 | 2163679.957 | 15619949.43 | 15619949.43 | 5950011723 | لا | 0 | 200101021151 | جاري | الكميات التي تم تركيبها | 45 | 42.96 | 2020-07-02 | 2022-07-02 | 2024-02-26 | 2024-02-26 |  |  |  |  | 42.3318 | 17.3556 | منتظم | No
2100082095 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 1027740 | 51387 | 1027740 | 924740 | 4030188853 | لا | 0 | 200609038149 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-11-21 | 2021-02-23 | 2021-02-07 | 2021-02-07 | 2021-02-23 |  | اخرى |  | 40.739 | 19.9163 | منجز | No
2100080872 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1365000 | 68250 | 1328556.24 | 1328556.24 | 4032040200 | لا | 0 | 200401075595 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 97 | 100 | 2019-09-15 | 2020-09-09 | 2020-09-09 | 2020-09-09 | 2020-09-09 |  |  |  | 40.8072 | 20.9469 | منجز | No
2100000943 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية | 8899875 | 444993.75 | 6072943.79 | 6072943.79 | 5950012194 | لا | 0 | 180801040278 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 87.63 | 100 | 2018-09-11 | 2019-08-31 | 2021-08-19 | 2021-08-19 | 2019-08-31 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.6509 | 17.1567 | منجز | No
2100009800 | أمانة / الرياض | تشييد | ذات اولوية عالية | 20999836 | 1049991.8 | 13148758.9 | 0 | 1010168999 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 56 | 100 | 2014-08-11 | 2016-07-31 | 2020-08-13 | 2020-08-13 | 2016-07-31 |  | ضعف كفاءة المقاول الفنية |  | 46.5859 | 24.7995 | منجز | Yes
2200235174 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 18779390.18 | 938969.509 | 2954258 | 2954258 | 3555000709 | نعم | 58779041 |  | جاري | منهجية القيمة المكتسبة | 22.38 | 22.77 | 2022-03-23 | 2023-09-21 | 2024-05-09 | 2024-05-09 |  |  |  |  | 38.19 | 24.0232 | منتظم | No
2100193336 | المؤسسة العامة للتقاعد | تشييد | ذات اولوية عالية | 5135785 | 256789.25 | 4622166.5 | 4622166.5 | 4032025725 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2020-10-20 | 2021-05-21 | 2021-11-30 | 2021-11-30 | 2021-05-21 |  |  |  | 39.7085 | 24.483 | منجز | No
2100012666 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 76055043.75 | 3802752.1875 | 68430103.57 | 68430103.57 | 1010168729 | لا | 0 |  | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 96 | 100 | 2018-12-27 | 2021-05-29 | 2021-05-29 | 2021-05-29 |  |  |  |  | 46.6974 | 24.6963 | Failed | No
2100191671 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 1876900 | 93845 | 1865176.8 | 1679070.2 | 1010227442 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99.97 | 100 | 2020-10-15 | 2021-10-15 | 2021-06-05 | 2021-06-05 | 2021-10-15 |  |  |  | 46.7211 | 24.7219 | منجز | No
2100100612 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1307000 | 65350 | 865465 | 865465 | 4030065096 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2011-09-10 | 2012-09-04 | 2012-09-04 | 2012-09-04 | 2012-09-04 |  | ضعف كفاءة المقاول الفنية |  | 42.8422 | 21.2496 | منجز | No
2100010835 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 12854300 | 642715 | 12839299.9 | 11399524.1 | 1010227442 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-10-20 | 2021-10-20 | 2021-05-18 | 2021-05-18 | 2021-10-20 |  | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100047106 | الهيئة الملكية للجبيل وينبع / مدينة جازان للصناعات الأساسية والتحويلية | تصميم | ذات اولوية متوسطة | 50123850 | 2506192.5 | 29265113.4 | 29265113.4 | 2051047662 | لا | 0 | 191001134655 | جاري | مدفوعات ساعات العمل | 55.7 | 63.45 | 2020-03-04 | 2025-03-03 | 2025-03-03 | 2025-03-03 |  |  | تأخرصرف المستحقات المالية |  | 42.371 | 17.3442 | متأخر | No
2200235211 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 52914839 | 2645741.95 | 2645742 | 2645742 | 4700004138 | نعم | 11204058 |  | جاري | منهجية القيمة المكتسبة | 3.27 | 6.05 | 2022-03-24 | 2024-03-22 | 2025-01-30 | 2025-01-30 |  |  |  |  | 38.19 | 24.0232 | منتظم | No
2100109071 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 11205803.09 | 560290.1545 | 2241161 | 2241161 | 2050018834 | لا | 0 |  | ايقاف كلي | التكلفة المفوترة | 20 | 100 | 2018-01-22 | 2020-01-20 | 2022-11-24 | 2022-11-24 |  |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | Failed | No
2100099374 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 3280885.23 | 164044.2615 | 0 | 0 | 4030052981 | لا | 0 |  | مسحوب | التكلفة المفوترة | 0 | 100 | 2015-11-22 | 2016-10-07 | 2023-08-16 | 2023-08-16 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | مسحوب | No
2100074745 | شركة المياه الوطنية / منطقة الحدود الشمالية | تشييد | ذات اولوية عالية | 17270075.6 | 863503.78 | 8585598.95 | 7280392.56 | 1011011290 | لا | 0 | 190909184628 | جاري | منهجية القيمة المكتسبة | 63.3 | 100 | 2019-01-30 | 2021-01-08 | 2023-05-15 | 2023-05-15 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.012 | 30.9719 | Failed | No
2100105221 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية وعاجلة | 133999633.8 | 6699981.69 | 10020121.48 | 10020121.48 | 4650049275 | لا | 0 | 180809054475 | جاري | منهجية القيمة المكتسبة | 91.4 | 98.47 | 2013-09-10 | 2016-08-07 | 2022-06-30 | 2022-06-30 |  |  | لا يوجد تأخير |  | 42.5429 | 16.8808 | Failed | No
2100065155 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3570000 | 178500 | 1289298.5 | 0 | 1010015152 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-08-24 | 2017-08-13 | 2020-11-19 | 2020-11-19 | 2017-08-13 |  | تأخرصرف المستحقات المالية |  | 46.6939 | 24.705 | منجز | Yes
2100006580 | أمانة / جازان | دراسة الجدوى | ذات اولوية متوسطة | 375960 | 18798 | 375960 | 375960 | 5900032159 | لا | 0 | 190701033307 | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 91 | 100 | 2019-07-02 | 2020-06-21 | 2020-06-21 | 2020-06-21 | 2020-06-21 |  | اخرى |  | 42.7276 | 16.7719 | منجز | No
2100075390 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 39161760 | 1958088 | 35633193 | 31520017 | 4650033361 | لا | 0 |  | جاري | تكلفة العمل المنجز | 80 | 100 | 2018-12-22 | 2022-06-19 | 2022-06-19 | 2022-06-19 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6027 | 24.5168 | متأخر | No
2100045415 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 778176 | 38908.8 | 470456.5 | 470456.5 | 3550022647 | لا | 0 | 190309004981 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2011-10-29 | 2012-10-23 | 2012-10-23 | 2012-10-23 | 2012-10-23 |  | ضعف كفاءة المقاول الفنية |  | 42.8396 | 21.253 | منجز | No
2100036584 | جامعة نجران | تشييد | ذات اولوية عالية | 5000000 | 250000 | 3349999 | 3349999 | 2066001761 | لا | 0 | 181209497497 | جاري | الكميات التي تم تركيبها | 77 | 100 | 2016-01-27 | 2016-11-06 | 2021-12-29 | 2021-12-29 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 44.2341 | 17.5757 | Failed | No
2100194143 | مستشفى الملك فيصل التخصصي ومركز الأبحاث | تشييد | ذات اولوية عالية | 6804112.35 | 340205.6175 | 4173726.73 | 3597513.92 | 4030009703 | لا | 0 | 201109150439 | جاري | منهجية القيمة المكتسبة | 90 | 100 | 2020-09-27 | 2021-06-24 | 2022-09-29 | 2022-09-29 |  |  |  |  | 39.1475 | 21.5588 | Failed | No
2100108592 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 120000000 | 6000000 | 73082304.38 | 73082304.38 | 4030068284 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 76 | 100 | 2010-06-07 | 2014-05-23 | 2019-09-29 | 2019-09-29 | 2014-05-23 |  | لا يوجد تأخير |  | 39.2234 | 21.6093 | منجز | No
2100082246 | أمانة / العاصمة المقدسة | أخرى | ذات اولوية متوسطة | 47171670 | 2358583.5 | 47171670 | 47171670 | 4031028157 | لا | 0 |  | جاري | تكلفة العمل المنجز | 100 | 100 | 2014-06-29 | 2016-06-28 | 2016-08-26 | 2016-08-26 |  |  | اخرى |  | 39.8665 | 21.3538 | خدمات عامة | No
2100079940 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية | 89803089 | 4490154.45 | 89799765.35 | 79930531.56 | 5860008190 | لا | 0 | 181109326470 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2012-12-18 | 2015-11-17 | 2021-02-16 | 2021-02-16 | 2015-11-17 |  | لا يوجد تأخير |  | 41.5686 | 19.8801 | منجز | No
2100006134 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 6694257.3 | 334712.865 | 3297547.92 | 3297547.92 | 1010213931 | لا | 0 |  | مسحوب | التكلفة المفوترة | 60 | 100 | 2014-03-11 | 2016-02-29 | 2018-12-07 | 2018-12-07 |  |  | ضعف كفاءة المقاول الفنية |  | 40.0549 | 29.8587 | مسحوب | No
2100048403 | وزارة الصحة / نجران | تشييد | ذات اولوية عالية وعاجلة | 14156557 | 707827.85 | 14156557 | 14156557 | 5950000083 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-04-10 | 2018-10-10 | 2021-02-28 | 2021-02-28 | 2018-10-10 |  | تأخرصرف المستحقات المالية |  | 44.1445 | 17.4945 | منجز | No
2100065413 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 4202891 | 210144.55 | 1201168.7 | 1017414.7 | 4700000316 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 30 | 100 | 2014-12-30 | 2016-08-21 | 2016-08-21 | 2016-08-21 |  |  | ضعف كفاءة المقاول الفنية |  | 38.1685 | 24.0286 | مسحوب | No
2100034532 | أمانة / حفر الباطن | تشييد | ذات اولوية متوسطة | 12835722 | 641786.1 | 12835722 | 11562000 | 1010136405 | لا | 0 | 190201038322 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-04-28 | 2020-10-19 | 2021-02-02 | 2021-02-02 | 2020-10-19 |  | ضعف كفاءة المقاول الفنية |  | 45.9973 | 28.36 | منجز | No
2100104716 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 8571233.89 | 428561.6945 | 3746122 | 3746122 | 1010150188 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 69 | 100 | 2015-01-05 | 2017-12-02 | 2022-12-31 | 2022-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 45.3525 | 25.8912 | مسحوب | No
2100032546 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 13848030 | 692401.5 | 11992113.85 | 11992113.85 | 4030044382 | لا | 0 | 200201000633 | جاري | التكلفة المفوترة | 86.6 | 86.6 | 2019-05-02 | 2021-04-09 | 2023-01-01 | 2023-01-01 |  |  |  |  | 39.8563 | 21.3764 | Failed | No
2200235233 | أمانة / الجوف | توريد وتركيب | ذات اولوية عالية وعاجلة | 1767750 | 88387.5 | 854800 | 854800 | 3403009863 | لا | 0 |  | جاري | تكلفة العمل المنجز | 89 | 46 | 2022-08-14 | 2023-06-13 | 2023-06-13 | 2023-06-13 |  |  |  |  | 40.2961 | 30.1674 | منتظم | No
2100105932 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية عالية | 60193850 | 3009692.5 | 60193850 | 60193850 | 5860008190 | لا | 0 | 180909067073 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2014-06-12 | 2017-05-10 | 2019-12-31 | 2019-12-31 |  | 2017-05-10 | لا يوجد تأخير |  | 42.0529 | 18.5228 | منجز | No
2100191306 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية | 24700999.5 | 1235049.975 | 0.01 | 0 | 5907008656 | لا | 0 | 200301082257 | ايقاف كلي | منهجية القيمة المكتسبة | 7.2 | 100 | 2020-06-01 | 2022-06-01 | 2023-04-30 | 2023-04-30 |  |  |  |  | 42.9468 | 16.5332 | Failed | Yes
2100100144 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية وعاجلة | 112363717.82 | 5618185.891 | 54385556.79 | 53154419.9 | 4030159937 | نعم | 39643676.25 | 180809041066 | مسحوب | منهجية القيمة المكتسبة | 63 | 99.19 | 2015-04-19 | 2018-03-18 | 2022-05-31 | 2022-05-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.4335 | 17.3346 | مسحوب | No
2100097241 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 65799600 | 3289980 | 36368604.47 | 36368604.47 | 2050011871 | لا | 0 | 200709052696 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99.51 | 100 | 2015-10-01 | 2018-04-01 | 2021-02-22 | 2021-02-22 | 2018-04-01 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.2838 | 21.4567 | منجز | No
2100037402 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 2351800 | 117590 | 2351800 | 2351800 | 4030006066 | لا | 0 | 181109341232 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-09-09 | 2020-02-22 | 2020-02-22 | 2020-02-22 | 2020-02-22 |  | اخرى |  | 40.8631 | 20.4216 | منجز | No
2100060550 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية وعاجلة | 17824420 | 891221 | 16628818.61 | 16041978 | 5950005816 | لا | 0 | 180801040277 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99 | 100 | 2018-09-11 | 2020-08-20 | 2021-03-31 | 2021-03-31 | 2020-08-20 |  | لا يوجد تأخير |  | 42.5429 | 16.8808 | منجز | No
2100088266 | الهيئة العامة للموانئ | توريد وتركيب | ذات اولوية عالية | 161803462 | 8090173.1 | 148673519 | 148673519 | 1010067622 | لا | 0 | 180809044020 | جاري | تكلفة العمل المنجز | 99 | 100 | 2013-11-25 | 2015-11-25 | 2022-06-30 | 2022-06-30 |  |  | تأخرصرف المستحقات المالية |  | 50.1967 | 26.4823 | Failed | No
2100069296 | وزارة الصحة / نجران | تشييد | ذات اولوية عالية وعاجلة | 7996197 | 399809.85 | 6321952.73 | 6321952.73 | 5950019143 | لا | 0 | 200809041706 | جاري | الكميات التي تم تركيبها | 100 | 100 | 2019-10-16 | 2020-04-16 | 2021-09-28 | 2021-09-28 |  |  | تأخرصرف المستحقات المالية |  | 44.2337 | 17.5451 | Failed | No
2100069716 | وزارة الصحة / نجران | تشييد | ذات اولوية عالية وعاجلة | 19677443.94 | 983872.197 | 19677443.94 | 19677443.94 | 5950000083 | لا | 0 | 200709065893 | جاري | الكميات التي تم تركيبها | 100 | 100 | 2019-07-30 | 2020-05-30 | 2021-06-13 | 2021-06-13 |  |  | تأخرصرف المستحقات المالية |  | 44.1441 | 17.4953 | Failed | No
2100061014 | وزارة العدل | تشييد | ذات اولوية عالية وعاجلة | 1269531285.24 | 63476564.262 | 593736965 | 593736965 | 1010010873 | لا | 0 | 180809057109 | مسحوب | تكلفة العمل المنجز | 64.06 | 0 | 2014-05-06 | 2017-10-09 | 2024-02-15 | 2024-02-15 |  |  | اخرى | مخطط لإعادة طرحه | 39.2022 | 21.6039 | مسحوب | No
2200235255 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 97085159.7 | 4854257.985 | 4854258 | 4854258 | 4700004138 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 1.7 | 3.61 | 2022-03-24 | 2024-03-22 | 2025-01-30 | 2025-01-30 |  |  |  |  | 38.19 | 24.0232 | منتظم | No
2100097322 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية وعاجلة | 36154333.15 | 1807716.6575 | 24928654.59 | 24928654.59 | 1010152417 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 94.76 | 100 | 2013-05-25 | 2015-05-04 | 2020-02-18 | 2020-02-18 | 2015-05-04 |  | لا يوجد تأخير |  | 42.437 | 27.1763 | منجز | No
2100065100 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2695800 | 134790 | 0 | 0 | 1116001737 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 85 | 100 | 2013-01-13 | 2015-01-03 | 2019-12-15 | 2019-12-15 | 2015-01-03 |  | ضعف كفاءة المقاول الفنية |  | 46.672 | 24.7013 | منجز | No
2100081944 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 3993928 | 199696.4 | 1874527.44 | 1874527.44 | 4650020357 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 47 | 100 | 2014-06-12 | 2015-05-31 | 2015-05-31 | 2015-05-31 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6517 | 24.4302 | مسحوب | No
2100098302 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 45877937.81 | 2293896.8905 | 27793049.56 | 27793049.56 | 1010200533 | لا | 0 | 180709022070 | ايقاف كلي | تكلفة العمل المنجز | 83 | 100 | 2014-05-05 | 2016-04-04 | 2025-12-31 | 2025-12-31 |  |  | تأخرصرف المستحقات المالية |  | 39.3521 | 21.4114 | Failed | No
2100107321 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 49007872.52 | 2450393.626 | 18468757.59 | 18265808.3 | 1010095105 | لا | 0 | 180709022146 | ايقاف كلي | تكلفة العمل المنجز | 56 | 87.85 | 2014-09-17 | 2016-08-17 | 2025-12-31 | 2025-12-31 |  |  | تأخرصرف المستحقات المالية |  | 49.5796 | 25.3938 | Failed | No
2100086074 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية | 50228521.88 | 2511426.094 | 36367745.272 | 34714260.208 | 1010319823 | لا | 0 | 180709022066 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 98.21 | 100 | 2015-05-21 | 2017-04-29 | 2021-05-09 | 2021-05-09 | 2017-04-29 |  | اخرى |  | 43.4352 | 26.6117 | منجز | No
2100102922 | شركة المياه الوطنية / منطقة الرياض | إشراف | ذات اولوية عالية | 15646680 | 782334 | 15646359.52 | 15646359.52 | 1010348048 | لا | 0 |  | منجز – استلام نهائي | مدفوعات ساعات العمل | 100 | 100 | 2018-11-06 | 2021-11-07 | 2021-11-07 | 2021-11-07 |  | 2021-11-07 | لا يوجد تأخير |  | 46.7941 | 24.6533 | منجز | No
2100104801 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 259746585 | 12987329.25 | 168002335.67 | 168002335.67 | 2050005846 | نعم | 81835339.81 |  | جاري | منهجية القيمة المكتسبة | 86.02 | 100 | 2019-09-25 | 2021-09-25 | 2022-05-30 | 2022-05-30 |  |  | ضعف كفاءة المقاول الفنية |  | 46.9482 | 24.5045 | Failed | No
2100020882 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية وعاجلة | 41121327 | 2056066.35 | 28224724 | 28224724 | 5907008656 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 94.6 | 100 | 2012-06-20 | 2013-12-03 | 2020-07-21 | 2020-07-21 | 2013-12-03 |  | لا يوجد تأخير |  | 42.6489 | 17.1599 | منجز | No
2100049140 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 127758558.9 | 6387927.945 | 37388099.45 | 37388099.45 | 5855000147 | لا | 0 |  | ايقاف كلي | منهجية القيمة المكتسبة | 37 | 100 | 2019-11-05 | 2021-12-09 | 2022-12-31 | 2022-12-31 |  |  | أوامر تغيير |  |  |  | Failed | No
2100191516 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 4053955 | 202697.75 | 3588905 | 3588905 | 4030187216 | لا | 0 | 200709052696 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 88.75 | 87.89 | 2020-11-06 | 2021-10-26 | 2021-08-22 | 2021-08-22 | 2021-10-26 |  |  |  | 39.2657 | 21.472 | منجز | No
2200229121 | الجمارك السعودية | تشييد | ذات اولوية عالية وعاجلة | 18530562.48 | 926528.124 | 14020250.01 | 14020250.01 | 1010212437 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2022-01-24 | 2022-03-10 | 2022-03-10 | 2022-03-10 | 2022-03-10 |  |  |  | 50.7567 | 24.7374 | منجز | No
2200229106 | أمانة / جدة | تشييد | ذات اولوية عالية وعاجلة | 16884307 | 844215.35 | 2400896.46 | 1541610 | 4030151328 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 42 | 95 | 2021-08-01 | 2023-01-14 | 2023-01-14 | 2023-01-14 |  |  |  | تم إنذار المقاول كتابيا | 39.1925 | 21.4858 | Failed | No
2100104020 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 150410417.35 | 7520520.8675 | 9520410.6 | 8821722.38 | 1131010605 | لا | 0 | 180709023878 | فسخ العقد | تكلفة العمل المنجز | 11 | 100 | 2015-02-19 | 2017-08-07 | 2026-12-31 | 2026-12-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 43.9461 | 26.3559 | مسحوب | No
2100093321 | شركة المياه الوطنية / منطقة الرياض | إشراف | ذات اولوية عالية | 13576000 | 678800 | 12958163.64 | 12958163.64 | 1010314421 | لا | 0 |  | منجز – استلام نهائي | مدفوعات ساعات العمل | 95.45 | 100 | 2017-06-28 | 2019-06-28 | 2020-01-28 | 2020-01-28 |  | 2019-06-28 | لا يوجد تأخير |  | 46.7939 | 24.6532 | منجز | No
2200226181 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية عالية | 30420070 | 1521003.5 | 0 | 0 | 5855029900 | لا | 0 | 210901166216 | جاري | منهجية القيمة المكتسبة | 0 | 0 | 2022-06-01 | 2024-06-01 | 2024-06-01 | 2024-06-01 |  |  |  |  | 42.5117 | 18.2465 | منتظم | No
2100156796 | الهيئة العامة للموانئ | تشييد | ذات اولوية عالية | 23694092.25 | 1184704.6125 | 9050453.02 | 9050453.02 | 1010161062 | لا | 0 | 180809052231 | ايقاف كلي | الكميات التي تم تركيبها | 51.2 | 100 | 2018-03-12 | 2019-08-24 | 2022-11-30 | 2022-11-30 |  |  |  |  | 35.5481 | 27.5656 | Failed | No
2100065166 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 296275 | 14813.75 | 0 | 0 | 1010043654 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-09-25 | 2020-09-19 | 2020-09-19 | 2020-09-19 | 2020-09-19 |  | اخرى |  | 45.5447 | 25.6206 | منجز | No
2100033386 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 6999707.5 | 349985.375 | 245575.95 | 0 | 5855001598 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 30 | 100 | 2013-11-12 | 2015-07-05 | 2020-09-06 | 2020-09-06 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6843 | 24.7025 | مسحوب | Yes
2200235270 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تصميم | ذات اولوية عالية وعاجلة | 104549674 | 5227483.7 | 0 | 0 | 1010322156 | لا | 0 |  | جاري | اخرى | 10.4 | 10.15 | 2022-08-21 | 2026-04-02 | 2026-04-02 | 2026-04-02 |  |  |  |  | 38.19 | 24.0232 | منتظم | No
2100107564 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية وعاجلة | 30579496.88 | 1528974.844 | 14246776.76 | 14246776.76 | 1010238279 | لا | 0 | 180709021948 | جاري | تكلفة العمل المنجز | 71 | 100 | 2012-12-04 | 2014-02-27 | 2025-12-31 | 2025-12-31 |  |  | تأخرصرف المستحقات المالية |  | 40.5118 | 21.3599 | Failed | No
2100089353 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية | 102639431.83 | 5131971.5915 | 67414585.25 | 57659942.03 | 1010034808 | لا | 0 | 180709021861 | جاري | تكلفة العمل المنجز | 89 | 100 | 2013-04-16 | 2015-06-25 | 2023-12-31 | 2023-12-31 |  |  | تأخرصرف المستحقات المالية |  | 39.7071 | 21.6348 | متأخر | No
2100060756 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 62262622 | 3113131.1 | 43594103.18 | 43594103.18 | 1010090968 | لا | 0 | 200709052696 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 69.07 | 100 | 2018-07-08 | 2020-06-16 | 2020-06-15 | 2020-06-15 | 2020-06-16 |  | ضعف كفاءة المقاول الفنية |  | 39.2954 | 21.383 | منجز | No
2100026596 | شركة المياه الوطنية / منطقة الرياض | تصميم | ذات اولوية عالية | 4917300 | 245865 | 4423488.76 | 4423488.76 | 1010322448 | لا | 0 |  | منجز – استلام نهائي | تكلفة العمل المنجز | 89.95 | 100 | 2018-09-09 | 2020-09-09 | 2021-06-24 | 2021-06-24 |  | 2020-09-09 | لا يوجد تأخير |  | 46.7943 | 24.653 | منجز | No
2200226170 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية عالية | 37263180.1 | 1863159.005 | 0 | 0 | 4031045263 | لا | 0 | 210901074328 | جاري | منهجية القيمة المكتسبة | 0 | 0 | 2022-06-12 | 2024-06-12 | 2024-06-12 | 2024-06-12 |  |  |  |  | 41.9246 | 19.1284 | منتظم | No
2200229401 | أمانة / جدة | تشييد | ذات اولوية عالية وعاجلة | 16546622 | 827331.1 | 2064572.07 | 2064572.07 | 4030151328 | لا | 0 | 210401124978 | جاري | الكميات التي تم تركيبها | 74.77 | 100 | 2021-08-01 | 2023-01-14 | 2023-01-14 | 2023-01-14 |  |  |  | تم إنذار المقاول كتابيا | 39.1925 | 21.4858 | Failed | No
2200229143 | أمانة / جدة | تشييد | ذات اولوية عالية وعاجلة | 16546622 | 827331.1 | 2064572.07 | 2064572.07 | 4030151328 | لا | 0 | 210401124978 | جاري | الكميات التي تم تركيبها | 74.77 | 100 | 2021-08-01 | 2023-01-14 | 2023-01-14 | 2023-01-14 |  |  |  | تم إنذار المقاول كتابيا | 39.1925 | 21.4858 | Failed | No
2100046421 | شركة المياه الوطنية / منطقة جازان | إشراف | ذات اولوية عالية وعاجلة | 1300000 | 65000 | 2327129.29 | 2327129.29 | 1010348048 | لا | 0 | 191201017237 | منجز – استلام نهائي | التكلفة المفوترة | 100 | 100 | 2019-12-08 | 2020-06-03 | 2022-06-03 | 2022-06-03 |  | 2020-06-03 | لا يوجد تأخير |  | 42.6251 | 17.592 | منجز | No
2100023236 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية | 89567950 | 4478397.5 | 57240426 | 54196780.56 | 2050018730 | لا | 0 | 180809056157 | جاري | منهجية القيمة المكتسبة | 77.13 | 100 | 2012-04-14 | 2015-03-13 | 2022-10-27 | 2022-10-27 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.9496 | 16.7159 | متأخر | No
2100060841 | المؤسسة العامة لتحلية المياه المالحة | تشييد | ذات اولوية عالية | 993036818 | 49651840.9 | 914008144.55 | 914008144.55 | 1010242485 | لا | 0 | 180701025766 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-11-05 | 2021-11-04 | 2021-11-04 | 2021-11-04 | 2021-11-04 |  | لا يوجد تأخير |  | 39.9912 | 21.3086 | منجز | No
2100074185 | وزارة الموارد البشرية والتنمية الإجتماعية | إشراف | ذات اولوية منخفضة | 1440000 | 72000 | 1724695 | 1724695 | 1010326184 | لا | 0 | 181109263357 | مسحوب | الكميات التي تم تركيبها | 65 | 100 | 2014-10-15 | 2017-03-19 | 2023-12-31 | 2023-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 44.0176 | 17.8465 | مسحوب | No
2100007416 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 46147681.99 | 2307384.0995 | 41729471.58 | 41729471.58 | 1010185409 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-07-17 | 2020-07-11 | 2021-08-03 | 2021-08-03 | 2020-07-11 |  | أوامر تغيير | أخرى |  |  | منجز | No
2200226155 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية عالية | 42851774 | 2142588.7 | 0 | 0 | 5855029073 | لا | 0 | 210901175579 | جاري | منهجية القيمة المكتسبة | 0 | 0 | 2022-06-01 | 2024-06-01 | 2024-06-01 | 2024-06-01 |  |  |  |  | 42.5117 | 18.2465 | منتظم | No
2100013311 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2315191.4 | 115759.57 | 2311905.4 | 0 | 1131026032 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-12-19 | 2018-12-03 | 2018-12-03 | 2018-12-03 | 2018-12-03 |  |  |  | 44.9442 | 26.4189 | منجز | Yes
2200235292 | الهيئة العامة للموانئ | تشييد | ذات اولوية عالية وعاجلة | 69290159 | 3464507.95 | 0 | 0 | 1010040445 | لا | 0 |  | جاري | تكلفة العمل المنجز | 1.5 | 1.5 | 2022-07-17 | 2024-07-06 | 2024-07-06 | 2024-07-06 |  |  |  |  | 42.5404 | 16.8873 | منتظم | No
2100035840 | مدينة الملك فهد الطبية | تشييد | ذات اولوية عالية | 57180021.23 | 2859001.0615 | 51326396.87 | 51326396.87 | 1010180118 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2012-09-30 | 2014-09-09 | 2021-12-30 | 2021-12-30 | 2014-09-09 |  | ضعف كفاءة المقاول الفنية |  | 46.702 | 24.686 | منجز | No
2100059662 | شركة المياه الوطنية / منطقة الجوف | تشييد | ذات اولوية عالية | 13895290 | 694764.5 | 3971345.25 | 3971345.25 | 5950004981 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 38.18 | 100 | 2010-12-26 | 2012-12-04 | 2023-07-28 | 2023-07-28 |  |  | ضعف كفاءة المقاول الفنية |  | 40.228 | 30.0096 | مسحوب | No
2100178415 | وزارة الثقافة | تشييد | ذات اولوية عالية | 41901461 | 2095073.05 | 52368.75 | 0 | 3350012131 | نعم | 3790124.75 | 201009228947 | مسحوب | منهجية القيمة المكتسبة | 3 | 100 | 2018-11-28 | 2019-12-18 | 2020-01-30 | 2020-01-30 |  |  | اخرى |  | 39.5774 | 24.4984 | مسحوب | Yes
2200235281 | وزارة الرياضة | توريد وتركيب | ذات اولوية عالية | 770385 | 38519.25 | 0 | 0 | 1010188861 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 20 | 20 | 2022-09-21 | 2023-03-20 | 2023-03-20 | 2023-03-20 |  |  |  |  | 50.0282 | 26.4889 | منتظم | No
2200226192 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية عالية | 16339421.74 | 816971.087 | 0 | 0 | 5860008190 | لا | 0 | 210901169644 | جاري | منهجية القيمة المكتسبة | 0 | 0 | 2022-06-05 | 2024-06-05 | 2024-06-05 | 2024-06-05 |  |  |  |  | 42.7662 | 18.3093 | منتظم | No
2100106061 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية متوسطة | 43940497.65 | 2197024.8825 | 16974668.93 | 14062769.26 | 1010067622 | لا | 0 | 190501063949 | جاري | منهجية القيمة المكتسبة | 80.05 | 100 | 2019-09-01 | 2022-03-01 | 2022-08-31 | 2022-08-31 |  |  | اخرى |  | 35.7296 | 27.3432 | متأخر | No
2100047994 | أمانة / الرياض | دراسة الجدوى | ذات اولوية متوسطة | 3063500 | 153175 | 0 | 0 | 1010415802 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2010-06-13 | 2012-06-02 | 2012-06-02 | 2012-06-02 | 2012-06-02 |  | اخرى |  |  |  | منجز | No
2100007685 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 13324034.72 | 666201.736 | 7956463.98 | 7956463.98 | 1010039430 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-11-26 | 2019-07-24 | 2019-12-06 | 2019-12-06 | 2019-07-24 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  |  |  | منجز | No
2100109174 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 6609742.89 | 330487.1445 | 2848289 | 2848289 | 1132000522 | لا | 0 |  | مسحوب | التكلفة المفوترة | 45 | 100 | 2010-10-02 | 2016-11-15 | 2023-05-17 | 2023-05-17 |  |  | ضعف كفاءة المقاول الفنية |  | 42.4987 | 18.2178 | مسحوب | No
2100103154 | شركة المياه الوطنية / منطقة جازان | إشراف | ذات اولوية عالية وعاجلة | 2916000 | 145800 | 2916000 | 2819703 | 1010314231 | لا | 0 |  | منجز – استلام نهائي | التكلفة المفوترة | 100 | 100 | 2015-03-19 | 2017-03-19 | 2017-03-19 | 2017-03-19 |  | 2017-03-19 | لا يوجد تأخير |  | 42.2736 | 17.7357 | منجز | No
2100087500 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 2600700 | 130035 | 2575377.6 | 2575377.6 | 1116008805 | لا | 0 | 181209469103 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 99.03 | 100 | 2016-05-02 | 2017-04-22 | 2020-01-18 | 2020-01-18 |  | 2017-04-22 | لا يوجد تأخير |  | 42.9095 | 23.8972 | منجز | No
2100021011 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية | 102099056 | 5104952.8 | 91325265.66 | 45931447.49 | 1010054406 | لا | 0 | 181109287491 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99.67 | 99.67 | 2010-05-17 | 2013-04-13 | 2020-01-08 | 2020-01-08 | 2013-04-13 |  | لا يوجد تأخير |  | 42.7694 | 17.0994 | منجز | No
2100105033 | المؤسسة العامة لتحلية المياه المالحة | تشييد | ذات اولوية عالية | 528729000 | 26436450 | 469958953.15 | 469958953.15 | 1010288154 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-02-12 | 2020-03-12 | 2020-03-12 | 2020-03-12 | 2020-03-12 |  | لا يوجد تأخير |  | 35.6643 | 27.3605 | منجز | No
2100108640 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية | 4840897.6 | 242044.88 | 2797376.76 | 2059819.16 | 1010235877 | نعم | 2914363.22 | 180709019689 | جاري | تكلفة العمل المنجز | 89 | 100 | 2018-02-02 | 2018-07-01 | 2024-12-31 | 2024-12-31 |  |  | تأخرصرف المستحقات المالية |  | 39.7177 | 24.4808 | متأخر | No
2100096515 | شركة المياه الوطنية / منطقة جازان | إشراف | ذات اولوية عالية وعاجلة | 5893800 | 294690 | 2230326 | 1690993.11 | 1010322156 | لا | 0 | 180901082949 | جاري | التكلفة المفوترة | 49.56 | 100 | 2018-09-25 | 2020-09-03 | 2022-07-31 | 2022-07-31 |  |  | لا يوجد تأخير |  | 42.5631 | 16.8842 | خدمات عامة | No
2100007221 | شركة المياه الوطنية / منطقة الباحة | إشراف | ذات اولوية عالية | 5199227 | 259961.35 | 8429424.81 | 7129687.06 | 1131052240 | لا | 0 | 180709022450 | جاري | التكلفة المفوترة | 100 | 100 | 2015-08-11 | 2018-08-11 | 2019-01-08 | 2019-01-08 |  |  | لا يوجد تأخير |  | 41.5856 | 19.8651 | خدمات عامة | No
2100066231 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 26949999 | 1347499.95 | 28306450 | 24952416 | 2051027318 | لا | 0 | 181009152766 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-08-02 | 2017-03-14 | 2021-02-07 | 2021-02-07 | 2017-03-14 |  |  |  | 50.0427 | 26.4165 | منجز | No
2100040180 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 8772828.99 | 438641.4495 | 7136045 | 7136045 | 1010183010 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-04-13 | 2016-04-02 | 2020-03-03 | 2020-03-03 | 2016-04-02 |  | ضعف كفاءة المقاول الفنية |  | 42.0529 | 18.5228 | منجز | No
2100103740 | وزارة التعليم | تشييد | ذات اولوية عالية | 10436372 | 521818.6 | 3928106.18 | 2916395.26 | 4030052981 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 30 | 100 | 2014-04-01 | 2016-03-20 | 2023-06-13 | 2023-06-13 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.5429 | 16.8808 | مسحوب | No
2100107763 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية | 41235912.77 | 2061795.6385 | 17043133.41 | 16003550.23 | 1010085001 | لا | 0 | 180709018076 | فسخ العقد | تكلفة العمل المنجز | 74 | 100 | 2014-04-07 | 2016-03-07 | 2025-12-31 | 2025-12-31 |  |  | تأخرصرف المستحقات المالية |  | 44.8525 | 26.3132 | مسحوب | No
2100023634 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 7291601.79 | 364580.0895 | 1010717.23 | 1010717.23 | 4030052981 | لا | 0 | 190409115708 | مسحوب | التكلفة المفوترة | 14 | 95 | 2018-10-29 | 2020-07-20 | 2023-06-08 | 2023-06-08 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | مسحوب | No
2100104230 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 8424558 | 421227.9 | 3148208.91 | 2532048.23 | 4030052981 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 38 | 100 | 2014-04-01 | 2016-03-20 | 2024-05-01 | 2024-05-01 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.5429 | 16.8808 | مسحوب | No
2100106595 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية وعاجلة | 8999992.4 | 449999.62 | 7979089.4 | 7979089.4 | 5855023504 | لا | 0 | 181201465757 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-02-03 | 2020-07-19 | 2020-12-29 | 2020-12-29 | 2020-07-19 |  | لا يوجد تأخير |  | 42.6535 | 17.0645 | منجز | No
2100059566 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية عالية | 21325830 | 1066291.5 | 18119214.53 | 16455543.09 | 4030159820 | لا | 0 | 190204404781 | جاري | منهجية القيمة المكتسبة | 86 | 92.38 | 2019-02-07 | 2022-01-05 | 2022-09-08 | 2022-09-08 |  |  | اخرى |  | 42.4989 | 18.2169 | متأخر | No
2100191026 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية وعاجلة | 6619935 | 330996.75 | 5212618 | 5212618 | 2050060814 | لا | 0 | 200701109980 | جاري | منهجية القيمة المكتسبة | 80.5 | 100 | 2020-09-02 | 2022-02-24 | 2022-11-01 | 2022-11-01 |  |  |  |  | 42.5544 | 17.1703 | Failed | No
2100108522 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 163353918.21 | 8167695.9105 | 159799863.43 | 159799863.43 | 1010329341 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-12-30 | 2019-12-30 | 2020-03-29 | 2020-03-29 | 2019-12-30 |  | منازعات قائمة | أخرى |  |  | منجز | No
2100043131 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 1738205 | 86910.25 | 251860 | 251860 | 5855018218 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 18 | 100 | 2015-07-28 | 2016-06-12 | 2022-11-23 | 2022-11-23 |  |  | ضعف كفاءة المقاول الفنية |  | 42.0529 | 18.5228 | مسحوب | No
2100106256 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية منخفضة | 9200000 | 460000 | 3160071.22 | 3160071.22 | 1131003889 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 98.53 | 100 | 2019-01-09 | 2020-06-24 | 2020-06-22 | 2020-06-22 |  | 2020-06-24 | لا يوجد تأخير |  | 36.0956 | 28.9012 | منجز | No
2200226166 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية عالية | 34314023.8 | 1715701.19 | 0 | 0 | 4031045263 | لا | 0 | 210801210294 | جاري | منهجية القيمة المكتسبة | 0 | 0 | 2022-06-12 | 2024-06-12 | 2024-06-12 | 2024-06-12 |  |  |  |  | 41.9296 | 18.9305 | منتظم | No
2100057606 | شركة المياه الوطنية / منطقة الحدود الشمالية | إشراف | ذات اولوية عالية | 8408000 | 420400 | 8375483.87 | 8375483.87 | 1010367378 | لا | 0 | 180709026188 | منجز – استلام ابتدائي | التكلفة المفوترة | 99.1 | 100 | 2014-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 | 2017-09-09 |  | لا يوجد تأخير |  | 41.0392 | 30.9665 | منجز | No
2200235314 | المؤسسة العامة للري | تشييد | ذات اولوية متوسطة | 3616674.1 | 180833.705 | 1217656.8 | 1217656.8 | 2050030952 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 78.3 | 29.4 | 2022-05-10 | 2023-03-09 | 2023-03-09 | 2023-03-09 |  |  |  |  | 50.0185 | 26.5198 | منتظم | No
2100088395 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 104070231 | 5203511.55 | 102192029.23 | 102192029.23 | 1010185409 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-12-30 | 2019-12-30 | 2020-05-28 | 2020-05-28 | 2019-12-30 |  | منازعات قائمة | أخرى |  |  | منجز | No
2200218105 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 59198345.3 | 2959917.265 | 7571916.39 | 7571916.39 | 1010127437 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 32 | 63 | 2021-12-22 | 2023-03-18 | 2023-08-02 | 2023-08-02 |  |  |  |  | 41.1 | 30.988 | Failed | No
2100109874 | شركة المياه الوطنية / منطقة الحدود الشمالية | تشييد | ذات اولوية عالية | 9491450 | 474572.5 | 8110757.72 | 8110757.72 | 1010187292 | لا | 0 | 180709023847 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2015-01-26 | 2017-01-04 | 2020-06-07 | 2020-06-07 |  | 2017-01-04 | لا يوجد تأخير |  | 44.7385 | 28.8838 | منجز | No
2200226203 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية عالية | 31919788.19 | 1595989.4095 | 0 | 0 | 5850031989 | لا | 0 | 210901075098 | جاري | منهجية القيمة المكتسبة | 0 | 0 | 2022-06-01 | 2023-12-02 | 2023-12-02 | 2023-12-02 |  |  |  |  | 42.5117 | 18.2465 | منتظم | No
2100089865 | وكالة / الإسكان | تشييد | ذات اولوية متوسطة | 23684713.66 | 1184235.683 | 23684713.66 | 23684713.66 | 1010210667 | لا | 0 |  | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-11-01 | 2018-11-01 | 2022-12-31 | 2022-12-31 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ | أخرى |  |  | Failed | No
2100069112 | أمانة / جدة | تشييد | ذات اولوية عالية | 66000060 | 3300003 | 66505804 | 66505804 | 4030131371 | لا | 0 | 190701073363 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 98.86 | 100 | 2019-09-29 | 2021-09-15 | 2021-12-14 | 2021-12-14 | 2021-09-15 |  | اخرى |  | 39.187 | 21.5004 | منجز | No
2100027274 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2700000 | 135000 | 2238375.6 | 2238375.6 | 1010191831 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 85 | 100 | 2010-01-16 | 2011-04-10 | 2023-02-03 | 2023-02-03 |  |  | ضعف كفاءة المقاول الفنية |  | 42.4987 | 18.2178 | مسحوب | No
2200235340 | جامعة جدة | تشييد | ذات اولوية عالية وعاجلة | 699996.42 | 34999.821 | 0 | 0 | 4030168618 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2022-07-28 | 2022-09-25 | 2022-10-16 | 2022-10-16 | 2022-09-25 |  |  |  | 39.1808 | 21.5799 | منجز | No
2100097344 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 135486789.9 | 6774339.495 | 112780382.8 | 112780382.8 | 4030007856 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99.2 | 100 | 2016-11-29 | 2018-05-15 | 2020-12-20 | 2020-12-20 | 2018-05-15 |  | لا يوجد تأخير |  | 40.4613 | 21.3728 | منجز | No
2100080065 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 35812233.21 | 1790611.6605 | 29305709.3 | 29305709.3 | 2055008173 | لا | 0 | 180809046050 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 99.88 | 100 | 2011-03-30 | 2013-09-01 | 2020-09-01 | 2020-09-01 |  | 2013-09-01 | لا يوجد تأخير |  | 48.4959 | 27.4692 | منجز | No
2100001094 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 21172662 | 1058633.1 | 7746194.8 | 7746194.8 | 1010066115 | لا | 0 |  | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-12-26 | 2019-08-23 | 2022-12-31 | 2022-12-31 |  |  | أوامر تغيير | أخرى |  |  | Failed | No
2100020565 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية وعاجلة | 129143044 | 6457152.2 | 95704171.14 | 95704171.14 | 2050018730 | لا | 0 | 180809041219 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 92.97 | 99.45 | 2013-06-24 | 2016-05-22 | 2020-12-30 | 2020-12-30 | 2016-05-22 |  | لا يوجد تأخير |  | 42.5429 | 16.8808 | منجز | No
2100003522 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 19412520.93 | 970626.0465 | 7750261.17 | 7750261.17 | 4030123131 | لا | 0 | 190309007345 | جاري | تكلفة العمل المنجز | 43 | 70 | 2019-02-03 | 2020-01-23 | 2023-12-31 | 2023-12-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.1677 | 21.5008 | Failed | No
2200229213 | الجمارك السعودية | تشييد | ذات اولوية عالية | 5347800 | 267390 | 4019878.84 | 4019878.84 | 1010464297 | لا | 0 |  | جاري | تكلفة العمل المنجز | 80 | 100 | 2022-01-19 | 2023-02-18 | 2023-05-21 | 2023-05-21 |  |  |  |  | 50.7237 | 24.7724 | متأخر | No
2100010684 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 126272205.73 | 6313610.2865 | 76085745.27 | 76085745.27 | 5855000147 | لا | 0 |  | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-10-18 | 2019-10-08 | 2022-12-31 | 2022-12-31 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ | أخرى |  |  | Failed | No
2100062101 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 46705208.15 | 2335260.4075 | 40829427.35 | 40829427.35 | 1010076961 | لا | 0 | 180709032091 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2015-10-25 | 2018-09-22 | 2020-08-30 | 2020-08-30 | 2018-09-22 |  | لا يوجد تأخير |  | 46.037 | 28.5074 | منجز | No
2100106536 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية عالية | 29986060 | 1499303 | 26847017.82 | 26847017.82 | 5855029073 | لا | 0 | 190301031590 | جاري | منهجية القيمة المكتسبة | 100 | 99.99 | 2019-05-29 | 2021-10-30 | 2022-07-17 | 2022-07-17 |  |  | لا يوجد تأخير |  | 42.4989 | 18.2169 | منتظم | No
2100061526 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية منخفضة | 3666950 | 183347.5 | 0 | 0 | 1010156161 | لا | 0 | 181001161045 | مسحوب | منهجية القيمة المكتسبة | 0.57 | 100 | 2018-09-06 | 2019-11-23 | 2023-07-30 | 2023-07-30 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 50.0476 | 26.696 | مسحوب | No
2100043304 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 25892947.5 | 1294647.375 | 19447947.5 | 19447947.5 | 1010012911 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 83.04 | 100 | 2018-02-19 | 2020-01-28 | 2020-07-27 | 2020-07-27 | 2020-01-28 |  | لا يوجد تأخير |  | 40.9811 | 21.4546 | منجز | No
2100061751 | شركة المياه الوطنية / منطقة الحدود الشمالية | تشييد | ذات اولوية عالية | 85965911.3 | 4298295.565 | 58776352.64 | 58776352.64 | 1010317283 | لا | 0 | 180709025855 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 99.96 | 100 | 2014-09-09 | 2017-08-06 | 2020-08-30 | 2020-08-30 |  | 2017-08-06 | لا يوجد تأخير |  | 41.0425 | 30.9628 | منجز | No
2100191892 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 31092700 | 1554635 | 10346483.8 | 10346483.8 | 5855021168 | لا | 0 | 200501021276 | جاري | منهجية القيمة المكتسبة | 43.91 | 43.91 | 2021-01-20 | 2022-12-31 | 2022-12-31 | 2022-12-31 |  |  |  |  | 40.2938 | 20.1387 | منتظم | No
2100106772 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 89652076.62 | 4482603.831 | 31872847.07 | 30363521.89 | 1010034808 | لا | 0 | 180709017534 | ايقاف كلي | تكلفة العمل المنجز | 63 | 100 | 2014-06-11 | 2016-11-27 | 2024-12-31 | 2024-12-31 |  |  | تأخرصرف المستحقات المالية |  | 43.0157 | 23.9852 | Failed | No
2100017054 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 12836640 | 641832 | 12714640 | 12714640 | 1010009590 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 99.04 | 100 | 2019-09-04 | 2020-12-04 | 2020-12-16 | 2020-12-16 |  | 2020-12-04 | لا يوجد تأخير |  | 46.7353 | 24.5836 | منجز | No
2100060631 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية وعاجلة | 63987950 | 3199397.5 | 46489475.33 | 46489474.33 | 5950005891 | لا | 0 | 180701017770 | جاري | منهجية القيمة المكتسبة | 90.95 | 100 | 2018-09-11 | 2021-08-09 | 2022-03-15 | 2022-03-15 |  |  | اخرى |  | 42.8481 | 16.9654 | متأخر | No
2100007604 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية عالية | 14410430 | 720521.5 | 12600711.35 | 12600711.35 | 5855007803 | لا | 0 | 180901088257 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 87 | 100 | 2018-09-11 | 2021-02-13 | 2021-06-29 | 2021-06-29 | 2021-02-13 |  | لا يوجد تأخير |  | 42.7302 | 18.3003 | منجز | No
2100010290 | وزارة الحرس الوطني / الشؤون الصحية | توريد وتركيب | ذات اولوية عالية | 8601802.13 | 430090.1065 | 8601802.11 | 8601802.11 | 1010207379 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-01-20 | 2020-08-20 | 2020-08-20 | 2020-08-20 | 2020-08-20 |  | ضعف كفاءة المقاول الفنية |  | 46.8771 | 24.7538 | منجز | No
2100000803 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 60000000 | 3000000 | 40778797.6 | 40778797.6 | 1010122914 | لا | 0 |  | ايقاف كلي | منهجية القيمة المكتسبة | 82.51 | 100 | 2018-08-13 | 2020-01-27 | 2022-12-31 | 2022-12-31 |  |  | لا يوجد تأخير |  | 40.2511 | 21.4546 | Failed | No
2100055274 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 98439812 | 4921990.6 | 51759708.72 | 47927292.22 | 1118000259 | لا | 0 | 180909074275 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99.87 | 100 | 2014-09-15 | 2017-02-17 | 2021-06-06 | 2021-06-06 | 2017-02-17 |  | ضعف كفاءة المقاول الفنية |  | 45.313 | 24.0763 | منجز | No
2100087356 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية | 19970528.55 | 998526.4275 | 16059989.79 | 16059989.79 | 5855010714 | لا | 0 | 180801040276 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 97.2 | 100 | 2018-09-11 | 2020-03-11 | 2022-03-31 | 2022-03-31 |  |  | تصاريح أعمال التنفيذ |  | 42.8149 | 17.6065 | Failed | No
2100068552 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية وعاجلة | 22368450 | 1118422.5 | 12641294 | 12352638.52 | 2050053367 | لا | 0 | 181201532661 | جاري | منهجية القيمة المكتسبة | 85.9 | 100 | 2019-07-01 | 2022-05-29 | 2022-07-02 | 2022-07-02 |  |  | اخرى |  | 41.7742 | 20.3059 | متأخر | No
2200226214 | شركة المياه الوطنية / منطقة عسير | إشراف | ذات اولوية عالية | 12146087 | 607304.35 | 0 | 0 | 2050101543 | لا | 0 | 211201137608 | جاري | التكلفة المفوترة | 2.15 | 0 | 2022-05-22 | 2024-05-21 | 2024-05-21 | 2024-05-21 |  |  |  |  | 42.5117 | 18.2465 | خدمات عامة | No
2200229261 | الجمارك السعودية | تشييد | ذات اولوية عالية | 5000000 | 250000 | 1758783.74 | 1758783.74 | 4031058260 | لا | 0 |  | جاري | تكلفة العمل المنجز | 98 | 100 | 2022-02-01 | 2022-07-31 | 2022-10-30 | 2022-10-30 |  |  |  |  | 37.1133 | 31.4792 | Failed | No
2100026740 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية وعاجلة | 9686534.42 | 484326.721 | 6517466.44 | 6517466.44 | 1010237447 | لا | 0 | 180709021230 | مسحوب | تكلفة العمل المنجز | 97 | 100 | 2013-11-01 | 2014-10-30 | 2024-12-31 | 2024-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 39.8193 | 21.2856 | مسحوب | No
2100056663 | شركة المياه الوطنية / منطقة الرياض | الخدمات الاستشارية | ذات اولوية عالية | 5821200 | 291060 | 5776338.57 | 5776338.57 | 1010321646 | لا | 0 |  | منجز – استلام نهائي | التكلفة المفوترة | 99.23 | 100 | 2019-02-03 | 2021-02-02 | 2021-10-23 | 2021-10-23 |  | 2021-02-02 | لا يوجد تأخير |  | 46.7946 | 24.6519 | منجز | No
2100012316 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية متوسطة | 13091605 | 654580.25 | 12370995.94 | 12370995.94 | 5850013780 | لا | 0 | 180901068719 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-09-18 | 2020-08-27 | 2020-11-18 | 2020-11-18 | 2020-08-27 |  | لا يوجد تأخير |  | 42.4989 | 18.2169 | منجز | No
2100079892 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 32686802.5 | 1634340.125 | 29663731.5 | 29663731.5 | 2050001536 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 98.84 | 100 | 2018-02-18 | 2020-02-18 | 2020-06-17 | 2020-06-17 |  | 2020-02-18 | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100055366 | وزارة الصحة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 736650 | 36832.5 | 736650 | 736650 | 1010219205 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-02-04 | 2019-05-03 | 2021-11-30 | 2021-11-30 | 2019-05-03 |  | تأخرصرف المستحقات المالية |  | 40.511 | 24.8706 | منجز | No
2200229272 | الجمارك السعودية | تشييد | ذات اولوية عالية | 6811363.4 | 340568.17 | 202779.5 | 202779.5 | 4031058260 | لا | 0 |  | جاري | تكلفة العمل المنجز | 54 | 100 | 2022-06-15 | 2022-09-14 | 2022-12-19 | 2022-12-19 |  |  |  |  | 50.7334 | 24.7184 | Failed | No
2100072914 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 77668049 | 3883402.45 | 68799847 | 68799847 | 3350002763 | لا | 0 | 181009132242 | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-01-20 | 2018-01-05 | 2023-02-06 | 2023-02-06 |  |  | أوامر تغيير |  | 41.7026 | 27.4939 | متأخر | No
2100040585 | شركة المياه الوطنية / منطقة حائل | إشراف | ذات اولوية عالية | 5878350 | 293917.5 | 15669904.58 | 15622629.58 | 2050101543 | لا | 0 | 180709028629 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-09-20 | 2016-09-20 | 2021-10-07 | 2021-10-07 | 2016-09-20 |  | لا يوجد تأخير |  | 40.4821 | 25.9852 | منجز | No
2100093365 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية متوسطة | 15657935 | 782896.75 | 15657925 | 15657925 | 5850031989 | لا | 0 | 190301022205 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-01-07 | 2020-06-22 | 2020-06-17 | 2020-06-17 |  | 2020-06-22 | لا يوجد تأخير |  | 42.4989 | 18.2169 | منجز | No
2200229283 | الجمارك السعودية | تشييد | ذات اولوية عالية | 4814000 | 240700 | 0 | 0 | 1010344765 | لا | 0 |  | جاري | تكلفة العمل المنجز | 29 | 100 | 2022-06-15 | 2023-06-14 | 2023-09-15 | 2023-09-15 |  |  |  |  | 47.1503 | 16.9778 | Failed | No
2100053583 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 38364800 | 1918240 | 36737019.72 | 36737019.72 | 4030159820 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2013-09-25 | 2015-09-03 | 2018-11-29 | 2018-11-29 | 2015-09-03 | 2020-06-16 |  |  | 39.8661 | 21.322 | منجز | No
2100097985 | جامعة طيبة | تشييد | ذات اولوية عالية | 80764408.64 | 4038220.432 | 30516691.77 | 29427672.63 | 1010306708 | لا | 0 | 181109377282 | جاري | تكلفة العمل المنجز | 34.84 | 78.74 | 2015-02-26 | 2017-07-31 | 2024-02-24 | 2024-02-24 |  |  | تأخرصرف المستحقات المالية | تم إشعار المقاول كتابيا بالتأخير | 39.6005 | 24.4595 | Failed | No
2100085794 | شركة المياه الوطنية / منطقة عسير | إشراف | ذات اولوية عالية | 2117000 | 105850 | 2064675 | 2064675 | 2050099301 | لا | 0 | 180701016720 | جاري | التكلفة المفوترة | 96.3 | 100 | 2018-07-11 | 2021-07-11 | 2022-06-25 | 2022-06-25 |  |  | لا يوجد تأخير |  | 42.2908 | 18.2013 | خدمات عامة | No
2100022890 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية | 5143877 | 257193.85 | 4635440 | 3126870 | 1010247322 | لا | 0 | 181001200126 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-11-19 | 2020-05-04 | 2020-03-15 | 2020-03-15 | 2020-05-04 |  | لا يوجد تأخير |  | 42.5429 | 16.8808 | منجز | No
2200229294 | الجمارك السعودية | تشييد | ذات اولوية عالية | 3000000 | 150000 | 1234097.5 | 1234097.5 | 4031193415 | لا | 0 |  | جاري | تكلفة العمل المنجز | 97 | 100 | 2022-01-16 | 2022-05-21 | 2022-07-15 | 2022-07-15 |  |  |  |  | 34.9666 | 29.3597 | Failed | No
2100105571 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 55542429.92 | 2777121.496 | 33997487.12 | 30537861.74 | 1010145283 | لا | 0 | 180709020977 | ايقاف كلي | تكلفة العمل المنجز | 82 | 100 | 2014-10-20 | 2016-09-19 | 2024-12-31 | 2024-12-31 |  |  | تأخرصرف المستحقات المالية |  | 37.3101 | 31.3926 | Failed | No
2100048274 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 2478645 | 123932.25 | 1294352 | 1294352 | 4030182654 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 50 | 100 | 2014-12-10 | 2019-02-18 | 2019-02-19 | 2019-02-19 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.7397 | 23.0098 | مسحوب | No
2200229386 | أمانة / جدة | تشييد | ذات اولوية عالية | 24431365 | 1221568.25 | 6116491.8 | 6116491.8 | 2051030949 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 71 | 86 | 2021-12-01 | 2023-05-16 | 2023-05-16 | 2023-05-16 |  |  |  |  | 39.1925 | 21.4858 | متأخر | No
2100022912 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 82483295.18 | 4124164.759 | 22254035.12 | 22254035.12 | 4030172446 | لا | 0 | 180709019869 | مسحوب | تكلفة العمل المنجز | 38 | 100 | 2014-05-27 | 2016-11-12 | 2026-12-31 | 2026-12-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 40.5413 | 21.3159 | مسحوب | No
2100097370 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 72949500 | 3647475 | 45608516.8 | 45608516.8 | 1010026934 | لا | 0 |  | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 78.5 | 100 | 2020-02-06 | 2022-01-15 | 2022-03-26 | 2022-03-26 |  |  | اخرى |  | 39.2748 | 21.4514 | متأخر | No
2100038846 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 33193480 | 1659674 | 33173104.83 | 29473235.26 | 1131014852 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-06-17 | 2020-12-18 | 2020-06-01 | 2020-06-01 |  | 2020-12-18 | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100191903 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 68943145 | 3447157.25 | 7244900 | 7244900 | 5851002147 | لا | 0 | 2200006104 | جاري | منهجية القيمة المكتسبة | 19.1 | 73.66 | 2020-07-01 | 2022-12-04 | 2023-08-27 | 2023-08-27 |  |  |  |  | 41.1138 | 19.1433 | Failed | No
2100191822 | شركة المياه الوطنية / منطقة حائل | دراسة بيئية | ذات اولوية عالية | 720000 | 36000 | 524700 | 524700 | 1010314421 | لا | 0 | 190301055248 | ايقاف جزئي | التكلفة المفوترة | 72.88 | 100 | 2019-01-15 | 2020-01-15 | 2022-06-01 | 2022-06-01 |  |  |  |  | 41.7452 | 27.4474 | Failed | No
2100003850 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 175133105.52 | 8756655.276 | 32116152.53 | 22904591.92 | 1010059275 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 18 | 100 | 2013-02-01 | 2015-07-21 | 2025-12-31 | 2025-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 48.4541 | 28.3702 | مسحوب | No
2200220990 | شركة المياه الوطنية / منطقة مكة المكرمة | تصميم وتشييد | ذات اولوية عالية وعاجلة | 16610850 | 830542.5 | 3659624.42 | 2523653.91 | 2051044264 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 32.63 | 50.31 | 2021-12-14 | 2022-12-15 | 2022-12-15 | 2022-12-15 |  |  |  |  | 40.6263 | 21.5063 | متأخر | No
2100015886 | شركة المياه الوطنية / منطقة عسير | إشراف | ذات اولوية عالية | 6036000 | 301800 | 4726160 | 4726160 | 4030283265 | لا | 0 | 180801062534 | منجز – استلام ابتدائي | التكلفة المفوترة | 76.27 | 100 | 2018-09-06 | 2020-08-16 | 2020-08-16 | 2020-08-16 | 2020-08-16 |  | لا يوجد تأخير |  | 43.4278 | 19.5738 | منجز | No
2100025933 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية عالية | 28530000 | 1426500 | 20093284 | 20093284 | 1010066115 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2013-11-10 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2017-01-07 | 2020-11-16 |  |  | 41.5317 | 18.2332 | منجز | No
2200229305 | الجمارك السعودية | تشييد | ذات اولوية عالية | 16858591.75 | 842929.5875 | 1137800.7 | 1137800.7 | 2055002705 | لا | 0 |  | جاري | تكلفة العمل المنجز | 66 | 100 | 2022-01-16 | 2022-09-15 | 2022-12-14 | 2022-12-14 |  |  |  |  | 48.4596 | 28.4207 | Failed | No
2100088071 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 10161441.2 | 508072.06 | 5728443.38 | 5728443.38 | 5855005104 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 85 | 100 | 2015-03-12 | 2017-03-01 | 2022-04-15 | 2022-04-15 | 2017-03-01 |  | ضعف كفاءة المقاول الفنية |  | 42.4987 | 18.2178 | منجز | No
2100020705 | شركة المياه الوطنية / منطقة جازان | إشراف | ذات اولوية عالية وعاجلة | 2640000 | 132000 | 2640000 | 2198547.58 | 1010348048 | لا | 0 | 181109287456 | منجز – استلام نهائي | التكلفة المفوترة | 100 | 100 | 2018-03-04 | 2019-03-03 | 2022-06-30 | 2022-06-30 |  | 2019-03-03 | لا يوجد تأخير |  | 42.625 | 17.5925 | منجز | No
2100108603 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية عالية | 11888255 | 594412.75 | 11866483.24 | 11866483.24 | 5855029900 | لا | 0 | 190301018961 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-04-14 | 2021-09-16 | 2021-10-31 | 2021-10-31 | 2021-09-16 |  | لا يوجد تأخير |  | 42.7302 | 18.3003 | منجز | No
2100005316 | شركة المياه الوطنية / منطقة تبوك | إشراف | ذات اولوية عالية وعاجلة | 7992000 | 399600 | 7593207.06 | 7422369.06 | 1010322448 | لا | 0 | 190201045970 | جاري | التكلفة المفوترة | 92.87 | 94.44 | 2019-09-01 | 2022-08-31 | 2022-10-31 | 2022-10-31 |  |  | لا يوجد تأخير |  | 36.5577 | 28.3859 | خدمات عامة | No
2100098125 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية | 85115795.8 | 4255789.79 | 70339690.8 | 59934840.27 | 5907008656 | لا | 0 | 180809056645 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 98.5 | 99.08 | 2012-02-20 | 2015-01-19 | 2021-06-13 | 2021-06-13 | 2015-01-19 |  | لا يوجد تأخير |  | 42.1125 | 16.695 | منجز | No
2200229320 | الجمارك السعودية | تشييد | ذات اولوية عالية | 9635000 | 481750 | 1018440 | 1018440 | 1010093247 | لا | 0 |  | جاري | تكلفة العمل المنجز | 91 | 100 | 2022-02-01 | 2022-06-02 | 2022-09-02 | 2022-09-02 |  |  |  |  | 37.1273 | 31.4911 | Failed | No
2200229316 | الجمارك السعودية | تشييد | ذات اولوية عالية | 36005442 | 1800272.1 | 2475510.88 | 2475510.88 | 1010147422 | لا | 0 |  | جاري | تكلفة العمل المنجز | 44 | 100 | 2022-05-10 | 2023-03-10 | 2023-06-14 | 2023-06-14 |  |  |  |  | 51.5119 | 24.1003 | Failed | No
2100023494 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية عالية وعاجلة | 53310431 | 2665521.55 | 20955899.31 | 20955899.31 | 1010166750 | لا | 0 |  | مسحوب | منهجية القيمة المكتسبة | 33.45 | 100 | 2012-02-11 | 2015-01-10 | 2022-12-31 | 2022-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 36.597 | 26.1013 | مسحوب | No
2100019633 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية متوسطة | 31400000 | 1570000 | 31398441.04 | 31398441.04 | 1010139922 | لا | 0 | 190701152272 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-10-16 | 2020-10-04 | 2020-10-04 | 2020-10-04 | 2020-10-04 |  | لا يوجد تأخير |  | 43.526 | 19.539 | منجز | No
2100104145 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية وعاجلة | 4839000 | 241950 | 4230060 | 4230060 | 2050060814 | لا | 0 | 180709023373 | ايقاف كلي | منهجية القيمة المكتسبة | 84 | 100 | 2015-08-16 | 2016-08-04 | 2022-09-30 | 2022-09-30 |  |  | تصاريح أعمال التنفيذ |  | 42.6801 | 16.7872 | Failed | No
2100004351 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية متوسطة | 28088979.5 | 1404448.975 | 22679018.51 | 21850783.61 | 1163002582 | لا | 0 | 180909107298 | جاري | منهجية القيمة المكتسبة | 85.61 | 100 | 2018-03-07 | 2021-02-01 | 2022-12-31 | 2022-12-31 |  |  | لا يوجد تأخير |  | 35.682 | 27.3526 | Failed | No
2100010570 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 5779952 | 288997.6 | 0 | 0 | 1010466292 | لا | 0 |  | جاري | التكلفة المفوترة | 1 | 100 | 2012-05-22 | 2013-11-13 | 2023-06-15 | 2023-06-15 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | Failed | No
2100001072 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 83927973.07 | 4196398.6535 | 21228714.76 | 20623229.96 | 1010034808 | لا | 0 | 180709020181 | ايقاف كلي | تكلفة العمل المنجز | 38 | 100 | 2014-08-25 | 2017-02-10 | 2026-12-31 | 2026-12-31 |  |  | تأخرصرف المستحقات المالية |  | 39.013 | 22.8435 | Failed | No
2100079800 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية عالية وعاجلة | 12999525 | 649976.25 | 11492215 | 11492215 | 5860008190 | لا | 0 | 190301019299 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-04-01 | 2021-03-08 | 2022-03-14 | 2022-03-14 | 2021-03-08 |  | أوامر سامية |  | 42.276 | 18.2348 | منجز | No
2200229342 | الجمارك السعودية | تشييد | ذات اولوية عالية | 3220000 | 161000 | 444057 | 444057 | 5911014153 | لا | 0 |  | جاري | تكلفة العمل المنجز | 90 | 100 | 2022-03-30 | 2023-01-30 | 2023-03-30 | 2023-03-30 |  |  |  |  | 50.7884 | 24.7284 | متأخر | No
2200235410 | جامعة شقراء | تشييد | ذات اولوية عالية | 6324632 | 316231.6 | 0 | 0 | 1113001164 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 8 | 8 | 2022-07-24 | 2023-03-21 | 2023-04-23 | 2023-04-23 |  |  |  |  | 45.2358 | 25.2116 | منتظم | No
2100012084 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية وعاجلة | 4008091.5 | 200404.575 | 3340053.3 | 3340053.3 | 1010287764 | نعم | 1365938.55 | 181109295525 | جاري | تكلفة العمل المنجز | 95 | 100 | 2018-09-27 | 2019-09-11 | 2023-12-31 | 2023-12-31 |  |  | تأخرصرف المستحقات المالية |  | 39.7168 | 24.4807 | متأخر | No
2100021722 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية | 80371085.54 | 4018554.277 | 29494859.13 | 29494859.13 | 2050040480 | لا | 0 | 180709022009 | جاري | تكلفة العمل المنجز | 56 | 100 | 2014-05-14 | 2016-10-30 | 2025-12-31 | 2025-12-31 |  |  | تأخرصرف المستحقات المالية |  | 49.989 | 26.1292 | Failed | No
2100033084 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية متوسطة | 28610444.83 | 1430522.2415 | 13162391.08 | 13162391.08 | 4650015928 | لا | 0 | 180909073077 | جاري | منهجية القيمة المكتسبة | 83.77 | 99.85 | 2011-12-13 | 2013-11-21 | 2023-05-16 | 2023-05-16 |  |  | لا يوجد تأخير |  | 36.5077 | 26.1742 | Failed | No
2100088690 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 11191044.23 | 559552.2115 | 6049152.46 | 0 | 3350003498 | لا | 0 |  | جاري | التكلفة المفوترة | 69 | 100 | 2013-03-22 | 2015-03-12 | 2021-12-15 | 2021-12-15 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | Failed | Yes
2200229390 | أمانة / جدة | تشييد | ذات اولوية عالية وعاجلة | 27618101 | 1380905.05 | 14477725.5 | 14477725.5 | 2050018628 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 83 | 100 | 2021-10-18 | 2022-07-25 | 2022-05-22 | 2022-05-22 | 2022-07-25 |  |  |  | 39.1925 | 21.4858 | منجز | No
2100074701 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 75215150.14 | 3760757.507 | 23358082.13 | 22006322.02 | 4031041927 | لا | 0 | 180709021147 | ايقاف كلي | تكلفة العمل المنجز | 66 | 100 | 2014-06-02 | 2016-11-18 | 2025-12-31 | 2025-12-31 |  |  | تأخرصرف المستحقات المالية |  | 39.9882 | 21.5471 | Failed | No
2100103526 | شركة المياه الوطنية / منطقة جازان | إشراف | ذات اولوية عالية وعاجلة | 9900000 | 495000 | 9900000 | 9900000 | 4030181473 | لا | 0 | 180709021035 | جاري | التكلفة المفوترة | 100 | 100 | 2015-05-28 | 2018-05-27 | 2022-03-31 | 2022-03-31 |  |  | لا يوجد تأخير |  | 42.4334 | 17.3343 | خدمات عامة | No
2100003975 | جامعة الملك خالد | تشييد | ذات اولوية عالية وعاجلة | 103538470.42 | 5176923.521 | 92000057.7 | 92000057.7 | 1010010506 | لا | 0 | 181009152160 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2017-05-11 | 2021-09-21 | 2022-07-24 | 2022-07-24 |  |  | تأخرصرف المستحقات المالية |  | 42.8114 | 18.1027 | متأخر | No
2100050982 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 2097320 | 104866 | 1509375 | 1509375 | 2060033083 | لا | 0 | 190309013811 | فسخ العقد | تكلفة العمل المنجز | 80 | 100 | 2015-06-23 | 2015-12-21 | 2015-12-21 | 2015-12-21 |  |  | تأخرصرف المستحقات المالية |  | 50.2127 | 25.6531 | مسحوب | No
2100037122 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية | 61009726.9 | 3050486.345 | 20757832.27 | 17924293.42 | 4031038849 | نعم | 35368557.57 | 180501008496 | ايقاف كلي | تكلفة العمل المنجز | 51 | 100 | 2018-10-02 | 2020-05-22 | 2026-12-31 | 2026-12-31 |  |  | تأخرصرف المستحقات المالية |  | 41.19 | 19.0853 | Failed | No
2100066356 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 29289849 | 1464492.45 | 28748456.85 | 28748456.85 | 4030170755 | لا | 0 | 181109342396 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 94.21 | 100 | 2015-03-19 | 2016-06-01 | 2020-06-29 | 2020-06-29 | 2016-06-01 |  | أوامر تغيير |  | 39.0278 | 22.784 | منجز | No
2100104436 | شركة المياه الوطنية / منطقة الحدود الشمالية | تشييد | ذات اولوية عالية | 24000000 | 1200000 | 23579333.11 | 21221689.44 | 1116002219 | لا | 0 | 180901073272 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 98.25 | 100 | 2018-11-07 | 2020-10-16 | 2021-06-09 | 2021-06-09 | 2020-10-16 |  | لا يوجد تأخير |  | 41.031 | 30.953 | منجز | No
2100056954 | شركة المياه الوطنية / منطقة الحدود الشمالية | إشراف | ذات اولوية عالية | 5093000 | 254650 | 4959700 | 4959700 | 1010326073 | لا | 0 | 181009201131 | منجز – استلام ابتدائي | التكلفة المفوترة | 98.8 | 100 | 2015-05-21 | 2017-11-21 | 2020-06-19 | 2020-06-19 | 2017-11-21 |  | لا يوجد تأخير |  | 43.5228 | 29.6273 | منجز | No
2100106293 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 22381409.57 | 1119070.4785 | 22381409.58 | 22381409.58 | 2051030949 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-02-18 | 2019-08-03 | 2019-07-31 | 2019-07-31 |  | 2019-08-03 | لا يوجد تأخير |  | 39.132 | 21.5503 | منجز | No
2100105965 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية متوسطة | 13557350 | 677867.5 | 4849028.3 | 4849028.3 | 1134003368 | لا | 0 | 180401002766 | جاري | منهجية القيمة المكتسبة | 65.83 | 100 | 2018-10-16 | 2021-09-14 | 2022-07-31 | 2022-07-31 |  |  | لا يوجد تأخير |  | 37.2862 | 24.9823 | Failed | No
2100074281 | وزارة الحرس الوطني / الشؤون الصحية | تشييد | ذات اولوية عالية | 54251434 | 2712571.7 | 29979239.21 | 29979239.21 | 1010052129 | لا | 0 | 181209462384 | جاري | الكميات التي تم تركيبها | 95 | 100 | 2009-11-03 | 2011-04-23 | 2023-03-30 | 2023-03-30 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5279 | 25.4582 | Failed | No
2100058100 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 2616488 | 130824.4 | 537543.8 | 537543.8 | 1010180774 | لا | 0 | 191201147242 | ايقاف كلي | تكلفة العمل المنجز | 25 | 100 | 2019-08-28 | 2020-08-22 | 2024-12-31 | 2024-12-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 43.1533 | 18.0358 | Failed | No
2100006716 | وزارة الحرس الوطني / الشؤون الصحية | تشييد | ذات اولوية عالية | 10091245 | 504562.25 | 6492102.31 | 6492102.31 | 1010251358 | لا | 0 | 181009154502 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2011-05-10 | 2013-06-30 | 2020-08-18 | 2020-08-18 | 2013-06-30 |  | ضعف كفاءة المقاول الفنية |  | 46.858 | 24.7442 | منجز | No
2200229423 | أمانة / جدة | تشييد | ذات اولوية عالية | 25150500 | 1257525 | 14695618.6 | 14695618.6 | 1128003753 | لا | 0 | 211201031145 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 86.9 | 100 | 2021-10-25 | 2022-05-30 | 2022-05-21 | 2022-05-21 | 2022-05-30 |  |  |  | 39.1925 | 21.4858 | منجز | No
2100008002 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية عالية | 35747724 | 1787386.2 | 23925760.34 | 23925760.34 | 1010136405 | لا | 0 | 181209442588 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 94.5 | 100 | 2006-06-25 | 2008-11-27 | 2022-04-30 | 2022-04-30 |  |  | لا يوجد تأخير |  | 36.501 | 26.1851 | Failed | No
2100190772 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 4257752.38 | 212887.619 | 3287126.13 | 3287126.13 | 1010276827 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 85 | 100 | 2019-12-25 | 2020-06-20 | 2020-06-23 | 2020-06-23 | 2020-06-20 |  |  |  | 40.4517 | 21.3169 | منجز | No
2100093881 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية متوسطة | 20935784 | 1046789.2 | 15679851.62 | 15679851.62 | 1010010466 | لا | 0 | 180909077117 | ايقاف كلي | منهجية القيمة المكتسبة | 80.1 | 98.4 | 2010-01-31 | 2011-07-17 | 2022-12-31 | 2022-12-31 |  |  | لا يوجد تأخير |  | 37.2558 | 25.1794 | Failed | No
2100103471 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 3337521.7 | 166876.085 | 168980 | 168980 | 1010233819 | لا | 0 | 190909165888 | مسحوب | التكلفة المفوترة | 7 | 100 | 2015-12-24 | 2016-12-18 | 2019-01-10 | 2019-01-10 |  |  | ضعف كفاءة المقاول الفنية |  | 40.0549 | 29.8587 | مسحوب | No
2100090764 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 17436058 | 871802.9 | 14085531.6 | 14085531.6 | 1011008214 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-03-11 | 2016-10-26 | 2021-05-02 | 2021-05-02 | 2016-10-26 |  | ضعف كفاءة المقاول الفنية |  | 37.9283 | 26.6042 | منجز | No
2100060141 | المؤسسة العامة للحبوب | تشييد | ذات اولوية عالية | 552510 | 27625.5 | 497259 | 497259 | 1111111111 | لا | 0 | 200801102558 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2020-01-26 | 2020-08-07 | 2020-08-07 | 2020-08-07 | 2020-08-07 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 49.599 | 25.54 | منجز | No
2100059710 | جامعة الملك خالد | تشييد | ذات اولوية عالية وعاجلة | 48585313.73 | 2429265.6865 | 48518239.72 | 48518239.72 | 2050004344 | لا | 0 | 180709035420 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-02-13 | 2019-02-02 | 2022-07-08 | 2022-07-08 |  |  | تأخرصرف المستحقات المالية |  | 42.8114 | 18.0836 | متأخر | No
2200229445 | أمانة / جدة | تشييد | ذات اولوية عالية وعاجلة | 23337133 | 1166856.65 | 1060828.365 | 0 | 4030013052 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 14 | 100 | 2021-12-23 | 2022-09-04 | 2022-09-04 | 2022-09-04 |  |  |  |  | 39.1925 | 21.4858 | Failed | Yes
2200229434 | أمانة / جدة | جيوتقنية | ذات اولوية عالية | 6762000 | 338100 | 4508000 | 4507999 | 1010103058 | لا | 0 | 210401075858 | جاري | تكلفة العمل المنجز | 58 | 60 | 2021-07-11 | 2023-06-19 | 2023-06-19 | 2023-06-19 |  |  |  |  | 39.1677 | 21.5007 | خدمات عامة | No
2100001050 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 85405000 | 4270250 | 63524051.9 | 63524051.9 | 1010012911 | لا | 0 |  | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 85.34 | 100 | 2018-11-01 | 2020-04-16 | 2022-12-31 | 2022-12-31 |  |  | لا يوجد تأخير |  | 40.4455 | 21.2754 | Failed | No
2100011001 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية وعاجلة | 71860063 | 3593003.15 | 57688352 | 57688352 | 2050018730 | لا | 0 | 180809054531 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99.6 | 100 | 2017-03-20 | 2018-03-09 | 2021-06-29 | 2021-06-29 | 2018-03-09 |  | لا يوجد تأخير |  | 42.5241 | 17.3714 | منجز | No
2100064271 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 20400585.92 | 1020029.296 | 130196 | 130196 | 1010178798 | لا | 0 |  | مسحوب | التكلفة المفوترة | 4 | 30 | 2015-04-23 | 2017-10-08 | 2021-10-27 | 2021-10-27 |  |  | ضعف كفاءة المقاول الفنية |  | 38.0524 | 24.1071 | مسحوب | No
2100107575 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية | 116918080 | 5845904 | 27493093.23 | 26585247.86 | 1010034808 | لا | 0 | 180709021245 | ايقاف كلي | تكلفة العمل المنجز | 40 | 100 | 2014-05-21 | 2016-11-06 | 2026-12-31 | 2026-12-31 |  |  | تأخرصرف المستحقات المالية |  | 39.9901 | 21.5499 | Failed | No
2100102421 | شركة المياه الوطنية / منطقة جازان | إشراف | ذات اولوية عالية وعاجلة | 4862880 | 243144 | 4420800 | 4420800 | 1010421282 | لا | 0 |  | منجز – استلام نهائي | التكلفة المفوترة | 100 | 100 | 2012-12-17 | 2013-12-16 | 2022-02-28 | 2022-02-28 |  | 2013-12-16 | لا يوجد تأخير |  | 42.6429 | 17.1559 | منجز | No
2100036212 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية وعاجلة | 56935360 | 2846768 | 14414641.87 | 12768001.01 | 5900008127 | لا | 0 | 180301001150 | جاري | منهجية القيمة المكتسبة | 66.15 | 100 | 2018-09-11 | 2021-08-09 | 2023-01-08 | 2023-01-08 |  |  | لا يوجد تأخير |  | 42.9815 | 17.0334 | Failed | No
2100109406 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 14362987.38 | 718149.369 | 14362987.38 | 14362987.38 | 1010070222 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-10-15 | 2017-10-04 | 2021-12-30 | 2021-12-30 | 2017-10-04 |  |  |  | 45.2591 | 25.2379 | منجز | No
2100033110 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية وعاجلة | 12786260.5 | 639313.025 | 10914015.5 | 10914015.5 | 5950007285 | لا | 0 | 180709029799 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 97.7 | 98.41 | 2013-02-20 | 2015-01-30 | 2022-02-28 | 2022-02-28 | 2015-01-30 |  | لا يوجد تأخير |  | 42.6429 | 17.156 | منجز | No
2100055053 | هيئة تطوير بوابة الدرعية | تصميم |  | 44546841 | 2227342.05 | 2866848 | 2866848 | 0 |  | 0 |  | جاري | التكلفة المفوترة | 22 | 22 | 2019-10-12 21:00 | 2021-12-04 00:59 | 2021-12-04 | 2021-12-04 |  |  | لا يوجد تأخير |  |  |  | منتظم | No
2100069672 | وزارة الثقافة | تشييد |  | 34537087.16 | 1726854.358 | 7869620.55 | 7869620.55 | 3350012131 |  | 0 |  | مسحوب | منهجية القيمة المكتسبة | 8 | 100 | 2017-11-16 00:59 | 2019-11-15 00:59 | 2020-03-16 | 2020-03-16 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  |  |  | مسحوب | No
2100073776 | وزارة الصحة / المدينة المنورة | تشييد | ذات اولوية منخفضة | 25722904 | 1286145.2 | 10858088 | 10858088 | 4650043690 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 48 | 100 | 2015-04-14 | 2017-03-22 | 2022-06-30 | 2022-06-30 |  |  | تأخرصرف المستحقات المالية |  | 39.36 | 24.28 | Failed | No
2200229493 | أمانة / جدة | تشييد | ذات اولوية عالية وعاجلة | 13532222 | 676611.1 | 2529880.98 | 1739404.88 | 4030132367 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 65 | 85 | 2021-02-01 | 2023-01-10 | 2023-01-10 | 2023-01-10 |  |  |  |  | 39.1925 | 21.4858 | متأخر | No
2200229504 | أمانة / جدة | تشييد | ذات اولوية عالية وعاجلة | 39839375 | 1991968.75 | 0 | 0 | 1132002624 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 0.2 | 7 | 2021-12-27 | 2023-12-15 | 2023-12-15 | 2023-12-15 |  |  |  |  | 39.1925 | 21.4858 | متأخر | No
2200229655 | أمانة / جدة | دراسات هندسية | ذات اولوية عالية | 1889979 | 94498.95 | 1039488.45 | 472494.75 | 4030282813 | لا | 0 | 210901139616 | جاري | اخرى | 100 | 100 | 2021-10-18 | 2022-10-07 | 2022-10-07 | 2022-10-07 |  |  |  |  | 39.1677 | 21.5007 | خدمات عامة | No
2200229633 | أمانة / جدة | الخدمات الاستشارية | ذات اولوية عالية | 766935 | 38346.75 | 191733.75 | 191733.75 | 1010182277 | لا | 0 |  | جاري | التكلفة المفوترة | 38 | 38 | 2021-11-30 | 2024-11-29 | 2024-11-29 | 2024-11-29 |  |  |  |  | 39.1677 | 21.5007 | خدمات عامة | No
2200229471 | أمانة / جدة | دراسات هندسية | ذات اولوية عالية | 1955000 | 97750 | 1955000 | 1348950 | 1010469884 | لا | 0 | 210209131396 | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2021-01-07 | 2022-07-08 | 2022-07-08 | 2022-07-08 | 2022-07-08 | 2022-07-09 |  |  | 39.1677 | 21.5007 | منجز | No
2100009973 | شركة المياه الوطنية / منطقة مكة المكرمة | إشراف | ذات اولوية عالية | 8383320 | 419166 | 8312500 | 8312500 | 4030286888 | لا | 0 |  | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2016-02-21 | 2018-08-20 | 2021-02-22 | 2021-02-22 | 2018-08-20 |  | لا يوجد تأخير |  | 39.2822 | 21.4582 | منجز | No
2200214141 | أمانة / الأحساء | أخرى | ذات اولوية عالية | 5572095 | 278604.75 | 5572095 | 5572095 | 2050018628 | نعم | 0.1 | 220101100553 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2021-11-07 | 2022-11-02 | 2022-11-02 | 2022-11-02 | 2022-11-02 |  |  |  | 49.6031 | 25.3178 | منجز | No
2100048624 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 2185000 | 109250 | 1422200 | 1422200 | 3450002829 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-09-04 | 2020-02-25 | 2021-04-15 | 2021-04-15 | 2020-02-25 |  | ضعف كفاءة المقاول الفنية |  | 38.669 | 31.6472 | منجز | No
2200229515 | أمانة / جدة | دراسات هندسية | ذات اولوية عالية | 876572 | 43828.6 | 474375 | 474375 | 1010051584 | لا | 0 |  | جاري | التكلفة المفوترة | 100 | 100 | 2020-12-20 | 2022-01-08 | 2022-02-10 | 2022-02-10 |  |  |  |  | 39.1677 | 21.5007 | خدمات عامة | No
2200229666 | أمانة / جدة | أخرى | ذات اولوية عالية | 45077736 | 2253886.8 | 34189813.27 | 31577195.01 | 4030151328 | لا | 0 | 191101192953 | جاري | اخرى | 58 | 58 | 2020-10-29 | 2023-10-29 | 2023-10-29 | 2023-10-29 |  |  |  |  | 39.1925 | 21.4858 | خدمات عامة | No
2100024135 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية وعاجلة | 99599206.08 | 4979960.304 | 66355568.09 | 66355568.09 | 5855000147 | لا | 0 | 181109375525 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 97.22 | 100 | 2011-07-09 | 2014-06-06 | 2020-01-12 | 2020-01-12 | 2014-06-06 |  | لا يوجد تأخير |  | 42.8338 | 16.9633 | منجز | No
2100015691 | شركة المياه الوطنية / منطقة مكة المكرمة | تصميم | ذات اولوية عالية | 26131137.6 | 1306556.88 | 4414542.6 | 4414542.6 | 1010326426 | لا | 0 | 200709052696 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-10-14 | 2019-01-30 | 2020-12-27 | 2020-12-27 | 2019-01-30 |  | لا يوجد تأخير |  | 39.2483 | 21.3393 | منجز | No
2100021350 | وزارة النقل والخدمات اللوجستية / منطقة تبوك | تشييد | ذات اولوية عالية | 42291051.68 | 2114552.584 | 273907 | 273907 | 1010412530 | نعم | 2047549 | 181109354253 | جاري | الكميات التي تم تركيبها | 4.73 | 24 | 2022-03-16 | 2023-08-28 | 2023-09-28 | 2023-09-28 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5982 | 28.413 | متأخر | No
2100008470 | وزارة الصحة / الحدود الشمالية | تشييد | لم تعد تحتاجها الجهة | 3239764 | 161988.2 | 3239764 | 3239764 | 3453004545 | لا | 0 | 181009128401 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2017-12-09 | 2018-11-30 | 2019-08-19 | 2019-08-19 | 2018-11-30 |  | أوامر تغيير |  | 42.2302 | 30.3603 | منجز | No
2100007265 | وزارة التعليم | تشييد | ذات اولوية عالية | 12756235.55 | 637811.7775 | 8212058.02 | 8212058.02 | 1010088518 | لا | 0 |  | مسحوب | التكلفة المفوترة | 78 | 100 | 2013-07-27 | 2015-10-15 | 2022-12-28 | 2022-12-28 |  |  | ضعف كفاءة المقاول الفنية |  | 38.0568 | 24.1147 | مسحوب | No
2100031080 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 6279900 | 313995 | 5650699.65 | 5650699.65 | 4030006066 | لا | 0 | 190901023206 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-06-09 | 2020-06-03 | 2022-01-01 | 2022-01-01 | 2020-06-03 |  | ضعف كفاءة المقاول الفنية |  | 42.842 | 21.2545 | منجز | No
2100006451 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 14931500 | 746575 | 12298979 | 12298979 | 1010074413 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 93.01 | 100 | 2020-03-26 | 2022-03-27 | 2021-10-24 | 2021-10-24 | 2022-03-27 |  | لا يوجد تأخير |  | 40.495 | 21.4226 | منجز | No
2100012504 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 9842505.75 | 492125.2875 | 9366457 | 9366457 | 4650021867 | لا | 0 | 180809055716 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2016-12-18 | 2017-12-13 | 2018-06-26 | 2018-06-26 | 2017-12-13 |  | ضعف كفاءة المقاول الفنية |  | 40.4135 | 21.2721 | منجز | No
2200229670 | أمانة / جدة | دراسات هندسية | ذات اولوية متوسطة | 34209000 | 1710450 | 28563057 | 28563057 | 4030276223 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 96 | 97 | 2019-09-01 | 2022-08-31 | 2022-08-31 | 2022-08-31 |  |  |  |  | 39.1925 | 21.4858 | خدمات عامة | No
2100060244 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 61990000 | 3099500 | 47445636.7 | 47445636.7 | 1010012911 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 93.9 | 100 | 2019-01-24 | 2021-01-02 | 2021-10-20 | 2021-10-20 | 2021-01-02 |  | لا يوجد تأخير |  | 40.3587 | 21.2747 | منجز | No
2100102395 | أمانة / الحدود الشمالية | دراسة الجدوى | ذات اولوية متوسطة | 9075563.84 | 453778.192 | 6285000 | 6285000 | 1010326770 | لا | 0 | 190509141994 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-03-19 | 2017-03-18 | 2022-02-16 | 2022-02-16 | 2017-03-18 |  | أوامر سامية |  | 41.0107 | 30.9778 | منجز | No
2100066264 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 20705481.68 | 1035274.084 | 16578491.98 | 16578491.98 | 1010197183 | لا | 0 | 190509045531 | جاري | منهجية القيمة المكتسبة | 92 | 100 | 2014-05-21 | 2016-05-10 | 2023-05-29 | 2023-05-29 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 41.0511 | 30.9699 | متأخر | No
2100054364 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 370726100 | 18536305 | 333653490 | 333653490 | 1010008118 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2007-07-03 | 2019-03-11 | 2019-03-11 | 2019-03-11 | 2019-03-11 | 2019-10-06 |  |  | 41.3349 | 20.3686 | منجز | No
2200229552 | أمانة / جدة | تشييد | ذات اولوية عالية وعاجلة | 9865415 | 493270.75 | 986541 | 986541 | 4030280934 | لا | 0 | 210801184421 | جاري | الكميات التي تم تركيبها | 89 | 100 | 2021-01-10 | 2022-11-04 | 2022-11-04 | 2022-11-04 |  |  |  |  | 39.1925 | 21.4858 | متأخر | No
2100092455 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية وعاجلة | 20000000 | 1000000 | 3029451.4 | 3029451.4 | 2050060814 | لا | 0 | 190901176339 | جاري | منهجية القيمة المكتسبة | 90.7 | 100 | 2019-10-06 | 2021-03-20 | 2022-06-30 | 2022-06-30 |  |  | لا يوجد تأخير |  | 42.5686 | 17.3385 | Failed | No
2200235432 | أمانة / القصيم | تشييد | ذات اولوية عالية | 17377962.09 | 868898.1045 | 0 | 0 | 1131013992 | لا | 0 |  | جاري | تكلفة العمل المنجز | 9 | 14 | 2022-09-27 | 2024-09-15 | 2024-09-15 | 2024-09-15 |  |  |  |  | 43.9818 | 26.3592 | منتظم | No
2100026832 | الجمارك السعودية | تشييد | ذات اولوية عالية | 557461199 | 27873059.95 | 331082120.74 | 331082120.74 | 1010254468 | لا | 0 | 181009219850 | جاري | تكلفة العمل المنجز | 59 | 100 | 2014-12-29 | 2017-11-24 | 2023-09-01 | 2023-09-01 |  |  | أوامر تغيير |  | 37.1189 | 31.5192 | Failed | No
2100074303 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 26540842 | 1327042.1 | 21209294.5 | 0 | 1010012745 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 65 | 100 | 2008-01-25 | 2014-05-06 | 2021-07-06 | 2021-07-06 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | مسحوب | Yes
2100018955 | المركز الوطني لتنمية الحياة الفطرية | تشييد | ذات اولوية متوسطة | 434274.75 | 21713.7375 | 434274.75 | 434274.75 | 1010102014 | لا | 0 | 180809038921 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2017-11-20 | 2019-04-30 | 2019-04-30 | 2019-04-30 | 2019-04-30 |  | لا يوجد تأخير |  | 46.6261 | 46.6261 | منجز | No
2100027366 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 92341535 | 4617076.75 | 92341535 | 92341535 | 1010090968 | لا | 0 | 181109343412 | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2012-09-08 | 2016-07-25 | 2020-02-25 | 2020-02-25 | 2016-07-25 | 2021-07-11 |  |  | 39.8192 | 21.3905 | منجز | No
No
2100060163 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 54487394 | 2724369.7 | 0 | 0 | 2050003475 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99.9 | 100 | 2018-02-18 | 2019-08-03 | 2019-07-11 | 2019-07-11 | 2019-08-03 |  | لا يوجد تأخير |  | 39.2241 | 21.5416 | منجز | No
2100080216 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية | 23432280 | 1171614 | 21774075.82 | 21774075.82 | 5850002600 | لا | 0 | 181001200125 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-11-04 | 2020-10-13 | 2020-10-13 | 2020-10-13 | 2020-10-13 |  | لا يوجد تأخير |  | 42.8565 | 16.956 | منجز | No
2200229725 | أمانة / جدة | دراسة بيئية | ذات اولوية عالية | 17957345 | 897867.25 | 13412779.35 | 12093699.05 | 4030170268 | لا | 0 | 210909171756 | جاري | تكلفة العمل المنجز | 90 | 90 | 2020-07-07 | 2023-06-07 | 2023-07-07 | 2023-07-07 |  |  |  |  | 39.1925 | 21.4858 | خدمات عامة | No
2100057223 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية وعاجلة | 144080515 | 7204025.75 | 98553200 | 98553200 | 1116000094 | نعم | 127543003.14 | 181009180395 | مسحوب | منهجية القيمة المكتسبة | 90.09 | 100 | 2010-05-18 | 2013-04-14 | 2022-08-31 | 2022-08-31 |  |  | ضعف كفاءة المقاول الفنية |  | 42.6216 | 17.1738 | مسحوب | No
2200229736 | وزارة الاعلام | توريد وتركيب | ذات اولوية عالية | 529805 | 26490.25 | 529805 | 529805 | 1010624711 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2022-09-26 | 2023-02-01 | 2022-11-04 | 2022-11-04 | 2023-02-01 |  |  | أخرى | 46.6956 | 24.6429 | منجز | No
2100098626 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 60770580 | 3038529 | 45647957.43 | 45647957.43 | 1010074413 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 85 | 100 | 2019-08-25 | 2021-08-25 | 2021-11-01 | 2021-11-01 | 2021-08-25 |  | لا يوجد تأخير |  | 40.4481 | 21.2747 | منجز | No
2100106691 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 4030000.21 | 201500.0105 | 3401527.99 | 3401527.99 | 1116004478 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-11-09 | 2016-11-03 | 2021-07-17 | 2021-07-17 | 2016-11-03 |  | ضعف كفاءة المقاول الفنية |  | 46.6561 | 24.7584 | منجز | No
2100100483 | وزارة البيئة والمياة والزراعة | دراسات هندسية | ذات اولوية متوسطة | 2400000 | 120000 | 842753.68 | 474543.88 | 4031089496 | لا | 0 | 200201058407 | جاري | تكلفة العمل المنجز | 64 | 100 | 2020-08-25 | 2020-11-10 | 2021-02-18 | 2021-02-18 |  |  |  |  | 47.1993 | 24.0721 | خدمات عامة | No
2100043002 | شركة المياه الوطنية / منطقة الحدود الشمالية | توريد وتركيب | ذات اولوية عالية | 3859744.35 | 192987.2175 | 3828476.19 | 3828476.19 | 1010220848 | لا | 0 | 190709027651 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 99.18 | 100 | 2019-04-15 | 2020-04-03 | 2020-04-04 | 2020-04-04 |  | 2020-04-03 | لا يوجد تأخير |  | 43.5201 | 29.6285 | منجز | No
2100005736 | شركة المياه الوطنية / منطقة مكة المكرمة | إشراف | ذات اولوية عالية | 7774800 | 388740 | 8065802.62 | 8065802.62 | 4030286888 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 100 | 100 | 2019-01-31 | 2021-01-30 | 2022-04-02 | 2022-04-02 |  |  | لا يوجد تأخير |  | 40.4459 | 21.3487 | خدمات عامة | No
2100037811 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية وعاجلة | 239664480.19 | 11983224.0095 | 160048564.72 | 160048564.72 | 1010014578 | لا | 0 | 180909089093 | جاري | مدفوعات ساعات العمل | 86.29 | 100 | 2010-06-28 | 2013-06-11 | 2024-12-31 | 2024-12-31 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | متأخر | No
2200229460 | أمانة / جدة | تشييد | ذات اولوية عالية وعاجلة | 28703195 | 1435159.75 | 6909215.56 | 6909215.56 | 1128003753 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 89.1 | 100 | 2021-10-25 | 2022-02-25 | 2022-05-30 | 2022-05-30 | 2022-02-25 |  |  |  | 39.1925 | 21.4858 | منجز | No
2100002892 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية وعاجلة | 30047760 | 1502388 | 26216129 | 22545459 | 5850017300 | لا | 0 | 190509103818 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 98.5 | 100 | 2014-11-06 | 2016-10-14 | 2022-03-01 | 2022-03-01 |  |  | لا يوجد تأخير |  | 43.2279 | 16.7733 | Failed | No
2100191391 | شركة المياه الوطنية / منطقة الحدود الشمالية | إشراف | ذات اولوية عالية وعاجلة | 3231900 | 161595 | 2867131.59 | 685909 | 1010949106 | لا | 0 | 191101092724 | منجز – استلام ابتدائي | التكلفة المفوترة | 69.8 | 100 | 2020-07-12 | 2021-07-12 | 2023-07-12 | 2023-07-12 | 2021-07-12 |  |  |  | 40.9341 | 30.9982 | منجز | No
2100088141 | جامعة الجوف | تشييد | ذات اولوية عالية | 94077884.64 | 4703894.232 | 94077884.64 | 84649748.89 | 2055002293 | لا | 0 | 180909090280 | جاري | تكلفة العمل المنجز | 100 | 100 | 2016-05-22 | 2021-01-27 | 2023-05-20 | 2023-05-20 |  |  | تأخرصرف المستحقات المالية |  | 40.0558 | 29.795 | منتظم | No
2100061191 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 51397785 | 2569889.25 | 46328219 | 46328219 | 1010067433 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 99.05 | 100 | 2018-01-14 | 2020-06-19 | 2020-05-31 | 2020-05-31 |  | 2020-06-19 | لا يوجد تأخير |  | 41.0889 | 19.126 | منجز | No
2100079822 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية | 5109905 | 255495.25 | 3835526.83 | 3835526.83 | 4650052854 | لا | 0 | 180909096917 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 97.44 | 97.31 | 2009-12-29 | 2012-11-26 | 2021-05-02 | 2021-05-02 | 2012-11-26 |  | لا يوجد تأخير |  | 39.7563 | 24.5621 | منجز | No
2100059146 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 97611543 | 4880577.15 | 83656431.19 | 83656431.19 | 2050003475 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 98.6 | 100 | 2017-11-05 | 2020-10-03 | 2021-10-25 | 2021-10-25 | 2020-10-03 |  | لا يوجد تأخير |  | 40.4935 | 21.4472 | منجز | No
2200229865 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 641890.44 | 32094.522 | 399552 | 399552 | 2050134606 | لا | 0 |  | جاري | تكلفة العمل المنجز | 72 | 55 | 2022-08-07 | 2023-05-29 | 2023-05-29 | 2023-05-29 |  |  |  |  | 47.0544 | 27.0069 | منتظم | No
2100057142 | جامعة الملك سعود | توريد وتركيب | ذات اولوية متوسطة | 14475197 | 723759.85 | 10413260.81 | 10413260.81 | 4030045960 | لا | 0 | 210309076561 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 99 | 100 | 2019-11-06 | 2020-05-02 | 2022-04-25 | 2022-04-25 | 2020-05-02 |  | لا يوجد تأخير |  |  |  | منجز | No
2100007464 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 4987340 | 249367 | 332132.03 | 332132.03 | 4030052981 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 8 | 100 | 2015-03-22 | 2016-09-13 | 2023-02-08 | 2023-02-08 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.5429 | 16.8808 | مسحوب | No
2100085691 | شركة المياه الوطنية / منطقة جازان | إشراف | ذات اولوية عالية وعاجلة | 8958600 | 447930 | 6705692 | 5809792.84 | 5900018330 | لا | 0 | 190401130002 | جاري | التكلفة المفوترة | 79.07 | 80 | 2019-08-20 | 2022-08-21 | 2022-08-21 | 2022-08-21 |  |  | لا يوجد تأخير |  | 42.1307 | 16.7026 | خدمات عامة | No
2100190606 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 96502790.3 | 4825139.515 | 23381413.78 | 21869487.38 | 1010224518 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 27.49 | 49.7 | 2021-01-07 | 2023-07-07 | 2023-07-07 | 2023-07-07 |  |  |  |  | 40.4362 | 21.3527 | متأخر | No
2100087404 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية وعاجلة | 1337823892 | 66891194.6 | 1061170632 | 1061170632 | 4030068284 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2010-08-21 | 2012-10-08 | 2015-05-31 | 2015-05-31 | 2012-10-08 |  | لا يوجد تأخير |  |  |  | منجز | No
2100004863 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 66082379.5 | 3304118.975 | 39414340.76 | 39414340.76 | 4030157663 | لا | 0 | 180709032068 | جاري | تكلفة العمل المنجز | 80 | 100 | 2014-09-07 | 2015-08-26 | 2021-12-31 | 2021-12-31 |  |  | تأخرصرف المستحقات المالية |  | 39.1677 | 21.5008 | متأخر | No
2200229681 | أمانة / جدة | أخرى | ذات اولوية عالية | 58408560 | 2920428 | 46019087.63 | 38232624.96 | 4030151328 | لا | 0 | 191001209765 | جاري | اخرى | 64 | 64 | 2020-10-01 | 2023-10-01 | 2023-10-01 | 2023-10-01 |  |  |  |  | 39.1925 | 21.4858 | خدمات عامة | No
2100042965 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 29550385.75 | 1477519.2875 | 20044084.75 | 20044084.75 | 2050001536 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-02-01 | 2020-01-10 | 2019-09-30 | 2019-09-30 | 2020-01-10 |  | لا يوجد تأخير |  | 39.1997 | 21.56 | منجز | No
2200229891 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 3259282.5 | 162964.125 | 1072950 | 1072950 | 2050018628 | لا | 0 |  | جاري | تكلفة العمل المنجز | 100 | 58.48 | 2022-07-07 | 2023-06-01 | 2023-06-01 | 2023-06-01 |  |  |  |  | 49.6707 | 25.9168 | منتظم | No
2200229902 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 1090775 | 54538.75 | 736273 | 736273 | 2056005766 | لا | 0 |  | جاري | تكلفة العمل المنجز | 75 | 55 | 2022-07-28 | 2023-05-27 | 2023-05-27 | 2023-05-27 |  |  |  |  | 48.4288 | 27.2669 | منتظم | No
2200235513 | الرئاسة العامة لهيئة الأمر بالمعروف والنهي عن المنكر | ترميم | ذات اولوية عالية | 983320 | 49166 | 268252.17 | 268252.17 | 1010056526 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 30 | 100 | 2022-08-24 | 2023-04-21 | 2023-04-21 | 2023-04-21 |  |  |  |  | 43.9875 | 26.0907 | Failed | No
2100191295 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية | 4987500 | 249375 | 285120 | 285120 | 5850002600 | لا | 0 | 200801062263 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 57.44 | 100 | 2020-10-27 | 2021-04-24 | 2022-03-31 | 2022-03-31 | 2021-04-24 |  |  |  | 42.8869 | 17.223 | منجز | No
2200215865 | وزارة الحرس الوطني / كلية الملك خالد العسكرية | توريد وتركيب | ذات اولوية عالية | 1678341.05 | 83917.0525 | 1678341.05 | 1678341.05 | 4030053945 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2021-07-27 | 2022-03-20 | 2022-03-20 | 2022-03-20 | 2022-03-20 |  |  |  | 46.8908 | 24.7412 | منجز | No
2100013661 | وزارة التعليم | تشييد | ذات اولوية عالية | 10846370.9 | 542318.545 | 8587387.23 | 8587387.23 | 1010081451 | لا | 0 |  | مسحوب | التكلفة المفوترة | 88 | 100 | 2013-12-25 | 2015-12-15 | 2020-04-22 | 2020-04-22 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | مسحوب | No
2100069720 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 82263425 | 4113171.25 | 81576934.15 | 81576934.15 | 1010090968 | لا | 0 | 181209522736 | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2012-11-10 | 2016-09-25 | 2020-10-31 | 2020-10-31 | 2016-09-25 | 2021-10-27 |  |  | 39.8165 | 21.2809 | منجز | No
2100073684 | وزارة التعليم | تشييد | ذات اولوية عالية | 12487584.6 | 624379.23 | 7800160.91 | 7692499.56 | 1010051817 | لا | 0 |  | مسحوب | التكلفة المفوترة | 64 | 100 | 2014-01-09 | 2015-12-30 | 2021-11-15 | 2021-11-15 |  |  | ضعف كفاءة المقاول الفنية |  | 46.739 | 24.772 | مسحوب | No
2100097506 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 81118500 | 4055925 | 59067891.7 | 59067891.7 | 2050018730 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 86.18 | 100 | 2013-12-02 | 2016-06-02 | 2020-09-14 | 2020-09-14 | 2016-06-02 |  | لا يوجد تأخير |  | 40.4579 | 21.3513 | منجز | No
2100191833 | شركة المياه الوطنية / منطقة حائل | إشراف | ذات اولوية عالية | 3840000 | 192000 | 458533.03 | 0 | 1010322448 | لا | 0 | 180201000194 | جاري | التكلفة المفوترة | 15.78 | 18.9 | 2022-02-13 | 2024-02-14 | 2024-02-14 | 2024-02-14 |  |  |  |  | 41.8896 | 27.8416 | خدمات عامة | Yes
2100063313 | شركة المياه الوطنية / منطقة حائل | إشراف | لم تعد تحتاجها الجهة | 3463000 | 173150 | 5852068.46 | 5852068.46 | 3350040777 | لا | 0 | 180709033443 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2013-09-16 | 2015-11-16 | 2021-01-31 | 2021-01-31 | 2015-11-16 |  | لا يوجد تأخير |  | 42.4362 | 27.0894 | منجز | No
2100106702 | وزارة التعليم | تشييد | ذات اولوية عالية | 12898042.16 | 644902.108 | 7276760.65 | 7111220.92 | 1010051817 | لا | 0 |  | مسحوب | التكلفة المفوترة | 70 | 100 | 2014-02-27 | 2016-02-17 | 2021-11-15 | 2021-11-15 |  |  | ضعف كفاءة المقاول الفنية |  | 46.8086 | 24.8272 | مسحوب | No
2200235535 | مدينة الملك عبدالله الطبية بالعاصمة المقدسة | تشييد | ذات اولوية عالية وعاجلة | 7583333.33 | 379166.6665 | 3022482.12 | 3022482.12 | 1010257711 | لا | 0 | 191001278724 | ايقاف كلي | الكميات التي تم تركيبها | 77 | 77 | 2021-02-07 | 2022-08-07 | 2023-04-16 | 2023-04-16 |  |  |  |  | 39.8811 | 21.382 | Failed | No
2100097440 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 159997800 | 7999890 | 77124449.58 | 77124449.58 | 1010297995 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 86 | 100 | 2015-12-29 | 2017-12-06 | 2021-11-07 | 2021-11-07 | 2017-12-06 |  | لا يوجد تأخير |  | 40.3916 | 21.2984 | منجز | No
2100001260 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 44100000 | 2205000 | 21642850.85 | 21642850.85 | 1010012911 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 83.08 | 100 | 2018-05-24 | 2020-05-24 | 2020-05-18 | 2020-05-18 | 2020-05-24 |  | لا يوجد تأخير |  | 40.4166 | 21.2746 | منجز | No
2100095690 | وزارة التعليم | تشييد | ذات اولوية عالية | 14449809.14 | 722490.457 | 10572355.45 | 10572355.45 | 1010076310 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 78 | 100 | 2008-04-23 | 2010-05-05 | 2010-05-05 | 2010-05-05 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6714 | 24.7776 | مسحوب | No
2100001164 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 85701606.54 | 4285080.327 | 77701609.05 | 77701609.05 | 1010076961 | لا | 0 | 180709031967 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2013-08-28 | 2016-07-26 | 2019-06-26 | 2019-06-26 |  | 2016-07-26 | لا يوجد تأخير |  | 46.037 | 28.5074 | منجز | No
2200235561 | أمانة / القصيم | تشييد | ذات اولوية عالية | 1714263 | 85713.15 | 1399984.1 | 1399984.1 | 1131010033 | لا | 0 |  | جاري | تكلفة العمل المنجز | 90 | 92 | 2021-10-04 | 2023-01-18 | 2023-01-18 | 2023-01-18 |  |  |  |  | 43.4163 | 27.2667 | منتظم | No
2200235550 | أمانة / القصيم | تشييد | ذات اولوية عالية | 2534700 | 126735 | 1520820 | 1520820 | 1131010033 | لا | 0 |  | جاري | تكلفة العمل المنجز | 76 | 76 | 2020-10-04 | 2023-09-11 | 2023-09-11 | 2023-09-11 |  |  |  |  | 43.4163 | 27.2667 | منتظم | No
2100035173 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 12416064 | 620803.2 | 8722660.21 | 0 | 3350003498 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 74 | 100 | 2013-03-23 | 2015-03-13 | 2021-12-15 | 2021-12-15 | 2015-03-13 |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | منجز | Yes
2100108183 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 49458319.55 | 2472915.9775 | 18336909.15 | 18241639.35 | 1010269001 | لا | 0 | 181109272464 | ايقاف كلي | تكلفة العمل المنجز | 53 | 97 | 2015-03-16 | 2017-02-13 | 2025-12-31 | 2025-12-31 |  |  | تأخرصرف المستحقات المالية |  | 46.7401 | 24.4426 | Failed | No
2100078783 | شركة المياه الوطنية / المنطقة الشرقية | إشراف | ذات اولوية عالية | 10396800 | 519840 | 10290033.85 | 10290033.85 | 2050099301 | لا | 0 | 180809054114 | منجز – استلام ابتدائي | التكلفة المفوترة | 98.97 | 100 | 2017-09-23 | 2019-03-23 | 2019-03-23 | 2019-03-23 | 2019-03-23 |  | لا يوجد تأخير |  | 45.9757 | 28.3882 | منجز | No
2100057330 | شركة المياه الوطنية / منطقة القصيم | دراسات هندسية | ذات اولوية متوسطة | 2250000 | 112500 | 2249990 | 2249990 | 1010076578 | لا | 0 | 180809043274 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2017-12-20 | 2018-10-19 | 2020-02-10 | 2020-02-10 | 2018-10-19 |  | لا يوجد تأخير |  | 43.9803 | 26.3438 | منجز | No
2100055926 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات الجوية | دراسة الجدوى | ذات اولوية متوسطة | 3672900 | 183645 | 3127765 | 3127765 | 1010326073 | لا | 0 | 200609044159 | جاري الاستلام الإبتدائي | مدفوعات ساعات العمل | 100 | 100 | 2020-04-01 | 2022-04-01 | 2022-05-31 | 2022-05-31 |  |  |  |  | 50.0734 | 26.4275 | متأخر | No
2100097742 | وزارة التجارة | تشييد | ذات اولوية عالية وعاجلة | 10698475.8 | 534923.79 | 9160895 | 9160895 | 1010277125 | لا | 0 | 181109373474 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-06-05 | 2020-06-04 | 2020-11-11 | 2020-11-11 |  | 2020-06-04 | أوامر تغيير |  | 45.3589 | 25.8899 | منجز | No
2100077711 | وزارة الداخلية / المديرية العامة للدفاع المدني | تشييد | ذات اولوية عالية | 4234818 | 211740.9 | 3215215.25 | 3215215.25 | 4031212343 | لا | 0 | 190501002546 | جاري | الكميات التي تم تركيبها | 86 | 100 | 2019-02-04 | 2020-05-21 | 2023-03-01 | 2023-03-01 |  |  | تأخرصرف المستحقات المالية |  | 39.1857 | 21.4966 | Failed | No
2100003345 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 139690394.96 | 6984519.748 | 93232185.65 | 93232185.65 | 1010185409 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 89 | 100 | 2019-08-28 | 2021-02-18 | 2023-03-31 | 2023-03-31 |  |  | أوامر تغيير | أخرى |  |  | متأخر | No
2100020624 | شركة المياه الوطنية / المنطقة الشرقية | إشراف | ذات اولوية عالية | 21995785.2 | 1099789.26 | 19370419.2 | 19370419.2 | 1010348048 | لا | 0 | 180401004070 | جاري | التكلفة المفوترة | 99.59 | 100 | 2018-10-09 | 2021-10-08 | 2022-04-30 | 2022-04-30 |  |  | لا يوجد تأخير |  | 50.2028 | 26.1918 | خدمات عامة | No
2100026530 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية | 30717000 | 1535850 | 27799013.57 | 12189030 | 1131007596 | لا | 0 | 180901083945 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 90 | 100 | 2018-11-14 | 2021-10-12 | 2022-01-30 | 2022-01-30 | 2021-10-12 |  | ضعف كفاءة المقاول الفنية |  | 43.9553 | 26.3508 | منجز | No
2200222176 | شركة المياه الوطنية / منطقة جازان | إشراف | ذات اولوية عالية وعاجلة | 18333000 | 916650 | 1356855 | 1256404 | 4030275039 | لا | 0 | 190901175326 | جاري | التكلفة المفوترة | 35.41 | 35.41 | 2020-10-07 | 2023-10-07 | 2023-10-07 | 2023-10-07 |  |  |  |  | 42.5706 | 16.8894 | خدمات عامة | No
2100003334 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 4013605.47 | 200680.2735 | 3485220.8 | 3485220.8 | 1116004478 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-11-17 | 2016-11-11 | 2022-08-10 | 2022-08-10 | 2016-11-11 |  | ضعف كفاءة المقاول الفنية |  | 46.7614 | 24.7709 | منجز | No
2100058494 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 4766207.57 | 238310.3785 | 498552.54 | 379485.21 | 1010213931 | لا | 0 |  | مسحوب | التكلفة المفوترة | 9 | 100 | 2014-01-23 | 2015-07-17 | 2023-08-31 | 2023-08-31 |  |  | ضعف كفاءة المقاول الفنية |  | 40.0549 | 29.8587 | مسحوب | No
2100003533 | وزارة الداخلية / ديوان وزارة الداخلية | إشراف | ذات اولوية عالية | 1138432181 | 56921609.05 | 974225339 | 971547049 | 1010312533 | لا | 0 |  | جاري | التكلفة المفوترة | 82 | 85 | 2014-03-09 | 2021-06-30 | 2025-03-26 | 2025-03-26 |  |  | تأخرصرف المستحقات المالية |  | 46.6563 | 24.7424 | خدمات عامة | No
2100102594 | وزارة التجارة | دراسة الجدوى | ذات اولوية عالية | 2547270 | 127363.5 | 2516114.88 | 2516114.88 | 1010348048 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 81 | 86 | 2018-06-05 | 2020-06-04 | 2020-11-11 | 2020-11-11 |  | 2020-06-04 | أوامر تغيير |  |  |  | منجز | No
2100093494 | شركة المياه الوطنية / منطقة حائل | إشراف | ذات اولوية عالية | 9804410 | 490220.5 | 5772487.04 | 5461225.54 | 1131051650 | لا | 0 | 180901079359 | جاري | التكلفة المفوترة | 62.05 | 80.24 | 2019-12-05 | 2022-08-06 | 2022-08-04 | 2022-08-04 |  |  | لا يوجد تأخير |  | 41.7353 | 27.5073 | خدمات عامة | No
2100019622 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية | 32972750 | 1648637.5 | 22858522.84 | 21013971.37 | 5850017300 | لا | 0 | 180709023856 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 94.4 | 100 | 2015-03-19 | 2017-02-25 | 2017-05-11 | 2017-05-11 | 2017-02-25 |  | لا يوجد تأخير |  | 42.3126 | 17.6915 | منجز | No
2100005935 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 949968 | 47498.4 | 0 | 0 | 3350017342 | لا | 0 |  | جاري | التكلفة المفوترة | 50 | 100 | 2006-09-30 | 2007-07-27 | 2023-11-22 | 2023-11-22 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | Failed | No
2200235583 | مدينة الملك عبدالله الطبية بالعاصمة المقدسة | تشييد | ذات اولوية عالية وعاجلة | 2897101.85 | 144855.0925 | 0 | 0 | 1010219886 | لا | 0 | 201001124660 | جاري | الكميات التي تم تركيبها | 11 | 11 | 2022-08-22 | 2024-02-22 | 2024-02-22 | 2024-02-22 |  |  |  |  | 39.8811 | 21.382 | منتظم | No
2100035836 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2312020 | 115601 | 0 | 0 | 3450006578 | لا | 0 |  | مسحوب | التكلفة المفوترة | 9 | 100 | 2015-05-13 | 2016-04-12 | 2022-11-23 | 2022-11-23 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0165 | 30.9619 | مسحوب | No
2100056173 | أمانة / الباحة | تصميم | ذات اولوية عالية | 9917000 | 495850 | 8853600 | 8853600 | 1010076578 | لا | 0 |  | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-10-24 | 2020-08-04 | 2022-12-04 | 2022-12-04 |  |  | اخرى |  |  |  | منتظم | No
2100061935 | وزارة التجارة | تشييد | ذات اولوية عالية | 8250000 | 412500 | 1303850 | 1303850 | 1124000200 | لا | 0 | 181101359573 | جاري | منهجية القيمة المكتسبة | 70 | 80 | 2019-02-20 | 2021-02-20 | 2022-08-09 | 2022-08-09 |  |  | اخرى |  | 47.3679 | 24.1792 | متأخر | No
2100075530 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3259254 | 162962.7 | 2117190 | 0 | 1126000984 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 86 | 100 | 2015-08-29 | 2017-02-19 | 2019-12-15 | 2019-12-15 | 2017-02-19 |  | ضعف كفاءة المقاول الفنية |  | 46.6761 | 24.7113 | منجز | Yes
2200230112 | وزارة الخارجية | تصميم | ذات اولوية عالية | 1996000 | 99800 | 1377240 | 1377240 | 0 | لا | 0 |  | جاري | تكلفة العمل المنجز | 90 | 100 | 2021-02-04 | 2022-11-30 | 2022-11-30 | 2022-11-30 |  |  |  |  | 4.3572 | 50.8476 | متأخر | No
2200230090 | وزارة الخارجية | تشييد | ذات اولوية عالية وعاجلة | 28068004.76 | 1403400.238 | 5241581.25 | 3929081.25 | 1010260949 | نعم | 3045763.39 | 191201093133 | ايقاف كلي | تكلفة العمل المنجز | 13 | 50 | 2020-10-20 | 2022-10-19 | 2024-01-31 | 2024-01-31 |  |  |  | تم تمديد الجدول الزمني | 32.5623 | 15.6235 | Failed | No
2200230101 | وزارة الخارجية | تصميم | ذات اولوية عالية | 10500000 | 525000 | 9450000 | 9450000 | 0 | لا | 0 |  | جاري | تكلفة العمل المنجز | 90 | 100 | 2015-11-08 | 2016-03-08 | 2022-12-31 | 2022-12-31 |  |  |  |  | 71.4704 | 51.1605 | متأخر | No
2200235594 | وزارة الرياضة | ترميم | ذات اولوية عالية | 2849045.65 | 142452.2825 | 0 | 0 | 1010188861 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 20 | 20 | 2022-09-18 | 2023-09-19 | 2023-09-19 | 2023-09-19 |  |  |  |  | 46.6753 | 24.7136 | منتظم | No
2100107800 | جامعة الأمير سطام بن عبدالعزيز | تشييد | ذات اولوية عالية | 14894020 | 744701 | 14824605.9 | 14824605.9 | 1010156720 | لا | 0 | 190809103722 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2017-09-12 | 2018-04-10 | 2022-05-15 | 2022-05-15 | 2018-04-10 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 45.0062 | 20.434 | منجز | No
2100000162 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1994428.7 | 99721.435 | 1426509 | 1426509 | 1010103133 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 95 | 100 | 2008-06-07 | 2009-05-23 | 2022-08-11 | 2022-08-11 | 2009-05-23 |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | منجز | No
2100030041 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 5410732.6 | 270536.63 | 3390860.3 | 0 | 1010154882 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 62.79 | 100 | 2015-02-24 | 2016-08-17 | 2020-03-20 | 2020-03-20 |  |  | ضعف كفاءة المقاول الفنية |  | 45.3779 | 24.053 | مسحوب | Yes
2100055543 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 17966752 | 898337.6 | 9822519 | 9822519 | 2051020158 | لا | 0 | 181209546917 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 99.8 | 100 | 2012-02-20 | 2014-02-19 | 2023-11-28 | 2023-11-28 |  |  | أوامر تغيير |  | 38.2145 | 24.0008 | Failed | No
2100002870 | وزارة التعليم | تشييد | ذات اولوية عالية | 7922104.49 | 396105.2245 | 2157123 | 2021937 | 1010221374 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 44 | 100 | 2015-02-15 | 2016-11-06 | 2017-11-18 | 2017-11-18 |  |  | ضعف كفاءة المقاول الفنية |  | 37.2612 | 27.0032 | مسحوب | No
2100060970 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية | 36852661.55 | 1842633.0775 | 22282079.43 | 22282079.43 | 5950011360 | نعم | 185439.41 | 181009193420 | جاري | تكلفة العمل المنجز | 66 | 100 | 2014-04-08 | 2017-01-22 | 2024-12-31 | 2024-12-31 |  |  | تأخرصرف المستحقات المالية |  | 41.8851 | 19.1358 | Failed | No
2100054434 | أمانة / جدة | تشييد | ذات اولوية عالية وعاجلة | 355878805 | 17793940.25 | 325406329.08 | 325406329.08 | 1010253433 | لا | 0 | 180909095141 | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 99.6 | 100 | 2014-01-15 | 2016-12-12 | 2022-02-28 | 2022-02-28 |  |  | سوء التخطيط الاولي للمشروع |  | 39.1892 | 21.5329 | Failed | No
2100062090 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 29996353.89 | 1499817.6945 | 25497113.94 | 17099984.86 | 1131012642 | نعم | 13259920.33 | 180709016452 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-06-07 | 2016-08-30 | 2023-02-28 | 2023-02-28 | 2016-08-30 |  | تأخرصرف المستحقات المالية |  | 41.3181 | 26.8355 | منجز | No
2100008606 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية | 18109110 | 905455.5 | 12897271.57 | 12897271.57 | 4030150126 | لا | 0 | 180809046345 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 82.01 | 100 | 2014-03-05 | 2016-02-13 | 2022-03-31 | 2022-03-31 | 2016-02-13 |  | ضعف كفاءة المقاول الفنية |  | 42.9496 | 16.7159 | منجز | No
2100087021 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 9539775 | 476988.75 | 4878420 | 4878420 | 2050060814 | لا | 0 | 191001076194 | جاري | منهجية القيمة المكتسبة | 75 | 100 | 2019-09-26 | 2020-07-18 | 2022-10-31 | 2022-10-31 |  |  | اخرى |  | 40.459 | 20.4811 | Failed | No
2100009402 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية | 62062855 | 3103142.75 | 23322258.86 | 23322258.86 | 1010305341 | لا | 0 | 180709025996 | مسحوب | منهجية القيمة المكتسبة | 43.03 | 100 | 2013-06-02 | 2016-04-30 | 2024-06-21 | 2024-06-21 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 40.9469 | 27.3111 | مسحوب | No
2100088034 | جامعة الجوف | تشييد | ذات اولوية متوسطة | 10403280 | 520164 | 7725551.3 | 4325551.3 | 7007068377 | لا | 0 |  | جاري | تكلفة العمل المنجز | 60 | 65 | 2020-10-01 | 2021-10-01 | 2022-12-01 | 2022-12-01 |  |  | تأخرصرف المستحقات المالية |  | 40.0486 | 29.7908 | منتظم | No
2100088734 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البرية | تشييد | ذات اولوية متوسطة | 2100000 | 105000 | 2100000 | 0 | 1010056094 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-11-25 | 2019-05-20 | 2022-10-24 | 2022-10-24 | 2019-05-20 |  | تأخرصرف المستحقات المالية |  | 36.6211 | 28.3841 | منجز | Yes
2100061795 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية وعاجلة | 7215500 | 360775 | 3883451.95 | 3843451.95 | 1010013226 | لا | 0 | 180809054232 | مسحوب | الكميات التي تم تركيبها | 77 | 100 | 2018-03-08 | 2018-12-08 | 2022-01-27 | 2022-01-27 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 49.5663 | 25.3912 | مسحوب | No
2100106315 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية وعاجلة | 70766814 | 3538340.7 | 42730007.96 | 42730007.96 | 4030017054 | لا | 0 | 181009158511 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 88.65 | 100 | 2012-12-29 | 2015-11-28 | 2023-03-31 | 2023-03-31 | 2015-11-28 |  | لا يوجد تأخير |  | 39.5739 | 24.5078 | منجز | No
2100018093 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية | 28670385 | 1433519.25 | 6858003 | 6858003 | 3350002763 | لا | 0 | 190401117628 | مسحوب | منهجية القيمة المكتسبة | 33.78 | 100 | 2019-10-22 | 2021-09-30 | 2023-05-01 | 2023-05-01 |  |  | ضعف كفاءة المقاول الفنية |  | 42.46 | 27.8569 | مسحوب | No
2100080183 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية وعاجلة | 16499878 | 824993.9 | 14628677.57 | 14628677.57 | 2050027608 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-11-23 | 2019-11-02 | 2020-02-26 | 2020-02-26 | 2019-11-02 |  | لا يوجد تأخير |  | 49.5486 | 25.4008 | منجز | No
2200229176 | الجمارك السعودية | تشييد | ذات اولوية عالية | 2500000 | 125000 | 1361025 | 1361025 | 1010093247 | لا | 0 |  | جاري | تكلفة العمل المنجز | 92 | 100 | 2022-05-29 | 2023-05-29 | 2023-05-29 | 2023-05-29 |  |  |  |  | 37.1311 | 31.4992 | متأخر | No
2100058995 | جامعة الملك خالد | تشييد | ذات اولوية عالية وعاجلة | 313349699 | 15667484.95 | 290890038.1 | 277409471.28 | 1010074952 | لا | 0 | 181009165169 | جاري | تكلفة العمل المنجز | 96.52 | 96.52 | 2013-06-03 | 2015-05-24 | 2022-09-21 | 2022-09-21 |  |  | تأخرصرف المستحقات المالية |  | 42.8114 | 18.0836 | منتظم | No
2100026526 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية وعاجلة | 185951500 | 9297575 | 96159219.8 | 96159219.8 | 1116000094 | لا | 0 | 180809054430 | مسحوب | منهجية القيمة المكتسبة | 60.78 | 100 | 2013-05-05 | 2015-04-14 | 2024-02-01 | 2024-02-01 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.2789 | 27.1142 | مسحوب | No
2100105582 | وزارة التعليم | تشييد | ذات اولوية عالية | 11714107.95 | 585705.3975 | 11369568.19 | 11369568.19 | 1116002219 | لا | 0 |  | جاري | التكلفة المفوترة | 98 | 100 | 2012-06-08 | 2014-05-29 | 2022-07-15 | 2022-07-15 |  |  | ضعف كفاءة المقاول الفنية |  | 38.0303 | 24.0997 | Failed | No
2100081211 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1417200 | 70860 | 600000 | 0 | 1126001301 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-08-01 | 2016-10-24 | 2019-07-09 | 2019-07-09 | 2016-10-24 |  | ضعف كفاءة المقاول الفنية |  | 45.6323 | 25.5936 | منجز | Yes
2100001116 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية وعاجلة | 55368818.12 | 2768440.906 | 7804242.09 | 6363786.13 | 1131022493 | نعم | 36551554.54 | 180709033825 | جاري | تكلفة العمل المنجز | 72 | 100 | 2017-06-12 | 2018-12-14 | 2026-12-31 | 2026-12-31 |  |  | تأخرصرف المستحقات المالية |  | 43.949 | 26.3845 | Failed | No
2100027086 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 32870207 | 1643510.35 | 0 | 0 | 1010106132 | لا | 0 | 180201000211 | مسحوب | تكلفة العمل المنجز | 1 | 100 | 2018-07-04 | 2020-06-12 | 2025-12-31 | 2025-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 50.0105 | 26.5521 | مسحوب | No
2200235631 | وزارة الرياضة | ترميم | ذات اولوية عالية | 2375325 | 118766.25 | 0 | 0 | 1010185891 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 20 | 20 | 2022-09-22 | 2023-09-21 | 2023-09-21 | 2023-09-21 |  |  |  |  | 50.1971 | 26.2172 | منتظم | No
2100018513 | شركة المياه الوطنية / منطقة جازان | إشراف | ذات اولوية عالية وعاجلة | 12120000 | 606000 | 4818453.09 | 3826486.65 | 1010348048 | لا | 0 | 180901082949 | منجز – استلام نهائي | التكلفة المفوترة | 88.95 | 100 | 2018-10-16 | 2020-09-21 | 2022-04-30 | 2022-04-30 |  | 2020-09-21 | لا يوجد تأخير |  | 42.6251 | 17.593 | منجز | No
2100063685 | شركة المياه الوطنية / منطقة جازان | إشراف | ذات اولوية عالية وعاجلة | 4426800 | 221340 | 3097575.67 | 3097575.67 | 4030275039 | لا | 0 | 181201457032 | جاري | التكلفة المفوترة | 75.29 | 100 | 2019-05-01 | 2022-03-30 | 2022-03-20 | 2022-03-20 |  |  | لا يوجد تأخير |  | 42.8201 | 17.6176 | خدمات عامة | No
2100101721 | شركة المياه الوطنية | دراسة بيئية | ذات اولوية عالية وعاجلة | 55136172 | 2756808.6 | 27471689 | 27471689 | 1010322156 | لا | 0 | 181109351713 | جاري | تكلفة العمل المنجز | 91 | 100 | 2010-03-13 | 2013-03-13 | 2022-11-01 | 2022-11-01 |  |  | لا يوجد تأخير |  | 46.6781 | 24.7094 | خدمات عامة | No
2200235642 | وزارة الرياضة | ترميم | ذات اولوية عالية | 2375325 | 118766.25 | 0 | 0 | 1010185891 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 20 | 20 | 2022-10-01 | 2023-09-30 | 2023-09-30 | 2023-09-30 |  |  |  |  | 46.6753 | 24.7136 | منتظم | No
2100080076 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية | 51116133.12 | 2555806.656 | 40367562.32 | 34704929.16 | 1010305737 | لا | 0 | 180709020419 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-04-30 | 2016-03-30 | 2023-03-03 | 2023-03-03 | 2016-03-30 |  | تأخرصرف المستحقات المالية |  | 49.5079 | 25.3146 | منجز | No
2200235653 | وزارة الرياضة | ترميم | ذات اولوية عالية | 2388870 | 119443.5 | 0 | 0 | 1010185891 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 20 | 20 | 2022-09-20 | 2023-09-21 | 2023-09-21 | 2023-09-21 |  |  |  |  | 39.8579 | 21.3891 | منتظم | No
2100191936 | شركة المياه الوطنية / منطقة مكة المكرمة | إشراف | ذات اولوية عالية وعاجلة | 3998550 | 199927.5 | 2438903.23 | 2438903.23 | 7001573174 | لا | 0 | 201101112376 | جاري | التكلفة المفوترة | 38.32 | 49 | 2021-01-18 | 2023-06-23 | 2023-06-23 | 2023-06-23 |  |  |  |  | 41.0744 | 19.1188 | خدمات عامة | No
2100011583 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 36868090 | 1843404.5 | 24491722.4 | 24491722.4 | 2050007224 | لا | 0 | 200709052696 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 93.501 | 100 | 2019-05-29 | 2021-05-06 | 2021-03-17 | 2021-03-17 | 2021-05-06 |  | لا يوجد تأخير |  | 39.1446 | 21.615 | منجز | No
2100102336 | شركة المياه الوطنية / منطقة مكة المكرمة | تحديث وتوريد | ذات اولوية عالية | 8312500 | 415625 | 7718750 | 7718750 | 4030286888 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2016-03-02 | 2018-09-02 | 2020-03-15 | 2020-03-15 | 2018-09-02 |  | لا يوجد تأخير |  | 39.6911 | 21.6178 | منجز | No
2100102675 | شركة المياه الوطنية / المنطقة الشرقية | إشراف | ذات اولوية عالية | 14765850 | 738292.5 | 14761310.25 | 14761310.25 | 1010314421 | لا | 0 | 180709030970 | منجز – استلام ابتدائي | التكلفة المفوترة | 99.97 | 100 | 2017-11-30 | 2020-11-30 | 2021-10-19 | 2021-10-19 | 2020-11-30 |  | لا يوجد تأخير |  | 50.0001 | 26.5651 | منجز | No
2100042980 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 83738050 | 4186902.5 | 64968303.47 | 64968303.47 | 2050001536 | لا | 0 |  | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-05-29 | 2021-05-06 | 2022-05-31 | 2022-05-31 |  |  | لا يوجد تأخير |  | 39.28 | 21.469 | Failed | No
2100040876 | أمانة / العاصمة المقدسة | تشطيب | ذات اولوية متوسطة | 1446720 | 72336 | 1442290 | 1442290 | 1010348048 | لا | 0 | 181009152711 | منجز – استلام نهائي | مدفوعات ساعات العمل | 95 | 95 | 2018-07-14 | 2019-07-14 | 2019-07-14 | 2019-07-14 | 2019-07-14 | 2022-04-11 | اخرى |  |  |  | منجز | No
2100099153 | الهيئة الملكية لمدينة الرياض | تشييد | ذات اولوية عالية | 54888553.55 | 2744427.6775 | 49415837.16 | 49415837.16 | 4030034104 | لا | 0 | 190301031870 | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2019-06-09 | 2022-05-07 | 2021-01-22 | 2021-01-22 | 2022-05-07 |  |  |  | 46.6809 | 24.5717 | منجز | No
2100061644 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية وعاجلة | 150000000 | 7500000 | 25986215.15 | 23167177.8 | 4030023505 | نعم | 51651383.16 | 190701086215 | جاري | منهجية القيمة المكتسبة | 45 | 50 | 2018-08-12 | 2021-07-11 | 2023-03-14 | 2023-03-14 |  |  | لا يوجد تأخير |  | 39.6005 | 24.4595 | منتظم | No
2100005202 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية عالية | 98188293.7 | 4909414.685 | 32396609.96 | 19402721.47 | 1128000011 | نعم | 6617267 | 190401080867 | جاري | منهجية القيمة المكتسبة | 46.39 | 53.41 | 2019-09-11 | 2022-09-11 | 2023-11-23 | 2023-11-23 |  |  | اخرى |  | 36.6437 | 28.3235 | متأخر | No
2100079903 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية وعاجلة | 61067792.2 | 3053389.61 | 40464069.81 | 40464069.81 | 1116000082 | لا | 0 | 181209543038 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 94.75 | 100 | 2012-06-18 | 2014-05-27 | 2020-09-15 | 2020-09-15 | 2014-05-27 |  | لا يوجد تأخير |  | 42.6739 | 17.4999 | منجز | No
2100106433 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 32846290 | 1642314.5 | 26448382.55 | 26448382.55 | 2050007224 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 85.65 | 2018-02-01 | 2020-01-10 | 2019-07-28 | 2019-07-28 | 2020-01-10 |  | لا يوجد تأخير |  | 39.2389 | 21.5172 | منجز | No
2100096526 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية | 72310377.03 | 3615518.8515 | 45705945.13 | 45705945.13 | 5950011360 | نعم | 18264304.65 | 180709019160 | مسحوب | تكلفة العمل المنجز | 90 | 100 | 2012-09-11 | 2014-05-04 | 2025-12-31 | 2025-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 42.6265 | 17.0028 | مسحوب | No
2200230193 | وزارة الرياضة | توريد وتركيب | ذات اولوية متوسطة | 808500 | 40425 | 808500 | 808500 | 4030280934 | لا | 0 | 191201013848 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2020-01-07 | 2022-10-25 | 2022-10-25 | 2022-10-25 | 2022-10-25 |  |  |  | 46.6869 | 24.6797 | منجز | No
2100056582 | شركة المياه الوطنية / منطقة تبوك | إشراف | ذات اولوية متوسطة | 11388600 | 569430 | 329066.67 | 329066.67 | 1010320035 | لا | 0 | 180809050052 | جاري | التكلفة المفوترة | 1.16 | 0 | 2017-11-27 | 2020-10-26 | 2020-10-26 | 2020-10-26 |  |  | لا يوجد تأخير |  | 37.289 | 25.0332 | خدمات عامة | No
2100004060 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 119268750 | 5963437.5 | 60771709.97 | 60771709.97 | 2050011871 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2013-11-03 | 2016-04-07 | 2020-04-01 | 2020-04-01 | 2016-04-07 |  | لا يوجد تأخير |  | 39.135 | 21.5598 | منجز | No
2100038990 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية وعاجلة | 15798825 | 789941.25 | 8534605.87 | 8534605.87 | 4030087384 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 58.02 | 100 | 2018-09-04 | 2019-07-04 | 2019-12-28 | 2019-12-28 | 2019-07-04 |  | لا يوجد تأخير |  | 50.1622 | 26.1322 | منجز | No
2100098033 | شركة المياه الوطنية / منطقة الجوف | تشييد | ذات اولوية عالية | 13573173 | 678658.65 | 13572878 | 13572878 | 1010328073 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-01-29 | 2019-01-18 | 2019-10-27 | 2019-10-27 | 2019-01-18 | 2020-10-14 | لا يوجد تأخير |  | 37.9774 | 30.7217 | منجز | No
2100080080 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 10000000 | 500000 | 9289217.6 | 9289217.6 | 2057001398 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-06-11 | 2020-05-09 | 2019-10-10 | 2019-10-10 |  | 2020-05-09 | لا يوجد تأخير |  | 50.0947 | 26.3599 | منجز | No
2100059452 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 76832046 | 3841602.3 | 55666249.38 | 55666249.38 | 2050003475 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-02-01 | 2020-01-10 | 2020-01-10 | 2020-01-10 | 2020-01-10 |  | لا يوجد تأخير |  | 39.2248 | 21.4869 | منجز | No
2100062156 | شركة المياه الوطنية / منطقة الحدود الشمالية | تشييد | ذات اولوية عالية | 74687756.06 | 3734387.803 | 24009059.64 | 24009059.64 | 2055006347 | لا | 0 | 180901070882 | مسحوب | منهجية القيمة المكتسبة | 38.78 | 75.08 | 2018-11-25 | 2021-10-23 | 2023-12-30 | 2023-12-30 |  |  | تصاريح أعمال التنفيذ |  | 41.0754 | 31.0003 | مسحوب | No
2100004771 | الهيئة الملكية لمدينة الرياض | تشييد | ذات اولوية عالية | 40155640.6 | 2007782.03 | 40155640.6 | 40155640.6 | 2055002293 | لا | 0 | 190209009640 | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2019-05-15 | 2020-10-25 | 2021-01-22 | 2021-01-22 | 2020-10-25 |  | اخرى |  | 46.5573 | 24.6414 | منجز | No
2200229353 | أمانة / جدة | تشييد | ذات اولوية عالية وعاجلة | 28123603 | 1406180.15 | 6894781 | 6894781 | 1128003753 | لا | 0 |  | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 70 | 100 | 2021-12-01 | 2022-09-08 | 2022-09-08 | 2022-09-08 |  |  |  |  | 39.1925 | 21.4858 | Failed | No
2100052990 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 998550 | 49927.5 | 998550 | 998550 | 4605000749 | لا | 0 | 200101001130 | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2019-12-22 | 2020-12-10 | 2020-12-09 | 2020-12-09 | 2020-12-10 |  | اخرى |  | 39.7883 | 22.267 | منجز | No
2100194250 | أمانة / جدة | تشييد | ذات اولوية عالية | 43388924 | 2169446.2 | 29984836.7 | 27840208.55 | 4030082715 | لا | 0 | 191001037931 | جاري | الكميات التي تم تركيبها | 90.1 | 94 | 2020-10-08 | 2022-09-16 | 2022-12-24 | 2022-12-24 |  |  |  |  | 39.1677 | 21.5008 | منتظم | No
2200235664 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 154582968 | 7729148.4 | 52821358 | 52821358 | 4030023505 | نعم | 147326614 |  | جاري | منهجية القيمة المكتسبة | 40.5 | 43.63 | 2022-03-22 | 2024-01-03 | 2024-06-03 | 2024-06-03 |  |  |  |  | 38.19 | 24.0232 | منتظم | No
2100105766 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 45499410 | 2274970.5 | 27157966.1 | 27157966.1 | 2050003475 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-02-01 | 2020-01-10 | 2020-01-06 | 2020-01-06 |  | 2020-01-10 | لا يوجد تأخير |  | 39.3017 | 21.4534 | منجز | No
2100061121 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 109111240 | 5455562 | 98170200.39 | 98170200.39 | 4030082735 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 98 | 100 | 2010-09-27 | 2013-02-28 | 2019-11-07 | 2019-11-07 | 2013-02-28 |  | لا يوجد تأخير |  | 39.0484 | 22.7549 | منجز | No
2100099330 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية | 11618430 | 580921.5 | 7263816.15 | 7263816.15 | 4650052854 | لا | 0 | 180809062603 | مسحوب | منهجية القيمة المكتسبة | 70.55 | 100 | 2012-05-07 | 2013-10-21 | 2023-03-01 | 2023-03-01 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.6969 | 27.506 | مسحوب | No
2200235690 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البحرية | أخرى | ذات اولوية عالية وعاجلة | 15208750 | 760437.5 | 0 | 0 | 2050050438 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 12 | 10 | 2022-10-04 | 2023-04-02 | 2023-04-02 | 2023-04-02 |  |  |  |  | 48.6337 | 28.1126 | خدمات عامة | No
2200235675 | الهيئة العامة للموانئ | الخدمات الاستشارية | ذات اولوية عالية | 204700 | 10235 | 86250 | 86250 | 2050111809 | لا | 0 |  | جاري | تكلفة العمل المنجز | 80 | 100 | 2022-10-13 | 2023-01-13 | 2023-01-13 | 2023-01-13 |  |  |  |  | 50.1985 | 26.4407 | خدمات عامة | No
2100092400 | وزارة التعليم | تشييد | ذات اولوية عالية | 9374410.81 | 468720.5405 | 8438769.729 | 8438769.729 | 1010060469 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2011-12-10 | 2013-08-31 | 2020-08-17 | 2020-08-17 | 2013-08-31 |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | منجز | No
2200229596 | أمانة / جدة | تشييد | ذات اولوية عالية وعاجلة | 9945425 | 497271.25 | 8379874 | 8379873 | 4030149957 | لا | 0 | 181201547180 | جاري | الكميات التي تم تركيبها | 97 | 100 | 2019-05-16 | 2021-04-23 | 2022-08-04 | 2022-08-04 |  |  |  |  | 39.1925 | 21.4858 | متأخر | No
2100061246 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية وعاجلة | 160404922.22 | 8020246.111 | 78111905 | 70741013.98 | 1116000082 | لا | 0 | 200609052493 | جاري | منهجية القيمة المكتسبة | 86.7 | 98.06 | 2010-06-09 | 2013-05-06 | 2022-07-06 | 2022-07-06 |  |  | اخرى |  | 42.6384 | 17.158 | متأخر | No
2100060620 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 13868875 | 693443.75 | 13843542.25 | 13843542.25 | 2050008262 | لا | 0 | 180809050471 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-12-28 | 2020-12-28 | 2020-12-27 | 2020-12-27 |  | 2020-12-28 | لا يوجد تأخير |  | 50.0978 | 26.4329 | منجز | No
2100191100 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية وعاجلة | 52577739 | 2628886.95 | 7235746 | 5124831.44 | 2050018730 | لا | 0 | 200201137441 | جاري | منهجية القيمة المكتسبة | 18.94 | 40.16 | 2020-12-16 | 2023-12-16 | 2023-12-15 | 2023-12-15 |  |  |  |  | 42.6456 | 16.9524 | متأخر | No
2100082143 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 2117520 | 105876 | 2218354.27 | 2218354.27 | 4030006066 | لا | 0 |  | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2019-01-02 | 2019-12-22 | 2019-12-22 | 2019-12-22 | 2019-12-22 | 2020-06-28 | ضعف كفاءة المقاول الفنية |  | 41.5567 | 19.1935 | منجز | No
2100042626 | وزارة التعليم | تشييد | ذات اولوية عالية | 6405016 | 320250.8 | 1354334.8 | 1354334.8 | 1132000522 | لا | 0 |  | مسحوب | التكلفة المفوترة | 26 | 100 | 2014-11-15 | 2016-08-06 | 2022-01-01 | 2022-01-01 |  |  | ضعف كفاءة المقاول الفنية |  | 43.9544 | 26.3504 | مسحوب | No
2200235701 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البحرية | تشييد | ذات اولوية عالية وعاجلة | 13110000 | 655500 | 6877000 | 6877000 | 2050050438 | لا | 0 | 220609261978 | جاري | الكميات التي تم تركيبها | 63 | 70 | 2022-07-05 | 2023-02-26 | 2023-02-26 | 2023-02-26 |  |  |  |  | 48.641 | 28.1084 | متأخر | No
2200229611 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 19550000 | 977500 | 6451500 | 6451500 | 1010618324 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 33 | 39 | 2022-02-27 | 2026-02-26 | 2026-02-26 | 2026-02-26 |  |  |  |  | 39.5799 | 24.4515 | متأخر | No
2100086391 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية وعاجلة | 57178622.45 | 2858931.1225 | 21781251.51 | 15878567.86 | 1010277656 | نعم | 44483538.38 | 181001160555 | جاري | تكلفة العمل المنجز | 48 | 100 | 2018-11-07 | 2019-11-02 | 2025-12-31 | 2025-12-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 50.108 | 26.3778 | Failed | No
2100026110 | شركة المياه الوطنية / منطقة مكة المكرمة | إشراف | ذات اولوية عالية | 37710191 | 1885509.55 | 15026098.45 | 15026098.45 | 1010078921 | لا | 0 | 200709052696 | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 99 | 100 | 2014-08-20 | 2016-08-19 | 2020-11-19 | 2020-11-19 | 2016-08-19 |  | لا يوجد تأخير |  | 39.1958 | 21.5679 | منجز | No
2100104845 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية | 38843900 | 1942195 | 32383200 | 32383200 | 4650052854 | لا | 0 | 180809055266 | مسحوب | منهجية القيمة المكتسبة | 95.86 | 100 | 2011-10-01 | 2013-09-09 | 2023-03-01 | 2023-03-01 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 40.3294 | 26.8453 | مسحوب | No
2200235723 | أمانة / حفر الباطن | تشييد | ذات اولوية عالية | 745694.75 | 37284.7375 | 671276.165 | 671276.16 | 2511006133 | لا | 0 |  | جاري | تكلفة العمل المنجز | 92 | 81 | 2022-08-29 | 2023-02-25 | 2023-02-25 | 2023-02-25 |  |  |  |  | 46.0153 | 28.3571 | منتظم | No
2100105840 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 50049569.47 | 2502478.4735 | 50049569.47 | 50049569.47 | 1010026934 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 99.995 | 100 | 2018-02-01 | 2020-01-10 | 2019-12-07 | 2019-12-07 |  | 2020-01-10 | لا يوجد تأخير |  | 39.2193 | 21.4885 | منجز | No
2100191656 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية | 40738026 | 2036901.3 | 13593798.99 | 7254918.15 | 5850002600 | لا | 0 | 200601094978 | جاري | منهجية القيمة المكتسبة | 52.8 | 100 | 2020-12-22 | 2022-06-06 | 2022-12-06 | 2022-12-06 |  |  |  |  | 41.5298 | 27.7339 | Failed | No
2100079240 | الجمارك السعودية | تشييد | ذات اولوية عالية | 26817751.25 | 1340887.5625 | 26065689.05 | 26065689.05 | 1010065292 | لا | 0 | 180909073731 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-03-16 | 2017-02-22 | 2021-12-30 | 2021-12-30 | 2017-02-22 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 37.132 | 31.5029 | منجز | No
2200235734 | أمانة / حفر الباطن | تشييد | ذات اولوية عالية | 3721400 | 186070 | 3721400 | 3721400 | 2511006133 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2021-11-09 | 2022-11-20 | 2022-11-20 | 2022-11-20 | 2022-11-20 |  |  |  | 45.9198 | 28.432 | منجز | No
2100049173 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 37981938.84 | 1899096.942 | 19353835.23 | 19353835.23 | 5855000147 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 86 | 100 | 2019-03-17 | 2020-03-11 | 2023-03-31 | 2023-03-31 |  |  | أوامر تغيير | أخرى |  |  | متأخر | No
2100191354 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية وعاجلة | 99999956.47 | 4999997.8235 | 5919988.09 | 0 | 1010014477 | لا | 0 | 190801004796 | جاري | منهجية القيمة المكتسبة | 7.62 | 21.02 | 2021-04-27 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  |  | 42.9164 | 28.2595 | متأخر | Yes
2200235756 | أمانة / جدة | تشييد | ذات اولوية عالية | 8494705 | 424735.25 | 0 | 0 | 4030148791 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 4 | 4 | 2022-09-21 | 2023-05-20 | 2023-05-20 | 2023-05-20 |  |  |  |  | 39.1676 | 21.5008 | منتظم | No
2100191984 | شركة المياه الوطنية / منطقة الجوف | إشراف | ذات اولوية عالية وعاجلة | 3203100 | 160155 | 1365895.13 | 1365895.13 | 1131051650 | لا | 0 | 201101313605 | منجز – استلام نهائي | مدفوعات ساعات العمل | 100 | 100 | 2021-01-07 | 2022-06-22 | 2022-06-22 | 2022-06-22 | 2022-06-22 | 2022-11-13 |  |  | 40.2064 | 29.9538 | منجز | No
2100028696 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 3200000 | 160000 | 2750979.24 | 2750979.24 | 5857026966 | لا | 0 |  | مسحوب | التكلفة المفوترة | 45 | 100 | 2012-08-27 | 2013-11-21 | 2023-05-10 | 2023-05-10 |  |  | ضعف كفاءة المقاول الفنية |  | 42.4987 | 18.2178 | مسحوب | No
2100047725 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية عالية | 15977325 | 798866.25 | 2919376 | 2919376 | 4030044382 | لا | 0 | 200101049576 | جاري | تكلفة العمل المنجز | 16.48 | 16.48 | 2019-12-06 | 2022-09-05 | 2022-08-07 | 2022-08-07 |  |  |  |  | 39.8775 | 21.3943 | متأخر | No
2100026504 | شركة المياه الوطنية / منطقة مكة المكرمة | إشراف | ذات اولوية عالية | 12429000 | 621450 | 20343035.32 | 20343035.32 | 1010314421 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2012-02-04 | 2013-08-03 | 2020-05-31 | 2020-05-31 | 2013-08-03 |  | لا يوجد تأخير |  | 39.1806 | 21.5703 | منجز | No
2100080043 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية وعاجلة | 29996440 | 1499822 | 17977744.62 | 17977744.62 | 2050041707 | لا | 0 | 180801041963 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 98.77 | 99 | 2018-10-30 | 2020-10-31 | 2022-03-31 | 2022-03-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 50.1495 | 26.1626 | Failed | No
2100075666 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2267247 | 113362.35 | 2142061 | 0 | 1111000356 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 100 | 2014-05-14 | 2015-11-05 | 2019-09-13 | 2019-09-13 | 2015-11-05 |  | ضعف كفاءة المقاول الفنية |  | 46.1295 | 24.6032 | منجز | Yes
2100080054 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية وعاجلة | 23087715 | 1154385.75 | 18726025.43 | 18726025.43 | 2054001362 | لا | 0 | 180809051619 | جاري | منهجية القيمة المكتسبة | 93.6 | 100 | 2018-01-15 | 2020-07-15 | 2022-04-19 | 2022-04-19 |  |  | اخرى |  | 50.1494 | 26.1594 | متأخر | No
2200235771 | أمانة / جدة | تشييد | ذات اولوية عالية | 10344057 | 517202.85 | 4283848 | 4283848 | 1010997845 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 86 | 86 | 2019-10-17 | 2022-12-10 | 2022-12-10 | 2022-12-10 |  |  |  |  | 39.1676 | 21.5008 | منتظم | No
2200235760 | أمانة / جدة | دراسات هندسية | ذات اولوية عالية | 24803460 | 1240173 | 0 | 0 | 1010464778 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 11 | 11 | 2022-09-29 | 2025-08-17 | 2025-08-17 | 2025-08-17 |  |  |  |  | 39.1676 | 21.5008 | خدمات عامة | No
2200235793 | جامعة الجوف | ترميم | ذات اولوية عالية | 15470258.42 | 773512.921 | 1450000 | 0 | 3400009021 | لا | 0 |  | جاري | تكلفة العمل المنجز | 25 | 25 | 2022-10-11 | 2023-08-12 | 2023-08-12 | 2023-08-12 |  |  |  |  | 40.045 | 29.7907 | منتظم | Yes
2100096176 | شركة المياه الوطنية / المنطقة الشرقية | إشراف | ذات اولوية عالية | 2947230 | 147361.5 | 2766849.39 | 2766849.39 | 2051063103 | لا | 0 | 180809044139 | جاري | التكلفة المفوترة | 97.33 | 100 | 2017-11-06 | 2019-05-06 | 2019-05-06 | 2019-05-06 |  |  | لا يوجد تأخير |  | 45.9738 | 28.4039 | خدمات عامة | No
2100059975 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 66490150 | 3324507.5 | 50357710.46 | 50357710.46 | 2050001536 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 92.26 | 100 | 2019-05-29 | 2021-05-06 | 2021-06-28 | 2021-06-28 | 2021-05-06 |  | لا يوجد تأخير |  | 39.2496 | 21.506 | منجز | No
2200235826 | أمانة / جدة | تشييد | ذات اولوية عالية | 31144948 | 1557247.4 | 0 | 0 | 1010033701 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 10 | 18 | 2022-06-29 | 2024-06-06 | 2024-06-06 | 2024-06-06 |  |  |  |  | 39.1676 | 21.5007 | متأخر | No
2200235815 | جامعة الجوف | أخرى | ذات اولوية عالية | 10411065 | 520553.25 | 0 | 0 | 7009403226 | لا | 0 |  | جاري | تكلفة العمل المنجز | 40 | 40 | 2022-10-19 | 2023-03-19 | 2023-03-19 | 2023-03-19 |  |  |  |  | 40.045 | 29.7907 | خدمات عامة | No
2100043234 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 26424346 | 1321217.3 | 18343306.6 | 18343306.6 | 2050001536 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 88.63 | 100 | 2018-02-18 | 2020-01-27 | 2022-01-31 | 2022-01-31 | 2020-01-27 |  | اخرى |  | 39.1656 | 21.5122 | منجز | No
2100102900 | شركة المياه الوطنية / المنطقة الشرقية | إشراف | ذات اولوية عالية | 6885000 | 344250 | 6879690.42 | 6879690.42 | 2050101543 | لا | 0 | 180501008821 | جاري | التكلفة المفوترة | 99.92 | 100 | 2018-08-05 | 2020-02-04 | 2023-08-13 | 2023-08-13 |  |  | لا يوجد تأخير |  | 49.6012 | 25.399 | خدمات عامة | No
2100100100 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 70980350 | 3549017.5 | 35392434.4 | 35392434.4 | 1010012911 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 74.64 | 100 | 2018-05-31 | 2020-05-09 | 2021-10-24 | 2021-10-24 | 2020-05-09 |  | لا يوجد تأخير |  | 40.6578 | 21.2746 | منجز | No
2100191914 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 68855795 | 3442789.75 | 0 | 0 | 5851002147 | لا | 0 | 2200006105 | ايقاف كلي | منهجية القيمة المكتسبة | 10.2 | 51.31 | 2020-06-21 | 2022-11-23 | 2023-08-27 | 2023-08-27 |  |  |  |  | 40.3074 | 20.1243 | Failed | No
2100107155 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 192629111.4 | 9631455.57 | 10972182.31 | 9880042.672 | 1010034808 | لا | 0 | 180709019924 | ايقاف كلي | تكلفة العمل المنجز | 20 | 95 | 2013-09-09 | 2016-02-26 | 2026-12-31 | 2026-12-31 |  |  | تأخرصرف المستحقات المالية |  | 39.2697 | 21.6179 | Failed | No
2200235830 | الهيئة الملكية لمحافظة العلا | تصميم وتشييد | ذات اولوية متوسطة | 43147826.4 | 2157391.32 | 2632017.27 | 2632017.27 | 3550005809 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 15 | 18 | 2022-06-25 | 2023-08-25 | 2023-08-25 | 2023-08-25 |  |  |  |  | 37.9936 | 26.509 | منتظم | No
2100006053 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 19681125 | 984056.25 | 14956343 | 14956343 | 4031012950 | لا | 0 | 190401134963 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 88.15 | 100 | 2019-09-05 | 2021-08-14 | 2022-01-31 | 2022-01-31 | 2021-08-14 |  | لا يوجد تأخير |  | 40.8645 | 20.4241 | منجز | No
2100016866 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 169800000 | 8490000 | 112648793.25 | 112648793.25 | 2050027608 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 75.99 | 100 | 2014-08-14 | 2017-07-12 | 2023-02-13 | 2023-02-13 |  |  | اخرى |  | 39.235 | 21.5868 | Failed | No
2100039874 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية | 77570683.73 | 3878534.1865 | 36831209.61 | 36069233.38 | 1010233574 | لا | 0 | 180709023151 | ايقاف كلي | تكلفة العمل المنجز | 62 | 100 | 2013-05-06 | 2015-10-23 | 2025-12-31 | 2025-12-31 |  |  | تأخرصرف المستحقات المالية |  | 42.6403 | 17.208 | Failed | No
2100000954 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية | 99591607.41 | 4979580.3705 | 21930146.81 | 19945923.35 | 1010034808 | لا | 0 | 180709019935 | ايقاف كلي | تكلفة العمل المنجز | 40 | 100 | 2014-04-30 | 2016-10-16 | 2026-12-31 | 2026-12-31 |  |  | تأخرصرف المستحقات المالية |  | 39.3522 | 21.4091 | Failed | No
2100087474 | شركة المياه الوطنية / منطقة حائل | تشييد | لم تعد تحتاجها الجهة | 33950600 | 1697530 | 33950600 | 33950600 | 4700009877 | لا | 0 | 181109337467 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-03-27 | 2020-08-29 | 2020-09-03 | 2020-09-03 |  | 2020-08-29 | لا يوجد تأخير |  | 40.9035 | 27.1645 | منجز | No
2100191800 | شركة المياه الوطنية / منطقة حائل | إشراف | ذات اولوية منخفضة | 5630260 | 281513 | 10543605.19 | 10543605.19 | 1010314421 | لا | 0 | 180709026055 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-01-06 | 2016-07-06 | 2022-01-30 | 2022-01-30 | 2016-07-06 |  | اخرى |  | 41.8912 | 27.8415 | منجز | No
2200235852 | الهيئة العامة للموانئ | تشييد | ذات اولوية عالية | 184000000 | 9200000 | 0 | 0 | 4030219311 | لا | 0 | 220501001338 | جاري | تكلفة العمل المنجز | 10 | 15 | 2022-09-01 | 2024-08-21 | 2024-08-21 | 2024-08-21 |  |  |  |  | 39.1342 | 21.4834 | منتظم | No
2100019865 | شركة المياه الوطنية / منطقة الجوف | تشييد | ذات اولوية عالية | 22986311 | 1149315.55 | 22986311 | 22986311 | 1010090267 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2015-07-26 | 2016-07-15 | 2017-02-24 | 2017-02-24 | 2016-07-15 | 2021-03-22 | لا يوجد تأخير |  | 38.2213 | 30.198 | منجز | No
2100084313 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 86355146 | 4317757.3 | 83032574 | 83032574 | 4650007032 | لا | 0 | 181109337860 | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2011-08-29 | 2014-01-29 | 2021-01-31 | 2021-01-31 | 2014-01-29 | 2021-01-31 |  |  | 39.8743 | 21.3866 | منجز | No
2100001680 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 13186477.18 | 659323.859 | 1719373.56 | 0 | 7001682611 | لا | 0 | 200609152679 | مسحوب | التكلفة المفوترة | 16 | 84 | 2015-12-06 | 2017-11-25 | 2022-08-17 | 2022-08-17 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | مسحوب | Yes
2100000991 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية وعاجلة | 85010167.34 | 4250508.367 | 30121537.37 | 30121537.37 | 2050040480 | لا | 0 | 180709022504 | جاري | تكلفة العمل المنجز | 57 | 100 | 2014-03-18 | 2016-09-03 | 2025-12-31 | 2025-12-31 |  |  | تأخرصرف المستحقات المالية |  | 49.6143 | 25.9166 | Failed | No
2100039443 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 90787992 | 4539399.6 | 86087992 | 86087992 | 4030179603 | لا | 0 | 180809040668 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-03-11 | 2020-03-10 | 2022-10-27 | 2022-10-27 | 2020-03-10 |  | تأخرصرف المستحقات المالية |  | 38.3605 | 23.9232 | منجز | No
2100201725 | شركة المياه الوطنية / منطقة مكة المكرمة | إشراف | ذات اولوية عالية وعاجلة | 5199876 | 259993.8 | 2968348.82 | 2968348.82 | 1010325732 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 54.33 | 67 | 2019-06-24 | 2022-06-24 | 2022-06-28 | 2022-06-28 |  |  |  |  | 39.1925 | 21.4858 | خدمات عامة | No
2100106105 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية وعاجلة | 57643030 | 2882151.5 | 20280406.23 | 17642341.08 | 2050101650 | لا | 0 |  | جاري | مدفوعات ساعات العمل | 39.46 | 21.63 | 2018-03-05 | 2019-11-06 | 2023-01-05 | 2023-01-05 |  |  | لا يوجد تأخير |  | 50.2033 | 26.2428 | منتظم | No
2100106083 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 14993760 | 749688 | 6345443 | 6345443 | 2050003475 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-12-14 | 2019-12-14 | 2019-12-08 | 2019-12-08 |  | 2019-12-14 | لا يوجد تأخير |  | 39.3322 | 21.466 | منجز | No
2100047040 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1689966 | 84498.3 | 372585 | 0 | 1116004307 | لا | 0 |  | مسحوب | اخرى | 23 | 100 | 2015-04-16 | 2016-07-09 | 2016-11-12 | 2016-11-12 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6891 | 24.7019 | مسحوب | Yes
2100057234 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية | 78268059.6 | 3913402.98 | 32762257.49 | 32479004.33 | 5950009827 | لا | 0 | 180709023364 | جاري | تكلفة العمل المنجز | 57 | 97 | 2014-03-24 | 2016-09-09 | 2025-12-31 | 2025-12-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.9178 | 16.635 | Failed | No
2100003032 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 692099.7 | 34604.985 | 0 | 0 | 5852002001 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0 | 100 | 2010-04-30 | 2010-12-26 | 2023-02-07 | 2023-02-07 |  |  | ضعف كفاءة المقاول الفنية |  | 42.4987 | 18.2178 | مسحوب | No
2100089854 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية | 78339749.65 | 3916987.4825 | 32015523.21 | 28315195.91 | 1010034808 | لا | 0 | 180709019903 | ايقاف كلي | تكلفة العمل المنجز | 60 | 100 | 2014-05-06 | 2016-10-22 | 2025-12-31 | 2025-12-31 |  |  | تأخرصرف المستحقات المالية |  | 39.3523 | 21.4074 | Failed | No
2100005670 | وزارة التعليم | تشييد | ذات اولوية عالية | 4259083.4 | 212954.17 | 784662.15 | 784662.15 | 5950005409 | لا | 0 | 200301122479 | منجز – استلام ابتدائي | التكلفة المفوترة | 93 | 50 | 2018-01-14 | 2018-10-11 | 2022-11-09 | 2022-11-09 | 2018-10-11 |  | ضعف كفاءة المقاول الفنية |  | 42.6509 | 17.1567 | منجز | No
2100027731 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 1901447 | 95072.35 | 1449640 | 1449640 | 5855005104 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 98 | 100 | 2015-01-13 | 2017-01-02 | 2022-02-25 | 2022-02-25 | 2017-01-02 |  | ضعف كفاءة المقاول الفنية |  | 42.4987 | 18.2178 | منجز | No
2100011653 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 61943433.79 | 3097171.6895 | 33005617.09 | 33005617.09 | 1010054406 | لا | 0 |  | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2013-08-20 | 2015-08-10 | 2022-12-31 | 2022-12-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال | أخرى | 40.197 | 29.9622 | Failed | No
2100008326 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البرية | تشييد | ذات اولوية متوسطة | 2776000 | 138800 | 2776000 | 2776000 | 3550126308 | لا | 0 | 191101275178 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-08-22 | 2020-02-21 | 2022-02-28 | 2022-02-28 | 2020-02-21 |  | تأخرصرف المستحقات المالية |  | 46.1317 | 28.3165 | منجز | No
2200235885 | وزارة الرياضة | تشييد | ذات اولوية متوسطة | 2928982.15 | 146449.1075 | 171810 | 171810 | 1010019520 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2022-05-15 | 2022-11-14 | 2022-11-14 | 2022-11-14 | 2022-11-14 |  |  |  | 39.5468 | 24.5133 | منجز | No
2200226225 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية وعاجلة | 812885 | 40644.25 | 0 | 0 | 5855021168 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 81.5 | 26.38 | 2022-04-17 | 2022-10-17 | 2022-10-17 | 2022-10-17 |  |  |  |  | 42.5706 | 16.8894 | منتظم | No
2100001190 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 7071425 | 353571.25 | 7071425 | 7071425 | 2251027822 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-02-21 | 2020-02-21 | 2019-09-28 | 2019-09-28 |  | 2020-02-21 | لا يوجد تأخير |  | 49.5775 | 25.3144 | منجز | No
2100039830 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 48020535 | 2401026.75 | 43502948 | 40101601 | 1010070601 | لا | 0 | 180809039892 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99 | 100 | 2015-08-04 | 2017-08-03 | 2022-11-14 | 2022-11-14 | 2017-08-03 |  | ضعف كفاءة المقاول الفنية |  | 38.3952 | 23.8389 | منجز | No
2200235896 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 12908520 | 645426 | 2016008 | 2016008 | 2251007095 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 35 | 35 | 2022-07-13 | 2024-07-02 | 2024-07-02 | 2024-07-02 |  |  |  |  | 49.5826 | 25.3611 | منتظم | No
2100043072 | وزارة التعليم | تشييد | ذات اولوية عالية | 1764535.53 | 88226.7765 | 1135925.6 | 1135925.6 | 4601000417 | لا | 0 | 190709018738 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2017-08-22 | 2018-08-17 | 2022-04-10 | 2022-04-10 | 2018-08-17 |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | منجز | No
2100042486 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 4386127.2 | 219306.36 | 0 | 0 | 1010188602 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0 | 100 | 2008-07-02 | 2009-12-23 | 2023-02-09 | 2023-02-09 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.5429 | 16.8808 | مسحوب | No
2100104554 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1100000 | 55000 | 0 | 0 | 1010242292 | لا | 0 |  | مسحوب | التكلفة المفوترة | 5 | 100 | 2013-05-13 | 2014-01-08 | 2023-01-24 | 2023-01-24 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0859 | 19.1571 | مسحوب | No
2200235900 | وزارة الرياضة | تشييد | ذات اولوية متوسطة | 3786283 | 189314.15 | 1239142.25 | 1125050.75 | 1010144692 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 100 | 100 | 2022-06-30 | 2022-12-29 | 2022-12-29 | 2022-12-29 |  |  |  |  | 43.9971 | 26.062 | منتظم | No
2100063921 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 436814.7 | 21840.735 | 0 | 0 | 1010214210 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 90 | 2019-12-18 | 2021-03-07 | 2021-03-07 | 2021-03-07 | 2021-03-07 |  | ضعف كفاءة المقاول الفنية |  | 45.4646 | 25.0653 | منجز | No
2100096736 | وزارة التعليم | تشييد | لم تعد تحتاجها الجهة | 2990560 | 149528 | 1175681 | 1175681 | 1010069591 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 42 | 100 | 2010-01-16 | 2011-04-12 | 2021-11-14 | 2021-11-14 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 43.1379 | 18.0853 | مسحوب | No
2100078746 | شركة المياه الوطنية / منطقة الجوف | إشراف | ذات اولوية عالية | 2999880 | 149994 | 3939642.92 | 3939642.92 | 4030188113 | لا | 0 | 180709024226 | منجز – استلام نهائي | التكلفة المفوترة | 100 | 100 | 2017-11-09 | 2019-11-08 | 2021-02-02 | 2021-02-02 | 2019-11-08 | 2021-02-03 | لا يوجد تأخير |  | 37.3527 | 31.3243 | منجز | No
2100097716 | وزارة التعليم | تشييد | ذات اولوية عالية | 7618101.88 | 380905.094 | 5944969.42 | 4582372.23 | 1132002624 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-01-12 | 2015-10-04 | 2021-04-28 | 2021-04-28 | 2015-10-04 |  | ضعف كفاءة المقاول الفنية |  | 39.836 | 21.4408 | منجز | No
2200235922 | وزارة الرياضة | تشييد | ذات اولوية متوسطة | 878117 | 43905.85 | 878117 | 878117 | 1010144692 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 100 | 100 | 2022-06-30 | 2022-12-29 | 2022-12-29 | 2022-12-29 |  |  |  |  | 39.2177 | 21.5631 | منتظم | No
2200226236 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية وعاجلة | 1549487 | 77474.35 | 0 | 0 | 5855021168 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 39.6 | 26.8 | 2022-04-17 | 2022-10-17 | 2022-10-17 | 2022-10-17 |  |  |  |  | 42.5922 | 16.8808 | منتظم | No
2100079122 | وزارة التعليم | تشييد | ذات اولوية عالية | 9446518.64 | 472325.932 | 1873736 | 1873736 | 1010187466 | لا | 0 |  | مسحوب | التكلفة المفوترة | 45 | 100 | 2014-01-09 | 2017-04-26 | 2023-03-25 | 2023-03-25 |  |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | مسحوب | No
2100006086 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية وعاجلة | 126467375.42 | 6323368.771 | 102596990.42 | 90597269.69 | 1010152370 | لا | 0 | 180709025296 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-05-15 | 2016-10-31 | 2022-05-04 | 2022-05-04 | 2016-10-31 |  | تأخرصرف المستحقات المالية |  | 42.789 | 18.3692 | منجز | No
2200235944 | وزارة الرياضة | تشييد | ذات اولوية متوسطة | 3595625.3 | 179781.265 | 438086.25 | 438086.25 | 1010144692 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 85 | 85 | 2022-06-29 | 2022-12-28 | 2023-01-25 | 2023-01-25 |  |  |  |  | 40.4776 | 21.4364 | منتظم | No
2100099083 | شركة المياه الوطنية / المنطقة الشرقية | إشراف | ذات اولوية عالية | 12527460 | 626373 | 12518057.61 | 12405890.94 | 2050099462 | لا | 0 | 180709035935 | جاري | التكلفة المفوترة | 96.63 | 100 | 2017-10-31 | 2020-11-01 | 2021-10-19 | 2021-10-19 |  |  | لا يوجد تأخير |  | 49.587 | 26.9628 | خدمات عامة | No
2100056980 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 67554129.3 | 3377706.465 | 67554129.3 | 67554129.3 | 1010026934 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 90.94 | 2017-09-11 | 2019-08-20 | 2019-08-20 | 2019-08-20 | 2019-08-20 |  | لا يوجد تأخير |  | 39.2962 | 21.3807 | منجز | No
2200235955 | وزارة الرياضة | تشييد | ذات اولوية متوسطة | 3563269.25 | 178163.4625 | 2232661.75 | 1248970.15 | 1010144692 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 65 | 65 | 2022-07-31 | 2023-01-30 | 2023-01-30 | 2023-01-30 |  |  |  |  | 46.0746 | 28.4485 | منتظم | No
2100096305 | شركة المياه الوطنية / المنطقة الشرقية | إشراف | ذات اولوية عالية | 15218280 | 760914 | 14472850.99 | 14472850.99 | 1010314421 | لا | 0 | 180201000396 | جاري | التكلفة المفوترة | 95.1 | 100 | 2018-06-05 | 2021-06-06 | 2022-02-21 | 2022-02-21 |  |  | لا يوجد تأخير |  | 50.089 | 26.4113 | خدمات عامة | No
2100075670 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1677300 | 83865 | 42073 | 0 | 1010268824 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 1 | 100 | 2015-08-08 | 2016-10-01 | 2020-10-10 | 2020-10-10 |  |  | تأخرصرف المستحقات المالية |  | 46.3865 | 24.9052 | مسحوب | Yes
2200236036 | أمانة / العاصمة المقدسة | الخدمات الاستشارية | ذات اولوية متوسطة | 8238925 | 411946.25 | 7721775 | 7721775 | 1010321498 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 98.57 | 98.57 | 2014-06-22 | 2017-06-21 | 2017-06-21 | 2017-06-21 | 2017-06-21 |  |  |  | 39.8579 | 21.3891 | منجز | No
2200236095 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 37963800 | 1898190 | 29390711 | 29390711 | 4031030163 | لا | 0 |  | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2015-03-22 | 2017-03-21 | 2017-08-21 | 2017-08-21 | 2017-03-21 | 2020-09-07 |  |  | 39.8579 | 21.3891 | منجز | No
2200235970 | وزارة الرياضة | تشييد | ذات اولوية متوسطة | 5380717.75 | 269035.8875 | 0 | 0 | 1010056286 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 0 | 0 | 2021-12-12 | 2022-02-12 | 2023-06-12 | 2023-06-12 |  |  |  |  | 39.1642 | 21.7633 | Failed | No
2200235981 | وزارة الرياضة | تشييد | ذات اولوية متوسطة | 3581286.3 | 179064.315 | 0 | 0 | 1010144692 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 70 | 70 | 2022-07-31 | 2023-01-30 | 2023-01-30 | 2023-01-30 |  |  |  |  | 50.0319 | 26.4736 | منتظم | No
2200235992 | وزارة الرياضة | تشييد | ذات اولوية متوسطة | 1687699.75 | 84384.9875 | 1455687.25 | 1455687.25 | 1010735699 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2022-09-08 | 2022-12-07 | 2022-12-07 | 2022-12-07 | 2022-12-07 |  |  |  | 42.5978 | 16.8395 | منجز | No
2100016774 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البرية | تشييد | ذات اولوية عالية | 955195.5 | 47759.775 | 955195.5 | 955195.5 | 5903011198 | لا | 0 | 191001000520 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-09-02 | 2020-02-25 | 2020-02-25 | 2020-02-25 | 2020-02-25 |  | اخرى |  | 42.7814 | 18.2776 | منجز | No
2100093380 | شركة المياه الوطنية / المنطقة الشرقية | إشراف | ذات اولوية عالية | 3264000 | 163200 | 1693731.15 | 1693731.15 | 2050101543 | لا | 0 | 190701160511 | جاري | التكلفة المفوترة | 56.75 | 100 | 2019-01-23 | 2020-05-22 | 2022-04-23 | 2022-04-23 |  |  | لا يوجد تأخير |  | 49.6631 | 25.4191 | خدمات عامة | No
2100011852 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2147569 | 107378.45 | 891005 | 396663 | 4603005625 | لا | 0 | 191101066049 | جاري | التكلفة المفوترة | 95 | 100 | 2019-09-01 | 2020-06-27 | 2023-02-01 | 2023-02-01 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0859 | 19.1571 | Failed | No
2200236084 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 16702800 | 835140 | 1591534.4 | 1591534.4 | 4030044382 | لا | 0 |  | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 95.27 | 95.27 | 2015-12-09 | 2018-06-08 | 2018-06-08 | 2018-06-08 |  |  |  |  | 39.8579 | 21.3891 | Failed | No
2100006193 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية | 19945000 | 997250 | 6422157.06 | 5128141.01 | 1010287764 | نعم | 21386107.93 | 190501113214 | ايقاف كلي | تكلفة العمل المنجز | 94 | 100 | 2019-01-09 | 2020-01-04 | 2025-12-31 | 2025-12-31 |  |  | تأخرصرف المستحقات المالية |  | 47.1856 | 23.9745 | Failed | No
2100099536 | شركة المياه الوطنية / المنطقة الشرقية | دراسات هندسية | ذات اولوية عالية | 20987879.85 | 1049393.9925 | 16165208.66 | 13711228.81 | 1010282788 | لا | 0 | 190501079977 | جاري | منهجية القيمة المكتسبة | 92.16 | 100 | 2019-09-29 | 2021-03-30 | 2022-06-30 | 2022-06-30 |  |  | لا يوجد تأخير |  | 50.1756 | 26.3728 | خدمات عامة | No
2100060745 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 138422538 | 6921126.9 | 92959969.2 | 92959969.2 | 1010067433 | لا | 0 | 180801063742 | جاري | منهجية القيمة المكتسبة | 91.13 | 99.49 | 2019-04-16 | 2022-03-14 | 2022-09-30 | 2022-09-30 |  |  | اخرى |  | 41.0803 | 19.1363 | متأخر | No
2100081896 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 10063731 | 503186.55 | 10063731 | 10063731 | 2050018628 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 95 | 100 | 2019-06-12 | 2020-11-25 | 2021-02-16 | 2021-02-16 | 2020-11-25 |  |  |  | 50.1526 | 26.3417 | منجز | No
2100009623 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 30541989.72 | 1527099.486 | 22392264.71 | 22392264.71 | 1010134746 | لا | 0 | 180809059296 | جاري | تكلفة العمل المنجز | 87 | 96 | 2017-02-01 | 2020-07-19 | 2023-01-29 | 2023-01-29 |  |  | اخرى | تم إشعار المقاول كتابيا بالتأخير | 49.6626 | 27.0037 | متأخر | No
2100087113 | رئاسة أمن الدولة / ديوان رئاسة أمن الدولة | تشييد | ذات اولوية عالية وعاجلة | 97435985.59 | 4871799.2795 | 29156855.92 | 29156855.92 | 1010024600 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 58 | 100 | 2019-08-06 | 2021-04-27 | 2023-06-14 | 2023-06-14 |  |  | تغيرات في نطاق المشروع |  | 46.9279 | 24.8899 | Failed | No
2200236003 | وزارة الرياضة | تشييد | ذات اولوية متوسطة | 3374462.25 | 168723.1125 | 1666913.5 | 1666913.5 | 1010289648 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 70 | 70 | 2022-09-11 | 2023-03-10 | 2023-03-10 | 2023-03-10 |  |  |  |  | 43.5023 | 25.8622 | منتظم | No
2200236132 | وزارة الرياضة | تشييد | ذات اولوية متوسطة | 998200 | 49910 | 998200 | 0 | 1010289648 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2022-03-03 | 2022-10-04 | 2022-06-02 | 2022-06-02 | 2022-10-04 |  |  |  | 50.1141 | 26.4272 | منجز | Yes
2100001223 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 45205538.98 | 2260276.949 | 16869035.36 | 16869035.36 | 1010074608 | لا | 0 | 180709021906 | ايقاف كلي | تكلفة العمل المنجز | 70 | 100 | 2014-03-13 | 2015-11-03 | 2025-12-31 | 2025-12-31 |  |  | تأخرصرف المستحقات المالية |  | 39.2269 | 21.527 | Failed | No
2100079936 | شركة المياه الوطنية / منطقة الجوف | تشييد | ذات اولوية عالية | 25958275 | 1297913.75 | 22613604.76 | 22613604.76 | 1116002219 | لا | 0 | 180201000139 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-03-27 | 2020-03-05 | 2021-11-14 | 2021-11-14 | 2020-03-05 |  | لا يوجد تأخير |  | 37.4215 | 31.2678 | منجز | No
2200236121 | أمانة / العاصمة المقدسة | أخرى | ذات اولوية متوسطة | 61515993 | 3075799.65 | 57602605.9 | 57602605.9 | 4030043565 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 93.67 | 93.67 | 2020-02-25 | 2022-02-24 | 2022-02-24 | 2022-02-24 | 2022-02-24 |  |  |  | 39.8579 | 21.3891 | منجز | No
2200236110 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 3560072.25 | 178003.6125 | 0 | 0 | 4031056144 | لا | 0 |  | جاري | تكلفة العمل المنجز | 0 | 0 | 2021-08-24 | 2023-08-23 | 2023-08-23 | 2023-08-23 |  |  |  |  | 39.8579 | 21.3891 | منتظم | No
2100082526 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية عالية | 9492850 | 474642.5 | 6071622.5 | 6071622.5 | 4031058315 | لا | 0 | 180709029018 | فسخ العقد | التكلفة المفوترة | 67.95 | 67.95 | 2014-12-28 | 2020-06-22 | 2020-06-22 | 2020-06-22 |  |  |  |  | 39.8674 | 21.3667 | مسحوب | No
2100071131 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1650000 | 82500 | 42103 | 0 | 1010245708 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 9 | 100 | 2015-10-31 | 2017-01-23 | 2021-07-04 | 2021-07-04 |  |  | تأخرصرف المستحقات المالية |  | 46.4527 | 24.7931 | Failed | Yes
2200236165 | أمانة / الطائف | تصميم وإشراف | ذات اولوية عالية | 5405184 | 270259.2 | 0 | 0 | 4030281454 | لا | 0 |  | جاري | مدفوعات ساعات العمل | 22 | 25 | 2021-12-01 | 2024-11-30 | 2024-11-30 | 2024-11-30 |  |  |  |  | 40.4248 | 21.2841 | منتظم | No
2200236154 | أمانة / الباحة | توريد | ذات اولوية عالية | 409400 | 20470 | 409400 | 0 | 5800011374 | لا | 0 |  | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 100 | 100 | 2022-10-24 | 2022-10-27 | 2022-10-27 | 2022-10-27 |  |  |  |  | 41.3883 | 20.3871 | Failed | Yes
2200236143 | أمانة / الباحة | تشييد | ذات اولوية عالية وعاجلة | 555404 | 27770.2 | 0 | 0 | 5805009876 | لا | 0 |  | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 100 | 100 |  | 2023-03-24 | 2023-03-24 | 2023-03-24 |  |  |  | أخرى | 41.3882 | 20.3871 | منتظم | No
2200236014 | أمانة / العاصمة المقدسة | الخدمات الاستشارية | ذات اولوية متوسطة | 494500 | 24725 | 0 | 0 | 4031063586 | لا | 0 |  | جاري | تكلفة العمل المنجز | 0 | 0 | 2022-07-19 | 2025-05-17 | 2025-05-17 | 2025-05-17 |  |  |  |  | 39.8579 | 21.3891 | خدمات عامة | No
2100016063 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البرية | تشييد | ذات اولوية منخفضة | 1778500 | 88925 | 1692760 | 1692760 | 1010411125 | لا | 0 | 200601049492 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-01-12 | 2020-09-08 | 2021-03-21 | 2021-03-21 | 2020-09-08 |  | المشروع ليس ذو أولوية في الوقت الحالي |  | 46.6814 | 24.7057 | منجز | No
2100064164 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1056075 | 52803.75 | 42113 | 0 | 1010211585 | لا | 0 | 4040225 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-08-23 | 2017-02-13 | 2019-10-13 | 2019-10-13 | 2017-02-13 |  | ضعف كفاءة المقاول الفنية |  | 46.5007 | 23.6168 | منجز | Yes
2100034090 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | دراسات هندسية | ذات اولوية عالية وعاجلة | 17891115 | 894555.75 | 17013049.54 | 17013049.54 | 1010412691 | لا | 0 | 180809058698 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 90 | 100 | 2015-02-09 | 2020-02-09 | 2023-02-09 | 2023-02-09 | 2020-02-09 |  |  | أخرى | 49.5436 | 26.954 | منجز | No
2200236202 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 57130937.5 | 2856546.875 | 10812907.25 | 10812907.25 | 4031032312 | لا | 0 |  | جاري | تكلفة العمل المنجز | 18.93 | 18.93 | 2021-08-01 | 2024-08-01 | 2024-08-01 | 2024-08-01 |  |  |  |  | 39.8579 | 21.3891 | منتظم | No
2100004104 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 3577209.33 | 178860.4665 | 2832538 | 2832538 | 1010326204 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-05-10 | 2016-07-03 | 2020-03-03 | 2020-03-03 | 2016-07-03 |  | ضعف كفاءة المقاول الفنية |  | 41.0859 | 19.1571 | منجز | No
2200236180 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 2699430.83 | 134971.5415 | 0 | 0 | 4031040484 | لا | 0 |  | جاري | تكلفة العمل المنجز | 29.64 | 29.64 | 2020-05-13 | 2022-04-21 | 2022-04-21 | 2022-04-21 |  |  |  |  | 39.8579 | 21.3891 | Failed | No
2200236250 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 57130937.5 | 2856546.875 | 6627812.99 | 6627812.99 | 4031032312 | لا | 0 |  | جاري | تكلفة العمل المنجز | 11.6 | 11.6 | 2021-08-01 | 2024-08-01 | 2024-08-01 | 2024-08-01 |  |  |  |  | 39.8579 | 21.3891 | منتظم | No
2200236191 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 3318140 | 165907 | 1 | 1 | 4030120858 | لا | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 5.6 | 5.6 | 2014-12-02 | 2015-11-21 | 2016-03-28 | 2016-03-28 |  |  |  |  | 39.8579 | 21.3891 | Failed | No
2100106466 | شركة المياه الوطنية / منطقة الجوف | تشييد | ذات اولوية متوسطة | 74997529.2 | 3749876.46 | 18661985.4 | 18661985.4 | 1010199022 | لا | 0 | 180709029295 | فسخ العقد | منهجية القيمة المكتسبة | 31.15 | 100 | 2014-10-19 | 2017-09-16 | 2023-04-19 | 2023-04-19 |  |  | عدم وجود مبالغ في البنود تغطي الأعمال المرصودة |  | 37.3406 | 31.3029 | مسحوب | No
2200236025 | أمانة / العاصمة المقدسة | الخدمات الاستشارية | ذات اولوية متوسطة | 1260000 | 63000 | 903467 | 903467 | 4031063586 | لا | 0 |  | جاري | تكلفة العمل المنجز | 68.05 | 68.05 | 2021-02-03 | 2023-12-03 | 2023-12-03 | 2023-12-03 |  |  |  |  | 39.8579 | 21.3891 | خدمات عامة | No
2100105604 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 81636812.75 | 4081840.6375 | 74692049.06 | 74692049.06 | 2050027608 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2016-05-17 | 2019-04-16 | 2020-03-04 | 2020-03-04 | 2019-04-16 |  | لا يوجد تأخير |  | 50.0583 | 26.3961 | منجز | No
2200236272 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 53013356.71 | 2650667.8355 | 10409949.93 | 10409949.93 | 4031032312 | لا | 0 |  | جاري | تكلفة العمل المنجز | 19.64 | 19.64 | 2021-08-01 | 2024-08-01 | 2024-08-01 | 2024-08-01 |  |  |  |  | 39.8579 | 21.3891 | منتظم | No
2200226240 | شركة المياه الوطنية / منطقة جازان | إشراف | ذات اولوية عالية | 9861480 | 493074 | 3368482.72 | 3368482.72 | 1010348048 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 33.11 | 33.11 | 2021-10-10 | 2023-04-10 | 2023-04-10 | 2023-04-10 |  |  |  |  | 42.9393 | 17.2377 | خدمات عامة | No
2200236390 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 13733175 | 686658.75 | 11355406.68 | 11355406.68 | 4031019772 | لا | 0 |  | منجز – استلام نهائي | تكلفة العمل المنجز | 82.69 | 82.69 | 2014-03-23 | 2016-03-22 | 2016-03-22 | 2016-03-22 | 2016-03-22 | 2022-07-26 |  |  | 39.8579 | 21.3891 | منجز | No
2100018524 | شركة المياه الوطنية / منطقة الجوف | إشراف | ذات اولوية عالية | 2520000 | 126000 | 2516161.29 | 2337774.19 | 1131051650 | لا | 0 |  | منجز – استلام نهائي | التكلفة المفوترة | 100 | 100 | 2018-10-09 | 2020-10-10 | 2020-10-10 | 2020-10-10 | 2020-10-10 | 2020-10-25 | لا يوجد تأخير |  | 39.8767 | 29.8066 | منجز | No
2200236353 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 9844000 | 492200 | 1248905.95 | 1248905.95 | 4031205267 | لا | 0 |  | جاري | تكلفة العمل المنجز | 12.69 | 12.69 | 2021-12-20 | 2024-01-16 | 2024-12-03 | 2024-12-03 |  |  |  | أخرى | 39.8579 | 21.3891 | Failed | No
2200218131 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 134844741.65 | 6742237.0825 | 8826060.16 | 8826060.16 | 1010069549 | لا | 0 |  | ايقاف كلي | منهجية القيمة المكتسبة | 18 | 100 | 2021-01-21 | 2022-07-15 | 2022-07-15 | 2022-07-15 |  |  |  | أخرى | 46.8412 | 24.984 | Failed | No
2100042755 | جامعة المجمعة | تشييد | ذات اولوية عالية وعاجلة | 99616527 | 4980826.35 | 93877135.02 | 93877135.02 | 1010060399 | نعم | 60269793.21 | 180709036703 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-02-24 | 2020-03-13 | 2020-03-14 | 2020-03-14 | 2020-03-13 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 45.4128 | 25.8654 | منجز | No
2200236375 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 20000000 | 1000000 | 236487.76 | 236487.76 | 2051060068 | لا | 0 |  | جاري | تكلفة العمل المنجز | 1.18 | 1.18 | 2020-03-19 | 2022-02-25 | 2022-12-04 | 2022-12-04 |  |  |  | أخرى | 39.8579 | 21.3891 | Failed | No
2100078945 | شركة المياه الوطنية / منطقة الجوف | تصميم | ذات اولوية عالية | 3900000 | 195000 | 3900000 | 3900000 | 4030188113 | لا | 0 | 180801043187 | منجز – استلام نهائي | التكلفة المفوترة | 100 | 100 | 2019-03-14 | 2020-09-13 | 2020-09-13 | 2020-09-13 | 2020-09-13 | 2020-07-02 | لا يوجد تأخير |  | 40.3811 | 30.1124 | منجز | No
2100073894 | وزارة الصحة / الحدود الشمالية | تشييد | ذات اولوية عالية | 14555543 | 727777.15 | 11405609.66 | 11405609.66 | 3450008383 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 82 | 100 | 2014-02-17 | 2017-07-01 | 2022-11-22 | 2022-11-22 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 38.6587 | 31.6706 | مسحوب | No
2100192360 | جامعة المجمعة | تشييد | ذات اولوية عالية وعاجلة | 9095300.26 | 454765.013 | 5930273.9 | 5930273.9 | 1010005046 | لا | 0 | 180909072732 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-09-03 | 2021-08-14 | 2021-08-14 | 2021-08-14 | 2021-08-14 |  |  |  | 45.4201 | 25.8772 | منجز | No
2100104532 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1998012 | 99900.6 | 199393.14 | 199393.14 | 1010075988 | لا | 0 |  | مسحوب | التكلفة المفوترة | 13 | 100 | 2007-10-23 | 2008-10-12 | 2023-02-09 | 2023-02-09 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | مسحوب | No
2200236386 | أمانة / العاصمة المقدسة | أخرى | ذات اولوية متوسطة | 8941537.5 | 447076.875 | 5169339.04 | 5169339.04 | 4030013052 | لا | 0 |  | جاري | تكلفة العمل المنجز | 57.81 | 57.81 | 2020-03-11 | 2022-02-17 | 2022-02-17 | 2022-02-17 |  |  |  |  | 39.8579 | 21.3891 | خدمات عامة | No
2100055930 | وزارة الصحة / الحدود الشمالية | تشييد | لم تعد تحتاجها الجهة | 20557350 | 1027867.5 | 20557350 | 20557350 | 1010238171 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-08-11 | 2020-08-21 | 2022-01-05 | 2022-01-05 | 2020-08-21 |  | التنسيق مع أصحاب المصلحه (خدمات |  | 43.5153 | 29.6394 | منجز | No
2100026600 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تصميم وتشييد | ذات اولوية عالية وعاجلة | 180275405.48 | 9013770.274 | 140503366.2 | 140503366.2 | 1010044805 | لا | 0 | 180809057733 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2013-11-11 | 2015-11-09 | 2020-06-13 | 2020-06-13 | 2015-11-09 |  | لا يوجد تأخير |  | 49.6626 | 27.0037 | منجز | No
2200218164 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 14785078.5 | 739253.925 | 6190390.55 | 6190390.55 | 1010185409 | لا | 0 |  | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2021-06-08 | 2022-04-03 | 2022-11-12 | 2022-11-12 |  |  |  |  | 41.3351 | 20.0096 | متأخر | No
2200226251 | شركة المياه الوطنية / منطقة جازان | إشراف | ذات اولوية عالية | 10320000 | 516000 | 0 | 0 | 5950005891 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 0 | 0 | 2022-07-18 | 2024-07-18 | 2024-07-18 | 2024-07-18 |  |  |  |  | 42.6269 | 17.1548 | خدمات عامة | No
2200226262 | شركة المياه الوطنية / منطقة مكة المكرمة | إشراف | ذات اولوية عالية | 10368000 | 518400 | 0 | 0 | 1131035992 | لا | 0 |  | جاري | التكلفة المفوترة | 0 | 0 | 2022-05-20 | 2025-05-20 | 2025-05-20 | 2025-05-20 |  |  |  |  | 39.2104 | 21.4635 | خدمات عامة | No
2100009203 | وزارة الدفاع / الإدارة الهندسية والاشغال بالخدمات الصحية | تشييد | ذات اولوية عالية وعاجلة | 94676224.8 | 4733811.24 | 52019453.28 | 52019453.28 | 1010093493 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 52 | 100 | 2016-03-14 | 2017-08-25 | 2022-04-30 | 2022-04-30 |  |  | عدم وجود مبالغ في البنود تغطي الأعمال المرصودة |  | 40.3984 | 21.26 | Failed | No
2100108360 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية وعاجلة | 92329710.63 | 4616485.5315 | 73606708.73 | 73027774.29 | 2050022661 | لا | 0 | 180709021924 | جاري | تكلفة العمل المنجز | 95 | 100 | 2012-05-27 | 2014-11-13 | 2023-12-31 | 2023-12-31 |  |  | تأخرصرف المستحقات المالية |  | 40.478 | 21.3584 | متأخر | No
2100106875 | وزارة التعليم | تشييد | ذات اولوية عالية | 10876608.06 | 543830.403 | 4910189.44 | 4212359.82 | 1010181431 | لا | 0 | 190309088755 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-07-26 | 2017-07-15 | 2022-08-11 | 2022-08-11 | 2017-07-15 |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | منجز | No
2200236493 | أمانة / العاصمة المقدسة | أخرى | ذات اولوية متوسطة | 749000 | 37450 | 721206.39 | 721206.39 | 4030183780 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 96.29 | 96.29 | 2019-08-05 | 2020-07-24 | 2020-07-24 | 2020-07-24 | 2020-07-24 |  |  |  | 39.8579 | 21.3891 | منجز | No
2100039664 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 720605 | 36030.25 | 0 | 0 | 1010318776 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 88 | 100 | 2013-11-09 | 2014-11-12 | 2019-12-08 | 2019-12-08 | 2014-11-12 |  | ضعف كفاءة المقاول الفنية |  | 45.3875 | 23.6177 | منجز | No
2100022761 | شركة المياه الوطنية / منطقة الجوف | إشراف | ذات اولوية عالية | 4338000 | 216900 | 4338000 | 4338000 | 4030188113 | لا | 0 | 180701035512 | منجز – استلام نهائي | التكلفة المفوترة | 100 | 100 | 2018-10-07 | 2021-10-06 | 2022-04-07 | 2022-04-07 | 2021-10-06 | 2021-11-13 | لا يوجد تأخير |  | 40.1986 | 29.9554 | منجز | No
2200236504 | أمانة / العاصمة المقدسة | الخدمات الاستشارية | ذات اولوية متوسطة | 1594320 | 79716 | 1522981 | 1522981 | 4031063586 | لا | 0 |  | منجز – استلام نهائي | تكلفة العمل المنجز | 95.53 | 95.53 | 2020-01-01 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-10-17 |  |  | 39.8579 | 21.3891 | منجز | No
2200236423 | أمانة / العاصمة المقدسة | الخدمات الاستشارية | ذات اولوية متوسطة | 10731391.73 | 536569.5865 | 8319202.31 | 8319202.31 | 1010273123 | لا | 0 |  | جاري | تكلفة العمل المنجز | 71.1 | 71.1 | 2020-06-07 | 2023-06-07 | 2023-06-07 | 2023-06-07 |  |  |  |  | 39.8579 | 21.3891 | خدمات عامة | No
2100199441 | جامعة جدة | ترميم | ذات اولوية متوسطة | 16454202 | 822710.1 | 0 | 0 | 4601000417 | لا | 0 |  | ايقاف جزئي | تكلفة العمل المنجز | 6 | 15 | 2021-05-03 | 2021-12-26 | 2021-12-26 | 2021-12-26 |  |  |  |  | 39.1808 | 21.579 | Failed | No
2100086332 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 5555968.43 | 277798.4215 | 2806578.83 | 2806578.83 | 1010213931 | لا | 0 |  | مسحوب | التكلفة المفوترة | 83 | 100 | 2014-03-17 | 2015-12-09 | 2023-01-15 | 2023-01-15 |  |  | ضعف كفاءة المقاول الفنية |  | 40.0549 | 29.8587 | مسحوب | No
2100043632 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 5489900 | 274495 | 0 | 0 | 1118000065 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 85 | 100 | 2013-10-12 | 2015-01-27 | 2017-01-30 | 2017-01-30 | 2015-01-27 |  | ضعف كفاءة المقاول الفنية |  | 42.9631 | 23.8862 | منجز | No
2200236434 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 22640362.5 | 1132018.125 | 4894374.45 | 4894374.45 | 5855027156 | لا | 0 |  | جاري | تكلفة العمل المنجز | 21.62 | 21.62 | 2020-03-12 | 2023-03-12 | 2023-03-12 | 2023-03-12 |  |  |  |  | 39.8579 | 21.3891 | منتظم | No
2100060572 | وزارة التعليم | تشييد | ذات اولوية عالية | 10454181 | 522709.05 | 8861940 | 8305526 | 4030140863 | لا | 0 | 190309088829 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-07-28 | 2017-08-15 | 2021-04-25 | 2021-04-25 | 2017-08-15 |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | منجز | No
2100013462 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2675250 | 133762.5 | 40806 | 0 | 1010217935 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 22 | 100 | 2013-02-23 | 2014-02-18 | 2021-06-20 | 2021-06-20 |  |  | ضعف كفاءة المقاول الفنية |  | 47.3323 | 24.1668 | مسحوب | Yes
2200236515 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 4870950 | 243547.5 | 2781583 | 2781583 | 4031022496 | لا | 0 |  | جاري | تكلفة العمل المنجز | 57.11 | 57.11 | 2021-02-14 | 2023-01-23 | 2023-01-23 | 2023-01-23 |  |  |  |  | 39.8579 | 21.3891 | منتظم | No
2100023052 | جامعة المجمعة | تشييد | ذات اولوية عالية وعاجلة | 8999991 | 449999.55 | 6919008.28 | 6919008.28 | 1010232156 | لا | 0 | 191201033981 | ايقاف جزئي | الكميات التي تم تركيبها | 80 | 100 | 2020-01-30 | 2021-12-31 | 2022-03-31 | 2022-03-31 |  |  | اخرى |  | 45.4105 | 25.863 | Failed | No
2200236456 | أمانة / العاصمة المقدسة | أخرى | ذات اولوية متوسطة | 7350000 | 367500 | 4498046.64 | 4498046.64 | 4031054258 | لا | 0 |  | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 61.2 | 61.2 | 2019-05-02 | 2020-05-01 | 2020-05-01 | 2020-05-01 |  |  |  |  | 39.8579 | 21.3891 | Failed | No
2100032336 | أمانة / الرياض | تشييد | ذات اولوية عالية | 224391291.6 | 11219564.58 | 179697395.51 | 122598789.88 | 1010326466 | لا | 0 | 190301026838 | جاري | الكميات التي تم تركيبها | 94.69 | 100 | 2019-10-05 | 2021-05-14 | 2021-05-18 | 2021-05-18 |  |  | التنسيق مع أصحاب المصلحه (خدمات |  | 46.6855 | 24.7082 | Failed | No
2200236526 | أمانة / العاصمة المقدسة | أخرى | ذات اولوية متوسطة | 1779750 | 88987.5 | 1731621 | 1731621 | 1010320728 | لا | 0 |  | جاري | تكلفة العمل المنجز | 97.3 | 97.3 | 2021-03-01 | 2023-02-07 | 2023-02-07 | 2023-02-07 |  |  |  |  | 39.8579 | 21.3891 | خدمات عامة | No
2100019740 | رئاسة أمن الدولة / ديوان رئاسة أمن الدولة | تشييد | ذات اولوية عالية وعاجلة | 16240900 | 812045 | 16240900 | 16240900 | 1010235877 | لا | 0 | 191201118418 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2020-01-23 | 2021-01-17 | 2022-03-17 | 2022-03-17 | 2021-01-17 |  | لا يوجد تأخير |  | 24.4473 | 46.8144 | منجز | No
2100104440 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية وعاجلة | 99234399.85 | 4961719.9925 | 44267559.57 | 21159275.06 | 7001490841 | لا | 0 | 180801054069 | جاري | منهجية القيمة المكتسبة | 85 | 100 | 2018-10-10 | 2021-09-08 | 2023-06-30 | 2023-06-30 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 43.9716 | 26.3067 | متأخر | No
2200228443 | أمانة / المنطقة الشرقية | تصميم وإشراف | ذات اولوية عالية | 19995000 | 999750 | 2652158.76 | 2652158.76 | 4030246002 | لا | 0 |  | ايقاف جزئي | التكلفة المفوترة | 13 | 100 | 2020-10-26 | 2022-12-10 | 2023-07-24 | 2023-07-24 |  |  |  |  | 50.0888 | 26.4207 | Failed | No
2100108334 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 3075726.83 | 153786.3415 | 2589312.16 | 998927.9 | 1010309164 | لا | 0 | 200509029022 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-11-24 | 2020-11-18 | 2024-12-31 | 2024-12-31 | 2020-11-18 |  | تأخرصرف المستحقات المالية |  | 49.5778 | 25.3902 | منجز | No
2200236530 | أمانة / العاصمة المقدسة | أخرى | ذات اولوية متوسطة | 10112359.95 | 505617.9975 | 3134510.36 | 3134510.36 | 4030013052 | لا | 0 |  | جاري | تكلفة العمل المنجز | 31 | 31 | 2020-11-23 | 2022-11-23 | 2022-11-23 | 2022-11-23 |  |  |  |  | 39.8579 | 21.3891 | خدمات عامة | No
2100005994 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 7123860.91 | 356193.0455 | 6960883.91 | 0 | 1010225334 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2010-07-12 | 2012-01-03 | 2019-04-11 | 2019-04-11 | 2012-01-03 |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | منجز | Yes
2200236471 | أمانة / العاصمة المقدسة | أخرى | ذات اولوية متوسطة | 12238170 | 611908.5 | 6526572 | 6526572 | 4030044382 | لا | 0 |  | جاري | تكلفة العمل المنجز | 49.01 | 49.01 | 2020-04-30 | 2022-04-09 | 2022-04-09 | 2022-04-09 |  |  |  |  | 39.8579 | 21.3891 | خدمات عامة | No
2200236563 | أمانة / العاصمة المقدسة | أخرى | ذات اولوية متوسطة | 19398750 | 969937.5 | 17458875 | 17458875 | 4031019772 | لا | 0 |  | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 74.44 | 74.44 | 2019-06-16 | 2019-12-10 | 2019-12-10 | 2019-12-10 |  |  |  |  | 39.8579 | 21.3891 | Failed | No
2200236482 | أمانة / العاصمة المقدسة | أخرى | ذات اولوية متوسطة | 31548137.04 | 1577406.852 | 23333615.7 | 23333615.7 | 4030082715 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 81 | 81 | 2012-07-14 | 2015-01-12 | 2015-01-12 | 2015-01-12 | 2015-01-12 |  |  |  | 39.8579 | 21.3891 | منجز | No
2100055506 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية عالية | 8461392.5 | 423069.625 | 3063346.76 | 2709286.51 | 5855028408 | لا | 0 | 190201003050 | جاري | منهجية القيمة المكتسبة | 37.67 | 41.13 | 2019-09-19 | 2021-08-28 | 2023-02-08 | 2023-02-08 |  |  | التنسيق مع أصحاب المصلحه (خدمات |  | 43.526 | 19.539 | منتظم | No
2100052146 | وزارة الصحة / الطائف | تشييد | ذات اولوية عالية وعاجلة | 1464425 | 73221.25 | 1023370 | 0 | 4035000994 | لا | 0 | 190601041884 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 99 | 100 | 2019-06-10 | 2020-01-31 | 2021-12-01 | 2021-12-01 | 2020-01-31 |  | تأخرصرف المستحقات المالية |  | 41.0145 | 21.055 | منجز | Yes
2100090801 | جامعة أم القرى | تشييد | ذات اولوية عالية وعاجلة | 63084749.55 | 3154237.4775 | 40280597.11 | 40280597.11 | 4030006877 | لا | 0 | 181109246573 | ايقاف كلي | تكلفة العمل المنجز | 72 | 100 | 2012-11-20 | 2014-10-20 | 2023-12-30 | 2023-12-30 |  |  | اخرى |  | 39.9275 | 21.3463 | Failed | No
2200236552 | أمانة / العاصمة المقدسة | أخرى | ذات اولوية متوسطة | 2976750 | 148837.5 | 2853409.56 | 2853409.56 | 4031083542 | لا | 0 |  | منجز – استلام نهائي | تكلفة العمل المنجز | 95.86 | 95.86 | 2020-01-15 | 2022-01-14 | 2022-01-14 | 2022-01-14 | 2022-01-14 | 2022-03-29 |  |  | 39.8579 | 21.3891 | منجز | No
2100001352 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 8482881.05 | 424144.0525 | 3600529.05 | 2821749.33 | 4030010046 | نعم | 19033031.14 | 190901022412 | جاري | تكلفة العمل المنجز | 85 | 100 | 2019-09-09 | 2020-08-28 | 2024-12-31 | 2024-12-31 |  |  | تأخرصرف المستحقات المالية |  | 39.0687 | 21.8623 | متأخر | No
2100008971 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 196416873 | 9820843.65 | 163709190.22 | 163709190.22 | 1010136405 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 99 | 100 | 2019-02-26 | 2020-08-19 | 2023-03-31 | 2023-03-31 |  |  | منازعات قائمة | أخرى |  |  | Failed | No
2100012530 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1738175 | 86908.75 | 41898 | 0 | 1010242510 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 42 | 100 | 2015-04-11 | 2016-07-04 | 2020-11-09 | 2020-11-09 |  |  | ضعف كفاءة المقاول الفنية |  | 46.0999 | 25.1158 | Failed | Yes
2200231346 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية عالية | 9039000 | 451950 | 0 | 0 | 2057001166 | لا | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 20 | 11 | 2022-09-18 | 2023-09-07 | 2023-09-07 | 2023-09-07 |  |  |  |  | 48.4887 | 28.4257 | Failed | No
2100039631 | شركة الكهرباء | تشييد | ذات اولوية متوسطة | 388603548 | 19430177.4 | 268876921 | 268876921 | 1010127329 | لا | 0 |  | جاري | التكلفة المفوترة | 95.9 | 100 | 2015-12-06 | 2017-11-25 | 2023-05-12 | 2023-05-12 |  |  | ضعف كفاءة المقاول الفنية |  | 42.7681 | 18.3214 | Failed | No
2100032760 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 74771924.76 | 3738596.238 | 69824807.96 | 69824807.96 | 2055014114 | لا | 0 | 180809059276 | جاري | منهجية القيمة المكتسبة | 91 | 100 | 2017-03-06 | 2019-03-04 | 2023-04-08 | 2023-04-08 |  |  | التنسيق مع أصحاب المصلحه (خدمات |  | 49.6626 | 27.0037 | متأخر | No
2100003286 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 52521288.5 | 2626064.425 | 26760509.74 | 26760509.74 | 4030155231 | لا | 0 | 180709019696 | ايقاف كلي | تكلفة العمل المنجز | 67 | 100 | 2014-09-12 | 2016-08-12 | 2024-12-31 | 2024-12-31 |  |  | تأخرصرف المستحقات المالية |  | 39.7162 | 24.4847 | Failed | No
2100003894 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 197000000 | 9850000 | 134858880.7 | 134858880.7 | 1010012911 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 90.98 | 100 | 2018-02-19 | 2021-01-16 | 2021-10-24 | 2021-10-24 | 2021-01-16 |  | لا يوجد تأخير |  | 40.6727 | 21.5834 | منجز | No
2100041775 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 13042815.01 | 652140.7505 | 1136743 | 1136743 | 1010304570 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 11 | 100 | 2014-11-12 | 2016-07-24 | 2016-07-24 | 2016-07-24 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | مسحوب | No
2100004152 | شركة المياه الوطنية / منطقة الجوف | تشييد | ذات اولوية عالية | 42610275 | 2130513.75 | 38243223.68 | 38243223.68 | 1010199022 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99 | 100 | 2014-06-11 | 2015-11-24 | 2020-01-19 | 2020-01-19 | 2015-11-24 |  | لا يوجد تأخير |  | 37.3525 | 31.3601 | منجز | No
2100004126 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2705105 | 135255.25 | 0 | 0 | 1129001539 | لا | 0 |  | مسحوب | التكلفة المفوترة | 8 | 100 | 2014-04-01 | 2015-03-27 | 2022-08-17 | 2022-08-17 |  |  | ضعف كفاءة المقاول الفنية |  | 40.2691 | 20.1489 | مسحوب | No
2100201950 | الهيئة العامة للزكاة والدخل | ترميم | ذات اولوية عالية | 499905 | 24995.25 | 0 | 0 | 1010261568 | لا | 0 |  | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2021-11-24 | 2021-12-29 | 2021-12-30 | 2021-12-30 |  | 2021-12-29 |  |  | 50.1706 | 26.3766 | منجز | No
2100069683 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 384222079.24 | 19211103.962 | 310007213.76 | 310007213.76 | 2055002293 | لا | 0 | 180809057301 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2009-07-29 | 2013-01-23 | 2020-09-26 | 2020-09-26 | 2013-01-23 |  | لا يوجد تأخير |  | 49.6626 | 27.0037 | منجز | No
2200231350 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 416587.5 | 20829.375 | 234600 | 234600 | 2251032226 | لا | 0 |  | جاري | تكلفة العمل المنجز | 60 | 49.33 | 2022-08-21 | 2023-06-17 | 2023-06-17 | 2023-06-17 |  |  |  |  | 48.2692 | 26.7654 | منتظم | No
2100033294 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 38124626.4 | 1906231.32 | 11649157.81 | 11649157.81 | 4650007352 | لا | 0 | 180709019808 | ايقاف كلي | تكلفة العمل المنجز | 37 | 100 | 2015-06-23 | 2017-12-19 | 2025-12-31 | 2025-12-31 |  |  | تأخرصرف المستحقات المالية |  | 39.7153 | 24.4836 | Failed | No
2100079962 | شركة المياه الوطنية / منطقة الجوف | تشييد | ذات اولوية عالية | 32550000.4 | 1627500.02 | 13883369.27 | 13883369.27 | 5950010109 | لا | 0 | 190509038303 | جاري | منهجية القيمة المكتسبة | 50.2 | 100 | 2016-10-31 | 2018-06-14 | 2023-07-26 | 2023-07-26 |  |  | عدم وجود مبالغ في البنود تغطي الأعمال المرصودة |  | 37.3275 | 31.3468 | Failed | No
2200236585 | أمانة / العاصمة المقدسة | أخرى | ذات اولوية متوسطة | 7380030 | 369001.5 | 5989861 | 5989861 | 5855027156 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 70.95 | 70.95 | 2019-12-22 | 2021-02-07 | 2021-02-07 | 2021-02-07 | 2021-02-07 |  |  |  | 39.8579 | 21.3891 | منجز | No
2100075412 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 210977 | 10548.85 | 210977 | 0 | 1116000436 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-01-09 | 2020-01-04 | 2019-12-25 | 2019-12-25 | 2020-01-04 |  |  |  | 44.3885 | 23.4874 | منجز | Yes
2200229600 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 45965325 | 2298266.25 | 32635380.75 | 32635380.75 | 3555000709 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 71 | 76 | 2021-01-17 | 2022-12-26 | 2022-12-26 | 2022-12-26 |  |  |  |  | 39.5744 | 24.4403 | منتظم | No
2200236600 | وزارة الرياضة | تحديث وتوريد | ذات اولوية متوسطة | 1415424.6 | 70771.23 | 476316.2 | 476316.2 | 1010056286 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2022-05-29 | 2022-08-28 | 2022-08-28 | 2022-08-28 | 2022-08-28 |  |  |  | 39.8579 | 21.3891 | منجز | No
2200236611 | وزارة الرياضة | توريد وتركيب | ذات اولوية متوسطة | 2338870 | 116943.5 | 0 | 0 | 1010185891 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 0 | 0 | 2022-08-28 | 2023-08-27 | 2023-08-27 | 2023-08-27 |  |  |  |  | 39.8579 | 21.3891 | منتظم | No
2100189490 | الهيئة العامة للزكاة والدخل | ترميم | ذات اولوية عالية | 4996539.45 | 249826.9725 | 499653.45 | 499653.45 | 1010261568 | لا | 0 |  | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2020-07-05 | 2020-08-31 | 2020-08-31 | 2020-08-31 |  | 2020-08-31 |  |  | 42.5579 | 16.9088 | منجز | No
2200226273 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 26337122.58 | 1316856.129 | 0 | 0 | 1118000259 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 0 | 0 | 2022-05-19 | 2025-05-19 | 2025-05-19 | 2025-05-19 |  |  |  |  | 39.215 | 21.3737 | منتظم | No
2100196011 | الهيئة العامة للزكاة والدخل | توريد وتركيب | ذات اولوية عالية | 188582.75 | 9429.1375 | 188582.75 | 188582.75 | 1010200847 | لا | 0 |  | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2021-05-06 | 2021-05-19 | 2021-05-19 | 2021-05-19 |  | 2021-05-19 |  |  | 40.457 | 21.2752 | منجز | No
2100064606 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 7799044 | 389952.2 | 1609721.56 | 0 | 1010010466 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 25 | 100 | 2015-08-03 | 2017-07-23 | 2021-06-10 | 2021-06-10 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 44.7638 | 23.7607 | Failed | Yes
2100074900 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3869605 | 193480.25 | 3162900 | 0 | 1010214019 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 88 | 100 | 2015-06-27 | 2016-12-18 | 2019-09-03 | 2019-09-03 | 2016-12-18 |  | ضعف كفاءة المقاول الفنية |  | 46.2752 | 24.4729 | منجز | Yes
2100190805 | شركة المياه الوطنية / منطقة الجوف | تشطيب | ذات اولوية عالية وعاجلة | 7836394.4 | 391819.72 | 7001798 | 7001798 | 1010014082 | لا | 0 | 201101082573 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2020-12-20 | 2021-04-18 | 2021-05-26 | 2021-05-26 | 2017-05-18 |  |  |  | 40.2408 | 29.9773 | منجز | No
2200236633 | أمانة / المدينة المنورة | دراسات هندسية | ذات اولوية متوسطة | 5980000 | 299000 | 0 | 0 | 4650047424 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 0 | 0 | 2022-10-31 | 2023-12-26 | 2023-12-26 | 2023-12-26 |  |  |  |  | 39.6005 | 24.4595 | خدمات عامة | No
2100031566 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 989400 | 49470 | 42067 | 0 | 1185000475 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 63 | 100 | 2015-07-29 | 2016-10-21 | 2019-07-06 | 2019-07-06 | 2016-10-21 |  | ضعف كفاءة المقاول الفنية |  | 45.399 | 26.4972 | منجز | Yes
2200231383 | أمانة / المنطقة الشرقية | هدم و ازالة | ذات اولوية متوسطة | 434700 | 21735 | 158700 | 158700 | 2056001712 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 99 | 99 | 2022-10-02 | 2022-12-31 | 2022-12-31 | 2022-12-31 | 2022-12-31 |  |  |  | 48.4855 | 27.4704 | منجز | No
2100007490 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 341668422 | 17083421.1 | 289956013.7 | 289956013.7 | 1010185409 | لا | 0 |  | ايقاف جزئي | منهجية القيمة المكتسبة | 99 | 100 | 2019-12-18 | 2021-06-10 | 2023-12-31 | 2023-12-31 |  |  | منازعات قائمة | أخرى |  |  | متأخر | No
2100061924 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 88494066 | 4424703.3 | 52987887.25 | 52987887.25 | 1010014477 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 95.05 | 100 | 2018-10-16 | 2020-10-16 | 2022-07-31 | 2022-07-31 | 2020-10-16 |  | لا يوجد تأخير |  | 46.5277 | 24.6651 | منجز | No
2200231394 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 348381 | 17419.05 | 348381 | 348381 | 2056005766 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 41.67 | 2022-09-01 | 2022-10-31 | 2022-10-31 | 2022-10-31 | 2022-10-31 |  |  |  | 48.4855 | 27.4704 | منجز | No
2100088174 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 79909309 | 3995465.45 | 52598508.15 | 52598508.15 | 4030126557 | لا | 0 | 181109267849 | جاري | منهجية القيمة المكتسبة | 72 | 97 | 2018-09-25 | 2021-03-23 | 2023-01-31 | 2023-01-31 |  |  | التنسيق مع أصحاب المصلحه (خدمات |  | 49.6626 | 27.0037 | Failed | No
2100041403 | شركة المياه الوطنية / منطقة الجوف | إشراف | ذات اولوية عالية وعاجلة | 4753833.87 | 237691.6935 | 5695835.97 | 5695835.97 | 1131051650 | لا | 0 | 180709020787 | منجز – استلام نهائي | التكلفة المفوترة | 100 | 100 | 2015-10-05 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2018-04-04 | 2019-11-28 | لا يوجد تأخير |  | 40.2296 | 29.9353 | منجز | No
2100091825 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 289146863.86 | 14457343.193 | 232034150.83 | 232034150.83 | 1010054406 | لا | 0 |  | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-09-10 | 2021-03-03 | 2022-12-31 | 2022-12-31 |  |  | منازعات قائمة | أخرى |  |  | منتظم | No
2100060395 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 12644082 | 632204.1 | 10784920.22 | 10784920.22 | 1011000444 | لا | 0 | 181009164928 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 98.78 | 100 | 2016-12-05 | 2020-10-23 | 2020-10-20 | 2020-10-20 |  | 2020-10-23 | لا يوجد تأخير |  | 46.8944 | 23.5058 | منجز | No
2100006230 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2055047 | 102752.35 | 0.01 | 0.01 | 2512356389 | لا | 0 |  | مسحوب | التكلفة المفوترة | 1 | 100 | 2013-05-27 | 2014-05-17 | 2023-08-16 | 2023-08-16 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0165 | 30.9619 | مسحوب | No
2100011992 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 14279434.69 | 713971.7345 | 0.01 | 0.01 | 1010081983 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 1 | 100 | 2019-07-27 | 2021-07-16 | 2021-07-16 | 2021-07-16 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5604 | 25.3897 | مسحوب | No
2100077884 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 49998767 | 2499938.35 | 24306884 | 21550475.99 | 1010122969 | لا | 0 | 180901109335 | جاري | منهجية القيمة المكتسبة | 70.25 | 73.71 | 2018-12-26 | 2020-12-25 | 2023-12-08 | 2023-12-08 |  |  | تأخرصرف المستحقات المالية |  | 38.2106 | 23.9926 | منتظم | No
2100061692 | شركة المياه الوطنية / منطقة الجوف | تشييد | ذات اولوية عالية وعاجلة | 164701422.9 | 8235071.145 | 12735676.35 | 12735676.35 | 1116000094 | لا | 0 | 180809055170 | مسحوب | منهجية القيمة المكتسبة | 9.51 | 100 | 2014-11-30 | 2017-10-28 | 2025-01-01 | 2025-01-01 |  |  | ضعف كفاءة المقاول الفنية |  | 39.998 | 29.7674 | مسحوب | No
2100100166 | هيئة تطوير منطقة المدينة المنورة | تشييد | ذات اولوية عالية | 24439742.25 | 1221987.1125 | 23351427.18 | 20707548.26 | 4650007588 | لا | 0 | 190309066408 | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2017-12-17 | 2019-12-16 | 2020-06-03 | 2020-06-03 | 2019-12-16 | 2021-06-03 |  |  | 39.8408 | 24.4747 | منجز | No
2200226284 | شركة المياه الوطنية / منطقة جازان | دراسات هندسية | ذات اولوية عالية | 2357500 | 117875 | 0 | 0 | 1010421282 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 0 | 0 | 2022-07-04 | 2023-01-30 | 2023-01-30 | 2023-01-30 |  |  |  |  | 42.1289 | 16.6884 | خدمات عامة | No
2100062705 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 5802172 | 290108.6 | 2408338.16 | 0 | 1010010466 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-09-11 | 2015-09-01 | 2019-11-11 | 2019-11-11 | 2015-09-01 |  | ضعف كفاءة المقاول الفنية |  | 45.2875 | 24.0741 | منجز | Yes
2100063814 | أمانة / عسير | تشييد | ذات اولوية عالية | 7687020 | 384351 | 1269048 | 1269048 | 5855036751 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 19 | 100 | 2017-02-08 | 2018-08-09 | 2018-08-09 | 2018-08-09 |  |  | ضعف كفاءة المقاول الفنية |  | 43.6593 | 18.7127 | مسحوب | No
2100041182 | أمانة / تبوك | تصميم | ذات اولوية متوسطة | 99750 | 4987.5 | 99750 | 99750 | 3550034877 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-05-02 | 2019-10-29 | 2019-10-29 | 2019-10-29 | 2019-10-29 |  | اخرى |  | 37.187 | 27.0479 | منجز | No
2100041510 | شركة المياه الوطنية / منطقة الجوف | إشراف | ذات اولوية عالية | 8021027.92 | 401051.396 | 10449509.4 | 10449509.4 | 1131052239 | لا | 0 | 180709023870 | منجز – استلام نهائي | التكلفة المفوترة | 100 | 100 | 2015-01-14 | 2018-01-13 | 2018-01-14 | 2018-01-14 | 2018-01-13 | 2022-08-31 | لا يوجد تأخير |  | 40.1517 | 29.8579 | منجز | No
2100026375 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 10547379.5 | 527368.975 | 8507555 | 0 | 1010225108 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 75 | 100 | 2015-01-13 | 2016-07-06 | 2017-07-06 | 2017-07-06 | 2016-07-06 |  |  |  | 45.7057 | 25.5491 | منجز | Yes
2100193502 | الجمارك السعودية | تشييد | ذات اولوية عالية | 15015136.1 | 750756.805 | 14904441.14 | 10513172.47 | 1010047800 | لا | 0 | 200701001468 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-06-06 | 2021-10-06 | 2022-02-28 | 2022-02-28 | 2021-10-06 |  |  |  | 37.12 | 31.431 | منجز | No
2100059640 | شركة الكهرباء | تشييد | ذات اولوية متوسطة | 530751048 | 26537552.4 | 390702152 | 390702152 | 1010057263 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 91.04 | 95.25 | 2013-02-03 | 2015-02-02 | 2022-12-29 | 2022-12-29 |  |  | اخرى |  | 39.897 | 21.4088 | منتظم | No
2100024430 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 178729315.99 | 8936465.7995 | 140698286.3 | 140698286.3 | 2051035332 | لا | 0 | 180809049343 | جاري | منهجية القيمة المكتسبة | 100 | 100 | 2014-12-04 | 2017-11-30 | 2023-04-21 | 2023-04-21 |  |  | اخرى |  | 49.6626 | 27.0037 | متأخر | No
2100084033 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 68000000 | 3400000 | 63550737.11 | 63550737.11 | 5950010121 | لا | 0 | 180501008092 | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2018-08-27 | 2020-08-05 | 2021-06-03 | 2021-06-03 | 2020-08-05 | 2022-05-24 |  |  | 42.8802 | 20.9631 | منجز | No
2100095211 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 911925773.6 | 45596288.68 | 386656528.0064 | 386656528.0064 | 1010154193 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 47 | 100 | 2014-06-04 | 2017-06-03 | 2020-09-26 | 2020-09-26 |  |  | ضعف كفاءة المقاول الفنية |  | 46.8499 | 24.6609 | مسحوب | No
2200226295 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 99499572.15 | 4974978.6075 | 0 | 0 | 1010224518 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 0.69 | 0 | 2022-04-24 | 2025-04-24 | 2025-04-24 | 2025-04-24 |  |  |  |  | 39.1612 | 21.2586 | منتظم | No
2200231431 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 486988 | 24349.4 | 278173.5 | 278173.5 | 2060049307 | لا | 0 |  | جاري | تكلفة العمل المنجز | 77 | 47 | 2022-08-30 | 2023-06-21 | 2023-06-21 | 2023-06-21 |  |  |  |  | 49.4797 | 25.9778 | منتظم | No
2100088362 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 137105129.08 | 6855256.454 | 105921854 | 105921854 | 1010185409 | لا | 0 |  | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2020-03-17 | 2021-09-08 | 2022-12-15 | 2022-12-15 |  |  | أوامر تغيير | أخرى |  |  | منتظم | No
2100000276 | وزارة التعليم | تشييد | ذات اولوية عالية | 14010484.68 | 700524.234 | 11649588.35 | 11649588.35 | 1010196220 | لا | 0 | 190209015460 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2013-10-08 | 2015-09-28 | 2021-03-02 | 2021-03-02 | 2015-09-28 |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | منجز | No
2100195812 | وزارة النقل والخدمات اللوجستية / منطقة تبوك | تشييد | ذات اولوية عالية | 64261890 | 3213094.5 | 5329600 | 5329600 | 1010055791 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 8.71 | 85.93 | 2020-08-30 | 2022-08-08 | 2022-08-08 | 2022-08-08 |  |  |  |  | 35.6891 | 27.3688 | Failed | No
2100044940 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2003250 | 100162.5 | 41745 | 0 | 1117002023 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 0 | 100 | 2014-12-02 | 2016-02-25 | 2016-02-25 | 2016-02-25 |  |  | تأخرصرف المستحقات المالية |  | 44.3843 | 23.4794 | Failed | Yes
2100095664 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 23866500 | 1193325 | 15434178.7 | 15434178.7 | 2060002548 | لا | 0 | 180809058474 | مسحوب | منهجية القيمة المكتسبة | 70 | 100 | 2012-06-04 | 2014-03-03 | 2023-10-16 | 2023-10-16 |  |  | عدم وجود كوادر كافية في الجهه لادارة المشروع |  | 49.5648 | 27.1019 | مسحوب | No
2100039546 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 20776691.44 | 1038834.572 | 18762341.91 | 18762341.91 | 1010185409 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-11-27 | 2021-05-20 | 2022-07-26 | 2022-07-26 | 2021-05-20 |  | التنسيق مع أصحاب المصلحه (خدمات | أخرى |  |  | منجز | No
2100103692 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية | 72360487.55 | 3618024.3775 | 18958207.35 | 18958207.35 | 4030172446 | لا | 0 | 180709019856 | مسحوب | تكلفة العمل المنجز | 42 | 100 | 2014-05-25 | 2016-11-10 | 2026-12-31 | 2026-12-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.9848 | 21.5402 | مسحوب | No
2100008024 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 92461660.59 | 4623083.0295 | 20630457.97 | 20630457.97 | 2055006347 | لا | 0 | 180101000019 | مسحوب | منهجية القيمة المكتسبة | 22 | 100 | 2018-10-14 | 2021-07-11 | 2023-07-11 | 2023-07-11 |  |  | تأخرصرف المستحقات المالية |  | 49.6626 | 27.0037 | مسحوب | No
2100087592 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 21221200 | 1061060 | 20741423.58 | 18185585.38 | 2050003475 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 99.9 | 96.41 | 2019-02-18 | 2021-02-19 | 2020-09-30 | 2020-09-30 |  | 2021-02-19 | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100022120 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 1649000 | 82450 | 1417665.05 | 1417665.05 | 1010296759 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-11-15 | 2019-11-15 | 2019-10-14 | 2019-10-14 |  | 2019-11-15 | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100043643 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2899800 | 144990 | 1260000 | 0 | 1010276830 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 70 | 100 | 2019-05-08 | 2021-04-27 | 2021-04-28 | 2021-04-28 |  |  |  |  | 44.9523 | 26.0165 | Failed | Yes
2100101802 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 536129979.53 | 26806498.9765 | 367464477.12 | 367464477.12 | 1010224378 | لا | 0 | 180809058456 | جاري | منهجية القيمة المكتسبة | 96 | 100 | 2010-11-08 | 2013-11-04 | 2023-10-31 | 2023-10-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 49.5648 | 27.1019 | متأخر | No
2100087990 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2263386.5 | 113169.325 | 0 | 0 | 1010045486 | لا | 0 |  | مسحوب | التكلفة المفوترة | 0 | 100 | 2015-07-29 | 2017-04-19 | 2023-02-02 | 2023-02-02 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.1677 | 21.5008 | مسحوب | No
2100023951 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية متوسطة | 3199486 | 159974.3 | 367723.03 | 367723.03 | 1010286739 | لا | 0 | 180709019929 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-11-16 | 2018-11-05 | 2020-12-22 | 2020-12-22 | 2018-11-05 |  | تصاريح أعمال التنفيذ |  | 44.3059 | 27.1954 | منجز | No
2100031216 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 5410425 | 270521.25 | 41189 | 0 | 1116004922 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 83.37 | 100 | 2013-06-11 | 2014-09-04 | 2019-10-19 | 2019-10-19 |  |  | ضعف كفاءة المقاول الفنية |  | 42.8348 | 23.9536 | مسحوب | Yes
2100062300 | أمانة / الرياض | دراسة الجدوى | ذات اولوية عالية | 513820 | 25691 | 100608 | 0 | 1118002523 | لا | 0 |  | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 98 | 35 | 2018-11-28 | 2020-11-17 | 2021-01-31 | 2021-01-31 | 2020-11-17 |  | اخرى |  |  |  | منجز | Yes
2100081642 | أمانة / القصيم | تشييد | ذات اولوية عالية | 3989975 | 199498.75 | 950000 | 900000 | 1128000011 | لا | 0 |  | ايقاف جزئي | تكلفة العمل المنجز | 27 | 28 | 2015-10-25 | 2023-11-28 | 2023-11-28 | 2023-11-28 |  |  | تأخرصرف المستحقات المالية |  | 43.6087 | 25.3356 | منتظم | No
2100193535 | وزارة الحرس الوطني / وكالة الشؤون الفنية | إشراف | ذات اولوية عالية | 73449718.67 | 3672485.9335 | 9573522.04 | 9573522.04 | 1010902667 | لا | 0 |  | ايقاف كلي | التكلفة المفوترة | 12 | 12 | 2020-06-30 | 2022-05-29 | 2024-08-01 | 2024-08-01 | [6 empty] | Failed | No
2100085676 | شركة المياه الوطنية / منطقة القصيم | إشراف | ذات اولوية عالية | 9720000 | 486000 | 9447420.15 | 9447420.15 | 1010348048 | لا | 0 | 180801053886 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2018-10-14 | 2021-03-18 | 2021-03-18 | 2021-03-18 | 2021-03-18 |  | لا يوجد تأخير |  | 43.5327 | 25.857 | منجز | No
2100026471 | أمانة / الرياض | تشييد | ذات اولوية عالية | 110255500 | 5512775 | 0 | 0 | 1010010466 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 85 | 100 | 2019-04-24 | 2022-03-21 | 2023-07-17 | 2023-07-17 |  |  |  |  | 44.8129 | 20.4486 | Failed | No
2100199894 | الجامعة الاسلامية بالمدينة المنورة | تصميم وتشييد | ذات اولوية عالية | 80227549.13 | 4011377.4565 | 999686 | 999686 | 1010219886 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 2 | 3 | 2022-10-09 | 2025-03-27 | 2025-03-27 | 2025-03-27 |  |  |  |  | 39.5654 | 24.4807 | منتظم | No
2100061714 | الهيئة العامة للموانئ | تشييد | ذات اولوية عالية وعاجلة | 18508226.69 | 925411.3345 | 10184189.06 | 10184189.06 | 5950011723 | نعم | 17699748.65 | 190301066359 | جاري | الكميات التي تم تركيبها | 87.5 | 100 | 2018-02-15 | 2019-02-03 | 2022-10-31 | 2022-10-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.5386 | 16.8915 | Failed | No
2100074060 | شركة المياه الوطنية / منطقة القصيم | إشراف | ذات اولوية عالية وعاجلة | 18360000 | 918000 | 11280990.95 | 9523070.55 | 1010348048 | لا | 0 | 180901071004 | جاري | التكلفة المفوترة | 70.31 | 70.31 | 2018-09-17 | 2023-09-17 | 2023-09-22 | 2023-09-22 |  |  | لا يوجد تأخير |  | 43.9573 | 26.3252 | خدمات عامة | No
2100044343 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 429900 | 21495 | 346960 | 0 | 3350032016 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 81 | 100 | 2015-11-02 | 2016-10-17 | 2019-10-23 | 2019-10-23 | 2016-10-17 |  | ضعف كفاءة المقاول الفنية |  | 45.8713 | 25.3051 | منجز | Yes
2100040810 | جامعة الإمام محمد بن سعود الاسلامية | تصميم | ذات اولوية متوسطة | 682500 | 34125 | 682500 | 0 | 1010078921 | لا | 0 | 181209447610 | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2018-07-31 | 2018-11-10 | 2018-07-01 | 2018-07-01 | 2018-11-10 |  | لا يوجد تأخير |  | 46.7082 | 24.8186 | منجز | Yes
2200226306 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 17812191.25 | 890609.5625 | 0 | 0 | 1118000259 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 0 | 0 | 2022-05-31 | 2024-05-31 | 2024-05-31 | 2024-05-31 |  |  |  |  | 39.2004 | 21.7462 | منتظم | No
2100108835 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية وعاجلة | 14695474.5 | 734773.725 | 692067.09 | 692067.09 | 1010289276 | لا | 0 | 181101227234 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 95.58 | 100 | 2018-12-19 | 2019-12-09 | 2021-10-06 | 2021-10-06 | 2019-12-09 |  | ضعف كفاءة المقاول الفنية |  | 44.2236 | 26.7343 | منجز | No
2100066846 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2495047.96 | 124752.398 | 507110 | 507110 | 4030140863 | لا | 0 | 190409041241 | جاري | التكلفة المفوترة | 85 | 100 | 2016-05-01 | 2017-04-26 | 2021-05-10 | 2021-05-10 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.1677 | 21.5008 | Failed | No
2200226660 | جامعة الملك خالد | توريد وتركيب | ذات اولوية عالية وعاجلة | 68652751.75 | 3432637.5875 | 53719346 | 48612429 | 1010434398 | لا | 0 |  | جاري | تكلفة العمل المنجز | 98.93 | 96.5 | 2021-10-10 | 2022-10-10 | 2023-01-26 | 2023-01-26 |  |  |  |  | 42.7071 | 18.0839 | منتظم | No
2100003625 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 5233121 | 261656.05 | 4592526.1 | 3818993.35 | 4032034978 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2018-08-08 | 2019-02-06 | 2019-02-06 | 2019-02-06 | 2019-02-06 |  |  |  | 40.4511 | 21.2747 | منجز | No
2100002612 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 10124520.9 | 506226.045 | 2037512 | 2037512 | 2050010484 | لا | 0 |  | مسحوب | التكلفة المفوترة | 15 | 100 | 2011-12-06 | 2013-11-25 | 2023-02-01 | 2023-02-01 |  |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | مسحوب | No
2100016752 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1620985 | 81049.25 | 941385 | 828987 | 4603008331 | لا | 0 | 191101177242 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2019-08-26 | 2020-04-22 | 2021-08-11 | 2021-08-11 | 2020-04-22 |  | ضعف كفاءة المقاول الفنية |  | 41.0859 | 19.1571 | منجز | No
2100103832 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 6771218 | 338560.9 | 0 | 0 | 1010142553 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0 | 100 | 2009-05-08 | 2010-12-21 | 2023-02-08 | 2023-02-08 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.5429 | 16.8808 | مسحوب | No
2100018325 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 13785607.85 | 689280.3925 | 7064889.57 | 7064889.57 | 7001681225 | لا | 0 |  | مسحوب | التكلفة المفوترة | 55 | 100 | 2012-04-02 | 2014-03-23 | 2023-03-08 | 2023-03-08 |  |  | ضعف كفاءة المقاول الفنية |  | 42.4987 | 18.2178 | مسحوب | No
2100048042 | شركة المياه الوطنية / منطقة القصيم | إشراف | ذات اولوية عالية | 4435200 | 221760 | 3979125.5 | 3882525.5 | 1010406797 | لا | 0 | 180709019812 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2017-09-17 | 2021-09-16 | 2022-02-04 | 2022-02-04 | 2021-09-16 |  | لا يوجد تأخير |  | 43.5229 | 25.8804 | منجز | No
2100030645 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4432630 | 221631.5 | 41723 | 0 | 1126000176 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 41 | 100 | 2015-07-30 | 2017-05-10 | 2018-12-18 | 2018-12-18 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6617 | 24.7044 | مسحوب | Yes
2100080334 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3298700 | 164935 | 2147209 | 0 | 1010110454 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-10-18 | 2015-12-12 | 2019-09-05 | 2019-09-05 | 2015-12-12 |  | ضعف كفاءة المقاول الفنية |  | 45.5801 | 20.4619 | منجز | Yes
2100104274 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 5367438 | 268371.9 | 0 | 0 | 2251017211 | لا | 0 |  | مسحوب | التكلفة المفوترة | 0 | 100 | 2017-03-12 | 2018-09-03 | 2018-08-03 | 2018-08-03 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5604 | 25.3897 | مسحوب | No
2200226634 | الهيئة العامة للموانئ | توريد وتركيب | ذات اولوية عالية وعاجلة | 790409759.85 | 39520487.9925 | 0 | 0 | 4030027340 | لا | 0 |  | جاري | تكلفة العمل المنجز | 0 | 16.67 | 2022-09-14 | 2024-02-13 | 2024-02-13 | 2024-02-13 |  |  |  |  | 49.6765 | 27.0206 | متأخر | No
2100094975 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 42364734 | 2118236.7 | 40114717 | 40114717 | 1010017123 | لا | 0 | 180809038627 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-09-20 | 2019-09-20 | 2023-02-02 | 2023-02-02 | 2019-09-20 |  | أوامر تغيير |  | 38.3471 | 23.9575 | منجز | No
2100012132 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2423763.86 | 121188.193 | 0 | 0 | 4030140863 | لا | 0 |  | ايقاف كلي | التكلفة المفوترة | 0 | 100 | 2015-07-28 | 2016-07-22 | 2023-05-05 | 2023-05-05 |  |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | Failed | No
2100190610 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية وعاجلة | 65695427.41 | 3284771.3705 | 17887027.61 | 12730554.12 | 1010157711 | لا | 0 | 200701047261 | جاري | منهجية القيمة المكتسبة | 75.05 | 77.5 | 2020-11-14 | 2023-04-19 | 2023-04-19 | 2023-04-19 |  |  |  |  | 43.6057 | 26.5043 | منتظم | No
2100057982 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2311119 | 115555.95 | 0 | 0 | 3450006578 | لا | 0 |  | مسحوب | التكلفة المفوترة | 10 | 100 | 2015-05-09 | 2016-04-08 | 2019-10-23 | 2019-10-23 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0165 | 30.9619 | مسحوب | No
2100017566 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 9025710.85 | 451285.5425 | 4267635.91 | 4000912.83 | 4030052981 | لا | 0 | 200609130074 | مسحوب | التكلفة المفوترة | 48 | 100 | 2014-04-01 | 2016-03-21 | 2022-08-26 | 2022-08-26 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | مسحوب | No
2100102292 | جامعة الملك سعود | إشراف | ذات اولوية عالية | 110000000 | 5500000 | 104602514.63 | 104602514.63 | 1010085518 | لا | 0 | 180601013498 | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2019-04-16 | 2021-04-15 | 2021-04-15 | 2021-04-15 | 2021-04-15 |  | تأخرصرف المستحقات المالية |  | 46.6172 | 24.733 | منجز | No
2100021814 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 15761842.5 | 788092.125 | 14915262 | 14915262 | 3555000709 | لا | 0 | 180809056626 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-09-26 | 2019-09-26 | 2022-12-29 | 2022-12-29 | 2019-09-26 |  | أوامر تغيير |  | 38.3216 | 23.969 | منجز | No
2100061434 | المؤسسة العامة لتحلية المياه المالحة | تشييد | ذات اولوية عالية | 865861000 | 43293050 | 794157861.32 | 794156000 | 1010012911 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-02-14 | 2020-03-16 | 2020-03-16 | 2020-03-16 | 2020-03-16 |  | تأخرصرف المستحقات المالية |  | 35.1959 | 28.021 | منجز | No
2100108824 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية وعاجلة | 2827860 | 141393 | 1055848.5 | 1055848.5 | 1010161812 | لا | 0 | 181001187320 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-12-23 | 2019-12-13 | 2020-12-23 | 2020-12-23 | 2019-12-13 |  | لا يوجد تأخير |  | 44.0155 | 26.3916 | منجز | No
2100031334 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 933167 | 46658.35 | 41377 | 0 | 1010264882 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 42 | 100 | 2013-12-03 | 2015-02-26 | 2021-06-23 | 2021-06-23 |  |  | ضعف كفاءة المقاول الفنية |  | 46.1132 | 25.1274 | مسحوب | Yes
2200226310 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 27668640 | 1383432 | 0 | 0 | 4700009877 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 0 | 0 | 2022-06-12 | 2024-06-12 | 2024-06-12 | 2024-06-12 |  |  |  |  | 39.1184 | 21.7591 | منتظم | No
2100022735 | جامعة الملك سعود | إشراف | ذات اولوية متوسطة | 12422627 | 621131.35 | 9786499.64 | 5660310.6 | 1010216984 | لا | 0 | 200309013292 | جاري | تكلفة العمل المنجز | 60 | 100 | 2019-07-07 | 2020-06-25 | 2023-02-16 | 2023-02-16 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال | تم إنذار المقاول كتابيا |  |  | خدمات عامة | No
2100030332 | أمانة / الرياض | تشييد | ذات اولوية عالية | 7735180 | 386759 | 6692866 | 0 | 1116003362 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-10-20 | 2016-10-09 | 2019-09-09 | 2019-09-09 | 2016-10-09 |  | ضعف كفاءة المقاول الفنية |  | 43.8147 | 25.0169 | منجز | Yes
2200236725 | المركز الوطني لتنمية الحياة الفطرية | تشييد | ذات اولوية عالية وعاجلة | 529460 | 26473 | 0 | 0 | 1010276571 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2022-04-03 | 2022-06-30 | 2022-06-30 | 2022-06-30 | 2022-06-30 |  |  |  | 46.4489 | 23.4363 | منجز | No
2100042501 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 4289520.86 | 214476.043 | 2127184.38 | 2127184.38 | 1128006951 | نعم | 1410371 | 210109013865 | مسحوب | منهجية القيمة المكتسبة | 45.285 | 100 | 2015-06-28 | 2016-12-10 | 2023-08-23 | 2023-08-23 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 44.4816 | 26.1805 | مسحوب | No
2100028906 | أمانة / عسير | تشييد | ذات اولوية عالية | 1488158 | 74407.9 | 0 | 0 | 2051035036 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 52 | 100 | 2018-11-14 | 2019-11-10 | 2020-03-09 | 2020-03-09 |  |  | ضعف كفاءة المقاول الفنية |  | 42.2557 | 18.7922 | مسحوب | No
2100108706 | وزارة التعليم | تشييد | ذات اولوية عالية | 14655383.86 | 732769.193 | 6686952.92 | 6686952.92 | 1010196220 | لا | 0 | 190809056943 | مسحوب | التكلفة المفوترة | 48 | 100 | 2013-12-04 | 2015-11-24 | 2022-02-02 | 2022-02-02 |  |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | مسحوب | No
2100074454 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 8330023 | 416501.15 | 5098811.54 | 5098811.54 | 1010223860 | لا | 0 |  | مسحوب | التكلفة المفوترة | 81 | 100 | 2012-10-12 | 2014-10-15 | 2023-05-03 | 2023-05-03 |  |  | ضعف كفاءة المقاول الفنية |  | 42.4987 | 18.2178 | مسحوب | No
2100087065 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 84355751 | 4217787.55 | 67316329.62 | 67316329.62 | 1010010466 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 99.82 | 100 | 2013-04-14 | 2016-03-13 | 2020-01-22 | 2020-01-22 |  | 2016-03-13 | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100064374 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2492790 | 124639.5 | 0 | 0 | 1116003536 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-01-18 | 2015-03-14 | 2015-11-15 | 2015-11-15 | 2015-03-14 |  | ضعف كفاءة المقاول الفنية |  | 46.4142 | 24.8992 | منجز | No
2100014280 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2199450.6 | 109972.53 | 635260.32 | 635260.32 | 1010045486 | لا | 0 |  | مسحوب | التكلفة المفوترة | 35 | 100 | 2015-07-29 | 2017-04-19 | 2023-05-10 | 2023-05-10 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.1677 | 21.5008 | مسحوب | No
2100056361 | وزارة الصحة / الطائف | تشييد | ذات اولوية عالية وعاجلة | 3288120 | 164406 | 1224500 | 0 | 4035000994 | لا | 0 | 190601041342 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 99 | 100 | 2019-06-10 | 2020-03-31 | 2022-01-31 | 2022-01-31 | 2020-03-31 |  | تأخرصرف المستحقات المالية |  | 40.4126 | 21.2423 | منجز | Yes
2100075121 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1016077.25 | 50803.8625 | 606991 | 0 | 1017000694 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 40 | 100 | 2015-07-29 | 2016-10-21 | 2019-09-21 | 2019-09-21 |  |  | ضعف كفاءة المقاول الفنية |  | 45.577 | 20.4595 | Failed | Yes
2100043466 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 6613500 | 330675 | 41809 | 0 | 1010157240 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 30 | 100 | 2015-04-15 | 2016-10-06 | 2020-09-04 | 2020-09-04 |  |  | ضعف كفاءة المقاول الفنية |  | 46.512 | 23.6135 | مسحوب | Yes
2100076661 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | دراسات هندسية | ذات اولوية عالية وعاجلة | 29950000 | 1497500 | 20462115.03 | 20462115.03 | 2251043785 | لا | 0 | 180809059008 | ايقاف جزئي | تكلفة العمل المنجز | 67 | 100 | 2012-07-31 | 2017-07-30 | 2023-07-31 | 2023-07-31 |  |  |  | أخرى | 49.5709 | 27.0046 | Failed | No
2200226321 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 13886279.7 | 694313.985 | 0 | 0 | 1010263725 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 0 | 0 | 2022-04-27 | 2024-04-28 | 2024-04-28 | 2024-04-28 |  |  |  |  | 39.0857 | 21.7816 | منتظم | No
2100190945 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية متوسطة | 8521957.5 | 426097.875 | 0 | 0 | 4650007032 | نعم | 2989427.4 | 200801095471 | جاري | منهجية القيمة المكتسبة | 0 | 95 | 2020-12-31 | 2022-06-30 | 2022-06-30 | 2022-06-30 |  |  |  |  | 38.8998 | 26.8397 | Failed | No
2100080124 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية وعاجلة | 6950682.3 | 347534.115 | 6837077.04 | 6837077.04 | 5950009685 | لا | 0 | 181209508869 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 98.58 | 100 | 2018-07-05 | 2020-12-06 | 2021-03-25 | 2021-03-25 |  | 2020-12-06 | لا يوجد تأخير |  | 45.5586 | 20.4478 | منجز | No
2100012924 | أمانة / عسير | تشييد | ذات اولوية عالية | 847220 | 42361 | 762458 | 762458 | 5856006665 | لا | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 50 | 100 | 2011-12-10 | 2023-03-14 | 2023-03-14 | 2023-03-14 |  |  | أوامر سامية |  | 42.6915 | 18.5932 | Failed | No
2100084991 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تصميم وتشييد | ذات اولوية عالية وعاجلة | 221166640 | 11058332 | 168868579.55 | 168868579.55 | 2051008235 | لا | 0 | 180809058498 | جاري | منهجية القيمة المكتسبة | 100 | 100 | 2014-10-22 | 2017-04-19 | 2023-09-27 | 2023-09-27 |  |  | نزع الملكيات |  | 49.5648 | 27.1019 | Failed | No
2200226332 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 319859867 | 15992993.35 | 0 | 0 | 1010120626 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 0 | 0 | 2022-06-28 | 2025-06-28 | 2025-06-28 | 2025-06-28 |  |  |  |  | 39.233 | 21.6429 | منتظم | No
2200226343 | شركة المياه الوطنية / منطقة مكة المكرمة | تصميم وتشييد | ذات اولوية عالية | 415000000 | 20750000 | 0 | 0 | 0 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 0 | 0 | 2022-06-08 | 2025-06-08 | 2025-06-08 | 2025-06-08 |  |  |  |  | 39.2642 | 21.4429 | منتظم | No
2100109325 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 10135855.3 | 506792.765 | 6146463.55 | 5997650.15 | 5859001126 | لا | 0 |  | مسحوب | التكلفة المفوترة | 83 | 100 | 2013-12-04 | 2015-11-24 | 2022-08-24 | 2022-08-24 |  |  | ضعف كفاءة المقاول الفنية |  | 42.1351 | 19.1255 | مسحوب | No
2100011922 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 10097682.24 | 504884.112 | 1.01 | 0.01 | 5950011052 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-12-14 | 2016-12-03 | 2020-08-29 | 2020-08-29 | 2016-12-03 |  | ضعف كفاءة المقاول الفنية |  | 44.2341 | 17.5757 | منجز | No
2200236740 | وزارة الطاقة | توريد وتركيب | ذات اولوية عالية وعاجلة | 13924623.2 | 696231.16 | 0 | 0 | 1010203896 | لا | 0 |  | جاري | تكلفة العمل المنجز | 0 | 0 | 2022-10-20 | 2028-01-20 | 2028-01-20 | 2028-01-20 |  |  |  |  | 46.636 | 24.7419 | منتظم | No
2100011141 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 152781492.53 | 7639074.6265 | 137425253.44 | 137425253.44 | 2050004953 | لا | 0 | 180801056345 | جاري | منهجية القيمة المكتسبة | 89 | 89 | 2018-11-12 | 2021-11-08 | 2024-05-16 | 2024-05-16 |  |  | لا يوجد تأخير |  | 49.6626 | 27.0037 | منتظم | No
2100104134 | وزارة التعليم | تشييد | ذات اولوية عالية | 6642846.5 | 332142.325 | 674816.35 | 0 | 5950007285 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 24.6 | 100 | 2014-06-15 | 2016-03-05 | 2022-05-11 | 2022-05-11 |  |  | ضعف كفاءة المقاول الفنية |  | 42.6509 | 17.1567 | مسحوب | Yes
2200226354 | شركة المياه الوطنية / منطقة مكة المكرمة | تصميم وتشييد | ذات اولوية عالية | 222750000 | 11137500 | 0 | 0 | 1010012911 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 0 | 0 | 2022-04-27 | 2025-04-27 | 2025-04-27 | 2025-04-27 |  |  |  |  | 39.2372 | 21.5693 | منتظم | No
2100103235 | شركة المياه الوطنية / منطقة الرياض | تصميم | ذات اولوية عالية | 4999890 | 249994.5 | 4789631.01 | 4789631.01 | 4030188113 | لا | 0 | 180909070174 | منجز – استلام نهائي | اخرى | 99.991 | 99.991 | 2018-06-03 | 2019-08-02 | 2019-10-16 | 2019-10-16 |  | 2019-08-02 | لا يوجد تأخير |  | 46.7936 | 24.6531 | منجز | No
2100190923 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 76552500 | 3827625 | 13908692.6 | 6813904.2 | 1010026934 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 21.5 | 31.23 | 2021-06-07 | 2022-11-20 | 2022-11-20 | 2022-11-20 |  |  |  |  | 39.8746 | 21.3843 | متأخر | No
2100040541 | شركة المياه الوطنية / منطقة الرياض | تصميم | ذات اولوية عالية | 4453000 | 222650 | 4452861.56 | 4452861.56 | 2050101543 | لا | 0 | 181109222051 | منجز – استلام نهائي | تكلفة العمل المنجز | 99.977 | 99.977 | 2019-03-17 | 2020-09-17 | 2020-09-17 | 2020-09-17 |  | 2020-09-17 | لا يوجد تأخير |  | 46.794 | 24.6531 | منجز | No
2200226365 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 81721600 | 4086080 | 0 | 0 | 1010017123 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 0 | 0 | 2022-05-17 | 2024-05-16 | 2024-05-16 | 2024-05-16 |  |  |  |  | 39.0618 | 21.7932 | منتظم | No
2200226376 | شركة المياه الوطنية / منطقة مكة المكرمة | إشراف | ذات اولوية عالية | 28288800 | 1414440 | 0 | 0 | 1010426678 | لا | 0 |  | جاري | التكلفة المفوترة | 0 | 0 | 2022-05-12 | 2025-05-12 | 2025-05-12 | 2025-05-12 |  |  |  |  | 39.1255 | 21.6132 | خدمات عامة | No
2100000066 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 3246174.195 | 162308.7098 | 411061.9 | 411061.9 | 2050052248 | لا | 0 |  | مسحوب | التكلفة المفوترة | 49 | 85 | 2016-02-07 | 2017-02-01 | 2020-05-20 | 2020-05-20 |  |  | ضعف كفاءة المقاول الفنية |  | 49.8802 | 26.0754 | مسحوب | No
2100002564 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 37702860.13 | 1885143.0065 | 0 | 0 | 2055004860 | لا | 0 |  | مسحوب | منهجية القيمة المكتسبة | 0 | 0 | 2019-03-02 | 2021-10-10 | 2023-06-10 | 2023-06-10 |  |  | ضعف كفاءة المقاول الفنية |  | 49.6626 | 27.0037 | مسحوب | No
2100094920 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | دراسات هندسية | ذات اولوية عالية وعاجلة | 70000000 | 3500000 | 66471226.32 | 66471226.32 | 1010902667 | لا | 0 | 190509106940 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 97 | 100 | 2014-08-06 | 2019-08-06 | 2021-08-06 | 2021-08-06 | 2019-08-06 |  |  |  | 49.1486 | 27.5055 | منجز | No
2100013974 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية عالية وعاجلة | 114812828 | 5740641.4 | 119242993 | 83995750.04 | 2050018628 | لا | 0 | 180801055988 | منجز – استلام ابتدائي | التكلفة المفوترة | 99 | 100 | 2018-12-29 | 2020-12-07 | 2021-11-16 | 2021-11-16 | 2020-12-07 |  |  |  | 50.1411 | 26.3345 | منجز | No
2100019073 | المؤسسة العامة لتحلية المياه المالحة | تشييد | ذات اولوية عالية | 223321090 | 11166054.5 | 212521523.58 | 212521523.58 | 1010011560 | لا | 0 | 180909107946 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-01-09 | 2021-09-04 | 2021-09-05 | 2021-09-05 | 2021-09-04 |  | تأخرصرف المستحقات المالية |  | 41.0359 | 20.9753 | منجز | No
2100010780 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 3760983.072 | 188049.1536 | 3203203.84 | 3203203.84 | 2050052248 | لا | 0 |  | مسحوب | التكلفة المفوترة | 90 | 100 | 2016-01-14 | 2017-01-08 | 2019-02-17 | 2019-02-17 |  |  | ضعف كفاءة المقاول الفنية |  | 47.6692 | 27.5714 | مسحوب | No
2100076856 | أمانة / تبوك | تشييد | ذات اولوية عالية وعاجلة | 4265520 | 213276 | 2815173.9 | 2815173.9 | 4650030480 | لا | 0 | 191001207239 | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 90 | 100 | 2019-08-24 | 2022-11-01 | 2023-03-19 | 2023-03-19 |  |  |  |  | 37.187 | 27.0479 | متأخر | No
2200226715 | أمانة / حفر الباطن | تشييد | ذات اولوية عالية | 2871809.95 | 143590.4975 | 0 | 0 | 2511006133 | لا | 0 |  | ايقاف جزئي | تكلفة العمل المنجز | 1 | 35 | 2022-06-02 | 2023-05-28 | 2023-09-28 | 2023-09-28 |  |  |  |  | 45.9627 | 28.3784 | Failed | No
2200226380 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 12978920 | 648946 | 0 | 0 | 1131014852 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 0.15 | 0 | 2022-05-08 | 2024-05-08 | 2024-05-08 | 2024-05-08 |  |  |  |  | 39.2779 | 21.301 | منتظم | No
2100082180 | وزارة الصحة / تجمع الشرقية | تشييد | ذات اولوية عالية | 2824000 | 141200 | 700000 | 700000 | 2051063580 | لا | 0 | 181009162747 | ايقاف كلي | تكلفة العمل المنجز | 20 | 100 | 2015-01-03 | 2017-04-04 | 2021-12-31 | 2021-12-31 |  |  | تصاريح أعمال التنفيذ |  | 50.1048 | 26.4082 | Failed | No
2100086590 | هيئة المدن الصناعية ومناطق التقنية | تشييد | ذات اولوية عالية | 91496340 | 4574817 | 40457175 | 35651333 | 1131013992 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 53 | 57 | 2019-12-04 | 2022-12-03 | 2023-09-22 | 2023-09-22 |  |  | اخرى |  | 26.218 | 44.1435 | منتظم | No
2200226391 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 49404346 | 2470217.3 | 0 | 0 | 1010070634 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 0.05 | 0.01 | 2022-04-24 | 2024-04-25 | 2024-04-25 | 2024-04-25 |  |  |  |  | 39.2989 | 21.419 | منتظم | No
2100016973 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 3883306.548 | 194165.3274 | 25908.05 | 25908.05 | 2050052248 | لا | 0 |  | مسحوب | التكلفة المفوترة | 89 | 100 | 2016-05-15 | 2017-05-10 | 2019-03-23 | 2019-03-23 |  |  | ضعف كفاءة المقاول الفنية |  | 49.9218 | 25.943 | مسحوب | No
2100091442 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 6039867.72 | 301993.386 | 0.01 | 0.01 | 1010008713 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0 | 100 | 2007-01-21 | 2008-10-13 | 2021-08-11 | 2021-08-11 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.5429 | 16.8808 | مسحوب | No
2200226402 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 50153000 | 2507650 | 0 | 0 | 1010158780 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 0.04 | 0 | 2022-05-15 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  |  |  |  | 40.4672 | 21.3642 | منتظم | No
2200226413 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 141158260 | 7057913 | 0 | 0 | 1010085982 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 0.05 | 0 | 2022-05-16 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  |  |  |  | 40.4991 | 21.4234 | منتظم | No
2100020580 | شركة المياه الوطنية / منطقة الحدود الشمالية | إشراف | ذات اولوية عالية | 4180433.33 | 209021.6665 | 3371721.35 | 3371721.35 | 1131052239 | لا | 0 | 190709027929 | جاري | التكلفة المفوترة | 98.5 | 100 | 2019-01-20 | 2021-07-19 | 2022-07-19 | 2022-07-19 |  |  | لا يوجد تأخير |  | 38.6674 | 31.6638 | خدمات عامة | No
2200226424 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 17539850 | 876992.5 | 0 | 0 | 4031054929 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 0 | 0 | 2022-05-16 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  |  |  |  | 40.4771 | 21.4231 | منتظم | No
2100015993 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2465164 | 123258.2 | 912040.173 | 912040.173 | 1010008713 | لا | 0 |  | مسحوب | التكلفة المفوترة | 55 | 100 | 2005-12-06 | 2012-12-16 | 2021-11-10 | 2021-11-10 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 43.1379 | 18.0853 | مسحوب | No
2200226435 | شركة المياه الوطنية / منطقة مكة المكرمة | إشراف | ذات اولوية عالية وعاجلة | 12276000 | 613800 | 164548.39 | 0 | 1131035992 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 1.37 | 0 | 2022-03-07 | 2025-03-05 | 2025-03-05 | 2025-03-05 |  |  |  |  | 40.4248 | 21.2841 | خدمات عامة | Yes
2100013930 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 4193700 | 209685 | 4193700 | 4193700 | 4032030986 | لا | 0 | 191101045496 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-10-06 | 2020-09-30 | 2021-06-16 | 2021-06-16 | 2020-09-30 |  |  |  | 40.43 | 21.2579 | منجز | No
2100082913 | أمانة / تبوك | تشييد | ذات اولوية عالية وعاجلة | 10284293.2 | 514214.66 | 10284293.2 | 10284293.2 | 3550019236 | لا | 0 | 180909107246 | مسحوب | الكميات التي تم تركيبها | 71 | 71 | 2013-12-30 | 2015-06-23 | 2021-07-01 | 2021-07-01 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | مسحوب | No
2100018771 | أمانة / عسير | تشييد | ذات اولوية عالية | 9448314 | 472415.7 | 3979088 | 700800 | 5852000047 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 86 | 100 | 2013-12-12 | 2015-03-27 | 2018-01-01 | 2018-01-01 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | مسحوب | No
2100108441 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 3337560.622 | 166878.0311 | 2139460 | 21394.6 | 2050052248 | لا | 0 |  | مسحوب | التكلفة المفوترة | 93 | 100 | 2016-01-17 | 2017-01-11 | 2019-05-05 | 2019-05-05 |  |  | ضعف كفاءة المقاول الفنية |  | 50.0219 | 25.8638 | مسحوب | No
2200236795 | وزارة الداخلية /الأحوال المدنية | تشييد | ذات اولوية عالية | 806856.75 | 40342.8375 | 0 | 0 | 3450010904 | لا | 0 |  | لم يبدأ | الكميات التي تم تركيبها | 0 | 0 | 2023-01-26 | 2023-04-26 | 2023-04-26 | 2023-04-26 |  |  |  | مخطط لإعادة طرحه | 43.514 | 29.6307 | منتظم | No
2200226446 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 3585000 | 179250 | 0 | 0 | 4031081402 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 0 | 0 | 2022-05-16 | 2024-05-15 | 2024-05-15 | 2024-05-15 |  |  |  |  | 40.4248 | 21.2841 | خدمات عامة | No
2200226450 | شركة المياه الوطنية / منطقة مكة المكرمة | إشراف | ذات اولوية عالية وعاجلة | 4142800 | 207140 | 0 | 0 | 1010322448 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 0 | 0 | 2022-04-03 | 2024-04-03 | 2024-04-03 | 2024-04-03 |  |  |  |  | 40.4248 | 21.2841 | خدمات عامة | No
2100104834 | الهيئة العامة للموانئ | تشييد | ذات اولوية عالية | 3578528 | 178926.4 | 237512 | 237512 | 1010233956 | لا | 0 | 180809043883 | مسحوب | تكلفة العمل المنجز | 15 | 100 | 2018-02-01 | 2019-02-01 | 2022-12-31 | 2022-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 50.2172 | 26.4924 | مسحوب | No
2200226472 | رئاسة أمن الدولة / القيادة العامة لطيران الأمن | تشييد | ذات اولوية عالية وعاجلة | 15219193.15 | 760959.6575 | 0 | 0 | 1010326818 | لا | 0 |  | جاري | تكلفة العمل المنجز | 12 | 20 | 2022-06-23 | 2023-01-23 | 2023-01-23 | 2023-01-23 |  |  |  |  | 47.5239 | 24.0652 | متأخر | No
2100067874 | أمانة / حفر الباطن | تشييد | ذات اولوية متوسطة | 11426680 | 571334 | 11310628 | 10342416 | 1010008188 | لا | 0 | 190509127863 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-03-05 | 2020-08-25 | 2020-12-09 | 2020-12-09 | 2020-08-25 |  | ضعف كفاءة المقاول الفنية |  | 45.9794 | 28.387 | منجز | No
2200226796 | أمانة / حفر الباطن | تشييد | ذات اولوية عالية | 3655713.15 | 182785.6575 | 3130300 | 3130300 | 1010019983 | لا | 0 |  | جاري | تكلفة العمل المنجز | 90 | 90 | 2022-02-22 | 2023-02-17 | 2023-02-17 | 2023-02-17 |  |  |  |  | 45.9627 | 28.3784 | منتظم | No
2100005246 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 8067557.597 | 403377.8799 | 5968414 | 5968414 | 1010060469 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2016-02-09 | 2017-10-31 | 2021-06-09 | 2021-06-09 | 2017-10-31 |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | منجز | No
2100019294 | أمانة / حفر الباطن | تشييد | ذات اولوية متوسطة | 10394500 | 519725 | 10393644 | 10393644 | 1010019983 | لا | 0 | 0 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-06-11 | 2021-01-21 | 2020-11-22 | 2020-11-22 | 2021-01-21 |  | ضعف كفاءة المقاول الفنية |  | 45.9502 | 28.4196 | منجز | No
2100074292 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 10213269 | 510663.45 | 4172455.98 | 3838011.79 | 1010277276 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 61 | 100 | 2014-03-11 | 2016-11-12 | 2023-02-01 | 2023-02-01 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.5429 | 16.8808 | مسحوب | No
2200231593 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 65999760 | 3299988 | 42505798 | 32220323 | 4030034104 | لا | 0 | 210801097730 | جاري | الكميات التي تم تركيبها | 68 | 71 | 2021-09-09 | 2023-07-12 | 2023-07-12 | 2023-07-12 |  |  |  |  | 46.6473 | 24.761 | منتظم | No
2100208025 | الهيئة العامة للطيران المدني | إشراف | ذات اولوية عالية وعاجلة | 20113200 | 1005660 | 14868024.81 | 13222179.79 | 4030276223 | لا | 0 | 190401063051 | جاري | مدفوعات ساعات العمل | 37.15 | 68.43 | 2019-12-22 | 2021-12-11 | 2023-08-26 | 2023-08-26 |  |  |  |  | 40.1103 | 29.7888 | خدمات عامة | No
2100085643 | جامعة الملك سعود | دعم فني | ذات اولوية متوسطة | 5895618 | 294780.9 | 0 | 0 | 1010007901 | لا | 0 | 210309058644 | جاري | تكلفة العمل المنجز | 90 | 90 | 2020-07-21 | 2020-12-14 | 2023-03-31 | 2023-03-31 |  |  | لا يوجد تأخير |  |  |  | خدمات عامة | No
2100011955 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2605253.02 | 130262.651 | 1454490 | 712451 | 4030140863 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2016-05-08 | 2017-05-03 | 2021-11-30 | 2021-11-30 | 2017-05-03 |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | منجز | No
2200226822 | أمانة / حفر الباطن | تشييد | ذات اولوية عالية | 5863604.36 | 293180.218 | 5092142.5 | 5092142.5 | 1010008188 | لا | 0 |  | جاري | تكلفة العمل المنجز | 91 | 87.5 | 2022-03-13 | 2023-03-13 | 2023-03-08 | 2023-03-08 |  |  |  |  | 45.9627 | 28.3784 | منتظم | No
2200226833 | أمانة / حفر الباطن | تشييد | ذات اولوية عالية | 5681000 | 284050 | 5085714 | 5085714 | 1010019983 | لا | 0 |  | جاري | تكلفة العمل المنجز | 92 | 77 | 2022-04-25 | 2023-04-25 | 2023-04-25 | 2023-04-25 |  |  |  |  | 45.9627 | 28.3784 | منتظم | No
2100002796 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 5873000 | 293650 | 1424214 | 1424214 | 1010252537 | لا | 0 |  | مسحوب | التكلفة المفوترة | 54 | 100 | 2014-08-19 | 2016-05-10 | 2023-08-15 | 2023-08-15 |  |  | ضعف كفاءة المقاول الفنية |  | 42.9095 | 23.8972 | مسحوب | No
2200226844 | أمانة / حفر الباطن | تشييد | ذات اولوية عالية | 472650 | 23632.5 | 339428.96 | 339428.96 | 2511016730 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 98 | 2022-07-24 | 2023-01-24 | 2023-01-24 | 2023-01-24 | 2023-01-24 |  |  |  | 45.9627 | 28.3784 | منجز | No
2100108555 | وزارة التعليم | تشييد | ذات اولوية عالية | 2547586 | 127379.3 | 552087.36 | 552087.36 | 4035000741 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2019-10-17 | 2020-05-04 | 2020-10-08 | 2020-10-08 | 2020-05-04 |  | ضعف كفاءة المقاول الفنية |  | 40.4511 | 21.2747 | منجز | No
2200226892 | المؤسسة العامة لتحلية المياه المالحة | تشييد | ذات اولوية عالية | 1679000000 | 83950000 | 620198351.02 | 510932705.75 | 1010419199 | لا | 0 | 201001078933 | جاري | منهجية القيمة المكتسبة | 63.8 | 63.8 | 2020-12-06 | 2024-01-05 | 2024-01-05 | 2024-01-05 |  |  |  |  | 39.5355 | 20.6903 | منتظم | No
2200231615 | وزارة الحرس الوطني / وكالة الشؤون الفنية | تشييد | ذات اولوية متوسطة | 23981735.04 | 1199086.752 | 3922756.73 | 0 | 3400101308 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 15 | 14 | 2022-07-20 | 2024-01-02 | 2024-01-02 | 2024-01-02 |  |  |  |  | 43.5202 | 29.6257 | منتظم | Yes
2200226936 | المؤسسة العامة لتحلية المياه المالحة | تشييد | ذات اولوية عالية | 90239503 | 4511975.15 | 48844442 | 48844442 | 4030128442 | لا | 0 | 200801034512 | جاري | تكلفة العمل المنجز | 78.9 | 100 | 2020-11-19 | 2022-12-31 | 2022-12-31 | 2022-12-31 |  |  |  |  | 39.8579 | 21.3891 | متأخر | No
2200226855 | أمانة / حفر الباطن | توريد وتركيب | ذات اولوية عالية | 3047500 | 152375 | 1386102.5 | 1386102.5 | 2511006133 | لا | 0 |  | جاري | تكلفة العمل المنجز | 45.48 | 70 | 2022-05-24 | 2022-11-20 | 2022-11-20 | 2022-11-20 |  |  |  |  | 45.9627 | 28.3784 | متأخر | No
2100088911 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية وعاجلة | 395051922.44 | 19752596.122 | 133514353.26 | 133514353.26 | 1010014578 | لا | 0 | 180909089093 | جاري | مدفوعات ساعات العمل | 70.76 | 78.74 | 2010-06-28 | 2013-06-11 | 2024-12-31 | 2024-12-31 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | متأخر | No
2100047386 | أمانة / عسير | تشييد | ذات اولوية عالية | 248885.7 | 12444.285 | 0 | 0 | 5850012824 | لا | 0 | 200209128404 | فسخ العقد | تكلفة العمل المنجز | 0 | 100 | 2019-08-04 | 2019-12-02 | 2020-09-16 | 2020-09-16 |  |  | سوء التخطيط الاولي للمشروع |  | 42.8114 | 18.0849 | مسحوب | No
2100048856 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 3527607.852 | 176380.3926 | 388732.31 | 388732.31 | 4030023505 | لا | 0 | 190809095858 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-07-06 | 2020-06-30 | 2021-03-16 | 2021-03-16 | 2020-06-30 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 49.7141 | 25.4068 | منجز | No
2200226870 | أمانة / حفر الباطن | توريد وتركيب | ذات اولوية عالية | 626525 | 31326.25 | 0 | 0 | 1010007332 | لا | 0 |  | جاري | تكلفة العمل المنجز | 30 | 35 | 2022-04-24 | 2022-12-21 | 2022-12-21 | 2022-12-21 |  |  |  |  | 45.9627 | 28.3784 | منتظم | No
2100015971 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية وعاجلة | 54937750 | 2746887.5 | 32819195.7 | 32819195.7 | 5850014380 | لا | 0 |  | مسحوب | منهجية القيمة المكتسبة | 59.47 | 100 | 2012-09-29 | 2014-09-08 | 2024-04-01 | 2024-04-01 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.6968 | 27.506 | مسحوب | No
2200226866 | أمانة / حفر الباطن | توريد وتركيب | ذات اولوية عالية | 626525 | 31326.25 | 0 | 0 | 1010007332 | لا | 0 |  | جاري | تكلفة العمل المنجز | 30 | 33 | 2022-09-21 | 2022-12-21 | 2022-12-21 | 2022-12-21 |  |  |  |  | 45.9975 | 28.3595 | منتظم | No
2100106190 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 10279110.19 | 513955.5095 | 8688051.54 | 0 | 1010183010 | لا | 0 |  | مسحوب | التكلفة المفوترة | 78 | 100 | 2013-10-05 | 2015-03-29 | 2022-05-04 | 2022-05-04 |  |  | ضعف كفاءة المقاول الفنية |  | 41.4779 | 20.0185 | مسحوب | Yes
2200226881 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية | 55922154 | 2796107.7 | 0 | 0 | 5855020873 | لا | 0 | 181001139597 | جاري | منهجية القيمة المكتسبة | 0 | 0 | 2022-06-21 | 2024-05-30 | 2024-05-30 | 2024-05-30 |  |  |  |  | 41.4362 | 19.756 | منتظم | No
2100015374 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 181218543 | 9060927.15 | 149676106.24 | 149676106.24 | 4030023505 | لا | 0 | 180809043422 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 99.98 | 100 | 2014-05-12 | 2016-05-11 | 2023-02-11 | 2023-02-11 |  |  |  |  | 38.2296 | 23.9988 | متأخر | No
2100103655 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2941243.04 | 147062.152 | 0 | 0 | 1010233305 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0 | 100 | 2015-02-15 | 2017-02-17 | 2023-02-15 | 2023-02-15 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.5429 | 16.8808 | مسحوب | No
2200210803 | المؤسسة العامة للحبوب | تصميم وتشييد | ذات اولوية عالية | 351350 | 17567.5 | 351350 | 351350 | 4650207709 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 1 | 1 | 2021-06-20 | 2021-08-20 | 2022-05-20 | 2022-05-20 | 2021-08-20 |  |  |  | 38.1989 | 24.0173 | منجز | No
2100094205 | وزارة النقل والخدمات اللوجستية / منطقة جازان | تشييد | ذات اولوية متوسطة | 29722889.55 | 1486144.4775 | 19052736 | 19052736 | 1010152168 | لا | 0 | 181109319096 | مسحوب | الكميات التي تم تركيبها | 77 | 100 | 2010-04-08 | 2013-03-04 | 2019-12-03 | 2019-12-03 |  |  | اخرى |  | 43.1161 | 17.2311 | مسحوب | No
2200226984 | الهيئة العامة للموانئ | تحديث وتوريد | ذات اولوية عالية | 5732510 | 286625.5 | 2991096.53 | 2991096.53 | 4030085464 | لا | 0 |  | جاري | تكلفة العمل المنجز | 97 | 100 | 2022-01-24 | 2022-07-23 | 2022-12-22 | 2022-12-22 |  |  |  |  | 39.1763 | 21.4483 | منتظم | No
2100095443 | هيئة الهلال الأحمر السعودي | تشييد | ذات اولوية عالية | 465000 | 23250 | 199881.8 | 199881.8 | 1010420294 | لا | 0 | 181209455940 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 98 | 100 | 2018-02-08 | 2018-08-05 | 2021-11-21 | 2021-11-21 | 2018-08-05 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.1587 | 25.1053 | منجز | No
2100054342 | وزارة الداخلية / المديرية العامة للدفاع المدني | تشييد | ذات اولوية عالية | 24430050.96 | 1221502.548 | 18376967.06 | 18376967.06 | 1010110300 | لا | 0 | 180701014843 | جاري | الكميات التي تم تركيبها | 85 | 90 | 2019-04-30 | 2021-12-01 | 2022-09-01 | 2022-09-01 |  |  | تأخرصرف المستحقات المالية |  | 46.8223 | 24.8323 | Failed | No
2100069576 | المؤسسة العامة للري | تشييد | ذات اولوية عالية | 135766186.37 | 6788309.3185 | 135257727.99 | 135257727.99 | 1010157711 | لا | 0 | 180809054150 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 75 | 100 | 2012-12-16 | 2018-10-05 | 2022-01-14 | 2022-01-14 | 2018-10-05 |  | ضعف كفاءة المقاول الفنية |  | 49.6364 | 25.3949 | منجز | No
2100090473 | وزارة التعليم | تشييد | ذات اولوية عالية | 8976627.9 | 448831.395 | 1051775.46 | 0 | 1010223860 | لا | 0 |  | مسحوب | التكلفة المفوترة | 21 | 100 | 2013-09-22 | 2015-09-13 | 2022-11-29 | 2022-11-29 |  |  | ضعف كفاءة المقاول الفنية |  | 42.6509 | 17.1567 | مسحوب | Yes
2100043024 | جامعة الملك سعود | تشييد | ذات اولوية عالية | 10291558 | 514577.9 | 9721587.78 | 9721587.78 | 1010217074 | لا | 0 | 190901134926 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-10-01 | 2019-10-01 | 2021-12-18 | 2021-12-18 | 2019-10-01 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 46.7098 | 24.6275 | منجز | No
2100020086 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | دراسات هندسية | ذات اولوية عالية وعاجلة | 16934790 | 846739.5 | 3582853.75 | 3582853.75 | 2251043785 | لا | 0 |  | جاري | تكلفة العمل المنجز | 19 | 91 | 2018-08-29 | 2023-08-28 | 2023-08-28 | 2023-08-28 |  |  |  | أخرى | 49.5686 | 26.9621 | خدمات عامة | No
2100103751 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 10389134 | 519456.7 | 0 | 0 | 1010051817 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0 | 100 | 2015-03-06 | 2019-03-27 | 2019-03-27 | 2019-03-27 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.5429 | 16.8808 | مسحوب | No
2100077302 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 276066714 | 13803335.7 | 224847029 | 224847029 | 1010066115 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 84.75 | 85.27 | 2009-10-13 | 2019-09-22 | 2022-12-31 | 2022-12-31 |  |  |  | أخرى | 46.8656 | 24.7986 | منتظم | No
2100053745 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 23375568.73 | 1168778.4365 | 21304028 | 21304028 | 1010066115 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-07-08 | 2015-10-03 | 2021-11-15 | 2021-11-15 | 2015-10-03 |  |  |  | 45.5239 | 23.474 | منجز | No
2100042512 | جامعة الملك سعود | تشييد | ذات اولوية عالية | 2518110 | 125905.5 | 2518110 | 2518110 | 1010217674 | لا | 0 | 200601070254 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-10-30 | 2019-06-23 | 2020-11-25 | 2020-11-25 | 2019-06-23 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 46.7098 | 24.6275 | منجز | No
2100107866 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 249537124 | 12476856.2 | 81209994.83 | 81209994.83 | 2051001558 | لا | 0 | 181001178688 | جاري | منهجية القيمة المكتسبة | 18 | 100 | 2019-02-26 | 2021-11-02 | 2023-10-01 | 2023-10-01 |  |  | ضعف كفاءة المقاول الفنية |  | 49.6626 | 27.0037 | Failed | No
2200231453 | جامعة جدة | ترميم | ذات اولوية عالية | 977500 | 48875 | 0 | 0 | 4030424798 | لا | 0 |  | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2022-09-07 | 2022-12-06 | 2023-01-18 | 2023-01-18 |  |  |  |  | 39.1839 | 21.5777 | متأخر | No
2100040795 | جامعة حائل | إشراف | ذات اولوية عالية وعاجلة | 11587200 | 579360 | 6831126 | 6348326 | 4030276223 | لا | 0 |  | جاري | التكلفة المفوترة | 58 | 58 | 2019-04-10 | 2021-04-09 | 2021-12-09 | 2021-12-09 |  |  | لا يوجد تأخير |  |  |  | خدمات عامة | No
2100091770 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2873646.41 | 143682.3205 | 1834412.65 | 1834412.65 | 1010233819 | لا | 0 | 190909163761 | مسحوب | التكلفة المفوترة | 73 | 100 | 2015-05-13 | 2016-05-07 | 2022-10-31 | 2022-10-31 |  |  | ضعف كفاءة المقاول الفنية |  | 40.0549 | 29.8587 | مسحوب | No
2100088756 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 3301767.07 | 165088.3535 | 2842176.93 | 2842176.93 | 3400009021 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2016-03-01 | 2017-02-24 | 2020-02-23 | 2020-02-23 | 2017-02-24 |  |  |  | 40.0549 | 29.8587 | منجز | No
2100011200 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 5375037 | 268751.85 | 2907116 | 0 | 3350007326 | لا | 0 |  | مسحوب | التكلفة المفوترة | 54 | 100 | 2013-09-09 | 2015-06-02 | 2019-01-31 | 2019-01-31 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | مسحوب | Yes
2100011933 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 98663761.18 | 4933188.059 | 70020716.98 | 70020716.98 | 1010076960 | لا | 0 | 180709034342 | جاري | منهجية القيمة المكتسبة | 89 | 100 | 2014-06-08 | 2016-12-04 | 2023-02-27 | 2023-02-27 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 49.6626 | 27.0037 | Failed | No
2100079391 | جامعة الملك سعود | تشييد | ذات اولوية عالية | 7343035 | 367151.75 | 3522482.5 | 3522482.5 | 1010181486 | لا | 0 | 201009121008 | جاري | تكلفة العمل المنجز | 90 | 100 | 2019-10-23 | 2020-10-09 | 2021-12-07 | 2021-12-07 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 46.7098 | 24.6275 | Failed | No
2100092035 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 5447015 | 272350.75 | 813450 | 813450 | 5850000978 | لا | 0 |  | ايقاف كلي | التكلفة المفوترة | 45 | 100 | 2006-11-15 | 2008-11-05 | 2022-02-09 | 2022-02-09 |  |  | ضعف كفاءة المقاول الفنية |  | 42.0529 | 18.5228 | Failed | No
2100086030 | وزارة الداخلية / ديوان وزارة الداخلية | تصميم وتشييد | ذات اولوية عالية وعاجلة | 1355372100.73 | 67768605.0365 | 529285803.22 | 529285803.22 | 1010199246 | لا | 0 | 180809053494 | جاري | منهجية القيمة المكتسبة | 45 | 45.27 | 2016-10-19 | 2019-06-04 | 2024-06-30 | 2024-06-30 |  |  | تأخرصرف المستحقات المالية | أخرى | 47.0512 | 17.5349 | Failed | No
2100078934 | شركة المياه الوطنية / منطقة الحدود الشمالية | إشراف | ذات اولوية عالية | 9297200 | 464860 | 8939021.93 | 8939021.93 | 1010406370 | لا | 0 | 180709026216 | منجز – استلام ابتدائي | التكلفة المفوترة | 98.86 | 100 | 2014-04-22 | 2017-04-22 | 2022-04-15 | 2022-04-15 | 2017-04-22 |  | لا يوجد تأخير |  | 41.0227 | 30.9755 | منجز | No
2100010360 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 250132238.41 | 12506611.9205 | 191584663.572 | 191584663.572 | 1010287504 | لا | 0 | 180809058733 | جاري | منهجية القيمة المكتسبة | 100 | 100 | 2012-10-23 | 2014-10-21 | 2023-08-11 | 2023-08-11 |  |  | لا يوجد تأخير |  | 49.6626 | 27.0037 | Failed | No
2200227006 | أمانة / الرياض | الخدمات الاستشارية | ذات اولوية متوسطة | 11475849.76 | 573792.488 | 5248800.05 | 5248800.05 | 1010322156 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 45 | 40 | 2022-05-16 | 2023-05-17 | 2023-05-17 | 2023-05-17 |  |  |  |  | 46.6736 | 24.6258 | خدمات عامة | No
2200227010 | الهيئة العامة للموانئ | توريد وتركيب | ذات اولوية عالية | 2338557 | 116927.85 | 724942.56 | 724942.56 | 4030017304 | لا | 0 |  | جاري | تكلفة العمل المنجز | 81 | 96 | 2022-04-17 | 2022-10-14 | 2022-12-15 | 2022-12-15 |  |  |  |  | 39.1707 | 21.4663 | متأخر | No
2100042571 | وزارة التعليم | تشييد | ذات اولوية عالية | 11564441.02 | 578222.051 | 4811490.46 | 4811490.46 | 1116004360 | لا | 0 | 190309007804 | مسحوب | التكلفة المفوترة | 44 | 100 | 2013-01-25 | 2015-01-17 | 2015-04-15 | 2015-04-15 |  |  | ضعف كفاءة المقاول الفنية |  | 41.4333 | 19.7855 | مسحوب | No
2200227021 | الهيئة العامة للموانئ | توريد وتركيب | ذات اولوية عالية | 4176447 | 208822.35 | 0 | 0 | 4030097299 | لا | 0 |  | جاري | تكلفة العمل المنجز | 38 | 48 | 2022-04-27 | 2022-10-24 | 2023-05-07 | 2023-05-07 |  |  |  |  | 39.1723 | 21.4729 | متأخر | No
2100044656 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 949050 | 47452.5 | 854144 | 0 | 1185000614 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-11-24 | 2015-09-20 | 2015-09-20 | 2015-09-20 | 2015-09-20 |  | ضعف كفاءة المقاول الفنية |  | 45.5688 | 20.4517 | منجز | Yes
2100014501 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 202355697.642 | 10117784.8821 | 164255751 | 164255751 | 2050018628 | لا | 0 | 190401088442 | جاري | تكلفة العمل المنجز | 80 | 85 | 2019-08-25 | 2021-08-14 | 2022-11-28 | 2022-11-28 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5425 | 25.3468 | منتظم | No
2100000136 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 15315472.06 | 765773.603 | 11052566.89 | 11052566.89 | 1010102752 | لا | 0 | 180709016877 | جاري | تكلفة العمل المنجز | 70 | 100 | 2017-09-26 | 2018-09-21 | 2022-12-31 | 2022-12-31 |  |  | تأخرصرف المستحقات المالية |  | 39.1677 | 21.5008 | Failed | No
2200227194 | المؤسسة العامة لتحلية المياه المالحة | تشييد | ذات اولوية عالية | 87627827 | 4381391.35 | 30188500.75 | 30188500.75 | 7001355564 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 57.8 | 58.1 | 2021-10-19 | 2023-10-19 | 2023-10-19 | 2023-10-19 |  |  |  |  | 39.8579 | 21.3891 | منتظم | No
2200231722 | وزارة النقل والخدمات اللوجستية / منطقة جازان | تشييد | ذات اولوية متوسطة | 23969878.35 | 1198493.9175 | 0 | 0 | 1123001261 | لا | 0 |  | جاري | تكلفة العمل المنجز | 0 | 0 | 2022-09-27 | 2023-09-15 | 2023-09-15 | 2023-09-15 |  |  |  |  | 43.1311 | 17.3392 | منتظم | No
2100065203 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 11286726 | 564336.3 | 3701322 | 0 | 1012001538 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 99 | 23 | 2019-02-26 | 2020-08-14 | 2020-08-15 | 2020-08-15 | 2020-08-14 |  |  |  | 47.1476 | 23.9888 | منجز | Yes
2200226553 | رئاسة أمن الدولة / القيادة العامة لطيران الأمن | توريد وتركيب | ذات اولوية عالية وعاجلة | 2496609.75 | 124830.4875 | 0 | 0 | 1010182840 | لا | 0 |  | لم يبدأ | تكلفة العمل المنجز | 0 | 10 |  |  |  | 2023-09-17 |  |  |  |  | 42.6523 | 18.233 | متأخر | No
2100065785 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 5814900 | 290745 | 1718306.66 | 0 | 1011000444 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 70.29 | 100 | 2013-07-29 | 2014-10-22 | 2014-10-22 | 2014-10-22 | 2014-10-22 |  |  |  | 47.1487 | 23.983 | منجز | Yes
2100013392 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 8916883.5 | 445844.175 | 6059165.66 | 5513000.29 | 4030140863 | لا | 0 | 190209015464 | جاري | التكلفة المفوترة | 82 | 100 | 2014-10-12 | 2016-07-03 | 2022-12-31 | 2022-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 40.2691 | 20.1489 | Failed | No
2100016715 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2775226 | 138761.3 | 2266852.99 | 2266852.99 | 4032024978 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2019-08-27 | 2020-04-19 | 2020-02-09 | 2020-02-09 | 2020-04-19 |  |  |  | 40.4511 | 21.2747 | منجز | No
2100078050 | وزارة الصحة / المدينة المنورة | تشييد | ذات اولوية عالية | 54903781.8 | 2745189.09 | 48729344 | 45320314 | 4650037481 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 85 | 100 | 2012-12-14 | 2014-11-22 | 2022-08-31 | 2022-08-31 |  |  | تأخرصرف المستحقات المالية |  | 39.5611 | 24.4929 | Failed | No
2100064282 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 14977228.87 | 748861.4435 | 13626136.69 | 13626136.69 | 4030016236 | لا | 0 | 180709018304 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2017-12-11 | 2018-08-15 | 2022-06-30 | 2022-06-30 |  |  | تأخرصرف المستحقات المالية |  | 39.1677 | 21.5008 | متأخر | No
2100034694 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 11550800 | 577540 | 9873976 | 9873976 | 1010158466 | لا | 0 |  | مسحوب | التكلفة المفوترة | 85.48 | 85.48 | 2014-07-17 | 2016-06-25 | 2017-04-16 | 2017-04-16 |  |  | اخرى |  | 39.8866 | 21.3561 | مسحوب | No
2100008131 | وزارة الدفاع / الإدارة الهندسية والاشغال بالخدمات الصحية | تشييد | ذات اولوية متوسطة | 12502713.6 | 625135.68 | 10325214.44 | 10325214.44 | 5951000854 | لا | 0 | 180909086697 | جاري | الكميات التي تم تركيبها | 85 | 100 | 2014-01-03 | 2017-11-19 | 2021-12-31 | 2021-12-31 |  |  | اخرى |  | 47.1849 | 17.5123 | Failed | No
2100009063 | وزارة المالية | تشييد | ذات اولوية متوسطة | 46674016.5 | 2333700.825 | 38926758.44 | 38926758.44 | 1010153533 | لا | 0 | 180809053485 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2012-04-16 | 2013-07-15 | 2018-11-08 | 2018-11-08 | 2013-07-15 |  | لا يوجد تأخير |  | 39.7597 | 21.4384 | منجز | No
2100032093 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1175500 | 58775 | 326600 | 0 | 1115001965 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 66 | 100 | 2018-10-28 | 2019-10-23 | 2019-10-19 | 2019-10-19 | 2019-10-23 |  |  |  | 46.6823 | 24.7231 | منجز | Yes
2100015912 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 5545492 | 277274.6 | 172415.6 | 172415.6 | 1010213931 | لا | 0 |  | مسحوب | التكلفة المفوترة | 70 | 100 | 2015-08-09 | 2017-07-29 | 2022-05-11 | 2022-05-11 |  |  | ضعف كفاءة المقاول الفنية |  | 40.4511 | 21.2747 | مسحوب | No
2100085956 | وزارة المالية | مساحة | ذات اولوية متوسطة | 173250 | 8662.5 | 51975 | 51975 | 7007707800 | لا | 0 |  | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 98 | 100 | 2019-02-28 | 2020-03-15 | 2022-11-01 | 2022-11-01 |  |  | موافقات |  | 40.4436 | 21.2561 | منتظم | No
2100080463 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3597000 | 179850 | 2514670.78 | 0 | 1010244841 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 96.03 | 100 | 2015-10-13 | 2017-04-05 | 2020-01-16 | 2020-01-16 | 2017-04-05 |  | ضعف كفاءة المقاول الفنية |  | 42.9464 | 23.9042 | منجز | Yes
2100046896 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 6355356 | 317767.8 | 6175906 | 0 | 1010258653 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 97.18 | 100 | 2014-09-23 | 2016-09-12 | 2020-03-18 | 2020-03-18 | 2016-09-12 |  | ضعف كفاءة المقاول الفنية |  | 46.6617 | 24.7206 | منجز | Yes
2200212940 | وزارة المالية | تشييد | ذات اولوية عالية | 15166107.36 | 758305.368 | 10633825.88 | 10633825.88 | 1010228607 | لا | 0 | 201101007629 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2021-10-17 | 2022-04-16 | 2022-09-01 | 2022-09-01 | 2022-04-16 |  |  |  | 46.7275 | 24.7878 | منجز | No
2100019084 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2609119.11 | 130455.9555 | 1953176.99 | 1295252.37 | 5861031775 | لا | 0 | 190309057516 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-12-01 | 2016-11-25 | 2021-11-24 | 2021-11-24 | 2016-11-25 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.221 | 18.0976 | منجز | No
2100194972 | هيئة المدن الصناعية ومناطق التقنية | تشييد | ذات اولوية عالية | 19224000 | 961200 | 9250175 | 9250175 | 4030126557 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 61 | 66 | 2021-05-04 | 2022-11-04 | 2023-05-03 | 2023-05-03 |  |  |  |  | 39.2384 | 21.4089 | منتظم | No
2100101861 | جامعة جدة | تشييد | ذات اولوية متوسطة | 11029262.71 | 551463.1355 | 8185466.78 | 3450594 | 1010054285 | لا | 0 | 200409077978 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-09-08 | 2020-10-04 | 2020-10-04 | 2020-10-04 | 2020-10-04 |  | أوامر تغيير |  | 21.8911 | 39.2563 | منجز | No
2100037844 | وزارة النقل والخدمات اللوجستية / منطقة جازان | تشييد | ذات اولوية متوسطة | 52516037.25 | 2625801.8625 | 37690080 | 37690080 | 1010184457 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 89.1 | 100 | 2008-06-15 | 2010-11-16 | 2022-06-30 | 2022-06-30 |  |  |  |  | 42.9354 | 16.6018 | مسحوب | No
2100198866 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية عالية | 103801084.67 | 5190054.2335 | 21386403 | 21386403 | 1010205512 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 32.95 | 41.1 | 2020-09-10 | 2022-08-19 | 2023-08-31 | 2023-08-31 |  |  |  | أخرى | 46.9359 | 24.881 | متأخر | No
2100095454 | وزارة الصحة / الجوف | تشييد | ذات اولوية عالية وعاجلة | 11390800 | 569540 | 10013518.49 | 10013518.49 | 3400010482 | لا | 0 | 210909172076 | جاري | الكميات التي تم تركيبها | 96 | 100 | 2019-11-30 | 2020-09-30 | 2023-02-28 | 2023-02-28 |  |  | تأخرصرف المستحقات المالية | تم تمديد الجدول الزمني | 39.8587 | 29.8067 | منتظم | No
2100075611 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 587295 | 29364.75 | 0 | 0 | 3350142637 | لا | 0 | 200501096165 | مسحوب | الكميات التي تم تركيبها | 42 | 100 | 2019-09-07 | 2020-02-06 | 2020-02-06 | 2020-02-06 |  |  | ضعف كفاءة المقاول الفنية |  | 42.4135 | 27.8869 | مسحوب | No
2100095642 | وزارة الصحة / القصيم | تشييد | ذات اولوية عالية وعاجلة | 49175767 | 2458788.35 | 31771123 | 31771123 | 1010023333 | لا | 0 | 181009134589 | جاري | تكلفة العمل المنجز | 99 | 100 | 2017-07-24 | 2020-03-26 | 2021-12-30 | 2021-12-30 |  |  | تأخرصرف المستحقات المالية |  | 43.9553 | 26.3508 | Failed | No
2100192813 | جامعة القصيم | تشييد | ذات اولوية عالية | 13940564.96 | 697028.248 | 12456908.15 | 12456908.15 | 1132000644 | لا | 0 | 180909083206 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-08-10 | 2015-06-06 | 2019-05-06 | 2019-05-06 | 2015-06-06 |  |  |  | 43.5397 | 25.8783 | منجز | No
2100052054 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية عالية | 2729475 | 136473.75 | 2646487 | 2646487 | 4031046580 | لا | 0 | 190301043597 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 96.96 | 96.96 | 2018-12-09 | 2020-12-08 | 2021-03-16 | 2021-03-16 |  |  |  |  | 39.8638 | 21.3734 | Failed | No
2100190540 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 8975000 | 448750 | 3553675 | 3553675 | 4032025656 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 75 | 78.77 | 2020-09-13 | 2022-03-14 | 2022-09-02 | 2022-09-02 |  |  |  |  | 39.881 | 21.413 | منتظم | No
2100105405 | جامعة الملك خالد | تشييد | ذات اولوية عالية وعاجلة | 106023061.1 | 5301153.055 | 95420753.16 | 95420753.16 | 2051037631 | لا | 0 | 180809037870 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2016-10-05 | 2017-09-20 | 2021-05-01 | 2021-05-01 |  |  | تأخرصرف المستحقات المالية |  | 42.8114 | 18.1027 | Failed | No
2100046093 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 29972710 | 1498635.5 | 20454455.5 | 0 | 1116005202 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-10-22 | 2016-10-11 | 2019-11-14 | 2019-11-14 | 2016-10-11 |  | ضعف كفاءة المقاول الفنية |  | 44.8263 | 24.3798 | منجز | Yes
2100077265 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 104187102.53 | 5209355.1265 | 89230893.22 | 89230893.22 | 2051034972 | لا | 0 | 180701015761 | جاري | منهجية القيمة المكتسبة | 83 | 100 | 2018-10-11 | 2021-04-08 | 2023-01-01 | 2023-01-01 |  |  | اخرى |  | 49.6626 | 27.0037 | متأخر | No
2100079155 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 5253193 | 262659.65 | 0.01 | 0.01 | 1131028136 | لا | 0 |  | جاري | تكلفة العمل المنجز | 8 | 100 | 2015-10-05 | 2016-12-21 | 2023-12-25 | 2023-12-25 |  |  | موافقات |  | 43.6083 | 26.2568 | Failed | No
2100023402 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 5192968.15 | 259648.4075 | 3073812.96 | 3073812.96 | 1010041144 | لا | 0 |  | مسحوب | التكلفة المفوترة | 80 | 100 | 2012-04-02 | 2013-11-23 | 2022-06-25 | 2022-06-25 |  |  | ضعف كفاءة المقاول الفنية |  | 43.9875 | 26.0873 | مسحوب | No
2200231895 | أمانة / حائل | تصميم وإشراف | ذات اولوية متوسطة | 1523175 | 76158.75 | 1523175 | 0 | 3350029913 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2021-01-07 | 2022-04-01 | 2022-04-01 | 2022-04-01 | 2022-04-01 |  |  |  | 41.1804 | 27.3782 | منجز | Yes
2100045651 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 398990 | 19949.5 | 0 | 0 | 1131040351 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 81.73 | 83 | 2019-01-23 | 2020-01-23 | 2022-11-17 | 2022-11-17 | 2020-01-23 |  | ضعف كفاءة المقاول الفنية |  | 45.1824 | 25.3447 | منجز | No
2100003124 | المؤسسة العامة لتحلية المياه المالحة | تشييد | ذات اولوية عالية | 1658404761.89 | 82920238.0945 | 1370520394.03 | 1370520394.03 | 1010440093 | لا | 0 | 200101012316 | جاري | منهجية القيمة المكتسبة | 99.2 | 100 | 2019-02-14 | 2022-07-07 | 2023-03-31 | 2023-03-31 |  |  | لا يوجد تأخير |  | 49.7881 | 26.8871 | منتظم | No
2100092223 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 142883339.72 | 7144166.986 | 102049787.7 | 102049787.7 | 4650030714 | لا | 0 | 181009177525 | جاري | الكميات التي تم تركيبها | 78.3 | 82.1 | 2013-02-19 | 2017-01-06 | 2023-02-14 | 2023-02-14 |  |  | ضعف كفاءة المقاول الفنية |  | 39.5069 | 21.3704 | منتظم | No
2200231906 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 691495 | 34574.75 | 0 | 0 | 3351005488 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 80 | 100 | 2022-09-01 | 2023-09-01 | 2023-09-01 | 2023-09-01 |  |  |  | العقد يسير حسب الخطة | 41.1804 | 27.3782 | متأخر | No
2100064665 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3990200 | 199510 | 0 | 0 | 1010196247 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 1 | 100 | 2010-04-29 | 2018-02-18 | 2018-12-19 | 2018-12-19 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | مسحوب | No
2100008842 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1725079 | 86253.95 | 786908 | 786908 | 2511482400 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2013-06-03 | 2014-04-29 | 2021-08-19 | 2021-08-19 | 2014-04-29 |  | ضعف كفاءة المقاول الفنية |  | 45.975 | 28.4334 | منجز | No
2100040040 | وزارة الداخلية / ديوان وزارة الداخلية | تصميم وتشييد | ذات اولوية عالية وعاجلة | 2593242629.12 | 129662131.456 | 1647204290.49 | 1612157729.42 | 1010199246 | لا | 0 | 180809053447 | جاري | منهجية القيمة المكتسبة | 81.1 | 100 | 2016-06-28 | 2018-12-14 | 2024-01-24 | 2024-01-24 |  |  | تأخرصرف المستحقات المالية | تم تمديد الجدول الزمني | 42.451 | 17.1827 | متأخر | No
2100102244 | وزارة الصحة / جدة | تشييد | ذات اولوية عالية وعاجلة | 9995187 | 499759.35 | 2463329.99 | 2463329.99 | 4030136675 | نعم | 2148718 | 181009147276 | مسحوب | الكميات التي تم تركيبها | 54 | 100 | 2014-08-13 | 2015-05-04 | 2023-02-28 | 2023-02-28 |  |  | ضعف كفاءة المقاول الفنية | مخطط لسحبه وإعادة ترسيته | 39.1726 | 21.5394 | مسحوب | No
2100097882 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 292604004.46 | 14630200.223 | 88570531.9 | 67848417.96 | 2055002293 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 94.1 | 100 | 2015-01-03 | 2016-06-26 | 2023-03-31 | 2023-03-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال | أخرى | 39.8335 | 21.4343 | Failed | No
2100109841 | وزارة الداخلية / ديوان وزارة الداخلية | تصميم وتشييد | ذات اولوية عالية وعاجلة | 820551385.79 | 41027569.2895 | 496519274.97 | 490766934.81 | 1010199246 | لا | 0 | 180809053447 | جاري | منهجية القيمة المكتسبة | 83.89 | 93.29 | 2015-03-31 | 2017-09-15 | 2023-10-01 | 2023-10-01 |  |  | تأخرصرف المستحقات المالية | أخرى | 42.0847 | 16.705 | متأخر | No
2100066172 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1140000 | 57000 | 1140000 | 0 | 1011008928 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-02-21 | 2020-02-16 | 2020-02-15 | 2020-02-15 | 2020-02-16 |  |  |  | 46.663 | 24.7131 | منجز | Yes
2100085816 | وزارة المالية - الحرمين | تشييد | ذات اولوية عالية وعاجلة | 4313000000 | 1000000000 | 1709260650 | 1709260650 | 4030068284 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 99.82 | 100 | 2012-12-15 | 2015-12-14 | 2023-03-31 | 2023-03-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.8208 | 21.4274 | متأخر | No
2100038684 | جامعة الملك فيصل | تصميم | ذات اولوية عالية | 850000 | 42500 | 850000 | 850000 | 1010327067 | لا | 0 | 180809056310 | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2013-11-25 | 2014-01-22 | 2014-01-22 | 2014-01-22 |  | 2014-01-22 | تأخرصرف المستحقات المالية |  | 49.5924 | 25.3429 | منجز | No
2100065450 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 15754775 | 787738.75 | 41710 | 0 | 1116001737 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 28 | 100 | 2015-02-09 | 2017-01-29 | 2021-02-04 | 2021-02-04 |  |  | تأخرصرف المستحقات المالية |  | 46.6871 | 24.7025 | Failed | Yes
2100005342 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 23982326.1 | 1199116.305 | 21983399.8 | 21905192.99 | 1010210667 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-11-28 | 2019-07-26 | 2019-12-23 | 2019-12-23 | 2019-07-26 | [5 empty] | منجز | No
2100095034 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 182919435.71 | 9145971.7855 | 50779792.26 | 50779792.26 | 2055002293 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2014-12-14 | 2016-06-06 | 2020-02-12 | 2020-02-12 | 2016-06-06 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال | أخرى | 39.3358 | 22.1552 | منجز | No
2100038861 | وزارة النقل والخدمات اللوجستية / منطقة القصيم | تشييد | ذات اولوية عالية | 66619248.49 | 3330962.4245 | 9244583 | 9244583 | 1010009590 | لا | 0 | 190701034275 | فسخ العقد | الكميات التي تم تركيبها | 13 | 24 | 2019-10-14 | 2021-10-02 | 2021-10-02 | 2021-10-02 |  |  | اخرى |  | 43.9818 | 26.3592 | مسحوب | No
2100077976 | المؤسسة العامة لتحلية المياه المالحة | توريد | ذات اولوية عالية | 1384413021.4 | 69220651.07 | 1297926801.07 | 1297926801.07 | 2050037927 | لا | 0 | 180401002962 | جاري | تكلفة العمل المنجز | 100 | 100 | 2018-09-10 | 2020-09-08 | 2022-09-28 | 2022-09-28 |  |  | تأخرصرف المستحقات المالية |  | 47.0237 | 24.9623 | متأخر | No
2100081152 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1120000 | 56000 | 732516.16 | 0 | 1010171813 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 100 | 2015-02-17 | 2016-05-12 | 2019-09-09 | 2019-09-09 | 2016-05-12 |  | ضعف كفاءة المقاول الفنية |  | 46.1068 | 25.1121 | منجز | Yes
2100091210 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2636600 | 131830 | 963120 | 0 | 1111001945 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 62 | 100 | 2015-02-16 | 2016-08-09 | 2020-08-29 | 2020-08-29 |  |  | ضعف كفاءة المقاول الفنية |  | 46.683 | 24.6988 | Failed | Yes
2100073990 | أمانة / الرياض | دراسة الجدوى | ذات اولوية متوسطة | 22866000 | 1143300 | 3787851 | 0 | 1010348048 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-01-23 | 2020-01-13 | 2021-05-27 | 2021-05-27 | 2020-01-13 |  | اخرى |  |  |  | منجز | Yes
2200231991 | وزارة الحرس الوطني / كلية الملك خالد العسكرية | أخرى | ذات اولوية عالية وعاجلة | 1659191.25 | 82959.5625 | 0 | 0 | 1010308179 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 50 | 50 | 2022-08-29 | 2022-12-01 | 2023-03-01 | 2023-03-01 |  |  |  |  | 46.8907 | 24.7414 | خدمات عامة | No
2200232131 | أمانة / عسير | تشييد | ذات اولوية عالية | 551408 | 27570.4 | 0 | 0 | 5860007938 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 0 | 100 | 2020-11-16 | 2021-12-31 | 2022-03-31 | 2022-03-31 |  |  |  |  | 41.9833 | 18.354 | مسحوب | No
2200232142 | أمانة / عسير | تشييد | ذات اولوية عالية | 5063025.5 | 253151.275 | 1297693.95 | 0 | 5855033218 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 50 | 100 | 2018-12-27 | 2019-12-27 | 2020-06-30 | 2020-06-30 |  |  |  |  | 42.6974 | 18.3215 | مسحوب | Yes
2100018126 | أمانة / تبوك | تشييد | ذات اولوية عالية وعاجلة | 13639611.3 | 681980.565 | 3156996.18 | 3156996.18 | 1010156220 | لا | 0 | 190703166819 | جاري | تكلفة العمل المنجز | 34.24 | 100 | 2018-12-16 | 2020-06-08 | 2023-04-20 | 2023-04-20 |  |  | ضعف كفاءة المقاول الفنية |  | 36.4689 | 26.2366 | Failed | No
2100060830 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية وعاجلة | 40419766.65 | 2020988.3325 | 32897463.97 | 32897463.97 | 1010257755 | لا | 0 | 180201000301 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 72.25 | 100 | 2018-11-21 | 2020-10-30 | 2021-08-31 | 2021-08-31 | 2020-10-30 |  | لا يوجد تأخير |  | 40.469 | 25.9866 | منجز | No
2100019681 | وزارة الصحة / تبوك | توريد وتركيب | ذات اولوية عالية | 979000 | 48950 | 0 | 0 | 3550013161 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 0 | 100 | 2017-12-05 | 2018-06-01 | 2020-02-17 | 2020-02-17 |  |  | ضعف كفاءة المقاول الفنية |  | 36.4411 | 26.2572 | مسحوب | No
2200232201 | أمانة / عسير | تشييد | ذات اولوية عالية | 11144952 | 557247.6 | 0 | 0 | 5864017249 | لا | 0 |  | جاري | تكلفة العمل المنجز | 26 | 100 | 2022-09-01 | 2023-09-30 | 2023-12-31 | 2023-12-31 |  |  |  |  | 42.4987 | 18.217 | Failed | No
2200232164 | أمانة / عسير | تشييد | ذات اولوية عالية | 1046325 | 52316.25 | 293907 | 0 | 5950018887 | لا | 0 |  | جاري | تكلفة العمل المنجز | 33 | 100 | 2021-02-01 | 2022-02-04 | 2023-03-31 | 2023-03-31 |  |  |  |  | 41.9834 | 18.354 | Failed | Yes
2100068563 | أمانة / تبوك | تشييد | ذات اولوية عالية | 2455500 | 122775 | 2455500 | 2455500 | 3552000023 | لا | 0 | 190509083167 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-11-19 | 2019-11-14 | 2019-11-14 | 2019-11-14 | 2019-11-14 |  | ضعف كفاءة المقاول الفنية |  | 35.7243 | 27.3457 | منجز | No
2200232116 | أمانة / عسير | تشييد | ذات اولوية عالية | 10865240 | 543262 | 5701346 | 0 | 5858017263 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 90 | 100 | 2019-01-01 | 2022-01-01 | 2019-06-30 | 2019-06-30 |  |  |  |  | 42.6977 | 18.322 | مسحوب | Yes
2100029481 | أمانة / تبوك | تشييد | ذات اولوية عالية وعاجلة | 5157358.5 | 257867.925 | 4641622.65 | 2578679 | 3552000023 | لا | 0 | 201109038195 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-09-04 | 2020-08-29 | 2021-03-02 | 2021-03-02 | 2020-08-29 |  | ضعف كفاءة المقاول الفنية |  | 36.558 | 28.3886 | منجز | No
2100042825 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية وعاجلة | 36640601.5 | 1832030.075 | 31484137.07 | 31484137.07 | 1132002394 | لا | 0 | 181109287519 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 98.28 | 100 | 2013-04-27 | 2015-04-06 | 2020-12-14 | 2020-12-14 | 2015-04-06 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.3541 | 26.688 | منجز | No
2100047176 | أمانة / تبوك | تشييد | لم تعد تحتاجها الجهة | 985200 | 49260 | 697880 | 697880 | 1010262187 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 70 | 100 | 2011-11-25 | 2012-11-26 | 2020-10-31 | 2020-10-31 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5876 | 28.4236 | مسحوب | No
2100042556 | رئاسة أمن الدولة / قوات الأمن الخاصة | تشييد | ذات اولوية عالية وعاجلة | 18045391.35 | 902269.5675 | 16240359.33 | 16240359.33 | 1010045581 | لا | 0 | 191201147163 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 95 | 100 | 2020-01-30 | 2022-01-09 | 2022-09-22 | 2022-09-22 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 46.567 | 24.8767 | متأخر | No
2200232120 | أمانة / عسير | تشييد | ذات اولوية عالية | 1589889 | 79494.45 | 1256771 | 1256771 | 5855255120 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 90 | 100 | 2020-11-18 | 2021-11-18 | 2022-03-31 | 2022-03-31 |  |  |  |  | 42.6974 | 18.3215 | مسحوب | No
2100064396 | أمانة / تبوك | تشييد | لم تعد تحتاجها الجهة | 1398000 | 69900 | 1258200 | 1258200 | 4650060073 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-05-23 | 2019-12-30 | 2017-05-23 | 2017-05-23 | 2019-12-30 |  | اخرى |  | 36.5862 | 28.3808 | منجز | No
2100100424 | هيئة المدن الصناعية ومناطق التقنية | إشراف | ذات اولوية عالية | 97135625 | 4856781.25 | 42141100 | 42141100 | 1010213041 | لا | 0 |  | جاري | التكلفة المفوترة | 44 | 44 | 2018-01-01 | 2022-12-31 | 2023-12-31 | 2023-12-31 |  |  | لا يوجد تأخير |  | 38.7183 | 31.6101 | خدمات عامة | No
2100025314 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 370461 | 18523.05 | 128800 | 128800 | 3357011803 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 50 | 100 | 2015-10-13 | 2016-06-09 | 2020-09-20 | 2020-09-20 |  |  | ضعف كفاءة المقاول الفنية |  | 36.6024 | 28.3965 | مسحوب | No
2100104086 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2158286 | 107914.3 | 0 | 0 | 1010246941 | لا | 0 |  | مسحوب | التكلفة المفوترة | 1 | 100 | 2011-10-03 | 2013-01-03 | 2013-03-15 | 2013-03-15 |  |  | ضعف كفاءة المقاول الفنية |  | 44.4412 | 24.5406 | مسحوب | No
2100089552 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 5219566.35 | 260978.3175 | 3236242.14 | 3236242.14 | 1010089371 | لا | 0 |  | مسحوب | التكلفة المفوترة | 74 | 100 | 2015-01-12 | 2016-09-03 | 2022-06-15 | 2022-06-15 |  |  | ضعف كفاءة المقاول الفنية |  | 40.8817 | 23.5031 | مسحوب | No
2100011981 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 10765167 | 538258.35 | 7209094 | 6597264 | 1010168033 | لا | 0 | 190709144502 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-08-07 | 2016-07-27 | 2022-02-16 | 2022-02-16 | 2016-07-27 |  | ضعف كفاءة المقاول الفنية |  | 41.0859 | 19.1571 | منجز | No
2100101301 | جامعة جدة | تشييد | ذات اولوية متوسطة | 24120227 | 1206011.35 | 9366311 | 9366311 | 4031052995 | لا | 0 | 190301052669 | جاري | تكلفة العمل المنجز | 82 | 100 | 2017-10-02 | 2021-04-29 | 2021-09-23 | 2021-09-23 |  |  | أوامر تغيير |  | 21.8911 | 39.2563 | Failed | No
2100057411 | شركة المياه الوطنية / منطقة تبوك | إشراف | ذات اولوية منخفضة | 8567100 | 428355 | 0 | 0 | 1010320035 | لا | 0 | 180809049889 | لم يبدأ | التكلفة المفوترة | 0 | 0 | 2017-12-01 | 2020-12-01 | 2020-12-01 | 2020-12-01 |  |  | لا يوجد تأخير |  | 35.8021 | 27.3396 | Failed | No
2100108172 | وزارة الداخلية / ديوان وزارة الداخلية | تصميم وتشييد | ذات اولوية عالية وعاجلة | 479895621.91 | 23994781.0955 | 389084473.06 | 389084473.06 | 1010199246 | لا | 0 | 180909071976 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99.98 | 100 | 2015-05-13 | 2017-10-28 | 2022-01-30 | 2022-01-30 | 2017-10-28 |  | تأخرصرف المستحقات المالية | تم تمديد الجدول الزمني | 43.0426 | 17.1849 | منجز | No
2200232330 | أمانة / المنطقة الشرقية | ترميم | ذات اولوية منخفضة | 9945775 | 497288.75 | 9945775 | 0 | 2050018628 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 87 | 100 | 2021-01-24 | 2022-01-24 | 2022-01-24 | 2022-01-24 | 2022-01-24 |  |  |  | 50.0888 | 26.4207 | منجز | Yes
2100027543 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 249900 | 12495 | 224910 | 224910 | 3351010628 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2020-01-12 | 2020-10-04 | 2020-10-05 | 2020-10-05 | 2020-10-04 |  |  |  | 36.5274 | 27.4158 | منجز | No
2100098431 | وزارة الداخلية / ديوان وزارة الداخلية | تصميم وتشييد | ذات اولوية عالية وعاجلة | 2459091753.6 | 122954587.68 | 1927743154.76 | 1903416364.67 | 1010199246 | لا | 0 | 180909071976 | جاري | منهجية القيمة المكتسبة | 93.51 | 100 | 2015-07-07 | 2017-12-22 | 2023-05-04 | 2023-05-04 |  |  | تأخرصرف المستحقات المالية | تم تمديد الجدول الزمني | 42.9446 | 17.0501 | متأخر | No
2100102303 | وزارة الدفاع / الإدارة الهندسية والاشغال بقوات الدفاع الجوي | تشييد | ذات اولوية متوسطة | 18746740.95 | 937337.0475 | 18746740.95 | 16870486.13 | 1010028451 | لا | 0 | 190101001135 | جاري | الكميات التي تم تركيبها | 96 | 100 | 2019-06-15 | 2021-06-05 | 2022-07-13 | 2022-07-13 |  |  | أوامر سامية |  | 39.1997 | 21.5157 | Failed | No
2100061574 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 19909209.39 | 995460.4695 | 13863348.44 | 8736085.1 | 1115001461 | لا | 0 | 181109358267 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-04-07 | 2016-03-07 | 2021-09-30 | 2021-09-30 | 2016-03-07 |  | تأخرصرف المستحقات المالية |  | 46.7825 | 24.7151 | منجز | No
2100007512 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 10326114 | 516305.7 | 10326114 | 10326114 | 1010026934 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 77.45 | 100 | 2018-12-30 | 2020-12-31 | 2020-07-18 | 2020-07-18 | 2020-12-31 |  | لا يوجد تأخير |  | 40.4737 | 21.4664 | منجز | No
2100010673 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2744958.84 | 137247.942 | 293047 | 293047 | 1186001400 | لا | 0 |  | جاري | التكلفة المفوترة | 15 | 100 | 2017-05-15 | 2018-11-06 | 2022-01-22 | 2022-01-22 |  |  | ضعف كفاءة المقاول الفنية |  | 44.4412 | 24.5406 | Failed | No
2100051122 | أمانة / تبوك | تشييد | ذات اولوية منخفضة | 1822000 | 91100 | 635440 | 635440 | 4700010229 | لا | 0 | 190301026163 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-01-27 | 2020-01-22 | 2021-01-08 | 2021-01-08 | 2020-01-22 |  | ضعف كفاءة المقاول الفنية |  | 37.2633 | 25.0313 | منجز | No
2100103095 | شركة المياه الوطنية / منطقة الرياض | إشراف | ذات اولوية عالية | 3456000 | 172800 | 3454865.16 | 3454865.16 | 4031072810 | لا | 0 | 190601080903 | منجز – استلام نهائي | تكلفة العمل المنجز | 99.95 | 99.95 | 2019-07-16 | 2020-07-16 | 2020-07-16 | 2020-07-16 |  | 2020-07-16 | لا يوجد تأخير |  | 46.8787 | 23.5328 | منجز | No
2100033563 | أمانة / تبوك | دراسات هندسية | ذات اولوية عالية وعاجلة | 3698100 | 184905 | 1615026 | 1615026 | 1010286187 | لا | 0 | 200409078713 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-11-10 | 2021-08-02 | 2022-02-02 | 2022-02-02 | 2021-08-02 |  | التنسيق مع أصحاب المصلحه (خدمات |  |  |  | منجز | No
2100104005 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية منخفضة | 4016979.4 | 200848.97 | 2576129.66 | 2576129.66 | 4032033034 | لا | 0 | 180909072811 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 80.5 | 100 | 2013-05-05 | 2014-10-19 | 2021-06-14 | 2021-06-14 | 2014-10-19 |  | ضعف كفاءة المقاول الفنية |  | 36.5902 | 28.381 | منجز | No
2100035711 | أمانة / تبوك | تشييد | ذات اولوية عالية | 568343 | 28417.15 | 568343 | 568343 | 1131015427 | لا | 0 | 190409035833 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-10-30 | 2019-10-19 | 2019-09-16 | 2019-09-16 | 2019-10-19 |  | اخرى |  | 38.5426 | 27.5871 | منجز | No
2100027856 | أمانة / تبوك | تشييد | ذات اولوية عالية | 3806516.7 | 190325.835 | 1330404 | 1330404 | 3553000167 | لا | 0 |  | جاري | تكلفة العمل المنجز | 36 | 40 | 2019-05-02 | 2021-03-25 | 2023-05-01 | 2023-05-01 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5617 | 28.3964 | منتظم | No
2100103552 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 10087861.4 | 504393.07 | 5958811.68 | 5958811.68 | 1010046644 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2013-09-27 | 2015-09-18 | 2020-08-11 | 2020-08-11 | 2015-09-18 |  | ضعف كفاءة المقاول الفنية |  | 40.4511 | 21.2747 | منجز | No
2100107074 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2091116.64 | 104555.832 | 1777449.14 | 1777449.14 | 1010249051 | لا | 0 |  | جاري الاستلام الإبتدائي | التكلفة المفوترة | 95 | 100 | 2020-06-01 | 2020-11-22 | 2022-02-17 | 2022-02-17 |  |  | اخرى |  | 45.2591 | 25.2379 | Failed | No
2100048182 | وزارة الداخلية / ديوان وزارة الداخلية | تصميم وتشييد | ذات اولوية عالية وعاجلة | 703626484.14 | 35181324.207 | 416457714.86 | 416457714.86 | 1010254468 | لا | 0 | 180809053588 | جاري | منهجية القيمة المكتسبة | 68.89 | 100 | 2015-05-19 | 2017-03-11 | 2023-08-02 | 2023-08-02 |  |  | تأخرصرف المستحقات المالية | تم تمديد الجدول الزمني | 51.4808 | 24.2988 | Failed | No
2100048532 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية | 64898532.7 | 3244926.635 | 50916097.25 | 47208979.92 | 1010108054 | لا | 0 | 180709019742 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-02-09 | 2017-04-19 | 2022-01-12 | 2022-01-12 | 2017-04-19 |  | لا يوجد تأخير |  | 45.3738 | 24.1064 | منجز | No
2100019316 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1088827 | 54441.35 | 591270 | 591270 | 1118000760 | لا | 0 |  | جاري | التكلفة المفوترة | 25 | 25 | 2019-09-12 | 2020-09-06 | 2022-12-31 | 2022-12-31 |  |  |  |  | 42.9095 | 23.8972 | منتظم | No
2100017264 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 2137500 | 106875 | 1258750 | 1258750 | 3350000631 | لا | 0 | 181201470281 | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 92 | 100 | 2018-10-24 | 2019-10-19 | 2022-10-31 | 2022-10-31 |  |  | ضعف كفاءة المقاول الفنية | أخرى | 41.7348 | 27.5046 | متأخر | No
2100039620 | وكالة / الإسكان | تشييد | ذات اولوية متوسطة | 228879941 | 11443997.05 | 62454918.4 | 62454918.4 | 1128000011 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 91 | 95 | 2019-12-11 | 2021-06-03 | 2023-12-31 | 2023-12-31 |  |  | التنسيق مع أصحاب المصلحه (خدمات | أخرى |  |  | متأخر | No
2200232385 | أمانة / المنطقة الشرقية | الخدمات الاستشارية | ذات اولوية متوسطة | 1975470 | 98773.5 | 472305 | 157435 | 1010326466 | لا | 0 |  | جاري | التكلفة المفوترة | 24 | 30 | 2022-09-20 | 2023-09-20 | 2023-09-20 | 2023-09-20 |  |  |  |  | 50.0888 | 26.4207 | خدمات عامة | No
2100063291 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 1140000 | 57000 | 0 | 0 | 3550036848 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 100 | 100 | 2015-11-25 | 2016-08-14 | 2021-08-16 | 2021-08-16 |  |  | ضعف كفاءة المقاول الفنية |  | 37.2651 | 25.05 | مسحوب | No
2100084722 | شركة الكهرباء | تشييد | ذات اولوية متوسطة | 397817797 | 19890889.85 | 356082646 | 356082646 | 1010090181 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2015-12-27 | 2018-05-27 | 2022-06-21 | 2022-06-21 | 2018-05-27 |  | لا يوجد تأخير |  | 39.7554 | 21.3687 | منجز | No
2100057013 | شركة المياه الوطنية / منطقة حائل | إشراف | لم تعد تحتاجها الجهة | 10236000 | 511800 | 15775062.15 | 15767429.89 | 1010314421 | لا | 0 | 180809053279 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2011-09-03 | 2014-09-03 | 2021-01-10 | 2021-01-10 | 2014-09-03 |  | لا يوجد تأخير |  | 41.7357 | 27.4936 | منجز | No
2100089633 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 41734299 | 2086714.95 | 41009393.16 | 37560663.01 | 2050005846 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-06-19 | 2020-06-19 | 2022-05-31 | 2022-05-31 | 2020-06-19 |  | لا يوجد تأخير |  | 39.7767 | 21.396 | منجز | No
2100090650 | أمانة / تبوك | تشييد | ذات اولوية عالية وعاجلة | 24853377 | 1242668.85 | 5535696 | 5535696 | 1010188619 | لا | 0 | 180901081227 | جاري | تكلفة العمل المنجز | 55 | 85 | 2019-03-30 | 2023-01-01 | 2024-01-01 | 2024-01-01 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5482 | 28.3939 | Failed | No
2100044402 | أمانة / تبوك | تشييد | ذات اولوية عالية | 11399287.5 | 569964.375 | 5740955 | 5740955 | 4700000126 | لا | 0 | 180909106442 | جاري | الكميات التي تم تركيبها | 75 | 100 | 2015-04-16 | 2016-10-07 | 2023-08-08 | 2023-08-08 |  |  | ضعف كفاءة المقاول الفنية |  | 37.2651 | 25.05 | Failed | No
2100023822 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية | 43582317.01 | 2179115.8505 | 27970619.36 | 27970619.36 | 1010047800 | لا | 0 | 180709018797 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2013-10-27 | 2015-10-17 | 2021-11-01 | 2021-11-01 | 2015-10-17 |  | تأخرصرف المستحقات المالية |  | 42.6457 | 17.209 | منجز | No
2100072936 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 64658190 | 3232909.5 | 28543350 | 23264750 | 1123000085 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 60.1 | 78.8 | 2019-01-16 | 2021-01-04 | 2023-03-31 | 2023-03-31 |  |  | اخرى |  | 45.9148 | 25.524 | متأخر | No
2100033143 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 5571450 | 278572.5 | 5107328.26 | 0 | 1116003362 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 100 | 2014-04-23 | 2016-08-13 | 2016-08-14 | 2016-08-14 | 2016-08-13 |  |  |  | 43.6945 | 24.6723 | منجز | Yes
2100093100 | أمانة / تبوك | تشييد | ذات اولوية عالية | 9278560 | 463928 | 5984671 | 3061925 | 1010366443 | لا | 0 | 19090914453 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 79 | 100 | 2019-06-26 | 2020-12-17 | 2021-09-01 | 2021-09-01 | 2020-12-17 |  | ضعف كفاءة المقاول الفنية |  | 38.5466 | 27.6109 | منجز | No
2100086752 | وزارة التعليم | تشييد | لم تعد تحتاجها الجهة | 2441051 | 122052.55 | 0 | 0 | 5857020213 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0 | 100 | 2010-10-01 | 2011-12-25 | 2021-11-10 | 2021-11-10 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 43.1379 | 18.0853 | مسحوب | No
2100103843 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية عالية وعاجلة | 27797960.47 | 1389898.0235 | 14934967.7 | 14934967.7 | 4030039641 | لا | 0 | 200309015319 | ايقاف جزئي | تكلفة العمل المنجز | 99 | 100 | 2018-01-28 | 2019-09-10 | 2022-07-29 | 2022-07-29 |  |  | تصاريح أعمال التنفيذ |  | 41.6721 | 18.003 | Failed | No
2100038673 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 213510423 | 10675521.15 | 157474560.53 | 157474560.53 | 1010090968 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 97.5 | 100 | 2018-05-01 | 2020-04-30 | 2022-03-31 | 2022-03-31 | 2020-04-30 |  | أوامر تغيير |  | 39.7754 | 21.5617 | منجز | No
2100032874 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3596720 | 179836 | 2468320 | 0 | 1010064540 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 99 | 100 | 2015-01-20 | 2016-04-14 | 2019-12-23 | 2019-12-23 | 2016-04-14 |  | ضعف كفاءة المقاول الفنية |  | 46.6823 | 24.7119 | منجز | Yes
2100066146 | وزارة التعليم | تشييد | ذات اولوية عالية | 2185045 | 109252.25 | 1039330 | 1039330 | 9501001865 | لا | 0 |  | مسحوب | التكلفة المفوترة | 48 | 100 | 2008-12-25 | 2009-12-19 | 2022-05-26 | 2022-05-26 |  |  | ضعف كفاءة المقاول الفنية |  | 42.6509 | 17.1567 | مسحوب | No
2100081185 | أمانة / تبوك | تشييد | ذات اولوية عالية | 2557458.75 | 127872.9375 | 345256 | 345256 | 7007970507 | لا | 652850 | 200601008855 | فسخ العقد | الكميات التي تم تركيبها | 14 | 14 | 2020-01-07 | 2020-12-31 | 2020-12-31 | 2020-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5254 | 28.4076 | مسحوب | No
2100007151 | شركة المياه الوطنية / منطقة الرياض | إشراف | ذات اولوية عالية وعاجلة | 2187850 | 109392.5 | 1005117.71 | 1005117.71 | 1010326770 | لا | 0 | 190501056663 | جاري | التكلفة المفوترة | 62.04 | 62.04 | 2019-07-21 | 2023-07-22 | 2023-07-22 | 2023-07-22 |  |  | لا يوجد تأخير |  | 45.3815 | 25.3551 | خدمات عامة | No
2100007044 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1278100 | 63905 | 589400 | 589400 | 3851217786 | لا | 0 |  | مسحوب | التكلفة المفوترة | 74 | 100 | 2009-10-26 | 2010-05-30 | 2011-12-06 | 2011-12-06 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0165 | 30.9619 | مسحوب | No
2100083252 | أمانة / تبوك | تشييد | ذات اولوية عالية وعاجلة | 9932606 | 496630.3 | 9932606 | 8724447.42 | 3450009076 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-08-16 | 2014-08-11 | 2019-03-17 | 2019-03-17 | 2014-08-11 |  | ضعف كفاءة المقاول الفنية |  | 36.5693 | 28.461 | منجز | No
2100097090 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 3077350 | 153867.5 | 1563787.93 | 1563787.93 | 1010224137 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 92.09 | 100 | 2020-03-09 | 2021-07-09 | 2022-04-30 | 2022-04-30 |  |  | لا يوجد تأخير |  | 46.8228 | 24.6509 | Failed | No
2100023531 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 2000000 | 100000 | 0 | 0 | 3550016111 | نعم | 1 |  | مسحوب | الكميات التي تم تركيبها | 0 | 100 | 2014-12-26 | 2015-12-21 | 2022-06-01 | 2022-06-01 |  |  | اخرى |  | 36.4689 | 26.2366 | مسحوب | No
2100046605 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1899200 | 94960 | 810868.55 | 0 | 1014000081 | لا | 0 | 5040240 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-11-07 | 2015-11-02 | 2019-10-10 | 2019-10-10 | 2015-11-02 |  | ضعف كفاءة المقاول الفنية |  | 46.6775 | 24.6938 | منجز | Yes
2100075563 | أمانة / تبوك | تشييد | ذات اولوية عالية | 2391165 | 119558.25 | 489038 | 489038 | 3350017280 | لا | 0 | 200501038064 | جاري | تكلفة العمل المنجز | 85 | 84 | 2019-12-01 | 2020-11-19 | 2023-03-08 | 2023-03-08 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5045 | 27.3971 | منتظم | No
2100041635 | شركة المياه الوطنية / منطقة الرياض | إشراف | ذات اولوية عالية | 13200000 | 660000 | 12495595.34 | 12495595.34 | 1010426678 | لا | 0 | 180909079925 | منجز – استلام نهائي | التكلفة المفوترة | 94.67 | 98.41 | 2018-04-17 | 2021-04-17 | 2022-05-20 | 2022-05-20 |  | 2021-04-17 | لا يوجد تأخير |  | 45.2545 | 25.2353 | منجز | No
2100032465 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1360146 | 68007.3 | 734290.736 | 0 | 1010225108 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 83 | 100 | 2014-10-21 | 2015-10-06 | 2019-12-18 | 2019-12-18 | 2015-10-06 |  | ضعف كفاءة المقاول الفنية |  | 45.4659 | 25.1056 | منجز | Yes
2100051903 | أمانة / الجوف | تشييد | ذات اولوية عالية | 5395478.4 | 269773.92 | 4251492.4 | 4251492.4 | 1010106885 | لا | 0 | 190309089091 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 83.5 | 100 | 2015-04-01 | 2017-03-10 | 2017-03-10 | 2017-03-10 | 2017-03-10 |  | ضعف كفاءة المقاول الفنية |  | 37.3604 | 31.3298 | منجز | No
2100008621 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 6744546.45 | 337227.3225 | 2887276.53 | 2887276.53 | 1010046644 | لا | 0 |  | مسحوب | التكلفة المفوترة | 42.81 | 100 | 2013-06-11 | 2015-08-30 | 2022-08-10 | 2022-08-10 |  |  | ضعف كفاءة المقاول الفنية |  | 40.4511 | 21.2747 | مسحوب | No
2100098851 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 9354203 | 467710.15 | 5267222.84 | 4076477 | 1010196220 | لا | 0 | 190309000324 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2012-12-17 | 2014-12-07 | 2021-08-11 | 2021-08-11 | 2014-12-07 |  | ضعف كفاءة المقاول الفنية |  | 41.0859 | 19.1571 | منجز | No
2100104252 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 1294560 | 64728 | 0 | 0 | 5865028202 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0 | 100 | 2010-02-13 | 2010-12-06 | 2023-02-02 | 2023-02-02 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.0529 | 18.5228 | مسحوب | No
2100086170 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2007577.05 | 100378.8525 | 0 | 0 | 1010188602 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0 | 100 | 2005-11-28 | 2006-10-13 | 2023-03-22 | 2023-03-22 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.5429 | 16.8808 | مسحوب | No
2100005552 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية متوسطة | 23596274.9 | 1179813.745 | 23523000.98 | 23523000.98 | 1010210389 | لا | 0 | 180909079647 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-03-21 | 2020-02-28 | 2019-12-22 | 2019-12-22 |  | 2020-02-28 | لا يوجد تأخير |  | 42.6031 | 20.0028 | منجز | No
2100096865 | شركة المياه الوطنية / منطقة الرياض | إشراف | ذات اولوية عالية | 12049200 | 602460 | 9958010.34 | 9156345.14 | 1010326770 | لا | 0 | 180201000290 | جاري | التكلفة المفوترة | 85.23 | 85.23 | 2019-11-24 | 2022-11-25 | 2022-11-25 | 2022-11-25 |  |  | لا يوجد تأخير |  | 45.3721 | 25.9179 | خدمات عامة | No
2100081163 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1427681.5 | 71384.075 | 1067300 | 0 | 1117002453 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 100 | 2014-08-31 | 2015-11-24 | 2016-12-19 | 2016-12-19 | 2015-11-24 |  |  |  | 46.6896 | 24.694 | منجز | Yes
2100008702 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 612025 | 30601.25 | 523440 | 0 | 1115001965 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 38 | 2019-02-12 | 2020-02-07 | 2019-10-29 | 2019-10-29 | 2020-02-07 |  |  |  | 47.2302 | 24.1597 | منجز | Yes
2100194526 | أمانة / جدة | تشييد | ذات اولوية عالية وعاجلة | 64383199 | 3219159.95 | 57979924.62 | 57979924.62 | 4030034104 | لا | 0 | 191001144343 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-06-21 | 2021-12-04 | 2022-12-03 | 2022-12-03 |  |  |  |  | 39.1637 | 21.7736 | منتظم | No
2100007280 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 4348402.15 | 217420.1075 | 2918353.03 | 2252054.37 | 5900009012 | لا | 0 | 190609040386 | منجز – استلام ابتدائي | التكلفة المفوترة | 95 | 100 | 2016-06-06 | 2017-07-31 | 2022-12-22 | 2022-12-22 | 2017-07-31 |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | منجز | No
2100060793 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية وعاجلة | 4165216.65 | 208260.8325 | 3796887.6 | 3796887.6 | 2050003475 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 96.45 | 100 | 2019-06-08 | 2020-06-08 | 2020-07-23 | 2020-07-23 |  | 2020-06-08 | لا يوجد تأخير |  | 50.0802 | 26.5703 | منجز | No
2100013020 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2137800 | 106890 | 2102800 | 0 | 1010258653 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 98.36 | 100 | 2014-11-05 | 2016-01-29 | 2021-06-16 | 2021-06-16 | 2016-01-29 |  | ضعف كفاءة المقاول الفنية |  | 45.3511 | 25.958 | منجز | Yes
2100066975 | أمانة / جدة | تشييد | ذات اولوية عالية وعاجلة | 32882955 | 1644147.75 | 32882947 | 32882947 | 1010044185 | لا | 0 | 190709094246 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-06-16 | 2020-04-06 | 2020-09-22 | 2020-09-22 | 2020-04-06 |  | التنسيق مع أصحاب المصلحه (خدمات |  | 39.2102 | 21.4902 | منجز | No
2100107553 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البرية | تشييد | ذات اولوية متوسطة | 4985589 | 249279.45 | 4985589 | 0 | 3550024970 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-01-09 | 2020-10-30 | 2021-06-25 | 2021-06-25 | 2020-10-30 |  | تأخرصرف المستحقات المالية |  | 36.5245 | 28.3829 | منجز | Yes
2100071024 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 60285997 | 3014299.85 | 32652331 | 32652331 | 1010247052 | لا | 0 | 181009188197 | فسخ العقد | الكميات التي تم تركيبها | 58.3 | 88 | 2012-09-19 | 2018-09-20 | 2018-09-20 | 2018-09-20 |  |  | اخرى |  | 42.6337 | 18.1804 | مسحوب | No
2100085971 | وزارة التعليم | تشييد | ذات اولوية عالية | 5758921.9 | 287946.095 | 3432695.14 | 3432695.14 | 1010046644 | لا | 0 |  | مسحوب | التكلفة المفوترة | 59.61 | 100 | 2013-05-01 | 2015-01-21 | 2020-10-08 | 2020-10-08 |  |  | ضعف كفاءة المقاول الفنية |  | 40.4511 | 21.2747 | مسحوب | No
2200232772 | أمانة / المنطقة الشرقية | تصميم وتشييد | ذات اولوية متوسطة | 125304000 | 6265200 | 699775 | 0 | 2050018628 | لا | 0 |  | لم يبدأ | التكلفة المفوترة | 1 | 19 |  | 2024-08-02 |  | 2024-07-04 |  |  |  | أخرى | 50.081 | 26.3801 | متأخر | Yes
2100089460 | وزارة الداخلية / ديوان وزارة الداخلية | تصميم وتشييد | ذات اولوية عالية وعاجلة | 315990196.33 | 15799509.8165 | 252246517.41 | 252246517.41 | 1010254468 | لا | 0 | 180809053561 | جاري | منهجية القيمة المكتسبة | 92.2 | 100 | 2016-01-06 | 2018-11-17 | 2023-01-12 | 2023-01-12 |  |  | تأخرصرف المستحقات المالية | أخرى | 42.6405 | 18.3114 | متأخر | No
2100012423 | أمانة / الرياض | تشييد | ذات اولوية عالية | 2303741 | 115187.05 | 1671790 | 0 | 1010197808 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-05-03 | 2017-04-22 | 2017-04-22 | 2017-04-22 | 2017-04-22 |  | ضعف كفاءة المقاول الفنية |  | 46.7135 | 24.7185 | منجز | Yes
2200232890 | أمانة / المنطقة الشرقية | تصميم وتشييد | ذات اولوية متوسطة | 8394270 | 419713.5 | 8898598 | 8898598 | 2050018628 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2020-05-03 | 2021-11-02 | 2022-03-12 | 2022-03-12 | 2021-11-02 |  |  |  | 50.0888 | 26.4207 | منجز | No
2100106514 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 4515701 | 225785.05 | 459655.25 | 0 | 5859001022 | لا | 0 | 201101422318 | جاري | التكلفة المفوترة | 70 | 100 | 2019-11-17 | 2021-03-11 | 2023-02-15 | 2023-02-15 |  |  | ضعف كفاءة المقاول الفنية |  | 42.1351 | 19.1255 | Failed | Yes
2100010010 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2396500 | 119825 | 41760 | 0 | 1116007586 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 0 | 100 | 2014-09-03 | 2015-11-27 | 2020-11-09 | 2020-11-09 |  |  | تأخرصرف المستحقات المالية |  | 46.6768 | 24.7169 | Failed | Yes
2200232761 | أمانة / المنطقة الشرقية | تصميم وإشراف | ذات اولوية عالية | 8362800 | 418140 | 696900 | 696900 | 1010419186 | لا | 0 |  | جاري | التكلفة المفوترة | 8 | 18 | 2022-09-01 | 2024-08-31 | 2024-08-31 | 2024-08-31 |  |  |  |  | 50.0888 | 26.4207 | متأخر | No
2100071120 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البرية | تشييد | ذات اولوية متوسطة | 1839172 | 91958.6 | 1839172 | 0 | 1010294276 | نعم | 232824.37 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2022-06-06 | 2022-07-06 | 2022-07-06 | 2022-07-06 | 2022-07-06 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 50.1091 | 26.4374 | منجز | Yes
2100099750 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية عالية | 34818593 | 1740929.65 | 34816645 | 34816645 | 5850031989 | لا | 0 | 180701034976 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-09-11 | 2020-02-25 | 2020-02-20 | 2020-02-20 |  | 2020-02-25 | لا يوجد تأخير |  | 43.1379 | 18.0853 | منجز | No
2200232945 | أمانة / المنطقة الشرقية | تصميم وتشييد | ذات اولوية متوسطة | 2891727 | 144586.35 | 2895594 | 2895594 | 2051038453 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 87 | 100 | 2020-08-09 | 2021-07-29 | 2021-09-02 | 2021-09-02 | 2021-07-29 |  |  |  | 50.1971 | 26.2172 | منجز | No
2100057831 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2892835 | 144641.75 | 1866000 | 0 | 1111001945 | لا | 0 |  | جاري | تكلفة العمل المنجز | 86 | 100 | 2014-09-18 | 2015-12-12 | 2016-07-11 | 2016-07-11 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6713 | 24.7144 | Failed | Yes
2100107774 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 4985600 | 249280 | 4985600 | 4985600 | 2055002705 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2018-10-13 | 2019-10-13 | 2019-12-13 | 2019-12-13 | 2019-10-13 |  | لا يوجد تأخير |  |  |  | منجز | No
2100106175 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | تشييد | ذات اولوية عالية | 123111199.08 | 6155559.954 | 89487691.51 | 83.1821 | 1010147053 | لا | 0 | 180909082428 | ايقاف كلي | تكلفة العمل المنجز | 76 | 100 | 2014-10-24 | 2022-08-11 | 2024-01-04 | 2024-01-04 |  |  | تأخرصرف المستحقات المالية |  | 39.1677 | 21.5008 | Failed | No
2200232934 | أمانة / المنطقة الشرقية | تصميم وتشييد | ذات اولوية متوسطة | 28222468 | 1411123.4 | 25400199 | 25400199 | 2060016650 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 94 | 100 | 2020-10-19 | 2022-04-20 | 2022-04-20 | 2022-04-20 | 2022-04-20 |  |  |  | 50.1971 | 26.2172 | منجز | No
2200232820 | أمانة / المنطقة الشرقية | تصميم وتشييد | ذات اولوية متوسطة | 8802761 | 440138.05 | 8802760 | 8802760 | 2050018628 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2020-05-03 | 2021-11-02 | 2022-01-31 | 2022-01-31 | 2021-11-02 |  |  |  | 50.0888 | 26.4207 | منجز | No
2100101780 | وزارة الموارد البشرية والتنمية الإجتماعية | إشراف | ذات اولوية منخفضة | 3320000 | 166000 | 6199696.77 | 6199696.77 | 1010322156 | لا | 0 | 190401116462 | مسحوب | الكميات التي تم تركيبها | 88 | 100 | 2012-05-22 | 2015-04-19 | 2022-02-04 | 2022-02-04 |  |  | ضعف كفاءة المقاول الفنية |  | 43.9667 | 26.3516 | مسحوب | No
2200232816 | أمانة / المنطقة الشرقية | دراسات هندسية | ذات اولوية متوسطة | 2367750 | 118387.5 | 2012587 | 2012587 | 1010464778 | لا | 0 |  | ايقاف جزئي | التكلفة المفوترة | 85 | 100 | 2020-07-12 | 2021-02-22 | 2021-02-22 | 2021-02-22 |  |  |  | أخرى | 50.0888 | 26.4207 | Failed | No
2200233096 | أمانة / عسير | تشييد | ذات اولوية عالية وعاجلة | 3994046 | 199702.3 | 0 | 0 | 5855039650 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 60 | 100 | 2015-01-17 | 2016-01-17 | 2016-01-17 | 2016-01-17 |  |  |  |  | 42.2982 | 19.9856 | مسحوب | No
2100016041 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2795275 | 139763.75 | 0 | 0 | 4031059792 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0 | 100 | 2018-06-25 | 2019-12-17 | 2023-09-13 | 2023-09-13 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.6509 | 17.1567 | مسحوب | No
2100000825 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية | 22980578 | 1149028.9 | 21521633.45 | 21521633.45 | 4650015928 | لا | 0 | 180809065484 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 99.5 | 2016-10-05 | 2019-09-03 | 2020-10-01 | 2020-10-01 | 2019-09-03 |  | لا يوجد تأخير |  | 37.8719 | 25.6315 | منجز | No
2200233181 | وزارة الداخلية / المديرية العامة لحرس الحدود | تشييد | ذات اولوية عالية | 2561625 | 128081.25 | 0 | 0 | 1010307343 | لا | 0 |  | جاري | تكلفة العمل المنجز | 1 | 38 | 2022-09-28 | 2023-06-28 | 2023-06-28 | 2023-06-28 |  |  |  |  | 36.5662 | 28.3835 | Failed | No
2200233170 | وزارة الداخلية / المديرية العامة لحرس الحدود | توريد وتركيب | ذات اولوية عالية | 228850 | 11442.5 | 0 | 0 | 1010202409 | لا | 0 |  | جاري الاستلام الإبتدائي | التكلفة المفوترة | 90 | 100 | 2022-09-15 | 2022-11-15 | 2022-11-15 | 2022-11-15 |  |  |  |  | 42.5363 | 17.374 | Failed | No
2200233166 | وزارة الداخلية / المديرية العامة لحرس الحدود | توريد وتركيب | ذات اولوية عالية | 524055 | 26202.75 | 0 | 0 | 1010059590 | لا | 0 |  | جاري | تكلفة العمل المنجز | 10 | 78 | 2022-08-17 | 2023-02-17 | 2023-02-17 | 2023-02-17 |  |  |  |  | 50.0718 | 26.4574 | Failed | No
2200233214 | جامعة الملك خالد | تشييد | ذات اولوية عالية وعاجلة | 36588717 | 1829435.85 | 31749203.1 | 29576302.75 | 1010074952 | لا | 0 | 181009152160 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2017-05-11 | 2018-11-01 | 2022-10-05 | 2022-10-05 |  |  |  |  | 42.7198 | 18.0953 | منتظم | No
2200233203 | وزارة الداخلية / المديرية العامة لحرس الحدود | ترميم | ذات اولوية عالية | 2081672.5 | 104083.625 | 496518.25 | 496518.25 | 5907036516 | لا | 0 |  | جاري | تكلفة العمل المنجز | 45 | 50 | 2022-08-10 | 2023-06-10 | 2023-06-10 | 2023-06-10 |  |  |  |  | 42.5706 | 16.8894 | منتظم | No
2100042641 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 3398924.51 | 169946.2255 | 1.01 | 0.01 | 1010238171 | لا | 0 |  | جاري | التكلفة المفوترة | 5 | 100 | 2017-12-27 | 2019-03-22 | 2019-03-22 | 2019-03-22 |  |  | ضعف كفاءة المقاول الفنية |  | 44.2341 | 17.5757 | Failed | No
2200233225 | جامعة الملك خالد | تشييد | ذات اولوية عالية وعاجلة | 153075198.92 | 7653759.946 | 137562260.85 | 116765084.97 | 1010219886 | لا | 0 | 190401107517 | جاري | تكلفة العمل المنجز | 95.09 | 95.09 | 2019-05-26 | 2021-05-15 | 2023-02-25 | 2023-02-25 |  |  |  |  | 42.7056 | 18.0862 | منتظم | No
2200233262 | وزارة الدفاع / الإدارة الهندسية والاشغال بقوة الصواريخ الإستراتيجية | تشييد | ذات اولوية عالية | 3841572.7 | 192078.635 | 276487.84 | 276487.84 | 1010235877 | لا | 0 | 200939236497 | جاري | الكميات التي تم تركيبها | 8 | 8 | 2022-09-21 | 2023-09-21 | 2023-09-21 | 2023-09-21 |  |  |  |  | 40.4248 | 21.2841 | منتظم | No
2100047821 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 3190010 | 159500.5 | 1500522.25 | 1500522.25 | 4031036822 | لا | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 53 | 53 | 2014-04-23 | 2016-04-30 | 2016-04-30 | 2016-04-30 |  |  | عدم اكتمال أو ضعف أعمال التصميم والدراسات |  | 39.3523 | 21.9034 | Failed | No
2100018922 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 44511602 | 2225580.1 | 41929551.46 | 41828303.88 | 4031046036 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-12-31 | 2019-12-31 | 2020-03-30 | 2020-03-30 | 2019-12-31 |  | منازعات قائمة | أخرى |  |  | منجز | No
2200233273 | المؤسسة العامة لتحلية المياه المالحة | تشييد | ذات اولوية عالية | 912141692 | 45607084.6 | 0 | 0 | 7006784990 | لا | 0 | 220101067555 | جاري | تكلفة العمل المنجز | 11.9 | 17.7 | 2022-05-22 | 2024-11-19 | 2024-11-19 | 2024-11-19 |  |  |  |  | 39.5355 | 20.6903 | متأخر | No
2200233133 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 18587151 | 929357.55 | 4488025.48 | 4488025.48 | 4031046580 | لا | 0 |  | جاري | تكلفة العمل المنجز | 24.15 | 24.15 | 2021-08-24 | 2023-08-23 | 2023-08-23 | 2023-08-23 |  |  |  |  | 39.8579 | 21.3891 | منتظم | No
2100191030 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 3471878 | 173593.9 | 1178298 | 0 | 4031036822 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 60.5 | 85.42 | 2021-04-08 | 2022-09-22 | 2022-09-22 | 2022-09-22 |  |  |  |  | 39.931 | 21.4599 | متأخر | Yes
2200233284 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 29331172.74 | 1466558.637 | 3110838.37 | 3110838.37 | 4030008335 | لا | 0 |  | جاري | تكلفة العمل المنجز | 10.61 | 10.61 | 2021-10-05 | 2023-10-05 | 2023-10-05 | 2023-10-05 |  |  |  |  | 39.8579 | 21.3891 | منتظم | No
2100030940 | أمانة / الرياض | تشييد | ذات اولوية عالية | 9783683.8 | 489184.19 | 41809 | 0 | 1010157240 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 25 | 100 | 2015-04-15 | 2017-04-04 | 2017-04-04 | 2017-04-04 |  |  | ضعف كفاءة المقاول الفنية |  | 46.5108 | 23.6117 | مسحوب | Yes
2100078271 | وزارة الصحة / جدة | تشييد | ذات اولوية عالية | 6142071 | 307103.55 | 6142071 | 6142071 | 1010240323 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-12-18 | 2019-04-17 | 2020-12-21 | 2020-12-21 | 2019-04-17 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.1014 | 21.7682 | منجز | No
2100048801 | وزارة الموارد البشرية والتنمية الإجتماعية | تشييد | ذات اولوية منخفضة | 16580940.94 | 829047.047 | 13954474.74 | 13954474.74 | 5950000083 | لا | 0 | 190309003182 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-04-20 | 2017-10-25 | 2021-12-31 | 2021-12-31 | 2017-10-25 |  | ضعف كفاءة المقاول الفنية |  | 44.4525 | 17.6375 | منجز | No
2200233321 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 28894821 | 1444741.05 | 22304132.77 | 22304132.77 | 1010010506 | لا | 0 |  | منجز – استلام نهائي | تكلفة العمل المنجز | 98.2 | 98.2 | 2014-08-27 | 2016-08-05 | 2016-10-12 | 2016-10-12 | 2016-08-05 | 2021-08-01 |  |  | 39.8579 | 21.3891 | منجز | No
2100057024 | شركة المياه الوطنية / منطقة الرياض | إشراف | ذات اولوية عالية | 166816925 | 8340846.25 | 166658683.99 | 166658683.99 | 1010078921 | لا | 0 |  | منجز – استلام نهائي | مدفوعات ساعات العمل | 99.91 | 100 | 2015-06-01 | 2018-05-31 | 2021-06-15 | 2021-06-15 |  | 2018-05-31 | لا يوجد تأخير |  | 46.7944 | 24.653 | منجز | No
2200233310 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 37458660.6 | 1872933.03 | 32984171.46 | 32984171.46 | 1010006004 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 88.05 | 88.05 | 2015-03-01 | 2017-02-28 | 2017-06-28 | 2017-06-28 | 2017-02-28 |  |  |  | 39.8579 | 21.3891 | منجز | No
2100081745 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 6658436 | 332921.8 | 4416753.36 | 0 | 1010015152 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 87 | 100 | 2013-12-22 | 2015-12-12 | 2020-02-16 | 2020-02-16 | 2015-12-12 |  | ضعف كفاءة المقاول الفنية |  | 46.6775 | 24.7025 | منجز | Yes
2200233306 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 4150370.07 | 207518.5035 | 57016.04 | 57016.04 | 4031057370 | لا | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 1.37 | 1.37 | 2019-06-14 | 2022-05-23 | 2022-05-23 | 2022-05-23 |  |  |  |  | 39.8579 | 21.3891 | Failed | No
2200233343 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 1799560 | 89978 | 376430 | 376430 | 4031052994 | لا | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 20.92 | 20.92 | 2015-05-03 | 2016-04-21 | 2016-04-21 | 2016-04-21 |  |  |  |  | 39.8579 | 21.3891 | Failed | No
2200233295 | المؤسسة العامة لتحلية المياه المالحة | تشييد | ذات اولوية عالية | 299950000 | 14997500 | 224636178 | 224636178 | 1010012911 | لا | 0 | 201001193543 | جاري | تكلفة العمل المنجز | 89.9 | 100 | 2021-01-03 | 2022-07-17 | 2022-12-01 | 2022-12-01 |  |  |  |  | 42.5117 | 18.2465 | متأخر | No
2100003990 | شركة المياه الوطنية / منطقة الحدود الشمالية | تصميم وتشييد | ذات اولوية عالية وعاجلة | 179768328 | 8988416.4 | 113549235.47 | 96119355.06 | 1131014852 | لا | 0 | 181201487935 | جاري | منهجية القيمة المكتسبة | 81.63 | 100 | 2015-05-07 | 2018-04-04 | 2022-11-30 | 2022-11-30 |  |  | اخرى |  | 40.9664 | 30.9774 | متأخر | No
2200233472 | أمانة / عسير | تشييد | ذات اولوية عالية | 2158568 | 107928.4 | 145727 | 0 | 5950018887 | لا | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 62 | 100 | 2020-03-22 | 2021-03-31 | 2023-03-31 | 2023-03-31 |  |  |  |  | 43.5247 | 19.5392 | Failed | Yes
2200233516 | أمانة / عسير | تشييد | ذات اولوية عالية | 3001801.3 | 150090.065 | 10555572.81 | 0 | 5850017638 | لا | 0 |  | جاري | تكلفة العمل المنجز | 82 | 100 | 2022-05-17 | 2023-05-30 | 2023-06-27 | 2023-06-27 |  |  |  |  | 43.3129 | 19.0987 | متأخر | Yes
2100060874 | وزارة الموارد البشرية والتنمية الإجتماعية | تشييد | ذات اولوية منخفضة | 19300396 | 965019.8 | 15912675.98 | 15912675.98 | 1010240933 | لا | 0 | 180709020386 | مسحوب | الكميات التي تم تركيبها | 84 | 100 | 2015-01-06 | 2018-07-29 | 2022-06-15 | 2022-06-15 |  |  | ضعف كفاءة المقاول الفنية |  | 40.1899 | 29.9607 | مسحوب | No
2200233354 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 18894500 | 944725 | 559592 | 559592 | 1010193266 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 5 | 5 | 2022-09-14 | 2024-03-07 | 2024-03-07 | 2024-03-07 |  |  |  |  | 49.7456 | 25.3764 | منتظم | No
2100020252 | وزارة الشـؤون الاسلامية والدعوة والارشاد | تشييد | ذات اولوية عالية | 526040 | 26302 | 0 | 0 | 3350022455 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 10 | 100 | 2017-11-23 | 2018-11-23 | 2020-02-23 | 2020-02-23 | 2018-11-23 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.7151 | 27.5083 | منجز | No
2100100973 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 147656960.07 | 7382848.0035 | 120346713.81 | 90439083.81 | 1116000094 | نعم | 90439083.81 |  | مسحوب | الكميات التي تم تركيبها | 82 | 100 | 2012-05-05 | 2015-04-05 | 2016-11-09 | 2016-11-09 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6814 | 24.7082 | مسحوب | No
2100063932 | أمانة / الجوف | تشييد | ذات اولوية عالية | 3089750 | 154487.5 | 1015690 | 1015690 | 3450013999 | لا | 0 | 190709035292 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 92 | 100 | 2018-11-19 | 2020-05-14 | 2020-05-15 | 2020-05-15 | 2020-05-14 |  | ضعف كفاءة المقاول الفنية |  | 37.354 | 31.3269 | منجز | No
2200233483 | أمانة / عسير | تشييد | ذات اولوية عالية | 8534915 | 426745.75 | 2938800.9 | 1901300 | 5855002494 | لا | 0 |  | جاري | تكلفة العمل المنجز | 47 | 100 | 2021-03-25 | 2022-03-31 | 2023-03-31 | 2023-03-31 |  |  |  |  | 43.2067 | 18.5567 | Failed | No
2200233450 | أمانة / عسير | تشييد | ذات اولوية عالية | 5011000 | 250550 | 0 | 0 | 5851003033 | لا | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 1 | 100 | 2020-06-10 | 2021-06-30 | 2024-03-31 | 2024-03-31 |  |  |  |  | 42.6035 | 19.9742 | Failed | No
2200233520 | أمانة / عسير | تشييد | ذات اولوية عالية | 3997550 | 199877.5 | 0 | 0 | 5860024921 | لا | 0 |  | جاري | تكلفة العمل المنجز | 30 | 100 | 2022-02-27 | 2023-02-28 | 2023-12-31 | 2023-12-31 |  |  |  |  | 41.9441 | 18.9324 | Failed | No
2200233380 | أمانة / الأحساء | تصميم وإشراف | ذات اولوية عالية | 3946800 | 197340 | 1061052 | 1061052 | 1010325732 | لا | 0 |  | جاري | مدفوعات ساعات العمل | 30 | 30 | 2022-05-18 | 2024-05-18 | 2024-05-18 | 2024-05-18 |  |  |  |  | 49.5604 | 25.3897 | منتظم | No
2200233391 | أمانة / الأحساء | إشراف | ذات اولوية عالية | 2760000 | 138000 | 1295545 | 1295545 | 1010325732 | لا | 0 |  | جاري | مدفوعات ساعات العمل | 47 | 47 | 2021-11-01 | 2023-11-02 | 2023-11-02 | 2023-11-02 |  |  |  |  | 49.5604 | 25.3897 | خدمات عامة | No
2200233494 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 4053865 | 202693.25 | 486600 | 486600 | 2050018628 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 23 | 23 | 2022-01-31 | 2023-06-07 | 2023-06-07 | 2023-06-07 |  |  |  |  | 49.5989 | 25.3559 | منتظم | No
2200233365 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 6356448 | 317822.4 | 6194520 | 6194520 | 4031030163 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 99.14 | 99.14 | 2020-01-20 | 2021-12-28 | 2022-03-27 | 2022-03-27 | 2021-12-28 |  |  |  | 39.8579 | 21.3891 | منجز | No
2100093446 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات الجوية | دراسات هندسية | ذات اولوية عالية | 1047900 | 52395 | 1047900 | 1047900 | 2251043785 | لا | 0 | 190901190557 | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2019-09-04 | 2020-01-03 | 2021-09-21 | 2021-09-21 | 2020-01-03 |  |  |  | 47.3174 | 24.1502 | منجز | No
2200233505 | أمانة / عسير | تشييد | ذات اولوية عالية | 6108772 | 305438.6 | 3093886 | 0 | 5855007548 | لا | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 50 | 100 | 2020-06-13 | 2021-06-29 | 2023-09-28 | 2023-09-28 |  |  |  |  | 42.4907 | 19.8614 | Failed | Yes
2200233413 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 1325000 | 66250 | 897768 | 897768 | 2251032226 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 75 | 75 | 2021-11-30 | 2023-02-22 | 2023-02-22 | 2023-02-22 |  |  |  |  | 49.7116 | 25.4059 | منتظم | No
2200233402 | أمانة / الأحساء | إشراف | ذات اولوية متوسطة | 2928912 | 146445.6 | 1213197 | 1213197 | 1010325732 | لا | 0 |  | جاري | مدفوعات ساعات العمل | 44 | 44 | 2021-11-14 | 2023-11-15 | 2023-11-15 | 2023-11-15 |  |  |  |  | 49.5604 | 25.3897 | خدمات عامة | No
2100077895 | أمانة / جدة | تشييد | ذات اولوية عالية وعاجلة | 82182450 | 4109122.5 | 72380465 | 72380465 | 4030007856 | لا | 0 | 190509129922 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-03-21 | 2020-03-08 | 2020-11-09 | 2020-11-09 | 2020-03-08 |  | أوامر تغيير |  | 39.1679 | 21.5004 | منجز | No
2100004970 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 97969436 | 4898471.8 | 87849994.62 | 87849994.62 | 2050005846 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 96.45 | 98.3 | 2019-06-26 | 2021-06-26 | 2022-11-30 | 2022-11-30 |  |  | لا يوجد تأخير |  | 39.951 | 21.4733 | منتظم | No
2200233424 | أمانة / الأحساء | دراسات هندسية | ذات اولوية متوسطة | 368000 | 18400 | 240000 | 240000 | 1010570397 | لا | 0 |  | جاري | مدفوعات ساعات العمل | 67 | 75 | 2021-12-13 | 2023-03-15 | 2023-03-15 | 2023-03-15 |  |  |  |  | 49.5604 | 25.3897 | خدمات عامة | No
2200233531 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 146423500 | 7321175 | 0 | 0 | 5801011479 | لا | 0 |  | جاري | تكلفة العمل المنجز | 0 | 0 |  | 2024-05-14 | 2024-05-14 | 2024-05-14 |  |  |  |  | 39.8579 | 21.3891 | منتظم | No
2200233553 | وزارة الصحة | تشييد | ذات اولوية عالية | 279010.7 | 13950.535 | 0 | 0 | 2051052964 | لا | 0 | 220801169628 | جاري | التكلفة المفوترة | 95 | 95 | 2022-07-31 | 2022-10-01 | 2022-10-01 | 2022-10-01 |  |  |  | أخرى | 50.1007 | 26.4129 | Failed | No
2200233542 | وزارة الصحة | تصميم وتشييد | ذات اولوية عالية | 1161189.5 | 58059.475 | 0 | 0 | 1010185891 | لا | 0 | 220401110612 | جاري | التكلفة المفوترة | 60 | 60 | 2022-06-01 | 2023-03-01 | 2023-03-01 | 2023-03-01 |  |  |  |  | 50.1007 | 26.4129 | منتظم | No
2100077836 | أمانة / جدة | تشييد | ذات اولوية عالية وعاجلة | 51350225 | 2567511.25 | 38875361 | 38875361 | 1010011560 | لا | 0 | 181209488491 | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2018-09-25 | 2019-06-18 | 2020-09-28 | 2020-09-28 | 2019-06-18 | 2021-11-11 | أوامر تغيير |  | 39.1514 | 21.5342 | منجز | No
2100023413 | وزارة التعليم | تشييد | ذات اولوية عالية | 1927477 | 96373.85 | 283985 | 0 | 4030123131 | لا | 0 |  | مسحوب | التكلفة المفوترة | 25 | 100 | 2008-07-26 | 2009-07-05 | 2013-05-13 | 2013-05-13 |  |  | ضعف كفاءة المقاول الفنية |  | 38.0623 | 24.0861 | مسحوب | Yes
2100085293 | أمانة / المدينة المنورة | دراسة الجدوى | ذات اولوية متوسطة | 18011330 | 900566.5 | 18011330 | 18011330 | 1131052059 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-08-26 | 2022-07-23 | 2022-06-23 | 2022-06-23 | 2022-07-23 |  | اخرى |  |  |  | منجز | No
2100104016 | وزارة التعليم | تشييد | ذات اولوية عالية | 10252170.56 | 512608.528 | 0.01 | 0.01 | 5950011291 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2013-11-17 | 2019-07-15 | 2019-07-15 | 2019-07-15 | 2019-07-15 |  | ضعف كفاءة المقاول الفنية |  | 44.2341 | 17.5757 | منجز | No
2100037612 | صندوق تنمية الموارد البشرية | تشييد | ذات اولوية منخفضة | 35100313.26 | 1755015.663 | 14122383.08 | 14122383.08 | 1010145283 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 75 | 100 | 2015-02-03 | 2017-01-11 | 2021-09-09 | 2021-09-09 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.1853 | 21.4661 | مسحوب | No
2200233590 | رئاسة أمن الدولة / المديرية العامة للمباحث | ترميم | ذات اولوية متوسطة | 1346266.75 | 67313.3375 | 0 | 0 | 1010419886 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 60 | 100 | 2022-05-09 | 2022-09-20 | 2023-03-07 | 2023-03-07 |  |  |  |  | 46.6992 | 24.6719 | Failed | No
2100006440 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1300000 | 65000 | 0 | 0 | 1010301436 | لا | 0 |  | مسحوب | التكلفة المفوترة | 0 | 100 | 2013-02-01 | 2013-10-01 | 2023-08-16 | 2023-08-16 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0859 | 19.1571 | مسحوب | No
2200233586 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 14972740.65 | 748637.0325 | 13287348.16 | 13287348.16 | 4030183716 | لا | 0 |  | جاري | تكلفة العمل المنجز | 88.74 | 88.74 | 2020-02-02 | 2022-02-01 | 2022-02-01 | 2022-02-01 |  |  |  |  | 39.8579 | 21.3891 | Failed | No
2100092282 | أمانة / الحدود الشمالية | تشييد | ذات اولوية متوسطة | 1889600 | 94480 | 1455010 | 1455010 | 1010253942 | لا | 0 | 181009119276 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2014-06-04 | 2015-08-28 | 2020-10-27 | 2020-10-27 | 2015-08-28 |  | ضعف كفاءة المقاول الفنية |  | 43.7414 | 28.7629 | منجز | No
2100193421 | جامعة تبوك | تشييد | ذات اولوية عالية وعاجلة | 163453323.2 | 8172666.16 | 111803459.68 | 111803459.68 | 1010122914 | لا | 0 | 180709033822 | جاري | الكميات التي تم تركيبها | 87 | 97 | 2014-12-22 | 2022-11-11 | 2023-05-11 | 2023-05-11 |  |  |  |  | 36.4832 | 28.3832 | متأخر | No
2100201633 | جامعة أم القرى | تشييد | ذات اولوية عالية وعاجلة | 333518416.24 | 16675920.812 | 262333019.07 | 262333019.07 | 4030138280 | لا | 0 | 211009013485 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2010-11-29 | 2013-10-05 | 2021-12-31 | 2021-12-31 | 2013-10-05 |  |  |  | 39.9389 | 21.323 | منجز | No
2200233623 | رئاسة أمن الدولة / المديرية العامة للمباحث | تشييد | ذات اولوية متوسطة | 1280191.5 | 64009.575 | 0 | 0 | 1010238249 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 25 | 100 | 2022-10-01 | 2023-03-22 | 2023-03-22 | 2023-03-22 |  |  |  |  | 46.6992 | 24.6719 | Failed | No
2100014943 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 4993193 | 249659.65 | 0 | 0 | 1010121536 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0 | 100 | 2007-11-02 | 2009-10-22 | 2023-05-05 | 2023-05-05 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.5429 | 16.8808 | مسحوب | No
2200233634 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 6667500 | 333375 | 839768.25 | 839768.25 | 4031022496 | لا | 0 |  | جاري | التكلفة المفوترة | 9 | 9 | 2021-02-28 | 2023-02-06 | 2023-02-06 | 2023-02-06 |  |  |  |  | 39.8579 | 21.3891 | منتظم | No
2100082154 | أمانة / جازان | تشييد | لم تعد تحتاجها الجهة | 2794810 | 139740.5 | 1800384 | 1800384 | 5900006007 | لا | 0 | 181009116096 | مسحوب | الكميات التي تم تركيبها | 64 | 100 | 2010-10-18 | 2011-10-13 | 2022-10-13 | 2022-10-13 |  |  | ضعف كفاءة المقاول الفنية |  | 42.9733 | 16.528 | مسحوب | No
2100191995 | شركة المياه الوطنية / منطقة الجوف | إشراف | ذات اولوية عالية وعاجلة | 15183000 | 759150 | 8091668.93 | 8091668.93 | 4030280093 | لا | 0 | 191201005168 | جاري | مدفوعات ساعات العمل | 55.98 | 55.98 | 2020-11-24 | 2023-04-29 | 2023-04-29 | 2023-04-29 |  |  |  |  | 40.2287 | 29.965 | خدمات عامة | No
2100103316 | شركة المياه الوطنية / منطقة الجوف | تشييد | ذات اولوية عالية | 85382319.09 | 4269115.9545 | 65840483.15 | 65840483.15 | 1010166750 | لا | 0 | 180709028214 | مسحوب | منهجية القيمة المكتسبة | 82 | 100 | 2014-09-25 | 2017-08-23 | 2022-12-31 | 2022-12-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 40.2253 | 29.8793 | مسحوب | No
2100088955 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 9847075.48 | 492353.774 | 8844775.06 | 8844775.06 | 1010081451 | لا | 0 |  | مسحوب | التكلفة المفوترة | 81 | 100 | 2014-05-18 | 2016-05-07 | 2019-05-08 | 2019-05-08 |  |  | ضعف كفاءة المقاول الفنية |  | 46.5607 | 24.6524 | مسحوب | No
2100058236 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 1096075 | 54803.75 | 401988.41 | 401988.41 | 3453002612 | لا | 0 |  | مسحوب | منهجية القيمة المكتسبة | 39 | 39 | 2015-02-25 | 2016-05-20 | 2021-12-01 | 2021-12-01 |  |  | ضعف كفاءة المقاول الفنية |  | 43.7452 | 28.7618 | مسحوب | No
2100053410 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 44647879.97 | 2232393.9985 | 35556196 | 35556196 | 1010184457 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2009-05-21 | 2011-11-21 | 2019-06-24 | 2019-06-24 | 2011-11-21 | 2021-11-24 |  |  | 39.8202 | 21.3958 | منجز | No
2100087010 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 15248585.22 | 762429.261 | 12754208.66 | 12754208.66 | 4030142803 | لا | 0 | 180709016089 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2017-05-24 | 2018-03-15 | 2022-12-31 | 2022-12-31 |  |  | تأخرصرف المستحقات المالية |  | 39.1677 | 21.5008 | متأخر | No
2100099676 | المؤسسة العامة لتحلية المياه المالحة | إشراف | ذات اولوية عالية | 82064351 | 4103217.55 | 68247725.5 | 68247725.5 | 1010197409 | لا | 0 | 180909095208 | جاري | منهجية القيمة المكتسبة | 89.7 | 100 | 2018-02-11 | 2022-08-11 | 2022-08-11 | 2022-08-11 |  |  |  |  | 39.0076 | 22.7186 | خدمات عامة | No
2100105206 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 59498150 | 2974907.5 | 51001421.18 | 51001421.18 | 1010026934 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 96.84 | 100 | 2018-04-23 | 2020-04-23 | 2020-06-04 | 2020-06-04 |  | 2020-04-23 | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100009085 | شركة المياه الوطنية / منطقة الجوف | تشييد | ذات اولوية عالية | 16101394.5 | 805069.725 | 16099863.5 | 13738944.5 | 5950014087 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-02-04 | 2019-10-17 | 2020-07-25 | 2020-07-25 | 2019-10-17 | 2021-11-10 | لا يوجد تأخير |  | 39.8362 | 29.8111 | منجز | No
2100201736 | الهيئة العامة للزكاة والدخل | توريد وتركيب | ذات اولوية عالية | 3985311.9 | 199265.595 | 0 | 0 | 1010246538 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2021-12-12 | 2022-08-17 | 2022-07-31 | 2022-07-31 |  | 2022-08-17 |  |  | 49.5644 | 25.3209 | منجز | No
2100058424 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 12753595 | 637679.75 | 1531295 | 1531295 | 1010072637 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 19 | 100 | 2015-07-23 | 2018-01-08 | 2023-02-15 | 2023-02-15 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0859 | 19.1571 | مسحوب | No
2100026773 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية عالية وعاجلة | 17164503.64 | 858225.182 | 17036718.12 | 17036718.12 | 1010249314 | لا | 0 | 190409067050 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2017-11-15 | 2020-05-14 | 2020-04-18 | 2020-04-18 | 2020-05-14 |  | اخرى |  | 39.2721 | 21.4563 | منجز | No
2100201703 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 2073779.96 | 103688.998 | 1371489.22 | 1371489.22 | 4030185953 | لا | 0 |  | ايقاف كلي | منهجية القيمة المكتسبة | 87.11 | 100 | 2021-05-20 | 2022-01-20 | 2022-04-30 | 2022-04-30 |  |  |  |  | 39.2073 | 21.4534 | Failed | No
2100099654 | شركة المياه الوطنية / منطقة مكة المكرمة | تصميم | ذات اولوية عالية | 4225367.6 | 211268.38 | 6261148.4 | 6261148.4 | 4030286888 | لا | 0 | 200709052696 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2017-01-15 | 2020-01-14 | 2020-01-14 | 2020-01-14 | 2020-01-14 |  | لا يوجد تأخير |  | 39.2213 | 21.5522 | منجز | No
2100103681 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية | 37847368 | 1892368.4 | 22199041.38 | 22199041.38 | 1010184370 | لا | 0 | 180709026181 | مسحوب | منهجية القيمة المكتسبة | 94.5 | 100 | 2014-01-28 | 2016-01-07 | 2022-12-01 | 2022-12-01 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.127 | 26.5029 | مسحوب | No
2100048882 | جامعة القصيم | تشييد | ذات اولوية متوسطة | 3657675 | 182883.75 | 2921250.4 | 2921250.4 | 1010092552 | لا | 0 | 200609028835 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-04-09 | 2019-10-06 | 2021-01-12 | 2021-01-12 |  |  | تأخرصرف المستحقات المالية |  | 43.7751 | 26.3101 | Failed | No
2100023940 | وزارة التعليم | تشييد | ذات اولوية عالية | 20212399.96 | 1010619.998 | 10055692.96 | 10055692.96 | 4030174393 | لا | 0 | 190301092483 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-01-13 | 2016-01-03 | 2018-09-20 | 2018-09-20 | 2016-01-03 |  | ضعف كفاءة المقاول الفنية |  | 39.836 | 21.4408 | منجز | No
2100026924 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 6249357 | 312467.85 | 4400951.68 | 4400951.68 | 1132002624 | لا | 0 | 190209016092 | منجز – استلام ابتدائي | التكلفة المفوترة | 82 | 100 | 2014-01-26 | 2016-01-16 | 2022-11-10 | 2022-11-10 | 2016-01-16 |  | ضعف كفاءة المقاول الفنية |  | 40.2691 | 20.1489 | منجز | No
2200211186 | شركة المياه الوطنية / منطقة المدينة المنورة | دراسة بيئية | ذات اولوية عالية | 500000 | 25000 | 294000 | 294000 | 4030279254 | لا | 0 | 180701036742 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 0 | 0 | 2019-01-06 | 2020-01-11 | 2020-01-11 | 2020-01-11 | 2020-01-11 |  |  |  | 39.5927 | 24.4446 | منجز | No
2100079520 | وزارة التعليم | تشييد | لم تعد تحتاجها الجهة | 1993365 | 99668.25 | 0 | 0 | 1010069591 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0 | 100 | 2010-12-18 | 2011-12-09 | 2021-11-10 | 2021-11-10 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 43.1379 | 18.0853 | مسحوب | No
2100013381 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 26324991 | 1316249.55 | 19445860.19 | 19445860.19 | 3350014401 | لا | 0 | 190301016091 | جاري | الكميات التي تم تركيبها | 93 | 100 | 2019-04-15 | 2023-03-30 | 2023-04-30 | 2023-04-30 |  |  |  |  | 41.7103 | 27.5041 | متأخر | No
2100044041 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 25734100 | 1286705 | 14292692.98 | 11802500.33 | 4700003298 | لا | 0 | 190301003721 | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 90 | 100 | 2019-04-27 | 2021-10-12 | 2023-04-06 | 2023-04-06 |  |  |  | تم إنذار المقاول كتابيا | 41.7208 | 27.5114 | متأخر | No
2100071584 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 731812.55 | 36590.6275 | 295620.92 | 295620.92 | 4036001622 | لا | 0 | 181009120105 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2016-01-03 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 |  |  |  | 40.4195 | 21.2487 | منجز | No
2100089891 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 8838090.22 | 441904.511 | 0.01 | 0.01 | 5950010876 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-12-10 | 2016-09-30 | 2021-12-07 | 2021-12-07 | 2016-09-30 |  | ضعف كفاءة المقاول الفنية |  | 44.2341 | 17.5757 | منجز | No
2100025922 | شركة المياه الوطنية | تشييد | ذات اولوية عالية | 192738888 | 9636944.4 | 151492527.66 | 151492527.66 | 5855000147 | لا | 0 | 180809063593 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99.43 | 100 | 2009-12-22 | 2011-11-30 | 2020-10-27 | 2020-10-27 | 2011-11-30 |  | لا يوجد تأخير |  | 39.3358 | 22.1552 | منجز | No
2100086376 | شركة المياه الوطنية / منطقة الحدود الشمالية | تصميم وتشييد | ذات اولوية عالية وعاجلة | 73589530.71 | 3679476.5355 | 33513968.93 | 33513968.93 | 1010188588 | نعم | 66464093.86 | 180201000138 | مسحوب | منهجية القيمة المكتسبة | 67.47 | 100 | 2018-04-16 | 2020-09-18 | 2023-02-15 | 2023-02-15 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 40.9664 | 30.9774 | مسحوب | No
2100083591 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1401000 | 70050 | 1401000 | 1401000 | 4031212978 | لا | 0 | 190401052146 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-03-07 | 2020-03-01 | 2020-03-01 | 2020-03-01 | 2020-03-01 |  |  |  | 40.9877 | 21.0575 | منجز | No
2100044741 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 279201705 | 13960085.25 | 211047331.4 | 211047331.4 | 1010044185 | لا | 0 | 181209412224 | جاري | الكميات التي تم تركيبها | 73.25 | 86 | 2013-05-15 | 2017-11-06 | 2019-11-20 | 2019-11-20 |  |  | عدم اكتمال أو ضعف أعمال التصميم والدراسات |  | 46.6869 | 24.6969 | Failed | No
2100079741 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية عالية | 15755605 | 787780.25 | 14386585.12 | 14386585.12 | 1116002556 | لا | 0 | 180709023717 | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 99 | 100 | 2018-10-09 | 2021-10-13 | 2021-10-13 | 2021-10-13 |  |  | اخرى |  | 41.1133 | 19.8997 | Failed | No
2100068154 | شركة المياه الوطنية | تشييد | لم تعد تحتاجها الجهة | 25377600 | 1268880 | 6090624 | 6090624 | 1010993201 | لا | 0 |  | مسحوب | منهجية القيمة المكتسبة | 24 | 100 | 2008-05-26 | 2011-04-25 | 2011-04-25 | 2011-04-25 |  |  | ضعف كفاءة المقاول الفنية |  | 36.3672 | 28.1761 | مسحوب | No
2100105556 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية وعاجلة | 96850000 | 4842500 | 52853679.6 | 52624110 | 1010257051 | نعم | 48514915.95 |  | جاري | منهجية القيمة المكتسبة | 63.04 | 100 | 2020-03-01 | 2021-06-02 | 2022-06-30 | 2022-06-30 |  |  | لا يوجد تأخير |  | 47.5389 | 25.1024 | Failed | No
2100191564 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية وعاجلة | 111378127 | 5568906.35 | 61918680.54 | 40641523.46 | 2050005846 | نعم | 182866178.26 |  | جاري | منهجية القيمة المكتسبة | 72.05 | 100 | 2021-03-30 | 2022-03-31 | 2022-03-30 | 2022-03-30 |  |  |  |  | 46.6446 | 24.5055 | Failed | No
2100087883 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 495320 | 24766 | 319240 | 319240 | 2251041268 | لا | 0 |  | جاري | التكلفة المفوترة | 90 | 100 | 2015-06-20 | 2016-06-14 | 2019-06-12 | 2019-06-12 |  |  | ضعف كفاءة المقاول الفنية |  | 50.6303 | 26.282 | Failed | No
2100065542 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 10475387.17 | 523769.3585 | 3207356.51 | 3207356.51 | 2055002421 | لا | 0 |  | مسحوب | التكلفة المفوترة | 50 | 100 | 2015-01-18 | 2017-01-07 | 2018-04-02 | 2018-04-02 |  |  | ضعف كفاءة المقاول الفنية |  | 45.975 | 28.4334 | مسحوب | No
2100015245 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 8086318.56 | 404315.928 | 1140446 | 1140446 | 1010081451 | لا | 0 |  | مسحوب | التكلفة المفوترة | 17 | 100 | 2016-09-27 | 2018-09-17 | 2021-06-24 | 2021-06-24 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | مسحوب | No
2100042663 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 17799774.94 | 889988.747 | 14663294.2 | 13236561.08 | 4030064711 | لا | 0 | 180709021228 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2017-09-18 | 2017-12-08 | 2022-12-31 | 2022-12-31 |  |  | تأخرصرف المستحقات المالية |  | 39.1677 | 21.5008 | منتظم | No
2100071352 | أمانة / الطائف | تصميم وإشراف | ذات اولوية متوسطة | 2478798.88 | 123939.944 | 2450952 | 2450952 | 4030281454 | لا | 0 | 180809065111 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-02-12 | 2021-02-11 | 2021-02-11 | 2021-02-11 | 2021-02-11 |  | ضعف كفاءة المقاول الفنية |  | 40.4248 | 21.2769 | منجز | No
2100103401 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2336112 | 116805.6 | 1834723.44 | 1834723.44 | 3350008677 | لا | 0 |  | جاري | التكلفة المفوترة | 92 | 100 | 2010-10-30 | 2011-12-24 | 2022-02-18 | 2022-02-18 |  |  | ضعف كفاءة المقاول الفنية |  | 45.313 | 24.0763 | Failed | No
2100000280 | وزارة التعليم | تشييد | ذات اولوية عالية | 10762927.08 | 538146.354 | 10762927.08 | 10762927.08 | 1010081451 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-03-26 | 2019-02-07 | 2019-02-07 | 2019-02-07 | 2019-02-07 |  | اخرى |  | 46.7098 | 24.6275 | منجز | No
2100004911 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 8425595 | 421279.75 | 962203.74 | 962203.74 | 1131022175 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 62 | 56 | 2019-03-30 | 2020-12-19 | 2023-02-15 | 2023-02-15 | 2020-12-19 |  | ضعف كفاءة المقاول الفنية |  | 43.6565 | 26.1508 | منجز | No
2100097381 | جامعة الإمام محمد بن سعود الاسلامية | تشييد | ذات اولوية متوسطة | 41056402.07 | 2052820.1035 | 41056402 | 36376804 | 3350003498 | لا | 0 | 180809039891 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-08-02 | 2016-07-02 | 2018-05-03 | 2018-05-03 | 2016-07-02 |  | لا يوجد تأخير |  | 41.6913 | 27.485 | منجز | No
2100085201 | وزارة الصحة / حائل | تشييد | ذات اولوية متوسطة | 1661185 | 83059.25 | 629447 | 543828 | 3350022365 | لا | 0 |  | جاري | تكلفة العمل المنجز | 85 | 100 | 2015-07-06 | 2016-03-28 | 2022-05-18 | 2022-05-18 |  |  | ضعف كفاءة المقاول الفنية |  | 41.3107 | 26.7827 | Failed | No
2100047062 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 674500 | 33725 | 512180.95 | 512180.95 | 4037000411 | لا | 0 | 201101223382 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-08-25 | 2020-02-20 | 2022-05-15 | 2022-05-15 | 2020-02-20 |  |  |  | 42.1753 | 22.7175 | منجز | No
2200220732 | المؤسسة العامة للتأمينات الاجتماعية | ترميم | ذات اولوية عالية | 25240801 | 1262040.05 | 19033629.06 | 19033629.06 | 1010189393 | لا | 0 |  | ايقاف كلي | منهجية القيمة المكتسبة | 100 | 100 | 2021-10-19 | 2022-04-18 | 2022-08-31 | 2022-08-31 |  |  |  |  | 50.218 | 26.3812 | Failed | No
2200220743 | المؤسسة العامة للتأمينات الاجتماعية | ترميم | ذات اولوية متوسطة | 20958000 | 1047900 | 11615415.89 | 11615415.89 | 2051040604 | لا | 0 |  | ايقاف كلي | منهجية القيمة المكتسبة | 96 | 100 | 2021-10-28 | 2022-04-27 | 2022-08-03 | 2022-08-03 |  |  |  |  | 50.189 | 26.3598 | Failed | No
2100023310 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 568756 | 28437.8 | 568756 | 568756 | 4031062372 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2019-11-17 | 2020-06-16 | 2020-09-07 | 2020-09-07 | 2020-06-16 |  | اخرى |  |  |  | منجز | No
2100191796 | شركة المياه الوطنية / منطقة حائل | إشراف | لم تعد تحتاجها الجهة | 7984928 | 399246.4 | 8668471.12 | 8668471.12 | 1010320035 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2013-04-23 | 2015-04-23 | 2015-04-23 | 2015-04-23 | 2015-04-23 |  |  |  | 41.7787 | 27.5006 | منجز | No
2100053686 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 305802463.3 | 15290123.165 | 305802463.3 | 305802463.3 | 1010090968 | لا | 0 | 181109316106 | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2010-06-20 | 2013-05-17 | 2019-06-26 | 2019-06-26 | 2013-05-17 | 2021-08-08 |  |  | 39.2618 | 21.2712 | منجز | No
2100007851 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 4824510 | 241225.5 | 1365387.3 | 1365387.3 | 1010088136 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 60 | 100 | 2012-08-19 | 2014-04-08 | 2016-03-09 | 2016-03-09 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 45.3525 | 25.8912 | مسحوب | No
2100016800 | وزارة التعليم | تشييد | ذات اولوية عالية | 15738057.18 | 786902.859 | 12656919.9 | 12656919.9 | 1116002219 | لا | 0 |  | جاري | التكلفة المفوترة | 98 | 100 | 2011-05-24 | 2013-06-06 | 2013-06-06 | 2013-06-06 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | Failed | No
2200220754 | المؤسسة العامة للتأمينات الاجتماعية | ترميم | ذات اولوية متوسطة | 2670000 | 133500 | 0 | 0 | 2050015998 | لا | 0 |  | ايقاف كلي | منهجية القيمة المكتسبة | 64 | 88.68 | 2022-01-20 | 2022-08-19 | 2022-08-19 | 2022-08-19 |  |  |  |  | 50.218 | 26.3812 | Failed | No
2100202952 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية وعاجلة | 3503857.04 | 175192.852 | 3503857.04 | 1964464.48 | 1010014082 | لا | 0 | 210101005626 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 98.77 | 100 | 2021-04-27 | 2021-10-21 | 2021-10-19 | 2021-10-19 | 2021-10-21 |  |  |  | 41.9801 | 27.0377 | منجز | No
2100061250 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية وعاجلة | 25841695 | 1292084.75 | 6865993.48 | 5680516.46 | 1010191039 | لا | 0 | 181101287583 | مسحوب | منهجية القيمة المكتسبة | 38.5 | 100 | 2018-04-29 | 2020-04-06 | 2023-09-27 | 2023-09-27 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.4487 | 27.1841 | مسحوب | No
2100036573 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية عالية | 246923346.61 | 12346167.3305 | 222231011 | 221167244 | 1010048595 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-03-23 | 2019-09-19 | 2022-03-15 | 2022-03-15 | 2019-09-19 |  |  |  | 45.7527 | 23.8265 | منجز | No
2100038135 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية منخفضة | 10841417 | 542070.85 | 1774879 | 1774879 | 1116001737 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 20.01 | 20.01 | 2019-01-17 | 2021-12-14 | 2021-05-02 | 2021-05-02 |  |  | اخرى |  | 46.6555 | 24.7075 | مسحوب | No
2100000011 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية وعاجلة | 15697813 | 784890.65 | 13823953.4 | 13823953.4 | 1010267848 | لا | 0 | 181009121686 | جاري | منهجية القيمة المكتسبة | 90.79 | 98.05 | 2015-02-11 | 2018-01-09 | 2022-12-31 | 2022-12-31 |  |  | اخرى |  | 39.8464 | 23.3417 | متأخر | No
2100012036 | وزارة التعليم | تشييد | ذات اولوية عالية | 11775856 | 588792.8 | 5862465.82 | 5646988.21 | 4650020435 | لا | 0 |  | مسحوب | التكلفة المفوترة | 76 | 100 | 2014-11-15 | 2016-11-05 | 2023-06-15 | 2023-06-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | No
2100083425 | أمانة / الجوف | تشييد | ذات اولوية عالية | 3724000 | 186200 | 1259200 | 1259200 | 3404013940 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 45 | 100 | 2014-08-14 | 2015-08-09 | 2015-08-09 | 2015-08-09 |  |  | ضعف كفاءة المقاول الفنية |  | 38.226 | 30.5113 | مسحوب | No
2100015735 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية عالية | 86904135 | 4345206.75 | 22008653.37 | 22008653.37 | 1116000094 | لا | 0 | 180909093907 | مسحوب | منهجية القيمة المكتسبة | 43.39 | 100 | 2012-10-17 | 2014-05-30 | 2022-12-31 | 2022-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 37.2869 | 24.9722 | مسحوب | No
2100005305 | شركة المياه الوطنية / منطقة القصيم | تصميم | ذات اولوية عالية وعاجلة | 6261000 | 313050 | 4579474.29 | 3756600 | 1010348048 | لا | 0 | 180901097668 | منجز – استلام نهائي | التكلفة المفوترة | 100 | 100 | 2018-09-27 | 2019-05-26 | 2022-06-30 | 2022-06-30 |  | 2019-05-26 | لا يوجد تأخير |  | 43.9913 | 26.3261 | منجز | No
2100016612 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية وعاجلة | 69725250 | 3486262.5 | 25015386.2 | 18861228.75 | 1010012911 | لا | 0 | 190401000853 | جاري | منهجية القيمة المكتسبة | 60.1 | 85.45 | 2019-07-18 | 2021-12-19 | 2022-10-12 | 2022-10-12 |  |  | لا يوجد تأخير |  | 44.1714 | 26.4275 | Failed | No
2100093671 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 73468097.5 | 3673404.875 | 50215115.39 | 50215115.39 | 2222222222 | لا | 0 | 180809041948 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99.54 | 100 | 2013-10-24 | 2016-09-20 | 2021-10-25 | 2021-10-25 | 2016-09-20 |  | لا يوجد تأخير |  | 44.4412 | 24.5406 | منجز | No
2100038216 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية متوسطة | 15611947.8 | 780597.39 | 13354531.44 | 13354531.44 | 5850022870 | لا | 0 | 180901079495 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 95.24 | 100 | 2018-12-16 | 2020-11-24 | 2021-07-04 | 2021-07-04 | 2020-11-24 |  | ضعف كفاءة المقاول الفنية |  | 43.9597 | 26.325 | منجز | No
2100013252 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2403000 | 120150 | 1758502.9 | 0 | 1010212192 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-09-07 | 2016-09-01 | 2021-06-17 | 2021-06-17 | 2016-09-01 |  | ضعف كفاءة المقاول الفنية |  | 47.3447 | 24.1342 | منجز | Yes
2100178463 | وزارة الثقافة | تشييد | ذات اولوية عالية | 23751199.89 | 1187559.9945 | 22908971.95 | 20750192.35 | 1010208611 | لا | 0 | 201009228671 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-10-17 | 2020-04-11 | 2020-05-11 | 2020-05-11 | 2020-04-11 |  |  |  | 39.8829 | 21.3436 | منجز | No
2100057503 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية وعاجلة | 84443410 | 4222170.5 | 46401894.54 | 38263740.91 | 1010010521 | لا | 0 | 181109240499 | جاري | منهجية القيمة المكتسبة | 75.61 | 99.77 | 2018-02-25 | 2021-01-22 | 2022-07-16 | 2022-07-16 |  |  | ضعف كفاءة المقاول الفنية |  | 43.9552 | 26.2771 | متأخر | No
2100058951 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية متوسطة | 19124383.3 | 956219.165 | 19543857.53 | 18776174.28 | 1129000025 | لا | 0 | 180709020391 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 81 | 100 | 2011-08-08 | 2015-06-25 | 2021-06-23 | 2021-06-23 | 2015-06-25 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 43.9544 | 26.3504 | منجز | No
2100190794 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 175930477 | 8796523.85 | 26707831 | 17069389.95 | 1010085982 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 25.9 | 26.84 | 2021-04-07 | 2024-04-07 | 2024-04-07 | 2024-04-07 |  |  |  |  | 40.3984 | 21.2614 | منتظم | No
2100092050 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية | 14786405.6 | 739320.28 | 14909028.63 | 13429240.83 | 4031045263 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2015-08-13 | 2017-07-22 | 2019-10-25 | 2019-10-25 |  | 2017-07-22 | لا يوجد تأخير |  | 39.5739 | 24.4791 | منجز | No
2100059404 | هيئة المدن الصناعية ومناطق التقنية | تشييد | ذات اولوية عالية | 2979806 | 148990.3 | 2979806 | 2979806 | 4030159937 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-09-01 | 2020-02-29 | 2020-09-09 | 2020-09-09 | 2020-02-29 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 26.398 | 50.1407 | منجز | No
2100068611 | شركة الكهرباء | تشييد | ذات اولوية متوسطة | 93866598 | 4693329.9 | 71476205 | 71476205 | 1010090181 | لا | 0 |  | جاري | اخرى | 99 | 100 | 2015-11-12 | 2017-12-12 | 2022-11-30 | 2022-11-30 |  |  | اخرى |  | 39.8645 | 21.4635 | متأخر | No
2100040213 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 86450555.5 | 4322527.775 | 33670916.27 | 33670916.27 | 2055014114 | لا | 0 | 180701015134 | جاري | منهجية القيمة المكتسبة | 50 | 100 | 2018-10-15 | 2021-04-12 | 2023-12-24 | 2023-12-24 |  |  | عدم وجود كوادر كافية في الجهه لادارة المشروع |  | 49.5648 | 27.1019 | Failed | No
2100087393 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية | 19999728.3 | 999986.415 | 18221638.88 | 18221638.88 | 2050003475 | لا | 0 | 180901083963 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-10-30 | 2021-04-03 | 2021-05-02 | 2021-05-02 |  | 2021-04-03 | لا يوجد تأخير |  | 43.9553 | 26.3508 | منجز | No
2100018745 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية | 13585540 | 679277 | 12176656.7 | 12176656.7 | 5860008190 | لا | 0 | 180301000530 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-10-18 | 2020-04-02 | 2021-02-15 | 2021-02-15 | 2020-04-02 |  | لا يوجد تأخير |  | 41.4631 | 19.7324 | منجز | No
2100058052 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1098846 | 54942.3 | 1043904 | 0 | 1010150014 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 100 | 2014-10-18 | 2016-01-04 | 2016-01-04 | 2016-01-04 | 2016-01-04 |  |  |  | 45.5296 | 23.533 | منجز | Yes
2100059415 | جامعة الإمام محمد بن سعود الاسلامية | تشييد | ذات اولوية عالية | 227700000 | 11385000 | 201766275.06 | 150428944.17 | 1010046693 | لا | 0 | 180809039938 | جاري الاستلام الإبتدائي | اخرى | 100 | 100 | 2012-11-17 | 2015-04-21 | 2020-09-19 | 2020-09-19 |  |  | تأخرصرف المستحقات المالية |  | 46.7098 | 24.6275 | Failed | No
2100004760 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 12740958.68 | 637047.934 | 4226979.8 | 4226979.8 | 1116004360 | لا | 0 |  | مسحوب | التكلفة المفوترة | 32 | 100 | 2012-09-07 | 2017-12-11 | 2017-12-11 | 2017-12-11 |  |  | ضعف كفاءة المقاول الفنية |  | 50.5194 | 26.5494 | مسحوب | No
2100101286 | وزارة الثقافة | تشييد | ذات اولوية عالية | 8013480 | 400674 | 8013480 | 8013480 | 4030154929 | لا | 0 |  | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2020-03-05 | 2020-05-20 | 2021-03-15 | 2021-03-15 | 2020-05-20 | 2021-03-15 | لا يوجد تأخير |  | 39.2234 | 21.4534 | منجز | No
2200221045 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 13385000 | 669250 | 1107940.1 | 1107940.1 | 4700009877 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 25.16 | 27.77 | 2022-02-28 | 2022-08-28 | 2022-08-28 | 2022-08-28 |  |  |  |  | 39.8915 | 21.4158 | منتظم | No
2200221060 | شركة المياه الوطنية / منطقة مكة المكرمة | إشراف | ذات اولوية عالية | 5376000 | 268800 | 3499322.08 | 3499322.08 | 1010326770 | لا | 0 |  | جاري | مدفوعات ساعات العمل | 70.15 | 100 | 2020-05-05 | 2022-05-05 | 2022-05-05 | 2022-05-05 |  |  |  |  | 39.1925 | 21.4858 | خدمات عامة | No
2200221071 | شركة المياه الوطنية / منطقة مكة المكرمة | توريد وتركيب | ذات اولوية عالية | 19200000 | 960000 | 8590737.78 | 8590737.78 | 1010276827 | لا | 0 |  | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2021-10-07 | 2022-04-07 | 2022-04-30 | 2022-04-30 |  |  |  |  | 39.1384 | 21.7675 | Failed | No
2200211466 | وزارة الصحة / القصيم | تشييد | ذات اولوية متوسطة | 2617900 | 130895 | 2617900 | 2617900 | 1131018576 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-11-02 | 2021-10-14 | 2022-02-28 | 2022-02-28 | 2021-10-14 |  |  |  | 43.9702 | 26.3487 | منجز | No
2100001444 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 6141261 | 307063.05 | 1784948 | 1784948 | 1010456278 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-03-07 | 2019-07-20 | 2019-09-12 | 2019-09-12 | 2019-07-20 |  |  |  | 41.0165 | 30.9619 | منجز | No
2100018130 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | دراسات هندسية | ذات اولوية عالية وعاجلة | 32973919 | 1648695.95 | 31946578.51 | 31946578.51 | 2051060068 | لا | 0 | 180809058553 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2013-11-24 | 2018-11-23 | 2022-11-23 | 2022-11-23 | 2018-11-23 |  |  |  | 49.1711 | 27.5037 | منجز | No
2100074583 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2839742 | 141987.1 | 0.01 | 0 | 1010046644 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 2 | 100 | 2016-11-27 | 2018-11-17 | 2018-11-17 | 2018-11-17 |  |  | ضعف كفاءة المقاول الفنية |  | 48.9757 | 27.4739 | مسحوب | Yes
2100028475 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | دراسات هندسية | ذات اولوية عالية وعاجلة | 7526495.34 | 376324.767 | 7287506.89 | 7287506.89 | 1010320728 | لا | 0 | 180809059288 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 91 | 100 | 2018-01-04 | 2021-01-03 | 2021-01-23 | 2021-01-23 | 2021-01-03 |  |  |  | 49.5711 | 26.954 | منجز | No
2100009295 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | دراسات هندسية | ذات اولوية عالية وعاجلة | 17048421.5 | 852421.075 | 12904133.13 | 12904133.13 | 2051059585 | لا | 0 | 180809059407 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 94 | 100 | 2015-10-14 | 2020-10-14 | 2023-07-14 | 2023-07-14 | 2020-10-14 |  |  | أخرى | 49.1864 | 27.5028 | منجز | No
2100033353 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية منخفضة | 5738700 | 286935 | 2643743.52 | 2643743.52 | 4650032626 | لا | 0 | 180909076946 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 80.14 | 98.56 | 2013-03-24 | 2015-03-03 | 2020-09-08 | 2020-09-08 | 2015-03-03 |  | لا يوجد تأخير |  | 37.6865 | 28.385 | منجز | No
2200221163 | شركة المياه الوطنية / منطقة عسير | إشراف | ذات اولوية عالية وعاجلة | 45781000 | 2289050 | 44273243.93 | 42321872.5 | 4030283265 | لا | 0 |  | جاري | التكلفة المفوترة | 97.92 | 89.9 | 2019-08-21 | 2022-07-19 | 2022-07-19 | 2022-07-19 |  |  |  |  | 42.5012 | 18.2097 | خدمات عامة | No
2200221174 | شركة المياه الوطنية / منطقة عسير | تصميم | ذات اولوية عالية | 5040000 | 252000 | 2730672 | 2730672 | 1010322448 | لا | 0 | 191101180468 | جاري | التكلفة المفوترة | 0 | 100 | 2020-12-13 | 2021-10-05 | 2021-10-05 | 2021-10-05 |  |  |  |  | 42.0534 | 18.5474 | Failed | No
2100194202 | أمانة / جدة | تشييد | ذات اولوية عالية | 19779900 | 988995 | 18472207.47 | 5193842.82 | 4030140655 | لا | 0 | 200909006425 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 98 | 100 | 2020-08-20 | 2020-12-16 | 2021-05-25 | 2021-05-25 | 2020-12-16 |  |  |  | 39.1677 | 21.5008 | منجز | No
2100089073 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 13649190.43 | 682459.5215 | 12284901.13 | 12284901.13 | 2050008923 | لا | 0 |  | جاري | التكلفة المفوترة | 90 | 100 | 2011-11-16 | 2013-11-05 | 2017-10-24 | 2017-10-24 |  |  | ضعف كفاءة المقاول الفنية |  | 50.5225 | 26.3731 | Failed | No
2100077906 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | دراسات هندسية | ذات اولوية عالية وعاجلة | 14486080 | 724304 | 8072394.63 | 8072394.63 | 2051059585 | لا | 0 | 180701018895 | جاري | تكلفة العمل المنجز | 29 | 90 | 2018-12-05 | 2023-12-04 | 2023-12-04 | 2023-12-04 |  |  |  | أخرى | 49.5755 | 26.9511 | خدمات عامة | No
2100076053 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | دراسات هندسية | ذات اولوية عالية وعاجلة | 26800000 | 1340000 | 12722648.81 | 12722648.81 | 1010326184 | لا | 0 | 180401001660 | جاري | تكلفة العمل المنجز | 45 | 90 | 2018-10-14 | 2023-10-13 | 2023-10-13 | 2023-10-13 |  |  |  | أخرى | 49.5587 | 26.9727 | خدمات عامة | No
2100202683 | شركة المياه الوطنية / منطقة نجران | تشييد | ذات اولوية عالية وعاجلة | 29920804.93 | 1496040.2465 | 17866064.26 | 17866064.26 | 5950005891 | لا | 0 | 180709023354 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 94.5 | 2020-10-17 | 2022-07-30 | 2021-11-28 | 2021-11-28 | 2022-07-30 |  |  |  | 44.2526 | 17.5636 | منجز | No
2200221815 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 134976736 | 6748836.8 | 37861617.1 | 37861617.1 | 4030151328 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 60 | 74 | 2020-01-20 | 2021-06-07 | 2023-06-30 | 2023-06-30 |  |  |  | أخرى | 39.2981 | 21.4298 | متأخر | No
2100017382 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 20101425 | 1005071.25 | 15515811.87 | 15515408 | 2050017509 | لا | 0 |  | جاري | التكلفة المفوترة | 90 | 100 | 2010-07-30 | 2012-07-19 | 2020-10-02 | 2020-10-02 |  |  | ضعف كفاءة المقاول الفنية |  | 50.599 | 26.3387 | Failed | No
2100198623 | وزارة الحرس الوطني / وكالة الشؤون الفنية | تحديث وتوريد | ذات اولوية متوسطة | 898750.3 | 44937.515 | 0 | 0 | 1010257074 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 0 | 100 | 2021-09-29 | 2022-03-24 | 2022-03-24 | 2022-03-24 |  |  |  |  | 43.9846 | 26.3255 | مسحوب | No
2100089530 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 12149366 | 607468.3 | 4865436 | 4865436 | 1132000522 | لا | 0 |  | جاري | التكلفة المفوترة | 51 | 100 | 2013-07-15 | 2015-07-05 | 2022-11-10 | 2022-11-10 |  |  | ضعف كفاءة المقاول الفنية |  | 43.9875 | 26.0873 | Failed | No
2100018756 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2201835.6 | 110091.78 | 0 | 0 | 1010045486 | لا | 0 |  | جاري | التكلفة المفوترة | 0 | 100 | 2015-07-29 | 2017-04-19 | 2023-05-17 | 2023-05-17 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.1677 | 21.5008 | Failed | No
2100190761 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية وعاجلة | 59462580.45 | 2973129.0225 | 0 | 0 | 1010012911 | لا | 0 | 200301168083 | ايقاف كلي | منهجية القيمة المكتسبة | 0 | 21.24 | 2020-12-26 | 2022-12-05 | 2023-07-02 | 2023-07-02 |  |  |  |  | 43.986 | 26.3537 | Failed | No
2100191133 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية وعاجلة | 7020000 | 351000 | 1970272 | 1970272 | 5850031989 | لا | 0 | 200401012148 | ايقاف كلي | منهجية القيمة المكتسبة | 57.9 | 100 | 2020-09-06 | 2021-09-01 | 2022-06-30 | 2022-06-30 |  |  |  |  | 42.1551 | 17.7263 | Failed | No
2100013182 | أمانة / الحدود الشمالية | تشييد | ذات اولوية متوسطة | 238770 | 11938.5 | 238770 | 238770 | 3450003520 | لا | 0 | 191201108423 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-05-25 | 2019-11-22 | 2019-11-22 | 2019-11-22 | 2019-11-22 |  |  |  | 41.0599 | 30.968 | منجز | No
2100066566 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 2072440 | 103622 | 1209000 | 1209000 | 2511004747 | لا | 0 | 200309139786 | مسحوب | منهجية القيمة المكتسبة | 70 | 70 | 2014-06-22 | 2014-12-20 | 2022-01-01 | 2022-01-01 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0515 | 30.9653 | مسحوب | No
2100066651 | أمانة / العاصمة المقدسة | أخرى | ذات اولوية متوسطة | 2667193.5 | 133359.675 | 2466149.49 | 2466149.49 | 4031073602 | لا | 0 | 5046260 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 75 | 75 | 2014-12-25 | 2016-12-02 | 2019-09-05 | 2019-09-05 | 2016-12-02 |  |  |  | 40.0106 | 21.9916 | منجز | No
2100027661 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 12419036 | 620951.8 | 7723532 | 7723532 | 3450002829 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 70 | 100 | 2012-11-03 | 2015-11-04 | 2020-07-01 | 2020-07-01 | 2015-11-04 |  | ضعف كفاءة المقاول الفنية |  | 41.0487 | 30.9718 | منجز | No
2100022540 | وزارة الصحة / الحدود الشمالية | تشييد | لم تعد تحتاجها الجهة | 4194220 | 209711 | 4192680 | 4192680 | 3450100657 | لا | 0 | 200309122640 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-12-24 | 2020-06-19 | 2021-06-17 | 2021-06-17 | 2020-06-19 |  | سوء التخطيط الاولي للمشروع |  | 41.0085 | 30.9751 | منجز | No
2100000092 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 1410675 | 70533.75 | 1410675 | 1410675 | 4031195955 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-09-29 | 2020-02-27 | 2020-07-23 | 2020-07-23 | 2020-02-27 |  | ضعف كفاءة المقاول الفنية |  |  |  | منجز | No
2200212446 | المؤسسة العامة للحبوب | تصميم وتشييد | ذات اولوية عالية | 397440 | 19872 | 380270 | 380270 | 3400117491 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2021-12-01 | 2022-09-16 | 2022-10-02 | 2022-10-02 | 2022-09-16 |  |  |  | 39.3409 | 29.8606 | منجز | No
2100047854 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 1218000 | 60900 | 577531.5 | 577531.5 | 3450010724 | لا | 0 |  | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 98 | 100 | 2020-01-15 | 2020-06-14 | 2023-05-28 | 2023-05-28 |  |  | ضعف كفاءة المقاول الفنية |  | 40.9542 | 30.9885 | منتظم | No
2100033596 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 1298980 | 64949 | 1363929 | 1216929 | 4603102229 | لا | 0 | 190201015847 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-09-20 | 2020-03-20 | 2020-03-19 | 2020-03-19 | 2020-03-20 |  | ضعف كفاءة المقاول الفنية |  | 41.053 | 19.5377 | منجز | No
2100032421 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 3843630 | 192181.5 | 1420721.6 | 1420721.6 | 3550022647 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 40 | 100 | 2010-08-25 | 2011-08-20 | 2020-06-12 | 2020-06-12 |  |  | ضعف كفاءة المقاول الفنية |  | 42.8415 | 21.2585 | مسحوب | No
2100043470 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 31000000 | 1550000 | 13347043.2 | 3410000 | 5950010109 | لا | 0 | 181109350194 | ايقاف كلي | تكلفة العمل المنجز | 78 | 78 | 2018-03-11 | 2020-02-29 | 2020-08-06 | 2020-08-06 |  |  | ضعف كفاءة المقاول الفنية |  | 40.4526 | 21.278 | Failed | No
2100074620 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 4959198.3 | 247959.915 | 4959198.3 | 4959198.3 | 4032003067 | لا | 0 |  | جاري | تكلفة العمل المنجز | 100 | 100 | 2019-12-29 | 2020-12-28 | 2021-02-16 | 2021-02-16 |  |  | اخرى |  |  |  | Failed | No
2100048285 | أمانة / جازان | تشييد | ذات اولوية عالية وعاجلة | 999888 | 49994.4 | 999888 | 999888 | 1010214056 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-02-20 | 2019-11-17 | 2020-02-20 | 2020-02-20 | 2019-11-17 |  | اخرى |  | 42.8233 | 16.4148 | منجز | No
2100046034 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 3942225 | 197111.25 | 3766415.6 | 3766415.6 | 5901011058 | لا | 0 | 190201022160 | منجز – استلام ابتدائي | اخرى | 96 | 100 | 2019-01-06 | 2019-11-27 | 2021-04-15 | 2021-04-15 | 2019-11-27 |  | ضعف كفاءة المقاول الفنية |  | 42.5898 | 16.8916 | منجز | No
2100067546 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 7389500 | 369475 | 6379600.49 | 6379600.49 | 1010179017 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-11-03 | 2021-10-23 | 2023-07-01 | 2023-07-01 | 2021-10-23 |  | ضعف كفاءة المقاول الفنية |  | 43.7395 | 28.7608 | منجز | No
2100076845 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1928650 | 96432.5 | 1928650 | 1928650 | 5855027156 | لا | 0 | 190809106353 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-02-17 | 2020-02-12 | 2020-02-12 | 2020-02-12 | 2020-02-12 |  | ضعف كفاءة المقاول الفنية |  | 42.8469 | 21.2532 | منجز | No
2100050422 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 1688663 | 84433.15 | 1654404 | 1654404 | 4030212516 | لا | 0 | 190309021338 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-09-16 | 2019-09-16 | 2020-11-29 | 2020-11-29 | 2019-09-16 |  | ضعف كفاءة المقاول الفنية |  | 40.8634 | 20.4217 | منجز | No
2100094614 | أمانة / الطائف | تشييد | ذات اولوية عالية | 2198610 | 109930.5 | 2198610 | 2198610 | 4030006066 | لا | 0 | 190309003037 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-08-16 | 2016-08-10 | 2016-08-10 | 2016-08-10 | 2016-08-10 |  | ضعف كفاءة المقاول الفنية |  | 42.8496 | 21.2549 | منجز | No
2100014770 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 9199998 | 459999.9 | 3208039 | 3208039 | 1010196247 | لا | 0 | 181109373930 | فسخ العقد | الكميات التي تم تركيبها | 24.3 | 100 | 2015-10-02 | 2019-10-17 | 2019-10-17 | 2019-10-17 |  |  | اخرى |  | 42.5619 | 18.2374 | مسحوب | No
2100076366 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 984000 | 49200 | 984000 | 984000 | 3451001151 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-10-03 | 2019-06-20 | 2019-06-27 | 2019-06-27 | 2019-06-20 |  |  |  | 38.6746 | 31.6542 | منجز | No
2100025255 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 310800 | 15540 | 68250 | 68250 | 2066002549 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 23 | 100 | 2019-09-15 | 2020-03-13 | 2020-12-21 | 2020-12-21 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5497 | 25.3991 | مسحوب | No
2100101264 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 329999304 | 16499965.2 | 193499594.44 | 193499594.44 | 4030198340 | لا | 0 | 180709032404 | جاري | منهجية القيمة المكتسبة | 97.5 | 100 | 2012-05-19 | 2015-05-19 | 2023-01-31 | 2023-01-31 |  |  | ضعف كفاءة المقاول الفنية |  | 38.1942 | 23.9999 | منتظم | No
2100004465 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 166246090.4 | 8312304.52 | 119370658.21 | 98687551.67 | 1010046644 | لا | 0 |  | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2011-05-17 | 2013-05-06 | 2022-12-31 | 2022-12-31 |  |  | ضعف كفاءة المقاول الفنية | أخرى | 49.5604 | 25.3897 | Failed | No
2100093483 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 4327300 | 216365 | 4326323.36 | 3893234.36 | 1010158780 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99.98 | 100 | 2019-10-17 | 2021-10-17 | 2021-06-21 | 2021-06-21 | 2021-10-17 |  | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100053421 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 2008622.4 | 100431.12 | 1134984 | 1134984 | 4031055866 | لا | 914488 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 90 | 100 | 2018-05-16 | 2019-08-03 | 2022-07-01 | 2022-07-01 | 2019-08-03 |  | تأخرصرف المستحقات المالية |  | 44.3129 | 29.1548 | منجز | No
2100021416 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 84788000 | 4239400 | 82744563 | 82744563 | 1010127437 | لا | 0 | 190309093739 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2014-05-25 | 2017-05-25 | 2019-07-01 | 2019-07-01 | 2017-05-25 |  |  |  | 41.0655 | 30.9678 | منجز | No
2100014206 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 4017496.1 | 200874.805 | 3103945.5 | 3103945.5 | 5950013363 | لا | 0 | 180709020961 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 91.39 | 100 | 2015-04-20 | 2021-03-31 | 2022-09-11 | 2022-09-11 | 2021-03-31 |  |  |  | 44.2415 | 17.5568 | منجز | No
2100000173 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية وعاجلة | 2526860 | 126343 | 2526860 | 2526860 | 1010354377 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2018-10-10 | 2019-06-12 | 2019-10-26 | 2019-10-26 | 2019-06-12 | [5 empty] | منجز | No
2100043702 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية وعاجلة | 9433055 | 471652.75 | 8641775 | 8641775 | 1010319823 | لا | 0 | 181009183384 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-06-03 | 2019-11-16 | 2019-11-14 | 2019-11-14 |  | 2019-11-16 | لا يوجد تأخير |  | 45.2591 | 25.2379 | منجز | No
2100060900 | أمانة / حفر الباطن | تشييد | ذات اولوية متوسطة | 19962000 | 998100 | 19962000 | 19962000 | 1010136405 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-04-26 | 2017-04-15 | 2019-04-17 | 2019-04-17 | 2017-04-15 |  | تأخرصرف المستحقات المالية |  | 45.9627 | 28.3784 | منجز | No
2100013613 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 6733496 | 336674.8 | 4142952 | 3545769 | 1010376749 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 53 | 100 | 2015-02-07 | 2017-01-26 | 2017-01-26 | 2017-01-26 |  |  | ضعف كفاءة المقاول الفنية |  | 39.5425 | 24.5851 | مسحوب | No
2100194622 | أمانة / جدة | توريد وتركيب | ذات اولوية متوسطة | 1241688 | 62084.4 | 1090655.99 | 1090655.99 | 4030162068 | لا | 0 | 200709044092 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2020-04-12 | 2021-09-25 | 2021-09-05 | 2021-09-05 | 2021-09-25 |  |  |  | 41.358 | 18.7633 | منجز | No
2100043186 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 27894288.94 | 1394714.447 | 24660610.13 | 22606632.11 | 1010224491 | لا | 0 | 181109309335 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 97.69 | 100 | 2015-03-04 | 2017-08-05 | 2019-10-27 | 2019-10-27 |  | 2017-08-05 | لا يوجد تأخير |  | 47.1615 | 25.5646 | منجز | No
2100194493 | أمانة / جدة | تشييد | ذات اولوية عالية وعاجلة | 95253144 | 4762657.2 | 87169561 | 87169561 | 4030034104 | لا | 0 | 191001210113 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-06-21 | 2021-09-21 | 2022-02-23 | 2022-02-23 | 2021-09-21 |  |  |  | 39.2935 | 21.5538 | منجز | No
2100203173 | جامعة الملك سعود | توريد وتركيب | ذات اولوية متوسطة | 1655581.67 | 82779.0835 | 701675.15 | 701675.15 | 1010004413 | لا | 0 | 210309060951 | ايقاف كلي | الكميات التي تم تركيبها | 50 | 50 | 2020-06-29 | 2021-03-31 | 2022-05-31 | 2022-05-31 |  |  |  | أخرى | 46.2732 | 24.4714 | Failed | No
2100194600 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 1987540 | 99377 | 2051243.22 | 985026.11 | 4030152625 | لا | 0 | 200309169344 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-11-28 | 2021-05-28 | 2021-09-30 | 2021-09-30 | 2021-05-28 |  |  |  | 41.5083 | 18.7746 | منجز | No
2100100656 | أمانة / الطائف | إشراف | ذات اولوية متوسطة | 2478600 | 123930 | 2269717.74 | 2269717.74 | 4030281454 | لا | 0 | 180909086767 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-01-29 | 2021-01-28 | 2021-01-28 | 2021-01-28 | 2021-01-28 |  |  |  | 40.4135 | 21.2804 | منجز | No
2100072564 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية عالية | 120303707 | 6015185.35 | 99436573.9 | 99436573.9 | 1010220868 | لا | 0 | 181009116647 | منجز – استلام نهائي | التكلفة المفوترة | 83.82 | 83.82 | 2018-04-21 | 2021-04-21 | 2021-04-21 | 2021-04-21 | 2021-04-21 | 2021-04-24 | اخرى |  | 39.8807 | 21.3699 | منجز | No
2100043820 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 70989999 | 3549499.95 | 21032283.2 | 21032283.2 | 2050001910 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 30 | 77 | 2017-12-20 | 2021-06-17 | 2024-01-17 | 2024-01-17 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.5622 | 24.5323 | مسحوب | No
2100078186 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 2576920 | 128846 | 2333394.78 | 2333394.78 | 1010219753 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 96.07 | 100 | 2018-10-08 | 2019-04-08 | 2019-08-20 | 2019-08-20 |  | 2019-04-08 | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100047305 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 2301000 | 115050 | 1570030 | 1570030 | 1010158252 | لا | 0 | 181001178497 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-10-08 | 2019-10-03 | 2020-05-13 | 2020-05-13 | 2019-10-03 |  |  |  | 41.0303 | 30.9674 | منجز | No
2100015960 | وزارة المالية - الحرمين | إشراف | ذات اولوية عالية وعاجلة | 3979159917 | 200000000 | 3053400207.3 | 3053400207.3 | 1010076578 | لا | 0 |  | جاري | مدفوعات ساعات العمل | 11 | 100 | 2014-02-05 | 2018-02-04 | 2024-11-16 | 2024-11-16 |  |  | اخرى |  | 39.6107 | 24.4675 | خدمات عامة | No
2100036470 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 2996090 | 149804.5 | 241734 | 241734 | 4031053186 | لا | 0 |  | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 9.03 | 9.03 | 2015-10-04 | 2016-09-22 | 2016-09-22 | 2016-09-22 |  |  |  |  | 39.3654 | 21.8755 | Failed | No
2100024334 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 2577012.75 | 128850.6375 | 2577012.75 | 2577012.75 | 1010364056 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2018-11-25 | 2019-10-09 | 2019-10-09 | 2019-10-09 | 2019-10-09 |  |  |  | 39.9608 | 21.3345 | منجز | No
2100034845 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية عالية | 19255289.87 | 962764.4935 | 1216715 | 1216715 | 4031041927 | لا | 0 | 181109342858 | جاري | الكميات التي تم تركيبها | 6.79 | 6.79 | 2019-07-14 | 2022-10-19 | 2022-12-14 | 2022-12-14 |  |  |  |  | 39.8575 | 21.3877 | منتظم | No
2100091932 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 746214 | 37310.7 | 341964 | 341964 | 3453003188 | لا | 0 | 200209133172 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-11-14 | 2020-11-13 | 2021-03-01 | 2021-03-01 | 2020-11-13 |  | اخرى |  | 43.1405 | 29.8511 | منجز | No
2100055016 | وزارة الخارجية | إشراف | لم تعد تحتاجها الجهة | 4976500 | 248825 | 2616012.5 | 0 | 1010325199 | لا | 0 | 180709034771 | فسخ العقد | مدفوعات ساعات العمل | 13 | 100 | 2015-01-06 | 2017-12-01 | 2017-12-01 | 2017-12-01 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | -15.985 | 18.0413 | مسحوب | Yes
2100081546 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 1098279 | 54913.95 | 469854 | 469854 | 5951000765 | لا | 0 | 181209477572 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-07-22 | 2020-07-10 | 2020-10-07 | 2020-10-07 | 2020-07-10 |  | اخرى |  | 44.2378 | 17.5565 | منجز | No
2100099201 | أمانة / الباحة | دراسة الجدوى | ذات اولوية متوسطة | 10548000 | 527400 | 10548000 | 10020600 | 1010326770 | لا | 0 | 181001116938 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 95 | 100 | 2018-10-17 | 2021-10-02 | 2021-10-02 | 2021-10-02 | 2021-10-02 |  | اخرى |  |  |  | منجز | No
2100195554 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 2730375 | 136518.75 | 979044.15 | 787353.18 | 5911007999 | لا | 0 | 200309071290 | مسحوب | الكميات التي تم تركيبها | 42 | 100 | 2019-01-10 | 2020-07-10 | 2021-02-25 | 2021-02-25 |  |  |  |  | 38.9277 | 22.8284 | مسحوب | No
2100091523 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 26696830 | 1334841.5 | 0 | 0 | 1113000601 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 36.01 | 100 | 2019-04-24 | 2022-03-21 | 2023-02-16 | 2023-02-16 |  |  |  |  | 45.8935 | 25.2846 | Failed | No
2100031135 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1474194 | 73709.7 | 42072 | 0 | 1113000601 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 61 | 100 | 2015-07-29 | 2016-10-21 | 2021-06-22 | 2021-06-22 |  |  | ضعف كفاءة المقاول الفنية |  | 45.5246 | 25.0961 | مسحوب | Yes
2100069580 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 19922300 | 996115 | 18329013.89 | 18329013.89 | 3450003821 | لا | 0 | 181009218111 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-11-01 | 2019-09-27 | 2021-08-01 | 2021-08-01 | 2019-09-27 |  |  |  | 41.0179 | 30.9642 | منجز | No
2100072041 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 7397345.75 | 369867.2875 | 2224324.1 | 2224324.1 | 5950013363 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 43 | 100 | 2015-03-01 | 2016-02-18 | 2016-02-18 | 2016-02-18 |  |  | ضعف كفاءة المقاول الفنية |  | 44.2154 | 17.5615 | مسحوب | No
2100049825 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 12807000 | 640350 | 12447392 | 12447392 | 1010082460 | لا | 0 | 190509020114 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2014-11-19 | 2020-09-26 | 2021-09-26 | 2021-09-26 | 2020-09-26 |  |  |  | 38.6721 | 31.6702 | منجز | No
2100042910 | الهيئة العامة للطيران المدني | تشييد | ذات اولوية عالية | 22968000 | 1148400 | 7120000 | 7120000 | 4650010903 | لا | 0 | 200101069377 | مسحوب | تكلفة العمل المنجز | 40 | 100 | 2017-01-03 | 2017-12-22 | 2017-12-22 | 2017-12-22 |  |  | منازعات قائمة |  | 49.5871 | 25.3882 | مسحوب | No
2100026935 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4681050 | 234052.5 | 2835736.6 | 0 | 1111000356 | لا | 0 |  | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 84 | 100 | 2014-04-19 | 2015-07-13 | 2022-11-30 | 2022-11-30 |  |  | ضعف كفاءة المقاول الفنية |  | 46.29 | 24.4547 | Failed | Yes
2100090322 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 3053266.94 | 152663.347 | 1264806 | 1264806 | 1010164501 | لا | 0 |  | مسحوب | التكلفة المفوترة | 41 | 100 | 2017-04-25 | 2018-04-20 | 2021-03-25 | 2021-03-25 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6103 | مسحوب | No
2100034112 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 8187500 | 409375 | 8187500 | 8187500 | 3450000664 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-08-25 | 2020-08-19 | 2020-12-01 | 2020-12-01 | 2020-08-19 |  | ضعف كفاءة المقاول الفنية |  | 41.0752 | 30.9365 | منجز | No
2100064212 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 5893875 | 294693.75 | 1511550 | 1511550 | 5950012580 | لا | 0 | 210501030518 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-07-03 | 2020-01-03 | 2021-10-25 | 2021-10-25 | 2020-01-03 |  | اخرى |  | 44.0559 | 17.5994 | منجز | No
2100027823 | أمانة / الحدود الشمالية | تشييد | ذات اولوية متوسطة | 639900 | 31995 | 639900 | 639900 | 3453002120 | لا | 0 | 190201028228 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-11-15 | 2019-07-12 | 2019-12-07 | 2019-12-07 | 2019-07-12 |  |  |  | 41.0104 | 31.0014 | منجز | No
2100062591 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 3251030 | 162551.5 | 1822958 | 1822958 | 5950020964 | لا | 0 | 210601172735 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 69 | 100 | 2014-04-29 | 2020-10-15 | 2020-10-15 | 2020-10-15 | 2020-10-15 |  | ضعف كفاءة المقاول الفنية |  | 44.7429 | 17.5496 | منجز | No
2100062731 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 77652185.16 | 3882609.258 | 69886966.64 | 69886966.64 | 3555000709 | لا | 0 |  | جاري | تكلفة العمل المنجز | 90 | 100 | 2019-01-21 | 2022-01-21 | 2023-07-31 | 2023-07-31 |  |  | ضعف كفاءة المقاول الفنية |  | 39.5817 | 24.5601 | متأخر | No
2100065914 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 904280 | 45214 | 779589 | 779589 | 5950010119 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 96 | 100 | 2019-06-17 | 2021-06-16 | 2021-10-20 | 2021-10-20 | 2021-06-16 |  | اخرى |  | 44.2471 | 17.5634 | منجز | No
2100036875 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 7364000 | 368200 | 2075514 | 2075514 | 4031045724 | لا | 0 | 180909106288 | جاري | تكلفة العمل المنجز | 27.5 | 27.5 | 2015-11-25 | 2018-04-28 | 2020-11-24 | 2020-11-24 |  |  |  | أخرى | 39.8729 | 21.3797 | Failed | No
2100096106 | أمانة / جدة | توريد وتركيب | ذات اولوية متوسطة | 13786676 | 689333.8 | 13786676.4 | 13786676.4 | 1010051584 | لا | 0 | 210809175043 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2020-01-16 | 2021-01-15 | 2021-01-15 | 2021-01-15 | 2021-01-15 |  | اخرى |  | 39.1715 | 21.5049 | منجز | No
2100028011 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 7408275 | 370413.75 | 6979935.6 | 6979935.6 | 4030044382 | لا | 0 | 190301009837 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 94.22 | 94.22 | 2019-05-15 | 2021-04-22 | 2021-07-21 | 2021-07-21 |  |  |  |  | 39.8514 | 21.3777 | Failed | No
2100042943 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 1606683 | 80334.15 | 1328797.06 | 1328797.06 | 5950005663 | نعم | 454878.51 | 190601019023 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-12-05 | 2020-11-23 | 2020-11-23 | 2020-11-23 |  | 2020-11-23 | تصاريح أعمال التنفيذ |  | 47.3078 | 24.1522 | منجز | No
2100078120 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 12714817.89 | 635740.8945 | 9958333.84 | 9394159.9 | 1010222168 | لا | 0 | 181109298841 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99.37 | 100 | 2014-09-14 | 2017-08-11 | 2021-06-09 | 2021-06-09 | 2017-08-11 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 45.8688 | 25.2426 | منجز | No
2100110316 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية | 1174797398.36 | 58739869.918 | 23835026.69 | 23835026.69 | 1010609431 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 4.68 | 97.7 | 2015-01-08 | 2018-12-17 | 2025-12-15 | 2025-12-15 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.8606 | 21.3342 | Failed | No
2100058866 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 1163400 | 58170 | 329700 | 329700 | 1010018550 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 80 | 100 | 2020-02-02 | 2020-07-31 | 2021-08-09 | 2021-08-09 | 2020-07-31 |  | ضعف كفاءة المقاول الفنية |  | 43.7351 | 28.7624 | منجز | No
2100195473 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 5985352 | 299267.6 | 5338326.29 | 5338326.29 | 5907024458 | لا | 0 | 200701098887 | جاري | الكميات التي تم تركيبها | 90 | 90 | 2020-11-14 | 2022-11-05 | 2022-11-05 | 2022-11-05 |  |  |  |  | 41.4713 | 20.0217 | متأخر | No
2100036105 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية عالية | 35591151 | 1779557.55 | 31766245 | 31766245 | 4030044382 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 89.25 | 89.25 | 2013-02-20 | 2015-08-21 | 2017-06-17 | 2017-06-17 | 2015-08-21 |  | نزع الملكيات |  | 39.8929 | 21.3896 | منجز | No
2100107402 | هيئة تطوير منطقة المدينة المنورة | تشييد | ذات اولوية عالية | 107503754.4 | 5375187.72 | 107503754.4 | 107503754.4 | 4030034104 | لا | 0 | 190309060468 | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2018-10-31 | 2020-10-30 | 2021-10-27 | 2021-10-27 | 2020-10-30 | 2022-01-31 | ضعف كفاءة المقاول الفنية |  | 39.5676 | 24.4817 | منجز | No
2100093833 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 43672400 | 2183620 | 37272787.69 | 33138859.16 | 1010012911 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 85.35 | 100 | 2016-02-22 | 2018-02-22 | 2020-06-03 | 2020-06-03 |  | 2018-02-22 | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100048506 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 2588020 | 129401 | 2588020 | 2588020 | 3453002636 | لا | 141980 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-08-04 | 2020-07-29 | 2020-12-01 | 2020-12-01 | 2020-07-29 |  | ضعف كفاءة المقاول الفنية |  | 43.7375 | 28.7629 | منجز | No
2100076182 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 2663500 | 133175 | 1777500 | 1777500 | 2511004747 | لا | 0 |  | مسحوب | منهجية القيمة المكتسبة | 71 | 71 | 2015-08-13 | 2015-10-29 | 2022-01-01 | 2022-01-01 |  |  | ضعف كفاءة المقاول الفنية |  | 44.317 | 29.1479 | مسحوب | No
2100026003 | أمانة / جدة | دراسات هندسية | ذات اولوية متوسطة | 1050000 | 52500 | 1050000 | 1050000 | 4650047424 | لا | 0 | 200101061162 | منجز – استلام نهائي | اخرى | 99 | 99 | 2020-02-11 | 2020-11-03 | 2020-11-03 | 2020-11-03 | 2020-11-03 | 2021-04-26 | اخرى |  | 39.1673 | 21.5131 | منجز | No
2100178360 | وزارة الثقافة | تشييد | ذات اولوية عالية | 73775278.82 | 3688763.941 | 52938243.02 | 49516172.11 | 1010044893 | لا | 0 | 201009174099 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 98 | 100 | 2017-04-26 | 2020-03-25 | 2021-12-31 | 2021-12-31 | 2020-03-25 | 2021-05-28 |  |  | 43.992 | 26.0923 | منجز | No
2100008783 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 77072335.17 | 3853616.7585 | 29419113.33 | 24069253.22 | 1010034808 | لا | 0 | 180709019777 | ايقاف كلي | تكلفة العمل المنجز | 59 | 95 | 2014-11-17 | 2017-04-20 | 2026-12-31 | 2026-12-31 |  |  | تأخرصرف المستحقات المالية |  | 46.0942 | 24.4578 | Failed | No
2100058645 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 29296560 | 1464828 | 5183328 | 5183328 | 1010233677 | لا | 0 |  | مسحوب | منهجية القيمة المكتسبة | 22.43 | 100 | 2012-10-07 | 2015-09-05 | 2025-04-13 | 2025-04-13 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 44.8241 | 26.3046 | مسحوب | No
2100032082 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 3818720 | 190936 | 3248567.99 | 3248567.99 | 1010239020 | نعم | 4439506.5 | 190601019291 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 95.35 | 100 | 2019-10-24 | 2021-04-07 | 2021-09-01 | 2021-09-01 | 2021-04-07 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 46.2928 | 24.4781 | منجز | No
2100051925 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 16082735 | 804136.75 | 102523.51 | 0 | 1116005202 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 98.38 | 100 | 2014-08-28 | 2016-08-17 | 2020-01-16 | 2020-01-16 | 2016-08-17 |  | ضعف كفاءة المقاول الفنية |  | 46.6727 | 24.7082 | منجز | Yes
2100073603 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 9024045 | 451202.25 | 431289.44 | 431289.44 | 1010052618 | لا | 0 |  | جاري | التكلفة المفوترة | 12 | 100 | 2013-08-21 | 2015-05-13 | 2023-06-15 | 2023-06-15 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | Failed | No
2100027683 | أمانة / الحدود الشمالية | تشييد | ذات اولوية متوسطة | 527450 | 26372.5 | 527450 | 527450 | 1131031178 | لا | 0 | 190301056836 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-01-20 | 2020-01-15 | 2020-01-13 | 2020-01-13 | 2020-01-15 |  |  |  | 43.7357 | 28.7665 | منجز | No
2100100833 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 733713.75 | 36685.6875 | 357800 | 357800 | 4034000979 | لا | 0 | 190901160686 | فسخ العقد | تكلفة العمل المنجز | 55 | 100 | 2019-07-03 | 2019-12-31 | 2022-01-01 | 2022-01-01 |  |  |  |  | 41.627 | 21.202 | مسحوب | No
2100062963 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3098175 | 154908.75 | 1589690 | 0 | 1114000037 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 84.55 | 100 | 2015-02-23 | 2016-05-18 | 2021-06-06 | 2021-06-06 | 2016-05-18 |  | ضعف كفاءة المقاول الفنية |  | 46.6843 | 24.7075 | منجز | Yes
2100093166 | أمانة / جازان | تشييد | ذات اولوية عالية | 10080210 | 504010.5 | 7618154 | 7618154 | 1131020873 | لا | 0 | 180809061404 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-08-21 | 2020-01-19 | 2021-08-05 | 2021-08-05 | 2020-01-19 |  | ضعف كفاءة المقاول الفنية |  | 42.6175 | 16.9512 | منجز | No
2100062720 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 438210 | 21910.5 | 256010 | 0 | 1010258205 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 93.67 | 51 | 2018-12-26 | 2019-12-21 | 2019-12-21 | 2019-12-21 | 2019-12-21 |  |  |  | 45.4661 | 25.6075 | منجز | Yes
2100062764 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1154040 | 57702 | 42149 | 0 | 1010359390 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 26 | 100 | 2015-09-29 | 2016-12-22 | 2019-09-06 | 2019-09-06 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6837 | 24.7181 | مسحوب | Yes
2100054821 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 684605 | 34230.25 | 615385 | 615385 | 4032027280 | لا | 0 | 181001140878 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-08-07 | 2019-08-02 | 2019-07-04 | 2019-07-04 | 2019-08-02 |  |  |  | 40.8313 | 20.729 | منجز | No
2100014081 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 888350 | 44417.5 | 390450 | 390450 | 3450011559 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 65 | 65 | 2019-12-09 | 2021-09-22 | 2023-05-29 | 2023-05-29 |  |  | ضعف كفاءة المقاول الفنية | مخطط لسحبه وإعادة ترسيته | 41.0622 | 30.9411 | منتظم | No
2100065800 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 701300 | 35065 | 134320 | 134320 | 4032027280 | لا | 0 | 200209133495 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 97 | 100 | 2019-07-30 | 2020-04-25 | 2021-11-03 | 2021-11-03 | 2020-04-25 |  |  |  | 40.8294 | 20.7265 | منجز | No
2100064562 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1282500 | 64125 | 903743 | 903743 | 4035001647 | لا | 0 | 200709004530 | فسخ العقد | تكلفة العمل المنجز | 66 | 100 | 2015-08-05 | 2016-07-30 | 2022-06-30 | 2022-06-30 |  |  | تأخرصرف المستحقات المالية |  | 40.8294 | 20.7262 | مسحوب | No
2100013090 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 2843070 | 142153.5 | 661660 | 661660 | 4031046917 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 24 | 100 | 2011-10-18 | 2012-10-12 | 2022-01-01 | 2022-01-01 |  |  | ضعف كفاءة المقاول الفنية |  | 42.8475 | 21.2544 | مسحوب | No
2100012213 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 4889000 | 244450 | 3079653.35 | 0 | 4036000789 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 60 | 100 | 2010-10-24 | 2011-10-19 | 2022-01-01 | 2022-01-01 |  |  | ضعف كفاءة المقاول الفنية |  | 42.8407 | 21.2552 | مسحوب | Yes
2100195834 | الهيئة العامة للزكاة والدخل | ترميم | ذات اولوية عالية | 7176000 | 358800 | 1200000 | 1200000 | 1010261568 | لا | 0 |  | منجز – استلام نهائي | تكلفة العمل المنجز | 70 | 70 | 2021-08-18 | 2021-12-29 | 2022-02-17 | 2022-02-17 |  | 2021-12-29 |  |  | 39.5677 | 24.4913 | منجز | No
2100073043 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية منخفضة | 101847000 | 5092350 | 101847000 | 101847000 | 1010185409 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2010-07-17 | 2012-12-17 | 2019-06-02 | 2019-06-02 | 2012-12-17 | 2020-07-14 |  |  | 41.0787 | 19.1279 | منجز | No
2100037155 | أمانة / الحدود الشمالية | تشييد | ذات اولوية متوسطة | 26706585.25 | 1335329.2625 | 23832585.25 | 23832585.25 | 1011010795 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 90 | 100 | 2015-02-03 | 2018-01-19 | 2023-05-28 | 2023-05-28 |  |  |  | تم إنذار المقاول كتابيا | 43.516 | 29.6217 | متأخر | No
2100075202 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 26551456.2 | 1327572.81 | 645506.19 | 645506.19 | 1010013977 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 2 | 100 | 2016-04-05 | 2018-03-14 | 2021-09-09 | 2021-09-09 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6175 | 24.4835 | مسحوب | No
2100066625 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 3111234 | 155561.7 | 3220559.31 | 3220559.31 | 2057002826 | لا | 0 | 190309055070 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-01-06 | 2020-03-23 | 2020-03-22 | 2020-03-22 | 2020-03-23 |  | ضعف كفاءة المقاول الفنية |  | 41.3028 | 18.9727 | منجز | No
2100014711 | أمانة / الحدود الشمالية | تشييد | ذات اولوية متوسطة | 2464850 | 123242.5 | 2464850 | 2464850 | 3452007023 | لا | 0 | 190409101508 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-09-03 | 2019-03-27 | 2019-05-30 | 2019-05-30 | 2019-03-27 |  | ضعف كفاءة المقاول الفنية |  | 38.6532 | 31.6716 | منجز | No
2100102874 | أمانة / نجران | تحديث وتوريد | ذات اولوية متوسطة | 14751600 | 737580 | 13315260 | 13315260 | 1010076578 | لا | 0 |  | جاري | تكلفة العمل المنجز | 99 | 100 | 2018-07-31 | 2021-11-23 | 2023-03-31 | 2023-03-31 |  |  | اخرى |  | 44.2476 | 17.5656 | منتظم | No
2100032351 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 7311681.88 | 365584.094 | 3126475 | 3126475 | 5950006647 | لا | 0 | 200609010929 | ايقاف كلي | تكلفة العمل المنجز | 51 | 74.62 | 2019-06-09 | 2020-09-08 | 2022-12-08 | 2022-12-08 |  |  |  |  | 44.2309 | 17.5598 | Failed | No
2100090366 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 622135.45 | 31106.7725 | 622135.45 | 622135.45 | 4030152625 | لا | 0 | 211109093777 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-01-16 | 2021-01-14 | 2021-01-14 | 2021-01-14 | 2021-01-14 |  | اخرى |  | 41.6377 | 19.5853 | منجز | No
2100031500 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 779985 | 38999.25 | 690272 | 690272 | 5950026666 | لا | 0 | 181209477572 | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2018-08-12 | 2019-08-02 | 2019-08-03 | 2019-08-03 | 2019-08-02 |  |  |  | 44.2321 | 17.5527 | منجز | No
2100100682 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 22111900.62 | 1105595.031 | 19830250.1 | 19830250.1 | 5950010109 | لا | 0 | 200609154524 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 98 | 100 | 2014-12-11 | 2016-12-24 | 2022-05-31 | 2022-05-31 | 2016-12-24 |  |  |  | 40.4123 | 21.2548 | منجز | No
2100195790 | الهيئة العامة للزكاة والدخل | ترميم | ذات اولوية عالية | 2798781 | 139939.05 | 1500000 | 1500000 | 1010195496 | لا | 0 |  | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2021-05-06 | 2021-08-03 | 2021-08-08 | 2021-08-08 |  | 2021-08-03 |  |  | 46.7136 | 24.656 | منجز | No
2100009866 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2351325 | 117566.25 | 495644 | 0 | 1123002179 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 33.18 | 1 | 2015-07-28 | 2017-01-18 | 2017-01-19 | 2017-01-19 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 46.6823 | 24.7019 | Failed | Yes
2100068331 | أمانة / جازان | تشييد | لم تعد تحتاجها الجهة | 4540000 | 227000 | 4539999.99 | 4539999.99 | 5850023439 | لا | 0 | 180809053491 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-10-07 | 2020-03-16 | 2020-12-03 | 2020-12-03 | 2020-03-16 |  | ضعف كفاءة المقاول الفنية |  | 42.5872 | 16.8809 | منجز | No
2100014140 | أمانة / جازان | تشييد | ذات اولوية عالية | 15938231 | 796911.55 | 649839.2 | 649839.2 | 1010168646 | لا | 0 | 181109306428 | مسحوب | الكميات التي تم تركيبها | 14 | 100 | 2015-10-20 | 2017-04-11 | 2019-04-23 | 2019-04-23 |  |  | ضعف كفاءة المقاول الفنية |  | 42.8352 | 16.9658 | مسحوب | No
2100108662 | وزارة التعليم | تشييد | لم تعد تحتاجها الجهة | 3889748 | 194487.4 | 0 | 0 | 1116004478 | لا | 0 |  | مسحوب | التكلفة المفوترة | 7 | 100 | 2017-11-28 | 2018-11-23 | 2021-02-04 | 2021-02-04 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | مسحوب | No
2100072671 | أمانة / جازان | تشييد | ذات اولوية عالية | 899695 | 44984.75 | 371502.5 | 371502.5 | 5903015063 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 40 | 100 | 2013-05-24 | 2014-05-09 | 2016-04-06 | 2016-04-06 |  |  | تأخرصرف المستحقات المالية |  | 42.5395 | 17.2685 | مسحوب | No
2100092783 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 2098580 | 104929 | 579794 | 579794 | 2511004747 | لا | 0 |  | مسحوب | منهجية القيمة المكتسبة | 28 | 28 | 2014-09-03 | 2015-11-28 | 2022-01-12 | 2022-01-12 |  |  | ضعف كفاءة المقاول الفنية |  | 44.3411 | 29.1315 | مسحوب | No
2100058472 | وزارة التعليم | تشييد | لم تعد تحتاجها الجهة | 12978541 | 648927.05 | 60548 | 60548 | 1010233904 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 3 | 100 | 2011-10-02 | 2013-12-08 | 2013-12-08 | 2013-12-08 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 46.7098 | 24.6275 | مسحوب | No
2100003496 | وزارة التعليم | تشييد | ذات اولوية عالية | 9421608 | 471080.4 | 9421608 | 9421608 | 1010081451 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2013-10-27 | 2018-09-20 | 2018-10-07 | 2018-10-07 | 2018-09-20 |  |  |  | 46.7098 | 24.6275 | منجز | No
2100057466 | وزارة الشـؤون الاسلامية والدعوة والارشاد | تشييد | ذات اولوية عالية | 1765845 | 88292.25 | 1765845 | 1765844 | 5901015279 | لا | 0 | 181101312083 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-03-27 | 2019-03-16 | 2019-09-16 | 2019-09-16 | 2019-03-16 |  |  |  | 42.606 | 16.8885 | منجز | No
2100004012 | وزارة التعليم | تشييد | ذات اولوية عالية | 17039808.02 | 851990.401 | 2086395.94 | 2086395.94 | 1010142553 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 15 | 100 | 2014-11-24 | 2018-06-03 | 2018-06-03 | 2018-06-03 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | مسحوب | No
2100033703 | أمانة / الباحة | تشييد | ذات اولوية عالية وعاجلة | 1228000 | 61400 | 531050 | 0 | 5802010434 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 65 | 63 | 2019-08-22 | 2021-05-03 | 2023-02-01 | 2023-02-01 |  |  | سوء التخطيط الاولي للمشروع | تم تمديد الجدول الزمني | 41.057 | 20.2337 | منتظم | Yes
2100000022 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية وعاجلة | 2373105 | 118655.25 | 2232795.68 | 2232795.68 | 1010096983 | لا | 0 |  | جاري | تكلفة العمل المنجز | 100 | 100 | 2019-08-09 | 2021-09-07 | 2021-09-07 | 2021-09-07 |  |  |  |  | 46.8595 | 24.7664 | Failed | No
2100036595 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1825346.82 | 91267.341 | 0 | 0 | 1131040351 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 25 | 75 | 2019-12-15 | 2020-12-09 | 2020-12-09 | 2020-12-09 | 2020-12-09 |  | ضعف كفاءة المقاول الفنية |  | 44.9488 | 26.0491 | منجز | No
2100026703 | أمانة / العاصمة المقدسة | إشراف | ذات اولوية متوسطة | 4857500 | 242875 | 4580153 | 4580153 | 2050003582 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2018-02-11 | 2020-02-10 | 2021-07-05 | 2021-07-05 | 2020-02-10 | 2020-02-17 | اخرى |  | 39.8151 | 21.4153 | منجز | No
2100107170 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2442092 | 122104.6 | 1643109 | 1643109 | 1010249051 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2016-01-26 | 2017-05-20 | 2022-01-29 | 2022-01-29 | 2017-05-20 |  |  |  | 45.2591 | 25.2379 | منجز | No
2100017080 | وزارة التعليم | تشييد | ذات اولوية عالية | 10637425.62 | 531871.281 | 4850667.76 | 3257402 | 1010051817 | لا | 0 |  | مسحوب | التكلفة المفوترة | 38 | 100 | 2014-02-05 | 2016-01-26 | 2016-10-22 | 2016-10-22 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7533 | 24.8268 | مسحوب | No
2100003415 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 59395519.05 | 2969775.9525 | 27661237.87 | 26030831.33 | 1010233574 | لا | 0 | 180709020783 | ايقاف كلي | تكلفة العمل المنجز | 66 | 95 | 2014-12-04 | 2017-02-11 | 2025-12-31 | 2025-12-31 |  |  | تأخرصرف المستحقات المالية |  | 46.6237 | 24.4815 | Failed | No
2100107645 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 3603503.93 | 180175.1965 | 3603503.93 | 3603503.93 | 1011009563 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-04-27 | 2016-04-18 | 2019-09-11 | 2019-09-11 | 2016-04-18 |  |  |  | 47.3078 | 24.1522 | منجز | No
2100065671 | وزارة الشـؤون الاسلامية والدعوة والارشاد | دراسة بيئية | ذات اولوية عالية | 2085600 | 104280 | 17658.45 | 17658.45 | 4031066930 | لا | 0 | 180801045618 | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2018-02-01 | 2020-01-30 | 2019-03-17 | 2019-03-17 | 2020-01-30 |  |  |  | 42.5617 | 16.8878 | منجز | No
2100099610 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 7013772 | 350688.6 | 4080265.4 | 4080265.4 | 4650052854 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 58 | 100 | 2014-10-22 | 2016-06-03 | 2021-09-08 | 2021-09-08 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6008 | 24.493 | مسحوب | No
2100003791 | وزارة التعليم | تشييد | ذات اولوية عالية | 11174773.73 | 558738.6865 | 8201918.45 | 7571341.93 | 1010081451 | لا | 0 |  | مسحوب | التكلفة المفوترة | 75 | 100 | 2014-10-14 | 2016-10-03 | 2019-07-02 | 2019-07-02 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7213 | 24.7585 | مسحوب | No
2100004594 | وزارة التعليم | تشييد | ذات اولوية عالية | 10922073.36 | 546103.668 | 10922073.36 | 10922073.36 | 1010081451 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2013-10-28 | 2019-07-13 | 2019-07-13 | 2019-07-13 | 2019-07-13 |  |  |  | 46.7098 | 24.6275 | منجز | No
2100033515 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 65433291.59 | 3271664.5795 | 18408628.99 | 17871062.72 | 1010095105 | لا | 0 | 180709019253 | ايقاف كلي | تكلفة العمل المنجز | 54 | 100 | 2014-09-13 | 2016-08-13 | 2025-12-31 | 2025-12-31 |  |  | تأخرصرف المستحقات المالية |  | 45.3915 | 25.8998 | Failed | No
2100064341 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية عالية وعاجلة | 31012011.5 | 1550600.575 | 22718127.97 | 22718127.97 | 1010276314 | لا | 0 | 181109343482 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2012-10-10 | 2015-09-07 | 2018-05-25 | 2018-05-25 | 2015-09-07 |  |  |  | 40.8386 | 20.1606 | منجز | No
2100017216 | وزارة التعليم | تشييد | ذات اولوية عالية | 4924241 | 246212.05 | 4107463 | 4107463 | 1010300402 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-09-17 | 2017-02-06 | 2017-02-06 | 2017-02-06 | 2017-02-06 |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | منجز | No
2100029260 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 84224438.45 | 4211221.9225 | 59799351.3 | 59799351.3 | 3555000709 | لا | 0 |  | جاري | تكلفة العمل المنجز | 71 | 80 | 2018-12-24 | 2023-10-23 | 2023-10-23 | 2023-10-23 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.5651 | 24.5389 | متأخر | No
2100023144 | جامعة الملك سعود | إشراف | ذات اولوية متوسطة | 3160000 | 158000 | 1545600 | 1545600 | 2252004545 | لا | 0 | 181201546519 | جاري | تكلفة العمل المنجز | 75 | 100 | 2018-06-26 | 2019-10-19 | 2022-04-03 | 2022-04-03 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال | تم إنذار المقاول كتابيا |  |  | خدمات عامة | No
2100043411 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 4434425 | 221721.25 | 286234.2 | 286157.2 | 1010267848 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 6 | 100 | 2015-07-27 | 2017-01-08 | 2017-01-09 | 2017-01-09 |  |  | ضعف كفاءة المقاول الفنية |  | 39.555 | 24.5307 | مسحوب | No
2100003636 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | تشييد | ذات اولوية عالية وعاجلة | 5936999.4 | 296849.97 | 458913.6 | 458913.6 | 1010156573 | لا | 0 | 180901081884 | مسحوب | تكلفة العمل المنجز | 7 | 100 | 2019-01-21 | 2020-07-14 | 2023-12-31 | 2023-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 47.3078 | 24.1522 | مسحوب | No
2100030682 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 2288916 | 114445.8 | 2288916 | 2288916 | 4653001234 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-05-19 | 2022-04-14 | 2022-04-14 | 2022-04-14 | 2022-04-14 |  |  |  | 39.5671 | 24.5441 | منجز | No
2100055694 | هيئة الهلال الأحمر السعودي | تشييد | ذات اولوية عالية | 1134497.7 | 56724.885 | 1080474 | 1080474 | 1010277656 | لا | 0 | 190401001122 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-02-11 | 2019-05-12 | 2021-05-31 | 2021-05-31 | 2019-05-12 |  | اخرى |  | 39.9864 | 21.3414 | منجز | No
2100019261 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 12746446 | 637322.3 | 11447121 | 11447121 | 1010158252 | لا | 0 | 190909096171 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2015-11-04 | 2017-10-24 | 2020-11-15 | 2020-11-15 | 2017-10-24 |  |  |  | 43.5254 | 29.6501 | منجز | No
2100048300 | أمانة / الحدود الشمالية | تشييد | ذات اولوية متوسطة | 4845225 | 242261.25 | 3756876 | 3756876 | 3450006687 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 90 | 90 | 2011-08-08 | 2012-08-02 | 2020-06-01 | 2020-06-01 | 2012-08-02 |  | ضعف كفاءة المقاول الفنية |  | 41.0262 | 30.9793 | منجز | No
2100083230 | أمانة / حائل | تشييد | ذات اولوية عالية | 439300 | 21965 | 301000 | 301000 | 3350022221 | لا | 0 | 190401050178 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-12-26 | 2019-12-19 | 2019-12-21 | 2019-12-21 | 2019-12-19 |  |  |  | 42.364 | 27.9137 | منجز | No
2100003382 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 7156547.04 | 357827.352 | 3853808.74 | 3853808.74 | 1116007562 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 80 | 100 | 2013-10-29 | 2015-10-19 | 2021-12-12 | 2021-12-12 | 2015-10-19 |  | ضعف كفاءة المقاول الفنية |  | 45.975 | 28.4334 | منجز | No
2100049324 | أمانة / الجوف | تشييد | ذات اولوية عالية وعاجلة | 48283850 | 2414192.5 | 42949094.9 | 42949094.9 | 3400011750 | لا | 0 | 190401032163 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-05-24 | 2021-11-09 | 2023-01-31 | 2023-01-31 | 2021-11-09 |  |  |  | 40.1138 | 29.8681 | منجز | No
2100032222 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية عالية | 8549999.92 | 427499.996 | 6964289.12 | 6964289.12 | 1010090968 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 97.04 | 97.04 | 2015-11-15 | 2017-05-15 | 2019-04-12 | 2019-04-12 | 2017-05-15 |  | تأخرصرف المستحقات المالية |  | 39.8696 | 21.3331 | منجز | No
2100095723 | المؤسسة العامة للتقاعد | تشييد | ذات اولوية عالية | 14455666 | 722783.3 | 13755666.05 | 13755666.05 | 4030201114 | لا | 10358639.45 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2015-05-27 | 2020-04-30 | 2021-11-30 | 2021-11-30 |  | 2020-04-30 | ضعف كفاءة المقاول الفنية |  | 39.1345 | 21.7231 | منجز | No
2100061736 | شركة المياه الوطنية / منطقة الحدود الشمالية | تشييد | ذات اولوية عالية | 19800000 | 990000 | 19800000 | 16926623.59 | 1010158252 | لا | 0 | 190609069220 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-07-04 | 2020-06-12 | 2021-02-11 | 2021-02-11 | 2020-06-12 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.2515 | 30.3541 | منجز | No
2100002752 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 4770050 | 238502.5 | 4219218 | 4219218 | 4650021867 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 88 | 100 | 2018-03-24 | 2021-04-25 | 2021-09-30 | 2021-09-30 | 2021-04-25 |  | ضعف كفاءة المقاول الفنية |  | 39.5765 | 24.5222 | منجز | No
2100015606 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 10217641.92 | 510882.096 | 3017149 | 3017148.77 | 1010072637 | لا | 0 | 190209015832 | مسحوب | التكلفة المفوترة | 60 | 100 | 2016-01-26 | 2017-07-19 | 2022-08-20 | 2022-08-20 |  |  | ضعف كفاءة المقاول الفنية |  | 42.0529 | 18.5228 | مسحوب | No
2100008551 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 123048319.92 | 6152415.996 | 123048319.92 | 123048319.92 | 1010185409 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-11-12 | 2020-11-06 | 2020-11-06 | 2020-11-06 | 2020-11-06 |  | أوامر تغيير |  |  |  | منجز | No
2100009494 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 8731175.86 | 436558.793 | 1062627.5 | 0 | 1010006362 | لا | 0 |  | مسحوب | التكلفة المفوترة | 12 | 100 | 2013-06-01 | 2015-02-21 | 2023-05-10 | 2023-05-10 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | مسحوب | Yes
2200223090 | أمانة / جدة | إشراف | ذات اولوية عالية | 37956453 | 1897822.65 | 0 | 0 | 1010610727 | لا | 0 | 210701127185 | جاري | الكميات التي تم تركيبها | 52.5 | 52.5 | 2022-01-03 | 2023-12-12 | 2023-12-12 | 2023-12-12 |  |  |  |  | 39.1677 | 21.5007 | خدمات عامة | No
2100042792 | مستشفى الملك فيصل التخصصي ومركز الأبحاث | تشييد | ذات اولوية عالية | 2078036 | 103901.8 | 1809109.86 | 1730286.1 | 1010011428 | لا | 0 | 181109334522 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-08-07 | 2018-08-01 | 2021-10-19 | 2021-10-19 | 2018-08-01 |  | موافقات |  | 46.6763 | 24.6711 | منجز | No
2100017695 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 10177069 | 508853.45 | 6739637.75 | 6739637.75 | 4030052981 | لا | 0 |  | جاري | التكلفة المفوترة | 78 | 100 | 2014-04-22 | 2016-04-11 | 2022-04-05 | 2022-04-05 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | Failed | No
2100011362 | رئاسة أمن الدولة / ديوان رئاسة أمن الدولة | تشييد | ذات اولوية عالية وعاجلة | 18233275.25 | 911663.7625 | 18233275.25 | 18020846.88 | 1010243700 | لا | 0 | 190601027976 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-07-25 | 2020-07-23 | 2021-11-30 | 2021-11-30 | 2020-07-23 |  | أوامر تغيير |  |  |  | منجز | No
2100062893 | جامعة بيشة | تشييد | ذات اولوية متوسطة | 499800 | 24990 | 499800 | 499800 | 4650051477 | لا | 0 | 200401010497 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2020-05-05 | 2020-10-02 | 2020-10-22 | 2020-10-22 | 2020-10-02 |  |  |  | 41.9397 | 19.7642 | منجز | No
2100203700 | وزارة الصحة/ الاحساء | ترميم | ذات اولوية متوسطة | 4090324 | 204516.2 | 1041642.7 | 678120.56 | 2050064138 | لا | 0 | 220309187587 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 66 | 33 | 2020-10-18 | 2021-06-17 | 2023-03-01 | 2023-03-01 |  |  |  |  | 49.5641 | 25.3592 | Failed | No
2100066684 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 1150704 | 57535.2 | 1150704 | 1150704 | 1011012161 | لا | 0 | 181209479374 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-09-02 | 2021-08-17 | 2021-12-12 | 2021-12-12 | 2021-08-17 |  |  |  | 49.0078 | 23.2619 | منجز | No
2100092772 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 645800 | 32290 | 676552.38 | 676552.38 | 4030198598 | لا | 0 | 191009029902 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-02-13 | 2020-01-20 | 2021-09-14 | 2021-09-14 | 2020-01-20 |  | اخرى |  | 40.2797 | 20.1518 | منجز | No
2100093236 | أمانة / جازان | تشييد | ذات اولوية عالية | 1598055 | 79902.75 | 1598055 | 1598055 | 1010162003 | لا | 0 | 181001159509 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-10-30 | 2019-10-25 | 2019-10-26 | 2019-10-26 | 2019-10-25 |  | اخرى |  | 42.6094 | 16.9554 | منجز | No
2100019062 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 11460614.31 | 573030.7155 | 6574259.06 | 0 | 3350003498 | لا | 0 |  | جاري | التكلفة المفوترة | 83 | 100 | 2011-10-02 | 2013-09-21 | 2022-02-02 | 2022-02-02 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | متأخر | Yes
2100081686 | أمانة / عسير | تشييد | ذات اولوية عالية وعاجلة | 6999665 | 349983.25 | 2673244 | 1605859 | 5860019265 | لا | 0 |  | جاري | تكلفة العمل المنجز | 92 | 100 | 2019-09-16 | 2020-09-11 | 2023-03-31 | 2023-03-31 |  |  |  |  | 42.2741 | 18.214 | Failed | No
2100043584 | أمانة / عسير | تشييد | ذات اولوية عالية | 892175 | 44608.75 | 278610 | 278610 | 5855035453 | لا | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 62 | 100 | 2013-05-26 | 2023-04-04 | 2023-04-04 | 2023-04-04 |  |  | أوامر سامية |  | 42.6734 | 18.5798 | Failed | No
2100037100 | أمانة / عسير | تشييد | ذات اولوية عالية | 1594000 | 79700 | 0 | 0 | 5855066033 | لا | 0 |  | جاري | تكلفة العمل المنجز | 86 | 100 | 2015-09-30 | 2016-09-30 | 2022-02-16 | 2022-02-16 |  |  | أوامر سامية |  | 43.2986 | 19.0858 | Failed | No
2100075036 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 898800 | 44940 | 0 | 0 | 5950019270 | لا | 0 | 220601025060 | مسحوب | تكلفة العمل المنجز | 0 | 0 | 2015-01-19 | 2016-01-09 | 2016-06-09 | 2016-06-09 |  |  | تأخرصرف المستحقات المالية |  | 44.2182 | 17.5362 | مسحوب | No
2100001993 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 9775579.6 | 488778.98 | 8195268 | 7810921.22 | 1010089371 | لا | 0 |  | مسحوب | التكلفة المفوترة | 90 | 100 | 2013-04-13 | 2015-04-04 | 2022-09-15 | 2022-09-15 |  |  | ضعف كفاءة المقاول الفنية |  | 37.2091 | 26.6936 | مسحوب | No
2100012493 | أمانة / عسير | تشييد | ذات اولوية عالية | 2498320 | 124916 | 0 | 0 | 5859005834 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-06-26 | 2020-06-26 | 2020-06-21 | 2020-06-21 | 2020-06-26 |  | ضعف كفاءة المقاول الفنية |  | 42.2746 | 18.2149 | منجز | No
2100065435 | أمانة / عسير | تشييد | ذات اولوية عالية | 14912415 | 745620.75 | 3717972 | 3717972 | 5850016183 | لا | 0 | 200909168581 | جاري | تكلفة العمل المنجز | 46 | 86 | 2018-12-09 | 2019-12-04 | 2023-03-31 | 2023-03-31 |  |  |  |  | 42.5096 | 18.2205 | Failed | No
2100099820 | مستشفى الملك فيصل التخصصي ومركز الأبحاث | الخدمات الاستشارية | ذات اولوية عالية | 88794425 | 4439721.25 | 84307068 | 84307068 | 4030216250 | لا | 0 | 180709022424 | جاري | تكلفة العمل المنجز | 95 | 100 | 2009-12-01 | 2012-11-15 | 2024-09-01 | 2024-09-01 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.1726 | 21.7434 | خدمات عامة | No
2100024146 | مستشفى الملك فيصل التخصصي ومركز الأبحاث | تشييد | ذات اولوية عالية وعاجلة | 107439269.92 | 5371963.496 | 70355477.54 | 56284382.01 | 1010085518 | لا | 0 | 190101006882 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-01-15 | 2020-01-09 | 2021-12-31 | 2021-12-31 | 2020-01-09 |  | أوامر سامية |  | 46.679 | 24.6705 | منجز | No
2100012655 | أمانة / جازان | تشييد | ذات اولوية عالية | 2145990 | 107299.5 | 0 | 0 | 5855037618 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-10-05 | 2020-09-29 | 2000-01-01 | 2021-02-07 | 2020-09-29 |  |  |  | 42.6915 | 18.5931 | منجز | No
2100026983 | أمانة / عسير | تشييد | ذات اولوية عالية | 1632415 | 81620.75 | 1463745 | 1463745 | 5856006665 | لا | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 63 | 100 | 2012-07-05 | 2023-04-04 | 2023-04-04 | 2023-04-04 |  |  | أوامر سامية |  | 42.6742 | 18.5697 | Failed | No
2100085341 | هيئة المدن الصناعية ومناطق التقنية | إشراف | ذات اولوية متوسطة | 108903500 | 5445175 | 92972073 | 90905307 | 1010937612 | لا | 0 |  | جاري | التكلفة المفوترة | 85 | 85 | 2019-02-10 | 2023-01-12 | 2023-07-12 | 2023-07-12 |  |  | لا يوجد تأخير |  | 46.6802 | 24.7057 | خدمات عامة | No
2100008982 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | تشييد | ذات اولوية عالية | 29455043.49 | 1472752.1745 | 9365902.6 | 9365902.6 | 1010409973 | لا | 0 | 181201400062 | ايقاف كلي | تكلفة العمل المنجز | 57 | 100 | 2019-02-12 | 2022-05-11 | 2023-12-31 | 2023-12-31 |  |  | تأخرصرف المستحقات المالية |  | 50.105 | 26.444 | Failed | No
2100008120 | وزارة الخارجية | تشييد | لم تعد تحتاجها الجهة | 71594143 | 3579707.15 | 26464745.4 | 26464745.4 | 0 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 55 | 100 | 2015-03-25 | 2017-03-25 | 2020-04-15 | 2020-04-15 |  |  | ضعف كفاءة المقاول الفنية |  | -7.9969 | 12.6011 | مسحوب | No
2100090252 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 3053266.94 | 152663.347 | 1778088.7 | 1778088.7 | 1010164501 | لا | 0 |  | مسحوب | التكلفة المفوترة | 58 | 100 | 2015-02-18 | 2016-02-13 | 2021-04-08 | 2021-04-08 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.5902 | مسحوب | No
2100076101 | أمانة / عسير | تشييد | ذات اولوية عالية | 3250004 | 162500.2 | 386000 | 386000 | 5858010028 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 20 | 100 | 2015-02-18 | 2016-02-19 | 2021-01-20 | 2021-01-20 |  |  | تأخرصرف المستحقات المالية |  | 43.5266 | 17.6578 | مسحوب | No
2100080916 | أمانة / عسير | تشييد | ذات اولوية عالية | 6972805 | 348640.25 | 1610406 | 1610406 | 5860019265 | لا | 0 | 190509000176 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-12-19 | 2019-12-19 | 2023-06-30 | 2023-06-30 |  |  | أوامر تغيير |  | 42.2752 | 18.2148 | Failed | No
2100030446 | أمانة / عسير | تشييد | ذات اولوية عالية وعاجلة | 1266411 | 63320.55 | 0 | 0 | 5856556542 | لا | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 0 | 100 | 2015-08-05 | 2023-04-04 | 2023-04-04 | 2023-04-04 |  |  | أوامر سامية |  | 42.6891 | 18.5786 | Failed | No
2100006532 | وزارة الموارد البشرية والتنمية الإجتماعية | تشييد | ذات اولوية منخفضة | 15795945 | 789797.25 | 14786285.11 | 14786285.11 | 1010231996 | لا | 0 | 181109280744 | جاري | الكميات التي تم تركيبها | 92 | 100 | 2018-02-06 | 2021-07-29 | 2021-12-31 | 2021-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5364 | 18.2245 | Failed | No
2100095955 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 282737136.66 | 14136856.833 | 252121409.01 | 252121409.01 | 2055014114 | لا | 0 | 180809049246 | جاري | منهجية القيمة المكتسبة | 88 | 98 | 2017-06-11 | 2020-06-07 | 2024-01-01 | 2024-01-01 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 49.5648 | 27.1019 | متأخر | No
2100100380 | وزارة الخارجية | إشراف | ذات اولوية عالية | 5797931.25 | 289896.5625 | 4983491.2 | 4983491.2 | 1010464778 | لا | 0 | 190401063789 | جاري | مدفوعات ساعات العمل | 85 | 100 | 2019-08-01 | 2021-08-03 | 2021-04-08 | 2021-04-08 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 32.6228 | 0.23675 | خدمات عامة | No
2100026633 | أمانة / عسير | تشييد | ذات اولوية عالية | 1470010 | 73500.5 | 153155 | 153155 | 5856006665 | لا | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 44 | 100 | 2012-01-14 | 2023-04-04 | 2023-04-04 | 2023-04-04 |  |  | أوامر سامية |  | 42.6928 | 18.5652 | Failed | No
2100098980 | وزارة الموارد البشرية والتنمية الإجتماعية | تشييد | ذات اولوية منخفضة | 20349591.6 | 1017479.58 | 18299850.51 | 18299850.51 | 1010253962 | لا | 0 | 190309001013 | مسحوب | الكميات التي تم تركيبها | 97 | 100 | 2013-03-21 | 2014-11-02 | 2021-09-13 | 2021-09-13 |  |  | ضعف كفاءة المقاول الفنية |  | 40.2107 | 30.0006 | مسحوب | No
2100021836 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تصميم | ذات اولوية عالية وعاجلة | 76908106 | 3845405.3 | 72049141.1 | 72049141.1 | 1010322156 | لا | 0 | 180809058485 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-04-22 | 2019-04-22 | 2020-12-02 | 2020-12-02 | 2019-04-22 |  |  |  | 49.1696 | 27.5041 | منجز | No
2100064035 | وزارة الموارد البشرية والتنمية الإجتماعية | تشييد | ذات اولوية منخفضة | 8413835.61 | 420691.7805 | 7572452.05 | 7572452.05 | 1010028451 | لا | 0 | 180709036989 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-12-23 | 2016-11-30 | 2020-07-06 | 2020-07-06 | 2016-11-30 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 40.2686 | 20.1707 | منجز | No
2100047655 | أمانة / عسير | تشييد | ذات اولوية عالية | 1686695 | 84334.75 | 840426 | 840426 | 5855037652 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 61 | 100 | 2015-05-31 | 2016-05-31 | 2022-03-16 | 2022-03-16 |  |  | أوامر سامية |  | 43.3171 | 19.0961 | مسحوب | No
2100086380 | الجمارك السعودية | تشييد | ذات اولوية عالية | 361866366.45 | 18093318.3225 | 145855080.54 | 145855080.54 | 2051001558 | لا | 0 | 200609052917 | مسحوب | منهجية القيمة المكتسبة | 43 | 100 | 2014-01-08 | 2016-12-05 | 2018-12-13 | 2018-12-13 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 50.7585 | 24.7197 | مسحوب | No
2100055532 | وزارة الموارد البشرية والتنمية الإجتماعية | تشييد | ذات اولوية منخفضة | 11947542 | 597377.1 | 11947542 | 11947542 | 4030010046 | نعم | 8717230.5 | 200109036100 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-07-03 | 2020-07-02 | 2021-12-31 | 2021-12-31 | 2020-07-02 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.5031 | 20.0114 | منجز | No
2100025244 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 9039264.44 | 451963.222 | 0 | 0 | 1010213931 | لا | 0 |  | مسحوب | التكلفة المفوترة | 1 | 33 | 2019-11-06 | 2021-08-06 | 2021-08-17 | 2021-08-17 |  |  | ضعف كفاءة المقاول الفنية |  | 40.0549 | 29.8587 | مسحوب | No
2100015481 | أمانة / الرياض | دراسات هندسية | ذات اولوية عالية | 44908500 | 2245425 | 44908500 | 42663075 | 1010468431 | لا | 0 | 190301002635 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2019-07-01 | 2021-12-31 | 2022-06-30 | 2022-06-30 | 2021-12-31 |  | اخرى |  |  |  | منجز | No
2100104996 | جامعة الإمام محمد بن سعود الاسلامية | تشييد | ذات اولوية متوسطة | 20230000.38 | 1011500.019 | 18194500.97 | 18194500.97 | 1010353173 | لا | 0 | 180909071580 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2011-03-16 | 2012-07-03 | 2018-03-29 | 2018-03-29 | 2012-07-03 |  | لا يوجد تأخير |  | 39.8322 | 23.4846 | منجز | No
2100026025 | أمانة / جازان | تشييد | ذات اولوية عالية | 804280 | 40214 | 656403.87 | 656403.87 | 5907014664 | لا | 0 | 180809062093 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 82 | 82 | 2015-01-06 | 2016-01-02 | 2018-10-02 | 2018-10-02 | 2016-01-02 |  | اخرى |  | 42.6096 | 16.9099 | منجز | No
2100083974 | جامعة الملك سعود | تشييد | ذات اولوية عالية | 109999152 | 5499957.6 | 99102514.67 | 71954127.39 | 1010085518 | لا | 0 | 180901013498 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-01-13 | 2021-01-12 | 2021-01-12 | 2021-01-12 | 2021-01-12 |  | تأخرصرف المستحقات المالية |  | 47 | 26.7317 | منجز | No
2100003721 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية | 49400925 | 2470046.25 | 44467185.5 | 44467185.5 | 5950005816 | لا | 0 | 190601014246 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 99.15 | 99.6 | 2019-07-04 | 2020-01-04 | 2022-05-01 | 2022-05-01 |  |  | لا يوجد تأخير |  | 42.5241 | 17.3714 | Failed | No
2100090156 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 9452813 | 472640.65 | 3445652.38 | 3445652.38 | 1010156720 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 57 | 100 | 2012-09-07 | 2016-12-26 | 2024-05-29 | 2024-05-29 |  |  | ضعف كفاءة المقاول الفنية |  | 45.3525 | 25.8912 | مسحوب | No
2100022960 | جامعة الإمام محمد بن سعود الاسلامية | تشييد | ذات اولوية متوسطة | 18888660 | 944433 | 3578059.4 | 2526315.75 | 5905015155 | نعم | 3578059.4 | 181209447333 | جاري | تكلفة العمل المنجز | 23 | 45 | 2018-08-01 | 2020-07-30 | 2023-09-30 | 2023-09-30 |  |  | تأخرصرف المستحقات المالية |  | 46.7098 | 17.2687 | Failed | No
2100049280 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 1285250 | 64262.5 | 1285250 | 1285250 | 3555000942 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-12-03 | 2019-09-25 | 2019-10-13 | 2019-10-13 | 2019-09-25 |  | اخرى |  | 35.6865 | 27.3504 | منجز | No
2200223204 | أمانة / جدة | تشييد | ذات اولوية عالية | 195071215 | 9753560.75 | 25039656.89 | 25039656.89 | 2050003475 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 34 | 27 | 2022-03-13 | 2024-03-13 | 2024-02-19 | 2024-02-19 |  |  |  |  | 39.1272 | 21.6486 | منتظم | No
2100073975 | أمانة / العاصمة المقدسة | تصميم | ذات اولوية متوسطة | 21580000 | 1079000 | 11952000 | 11952000 | 1010326466 | لا | 0 |  | منجز – استلام نهائي | مدفوعات ساعات العمل | 100 | 100 | 2015-07-31 | 2017-01-28 | 2019-12-25 | 2019-12-25 | 2017-01-28 | 2020-03-10 | تغيرات في نطاق المشروع |  |  |  | منجز | No
2100101220 | مدينة الملك سعود الطبية | تشييد |  | 2860910 | 143045.5 | 0 | 0 | 1010282171 |  | 0 |  | جاري | تكلفة العمل المنجز | 80 | 100 | 2017-11-30 00:59 | 2018-08-30 00:59 |  |  |  |  | اخرى |  | 46.6906 | 24.6282 | Failed | No
2100105442 | جامعة الإمام محمد بن سعود الاسلامية | تشييد | ذات اولوية عالية وعاجلة | 1003989474 | 50199473.7 | 709187397.03 | 701306818 | 1010053925 | لا | 0 | 181209487622 | جاري | اخرى | 80 | 100 | 2011-10-29 | 2012-10-17 | 2023-12-31 | 2023-12-31 |  |  | أوامر تغيير |  | 46.7098 | 24.6275 | Failed | No
2100064713 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 16385565 | 819278.25 | 11797606.8 | 11797606.8 | 4650050716 | لا | 0 |  | ايقاف جزئي | الكميات التي تم تركيبها | 72 | 78 | 2019-07-10 | 2021-11-05 | 2023-03-25 | 2023-03-25 |  |  | ضعف كفاءة المقاول الفنية |  | 39.5516 | 24.4935 | متأخر | No
2100103364 | وزارة التعليم | تشييد | ذات اولوية عالية | 20978226 | 1048911.3 | 2266594 | 2266594 | 1010142553 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 14 | 100 | 2015-08-16 | 2017-12-03 | 2017-12-03 | 2017-12-03 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | مسحوب | No
2100087290 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 20160500 | 1008025 | 15984387 | 15984387 | 1010149483 | لا | 0 | 180809049897 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 98.68 | 100 | 2017-07-25 | 2019-01-08 | 2021-05-03 | 2021-05-03 | 2019-01-08 |  | لا يوجد تأخير |  | 42.1765 | 22.7215 | منجز | No
2100102432 | جامعة الإمام محمد بن سعود الاسلامية | دراسة الجدوى | ذات اولوية متوسطة | 45179526.33 | 2258976.3165 | 31913432.8663 | 31542020.5063 | 1010078921 | لا | 0 | 180909096957 | جاري | اخرى | 80 | 100 | 2011-10-29 | 2012-10-17 | 2023-08-31 | 2023-08-31 |  |  | تغيرات في نطاق المشروع |  | 46.6931 | 24.8098 | خدمات عامة | No
2100092293 | أمانة / حفر الباطن | تشييد | ذات اولوية متوسطة | 7671290 | 383564.5 | 7671285 | 7671285 | 1010019983 | لا | 0 | 0 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-11-06 | 2020-04-29 | 2019-12-18 | 2019-12-18 | 2020-04-29 |  |  |  | 45.9864 | 28.3737 | منجز | No
2100090716 | أمانة / تبوك | تشييد | ذات اولوية عالية | 9356900 | 467845 | 7071745 | 7071745 | 4030243076 | لا | 7071745 | 181101246411 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-03-30 | 2020-07-19 | 2020-09-20 | 2020-09-20 | 2020-07-19 |  |  |  | 37.2604 | 25.0377 | منجز | No
2100029385 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1150990 | 57549.5 | 1150990 | 1150990 | 4032040200 | لا | 0 | 181201409458 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-07-01 | 2019-06-26 | 2019-06-26 | 2019-06-26 | 2019-06-26 |  |  |  | 40.8104 | 20.9475 | منجز | No
2100033832 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 2926423.5 | 146321.175 | 0 | 0 | 4031204093 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 1 | 49 | 2019-01-15 | 2020-12-23 | 2020-12-23 | 2020-12-23 |  |  | ضعف كفاءة المقاول الفنية |  | 39.5708 | 24.5291 | مسحوب | No
2100021324 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 24311736.2 | 1215586.81 | 17691095.6 | 17691095.6 | 2051034972 | لا | 0 | 181209434330 | جاري | منهجية القيمة المكتسبة | 98 | 99 | 2019-11-11 | 2020-08-07 | 2023-03-30 | 2023-03-30 |  |  | التنسيق مع أصحاب المصلحه (خدمات | أخرى |  |  | منتظم | No
2100079332 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية | 4302110 | 215105.5 | 3217341 | 2792698.6 | 5808011381 | لا | 0 | 180301000603 | مسحوب | منهجية القيمة المكتسبة | 86.5 | 100 | 2015-02-12 | 2017-01-21 | 2022-10-30 | 2022-10-30 |  |  | ضعف كفاءة المقاول الفنية |  | 41.2405 | 19.951 | مسحوب | No
2100049383 | أمانة / جازان | تشييد | ذات اولوية عالية | 5590500 | 279525 | 4750037.5 | 4750037.5 | 5901009307 | لا | 0 | 180909095475 | ايقاف كلي | الكميات التي تم تركيبها | 93 | 100 | 2014-11-08 | 2015-11-04 | 2019-12-31 | 2019-12-31 |  |  | اخرى |  | 42.8387 | 16.9542 | Failed | No
2100191881 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 11477900 | 573895 | 9892379.57 | 9892379.57 | 4030196153 | لا | 0 | 190401128305 | جاري | منهجية القيمة المكتسبة | 82.8 | 100 | 2020-06-21 | 2022-05-30 | 2022-07-31 | 2022-07-31 |  |  |  |  | 41.6263 | 21.1963 | متأخر | No
2100099595 | وزارة الصحة / تجمع الشرقية | تحديث وتوريد | ذات اولوية عالية | 2353322 | 117666.1 | 2353322 | 2353322 | 2051040812 | لا | 0 | 191101046411 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-05-19 | 2020-02-19 | 2020-02-19 | 2020-02-19 | 2020-02-19 |  | تصاريح أعمال التنفيذ |  | 50.1008 | 26.4129 | منجز | No
2100097521 | الهيئة الملكية لمدينة الرياض | تشييد | ذات اولوية عالية | 140752874.02 | 7037643.701 | 74530234.1 | 74530234.1 | 1010044185 | لا | 0 | 190209005643 | جاري | الكميات التي تم تركيبها | 75 | 99 | 2018-07-15 | 2020-06-22 | 2023-03-31 | 2023-03-31 |  |  |  |  | 46.6469 | 24.7204 | متأخر | No
2100178426 | وزارة الثقافة | تشييد | ذات اولوية عالية | 14603919.75 | 730195.9875 | 3981788.62 | 3981788.62 | 1010039430 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 57 | 100 | 2019-04-08 | 2021-02-05 | 2021-05-20 | 2021-05-20 |  |  |  |  | 41.733 | 27.4637 | Failed | No
2100038636 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية متوسطة | 61173315.67 | 3058665.7835 | 18661985.4 | 18661985.4 | 1010012911 | لا | 0 | 180709022045 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 98.26 | 100 | 2013-03-02 | 2015-02-09 | 2021-04-12 | 2021-04-12 |  | 2015-02-09 | لا يوجد تأخير |  | 43.9544 | 26.3504 | منجز | No
2100003706 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 54026582.86 | 2701329.143 | 28864297.21 | 24643632.72 | 1010014477 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 77.22 | 100 | 2018-06-20 | 2020-06-20 | 2022-06-20 | 2022-06-20 |  |  | اخرى |  | 46.6443 | 24.6391 | متأخر | No
2100101091 | معهد الإدارة العامة | إشراف | ذات اولوية عالية وعاجلة | 2095632 | 104781.6 | 1849599 | 1849599 | 1010171914 | لا | 0 | 191101250687 | جاري | التكلفة المفوترة | 88 | 70 | 2020-01-02 | 2020-07-02 | 2023-02-02 | 2023-02-02 |  |  |  |  | 39.1557 | 21.601 | خدمات عامة | No
2100192430 | جامعة الملك عبدالعزيز | توريد وتركيب | ذات اولوية متوسطة | 3404054 | 170202.7 | 0 | 0 | 1010055929 | لا | 0 | 200101055401 | جاري | تكلفة العمل المنجز | 15 | 15 | 2019-06-09 | 2020-05-14 | 2023-12-31 | 2023-12-31 |  |  |  |  | 39.2391 | 21.4933 | منتظم | No
2100001536 | جامعة طيبة | تشييد | ذات اولوية عالية | 53722267 | 2686113.35 | 26169510.38 | 26169510.38 | 1010010873 | لا | 0 | 180709036052 | جاري | تكلفة العمل المنجز | 50 | 65.4 | 2012-11-22 | 2019-06-01 | 2024-07-04 | 2024-07-04 |  |  | تغيرات في نطاق المشروع | تم تمديد الجدول الزمني | 39.6005 | 24.4595 | متأخر | No
2100024220 | مستشفى الملك فيصل التخصصي ومركز الأبحاث | تشييد | ذات اولوية عالية وعاجلة | 30948428 | 1547421.4 | 37024466.48 | 25829163.44 | 1010005046 | لا | 0 | 181109316314 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-07-08 | 2019-07-03 | 2021-05-31 | 2021-05-31 | 2019-07-03 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 46.6791 | 24.672 | منجز | No
2100105851 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 41691487 | 2084574.35 | 31230470.54 | 31230470.54 | 1010014477 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 98.86 | 100 | 2018-01-01 | 2020-01-01 | 2021-03-23 | 2021-03-23 | 2020-01-01 |  | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100077022 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 415559050 | 20777952.5 | 375978052.9275 | 375978052.9275 | 1010044185 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 99.75 | 100 | 2019-01-02 | 2021-06-05 | 2023-02-27 | 2023-02-27 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6773 | 24.7094 | منتظم | No
2100001105 | شركة المياه الوطنية / منطقة نجران | تشييد | ذات اولوية عالية | 10331000 | 516550 | 4666252 | 4188708 | 5850002110 | لا | 0 | 191001157055 | جاري | منهجية القيمة المكتسبة | 61.79 | 100 | 2020-06-23 | 2021-06-12 | 2022-01-16 | 2022-01-16 |  |  | لا يوجد تأخير |  | 44.2144 | 18.5404 | Failed | No
2100108754 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2920361.73 | 146018.0865 | 2764312.75 | 2764312.75 | 5805011535 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-08-10 | 2015-08-02 | 2015-08-02 | 2015-08-02 | 2015-08-02 |  | اخرى |  | 41.4779 | 20.0185 | منجز | No
2100189630 | وزارة السياحة | تصميم وتشييد | ذات اولوية عالية وعاجلة | 109441745 | 5472087.25 | 85730977 | 85730977 | 4030138292 | لا | 0 | 201101086086 | جاري | تكلفة العمل المنجز | 99 | 99 | 2020-12-21 | 2022-02-21 | 2022-08-23 | 2022-08-23 |  |  |  |  | 46.6237 | 24.6835 | Failed | No
2100010544 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البرية | تشييد | ذات اولوية متوسطة | 6094341 | 304717.05 | 0 | 0 | 2511006797 | لا | 0 |  | مسحوب | اخرى | 0 | 0 | 2019-09-02 | 2021-03-05 | 2021-03-05 | 2021-03-05 |  |  | ضعف كفاءة المقاول الفنية |  | 50.0917 | 26.4535 | مسحوب | No
2100080146 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 5932110 | 296605.5 | 4734089.39 | 4734089.39 | 1010249593 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 92.36 | 100 | 2019-02-06 | 2020-02-06 | 2020-02-06 | 2020-02-06 |  | 2020-02-06 | لا يوجد تأخير |  | 46.5932 | 24.7295 | منجز | No
2100190971 | شركة المياه الوطنية / منطقة تبوك | إشراف | ذات اولوية عالية | 8035000 | 401750 | 3958458.03 | 3958458.03 | 1010322156 | لا | 0 | 191101339548 | جاري | التكلفة المفوترة | 60 | 60 | 2020-10-01 | 2022-03-31 | 2022-03-01 | 2022-03-01 |  |  |  |  | 36.52 | 28.4202 | خدمات عامة | No
2100068434 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 13393618.23 | 669680.9115 | 12207698 | 12207698 | 4031018104 | لا | 0 | 200309038129 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 74.52 | 74.52 | 2019-09-30 | 2021-09-29 | 2022-02-07 | 2022-02-07 | 2021-09-29 |  |  |  | 39.8845 | 21.3425 | منجز | No
2100038986 | شركة المياه الوطنية / منطقة الجوف | تشييد | ذات اولوية عالية وعاجلة | 69261181.5 | 3463059.075 | 69261181.5 | 69261181.5 | 5855014577 | لا | 0 | 180709024996 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2015-10-05 | 2018-03-10 | 2020-12-06 | 2020-12-06 | 2018-03-10 | 2022-01-12 | لا يوجد تأخير |  | 40.2296 | 29.9353 | منجز | No
2100061810 | وزارة الثقافة | تشييد |  | 1700000 | 85000 | 916909.05 | 916909.05 | 1113001181 |  | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-03-20 00:59 | 2020-01-20 00:59 | 2020-01-20 | 2020-01-20 | 2020-01-20 00:59 |  | لا يوجد تأخير |  |  |  | منجز | No
2100105302 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 4498489.4 | 224924.47 | 3966797.41 | 3966797.41 | 2050047957 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 94.26 | 100 | 2018-02-28 | 2019-08-13 | 2019-12-29 | 2019-12-29 |  | 2019-08-13 | لا يوجد تأخير |  | 49.9726 | 26.5813 | منجز | No
2100208110 | الرئاسة العامة لهيئة الأمر بالمعروف والنهي عن المنكر | تشييد | ذات اولوية عالية | 16837378 | 841868.9 | 11248389.38 | 11248389.38 | 4650032626 | لا | 0 | 201109182148 | جاري | الكميات التي تم تركيبها | 86 | 100 | 2017-10-18 | 2018-10-13 | 2022-11-30 | 2022-11-30 |  |  |  | لم يتم اتخاذ أي إجراء | 39.8888 | 29.8108 | Failed | No
2100011056 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 2689357.5 | 134467.875 | 2084181.19 | 2084181.19 | 2511104587 | لا | 0 |  | جاري | اخرى | 80 | 100 | 2020-08-02 | 2021-01-08 | 2021-03-04 | 2021-03-04 |  |  |  |  | 46.8595 | 24.7664 | Failed | No
2100016295 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية عالية | 29486050 | 1474302.5 | 25550214.14 | 25550214.14 | 4031033277 | لا | 0 |  | جاري | تكلفة العمل المنجز | 90.27 | 90.27 | 2014-01-04 | 2016-03-31 | 2024-04-21 | 2024-04-21 |  |  |  | أخرى | 39.8598 | 21.3516 | Failed | No
2100020646 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 4172470 | 208623.5 | 3729000 | 3729000 | 2511104587 | لا | 0 |  | جاري | اخرى | 85 | 100 | 2019-09-29 | 2020-09-28 | 2020-09-28 | 2020-09-28 | [6 empty] | Failed | No
2100074690 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 58738525 | 2936926.25 | 37985964.41 | 37985964.41 | 1116000094 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 97.78 | 100 | 2012-12-12 | 2014-12-12 | 2019-12-05 | 2019-12-05 | 2014-12-12 |  | لا يوجد تأخير |  | 40.5278 | 21.6543 | منجز | No
2100074734 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 18983800 | 949190 | 18852875.94 | 16983472.84 | 1010227442 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 99.83 | 100 | 2019-03-07 | 2020-09-07 | 2020-08-30 | 2020-08-30 |  | 2020-09-07 | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100068364 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية عالية | 3748949 | 187447.45 | 290708.64 | 290708.64 | 5907010955 | لا | 0 | 190901153045 | جاري | تكلفة العمل المنجز | 7.75 | 7.75 | 2019-10-17 | 2021-09-24 | 2021-12-23 | 2021-12-23 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ | أخرى | 39.8676 | 21.381 | Failed | No
2100009122 | شركة المياه الوطنية / منطقة الحدود الشمالية | تشييد | ذات اولوية عالية | 8410878.79 | 420543.9395 | 7569002.74 | 7569002.74 | 1010306778 | لا | 0 | 190901188554 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-12-22 | 2021-11-30 | 2022-06-30 | 2022-06-30 | 2021-11-30 |  | لا يوجد تأخير |  | 43.5429 | 29.6392 | منجز | No
2100099363 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية وعاجلة | 527790268.5 | 26389513.425 | 331985880.19 | 239679434.52 | 1010012911 | لا | 0 | 200809039016 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 98.91 | 100 | 2014-04-21 | 2017-03-20 | 2021-10-27 | 2021-10-27 | 2017-03-20 |  | لا يوجد تأخير |  | 46.682 | 24.697 | منجز | No
2100024216 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 26949420.11 | 1347471.0055 | 0 | 0 | 2051002769 | لا | 0 |  | مسحوب | منهجية القيمة المكتسبة | 0 | 0 | 2019-01-24 | 2022-01-25 | 2023-01-30 | 2023-01-30 |  |  | ضعف كفاءة المقاول الفنية |  | 49.6626 | 27.0037 | مسحوب | No
2100092374 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 91988637.79 | 4599431.8895 | 43967726.37 | 41918550.99 | 4030179603 | نعم | 45402677.67 | 180709021206 | ايقاف كلي | تكلفة العمل المنجز | 71 | 95 | 2015-06-16 | 2017-06-15 | 2025-12-31 | 2025-12-31 |  |  | تأخرصرف المستحقات المالية |  | 39.3533 | 21.4139 | Failed | No
2200223720 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 42264752.61 | 2113237.6305 | 28602607.98 | 16662663 | 1010054406 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2013-08-19 | 2015-08-09 | 2020-05-28 | 2020-05-28 | 2015-08-09 |  |  |  | 37.3292 | 31.3542 | منجز | No
2100078562 | أمانة / العاصمة المقدسة | دراسة الجدوى | ذات اولوية متوسطة | 4072500 | 203625 | 3820902 | 3820902 | 4030192494 | لا | 0 |  | منجز – استلام نهائي | اخرى | 99.91 | 99.91 | 2018-03-07 | 2021-03-06 | 2021-03-06 | 2021-03-06 | 2021-03-06 | 2021-03-14 | اخرى |  |  |  | منجز | No
2100038662 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 2935215 | 146760.75 | 2598594 | 2598594 | 1010061463 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99.23 | 100 | 2020-03-09 | 2021-07-09 | 2022-02-01 | 2022-02-01 | 2021-07-09 |  | لا يوجد تأخير |  | 46.5441 | 24.693 | منجز | No
2200223764 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 634120482.22 | 31706024.111 | 502420171.56 | 502420171.56 | 1010054406 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2012-04-11 | 2015-03-27 | 2019-12-06 | 2019-12-06 | 2015-03-27 |  |  |  | 44.4269 | 24.5135 | منجز | No
2100036304 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 3147248.76 | 157362.438 | 3147248.76 | 3147248.76 | 5950009015 | لا | 0 | 181009124882 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2017-12-27 | 2019-04-03 | 2019-04-03 | 2019-04-03 | 2019-04-03 |  |  |  | 42.8562 | 21.2513 | منجز | No
2100086925 | شركة المياه الوطنية / منطقة الحدود الشمالية | تشييد | ذات اولوية عالية | 6560000 | 328000 | 4310204.54 | 4310204.54 | 3450006303 | نعم | 0.01 | 200645000383 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 97 | 100 | 2020-05-13 | 2022-04-21 | 2021-11-21 | 2021-11-21 | 2022-04-21 |  | لا يوجد تأخير |  | 38.6491 | 31.7058 | منجز | No
2100007243 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية | 40000000 | 2000000 | 36887086.4 | 36887086.4 | 4031045263 | لا | 0 | 180901083069 | جاري | منهجية القيمة المكتسبة | 100 | 100 | 2018-11-27 | 2021-10-25 | 2022-09-01 | 2022-09-01 |  |  | لا يوجد تأخير |  | 41.2855 | 20.1136 | منتظم | No
2100071046 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 4727226.42 | 236361.321 | 0 | 0 | 1010188602 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0 | 100 | 2005-12-05 | 2007-08-28 | 2023-05-17 | 2023-05-17 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.5429 | 16.8808 | مسحوب | No
2100024710 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية | 258428447.87 | 12921422.3935 | 84671345.48 | 84671345.48 | 1010277276 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 49.45 | 56.51 | 2014-11-25 | 2018-11-03 | 2024-06-30 | 2024-06-30 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.487 | 20.0319 | متأخر | No
2100189921 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية عالية وعاجلة | 21203201.25 | 1060160.0625 | 19050236.92 | 19050236.92 | 1010177101 | لا | 0 | 190909013898 | جاري | تكلفة العمل المنجز | 97 | 100 | 2018-11-01 | 2021-01-05 | 2021-08-22 | 2021-08-22 |  |  |  |  | 44.3927 | 24.4964 | Failed | No
2100108382 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية | 518367209.28 | 25918360.464 | 192155967.17 | 192155967.17 | 1010277276 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 53.53 | 63.24 | 2014-11-25 | 2018-11-03 | 2024-06-30 | 2024-06-30 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.6354 | 18.27 | متأخر | No
2100039863 | مدينة الملك فهد الطبية | تشييد | ذات اولوية عالية | 11500000 | 575000 | 5773103.73 | 5773103.73 | 1010224897 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-09-05 | 2016-05-05 | 2021-12-19 | 2021-12-19 | 2016-05-05 |  |  |  | 46.702 | 24.686 | منجز | No
2100021652 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية | 329825494.99 | 16491274.7495 | 0 | 0 | 1010277276 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 0 | 0.21 | 2014-11-25 | 2018-11-03 | 2024-06-30 | 2024-06-30 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 44.2131 | 17.5614 | منتظم | No
2100070851 | وزارة الحج والعمرة | تشييد | ذات اولوية عالية وعاجلة | 27614119.49 | 1380705.9745 | 9917242.48 | 9917242.48 | 4030168186 | لا | 0 | 190501084475 | جاري | الكميات التي تم تركيبها | 40 | 40 | 2019-10-13 | 2022-12-09 | 2022-09-05 | 2022-09-05 |  |  |  |  | 39.7679 | 21.4155 | Failed | No
2100032756 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 88848723.2 | 4442436.16 | 61175285 | 60514225 | 1010297995 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 74.64 | 100 | 2014-10-14 | 2016-09-21 | 2021-10-25 | 2021-10-25 | 2016-09-21 |  | لا يوجد تأخير |  | 40.4553 | 21.3005 | منجز | No
2100191240 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 11174000 | 558700 | 5246150 | 5246150 | 4031041927 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 90.3 | 100 | 2020-04-16 | 2021-04-15 | 2022-01-25 | 2022-01-25 |  |  |  |  | 39.903 | 21.4035 | Failed | No
2100191310 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية | 26395140 | 1319757 | 6849621.36 | 6849621.36 | 5950005816 | لا | 0 | 190901066121 | جاري | منهجية القيمة المكتسبة | 50 | 100 | 2020-09-22 | 2022-03-17 | 2023-05-31 | 2023-05-31 |  |  |  |  | 42.9815 | 17.1912 | Failed | No
2100039270 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 64808084 | 3240404.2 | 31607744 | 31607744 | 1010010872 | لا | 0 | 200209139321 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 96.5 | 100 | 2013-06-18 | 2015-06-18 | 2023-06-20 | 2023-06-20 |  |  | ضعف كفاءة المقاول الفنية |  | 38.3778 | 23.9235 | Failed | No
2100048344 | أمانة / جدة | تشييد | ذات اولوية عالية | 9439662 | 471983.1 | 1669957.5 | 1454239.37 | 1010187400 | لا | 0 | 181109282818 | ايقاف كلي | تكلفة العمل المنجز | 77 | 100 | 2015-09-17 | 2017-03-17 | 2021-11-01 | 2021-11-01 |  |  | ضعف كفاءة المقاول الفنية |  | 39.1517 | 21.6183 | Failed | No
2100108113 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2251120.79 | 112556.0395 | 1360034.29 | 1360034.29 | 1010307425 | لا | 0 |  | جاري | التكلفة المفوترة | 77 | 100 | 2015-10-04 | 2016-11-27 | 2022-02-10 | 2022-02-10 |  |  | ضعف كفاءة المقاول الفنية |  | 45.313 | 24.0763 | Failed | No
2100002951 | أمانة / عسير | دراسات هندسية | ذات اولوية عالية | 7995750 | 399787.5 | 799575 | 0 | 1010461905 | لا | 0 |  | جاري | تكلفة العمل المنجز | 90 | 100 | 2019-06-12 | 2020-06-06 | 2023-03-31 | 2023-03-31 |  |  | التنسيق مع أصحاب المصلحه (خدمات |  |  |  | خدمات عامة | Yes
2100041333 | وزارة التعليم | تشييد | ذات اولوية عالية | 11933883 | 596694.15 | 4260267 | 2325184 | 1010025363 | لا | 0 | 190409065152 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2013-04-10 | 2017-07-17 | 2021-05-05 | 2021-05-05 | 2017-07-17 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 43.1379 | 18.0853 | منجز | No
2100097064 | جامعة الباحة | تشييد | ذات اولوية عالية | 166135000 | 8306750 | 12901217.18 | 12901217.18 | 4030154193 | لا | 0 | 180709030543 | جاري | الكميات التي تم تركيبها | 52.5 | 96 | 2014-05-14 | 2023-02-11 | 2023-02-11 | 2023-02-11 |  |  |  |  | 21.7806 | 42.0589 | Failed | No
2100190326 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية عالية وعاجلة | 43058668.06 | 2152933.403 | 36891681.41 | 36891681.41 | 4030140033 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-01-16 | 2019-08-30 | 2021-09-09 | 2021-09-09 | 2019-08-30 |  |  |  | 40.2686 | 20.1432 | منجز | No
2100190886 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 939130.2 | 46956.51 | 798260.67 | 798260.67 | 4031059045 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 94.75 | 100 | 2020-12-06 | 2021-06-07 | 2021-06-02 | 2021-06-02 | 2021-06-07 |  |  |  | 39.9076 | 21.4064 | منجز | No
2100191214 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية عالية | 72795077.25 | 3639753.8625 | 19097806.31 | 19097806.31 | 5855007803 | لا | 0 | 200501060568 | جاري | منهجية القيمة المكتسبة | 43.47 | 47.78 | 2020-12-16 | 2022-11-25 | 2023-05-31 | 2023-05-31 |  |  |  |  | 42.188 | 19.1448 | منتظم | No
2100044590 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 1308370 | 65418.5 | 1308370 | 1308370 | 1010246223 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-11-23 | 2021-03-13 | 2021-06-14 | 2021-06-14 | 2021-03-13 |  |  |  | 48.4624 | 27.477 | منجز | No
2100192555 | جامعة الملك عبدالعزيز | توريد وتركيب | ذات اولوية متوسطة | 2798167.05 | 139908.3525 | 2798167.05 | 2798167.05 | 1010055929 | لا | 0 | 191001158283 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-02-17 | 2019-04-21 | 2021-01-25 | 2021-01-25 |  |  |  |  | 38.9603 | 22.7892 | Failed | No
2100042420 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 16198688.56 | 809934.428 | 2085983.16 | 2085983.16 | 1010223860 | لا | 0 | 190209008381 | مسحوب | التكلفة المفوترة | 25 | 100 | 2013-01-27 | 2014-01-28 | 2023-02-01 | 2023-02-01 |  |  | ضعف كفاءة المقاول الفنية |  | 42.4987 | 18.2178 | مسحوب | No
2100030004 | أمانة / الجوف | تشييد | ذات اولوية عالية | 1992659 | 99632.95 | 651340 | 651340 | 3400011214 | لا | 0 | 400170000 | فسخ العقد | الكميات التي تم تركيبها | 33 | 100 | 2015-01-12 | 2016-02-10 | 2021-07-14 | 2021-07-14 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 37.1473 | 31.4806 | مسحوب | No
2100190960 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية عالية | 23158691.13 | 1157934.5565 | 12486281.11 | 12486281.11 | 1010067622 | نعم | 1417624.65 | 200101044770 | جاري | منهجية القيمة المكتسبة | 66.02 | 100 | 2020-09-17 | 2022-03-18 | 2022-12-31 | 2022-12-31 |  |  |  |  | 37.2723 | 25.0395 | Failed | No
2100008632 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 412886767 | 20644338.35 | 322101510.96 | 319398089.65 | 4030007856 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 86.4 | 100 | 2015-06-25 | 2018-06-25 | 2021-10-20 | 2021-10-20 | 2018-06-25 |  | التنسيق مع أصحاب المصلحه (خدمات |  | 39.7774 | 21.3616 | منجز | No
2100100004 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 79678034.71 | 3983901.7355 | 61139744.99 | 48902892.14 | 1010251358 | لا | 0 | 180709034621 | مسحوب | تكلفة العمل المنجز | 84 | 100 | 2012-10-06 | 2015-01-31 | 2023-12-31 | 2023-12-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.1677 | 21.5008 | مسحوب | No
2100192651 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 12521952 | 626097.6 | 0 | 0 | 4030123131 | لا | 0 | 191001167764 | لم يبدأ | تكلفة العمل المنجز | 0 | 0 | 2018-05-13 | 2019-02-05 | 2023-12-31 | 2023-12-31 |  |  |  |  | 39.239 | 21.4933 | منتظم | No
2100058354 | جامعة نجران | تشييد | ذات اولوية عالية وعاجلة | 12130555 | 606527.75 | 4993019 | 4993019 | 1010060399 | لا | 0 | 181209509310 | جاري | الكميات التي تم تركيبها | 81 | 100 | 2015-01-05 | 2015-12-23 | 2022-06-12 | 2022-06-12 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 44.2341 | 17.5757 | Failed | No
2100007560 | جامعة نجران | تشييد | ذات اولوية عالية وعاجلة | 99845201 | 4992260.05 | 89860652 | 89860652 | 1010060399 | لا | 0 | 181209512647 | جاري | الكميات التي تم تركيبها | 95 | 100 | 2013-05-13 | 2016-09-04 | 2021-12-31 | 2021-12-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 44.2341 | 17.5757 | Failed | No
2100068865 | شركة المياه الوطنية / منطقة عسير | مشروع تخطيط شامل | ذات اولوية عالية | 21000000 | 1050000 | 9061473.33 | 9061473.33 | 1010143335 | لا | 0 | 190401069881 | جاري | التكلفة المفوترة | 60.31 | 100 | 2019-08-25 | 2021-02-06 | 2022-01-23 | 2022-01-23 |  |  | لا يوجد تأخير |  | 42.4889 | 18.2116 | خدمات عامة | No
2100059743 | شركة المياه الوطنية | تشييد | ذات اولوية عالية | 78316128.06 | 3915806.403 | 57449722.06 | 57449722.06 | 1116000082 | لا | 0 | 180809050304 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99.8 | 100 | 2012-10-02 | 2015-08-31 | 2019-11-19 | 2019-11-19 | 2015-08-31 |  | لا يوجد تأخير |  | 41.0859 | 19.1571 | منجز | No
2100191273 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية عالية | 12593651.15 | 629682.5575 | 12592086 | 12592086 | 5855015373 | لا | 0 | 200801080525 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2020-11-02 | 2021-04-28 | 2021-04-18 | 2021-04-18 |  | 2021-04-28 |  |  | 42.6138 | 19.9566 | منجز | No
2100000044 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية عالية وعاجلة | 27886185 | 1394309.25 | 23138060 | 23138060 | 5860008190 | لا | 0 | 180909077413 | جاري | منهجية القيمة المكتسبة | 93.9 | 100 | 2017-12-04 | 2020-11-01 | 2022-06-25 | 2022-06-25 |  |  | اخرى |  | 42.276 | 18.2348 | متأخر | No
2100014685 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 2856750 | 142837.5 | 2992785.69 | 2992785.69 | 4030237556 | لا | 0 | 181109359110 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-08-12 | 2020-02-03 | 2020-02-03 | 2020-02-03 | 2020-02-03 |  | اخرى |  | 41.3062 | 18.9778 | منجز | No
2100100870 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1813000 | 90650 | 1432200 | 1432200 | 4601002218 | لا | 0 | 190201020322 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 81 | 100 | 2019-03-10 | 2020-03-04 | 2022-06-30 | 2022-06-30 | 2020-03-04 |  |  |  | 40.8074 | 20.9465 | منجز | No
2100190153 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية عالية | 18315470 | 915773.5 | 0 | 0 | 4650022240 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 32 | 100 | 2018-05-14 | 2021-07-27 | 2022-01-27 | 2022-01-27 |  |  |  |  | 43.2053 | 18.5103 | Failed | No
2100059010 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية متوسطة | 9646500 | 482325 | 2826200 | 2826200 | 1116002556 | لا | 0 | 181109375168 | جاري | الكميات التي تم تركيبها | 3 | 90 | 2014-01-02 | 2022-02-02 | 2022-09-05 | 2022-09-05 |  |  |  |  | 43.6014 | 18.2642 | Failed | No
2100191284 | شركة المياه الوطنية / منطقة عسير | تصميم | ذات اولوية عالية | 21840000 | 1092000 | 22672000 | 6552000 | 4030283265 | لا | 0 | 190901123328 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2020-04-07 | 2021-09-21 | 2022-05-11 | 2022-05-11 | 2021-09-21 |  |  |  | 42.4895 | 18.2104 | منجز | No
2100089143 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 94075816 | 4703790.8 | 54726816.8 | 47681975.18 | 4030210825 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 64.55 | 74.47 | 2019-09-26 | 2022-09-27 | 2022-03-31 | 2022-03-31 |  |  | اخرى |  | 39.716 | 21.3938 | متأخر | No
2100106120 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 14829390 | 741469.5 | 13149879.37 | 13149879.37 | 1010224518 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 99.86 | 100 | 2019-03-06 | 2020-03-06 | 2020-12-09 | 2020-12-09 |  | 2020-03-06 | لا يوجد تأخير |  | 46.8823 | 24.8024 | منجز | No
2100062123 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3821274 | 191063.7 | 412.67 | 0 | 1010318776 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 19 | 100 | 2014-01-04 | 2015-03-30 | 2020-08-18 | 2020-08-18 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6775 | 24.7025 | مسحوب | Yes
2100063792 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 20819689 | 1040984.45 | 6487785.81 | 6487785.81 | 1010156182 | لا | 0 | 181201457910 | جاري | تكلفة العمل المنجز | 44.48 | 64.48 | 2019-03-09 | 2021-08-14 | 2021-08-20 | 2021-08-20 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6759 | 24.7032 | Failed | No
2100016144 | شركة المياه الوطنية / منطقة جازان | إشراف | ذات اولوية عالية وعاجلة | 12500000 | 625000 | 1843897 | 0 | 1010348048 | لا | 0 | 180801040275 | جاري | التكلفة المفوترة | 92.28 | 100 | 2018-09-11 | 2021-09-10 | 2022-03-30 | 2022-03-30 |  |  | لا يوجد تأخير |  | 42.9552 | 16.7103 | خدمات عامة | Yes
2100087124 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية | 16738789 | 836939.45 | 12430756.65 | 12265743.07 | 1010231237 | نعم | 12430756.65 | 180709026242 | مسحوب | منهجية القيمة المكتسبة | 80.02 | 100 | 2014-07-09 | 2016-06-17 | 2023-03-29 | 2023-03-29 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.4409 | 27.1923 | مسحوب | No
2100059463 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية وعاجلة | 61044203 | 3052210.15 | 34712861 | 24791770.76 | 1010066135 | لا | 0 | 180201000146 | جاري | منهجية القيمة المكتسبة | 85.1 | 100 | 2018-09-11 | 2021-08-09 | 2022-07-31 | 2022-07-31 |  |  | تأخرصرف المستحقات المالية |  | 42.1316 | 16.7008 | متأخر | No
2100023892 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية وعاجلة | 40711141.35 | 2035557.0675 | 22529799.35 | 22529799.35 | 1010076961 | لا | 0 | 180709030583 | مسحوب | منهجية القيمة المكتسبة | 91.78 | 100 | 2016-05-03 | 2018-10-26 | 2022-06-27 | 2022-06-27 |  |  | لا يوجد تأخير |  | 49.9893 | 26.6643 | مسحوب | No
2100016262 | وزارة التعليم | تشييد | لم تعد تحتاجها الجهة | 2461114.74 | 123055.737 | 1325123 | 1325123 | 1010181968 | لا | 0 |  | ايقاف جزئي | التكلفة المفوترة | 49 | 100 | 2018-09-17 | 2019-11-16 | 2019-11-16 | 2019-11-16 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | Failed | No
2100007442 | شركة المياه الوطنية / منطقة عسير | إشراف | ذات اولوية عالية | 19908000 | 995400 | 18904097 | 18904097 | 4030283265 | لا | 0 | 180809044605 | منجز – استلام ابتدائي | التكلفة المفوترة | 89.12 | 100 | 2017-07-09 | 2020-06-07 | 2020-06-07 | 2020-06-07 | 2020-06-07 |  | لا يوجد تأخير |  | 42.4888 | 18.2122 | منجز | No
2100015046 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 1540600 | 77030 | 1540600 | 1540600 | 2050106016 | لا | 0 | 190509053510 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-11-27 | 2019-11-13 | 2019-11-13 | 2019-11-13 | 2019-11-13 |  |  |  | 48.4837 | 28.4254 | منجز | No
2100013230 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1098088 | 54904.4 | 459300 | 0 | 2051034938 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-06-27 | 2019-06-22 | 2019-06-22 | 2019-06-22 | 2019-06-22 |  | ضعف كفاءة المقاول الفنية |  | 46.6768 | 24.7119 | منجز | Yes
2100023811 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية وعاجلة | 23958081 | 1197904.05 | 13555011.35 | 13555011.35 | 5950004848 | لا | 0 | 180709025041 | جاري | منهجية القيمة المكتسبة | 82.61 | 100 | 2019-04-21 | 2021-03-29 | 2022-09-01 | 2022-09-01 |  |  | لا يوجد تأخير |  | 42.819 | 17.6178 | Failed | No
2100090344 | وزارة التعليم | تشييد | ذات اولوية عالية | 22803106.66 | 1140155.333 | 20009696 | 20009696 | 1010099661 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-04-13 | 2016-09-29 | 2021-05-17 | 2021-05-17 | 2016-09-29 |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | منجز | No
2100088001 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 5344713.64 | 267235.682 | 5338602.71 | 5338302.71 | 1128119385 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2018-06-04 | 2019-05-01 | 2022-06-08 | 2022-06-08 | 2019-05-01 |  |  |  | 45.2591 | 25.2379 | منجز | No
2100004281 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2024289 | 101214.45 | 142461.197 | 142461.197 | 1010026700 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 23 | 100 | 2006-07-10 | 2007-05-25 | 2019-02-27 | 2019-02-27 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 36.5638 | 28.4092 | مسحوب | No
2100003942 | وزارة التعليم | تشييد | ذات اولوية عالية وعاجلة | 8674531 | 433726.55 | 6098862 | 6098862 | 1010095105 | لا | 0 |  | مسحوب | التكلفة المفوترة | 88 | 100 | 2015-04-19 | 2017-01-08 | 2022-08-24 | 2022-08-24 |  |  | ضعف كفاءة المقاول الفنية |  | 45.3525 | 25.8912 | مسحوب | No
2100005036 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 6892159.3 | 344607.965 | 3021746 | 3021746 | 2943000000 | لا | 0 |  | مسحوب | التكلفة المفوترة | 51 | 100 | 2013-12-09 | 2015-06-02 | 2024-02-14 | 2024-02-14 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7271 | 22.2863 | مسحوب | No
2100007232 | وزارة التعليم | تشييد | ذات اولوية عالية | 4319127 | 215956.35 | 0 | 0 | 4030085763 | لا | 0 |  | مسحوب | التكلفة المفوترة | 1 | 100 | 2008-04-13 | 2010-01-03 | 2010-01-03 | 2010-01-03 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | مسحوب | No
2100009262 | وزارة الصحة / ديوان الوزارة | تشييد | ذات اولوية عالية | 413681451 | 20684072.55 | 295351043.13 | 295351043.13 | 1010053925 | لا | 0 | 181109277390 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 99.28 | 99.97 | 2012-09-10 | 2015-08-07 | 2020-09-13 | 2020-09-13 | 2015-08-07 |  | تأخرصرف المستحقات المالية |  | 39.0981 | 21.7661 | منجز | No
2100084490 | الهيئة الملكية للجبيل وينبع / مدينة جازان للصناعات الأساسية والتحويلية | تشييد | ذات اولوية متوسطة | 125997758.56 | 6299887.928 | 88283187.99 | 88283187.99 | 2055014114 | لا | 0 | 190101004062 | جاري | تكلفة العمل المنجز | 57.86 | 67.37 | 2019-04-01 | 2022-03-31 | 2023-09-30 | 2023-09-30 |  |  | اخرى |  | 42.338 | 17.3332 | متأخر | No
2100022562 | وزارة الصحة/ الاحساء | تشييد | ذات اولوية متوسطة | 6345322.5 | 317266.125 | 5719140 | 3014065.8 | 2251002570 | لا | 0 | 201109312420 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 50 | 50 | 2020-01-22 | 2020-07-15 | 2022-03-29 | 2022-03-29 | 2020-07-15 |  | اخرى |  | 49.6121 | 25.4583 | منجز | No
2100047530 | أمانة / الجوف | تشييد | ذات اولوية عالية وعاجلة | 5814080 | 290704 | 3779580 | 3779580 | 3350013518 | لا | 0 | 181001172169 | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-10-31 | 2019-10-19 | 2023-01-23 | 2023-01-23 |  |  | ضعف كفاءة المقاول الفنية |  | 38.2235 | 30.5132 | منتظم | No
2100006156 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 124016322 | 6200816.1 | 89695837.69 | 89695837.69 | 4030068284 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 98.51 | 100 | 2013-12-25 | 2015-03-25 | 2021-03-01 | 2021-03-01 | 2015-03-25 |  | لا يوجد تأخير |  | 39.8129 | 21.4594 | منجز | No
2100094916 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 2985702 | 149285.1 | 2694741 | 2694741 | 4031057370 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 80.51 | 100 | 2017-08-23 | 2018-06-19 | 2019-11-11 | 2019-11-11 | 2018-06-19 |  | لا يوجد تأخير |  | 39.9069 | 21.0476 | منجز | No
2100000932 | شركة المياه الوطنية / المنطقة الشرقية | تصميم وتشييد | ذات اولوية عالية | 256695883 | 12834794.15 | 276688368.9 | 236384388.6 | 2050101650 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 98.02 | 100 | 2017-01-22 | 2018-09-22 | 2021-07-14 | 2021-07-14 | 2018-09-22 |  | لا يوجد تأخير |  | 50.0764 | 26.2486 | منجز | No
2100061040 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 77181050 | 3859052.5 | 50736869.7 | 50736869.7 | 2050001536 | لا | 0 | 200709052696 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-05-29 | 2021-05-06 | 2021-07-29 | 2021-07-29 | 2021-05-06 |  | لا يوجد تأخير |  | 39.144 | 21.6242 | منجز | No
2100191402 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 34284370 | 1714218.5 | 24863829 | 24863829 | 1010319823 | لا | 0 | 200709052696 | جاري | منهجية القيمة المكتسبة | 92 | 100 | 2020-09-06 | 2021-07-06 | 2022-07-31 | 2022-07-31 |  |  |  |  | 39.1905 | 21.6643 | Failed | No
2100099466 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 37046159 | 1852307.95 | 16925171.53 | 16925171.53 | 2050003475 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-02-01 | 2019-07-18 | 2019-07-11 | 2019-07-11 | 2019-07-18 |  | لا يوجد تأخير |  | 39.2175 | 21.5346 | منجز | No
2100191424 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 20992100 | 1049605 | 13049750 | 12768000 | 1010278841 | لا | 0 | 200709052696 | جاري | منهجية القيمة المكتسبة | 100 | 100 | 2020-11-02 | 2022-04-17 | 2022-06-30 | 2022-06-30 |  |  |  |  | 39.1134 | 21.698 | متأخر | No
2100037111 | شركة المياه الوطنية / منطقة مكة المكرمة | إشراف | ذات اولوية عالية | 12267156 | 613357.8 | 11767774.58 | 11767774.58 | 1010326770 | لا | 0 |  | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 96 | 100 | 2018-05-13 | 2020-05-12 | 2022-03-31 | 2022-03-31 | 2020-05-12 |  | لا يوجد تأخير |  | 39.207 | 21.5471 | منجز | No
2100086634 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية | 109777167.5 | 5488858.375 | 76471695.82 | 60675689.01 | 1010166750 | لا | 0 | 200409110626 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 90.54 | 100 | 2015-05-12 | 2017-04-20 | 2021-06-03 | 2021-06-03 | 2017-04-20 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.2855 | 20.1136 | منجز | No
2100074244 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 13847775 | 692388.75 | 71607 | 0 | 1010060469 | لا | 0 | 190209008446 | ايقاف كلي | التكلفة المفوترة | 6 | 100 | 2013-10-01 | 2015-09-21 | 2023-01-01 | 2023-01-01 |  |  | ضعف كفاءة المقاول الفنية |  | 42.4987 | 18.2178 | Failed | Yes
2100106632 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 27219935 | 1360996.75 | 26064523.41 | 26064523.41 | 2050003475 | لا | 0 | 200709052696 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 98.21 | 100 | 2019-09-17 | 2020-09-06 | 2020-12-26 | 2020-12-26 | 2020-09-06 |  | لا يوجد تأخير |  | 39.2134 | 21.38 | منجز | No
2100190912 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية وعاجلة | 15223975 | 761198.75 | 5020516.87 | 5020516.87 | 4031045263 | لا | 0 | 200601043382 | جاري | منهجية القيمة المكتسبة | 73.3 | 49.86 | 2020-12-06 | 2023-11-04 | 2023-11-04 | 2023-11-04 |  |  |  |  | 41.4753 | 20.0103 | منتظم | No
2100001805 | وزارة الثقافة | تشييد |  | 1109294 | 55464.7 | 161093 | 161093 | 1010298707 |  | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-09-16 00:59 | 2020-01-15 00:59 | 2020-01-15 | 2020-01-15 | 2020-01-15 00:59 |  | لا يوجد تأخير |  |  |  | منجز | No
2100003010 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية عالية | 8468689 | 423434.45 | 8468680 | 7621940 | 5855029073 | لا | 0 | 190301025500 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 98.93 | 2019-05-06 | 2021-04-13 | 2021-05-17 | 2021-05-17 | 2021-04-13 |  | لا يوجد تأخير |  | 42.4989 | 18.2169 | منجز | No
2100091291 | أمانة / عسير | تشييد | ذات اولوية عالية | 1149115 | 57455.75 | 0 | 0 | 5855036745 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 38 | 100 | 2015-05-10 | 2016-01-06 | 2016-07-31 | 2016-07-31 |  |  | تأخرصرف المستحقات المالية |  |  |  | مسحوب | No
2100101161 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | ترميم | ذات اولوية عالية وعاجلة | 9910721 | 495536.05 | 9070260 | 9070260 | 2050087924 | لا | 0 | 181109231750 | منجز – استلام ابتدائي | اخرى | 92.12 | 100 | 2013-01-01 | 2015-12-31 | 2022-12-20 | 2022-12-20 | 2015-12-31 |  |  |  | 38.193 | 24.0195 | منجز | No
2100101150 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تصميم | ذات اولوية عالية وعاجلة | 32237150 | 1611857.5 | 31393405 | 31393405 | 2051047662 | لا | 0 | 181109247188 | جاري | اخرى | 99.25 | 98.08 | 2018-02-07 | 2023-02-06 | 2023-02-06 | 2023-02-06 |  |  |  |  | 38.2007 | 24.017 | منتظم | No
2100018255 | المؤسسة العامة للري | تشييد | ذات اولوية عالية | 91754337.6 | 4587716.88 | 83335115.58 | 83335115.58 | 1010166750 | لا | 0 | 181109376692 | جاري الاستلام الإبتدائي | اخرى | 100 | 100 | 2013-11-08 | 2017-02-01 | 2022-07-14 | 2022-07-14 |  |  | ضعف كفاءة المقاول الفنية |  | 49.6621 | 25.3639 | Failed | No
2100106153 | شركة المياه الوطنية / منطقة تبوك | تشييد | لم تعد تحتاجها الجهة | 29079952.8 | 1453997.64 | 225344.79 | 225344.79 | 1010178884 | لا | 0 | 180909094234 | جاري | منهجية القيمة المكتسبة | 0.97 | 100 | 2015-01-23 | 2017-12-21 | 2022-06-30 | 2022-06-30 |  |  | لا يوجد تأخير |  | 35.997 | 27.9866 | Failed | No
2100047703 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية منخفضة | 2389800 | 119490 | 1114584.13 | 1114584.13 | 1010262459 | لا | 0 | 181209497721 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 97.41 | 98.41 | 2018-01-31 | 2019-01-20 | 2020-04-08 | 2020-04-08 | 2019-01-20 |  | لا يوجد تأخير |  | 36.5426 | 28.4036 | منجز | No
2100054235 | وزارة الداخلية / مديرية الأمن العام | تشييد | ذات اولوية متوسطة | 1294814.85 | 64740.7425 | 1294814.85 | 1294814.85 | 1010096215 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-03-04 | 2020-08-28 | 2020-11-28 | 2020-11-28 | 2020-08-28 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 49.9973 | 26.4209 | منجز | No
2100104112 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2980374 | 149018.7 | 327841 | 0 | 3550027760 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 11 | 100 | 2013-06-18 | 2014-09-12 | 2105-06-23 | 2105-06-23 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | مسحوب | Yes
2100085374 | أمانة / تبوك | دراسة الجدوى | ذات اولوية متوسطة | 2822066.82 | 141103.341 | 2822066.82 | 2822066.82 | 4030229175 | لا | 0 | 1911094288 | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2019-11-12 | 2021-11-11 | 2021-11-11 | 2021-11-11 | 2021-11-11 |  | اخرى |  |  |  | منجز | No
2100067793 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 955000 | 47750 | 855000 | 855000 | 3351012191 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-12-26 | 2020-12-02 | 2021-09-01 | 2021-09-01 | 2020-12-02 |  |  |  | 34.9451 | 29.2864 | منجز | No
2100016026 | رئاسة أمن الدولة / ديوان رئاسة أمن الدولة | تشييد | ذات اولوية عالية وعاجلة | 19329192.38 | 966459.619 | 19736486.2 | 16563443.61 | 1010226539 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-09-04 | 2021-07-15 | 2022-11-17 | 2022-11-17 | 2021-07-15 |  | تأخرصرف المستحقات المالية |  | 45.4549 | 24.5673 | منجز | No
2100060211 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 39450444.18 | 1972522.209 | 25119524.88 | 23997567.23 | 4030010170 | لا | 0 | 181001125232 | جاري | تكلفة العمل المنجز | 66.25 | 77 | 2018-10-01 | 2019-08-04 | 2024-06-30 | 2024-06-30 |  |  | تأخرصرف المستحقات المالية |  | 39.1677 | 21.5008 | متأخر | No
2100042652 | جامعة القصيم | تشييد | ذات اولوية عالية | 3650247.75 | 182512.3875 | 2143408.25 | 2062315.47 | 1131028904 | لا | 0 | 200409030207 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-06-30 | 2020-02-25 | 2022-06-15 | 2022-06-15 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 43.7638 | 26.3532 | Failed | No
2100102023 | وزارة الصحة/ الاحساء | تشييد | ذات اولوية متوسطة | 946000 | 47300 | 500000 | 110976.07 | 2251059201 | لا | 0 | 180909110731 | مسحوب | تكلفة العمل المنجز | 68 | 32 | 2018-02-04 | 2019-01-24 | 2019-09-03 | 2019-09-03 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5533 | 25.4569 | مسحوب | No
2100068250 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 344266 | 17213.3 | 360659.61 | 360659.61 | 4601002260 | لا | 0 | 190309050425 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-09-09 | 2020-02-20 | 2020-02-22 | 2020-02-22 | 2020-02-20 |  | ضعف كفاءة المقاول الفنية |  | 39.1902 | 21.4767 | منجز | No
2100013425 | أمانة / الجوف | تشييد | ذات اولوية متوسطة | 1998050 | 99902.5 | 0 | 0 | 3450009076 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 0 | 100 | 2015-03-10 | 2016-01-08 | 2021-06-13 | 2021-06-13 |  |  | منازعات قائمة |  | 37.1473 | 31.4806 | مسحوب | No
2100105044 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية متوسطة | 7277691.72 | 363884.586 | 303622.41 | 0 | 1010153346 | لا | 0 | 180909071076 | مسحوب | منهجية القيمة المكتسبة | 34 | 100 | 2014-02-10 | 2015-07-26 | 2022-12-31 | 2022-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 37.5615 | 27.6524 | مسحوب | Yes
2100038430 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية عالية | 90128467.27 | 4506423.3635 | 60538441.3 | 57986896.8 | 1010180774 | لا | 0 | 191001130760 | جاري | الكميات التي تم تركيبها | 96.57 | 79.2 | 2020-01-05 | 2022-06-19 | 2022-05-30 | 2022-05-30 |  |  |  |  | 42.5161 | 18.106 | متأخر | No
2100058225 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2410321 | 120516.05 | 740324 | 740324 | 3552000068 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 26 | 100 | 2014-09-02 | 2015-11-27 | 2023-12-15 | 2023-12-15 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 36.5638 | 28.4092 | مسحوب | No
2100050245 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 5070340 | 253517 | 4512604 | 4512604 | 1010156220 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 95 | 100 | 2016-02-16 | 2018-02-05 | 2020-11-09 | 2020-11-09 | 2018-02-05 |  | ضعف كفاءة المقاول الفنية |  | 36.5969 | 28.4149 | منجز | No
2100051461 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 3529134 | 176456.7 | 205792.65 | 205792.65 | 4030201495 | لا | 0 | 200409077560 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 55 | 68 | 2019-07-12 | 2021-01-02 | 2021-10-26 | 2021-10-26 | 2021-01-02 |  | ضعف كفاءة المقاول الفنية |  | 35.7243 | 27.3457 | منجز | No
2100043400 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 54846121.4 | 2742306.07 | 32628170.66 | 29070658.26 | 5950014087 | لا | 0 | 180709020108 | ايقاف كلي | تكلفة العمل المنجز | 75 | 95 | 2014-10-22 | 2016-09-21 | 2024-12-31 | 2024-12-31 |  |  | تأخرصرف المستحقات المالية |  | 40.1565 | 29.9585 | Failed | No
2100103611 | وزارة التجارة | دراسة الجدوى | ذات اولوية عالية | 2925831.34 | 146291.567 | 2221696.82 | 2221696.82 | 1010348048 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-07-11 | 2020-07-10 | 2021-09-05 | 2021-09-05 |  | 2020-07-10 | أوامر تغيير |  |  |  | منجز | No
2100074056 | شركة المياه الوطنية / المنطقة الشرقية | إشراف | ذات اولوية عالية | 5697000 | 284850 | 5529129.03 | 5529129.03 | 2050107656 | لا | 0 | 180809252532 | منجز – استلام ابتدائي | التكلفة المفوترة | 97.08 | 100 | 2017-10-18 | 2019-04-17 | 2019-07-19 | 2019-07-19 | 2019-04-17 |  | لا يوجد تأخير |  | 48.5323 | 28.4302 | منجز | No
2100053966 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 17000000 | 850000 | 15299999.95 | 15299999.95 | 5855029980 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2010-11-04 | 2014-04-05 | 2014-04-05 | 2014-04-05 | 2014-04-05 |  |  |  | 42.5031 | 18.2734 | منجز | No
2100069952 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 90783142.65 | 4539157.1325 | 55712867.25 | 55712867.25 | 1010009590 | لا | 0 | 190501101105 | جاري | الكميات التي تم تركيبها | 69.8 | 69.2 | 2019-07-18 | 2020-12-29 | 2023-02-21 | 2023-02-21 |  |  |  |  | 42.7646 | 21.5456 | منتظم | No
2100038824 | وزارة النقل والخدمات اللوجستية / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 30000000 | 1500000 | 22523410.04 | 22523410.04 | 2251029078 | لا | 0 | 190601033655 | ايقاف جزئي | الكميات التي تم تركيبها | 86 | 92.3 | 2019-07-31 | 2020-07-15 | 2023-01-22 | 2023-01-22 |  |  |  |  | 49.4225 | 25.3525 | متأخر | No
2100053594 | وزارة النقل والخدمات اللوجستية / منطقة جازان | تشييد | ذات اولوية متوسطة | 131127615.5 | 6556380.775 | 65992917.28 | 65992917.28 | 1010066115 | لا | 0 | 181009186759 | جاري | الكميات التي تم تركيبها | 64.79 | 73.8 | 2013-10-22 | 2017-09-07 | 2023-05-31 | 2023-05-31 |  |  |  |  | 42.7853 | 17.6218 | متأخر | No
2100054283 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 60799998 | 3039999.9 | 0 | 0 | 1010033701 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2005-07-22 | 2007-07-28 | 2007-07-28 | 2007-07-28 | 2007-07-28 | 2015-04-17 |  |  | 42.643 | 18.2212 | منجز | No
2100038695 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 82889107.9 | 4144455.395 | 81709408.55 | 81709408.55 | 5950000060 | لا | 0 | 181109343737 | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2014-11-12 | 2017-10-08 | 2020-06-10 | 2020-06-10 | 2017-10-08 | 2021-05-29 |  |  | 39.8324 | 21.4122 | منجز | No
2100016634 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 53857250 | 2692862.5 | 42477762.24 | 42477762.24 | 2050001536 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 88 | 100 | 2018-02-18 | 2020-01-27 | 2022-04-30 | 2022-04-30 | 2020-01-27 |  | لا يوجد تأخير |  | 39.1071 | 21.5983 | منجز | No
2100054014 | وزارة النقل والخدمات اللوجستية / منطقة حائل | تشييد | ذات اولوية عالية | 137439439 | 6871971.95 | 123695491.9 | 93786646 | 1010048595 | لا | 0 | 181109353733 | جاري | تكلفة العمل المنجز | 93.11 | 92 | 2013-12-19 | 2020-11-01 | 2023-03-04 | 2023-03-04 |  |  |  |  | 41.6991 | 27.4773 | منتظم | No
2100010080 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 114678961.75 | 5733948.0875 | 91844688 | 91844688 | 5855000147 | لا | 0 | 191009033201 | مسحوب | الكميات التي تم تركيبها | 87.77 | 100 | 2013-11-24 | 2017-10-10 | 2022-07-19 | 2022-07-19 |  |  |  |  | 42.7318 | 18.2835 | مسحوب | No
2100015304 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | لم تعد تحتاجها الجهة | 190000000 | 9500000 | 0 | 0 | 4030007516 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 42 | 100 | 2010-12-16 | 2014-12-31 | 2023-05-23 | 2023-05-23 |  |  | ضعف كفاءة المقاول الفنية |  | 39.3366 | 21.412 | مسحوب | No
2100084136 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية منخفضة | 5748000 | 287400 | 5173200 | 5173200 | 5855028046 | لا | 0 | 181109368440 | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2012-08-28 | 2018-04-27 | 2018-04-27 | 2018-04-27 | 2018-04-27 | 2020-04-01 |  |  | 42.564 | 18.1751 | منجز | No
2100054390 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية منخفضة | 109399850 | 5469992.5 | 108851481 | 108851481 | 5855005058 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2009-08-22 | 2014-01-31 | 2020-08-26 | 2020-08-26 | 2014-01-31 | 2020-10-20 |  |  | 42.4821 | 18.512 | منجز | No
2100020053 | وزارة النقل والخدمات اللوجستية / منطقة جازان | تشييد | ذات اولوية متوسطة | 49957700 | 2497885 | 35591374.24 | 35591374.24 | 1010066115 | لا | 0 | 181109351607 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2012-10-30 | 2015-04-02 | 2022-04-16 | 2022-04-16 | 2015-04-02 |  |  |  | 42.9393 | 17.2377 | منجز | No
2100040891 | أمانة / تبوك | تصميم | ذات اولوية متوسطة | 1989750 | 99487.5 | 1989750 | 1707825 | 1010323435 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-09-14 | 2021-03-07 | 2021-03-07 | 2021-03-07 | 2021-03-07 |  | تغيرات في نطاق المشروع |  |  |  | منجز | No
2100008934 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 5866713 | 293335.65 | 0 | 0 | 1010052618 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 10 | 100 | 2013-11-18 | 2015-08-11 | 2023-12-15 | 2023-12-15 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | مسحوب | No
2100042722 | جامعة الطائف | تشييد | ذات اولوية متوسطة | 105064230.14 | 5253211.507 | 84044956.18 | 84044956.18 | 1010028011 | لا | 0 | 181109250111 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2013-07-07 | 2019-12-08 | 2019-12-08 | 2019-12-08 | 2019-12-08 |  | لا يوجد تأخير |  | 40.4972 | 21.337 | منجز | No
2100015761 | وزارة الرياضة | تشييد | ذات اولوية عالية | 30764238 | 1538211.9 | 3980307.74 | 3980307.74 | 1010006362 | نعم | 304916.18 | 180909080511 | مسحوب | تكلفة العمل المنجز | 42 | 100 | 2014-05-27 | 2016-10-28 | 2019-03-31 | 2019-03-31 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | مسحوب | No
2100061784 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية | 23816420 | 1190821 | 21955869.94 | 21955869.94 | 1131022283 | لا | 0 | 180809050276 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 98 | 100 | 2018-02-14 | 2019-02-03 | 2019-02-03 | 2019-02-03 | 2019-02-03 |  | لا يوجد تأخير |  | 43.7931 | 26.3834 | منجز | No
2100084011 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 1599778 | 79988.9 | 0 | 0 | 5855039588 | لا | 0 | 180301001452 | فسخ العقد | الكميات التي تم تركيبها | 55.76 | 55.76 | 2018-01-08 | 2018-09-18 | 2018-09-18 | 2018-09-18 |  |  | اخرى |  | 42.5522 | 18.1913 | مسحوب | No
2100084092 | وزارة النقل والخدمات اللوجستية / منطقة حائل | تشييد | ذات اولوية متوسطة | 4126575 | 206328.75 | 0 | 0 | 3357001499 | لا | 0 | 191201095366 | فسخ العقد | الكميات التي تم تركيبها | 0 | 20 | 2020-02-05 | 2021-01-23 | 2021-01-24 | 2021-01-24 |  |  | اخرى |  | 41.7147 | 27.4884 | مسحوب | No
2100063022 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 4368100 | 218405 | 3804615 | 2542000 | 1010262459 | لا | 0 | 180909107441 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-10-11 | 2017-04-03 | 2020-12-30 | 2020-12-30 | 2017-04-03 |  | ضعف كفاءة المقاول الفنية |  | 35.0202 | 28.4788 | منجز | No
2100070313 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية منخفضة | 47578413 | 2378920.65 | 42756679 | 42756679 | 1010247052 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2010-11-04 | 2019-03-11 | 2019-03-11 | 2019-03-11 | 2019-03-11 | 2019-12-06 |  |  | 41.9239 | 18.9304 | منجز | No
2100061972 | وزارة الرياضة | تشييد | ذات اولوية متوسطة | 41238268.01 | 2061913.4005 | 6503620.82 | 6503620.82 | 1010015350 | نعم | 551301.95 |  | مسحوب | تكلفة العمل المنجز | 62 | 100 | 2011-10-15 | 2014-03-17 | 2014-03-17 | 2014-03-17 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5706 | 16.8894 | مسحوب | No
2100105265 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 11077787 | 553889.35 | 11077787 | 11077787 | 4030142991 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 86.85 | 2020-02-25 | 2021-08-09 | 2021-07-28 | 2021-07-28 | 2021-08-09 |  | لا يوجد تأخير |  | 39.2516 | 21.4563 | منجز | No
2100015783 | وزارة الصحة / الطائف | تشييد | ذات اولوية عالية | 2049684 | 102484.2 | 30500 | 0 | 4032020411 | لا | 0 | 190701114603 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-09-09 | 2020-01-05 | 2021-10-01 | 2021-10-01 | 2020-01-05 |  | تأخرصرف المستحقات المالية |  | 40.4127 | 21.2457 | منجز | Yes
2100092396 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 933579 | 46678.95 | 0 | 0 | 1010059275 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 30 | 100 | 2016-01-09 | 2018-08-30 | 2023-01-15 | 2023-01-15 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | مسحوب | No
2100053955 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 72488510 | 3624425.5 | 72483274.9 | 72483274.9 | 1010066115 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2011-08-17 | 2014-01-17 | 2018-09-02 | 2018-09-02 | 2014-01-17 | 2019-10-02 |  |  | 39.7529 | 21.3542 | منجز | No
2100054320 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية منخفضة | 47725957 | 2386297.85 | 47721637 | 47721637 | 1010066115 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2012-10-09 | 2015-09-11 | 2016-05-04 | 2016-05-04 | 2015-09-11 | 2018-08-30 |  |  | 39.8417 | 21.4027 | منجز | No
2100096530 | وزارة الرياضة | تشييد | ذات اولوية متوسطة | 36651170 | 1832558.5 | 4832172.27 | 4832172.27 | 1010006362 | لا | 0 | 180909080505 | مسحوب | الكميات التي تم تركيبها | 59 | 100 | 2013-04-17 | 2015-06-19 | 2021-05-26 | 2021-05-26 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | مسحوب | No
2100087695 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 11316942 | 565847.1 | 9902584 | 9902584 | 4030176726 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 93.94 | 100 | 2018-01-11 | 2019-06-27 | 2020-01-29 | 2020-01-29 |  | 2019-06-27 | لا يوجد تأخير |  | 39.1302 | 22.2718 | منجز | No
2100000125 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية متوسطة | 99682165 | 4984108.25 | 6383108.81 | 6383108.81 | 4030139128 | لا | 0 | 200409068660 | جاري | منهجية القيمة المكتسبة | 11.49 | 100 | 2014-10-29 | 2017-09-25 | 2022-09-23 | 2022-09-23 |  |  | لا يوجد تأخير |  | 36.6011 | 28.3495 | Failed | No
2100007755 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية عالية | 41988174.8 | 2099408.74 | 18559675.67 | 18559675.67 | 1010013318 | لا | 0 |  | مسحوب | منهجية القيمة المكتسبة | 55.08 | 100 | 2011-12-17 | 2013-11-25 | 2022-12-31 | 2022-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 35.7341 | 27.3269 | مسحوب | No
2100038312 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 466728249.76 | 23336412.488 | 466728249.22 | 466728249.22 | 1010054406 | لا | 0 | 181109368844 | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2012-12-24 | 2014-06-08 | 2017-08-08 | 2017-08-08 | 2014-06-08 | 2021-08-12 |  |  | 39.1939 | 21.4692 | منجز | No
2100033412 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 47844781.73 | 2392239.0865 | 7918071.417 | 7343797.869 | 1010258619 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 19 | 100 | 2014-04-14 | 2016-03-14 | 2025-12-31 | 2025-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 41.9331 | 17.9435 | مسحوب | No
2100070173 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 124403182 | 6220159.1 | 124403182 | 124403182 | 4030013052 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2009-08-09 | 2012-07-07 | 2019-01-31 | 2019-01-31 | 2012-07-07 | 2020-09-20 |  |  | 39.8145 | 21.3932 | منجز | No
2100195576 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 145213721.86 | 7260686.093 | 35220351.6 | 35220351.6 | 4650007032 | نعم | 190000000 |  | جاري | الكميات التي تم تركيبها | 39.3 | 64.4 | 2020-06-25 | 2022-06-02 | 2023-05-23 | 2023-05-23 |  |  |  |  | 39.3321 | 21.3256 | Failed | No
2100062510 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 51520265 | 2576013.25 | 28974731 | 28974731 | 1010178838 | لا | 0 | 200209137484 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2013-05-29 | 2015-05-28 | 2017-05-21 | 2017-05-21 | 2015-05-28 |  | ضعف كفاءة المقاول الفنية |  | 38.2189 | 24.0343 | منجز | No
2100008945 | وزارة التعليم | تشييد | ذات اولوية عالية | 8698033.2 | 434901.66 | 6958426 | 6958426 | 1010225334 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2012-01-14 | 2013-09-05 | 2020-12-03 | 2020-12-03 | 2013-09-05 |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | منجز | No
2100014416 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 1773000 | 88650 | 1861650 | 1656060 | 5802010434 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-12-02 | 2020-05-26 | 2020-08-18 | 2020-08-18 | 2020-05-26 |  | ضعف كفاءة المقاول الفنية |  | 41.299 | 18.9751 | منجز | No
2100037391 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 109517203.4 | 5475860.17 | 98999099.1 | 98999099.1 | 1010004737 | لا | 0 | 200401010909 | مسحوب | الكميات التي تم تركيبها | 92.44 | 100 | 2010-07-10 | 2011-09-25 | 2023-12-27 | 2023-12-27 |  |  | ضعف كفاءة المقاول الفنية |  | 40.4387 | 21.3328 | مسحوب | No
2100034440 | وزارة النقل والخدمات اللوجستية / منطقة المدينة المنورة | تشييد | ذات اولوية متوسطة | 7770000 | 388500 | 3847920 | 3847920 | 3550021826 | نعم | 5680508 | 191101265782 | جاري | الكميات التي تم تركيبها | 82 | 100 | 2020-01-29 | 2021-01-21 | 2021-10-01 | 2021-10-01 |  |  |  |  | 39.4269 | 24.6066 | Failed | No
2100034366 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 3233100 | 161655 | 3387057.65 | 3387057.65 | 4030006066 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-01-10 | 2020-03-27 | 2020-03-15 | 2020-03-15 | 2020-03-27 |  | اخرى |  | 41.3057 | 18.9745 | منجز | No
2100098276 | وزارة النقل والخدمات اللوجستية / منطقة القصيم | تشييد | ذات اولوية عالية | 144421260.6 | 7221063.03 | 129985976.76 | 129985976.76 | 1116001737 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2012-06-26 | 2016-05-12 | 2019-10-06 | 2019-10-06 | 2016-05-12 |  |  |  | 42.9453 | 25.8846 | منجز | No
2100070980 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | لم تعد تحتاجها الجهة | 37014469.75 | 1850723.4875 | 0 | 0 | 1116000094 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 53.11 | 53.11 | 2011-09-21 | 2014-02-22 | 2015-01-13 | 2015-01-13 |  |  | اخرى |  | 40.4117 | 21.2804 | مسحوب | No
2100042313 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2505434 | 125271.7 | 0 | 0 | 1010245520 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 40 | 100 | 2011-07-31 | 2012-10-15 | 2019-02-18 | 2019-02-18 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 36.5638 | 28.4092 | مسحوب | No
2100041226 | أمانة / تبوك | دراسة الجدوى | ذات اولوية عالية وعاجلة | 3779200 | 188960 | 3779200 | 3732413 | 4030229175 | لا | 0 |  | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2017-11-12 | 2019-11-12 | 2019-11-12 | 2019-11-12 | 2019-11-12 |  | اخرى |  |  |  | منجز | No
2100033935 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 2263300 | 113165 | 2263300 | 2263300 | 4605000749 | لا | 0 | 200101001125 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 98 | 2019-11-03 | 2020-10-21 | 2021-01-18 | 2021-01-18 | 2020-10-21 |  | اخرى |  | 41.3076 | 18.9757 | منجز | No
2100094216 | وزارة النقل والخدمات اللوجستية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية | 314686500 | 15734325 | 244978184.25 | 244978184.25 | 4650007032 | لا | 0 | 180701023396 | جاري | الكميات التي تم تركيبها | 85.2 | 90.92 | 2013-12-23 | 2016-11-20 | 2023-09-15 | 2023-09-15 |  |  |  |  | 39.4949 | 24.3962 | متأخر | No
2100060060 | أمانة / جدة | تشييد | ذات اولوية عالية | 9982567 | 499128.35 | 7764397.59 | 7764397.59 | 4030134089 | لا | 0 | 190901062323 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 97 | 99 | 2019-11-06 | 2021-10-14 | 2022-01-12 | 2022-01-12 | 2021-10-14 |  | اخرى |  | 39.1838 | 21.5309 | منجز | No
2100059883 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 178846379.87 | 8942318.9935 | 80522405.48 | 60164624.41 | 1010152168 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 77 | 100 | 2013-09-18 | 2015-03-12 | 2023-03-31 | 2023-03-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال | أخرى | 36.5638 | 28.4092 | Failed | No
2100038010 | وزارة النقل والخدمات اللوجستية / منطقة القصيم | تشييد | ذات اولوية عالية | 71002644 | 3550132.2 | 27498931.56 | 27498931.56 | 1116000094 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 39.43 | 100 | 2010-06-24 | 2012-11-25 | 2018-02-10 | 2018-02-10 |  |  | اخرى |  | 44.0964 | 26.3266 | مسحوب | No
2100195731 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 104499990.26 | 5224999.513 | 35696075 | 35696075 | 4031046036 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 46.13 | 52.9 | 2020-08-20 | 2022-07-29 | 2023-09-15 | 2023-09-15 |  |  |  |  | 40.0088 | 21.6206 | متأخر | No
2100037774 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 8878999.5 | 443949.975 | 8878999.5 | 8878999.5 | 4030165513 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2012-09-08 | 2014-08-16 | 2018-04-05 | 2018-04-05 | 2014-08-16 | 2020-02-24 |  |  | 39.8356 | 21.4066 | منجز | No
2100085573 | أمانة / جدة | دراسات هندسية | ذات اولوية متوسطة | 6500000 | 325000 | 6500000 | 6500000 | 4030242069 | لا | 0 | 191001116579 | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2019-09-12 | 2020-02-07 | 2020-02-07 | 2020-02-07 | 2020-02-07 | 2020-02-06 | اخرى |  | 39.1715 | 21.5049 | منجز | No
2100032454 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية عالية | 16960968 | 848048.4 | 14828085.54 | 14828085.54 | 1010077408 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 90 | 100 | 2012-05-28 | 2013-03-19 | 2022-09-01 | 2022-09-01 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 37.2877 | 24.9773 | Failed | No
2100053701 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 45756464 | 2287823.2 | 38219985 | 38219985 | 1010108612 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 98.86 | 98.86 | 2011-06-08 | 2013-03-19 | 2022-03-31 | 2022-03-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 47.1334 | 24.9294 | مسحوب | No
2100089515 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 6402935 | 320146.75 | 5487172.5 | 5487172.5 | 1132000522 | لا | 0 |  | مسحوب | التكلفة المفوترة | 85 | 100 | 2010-05-13 | 2011-11-26 | 2021-11-16 | 2021-11-16 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | مسحوب | No
2100077626 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 67622438.8 | 3381121.94 | 67580096.29 | 67580096.29 | 1010185409 | لا | 0 | 200909172274 | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2011-06-20 | 2013-11-20 | 2019-02-02 | 2019-02-02 | 2013-11-20 | 2020-02-24 |  |  | 40.446 | 21.3012 | منجز | No
2100043971 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 4997842.5 | 249892.125 | 4126159 | 299424.62 | 5950019171 | لا | 0 | 220601025060 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 97.18 | 100 | 2019-11-30 | 2021-12-07 | 2022-09-10 | 2022-09-10 | 2021-12-07 |  | تأخرصرف المستحقات المالية |  | 44.2267 | 17.5553 | منجز | No
2100097790 | جامعة الجوف | تشييد | ذات اولوية متوسطة | 12271267.8 | 613563.39 | 8188678.1 | 7688678.1 | 1010355209 | لا | 0 | 190401014781 | جاري | تكلفة العمل المنجز | 75 | 95 | 2020-04-25 | 2021-04-15 | 2023-03-26 | 2023-03-26 |  |  | تأخرصرف المستحقات المالية |  | 40.0425 | 29.7947 | متأخر | No
2100077545 | وزارة النقل والخدمات اللوجستية / منطقة الباحة | تشييد | ذات اولوية عالية | 119563000 | 5978150 | 107606691.5 | 107606691.5 | 5855000147 | لا | 0 | 180901072568 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2009-12-02 | 2017-02-14 | 2018-08-28 | 2018-08-28 | 2017-02-14 |  |  |  | 41.464 | 20.0266 | منجز | No
2100074535 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 9900803.65 | 495040.1825 | 4343314.5 | 0 | 1010181437 | لا | 0 |  | مسحوب | التكلفة المفوترة | 44 | 100 | 2014-01-30 | 2017-04-14 | 2017-11-29 | 2017-11-29 |  |  | ضعف كفاءة المقاول الفنية |  | 50.4535 | 26.5614 | مسحوب | Yes
2100066032 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 1531785 | 76589.25 | 0 | 0 | 4650048401 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 1 | 100 | 2011-01-07 | 2012-07-07 | 2021-09-08 | 2021-09-08 |  |  | ضعف كفاءة المقاول الفنية |  | 39.1182 | 24.076 | مسحوب | No
2100065682 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 13491310 | 674565.5 | 1577318.94 | 1577318.94 | 5855043289 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 65 | 100 | 2015-01-29 | 2018-01-10 | 2018-01-10 | 2018-01-10 |  |  | ضعف كفاءة المقاول الفنية |  | 41.2843 | 20.1621 | مسحوب | No
2100079925 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية متوسطة | 6927575 | 346378.75 | 3699648.35 | 3699648.35 | 1134003368 | لا | 0 | 180909080799 | جاري | منهجية القيمة المكتسبة | 81.95 | 100 | 2018-01-18 | 2020-12-16 | 2022-09-04 | 2022-09-04 |  |  | لا يوجد تأخير |  | 37.2626 | 25.0304 | Failed | No
2100199942 | شركة المياه الوطنية / منطقة القصيم | إشراف | ذات اولوية عالية وعاجلة | 4999500 | 249975 | 385510 | 385510 | 1010323435 | لا | 0 | 201201111474 | جاري | منهجية القيمة المكتسبة | 43.97 | 15 | 2021-07-14 | 2024-06-28 | 2024-06-28 | 2024-06-28 |  |  |  |  | 43.9818 | 26.3592 | خدمات عامة | No
2100099444 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية متوسطة | 169357307.5 | 8467865.375 | 146317767.06 | 146317767.06 | 1010317283 | لا | 0 | 180809064074 | جاري | منهجية القيمة المكتسبة | 95.69 | 100 | 2018-01-01 | 2020-11-29 | 2022-06-30 | 2022-06-30 |  |  | لا يوجد تأخير |  | 36.5326 | 28.378 | Failed | No
2100066242 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 2042992 | 102149.6 | 1805890 | 1805890 | 3453002985 | لا | 0 |  | مسحوب | منهجية القيمة المكتسبة | 88 | 100 | 2015-08-24 | 2016-08-19 | 2021-03-20 | 2021-03-20 |  |  | ضعف كفاءة المقاول الفنية |  | 40.9928 | 30.9458 | مسحوب | No
2100074653 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 37326088.5 | 1866304.425 | 21643924.3 | 21643924.3 | 2050001536 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-02-01 | 2020-01-10 | 2020-01-07 | 2020-01-07 | 2020-01-10 |  | لا يوجد تأخير |  | 39.1987 | 21.5549 | منجز | No
2100066732 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 2072219 | 103610.95 | 1937583.5 | 1937583.5 | 3450007082 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 94 | 100 | 2015-07-08 | 2016-07-03 | 2020-07-16 | 2020-07-16 | 2016-07-03 |  | ضعف كفاءة المقاول الفنية |  | 43.5259 | 29.6308 | منجز | No
2100103040 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 130094760 | 6504738 | 94352400.91 | 94352400.91 | 1010022661 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 92 | 100 | 2014-12-16 | 2016-04-09 | 2023-03-31 | 2023-03-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال | أخرى | 37.2633 | 25.0313 | Failed | No
2100192404 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 69579407.11 | 3478970.3555 | 17781028.84 | 17781028.84 | 4030157663 | لا | 0 | 180709018482 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2013-06-15 | 2015-05-24 | 2018-09-03 | 2018-09-03 | 2015-05-24 |  |  |  | 39.2391 | 21.4933 | منجز | No
2100200196 | وزارة الداخلية / المديرية العامة للسجون | تشييد | ذات اولوية عالية وعاجلة | 58929988.44 | 2946499.422 | 56008584.51 | 56008584.51 | 1010184923 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2016-01-04 | 2021-10-30 | 2022-04-25 | 2022-04-25 | 2021-10-30 |  |  |  | 43.9535 | 26.3715 | منجز | No
2100104646 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1326438 | 66321.9 | 830745.6 | 830745.6 | 4650005144 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 55 | 100 | 2007-09-28 | 2008-09-16 | 2012-02-16 | 2012-02-16 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | مسحوب | No
2100074631 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 9493623.9 | 474681.195 | 8290098.75 | 7800300.87 | 1010107136 | لا | 0 | 180809042406 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 93.68 | 100 | 2015-07-12 | 2017-06-20 | 2020-11-03 | 2020-11-03 |  | 2017-06-20 | ضعف كفاءة المقاول الفنية |  | 47.3078 | 24.1522 | منجز | No
2100073194 | المؤسسة العامة للحبوب | تشييد | ذات اولوية عالية | 1998150 | 99907.5 | 1998150 | 1998150 | 1010080249 | لا | 0 | 190309094381 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-04-11 | 2019-03-31 | 2019-03-31 | 2019-03-31 | 2019-03-31 |  | اخرى |  | 36.5491 | 28.4895 | منجز | No
2100071691 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 18494100 | 924705 | 17338035.27 | 17338035.27 | 4031045076 | لا | 0 | 181001197064 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 95 | 100 | 2019-07-03 | 2020-06-27 | 2023-04-04 | 2023-04-04 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 40.4601 | 21.2649 | Failed | No
2100023026 | وزارة الدفاع / الإدارة الهندسية والاشغال بقوات الدفاع الجوي | تشييد | ذات اولوية متوسطة | 2285610.6 | 114280.53 | 2285610.6 | 2057049.54 | 1010307343 | لا | 0 | 200101060538 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2020-06-02 | 2021-05-22 | 2021-11-11 | 2021-11-11 | 2021-05-22 |  | أوامر سامية |  | 36.5174 | 28.3819 | منجز | No
2100094404 | وزارة النقل والخدمات اللوجستية / منطقة جازان | تشييد | ذات اولوية متوسطة | 53749967.6 | 2687498.38 | 16851886.29 | 16851886.29 | 5855007548 | لا | 0 | 181109319736 | فسخ العقد | الكميات التي تم تركيبها | 42 | 100 | 2009-08-18 | 2010-08-07 | 2017-08-22 | 2017-08-22 |  |  | اخرى |  | 43.1311 | 17.3392 | مسحوب | No
2100067244 | أمانة / عسير | تشييد | ذات اولوية عالية | 1299950 | 64997.5 | 1106678.26 | 1106678.26 | 5860005901 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-06-29 | 2020-06-22 | 2020-08-23 | 2020-08-23 | 2020-06-22 |  |  |  | 41.917 | 19.7563 | منجز | No
2100047946 | أمانة / الحدود الشمالية | إشراف | ذات اولوية عالية وعاجلة | 1501200 | 75060 | 347500 | 347500 | 1010948531 | لا | 0 | 190509007761 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-09-30 | 2021-09-30 | 2021-09-14 | 2021-09-14 | 2021-09-30 |  | اخرى |  | 43.5129 | 29.6294 | منجز | No
2100088535 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | تشييد | ذات اولوية عالية | 16757625.15 | 837881.2575 | 15080491.03 | 14448400.91 | 2051043740 | لا | 0 | 190501016875 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-08-21 | 2021-05-20 | 2022-04-30 | 2022-04-30 | 2021-05-20 |  | تأخرصرف المستحقات المالية |  | 36.5638 | 28.4092 | منجز | No
2100024743 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية منخفضة | 38913708.87 | 1945685.4435 | 1534041.94 | 1534041.94 | 2050022550 | لا | 0 | 180909072871 | جاري | منهجية القيمة المكتسبة | 92.5 | 99.1 | 2012-10-15 | 2015-09-13 | 2022-07-31 | 2022-07-31 |  |  | لا يوجد تأخير |  | 38.5177 | 27.6133 | Failed | No
2100054051 | وزارة النقل والخدمات اللوجستية / منطقة جازان | تشييد | ذات اولوية عالية | 134813798.45 | 6740689.9225 | 97066010.81 | 97066010.81 | 5900000115 | لا | 0 | 181109306645 | جاري | الكميات التي تم تركيبها | 92.76 | 100 | 2009-08-15 | 2012-07-13 | 2022-12-30 | 2022-12-30 |  |  |  |  | 43.1082 | 17.2391 | متأخر | No
2100010953 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 945602 | 47280.1 | 0 | 0 | 2514000069 | لا | 0 |  | مسحوب | التكلفة المفوترة | 100 | 100 | 2006-05-08 | 2007-01-02 | 2008-09-19 | 2008-09-19 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | مسحوب | No
2100038264 | وزارة النقل والخدمات اللوجستية / منطقة جازان | تشييد | ذات اولوية متوسطة | 9628160.58 | 481408.029 | 7254500 | 7254500 | 5858014051 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 57.04 | 100 | 2010-11-25 | 2013-04-28 | 2019-12-02 | 2019-12-02 |  |  | اخرى |  | 42.9393 | 17.2377 | مسحوب | No
2100040644 | هيئة المدن الصناعية ومناطق التقنية | تصميم | ذات اولوية عالية | 62709569 | 3135478.45 | 62707590 | 62707590 | 1010213041 | لا | 0 |  | جاري الاستلام الإبتدائي | التكلفة المفوترة | 100 | 100 | 2017-12-24 | 2021-11-23 | 2022-12-24 | 2022-12-24 |  |  | لا يوجد تأخير |  | 46.6816 | 24.7082 | منتظم | No
2100067642 | أمانة / جدة | تشييد | ذات اولوية عالية وعاجلة | 12772168 | 638608.4 | 11022565 | 11022565 | 4650007032 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 86 | 86 | 2015-06-03 | 2017-05-13 | 2020-11-15 | 2020-11-15 | 2017-05-13 | 2020-11-15 | اخرى |  | 39.1744 | 21.5308 | منجز | No
2100191251 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية عالية | 43073848 | 2153692.4 | 15663925.1 | 10723583.85 | 5850022870 | لا | 0 | 200301073036 | جاري | منهجية القيمة المكتسبة | 87.65 | 97.03 | 2021-02-13 | 2022-07-30 | 2022-11-01 | 2022-11-01 |  |  |  |  | 42.8784 | 18.3057 | متأخر | No
2100041856 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية متوسطة | 25639230 | 1281961.5 | 6849508.89 | 6849508.89 | 1010184370 | لا | 0 |  | مسحوب | منهجية القيمة المكتسبة | 13.37 | 100 | 2012-02-04 | 2014-01-13 | 2022-12-31 | 2022-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 37.2857 | 24.8709 | مسحوب | No
2100017824 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 933579 | 46678.95 | 392040 | 392040 | 2057001038 | لا | 0 |  | مسحوب | التكلفة المفوترة | 38 | 100 | 2012-07-13 | 2013-04-09 | 2017-05-25 | 2017-05-25 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | مسحوب | No
2100076705 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تصميم | ذات اولوية عالية وعاجلة | 39822000 | 1991100 | 40902013.55 | 40902013.55 | 2051060090 | لا | 0 | 180809059328 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 97 | 100 | 2017-05-11 | 2022-05-10 | 2022-05-10 | 2022-05-10 | 2022-05-10 |  |  | أخرى | 49.5646 | 27.0097 | منجز | No
2100002402 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 62113501 | 3105675.05 | 49751810.05 | 49751810.05 | 1010010506 | لا | 0 | 180809056899 | جاري | منهجية القيمة المكتسبة | 80 | 100 | 2018-03-26 | 2021-01-18 | 2023-05-08 | 2023-05-08 |  |  | أوامر سامية |  | 49.6626 | 27.0037 | متأخر | No
2100097602 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية متوسطة | 40346415 | 2017320.75 | 25695121.15 | 25695121.15 | 1010108475 | لا | 0 | 180909078930 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 96 | 100 | 2011-03-20 | 2014-02-15 | 2022-06-30 | 2022-06-30 |  |  | اخرى |  | 37.1543 | 25.4786 | متأخر | No
2100100354 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 59428291.2 | 2971414.56 | 56493109.67 | 56493109.67 | 1010010506 | لا | 0 | 180901100820 | جاري | منهجية القيمة المكتسبة | 94 | 99 | 2019-04-07 | 2021-04-11 | 2023-09-28 | 2023-09-28 |  |  | لا يوجد تأخير |  | 49.5648 | 27.1019 | منتظم | No
2100055812 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 55720652 | 2786032.6 | 51884141.5 | 51884141.5 | 1010010506 | لا | 0 | 180809049091 | جاري | منهجية القيمة المكتسبة | 91 | 97 | 2017-12-03 | 2019-12-01 | 2023-11-07 | 2023-11-07 |  |  | التنسيق مع أصحاب المصلحه (خدمات |  | 49.5648 | 27.1019 | متأخر | No
2100084641 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | دراسات هندسية | ذات اولوية عالية وعاجلة | 21283625 | 1064181.25 | 2411555.76 | 2411555.76 | 4030221168 | لا | 0 | 180901069850 | جاري | تكلفة العمل المنجز | 17 | 88 | 2018-12-12 | 2023-12-11 | 2023-12-11 | 2023-12-11 |  |  |  |  | 49.1857 | 27.4991 | خدمات عامة | No
2100015175 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | دراسات هندسية | ذات اولوية عالية وعاجلة | 35718000 | 1785900 | 36122127.49 | 36122127.49 | 2051060090 | لا | 0 | 180101000028 | جاري | تكلفة العمل المنجز | 95 | 91 | 2018-09-06 | 2023-09-05 | 2023-09-05 | 2023-09-05 |  |  |  | أخرى | 49.5945 | 26.9784 | خدمات عامة | No
2100205424 | وزارة الثقافة | تصميم وتشييد | ذات اولوية عالية | 27483924.18 | 1374196.209 | 15000000 | 15000000 | 1010323762 | لا | 0 |  | منجز – استلام نهائي | اخرى | 100 | 100 | 2021-09-16 | 2022-04-12 | 2022-02-28 | 2022-02-28 | 2022-04-12 | 2022-05-11 |  |  | 50.2019 | 26.2818 | منجز | No
2100027403 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية منخفضة | 217827222 | 10891361.1 | 152779590.15 | 152779590.15 | 1010012911 | لا | 0 | 180909079374 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99.2 | 100 | 2012-02-07 | 2015-01-06 | 2020-12-02 | 2020-12-02 | 2015-01-06 |  | لا يوجد تأخير |  | 36.1259 | 28.8962 | منجز | No
2100003463 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية متوسطة | 5604550 | 280227.5 | 4572334.51 | 3857589.47 | 1010178884 | لا | 0 | 180909075109 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 85.56 | 100 | 2014-01-15 | 2015-12-25 | 2020-04-21 | 2020-04-21 | 2015-12-25 |  | لا يوجد تأخير |  | 34.9455 | 29.2847 | منجز | No
2100069856 | وزارة الخارجية | تشييد | ذات اولوية عالية | 42883792.5 | 2144189.625 | 31213306.5 | 31213060.5 | 0 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 89 | 89 | 2013-06-24 | 2015-10-13 | 2016-12-28 | 2016-12-28 |  |  | ضعف كفاءة المقاول الفنية |  | 7.433 | 9.0709 | مسحوب | No
2100105324 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 21266635 | 1063331.75 | 11478686 | 11478686 | 2050011871 | نعم | 11483686 | 180809054095 | مسحوب | منهجية القيمة المكتسبة | 56.42 | 100 | 2017-12-19 | 2020-12-20 | 2023-09-06 | 2023-09-06 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 45.9295 | 28.4247 | مسحوب | No
2100106411 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 14865900 | 743295 | 3339503.66 | 3339503.66 | 2050011871 | لا | 0 | 181101244938 | مسحوب | منهجية القيمة المكتسبة | 42.75 | 100 | 2019-01-09 | 2021-01-10 | 2023-07-09 | 2023-07-09 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 49.9342 | 26.5557 | مسحوب | No
2100016461 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 6999505 | 349975.25 | 1731439.22 | 1731439.22 | 2050011871 | لا | 0 | 180801048559 | مسحوب | منهجية القيمة المكتسبة | 37.3 | 100 | 2018-10-25 | 2020-10-26 | 2023-10-26 | 2023-10-26 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 49.9815 | 26.5957 | مسحوب | No
2100040025 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 17581512 | 879075.6 | 16750866 | 16750866 | 4700106511 | لا | 0 | 180809052827 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-11-12 | 2018-12-12 | 2022-05-07 | 2022-05-07 | 2018-12-12 |  | أوامر تغيير |  | 38.233 | 24.0266 | منجز | No
2100190750 | شركة المياه الوطنية / منطقة الجوف | تشييد | ذات اولوية عالية | 28168012.73 | 1408400.6365 | 13197740.09 | 13197740.09 | 1010144696 | لا | 0 | 200901103709 | جاري | تكلفة العمل المنجز | 51.7 | 100 | 2021-01-06 | 2022-06-22 | 2022-12-31 | 2022-12-31 |  |  |  |  | 40.2114 | 29.9762 | Failed | No
2100084582 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 21263915 | 1063195.75 | 21263915 | 21263915 | 4030023505 | لا | 0 | 180701027960 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-10-16 | 2020-10-15 | 2022-09-29 | 2022-09-29 | 2020-10-15 |  |  |  | 38.2114 | 23.9951 | منجز | No
2100079870 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 26780355 | 1339017.75 | 16515663.2 | 16515663.2 | 1010190571 | لا | 0 | 180801054851 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 92.78 | 99.67 | 2019-03-04 | 2021-08-06 | 2021-11-10 | 2021-11-10 | 2021-08-06 |  | لا يوجد تأخير |  | 39.7981 | 22.2624 | منجز | No
2100000862 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية وعاجلة | 51200000 | 2560000 | 766746.44 | 766746.44 | 2055006347 | لا | 0 | 190401038359 | جاري | منهجية القيمة المكتسبة | 6.65 | 69.38 | 2019-07-23 | 2022-07-23 | 2022-12-31 | 2022-12-31 |  |  | لا يوجد تأخير |  | 50.1464 | 26.1842 | Failed | No
2100016483 | وزارة التعليم | تشييد | ذات اولوية عالية | 5564735.47 | 278236.7735 | 4699038.44 | 4699038.44 | 1010466292 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2011-02-19 | 2012-12-09 | 2019-01-01 | 2019-01-01 | 2012-12-09 |  |  |  | 36.5638 | 28.4092 | منجز | No
2100037671 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | تشييد | ذات اولوية متوسطة | 61486508.41 | 3074325.4205 | 55329743.81 | 55329743.81 | 1010047800 | لا | 0 | 180709032102 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2016-02-28 | 2018-07-12 | 2021-09-24 | 2021-09-24 | 2018-07-12 |  | لا يوجد تأخير |  | 36.5638 | 28.4092 | منجز | No
2100011535 | المؤسسة العامة للتقاعد | تشييد | ذات اولوية عالية | 1819185381.14 | 90959269.057 | 1247391414.33 | 1247391414.33 | 1010242485 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2015-03-16 | 2020-09-01 | 2021-11-30 | 2021-11-30 | 2020-09-01 |  | اخرى |  | 39.126 | 21.7258 | منجز | No
2100071072 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | تشييد | ذات اولوية متوسطة | 160735407.18 | 8036770.359 | 160142412.7 | 143738356 | 1010047800 | لا | 0 | 180709032022 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-07-23 | 2017-12-25 | 2021-09-24 | 2021-09-24 | 2017-12-25 |  | لا يوجد تأخير |  | 36.5638 | 28.4092 | منجز | No
2100096843 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2556565 | 127828.25 | 206330 | 206330 | 4700010050 | لا | 0 |  | مسحوب | التكلفة المفوترة | 11 | 100 | 2010-11-27 | 2012-08-14 | 2012-08-12 | 2012-08-12 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | مسحوب | No
2100006893 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2500320 | 125016 | 676249 | 676249 | 1010245520 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 26 | 100 | 2010-12-12 | 2012-02-27 | 2021-12-30 | 2021-12-30 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | مسحوب | No
2100056792 | أمانة / تبوك | دراسة الجدوى | ذات اولوية عالية | 1323000 | 66150 | 97146 | 0 | 3550034877 | لا | 0 | 200309018878 | ايقاف كلي | مدفوعات ساعات العمل | 18 | 29 | 2019-07-06 | 2023-01-03 | 2024-01-01 | 2024-01-01 |  |  | عدم وجود كوادر كافية في الجهه لادارة المشروع |  |  |  | Failed | Yes
2100071304 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 420592 | 21029.6 | 0 | 0 | 1116001737 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 93 | 100 | 2019-02-10 | 2019-12-26 | 2022-01-09 | 2022-01-09 | 2019-12-26 |  | ضعف كفاءة المقاول الفنية |  |  |  | منجز | No
2100109384 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 933579 | 46678.95 | 0 | 0 | 2057001038 | لا | 0 |  | جاري | التكلفة المفوترة | 45 | 100 | 2012-07-13 | 2013-04-10 | 2023-12-15 | 2023-12-15 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | Failed | No
2100106934 | وزارة التعليم | تشييد | ذات اولوية عالية | 8888768 | 444438.4 | 6817275 | 3050065.3 | 1010060469 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2016-02-17 | 2017-11-08 | 2020-11-25 | 2020-11-25 | 2017-11-08 |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | منجز | No
2100057816 | الجمارك السعودية | تشييد | ذات اولوية عالية | 287300186.59 | 14365009.3295 | 245758308.7 | 245758308.7 | 1010196220 | لا | 0 | 180709028081 | جاري | تكلفة العمل المنجز | 93 | 100 | 2014-04-02 | 2017-02-27 | 2022-04-19 | 2022-04-19 |  |  | ضعف كفاءة المقاول الفنية |  | 34.9228 | 29.2226 | متأخر | No
2100088336 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البحرية | تشييد | ذات اولوية متوسطة | 10869118.26 | 543455.913 | 4191304 | 4191304 | 1010219247 | لا | 0 | 201209150449 | جاري | الكميات التي تم تركيبها | 60 | 100 | 2020-04-23 | 2021-08-16 | 2022-10-31 | 2022-10-31 |  |  |  |  | 49.6098 | 26.9797 | Failed | No
2100108150 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البحرية | تشييد | ذات اولوية متوسطة | 28995000 | 1449750 | 24400974.83 | 24400974.83 | 1010256208 | لا | 0 | 180801061918 | جاري | الكميات التي تم تركيبها | 90 | 100 | 2019-04-02 | 2020-12-07 | 2023-02-28 | 2023-02-28 |  |  |  |  | 39.1914 | 21.5642 | Failed | No
2100019224 | وزارة التعليم | تشييد | ذات اولوية عالية | 2732957 | 136647.85 | 654600 | 0 | 4650003991 | لا | 0 |  | مسحوب | التكلفة المفوترة | 24 | 100 | 2010-02-14 | 2011-02-02 | 2013-05-13 | 2013-05-13 |  |  | ضعف كفاءة المقاول الفنية |  | 38.0623 | 24.0861 | مسحوب | Yes
2100021663 | وزارة الخارجية | تصميم | ذات اولوية عالية | 940000 | 47000 | 376000 | 376000 | 1010417337 | لا | 0 | 181209472786 | جاري | تكلفة العمل المنجز | 40 | 100 | 2014-11-13 | 2015-11-06 | 2015-11-06 | 2015-11-06 |  |  | عدم اكتمال أو ضعف أعمال التصميم والدراسات |  | -66.8918 | 10.4784 | Failed | No
2100011126 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البرية | تشييد | ذات اولوية متوسطة | 1951372.5 | 97568.625 | 1951372.5 | 1951372.5 | 3550023146 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-02-19 | 2021-04-19 | 2021-03-01 | 2021-03-01 | 2021-04-19 |  | تأخرصرف المستحقات المالية |  | 36.6345 | 28.3335 | منجز | No
2100000792 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البرية | تشييد | ذات اولوية متوسطة | 4970805 | 248540.25 | 4970805 | 4970805 | 1010209661 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-10-25 | 2021-04-07 | 2021-12-31 | 2021-12-31 | 2021-04-07 |  | تأخرصرف المستحقات المالية |  | 36.5627 | 28.3807 | منجز | No
2100194084 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 3999996 | 199999.8 | 4184792.04 | 4184792.04 | 4605000749 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 80 | 86 | 2019-12-03 | 2021-07-02 | 2021-08-25 | 2021-08-25 | 2021-07-02 |  |  |  | 39.3386 | 22.128 | منجز | No
2100195020 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 9915911.05 | 495795.5525 | 6585812.5 | 6585812.5 | 1010045354 | لا | 0 | 181101278701 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-09-26 | 2022-09-10 | 2022-09-10 | 2022-09-10 | 2022-09-10 |  |  |  | 40.4511 | 21.2747 | منجز | No
2100104871 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات الجوية | تشييد | ذات اولوية عالية | 445211113.33 | 22260555.6665 | 218480082.89 | 218480082.89 | 4030007353 | لا | 0 | 191001155347 | جاري | الكميات التي تم تركيبها | 42 | 60 | 2020-02-02 | 2023-10-30 | 2023-10-30 | 2023-10-30 |  |  | تصاريح أعمال التنفيذ |  | 50.0599 | 26.4003 | متأخر | No
2100046045 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 6253034 | 312651.7 | 4689776 | 0 | 1116002399 | لا | 0 |  | مسحوب | التكلفة المفوترة | 75 | 42 | 2011-01-16 | 2012-07-01 | 2023-01-15 | 2023-01-15 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | مسحوب | Yes
2100024640 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 13834762 | 691738.1 | 2700000 | 9638.133 | 1010192035 | لا | 0 |  | جاري | التكلفة المفوترة | 86 | 100 | 2015-11-24 | 2016-11-18 | 2022-03-01 | 2022-03-01 |  |  | ضعف كفاءة المقاول الفنية |  | 47.5649 | 26.8621 | Failed | No
2100097274 | أمانة / تبوك | دراسة الجدوى | ذات اولوية متوسطة | 4749240 | 237462 | 4749240 | 4749240 | 4030280962 | لا | 0 |  | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2018-12-10 | 2020-11-29 | 2020-11-29 | 2020-11-29 | 2020-11-29 |  | اخرى |  |  |  | منجز | No
2100069565 | المؤسسة العامة للري | تشييد | ذات اولوية عالية | 91531196 | 4576559.8 | 86367310 | 86367310 | 2251002422 | لا | 0 | 181109289426 | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2013-11-10 | 2018-01-18 | 2022-03-15 | 2022-03-15 | 2018-01-18 |  | ضعف كفاءة المقاول الفنية |  | 49.6237 | 25.4375 | منجز | No
2100016951 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البرية | تشييد | ذات اولوية متوسطة | 4276329.75 | 213816.4875 | 4276329.75 | 4276329.75 | 4030075785 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2019-08-21 | 2020-07-25 | 2021-09-21 | 2021-09-21 | 2020-07-25 |  | لا يوجد تأخير |  | 39.2042 | 21.5016 | منجز | No
2100065365 | أمانة / الجوف | تشييد | ذات اولوية عالية | 333000 | 16650 | 299000 | 299000 | 3400014158 | لا | 0 | 191101095671 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-09-17 | 2020-03-12 | 2020-03-12 | 2020-03-12 | 2020-03-12 |  | اخرى |  | 40.2961 | 30.1674 | منجز | No
2100088550 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات الجوية | تشييد | ذات اولوية متوسطة | 2581250 | 129062.5 | 2581250 | 2581250 | 2051027134 | لا | 0 | 180909067293 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-06-06 | 2019-05-26 | 2021-12-31 | 2021-12-31 | 2019-05-26 |  | ضعف كفاءة المقاول الفنية |  | 40.4416 | 21.2866 | منجز | No
2200212951 | شركة المياه الوطنية / منطقة الرياض | إشراف | ذات اولوية عالية | 3291600 | 164580 | 687132.91 | 530322.91 | 1010322448 | لا | 0 |  | جاري | التكلفة المفوترة | 13.79 | 13.79 | 2021-10-28 | 2023-10-29 | 2023-10-29 | 2023-10-29 |  |  |  |  | 46.7939 | 24.653 | خدمات عامة | No
2100072590 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 19018255.24 | 950912.762 | 13740208.7 | 13740208.7 | 1011011290 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 76 | 90 | 2019-05-14 | 2021-05-03 | 2023-07-30 | 2023-07-30 |  |  |  | تم إنذار المقاول كتابيا | 43.5175 | 29.6343 | متأخر | No
2100205601 | هيئة المدن الصناعية ومناطق التقنية | تشييد | ذات اولوية عالية | 20500000 | 1025000 | 3857795 | 3857795 | 4030087384 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 28 | 30 | 2021-06-28 | 2023-04-04 | 2023-04-04 | 2023-04-04 |  |  |  |  | 39.9838 | 29.7741 | منتظم | No
2100072870 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 4889000 | 244450 | 4889000 | 4741233 | 3400011214 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-04-14 | 2016-01-08 | 2017-11-19 | 2017-11-19 | 2016-01-08 |  | اخرى |  | 36.5279 | 28.3861 | منجز | No
2100011325 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 899361.75 | 44968.0875 | 899361.75 | 899361.75 | 1010270830 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2019-05-12 | 2020-07-05 | 2020-10-03 | 2020-10-03 | 2020-07-05 |  | اخرى |  |  |  | منجز | No
2100057713 | وزارة الدفاع / الإدارة الهندسية والاشغال بقوات الدفاع الجوي | تشييد | ذات اولوية متوسطة | 13448610 | 672430.5 | 13448610 | 12137370.53 | 4031038849 | لا | 0 | 190601014633 | جاري | الكميات التي تم تركيبها | 97 | 100 | 2019-09-29 | 2021-06-20 | 2021-12-31 | 2021-12-31 |  |  | أوامر سامية |  | 42.793 | 18.2409 | Failed | No
2100072310 | أمانة / جازان | تشييد | ذات اولوية عالية | 19453924 | 972696.2 | 6353626 | 6353626 | 5900007895 | لا | 0 | 180401002070 | جاري | تكلفة العمل المنجز | 76 | 100 | 2018-12-13 | 2020-04-24 | 2021-11-11 | 2021-11-11 |  |  | ضعف كفاءة المقاول الفنية |  | 42.9541 | 16.7108 | Failed | No
2100108721 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 3660986.1 | 183049.305 | 2802426.1 | 1597892.26 | 3553000454 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2016-02-09 | 2017-05-05 | 2021-09-30 | 2021-09-30 | 2017-05-05 |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | منجز | No
2100052102 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 4000000 | 200000 | 4058778.76 | 4058778.76 | 1010051001 | لا | 0 | 190401103422 | منجز – استلام ابتدائي | اخرى | 98 | 100 | 2019-06-09 | 2020-11-22 | 2021-05-30 | 2021-05-30 | 2020-11-22 |  | ضعف كفاءة المقاول الفنية |  | 42.568 | 16.8959 | منجز | No
2100053476 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 328779.61 | 16438.9805 | 328779.61 | 328779.61 | 4046000743 | لا | 0 | 181009114810 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-07-03 | 2019-06-28 | 2019-06-28 | 2019-06-28 | 2019-06-28 |  |  |  | 40.9894 | 21.0595 | منجز | No
2100102093 | أمانة / العاصمة المقدسة | دراسات هندسية | ذات اولوية متوسطة | 10000000 | 500000 | 9385000 | 9385000 | 1010323435 | لا | 0 | 180501007835 | منجز – استلام نهائي | اخرى | 100 | 100 | 2018-08-01 | 2020-07-31 | 2021-07-05 | 2021-07-05 | 2020-07-31 | 2020-09-01 | اخرى |  | 39.8995 | 21.3684 | منجز | No
2100076860 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 25155960 | 1257798 | 22027234.42 | 22027234.42 | 4030008335 | لا | 0 | 180909105671 | منجز – استلام نهائي | تكلفة العمل المنجز | 91 | 91 | 2015-04-02 | 2017-03-02 | 2018-11-19 | 2018-11-19 | 2017-03-02 | 2020-12-09 |  |  | 39.8854 | 21.3709 | منجز | No
2100026714 | وزارة الدفاع / الإدارة الهندسية والاشغال بقوات الدفاع الجوي | تشييد | ذات اولوية متوسطة | 26132823.94 | 1306641.197 | 26132823.94 | 22406283.25 | 1010006082 | لا | 0 | 181101302119 | جاري | الكميات التي تم تركيبها | 97 | 100 | 2019-03-23 | 2021-03-13 | 2022-02-08 | 2022-02-08 |  |  | أوامر سامية |  | 46.7006 | 24.6757 | Failed | No
2100079881 | شركة المياه الوطنية | تشييد | ذات اولوية عالية وعاجلة | 749721093.92 | 37486054.696 | 633762984.55 | 633762984.55 | 1010012911 | نعم | 18511859 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 99.31 | 100 | 2017-07-04 | 2019-06-19 | 2021-12-11 | 2021-12-11 | 2019-06-19 |  | لا يوجد تأخير |  | 41.0165 | 30.9619 | منجز | No
2100043293 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 6042705 | 302135.25 | 1632825.12 | 1632825.12 | 1010466292 | لا | 0 |  | مسحوب | التكلفة المفوترة | 64 | 37 | 2011-05-14 | 2012-11-05 | 2023-06-15 | 2023-06-15 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | مسحوب | No
2100042523 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2650008 | 132500.4 | 0 | 0 | 3552000129 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0.5 | 100 | 2011-05-16 | 2012-07-09 | 2012-08-11 | 2012-08-11 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | مسحوب | No
2100067395 | أمانة / تبوك | تشييد | ذات اولوية عالية | 3187400 | 159370 | 2865210 | 2865210 | 3552000023 | لا | 0 | 190909086930 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-07-05 | 2020-06-29 | 2020-06-29 | 2020-06-29 | 2020-06-29 |  | ضعف كفاءة المقاول الفنية |  | 35.7243 | 27.3457 | منجز | No
2100072015 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 19736710 | 986835.5 | 15937500 | 15937500 | 1011010795 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 88 | 100 | 2014-05-26 | 2016-05-14 | 2023-05-28 | 2023-05-28 |  |  | ضعف كفاءة المقاول الفنية |  | 43.5294 | 29.6222 | متأخر | No
2100099584 | أمانة / العاصمة المقدسة | دراسة بيئية | ذات اولوية متوسطة | 1699995 | 84999.75 | 1676818 | 1676818 | 4031067724 | لا | 0 |  | جاري الاستلام الإبتدائي | مدفوعات ساعات العمل | 93.94 | 93.94 | 2018-10-21 | 2020-04-20 | 2020-04-20 | 2020-04-20 |  |  | اخرى |  | 39.8672 | 21.3714 | Failed | No
2100195370 | رئاسة أمن الدولة / قوات الأمن الخاصة | تشييد | ذات اولوية عالية | 41080154 | 2054007.7 | 36971651.72 | 36971651.72 | 1010127437 | لا | 0 | 200801062182 | ايقاف جزئي | الكميات التي تم تركيبها | 85 | 90 | 2020-11-19 | 2022-05-05 | 2023-02-08 | 2023-02-08 |  |  |  |  | 46.5648 | 24.8786 | متأخر | No
2100153134 | الهيئة العامة للموانئ | توريد وتركيب | ذات اولوية عالية وعاجلة | 13636945 | 681847.25 | 12273250.5 | 12273250.5 | 7001746549 | لا | 0 | 190701174013 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-10-10 | 2021-03-24 | 2021-12-30 | 2021-12-30 | 2021-03-24 |  |  |  | 38.2045 | 23.9747 | منجز | No
2100108651 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 1721554 | 86077.7 | 840297 | 840297 | 2511482400 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2013-06-04 | 2014-04-30 | 2014-05-07 | 2014-05-07 | 2014-04-30 |  | ضعف كفاءة المقاول الفنية |  | 45.975 | 28.4334 | منجز | No
2100013554 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 35510828.232 | 1775541.4116 | 23624906.48 | 23624906.48 | 1132002624 | لا | 0 |  | جاري | التكلفة المفوترة | 74 | 100 | 2014-12-02 | 2015-05-06 | 2022-03-20 | 2022-03-20 |  |  | ضعف كفاءة المقاول الفنية |  | 43.4919 | 25.8758 | Failed | No
2100048075 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 1000000 | 50000 | 250000 | 250000 | 4031046036 | لا | 0 | 6046345 | جاري الاستلام الإبتدائي | التكلفة المفوترة | 25 | 100 | 2014-04-11 | 2016-04-18 | 2017-10-23 | 2017-10-23 |  |  |  |  | 39.8668 | 21.3331 | Failed | No
2100084652 | وزارة البيئة والمياة والزراعة | دراسات هندسية | ذات اولوية متوسطة | 2782500 | 139125 | 1669500 | 1669500 | 4031089496 | لا | 0 | 190301085470 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-04-25 | 2020-01-01 | 2000-01-01 | 2000-01-01 | 2020-01-01 |  |  |  | 40.4939 | 21.2935 | منجز | No
2100094430 | وزارة الداخلية / مديرية الأمن العام | تشييد | ذات اولوية متوسطة | 2269150.8 | 113457.54 | 2000624.33 | 2000624.33 | 1010250698 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-10-29 | 2020-10-29 | 2021-10-29 | 2021-10-29 | 2020-10-29 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  |  |  | منجز | No
2100033994 | وزارة الداخلية / مديرية الأمن العام | تشييد | ذات اولوية متوسطة | 2364406.8 | 118220.34 | 1225048.28 | 1225048.28 | 1010250698 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-01-29 | 2021-01-29 | 2021-04-29 | 2021-04-29 | 2021-01-29 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 43.5508 | 29.5946 | منجز | No
2100074616 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 8732120.64 | 436606.032 | 1846248 | 1846248 | 1010046644 | لا | 0 |  | مسحوب | التكلفة المفوترة | 21 | 100 | 2015-07-22 | 2017-07-11 | 2018-01-09 | 2018-01-09 |  |  | ضعف كفاءة المقاول الفنية |  | 50.4171 | 26.5891 | مسحوب | No
2100074491 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2995525 | 149776.25 | 526970 | 526970 | 4042002319 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 30 | 100 | 2011-01-03 | 2012-02-27 | 2021-08-03 | 2021-08-03 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 40.2691 | 20.1489 | مسحوب | No
2100031754 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 16045814 | 802290.7 | 0 | 0 | 5950010121 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 80 | 100 | 2012-12-09 | 2020-06-11 | 2020-06-11 | 2020-06-11 |  |  | ضعف كفاءة المقاول الفنية |  | 44.2381 | 17.5921 | مسحوب | No
2100195381 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 1737960 | 86898 | 1737960 | 1737960 | 1010161812 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-12-07 | 2021-04-06 | 2021-04-06 | 2021-04-06 | 2021-04-06 |  |  |  | 39.6016 | 24.4683 | منجز | No
2100009354 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 3680863.2 | 184043.16 | 3680863.2 | 3680863.2 | 4032003067 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2019-06-03 | 2020-01-07 | 2020-02-20 | 2020-02-20 | 2020-01-07 | [5 empty] | منجز | No
2100056770 | شركة المياه الوطنية | دراسة الجدوى | ذات اولوية عالية وعاجلة | 26222000 | 1311100 | 26800878.64 | 24885241 | 2051011487 | لا | 0 |  | جاري | التكلفة المفوترة | 82.25 | 82.25 | 2018-06-10 | 2019-10-09 | 2022-07-22 | 2022-07-22 |  |  | لا يوجد تأخير |  | 38.9401 | 31.6776 | خدمات عامة | No
2100006355 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية منخفضة | 32676452.54 | 1633822.627 | 21897888.8 | 21897888.8 | 1010220371 | لا | 0 | 180909076918 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 81.07 | 100 | 2012-06-24 | 2014-11-26 | 2022-09-30 | 2022-09-30 | 2014-11-26 |  | لا يوجد تأخير |  | 36.5218 | 28.3851 | منجز | No
2100041204 | وزارة الداخلية / مديرية الأمن العام | تشييد | ذات اولوية متوسطة | 2313980.93 | 115699.0465 | 2313960.77 | 2313960.77 | 1010250698 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-10-02 | 2020-10-02 | 2020-10-02 | 2020-10-02 | 2020-10-02 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 43.5162 | 17.6659 | منجز | No
2100015455 | وزارة التعليم | تشييد | ذات اولوية عالية | 10292385 | 514619.25 | 6399690 | 6399690 | 1010051817 | لا | 0 |  | مسحوب | التكلفة المفوترة | 65 | 100 | 2013-04-13 | 2015-04-03 | 2015-10-31 | 2015-10-31 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | مسحوب | No
2100072100 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 7469932.5 | 373496.625 | 7449977 | 7449977 | 1010409973 | لا | 0 | 180601013746 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-11-07 | 2020-04-30 | 2020-05-01 | 2020-05-01 | 2020-04-30 |  | ضعف كفاءة المقاول الفنية |  | 49.6026 | 25.3799 | منجز | No
2100038555 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 97075049 | 4853752.45 | 91005549 | 91005549 | 5855000147 | لا | 0 |  | ايقاف جزئي | الكميات التي تم تركيبها | 98.4 | 100 | 2008-07-03 | 2011-06-01 | 2019-05-06 | 2019-05-06 |  |  | اخرى |  | 42.8209 | 18.2166 | Failed | No
2100046163 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 790977 | 39548.85 | 0 | 0 | 5901014606 | لا | 0 | 406029901186 | مسحوب | تكلفة العمل المنجز | 36 | 100 | 2011-02-28 | 2019-02-11 | 2019-02-19 | 2019-02-19 |  |  | اخرى |  | 42.5356 | 17.3734 | مسحوب | No
2100070442 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 22694773.75 | 1134738.6875 | 21768731.87 | 21768731.87 | 1010066115 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2010-06-08 | 2012-05-15 | 2018-06-07 | 2018-06-07 | 2012-05-15 | 2020-02-19 |  |  | 39.226 | 21.4724 | منجز | No
2100062193 | أمانة / عسير | تشييد | ذات اولوية عالية | 5999665 | 299983.25 | 199000 | 199000 | 5858010028 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 4 | 100 | 2014-12-24 | 2015-09-19 | 2022-07-31 | 2022-07-31 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 43.3426 | 17.5663 | مسحوب | No
2100027554 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية | 10736722 | 536836.1 | 8450135.2 | 8450135.2 | 4650011120 | لا | 0 | 181009126015 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 90 | 100 | 2012-11-24 | 2015-10-23 | 2022-05-31 | 2022-05-31 |  |  | لا يوجد تأخير |  | 39.3411 | 25.5467 | Failed | No
2100047806 | أمانة / جازان | تشييد | ذات اولوية عالية وعاجلة | 1675000 | 83750 | 0 | 0 | 5906328881 | لا | 0 |  | مسحوب | منهجية القيمة المكتسبة | 0 | 12 | 2019-10-19 | 2020-10-13 | 2020-10-13 | 2020-10-13 |  |  | ضعف كفاءة المقاول الفنية |  | 42.7254 | 16.7715 | مسحوب | No
2100011421 | وزارة التعليم | تشييد | ذات اولوية عالية | 13367122 | 668356.1 | 10773306 | 10773306 | 1010211349 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-12-27 | 2016-12-16 | 2021-08-22 | 2021-08-22 | 2016-12-16 |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | منجز | No
2100091851 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 1470500 | 73525 | 472000 | 472000 | 2511004747 | لا | 0 | 190309094013 | مسحوب | منهجية القيمة المكتسبة | 32 | 100 | 2015-01-20 | 2016-01-16 | 2022-01-01 | 2022-01-01 |  |  | ضعف كفاءة المقاول الفنية |  | 44.3175 | 29.1504 | مسحوب | No
2100030811 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية | 67536739.9 | 3376836.995 | 56009393.78 | 56009393.78 | 4650004469 | لا | 0 | 180809047967 | جاري | منهجية القيمة المكتسبة | 86.3 | 100 | 2015-02-22 | 2016-08-06 | 2023-01-23 | 2023-01-23 |  |  | لا يوجد تأخير |  | 39.6457 | 24.2586 | Failed | No
2100097112 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية | 15000000 | 750000 | 1555996.31 | 1555996.31 | 4650016168 | لا | 0 | 180201000180 | جاري | منهجية القيمة المكتسبة | 14.9 | 100 | 2018-03-22 | 2021-02-17 | 2023-06-30 | 2023-06-30 |  |  | لا يوجد تأخير |  | 39.293 | 25.6774 | Failed | No
2100019493 | أمانة / جازان | تشييد | ذات اولوية عالية | 799995 | 39999.75 | 790855 | 790855 | 5911015317 | لا | 0 | 200709173588 | منجز – استلام ابتدائي | اخرى | 99 | 99 | 2019-10-12 | 2020-02-09 | 2020-01-27 | 2020-01-27 | 2020-02-09 |  | ضعف كفاءة المقاول الفنية |  | 42.6107 | 16.9094 | منجز | No
2100075950 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 3970600 | 198530 | 3478114.4 | 3478114.4 | 5950009015 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 90 | 90 | 2018-11-14 | 2020-01-02 | 2019-11-03 | 2019-11-03 | 2020-01-02 |  |  |  | 44.1898 | 17.831 | منجز | No
2100194401 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 1782000 | 89100 | 396284.63 | 396284.63 | 4030162068 | لا | 363226 | 211201025600 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2021-06-06 | 2022-11-19 | 2022-05-25 | 2022-05-25 | 2022-11-19 |  | ضعف كفاءة المقاول الفنية |  | 41.8523 | 19.415 | منجز | No
2100088885 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البرية | تشييد | ذات اولوية متوسطة | 2699813 | 134990.65 | 2699813 | 2699813 | 5850029760 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-10-17 | 2020-03-05 | 2020-03-05 | 2020-03-05 | 2020-03-05 |  | لا يوجد تأخير |  | 46.1527 | 28.3008 | منجز | No
2100191866 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية وعاجلة | 33047444.86 | 1652372.243 | 11649300.7 | 10687938.05 | 4030023505 | لا | 0 | 200201138045 | جاري | منهجية القيمة المكتسبة | 63.62 | 100 | 2020-11-11 | 2021-10-31 | 2022-12-31 | 2022-12-31 |  |  |  |  | 39.5948 | 24.507 | Failed | No
2100086844 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية وعاجلة | 68838500 | 3441925 | 29836908.61 | 29836908.61 | 2050011871 | لا | 0 | 181009158666 | جاري | منهجية القيمة المكتسبة | 53.7 | 100 | 2018-01-07 | 2020-12-05 | 2022-06-28 | 2022-06-28 |  |  | لا يوجد تأخير |  | 38.7891 | 23.7842 | Failed | No
2100085083 | وزارة الصحة / مكة المكرمة | تشييد | ذات اولوية منخفضة | 5965460 | 298273 | 413713.97 | 413713.97 | 4031048910 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 16 | 20 | 2016-04-17 | 2016-10-11 | 2022-12-25 | 2022-12-25 |  |  | عدم وجود مبالغ في البنود تغطي الأعمال المرصودة |  | 39.2929 | 22.1781 | مسحوب | No
2100022326 | وزارة الصحة / حفر الباطن | تشييد | ذات اولوية عالية | 42296800 | 2114840 | 3679561 | 3679561 | 2055002421 | لا | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 12 | 100 | 2015-03-10 | 2017-02-15 | 2017-12-31 | 2017-12-31 |  |  | اخرى |  | 45.9541 | 28.309 | Failed | No
2100017356 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 628900 | 31445 | 628900 | 0 | 1123002131 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2017-12-03 | 2018-11-18 | 2021-06-17 | 2021-06-17 | 2018-11-18 |  |  |  | 44.9002 | 26.2417 | منجز | Yes
2100076436 | أمانة / جازان | تشييد | ذات اولوية عالية | 859290 | 42964.5 | 716712.17 | 716712.17 | 5903025849 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 83 | 100 | 2018-08-11 | 2019-08-27 | 2019-07-28 | 2019-07-28 | 2019-08-27 |  | اخرى |  | 42.5383 | 17.2667 | منجز | No
2100101566 | وزارة الصحة / حائل | تشييد | ذات اولوية عالية | 1183245 | 59162.25 | 1183245 | 1183245 | 1010262386 | لا | 0 | 201209030809 | جاري | تكلفة العمل المنجز | 100 | 100 | 2019-11-30 | 2020-04-25 | 2020-07-09 | 2020-07-09 |  |  | تصاريح أعمال التنفيذ |  | 41.6922 | 27.5705 | Failed | No
2100104683 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية وعاجلة | 49994944 | 2499747.2 | 23556744.37 | 23556744.37 | 2050011871 | لا | 0 | 181009158689 | جاري | منهجية القيمة المكتسبة | 60.95 | 100 | 2018-01-01 | 2020-11-29 | 2022-12-31 | 2022-12-31 |  |  | لا يوجد تأخير |  | 39.587 | 24.4769 | Failed | No
2100105814 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية وعاجلة | 67039888 | 3351994.4 | 23706342.4822 | 15019321.79 | 4650033361 | لا | 0 | 190201035289 | جاري | منهجية القيمة المكتسبة | 39.7 | 69 | 2019-06-09 | 2022-05-07 | 2024-04-01 | 2024-04-01 |  |  | لا يوجد تأخير |  | 39.6593 | 24.3972 | Failed | No
2100095734 | وزارة الصحة / مكة المكرمة | تشييد | ذات اولوية متوسطة | 29417425 | 1470871.25 | 19652761 | 19652761 | 1010170119 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 68 | 100 | 2014-02-11 | 2017-11-27 | 2022-12-20 | 2022-12-20 |  |  | ضعف كفاءة المقاول الفنية |  | 40.1213 | 21.6601 | مسحوب | No
2100024861 | أمانة / حفر الباطن | تشييد | ذات اولوية متوسطة | 128718450 | 6435922.5 | 103863003 | 103863003 | 1011010795 | لا | 0 | 190701112449 | جاري | تكلفة العمل المنجز | 83 | 92 | 2019-11-19 | 2023-04-25 | 2023-04-25 | 2023-04-25 |  |  |  |  | 45.9667 | 28.3736 | متأخر | No
2100081535 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 6842850 | 342142.5 | 0 | 0 | 1010234015 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 65 | 100 | 2015-02-27 | 2016-08-20 | 2021-07-05 | 2021-07-05 |  |  | ضعف كفاءة المقاول الفنية |  | 46.4158 | 24.8987 | مسحوب | No
2100063991 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 2085790 | 104289.5 | 0 | 0 | 3555000646 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 100 | 100 | 2011-09-05 | 2012-08-30 | 2021-11-30 | 2021-11-30 |  |  | أوامر تغيير |  | 35.7243 | 27.3457 | مسحوب | No
2100022691 | شركة المياه الوطنية / منطقة المدينة المنورة | إشراف | ذات اولوية عالية وعاجلة | 22426775 | 1121338.75 | 20678412.44 | 20678412.44 | 1010322448 | لا | 0 | 180909078839 | جاري | التكلفة المفوترة | 0 | 0 | 2017-12-20 | 2020-12-19 | 2021-03-19 | 2021-03-19 |  |  | لا يوجد تأخير |  | 39.5456 | 24.3716 | خدمات عامة | No
2100035560 | وزارة الداخلية / مديرية الأمن العام | تشييد | ذات اولوية متوسطة | 2094697.5 | 104734.875 | 2094697.5 | 2094697.5 | 1010070662 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-11-10 | 2020-11-10 | 2021-01-10 | 2021-01-10 | 2020-11-10 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 46.1009 | 25.4101 | منجز | No
2100015142 | وزارة الداخلية / مديرية الأمن العام | تشييد | ذات اولوية متوسطة | 2300235 | 115011.75 | 81795 | 81795 | 3350012618 | لا | 0 |  | جاري | تكلفة العمل المنجز | 4 | 80 | 2020-03-16 | 2021-03-15 | 2021-03-15 | 2021-03-15 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.0382 | 27.9519 | Failed | No
2100081174 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 274000 | 13700 | 0 | 0 | 1010162003 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 79 | 15 | 2019-04-26 | 2020-07-19 | 2020-07-19 | 2020-07-19 | 2020-07-19 |  |  |  | 46.8828 | 23.4875 | منجز | No
2100194040 | وزارة الداخلية / المديرية العامة لحرس الحدود | تشييد | ذات اولوية عالية | 1749485.8 | 87474.29 | 1749485.8 | 1749485.8 | 7003878175 | لا | 0 | 210201150619 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2021-02-17 | 2022-02-17 | 2022-02-07 | 2022-02-07 | 2022-02-17 |  |  |  | 39.1581 | 21.4917 | منجز | No
2100194073 | وزارة الداخلية / المديرية العامة لحرس الحدود | تشييد | ذات اولوية عالية | 2887885.92 | 144394.296 | 0 | 0 | 1010214056 | لا | 0 | 200901013858 | مسحوب | تكلفة العمل المنجز | 10 | 100 | 2021-09-09 | 2021-12-10 | 2021-12-10 | 2021-12-10 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5839 | 16.8422 | مسحوب | No
2100091416 | أمانة / الجوف | تشييد | ذات اولوية عالية | 8098312.56 | 404915.628 | 8098312.56 | 8098312.56 | 3402001019 | لا | 0 | 191101306259 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-09-18 | 2020-09-12 | 2020-09-12 | 2020-09-12 | 2020-09-12 |  |  |  | 39.8888 | 29.8108 | منجز | No
2100023483 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية | 5407940 | 270397 | 5062898.31 | 5062898.31 | 4650016549 | لا | 0 | 190609010074 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-02-01 | 2020-01-10 | 2020-01-05 | 2020-01-05 |  | 2020-01-10 | لا يوجد تأخير |  | 38.1639 | 25.0626 | منجز | No
2100056416 | أمانة / الحدود الشمالية | دراسة الجدوى | ذات اولوية عالية وعاجلة | 1132800 | 56640 | 377599.958 | 377599.958 | 1010948538 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-10-29 | 2020-10-29 | 2020-10-17 | 2020-10-17 | 2020-10-29 |  | اخرى |  |  |  | منجز | No
2100048215 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 1092892.5 | 54644.625 | 0 | 0 | 3450010117 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 95 | 100 | 2019-06-11 | 2019-12-08 | 2020-12-01 | 2020-12-01 | 2019-12-08 |  | ضعف كفاءة المقاول الفنية |  | 41.595 | 30.6942 | منجز | No
2100021711 | أمانة / العاصمة المقدسة | الخدمات الاستشارية | ذات اولوية متوسطة | 9410434 | 470521.7 | 7515299 | 7515299 | 4031084298 | لا | 0 | 190201003669 | جاري | مدفوعات ساعات العمل | 70.46 | 70.46 | 2019-03-31 | 2022-10-26 | 2022-09-28 | 2022-09-28 |  |  | اخرى |  |  |  | خدمات عامة | No
2100023774 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية | 19670369 | 983518.45 | 17014368.48 | 17014368.48 | 4650015928 | لا | 0 | 181009130206 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 96 | 2014-12-15 | 2017-11-12 | 2021-03-21 | 2021-03-21 | 2017-11-12 |  | لا يوجد تأخير |  | 40.2357 | 23.2687 | منجز | No
2100028792 | أمانة / الرياض | تشييد | ذات اولوية عالية | 4528678.35 | 226433.9175 | 42150 | 0 | 1010218505 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 84 | 100 | 2015-10-28 | 2017-01-20 | 2017-01-20 | 2017-01-20 |  |  | تأخرصرف المستحقات المالية |  | 44.8167 | 20.4403 | Failed | Yes
2100012611 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 16629.25 | 831.4625 | 41364 | 0 | 1010240630 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 90 | 100 | 2013-08-16 | 2014-11-09 | 2019-09-22 | 2019-09-22 | 2014-11-09 |  | ضعف كفاءة المقاول الفنية |  | 46.6754 | 24.7131 | منجز | Yes
2100071013 | وزارة الداخلية / مديرية الأمن العام | تشييد | ذات اولوية متوسطة | 502283.25 | 25114.1625 | 379569.75 | 379569.75 | 1010174451 | لا | 0 |  | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-02-23 | 2020-08-23 | 2020-08-23 | 2020-08-23 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.8743 | 21.3659 | Failed | No
2100019154 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 1315950 | 65797.5 | 1315950 | 1315950 | 1010158252 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2020-02-11 | 2020-11-07 | 2020-11-14 | 2020-11-14 | 2020-11-07 |  | ضعف كفاءة المقاول الفنية |  | 41.0927 | 30.9762 | منجز | No
2100099271 | وزارة الداخلية / المديرية العامة لحرس الحدود | إشراف | ذات اولوية عالية | 37487491.38 | 1874374.569 | 35082488.92 | 35082488.92 | 1010321365 | لا | 0 | 180501010649 | جاري | تكلفة العمل المنجز | 94 | 98 | 2018-07-29 | 2023-04-29 | 2023-04-29 | 2023-04-29 |  |  | لا يوجد تأخير |  | 51.9973 | 19.0239 | خدمات عامة | No
2100084140 | وزارة الداخلية / المديرية العامة لحرس الحدود | تشييد | ذات اولوية عالية وعاجلة | 2062355.83 | 103117.7915 | 2062355.83 | 2062355.83 | 3401010075 | لا | 0 | 200501053939 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-02-19 | 2021-02-07 | 2021-09-19 | 2021-09-19 | 2021-02-07 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 37.9743 | 30.7266 | منجز | No
2100082283 | أمانة / تبوك | تشييد | ذات اولوية منخفضة | 12737140.1 | 636857.005 | 12737140 | 12737140 | 4650032626 | لا | 0 | 190309046031 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-10-23 | 2018-06-06 | 2016-05-11 | 2016-05-11 | 2018-06-06 |  | اخرى |  | 37.2661 | 25.0459 | منجز | No
2100035276 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 3856756 | 192837.8 | 3856756 | 3856756 | 5806014264 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-01-21 | 2020-07-07 | 2020-07-05 | 2020-07-05 | 2020-07-07 |  |  |  | 41.2428 | 19.9308 | منجز | No
2100190002 | وزارة البيئة والمياة والزراعة | ترميم | ذات اولوية متوسطة | 2959732 | 147986.6 | 1781994.02 | 1781994.02 | 1010273396 | لا | 0 | 201101387482 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2021-01-26 | 2021-08-20 | 2021-08-20 | 2021-08-20 | 2021-08-20 |  |  |  | 41.5813 | 19.8648 | منجز | No
2100069370 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية وعاجلة | 86737323.75 | 4336866.1875 | 62551483.8 | 62551483.8 | 4030004451 | لا | 0 |  | مسحوب | منهجية القيمة المكتسبة | 94 | 100 | 2009-04-04 | 2012-03-01 | 2022-07-18 | 2022-07-18 |  |  | ضعف كفاءة المقاول الفنية |  | 39.5838 | 24.5772 | مسحوب | No
2100085702 | شركة المياه الوطنية / منطقة المدينة المنورة | إشراف | ذات اولوية عالية وعاجلة | 15930000 | 796500 | 15432025.59 | 15432025.59 | 2050101543 | لا | 0 | 180401005219 | جاري | تكلفة العمل المنجز | 0 | 0 | 2018-05-21 | 2021-05-20 | 2021-05-21 | 2021-05-21 |  |  | لا يوجد تأخير |  | 39.5861 | 24.4588 | خدمات عامة | No
2200213205 | وزارة الحرس الوطني / وكالة الشؤون الفنية | ترميم | ذات اولوية متوسطة | 524206.8 | 26210.34 | 230605.59 | 230605.59 | 1011014184 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 52 | 100 | 2022-02-02 | 2022-05-31 | 2022-12-24 | 2022-12-24 |  |  |  | تم إنذار المقاول كتابيا | 46.6855 | 24.7063 | Failed | No
2100095082 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 99283993.15 | 4964199.6575 | 61249192.23 | 45482172.71 | 4030174978 | لا | 0 | 180401003454 | جاري | الكميات التي تم تركيبها | 68 | 100 | 2018-08-28 | 2021-02-13 | 2023-01-02 | 2023-01-02 |  |  | ضعف كفاءة المقاول الفنية |  | 41.7163 | 27.5048 | Failed | No
2100028136 | أمانة / جدة | تشييد | ذات اولوية عالية | 30383209 | 1519160.45 | 26746548.9 | 26746548.9 | 4030151328 | لا | 0 | 181001181486 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 96.5 | 100 | 2019-01-15 | 2020-12-23 | 2021-07-19 | 2021-07-19 | 2020-12-23 |  | اخرى |  | 39.2011 | 21.5207 | منجز | No
2100042836 | وزارة التجارة | تشييد | ذات اولوية عالية | 22914579 | 1145728.95 | 13037772 | 13037772 | 5857020213 | لا | 0 | 180301000639 | جاري | منهجية القيمة المكتسبة | 75 | 85 | 2018-07-11 | 2021-01-10 | 2022-03-16 | 2022-03-16 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.5807 | 16.8556 | متأخر | No
2100024415 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 985000 | 49250 | 232263 | 0 | 1017001594 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 24 | 100 | 2015-08-09 | 2017-01-30 | 2021-07-04 | 2021-07-04 |  |  | ضعف كفاءة المقاول الفنية |  | 45.5559 | 20.4467 | مسحوب | Yes
2100022606 | وزارة الداخلية / ديوان وزارة الداخلية | إشراف | ذات اولوية عالية وعاجلة | 628211208 | 31410560.4 | 557215708.8 | 551993294.27 | 1010382831 | لا | 0 |  | جاري | مدفوعات ساعات العمل | 93 | 93 | 2013-07-31 | 2016-07-14 | 2024-03-31 | 2024-03-31 |  |  | لا يوجد تأخير |  |  |  | خدمات عامة | No
2100030844 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3247342.963 | 162367.1481 | 41370 | 0 | 1010214105 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 80 | 100 | 2014-02-01 | 2015-04-27 | 2015-04-27 | 2015-04-27 | 2015-04-27 |  | ضعف كفاءة المقاول الفنية |  | 46.6809 | 24.7057 | منجز | Yes
2100083241 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 39871006 | 1993550.3 | 35095658 | 35095658 | 1010069549 | لا | 0 | 181109296216 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 88 | 92 | 2018-01-24 | 2019-07-18 | 2022-09-10 | 2022-09-10 | 2019-07-18 |  | التنسيق مع أصحاب المصلحه (خدمات |  | 41.7554 | 27.4628 | منجز | No
2100028280 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 15537759 | 776887.95 | 13983983 | 13983983 | 2251031375 | لا | 0 | 180909102028 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-05-25 | 2016-05-14 | 2021-08-31 | 2021-08-31 | 2016-05-14 |  | ضعف كفاءة المقاول الفنية |  | 49.7214 | 25.3768 | منجز | No
2100070000 | شركة المياه الوطنية / منطقة المدينة المنورة | دراسات هندسية | ذات اولوية عالية | 31567830 | 1578391.5 | 24153795 | 24153795 | 1010412691 | لا | 0 | 190301012149 | جاري | تكلفة العمل المنجز | 83.98 | 0 | 2019-07-21 | 2021-01-20 | 2022-06-30 | 2022-06-30 |  |  | لا يوجد تأخير |  | 39.6119 | 24.4589 | خدمات عامة | No
2100062344 | المؤسسة العامة لتحلية المياه المالحة | توريد | ذات اولوية عالية | 1590723854.64 | 79536192.732 | 1426924320.5 | 1426924320.5 | 2050071522 | لا | 0 | 180401002979 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-09-10 | 2021-07-31 | 2022-09-28 | 2022-09-28 | 2021-07-31 |  | تأخرصرف المستحقات المالية |  | 47.0235 | 24.9622 | منجز | No
2100027355 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2844911.6 | 142245.58 | 747860 | 0 | 1111001945 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 9 | 100 | 2015-02-10 | 2016-10-02 | 2018-01-16 | 2018-01-16 |  |  | ضعف كفاءة المقاول الفنية |  | 46.674 | 24.7107 | مسحوب | Yes
2100109012 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية وعاجلة | 921130388.78 | 46056519.439 | 669270976.86 | 669270976.86 | 1010014578 | لا | 0 | 180909089093 | جاري | مدفوعات ساعات العمل | 79.39 | 98.33 | 2010-06-28 | 2013-06-11 | 2024-12-31 | 2024-12-31 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | متأخر | No
2100076252 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 56388019.14 | 2819400.957 | 55200143 | 55200143 | 2251035252 | لا | 0 | 180101000007 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-09-24 | 2015-09-19 | 2018-11-30 | 2018-11-30 | 2015-09-19 |  |  |  | 49.5848 | 25.3741 | منجز | No
2100016111 | وزارة الدفاع / الإدارة الهندسية والاشغال بالخدمات الصحية | تشييد | ذات اولوية متوسطة | 1699084.65 | 84954.2325 | 1699084.65 | 1699084.65 | 1010305944 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2020-04-20 | 2021-10-27 | 2022-03-31 | 2022-03-31 | 2021-10-27 |  | لا يوجد تأخير |  | 46.68 | 24.7032 | منجز | No
2100056313 | وزارة الصحة / عسير | تشييد | ذات اولوية عالية وعاجلة | 13844048.78 | 692202.439 | 453352.04 | 0 | 2051027988 | لا | 0 | 200301126843 | جاري | تكلفة العمل المنجز | 5 | 100 | 2020-09-16 | 2022-09-16 | 2024-08-09 | 2024-08-09 |  |  | موافقات | تم تمديد الجدول الزمني | 42.1662 | 18.9611 | Failed | Yes
2100022175 | وزارة الصحة / عسير | تشييد | ذات اولوية عالية وعاجلة | 42663930.39 | 2133196.5195 | 29571176.97 | 29571176.97 | 1010159118 | لا | 0 | 181009119713 | جاري | تكلفة العمل المنجز | 92 | 100 | 2012-10-05 | 2014-04-05 | 2023-04-21 | 2023-04-21 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.5222 | 18.2029 | Failed | No
2100190400 | وزارة البيئة والمياة والزراعة | ترميم | ذات اولوية عالية وعاجلة | 927150 | 46357.5 | 0 | 0 | 1010524294 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 7 | 100 | 2021-04-27 | 2021-11-20 | 2021-11-20 | 2021-11-20 |  |  | ضعف كفاءة المقاول الفنية |  | 46.2794 | 24.4914 | مسحوب | No
2200213555 | وزارة البيئة والمياة والزراعة | ترميم | ذات اولوية متوسطة | 2237461.85 | 111873.0925 | 1969939.65 | 1969939.65 | 1010335499 | لا | 0 |  | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 99 | 100 | 2021-09-19 | 2022-12-05 | 2022-12-05 | 2022-12-05 |  |  |  |  | 49.5687 | 26.9598 | متأخر | No
2100061456 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 791900 | 39595 | 0 | 0 | 3357008006 | لا | 0 | 200101060971 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-12-16 | 2019-12-10 | 2021-09-07 | 2021-09-07 | 2019-12-10 |  |  |  | 42.1232 | 26.5078 | منجز | No
2100094850 | أمانة / العاصمة المقدسة | دراسة بيئية | ذات اولوية متوسطة | 5226375 | 261318.75 | 5226375 | 5226375 | 1010463299 | لا | 0 | 191001150663 | منجز – استلام نهائي | مدفوعات ساعات العمل | 100 | 100 | 2019-09-24 | 2020-03-24 | 2020-03-24 | 2020-03-24 | 2020-03-24 | 2020-07-02 | اخرى |  |  |  | منجز | No
2100001610 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية | 44351480.53 | 2217574.0265 | 25242437.13 | 20798776.87 | 1116003901 | لا | 0 | 180709022904 | ايقاف كلي | تكلفة العمل المنجز | 57 | 94 | 2015-01-17 | 2016-12-17 | 2024-12-31 | 2024-12-31 |  |  | تأخرصرف المستحقات المالية |  | 41.2691 | 19.9232 | Failed | No
2100008374 | مستشفى الملك فيصل التخصصي ومركز الأبحاث | تشييد | ذات اولوية عالية | 17745715.55 | 887285.7775 | 15915177.37 | 15147447.54 | 2252004545 | لا | 0 | 200309016198 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-01-21 | 2019-01-15 | 2021-11-04 | 2021-11-04 | 2019-01-15 |  | أوامر تغيير |  | 46.6751 | 24.6714 | منجز | No
2100012876 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 15494439.99 | 774721.9995 | 10197395 | 0 | 1111000356 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 73 | 100 | 2014-08-03 | 2016-03-25 | 2020-05-04 | 2020-05-04 |  |  | ضعف كفاءة المقاول الفنية |  | 46.674 | 24.7131 | Failed | Yes
2100022573 | مستشفى الملك فيصل التخصصي ومركز الأبحاث | الخدمات الاستشارية | ذات اولوية عالية | 14210880 | 710544 | 13898240.64 | 11463838.03 | 1010359384 | لا | 0 | 190801055282 | جاري الاستلام الإبتدائي | مدفوعات ساعات العمل | 97.64 | 97.64 | 2019-10-01 | 2021-09-30 | 2023-01-31 | 2023-01-31 |  |  | لا يوجد تأخير |  | 46.6767 | 24.6711 | منتظم | No
2100031964 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 15034775.4 | 751738.77 | 1365180 | 0 | 4650020435 | لا | 0 |  | مسحوب | التكلفة المفوترة | 16 | 100 | 2013-10-29 | 2015-07-22 | 2024-01-15 | 2024-01-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | Yes
2100041381 | أمانة / جدة | دراسات هندسية | ذات اولوية متوسطة | 2074800 | 103740 | 2074800 | 2074800 | 4030257071 | لا | 0 | 200201067403 | منجز – استلام نهائي | اخرى | 93 | 93 | 2020-01-29 | 2020-10-21 | 2020-10-21 | 2020-10-21 | 2020-10-21 | 2020-10-22 | اخرى |  | 39.1715 | 21.5049 | منجز | No
2100047972 | أمانة / الرياض | دراسات هندسية | ذات اولوية متوسطة | 17285625 | 864281.25 | 13864829.87 | 13864829.87 | 1010464778 | لا | 0 |  | جاري | التكلفة المفوترة | 80 | 80 | 2018-05-20 | 2020-05-09 | 2021-07-01 | 2021-07-01 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  |  |  | خدمات عامة | No
2100052021 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 876592.5 | 43829.625 | 0 | 0 | 1116005202 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-12-23 | 2019-12-08 | 2019-12-08 | 2019-12-08 | 2019-12-08 |  | ضعف كفاءة المقاول الفنية |  | 46.6809 | 24.7157 | منجز | No
2100044004 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 5779540 | 288977 | 4874233.481 | 0 | 1010064540 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-02-16 | 2017-11-08 | 2017-11-09 | 2017-11-09 | 2017-11-08 |  |  |  | 46.663 | 24.7219 | منجز | Yes
2100050794 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 5381500 | 269075 | 2221000 | 2221000 | 1010158252 | لا | 0 | 181101259432 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 99 | 2019-01-13 | 2021-01-01 | 2021-08-01 | 2021-08-01 | 2021-01-01 |  |  |  | 43.5096 | 29.627 | منجز | No
2100066905 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 3335000 | 166750 | 1867600 | 1867600 | 1122002403 | لا | 0 | 191201044811 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-01-06 | 2021-08-09 | 2023-05-29 | 2023-05-29 | 2021-08-09 |  | ضعف كفاءة المقاول الفنية |  | 43.7408 | 28.7614 | منجز | No
2100082040 | أمانة / الحدود الشمالية | تشييد | ذات اولوية متوسطة | 367420 | 18371 | 367420 | 367420 | 3453003166 | لا | 0 | 190409006909 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-12-30 | 2019-12-26 | 2019-10-18 | 2019-10-18 | 2019-12-26 |  |  |  | 41.0121 | 30.9671 | منجز | No
2100095686 | جامعة شقراء | تشييد | ذات اولوية عالية | 30743008.87 | 1537150.4435 | 2679400.4 | 2679400.4 | 1010114475 | لا | 0 | 181101257884 | ايقاف جزئي | تكلفة العمل المنجز | 100 | 100 | 2019-01-27 | 2019-11-23 | 2022-02-09 | 2022-02-09 |  |  | أوامر تغيير |  | 45.1446 | 25.177 | Failed | No
2100078175 | جامعة شقراء | تشييد | ذات اولوية عالية | 108903512 | 5445175.6 | 53888658.7 | 53888658.7 | 1010003091 | لا | 0 | 180709031849 | مسحوب | تكلفة العمل المنجز | 55 | 100 | 2013-01-23 | 2016-01-08 | 2019-09-22 | 2019-09-22 |  |  | ضعف كفاءة المقاول الفنية |  | 45.1429 | 25.1774 | مسحوب | No
2200214244 | أمانة / الرياض | دراسات هندسية | ذات اولوية متوسطة | 14711950 | 735597.5 | 8384650 | 14 | 1010327067 | لا | 0 | 21010101006475 | جاري | تكلفة العمل المنجز | 56.9 | 46.3 | 2021-08-12 | 2024-08-11 | 2024-08-11 | 2024-08-11 |  |  |  |  | 46.7349 | 24.7663 | خدمات عامة | No
2100092105 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 2706500 | 135325 | 1562699.5 | 742500 | 1010181249 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 55 | 70 | 2018-07-17 | 2020-03-09 | 2023-07-30 | 2023-07-30 |  |  | ضعف كفاءة المقاول الفنية | مخطط لسحبه وإعادة ترسيته | 43.5322 | 29.613 | متأخر | No
2100098313 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 4217250 | 210862.5 | 4217250 | 4217250 | 3450002829 | لا | 0 | 181001193184 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-09-04 | 2020-02-25 | 2021-09-22 | 2021-09-22 | 2020-02-25 |  | ضعف كفاءة المقاول الفنية |  | 38.6732 | 31.6571 | منجز | No
2200213592 | وزارة البيئة والمياة والزراعة | ترميم | ذات اولوية متوسطة | 1180133.85 | 59006.6925 | 1180133.85 | 1180133.85 | 1010335499 | لا | 0 | 190201032783 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-03-25 | 2020-06-21 | 2020-06-21 | 2020-06-21 | 2020-06-21 |  |  |  | 49.3653 | 23.167 | منجز | No
2200213404 | أمانة / الجوف | تشييد | ذات اولوية عالية وعاجلة | 7129756.2 | 356487.81 | 3872910 | 3872910 | 3452004161 | لا | 0 | 200309019639 | جاري | تكلفة العمل المنجز | 98 | 100 | 2019-02-14 | 2020-02-09 | 2023-02-15 | 2023-02-15 |  |  |  |  | 38.2216 | 30.5155 | Failed | No
2100017426 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2097500 | 104875 | 1676136.6 | 0 | 1010211585 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 95 | 100 | 2015-10-08 | 2017-03-31 | 2020-01-31 | 2020-01-31 | 2017-03-31 |  | ضعف كفاءة المقاول الفنية |  | 46.7001 | 24.7019 | منجز | Yes
2100089320 | الهيئة العامة للموانئ | تشييد | ذات اولوية منخفضة | 27640468.12 | 1382023.406 | 16995407.4 | 16995407.4 | 2051056418 | نعم | 1159667 | 210101081064 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 61 | 100 | 2020-05-02 | 2020-10-26 | 2021-06-30 | 2021-06-30 | 2020-10-26 |  | ضعف كفاءة المقاول الفنية |  | 49.6721 | 27.0201 | منجز | No
2100105512 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 14926650 | 746332.5 | 12627315.53 | 12627315.53 | 1010224518 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 93.14 | 100 | 2018-12-02 | 2020-12-02 | 2021-02-13 | 2021-02-13 |  | 2020-12-02 | لا يوجد تأخير |  | 46.6761 | 24.745 | منجز | No
2100045006 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 231260 | 11563 | 0 | 0 | 1115001965 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 98 | 100 | 2019-10-20 | 2020-10-14 | 2021-12-19 | 2021-12-19 | 2020-10-14 |  |  |  | 46.674 | 24.7219 | منجز | No
2100065240 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 11765290 | 588264.5 | 3329900 | 0 | 1011000444 | لا | 0 |  | جاري | تكلفة العمل المنجز | 62 | 23 | 2019-02-28 | 2020-08-21 | 2022-09-28 | 2022-09-28 |  |  |  |  | 46.6919 | 24.7069 | Failed | Yes
2100012703 | وزارة الخارجية | تشييد | لم تعد تحتاجها الجهة | 110803992.34 | 5540199.617 | 84104502.08 | 84104502.08 | 0 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 73 | 100 | 2015-09-10 | 2017-09-10 | 2021-02-01 | 2021-02-01 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 28.3372 | -15.4063 | مسحوب | No
2100191575 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية وعاجلة | 12327802.98 | 616390.149 | 11034596.56 | 11034596.56 | 1010328073 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99.13 | 100 | 2021-02-14 | 2021-10-13 | 2021-10-13 | 2021-10-13 | 2021-10-13 |  |  |  | 46.6134 | 24.4689 | منجز | No
2100062860 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4870870 | 243543.5 | 1232845.1 | 0 | 1185000614 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 21 | 100 | 2014-08-26 | 2016-02-17 | 2022-11-18 | 2022-11-18 |  |  | ضعف كفاءة المقاول الفنية |  | 44.861 | 20.4658 | مسحوب | Yes
2100189836 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية عالية | 9121650 | 456082.5 | 4633545.6 | 4633545.6 | 1116002556 | لا | 0 | 180709028330 | جاري | الكميات التي تم تركيبها | 70 | 100 | 2013-06-30 | 2016-05-27 | 2021-07-24 | 2021-07-24 |  |  |  |  | 42.8638 | 19.0969 | Failed | No
2200213640 | وزارة البيئة والمياة والزراعة | أخرى | ذات اولوية متوسطة | 62370 | 3118.5 | 62370 | 62370 | 5855033786 | لا | 0 | 190801109669 | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2019-09-08 | 2019-12-05 | 2019-12-05 | 2019-12-05 | 2019-12-05 |  |  |  | 41.0787 | 19.1281 | منجز | No
2200213415 | أمانة / الجوف | تشييد | ذات اولوية عالية وعاجلة | 2583672 | 129183.6 | 2352315.72 | 2352315.72 | 3350000106 | لا | 0 | 211103054893 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 86 | 2020-09-13 | 2022-09-22 | 2022-10-14 | 2022-10-14 | 2022-09-22 |  |  |  | 37.9812 | 30.7109 | منجز | No
2200213102 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية وعاجلة | 2397500 | 119875 | 994902.8 | 994902.8 | 1010336711 | لا | 0 |  | جاري | تكلفة العمل المنجز | 99.77 | 100 | 2021-10-21 | 2022-06-21 | 2022-06-21 | 2022-06-21 |  |  |  |  | 46.7948 | 24.6524 | متأخر | No
2100028346 | جامعة القصيم | تشييد | ذات اولوية عالية وعاجلة | 52932040 | 2646602 | 12086747.8 | 12086747.8 | 1010028011 | نعم | 12086747.8 |  | فسخ العقد | تكلفة العمل المنجز | 13 | 100 | 2007-12-12 | 2009-06-04 | 2009-06-04 | 2009-06-04 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 43.7729 | 26.3523 | مسحوب | No
2200213706 | وزارة البيئة والمياة والزراعة | أخرى | ذات اولوية متوسطة | 474662.5 | 23733.125 | 367867.52 | 367867.52 | 4030147825 | لا | 0 | 200501090642 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2020-04-12 | 2021-06-28 | 2021-06-28 | 2021-06-28 | 2021-06-28 |  |  |  | 42.5706 | 16.8894 | منجز | No
2100091464 | وزارة الصحة / بيشة | ترميم | ذات اولوية عالية وعاجلة | 84232209 | 4211610.45 | 16000000 | 11000000 | 1010032384 | لا | 0 | 180501011246 | جاري | منهجية القيمة المكتسبة | 50.5 | 100 | 2018-11-14 | 2021-11-30 | 2022-12-30 | 2022-12-30 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5973 | 19.9716 | Failed | No
2100010754 | جامعة الطائف | تشييد | ذات اولوية متوسطة | 99237926.34 | 4961896.317 | 78554768.33 | 78554768.33 | 1010028011 | لا | 0 | 181109364740 | جاري | تكلفة العمل المنجز | 82 | 87 | 2019-01-10 | 2020-08-31 | 2023-08-02 | 2023-08-02 |  |  | لا يوجد تأخير |  | 40.4887 | 21.3265 | منتظم | No
2100095233 | وزارة الصحة / بيشة | تشييد | ذات اولوية عالية | 2299964 | 114998.2 | 0 | 0 | 7013406280 | نعم | 1291792.32 | 200639169665 | جاري | تكلفة العمل المنجز | 75 | 30 | 2022-05-09 | 2023-10-22 | 2023-10-22 | 2023-10-22 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.908 | 19.6434 | منتظم | No
2100190890 | ديوان المظالم | إشراف | ذات اولوية عالية | 4075425.9 | 203771.295 | 2521876.71 | 2521876.71 | 1010428289 | لا | 0 | 200101004899 | جاري | منهجية القيمة المكتسبة | 68 | 72 | 2019-12-10 | 2022-12-09 | 2022-12-09 | 2022-12-09 |  |  |  | تم تمديد الجدول الزمني | 46.6206 | 24.7089 | خدمات عامة | No
2100098582 | شركة المياه الوطنية / منطقة الحدود الشمالية | تشييد | ذات اولوية عالية | 32079175 | 1603958.75 | 32079174.5 | 22725735.36 | 1010158252 | لا | 0 | 181109309355 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2015-04-22 | 2017-09-23 | 2020-04-19 | 2020-04-19 |  | 2017-09-23 | لا يوجد تأخير |  | 43.5539 | 29.5954 | منجز | No
2100002170 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 10804782 | 540239.1 | 2326295 | 0 | 3350003498 | لا | 0 |  | ايقاف كلي | التكلفة المفوترة | 20 | 100 | 2013-07-03 | 2015-06-23 | 2022-09-21 | 2022-09-21 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | Failed | Yes
2100032362 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 6260446 | 313022.3 | 41735 | 0 | 1010056094 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 96.65 | 100 | 2014-09-20 | 2016-03-13 | 2019-09-13 | 2019-09-13 | 2016-03-13 |  | ضعف كفاءة المقاول الفنية |  | 46.6651 | 24.6951 | منجز | Yes
2100019364 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 2736700 | 136835 | 1494000 | 1494000 | 3450013972 | لا | 0 |  | مسحوب | منهجية القيمة المكتسبة | 34 | 34 | 2015-05-29 | 2020-09-15 | 2020-09-15 | 2020-09-15 |  |  | تأخرصرف المستحقات المالية |  | 42.2463 | 30.3332 | مسحوب | No
2100191170 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 16709000 | 835450 | 14530354.5 | 14530354.5 | 1010276827 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 95 | 100 | 2020-10-06 | 2021-04-06 | 2021-05-22 | 2021-05-22 | 2021-04-06 |  |  |  | 39.9057 | 21.3945 | منجز | No
2100087430 | شركة المياه الوطنية / منطقة الحدود الشمالية | تشييد | ذات اولوية عالية | 4966465 | 248323.25 | 4966465 | 4966465 | 1010239020 | لا | 0 | 181001165722 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-07-03 | 2020-06-11 | 2020-05-14 | 2020-05-14 |  | 2020-06-11 | لا يوجد تأخير |  | 38.6644 | 31.6517 | منجز | No
2100002671 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 92967075 | 4648353.75 | 73001884.59 | 73001884.59 | 4030007856 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 94.27 | 100 | 2015-03-30 | 2016-03-19 | 2022-01-31 | 2022-01-31 | 2016-03-19 |  | لا يوجد تأخير |  | 39.1139 | 21.3408 | منجز | No
2100051844 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 4516665.2 | 225833.26 | 511256.78 | 337264.01 | 1010213931 | لا | 0 |  | مسحوب | التكلفة المفوترة | 9 | 100 | 2014-01-23 | 2015-07-17 | 2023-04-30 | 2023-04-30 |  |  | ضعف كفاءة المقاول الفنية |  | 40.0549 | 29.8587 | مسحوب | No
2100043853 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 7290570 | 364528.5 | 2001377.7999 | 0 | 1010206151 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 79.93 | 100 | 2012-06-22 | 2015-11-21 | 2015-11-22 | 2015-11-22 |  |  | ضعف كفاءة المقاول الفنية |  | 45.2762 | 24.0651 | مسحوب | Yes
2100189593 | الهيئة الملكية للجبيل وينبع / مدينة جازان للصناعات الأساسية والتحويلية | تشييد | ذات اولوية منخفضة | 54000000 | 2700000 | 46498070 | 45527046.61 | 4030113058 | نعم | 45527046.61 | 180809048838 | فسخ العقد | الكميات التي تم تركيبها | 84 | 100 | 2017-11-12 | 2020-05-04 | 2021-11-24 | 2021-11-24 |  |  |  | مخطط لإعادة طرحه | 42.3238 | 17.3768 | مسحوب | No
2100105770 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية عالية | 36344535 | 1817226.75 | 31365439.34 | 30820960.33 | 5850017202 | لا | 0 | 181201408231 | جاري | منهجية القيمة المكتسبة | 86.7 | 96.14 | 2019-03-03 | 2022-01-29 | 2022-11-01 | 2022-11-01 |  |  | اخرى |  | 42.4989 | 18.2169 | متأخر | No
2100075235 | أمانة / عسير | تشييد | ذات اولوية عالية | 1748340 | 87417 | 0 | 0 | 5859002387 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 13 | 100 | 2015-10-03 | 2016-09-27 | 2021-09-14 | 2021-09-14 |  |  | تأخرصرف المستحقات المالية |  |  |  | مسحوب | No
2100094161 | أمانة / عسير | تشييد | ذات اولوية عالية | 1540676 | 77033.8 | 0 | 0 | 5855041956 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 45 | 100 | 2015-12-27 | 2016-12-27 | 2023-12-30 | 2023-12-30 |  |  | ضعف كفاءة المقاول الفنية |  | 41.9894 | 18.3398 | مسحوب | No
2100012434 | أمانة / عسير | تشييد | ذات اولوية عالية | 1731024 | 86551.2 | 1098299 | 1098299 | 5857048289 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 64 | 100 | 2015-06-11 | 2016-06-06 | 2021-12-30 | 2021-12-30 |  |  | تأخرصرف المستحقات المالية |  | 43.1379 | 18.0853 | مسحوب | No
2100025130 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 18511358.13 | 925567.9065 | 1798541.61 | 1798541.61 | 1010081983 | لا | 0 |  | مسحوب | التكلفة المفوترة | 10 | 100 | 2016-07-27 | 2019-01-11 | 2019-01-11 | 2019-01-11 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5604 | 25.3897 | مسحوب | No
2100040375 | وزارة الصحة / التجمع الاول | تشييد | لم تعد تحتاجها الجهة | 23325165 | 1166258.25 | 1742750 | 1742750 | 1018000245 | لا | 0 | 181009135090 | جاري | الكميات التي تم تركيبها | 10 | 100 | 2014-03-01 | 2015-05-31 | 2017-09-24 | 2017-09-24 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 44.7813 | 20.4716 | Failed | No
2100107925 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 39779056.8 | 1988952.84 | 35617153.62 | 35555176.34 | 1123000085 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-02-17 | 2020-09-24 | 2021-03-24 | 2021-03-24 | 2020-09-24 |  | أوامر تغيير | أخرى |  |  | منجز | No
2100037730 | وزارة النقل والخدمات اللوجستية / منطقة حائل | تشييد | ذات اولوية متوسطة | 77978504 | 3898925.2 | 69930647 | 50225319 | 1010069549 | لا | 0 | 180701028872 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-07-21 | 2018-04-09 | 2021-06-06 | 2021-06-06 | 2018-04-09 |  |  |  | 41.6987 | 27.5004 | منجز | No
2100072951 | وزارة النقل والخدمات اللوجستية / منطقة القصيم | تشييد | ذات اولوية عالية | 20427090 | 1021354.5 | 13530910 | 13530910 | 1010184457 | لا | 0 | 181109344039 | مسحوب | الكميات التي تم تركيبها | 69.27 | 100 | 2010-06-15 | 2012-05-23 | 2014-01-03 | 2014-01-03 |  |  | اخرى |  | 43.0493 | 26.8792 | مسحوب | No
2100028571 | جامعة حفر الباطن | تشييد | ذات اولوية عالية وعاجلة | 29409580 | 1470479 | 23802116 | 23802116 | 2050011871 | لا | 0 | 190309099932 | ايقاف كلي | تكلفة العمل المنجز | 95 | 95 | 2014-03-06 | 2014-09-02 | 2022-03-31 | 2022-03-31 |  |  | تصاريح أعمال التنفيذ |  | 45.9448 | 28.2414 | Failed | No
2100033364 | وزارة التعليم | تشييد | ذات اولوية عالية | 6133055 | 306652.75 | 2373170 | 0 | 4030065868 | لا | 0 |  | مسحوب | التكلفة المفوترة | 39 | 100 | 2010-10-01 | 2012-05-24 | 2023-12-15 | 2023-12-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | Yes
2100092960 | الهيئة الملكية للجبيل وينبع / مدينة جازان للصناعات الأساسية والتحويلية | دراسة الجدوى | ذات اولوية متوسطة | 53875500 | 2693775 | 38993180.65 | 38993180.65 | 2051047662 | لا | 0 | 191001145286 | جاري | مدفوعات ساعات العمل | 66.4 | 66.52 | 2020-03-04 | 2025-03-03 | 2025-03-03 | 2025-03-03 |  |  | تأخرصرف المستحقات المالية |  | 42.3705 | 17.3454 | خدمات عامة | No
2100101813 | وزارة الصحة / الباحة | تشييد | ذات اولوية متوسطة | 15105282 | 755264.1 | 5470894.72 | 5470894.72 | 4030008659 | نعم | 4274149 | 181009166709 | مسحوب | الكميات التي تم تركيبها | 55 | 100 | 2017-09-18 | 2021-01-23 | 2021-01-23 | 2021-01-23 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال | أخرى | 41.4626 | 20.0141 | مسحوب | No
2100068110 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 7986457.5 | 399322.875 | 1460830.44 | 1460830.44 | 2050027937 | لا | 0 | 190909071601 | مسحوب | تكلفة العمل المنجز | 40 | 100 | 2019-06-09 | 2020-06-03 | 2021-02-01 | 2021-02-01 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 49.5888 | 25.3719 | مسحوب | No
2100101651 | جامعة القصيم | تشييد | ذات اولوية عالية | 15595293 | 779764.65 | 13864074.65 | 13864074.65 | 1010187466 | لا | 0 | 180709028697 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-04-20 | 2015-02-14 | 2022-06-16 | 2022-06-16 | 2015-02-14 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 43.994 | 26.1134 | منجز | No
2100041871 | وزارة الدفاع / الإدارة الهندسية والاشغال بقوات الدفاع الجوي | تشييد | ذات اولوية متوسطة | 3195577.4 | 159778.87 | 3195577.4 | 2479339.93 | 4031053186 | لا | 0 | 19080101252 | جاري | الكميات التي تم تركيبها | 85 | 100 | 2019-08-09 | 2021-04-24 | 2022-04-03 | 2022-04-03 |  |  | أوامر سامية |  | 40.4346 | 21.2788 | متأخر | No
2100024172 | وزارة التعليم | تشييد | ذات اولوية عالية | 12434603.28 | 621730.164 | 4775275 | 4615145.84 | 4030288443 | لا | 0 |  | مسحوب | التكلفة المفوترة | 88 | 100 | 2015-01-21 | 2017-01-11 | 2022-12-15 | 2022-12-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | No
2100042582 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1740313.12 | 87015.656 | 959595 | 959595 | 2511482400 | لا | 0 |  | مسحوب | التكلفة المفوترة | 60 | 100 | 2013-06-01 | 2014-04-27 | 2020-06-01 | 2020-06-01 |  |  | ضعف كفاءة المقاول الفنية |  | 45.975 | 28.4334 | مسحوب | No
2100043746 | أمانة / الجوف | تشييد | ذات اولوية عالية | 6410752.5 | 320537.625 | 4563502 | 4563502 | 3452000190 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 86 | 100 | 2014-09-10 | 2016-01-04 | 2016-01-04 | 2016-01-04 | 2016-01-04 |  | ضعف كفاءة المقاول الفنية |  | 37.3614 | 31.3296 | منجز | No
2100077803 | الهيئة الملكية للجبيل وينبع / مدينة جازان للصناعات الأساسية والتحويلية | مساحة | ذات اولوية متوسطة | 12224900 | 611245 | 8245326.5 | 7029558 | 1010320728 | لا | 0 | 181209449607 | جاري | مدفوعات ساعات العمل | 77.2 | 79.7 | 2017-11-27 | 2021-11-21 | 2023-04-18 | 2023-04-18 |  |  | اخرى |  | 42.3699 | 17.3494 | خدمات عامة | No
2100109760 | مدينة الملك فهد الطبية | تشييد | ذات اولوية عالية | 33421456 | 1671072.8 | 29993194.1 | 24471253.2 | 1010034808 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-05-29 | 2019-11-29 | 2021-03-24 | 2021-03-24 | 2019-11-29 |  |  |  | 46.702 | 24.686 | منجز | No
2100026062 | أمانة / تبوك | تصميم | ذات اولوية متوسطة | 944998 | 47249.9 | 629998 | 629998 | 5950029845 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-10-14 | 2020-04-11 | 2021-02-17 | 2021-02-17 | 2020-04-11 |  | اخرى |  |  |  | منجز | No
2100107144 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 17429342.28 | 871467.114 | 17429342.28 | 15481323.52 | 1010045581 | لا | 0 | 181009131223 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-08-13 | 2016-11-05 | 2021-10-22 | 2021-10-22 | 2016-11-05 |  | تأخرصرف المستحقات المالية |  | 46.7809 | 24.714 | منجز | No
2100096154 | الهيئة العامة للموانئ | تصميم | ذات اولوية عالية | 700000 | 35000 | 350000 | 350000 | 4030228354 | لا | 0 | 200801006426 | جاري | اخرى | 98 | 100 | 2019-09-11 | 2020-02-08 | 2023-01-15 | 2023-01-15 |  |  | لا يوجد تأخير |  | 39.1723 | 21.472 | Failed | No
2100110051 | مدينة الملك فهد الطبية | تشييد | ذات اولوية عالية | 1265344637.14 | 63267231.857 | 655945546.79 | 655945546.79 | 1010056779 | لا | 0 |  | جاري | تكلفة العمل المنجز | 58 | 100 | 2012-11-06 | 2022-10-22 | 2022-10-20 | 2022-10-20 |  |  | ضعف كفاءة المقاول الفنية |  | 46.702 | 24.686 | Failed | No
2100033434 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 9789798 | 489489.9 | 8001345.45 | 8001345.45 | 2050041707 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 85 | 100 | 2019-04-02 | 2021-03-11 | 2021-09-18 | 2021-09-18 | 2021-03-11 |  |  |  | 50.2026 | 26.2306 | منجز | No
2100006495 | وزارة التعليم | تشييد | ذات اولوية عالية | 7094973.04 | 354748.652 | 6371385 | 6371385 | 4030176726 | لا | 0 | 190409049543 | ايقاف جزئي | التكلفة المفوترة | 90 | 100 | 2018-04-30 | 2019-12-21 | 2021-01-01 | 2021-01-01 |  |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | Failed | No
2100070884 | وزارة النقل والخدمات اللوجستية / منطقة جازان | تشييد | ذات اولوية متوسطة | 52841732 | 2642086.6 | 8946400 | 8946400 | 1010152168 | لا | 0 | 181109305004 | مسحوب | الكميات التي تم تركيبها | 21.59 | 100 | 2014-05-22 | 2016-10-23 | 2019-12-01 | 2019-12-01 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 43.1311 | 17.3392 | مسحوب | No
2100199592 | جامعة تبوك | إشراف | ذات اولوية عالية وعاجلة | 21746150.4 | 1087307.52 | 10206884.8 | 9378737.6 | 1010322156 | لا | 0 | 211001039670 | جاري | مدفوعات ساعات العمل | 60.77 | 60.77 | 2021-10-14 | 2023-10-13 | 2023-10-13 | 2023-10-13 |  |  |  |  | 36.4768 | 28.3941 | خدمات عامة | No
2100003076 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1540489 | 77024.45 | 1284637.45 | 0 | 4030149405 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 45 | 50 | 2019-06-12 | 2020-02-07 | 2020-11-23 | 2020-11-23 | 2020-02-07 |  | ضعف كفاءة المقاول الفنية |  | 46.7271 | 22.2863 | منجز | Yes
2100001665 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 14227841.71 | 711392.0855 | 0 | 0 | 1010081983 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 1 | 100 | 2019-05-05 | 2021-04-24 | 2021-05-31 | 2021-05-31 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5604 | 25.3897 | مسحوب | No
2100055020 | شركة الكهرباء | تشييد | ذات اولوية متوسطة | 39649184 | 1982459.2 | 26394515 | 26394515 | 1010157290 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 99 | 100 | 2015-11-01 | 2019-08-30 | 2022-02-28 | 2022-02-28 | 2019-08-30 |  | لا يوجد تأخير |  | 36.559 | 28.3914 | منجز | No
2100004664 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 97147037.87 | 4857351.8935 | 62170738 | 62170738 | 2050004953 | لا | 0 | 180701014913 | جاري | منهجية القيمة المكتسبة | 65 | 100 | 2018-11-18 | 2021-05-16 | 2023-04-16 | 2023-04-16 |  |  | ضعف كفاءة المقاول الفنية |  | 49.6626 | 27.0037 | Failed | No
2100087533 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 389787031.51 | 19489351.5755 | 271426966.81 | 271426966.81 | 2051030201 | لا | 0 | 180809059185 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 98 | 100 | 2013-10-31 | 2016-10-27 | 2023-03-30 | 2023-03-30 |  |  | ضعف كفاءة المقاول الفنية |  | 49.6626 | 27.0037 | منتظم | No
2100084162 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 182648024 | 9132401.2 | 153879538 | 153879538 | 1010090968 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 88.14 | 89.18 | 2014-08-14 | 2017-07-11 | 2023-03-12 | 2023-03-12 |  |  |  |  | 39.8471 | 21.3635 | منتظم | No
2100199625 | جامعة شقراء | ترميم | ذات اولوية عالية | 471845 | 23592.25 | 0 | 0 | 1131044249 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 88 | 100 | 2021-05-23 | 2021-08-21 | 2022-06-01 | 2022-06-01 |  |  |  |  | 45.1431 | 25.1736 | Failed | No
2100055591 | وزارة الصحة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 3283470 | 164173.5 | 0 | 0 | 4650040868 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 40 | 100 | 2018-12-18 | 2019-09-08 | 2022-06-30 | 2022-06-30 |  |  | تأخرصرف المستحقات المالية |  | 39.5462 | 24.4699 | Failed | No
2100033600 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 5919590 | 295979.5 | 4876056.2 | 0 | 1010015152 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-10-08 | 2015-09-28 | 2019-08-26 | 2019-08-26 | 2015-09-28 |  | ضعف كفاءة المقاول الفنية |  | 46.6747 | 24.7038 | منجز | Yes
2100023973 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2006958 | 100347.9 | 221000.77 | 221000.77 | 1010026700 | لا | 0 |  | مسحوب | التكلفة المفوترة | 23 | 100 | 2006-07-09 | 2007-05-24 | 2009-01-05 | 2009-01-05 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | مسحوب | No
2100034436 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1831767 | 91588.35 | 41709 | 0 | 1010279126 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 94.98 | 100 | 2014-07-20 | 2015-10-13 | 2021-06-27 | 2021-06-27 | 2015-10-13 |  | ضعف كفاءة المقاول الفنية |  | 45.8825 | 25.2964 | منجز | Yes
2100087603 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 2066250 | 103312.5 | 978312 | 978312 | 2057003900 | لا | 0 | 200709130121 | فسخ العقد | منهجية القيمة المكتسبة | 100 | 100 | 2017-09-28 | 2020-08-27 | 2020-08-27 | 2020-08-27 |  |  | تغيرات في نطاق المشروع |  | 48.4953 | 28.4335 | مسحوب | No
2100105980 | شركة المياه الوطنية / منطقة الحدود الشمالية | تشييد | ذات اولوية عالية | 32017022 | 1600851.1 | 28782951.26 | 28782951.26 | 2054001027 | نعم | 5980500.52 | 180501011571 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-09-12 | 2021-02-13 | 2021-08-22 | 2021-08-22 | 2021-02-13 |  | لا يوجد تأخير |  | 41.0226 | 30.9583 | منجز | No
2100043341 | وزارة البيئة والمياة والزراعة | دراسة الجدوى | ذات اولوية متوسطة | 3657000 | 182850 | 3276943.25 | 3276943.25 | 1010363448 | لا | 0 | 190509012272 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2017-01-09 | 2018-12-18 | 2018-08-18 | 2018-08-18 | 2018-12-18 | [5 empty] | منجز | No
2100191203 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 11979500 | 598975 | 7590796.9 | 7590796.9 | 1010012911 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 90.28 | 100 | 2020-10-01 | 2021-03-27 | 2021-03-27 | 2021-03-27 | 2021-03-27 |  |  |  | 39.924 | 21.3859 | منجز | No
2100084744 | هيئة الهلال الأحمر السعودي | تشييد | ذات اولوية عالية | 15375308.2 | 768765.41 | 11554639.83 | 11554639.83 | 1010239020 | لا | 0 | 190709029964 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 100 | 2019-09-24 | 2022-04-16 | 2022-09-01 | 2022-09-01 | 2022-04-16 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 50.2159 | 26.2706 | منجز | No
2100068143 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 11432185 | 571609.25 | 6328486 | 0 | 3350003498 | لا | 0 |  | جاري | التكلفة المفوترة | 62 | 100 | 2013-02-05 | 2015-01-26 | 2021-12-15 | 2021-12-15 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | Failed | Yes
2100013753 | جامعة الملك سعود | تشييد | ذات اولوية عالية | 23400000 | 1170000 | 5163295 | 4346116.68 | 1010102752 | لا | 0 | 180401002081 | جاري | تكلفة العمل المنجز | 25 | 38 | 2018-07-15 | 2020-07-14 | 2023-09-13 | 2023-09-13 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 46.7098 | 24.6275 | متأخر | No
2100000873 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية عالية وعاجلة | 5806963.2 | 290348.16 | 4641888.01 | 4641888.01 | 1010233904 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2011-12-11 | 2013-11-18 | 2014-05-13 | 2014-05-13 | 2013-11-18 |  |  |  | 41.4139 | 20.2992 | منجز | No
2100190190 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية عالية وعاجلة | 95560613.4 | 4778030.67 | 63576243.82 | 63576243.82 | 1116000094 | نعم | 75099159 |  | مسحوب | الكميات التي تم تركيبها | 97 | 100 | 2012-10-16 | 2015-08-23 | 2015-08-23 | 2015-08-23 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.4638 | 20.0118 | مسحوب | No
2100104731 | شركة المياه الوطنية / منطقة الحدود الشمالية | تشييد | ذات اولوية عالية | 116820795.16 | 5841039.758 | 84313456.83 | 84313456.83 | 1010175465 | لا | 0 | 180709026104 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 97.5 | 100 | 2015-02-02 | 2017-12-31 | 2021-08-16 | 2021-08-16 | 2017-12-31 |  | تأخرصرف المستحقات المالية |  | 38.6719 | 31.6638 | منجز | No
2100003194 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية وعاجلة | 29522107 | 1476105.35 | 26569099.64 | 26569099.64 | 3451000618 | لا | 0 | 181109326549 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 95.54 | 100 | 2018-03-29 | 2021-02-24 | 2022-02-07 | 2022-02-07 | 2021-02-24 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.6969 | 27.506 | منجز | No
2100087754 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية متوسطة | 14587308.75 | 729365.4375 | 9559021.95 | 9559021.95 | 1163002582 | لا | 0 | 190401140450 | جاري | منهجية القيمة المكتسبة | 71.2 | 100 | 2019-09-01 | 2021-09-01 | 2022-06-30 | 2022-06-30 |  |  | لا يوجد تأخير |  | 35.7739 | 27.2748 | Failed | No
2100036606 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2043909 | 102195.45 | 968713 | 968713 | 3350022541 | لا | 0 |  | جاري | التكلفة المفوترة | 25 | 100 | 2011-06-03 | 2012-05-28 | 2021-12-15 | 2021-12-15 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | Failed | No
2100020801 | وزارة الشـؤون الاسلامية والدعوة والارشاد | تشييد | ذات اولوية عالية | 492450 | 24622.5 | 249966.78 | 249966.77 | 5950008566 | لا | 0 | 180909070524 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-03-25 | 2019-06-25 | 2019-11-25 | 2019-11-25 | 2019-06-25 |  | تأخرصرف المستحقات المالية |  | 44.2234 | 17.553 | منجز | No
2100017640 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2302197 | 115109.85 | 0 | 0 | 1010264386 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0 | 100 | 2010-08-17 | 2011-10-11 | 2020-10-27 | 2020-10-27 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | مسحوب | No
2100109362 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 56805464.79 | 2840273.2395 | 26473112.55 | 26057769.98 | 1010184370 | لا | 0 | 180709019394 | ايقاف كلي | تكلفة العمل المنجز | 77 | 100 | 2014-04-09 | 2016-09-25 | 2024-12-31 | 2024-12-31 |  |  | تأخرصرف المستحقات المالية |  | 46.7411 | 24.4435 | Failed | No
2100008816 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2166099 | 108304.95 | 2166099 | 2166099 | 1010223876 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2012-05-16 | 2013-05-11 | 2017-01-24 | 2017-01-24 | 2013-05-11 |  |  |  | 44.7813 | 20.4716 | منجز | No
2100087920 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 10726062.64 | 536303.132 | 3835911 | 3385377.24 | 1128003208 | لا | 0 |  | جاري الاستلام الإبتدائي | التكلفة المفوترة | 64 | 100 | 2015-12-20 | 2017-12-09 | 2022-01-06 | 2022-01-06 |  |  | ضعف كفاءة المقاول الفنية |  | 45.2591 | 25.2379 | Failed | No
2100038124 | وزارة النقل والخدمات اللوجستية / منطقة الجوف | تشييد | ذات اولوية متوسطة | 95000000 | 4750000 | 14037598.4 | 14037598.4 | 1010195745 | لا | 0 | 181109364191 | فسخ العقد | تكلفة العمل المنجز | 19 | 100 | 2014-06-23 | 2017-05-20 | 2017-05-20 | 2017-05-20 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 40.3201 | 30.2064 | مسحوب | No
2100017323 | وزارة التعليم | تشييد | ذات اولوية عالية | 3570708 | 178535.4 | 2563416 | 2563416 | 1010233305 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-03-30 | 2015-03-25 | 2022-08-17 | 2022-08-17 | 2015-03-25 |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | منجز | No
2100012390 | وزارة الداخلية / ديوان وزارة الداخلية | تصميم وتشييد | ذات اولوية عالية وعاجلة | 2918861004 | 145943050.2 | 2432979478 | 2424687750 | 1010277276 | لا | 0 | 181009208989 | جاري | التكلفة المفوترة | 85 | 95.22 | 2014-11-20 | 2020-06-10 | 2025-01-13 | 2025-01-13 |  |  | تأخرصرف المستحقات المالية |  | 46.7098 | 24.6275 | متأخر | No
2100091663 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 5536593 | 276829.65 | 658281 | 0 | 1010145477 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2009-10-23 | 2011-04-16 | 2021-11-29 | 2021-11-29 | 2011-04-16 |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | منجز | Yes
2100024603 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 8950859.7 | 447542.985 | 7286243.83 | 7286243.83 | 1010149133 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 86 | 100 | 2013-10-21 | 2015-07-13 | 2021-01-01 | 2021-01-01 | 2015-07-13 |  | ضعف كفاءة المقاول الفنية |  | 46.7271 | 22.2863 | منجز | No
2100090230 | وزارة التعليم | تشييد | ذات اولوية عالية | 3139419.32 | 156970.966 | 2339205.05 | 2339205.05 | 1010191039 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-01-21 | 2016-01-16 | 2022-08-09 | 2022-08-09 | 2016-01-16 |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | منجز | No
2100064046 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1532050 | 76602.5 | 41533 | 0 | 1186001365 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 86 | 100 | 2014-03-26 | 2015-01-20 | 2022-12-21 | 2022-12-21 | 2015-01-20 |  | ضعف كفاءة المقاول الفنية |  | 43.6981 | 24.6721 | منجز | Yes
2100100284 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 2609155.71 | 130457.7855 | 2185070.04 | 2185070.04 | 1010007606 | نعم | 1222322.91 | 190601040135 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-07-24 | 2020-03-20 | 2023-02-01 | 2023-02-01 | 2020-03-20 |  | تأخرصرف المستحقات المالية |  | 42.0619 | 18.5113 | منجز | No
2100107063 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 10358659.85 | 517932.9925 | 9078024.35 | 0 | 3350009307 | لا | 0 |  | جاري | التكلفة المفوترة | 92 | 100 | 2013-03-12 | 2015-03-02 | 2022-05-10 | 2022-05-10 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | متأخر | Yes
2100191844 | شركة المياه الوطنية / منطقة حائل | إشراف | ذات اولوية عالية وعاجلة | 4981800 | 249090 | 3020187.46 | 914616.33 | 1010322156 | لا | 0 | 201101307033 | جاري | التكلفة المفوترة | 60.62 | 71.65 | 2020-12-31 | 2022-07-31 | 2022-07-31 | 2022-07-31 |  |  |  |  | 41.657 | 27.5119 | خدمات عامة | No
2100063862 | شركة المياه الوطنية / منطقة حائل | إشراف | ذات اولوية عالية | 10245400 | 512270 | 11611427.45 | 11594927.45 | 1010314421 | لا | 0 | 180709023804 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-05-11 | 2018-05-10 | 2021-09-26 | 2021-09-26 | 2018-05-10 |  | لا يوجد تأخير |  | 41.8039 | 27.6076 | منجز | No
2100098663 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 3644906 | 182245.3 | 2363863 | 2363863 | 4030194980 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 72 | 100 | 2014-11-03 | 2016-01-27 | 2022-11-23 | 2022-11-23 |  |  | ضعف كفاءة المقاول الفنية |  | 40.2691 | 20.1489 | مسحوب | No
2200216845 | وزارة المالية - الحرمين | ادارة مشاريع | ذات اولوية عالية وعاجلة | 1107000000 | 24000000 | 753994052.38 | 753475172.38 | 4030283265 | لا | 0 |  | جاري | مدفوعات ساعات العمل | 70.28 | 70.28 | 2017-07-09 | 2020-07-09 | 2023-07-09 | 2023-07-09 |  |  |  |  | 39.1679 | 21.5154 | خدمات عامة | No
2100037800 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية | 45592490 | 2279624.5 | 40412918 | 40412917.92 | 4030156606 | لا | 0 | 180909088566 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 96.46 | 100 | 2014-12-25 | 2016-12-02 | 2021-06-28 | 2021-06-28 | 2016-12-02 |  | لا يوجد تأخير |  | 40.4731 | 26.0049 | منجز | No
2100022190 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية وعاجلة | 45782586.19 | 2289129.3095 | 20558476.96 | 20558476.96 | 1010085001 | لا | 0 | 180709020052 | فسخ العقد | تكلفة العمل المنجز | 65 | 100 | 2014-04-24 | 2016-03-24 | 2025-12-31 | 2025-12-31 |  |  | تأخرصرف المستحقات المالية |  | 42.6021 | 18.3133 | مسحوب | No
2100048742 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 82112234.07 | 4105611.7035 | 8195269.91 | 8195269.91 | 1010074445 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 10 | 100 | 2015-04-09 | 2017-09-25 | 2026-12-31 | 2026-12-31 |  |  | منازعات قائمة |  | 42.8911 | 16.9911 | مسحوب | No
2100095045 | المؤسسة العامة لتحلية المياه المالحة | إشراف | ذات اولوية عالية | 54857001 | 2742850.05 | 51770639.01 | 51770639.01 | 1010440438 | لا | 0 | 191201116838 | جاري | اخرى | 96.6 | 100 | 2020-03-08 | 2022-09-07 | 2022-09-07 | 2022-09-07 |  |  |  |  | 40.2664 | 20.1309 | خدمات عامة | No
2100041941 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية وعاجلة | 306829000 | 15341450 | 182428652.3 | 182428652.3 | 1116000094 | لا | 0 | 180809054223 | مسحوب | منهجية القيمة المكتسبة | 63.47 | 100 | 2013-12-02 | 2015-11-11 | 2024-02-01 | 2024-02-01 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.0539 | 27.6244 | مسحوب | No
2100074325 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية وعاجلة | 58889639.03 | 2944481.9515 | 34040026.01 | 34040026.01 | 1010153533 | لا | 0 | 180709026270 | مسحوب | منهجية القيمة المكتسبة | 58.63 | 100 | 2013-08-19 | 2016-07-17 | 2024-06-30 | 2024-06-30 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.6684 | 27.5626 | مسحوب | No
2100006403 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 4227355 | 211367.75 | 4227355 | 4227355 | 2050007224 | نعم | 16974559 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-12-27 | 2019-08-21 | 2019-08-19 | 2019-08-19 |  | 2019-08-21 | لا يوجد تأخير |  | 39.181 | 21.5998 | منجز | No
2100074351 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية | 34653000 | 1732650 | 15161610.15 | 15161610.15 | 4030057371 | لا | 0 | 180709031901 | مسحوب | منهجية القيمة المكتسبة | 59.31 | 100 | 2014-01-14 | 2015-12-24 | 2023-08-17 | 2023-08-17 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.127 | 26.5029 | مسحوب | No
2100009505 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية متوسطة | 10997150 | 549857.5 | 10997149.95 | 10997149.95 | 4040066608 | لا | 0 | 181101275636 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-12-23 | 2020-12-01 | 2020-08-26 | 2020-08-26 |  | 2020-12-01 | لا يوجد تأخير |  | 43.5067 | 17.6708 | منجز | No
2100060373 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية وعاجلة | 60074909 | 3003745.45 | 48045527.41 | 43253934.67 | 5860008190 | لا | 0 | 180709028445 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 97.64 | 100 | 2012-11-12 | 2014-10-21 | 2019-03-04 | 2019-03-04 | 2014-10-21 |  | لا يوجد تأخير |  | 42.5429 | 16.8808 | منجز | No
2100050271 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 6720850 | 336042.5 | 6720850 | 6720850 | 2251032617 | لا | 0 | 181001177066 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-12-15 | 2020-12-04 | 2020-12-05 | 2020-12-05 | 2020-12-04 |  | اخرى |  | 49.5822 | 25.3691 | منجز | No
2100086774 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 133632075.57 | 6681603.7785 | 49976024.46 | 49976024.46 | 1010057502 | لا | 0 | 180709021271 | فسخ العقد | تكلفة العمل المنجز | 38 | 98 | 2014-08-03 | 2017-01-19 | 2026-12-31 | 2026-12-31 |  |  | تأخرصرف المستحقات المالية |  | 39.0107 | 22.8498 | مسحوب | No
2100091125 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 9763124.01 | 488156.2005 | 8138417.86 | 6335704 | 1010060469 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2017-07-10 | 2019-06-30 | 2020-09-16 | 2020-09-16 | 2019-06-30 |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | منجز | No
2100089235 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 72303860 | 3615193 | 57689227.99 | 57689227.99 | 2052002700 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2013-02-15 | 2015-01-25 | 2019-03-14 | 2019-03-14 |  | 2015-01-25 | لا يوجد تأخير |  | 39.3371 | 21.4613 | منجز | No
2100018701 | شركة المياه الوطنية / منطقة تبوك | إشراف | ذات اولوية عالية | 5659200 | 282960 | 0 | 0 | 1131052239 | لا | 0 | 181001154163 | لم يبدأ | التكلفة المفوترة | 0 | 0 | 2018-09-01 | 2021-09-01 | 2021-10-16 | 2021-10-16 |  |  | لا يوجد تأخير |  | 36.4873 | 26.2317 | Failed | No
2100082530 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 4198650 | 209932.5 | 700000 | 700000 | 2250029534 | لا | 0 | 181109286466 | فسخ العقد | تكلفة العمل المنجز | 17 | 100 | 2015-11-04 | 2016-10-30 | 2017-01-05 | 2017-01-05 |  |  | تأخرصرف المستحقات المالية |  | 49.5847 | 25.3787 | مسحوب | No
2100108986 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2057951 | 102897.55 | 679908 | 679908 | 4030164266 | لا | 0 | 201109002915 | مسحوب | التكلفة المفوترة | 50 | 100 | 2017-08-02 | 2018-07-28 | 2021-12-23 | 2021-12-23 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0859 | 19.1571 | مسحوب | No
2100100181 | الهيئة الملكية لمدينة الرياض | تشييد | ذات اولوية عالية | 46103993223.7 | 2305199661.185 | 41282717944.1 | 41282717944.1 | 2051008820 | لا | 0 | 190209017624 | جاري | اخرى | 91.22 | 100 | 2013-10-30 | 2018-10-29 | 2022-06-30 | 2022-06-30 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 46.6755 | 24.7132 | Failed | No
2100099411 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 37049778.8 | 1852488.94 | 28057837.25 | 28057837.25 | 2050001536 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 83.55 | 2018-02-01 | 2020-01-10 | 2019-05-02 | 2019-05-02 |  | 2020-01-10 | لا يوجد تأخير |  | 39.1905 | 21.5577 | منجز | No
2200213721 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية وعاجلة | 69355000.94 | 3467750.047 | 16307678.5 | 2286516.25 | 1010257755 | لا | 0 | 210101004692 | جاري | منهجية القيمة المكتسبة | 26.13 | 14.55 | 2021-11-15 | 2023-10-25 | 2023-10-25 | 2023-10-25 |  |  |  |  | 41.6985 | 27.5026 | منتظم | No
2100000405 | شركة المياه الوطنية / منطقة الحدود الشمالية | تشييد | ذات اولوية عالية | 1942876.55 | 97143.8275 | 1942876.55 | 1942876.55 | 3451001742 | نعم | 3359644 | 190301011711 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-07-03 | 2020-06-22 | 2020-06-09 | 2020-06-09 |  | 2020-06-22 | لا يوجد تأخير |  | 38.7272 | 31.6615 | منجز | No
2100048156 | شركة المياه الوطنية / منطقة الحدود الشمالية | إشراف | ذات اولوية عالية | 6667323.6 | 333366.18 | 6604585.27 | 6604585.27 | 1010407952 | لا | 0 | 180709019391 | منجز – استلام ابتدائي | التكلفة المفوترة | 99.97 | 100 | 2015-06-21 | 2018-06-20 | 2018-12-04 | 2018-12-04 | 2018-06-20 |  | لا يوجد تأخير |  | 41.0334 | 30.9538 | منجز | No
2100020145 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية متوسطة | 8334000 | 416700 | 8535867 | 8535867 | 1131027450 | لا | 0 | 180709019634 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 97.5 | 100 | 2018-02-04 | 2020-01-13 | 2020-04-08 | 2020-04-08 |  | 2020-01-13 | لا يوجد تأخير |  | 43.9544 | 26.3504 | منجز | No
2100024404 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البرية | تشييد | ذات اولوية متوسطة | 14994509.25 | 749725.4625 | 8861018 | 8861018 | 2511006797 | لا | 0 | 200909084869 | جاري | الكميات التي تم تركيبها | 100 | 100 | 2019-09-30 | 2020-04-20 | 2022-11-09 | 2022-11-09 |  |  | اخرى |  | 50.0514 | 26.355 | متأخر | No
2100055451 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 209717696 | 10485884.8 | 123872607.6 | 123872607.6 | 1010224378 | لا | 0 | 200209139810 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2010-06-07 | 2012-06-12 | 2022-11-27 | 2022-11-27 | 2012-06-12 |  | ضعف كفاءة المقاول الفنية |  | 38.2101 | 23.9954 | منجز | No
2100079030 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 18369780 | 918489 | 0.02 | 0.02 | 4030065868 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 65 | 100 | 2008-12-15 | 2010-12-05 | 2018-07-09 | 2018-07-09 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.836 | 21.4408 | مسحوب | No
2100071750 | أمانة / تبوك | تشييد | ذات اولوية عالية | 1042908.75 | 52145.4375 | 754400 | 754400 | 3550022094 | لا | 0 | 200501038056 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 72 | 100 | 2015-10-27 | 2017-09-14 | 2021-04-30 | 2021-04-30 | 2017-09-14 |  | ضعف كفاءة المقاول الفنية |  | 36.5034 | 27.398 | منجز | No
2100058531 | شركة الكهرباء | تشييد | ذات اولوية متوسطة | 244029777 | 12201488.85 | 207133042 | 207133042 | 1010011560 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2015-12-18 | 2018-05-08 | 2022-06-16 | 2022-06-16 | 2018-05-08 |  | تصاريح أعمال التنفيذ |  | 39.2485 | 21.5246 | منجز | No
2100086402 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 30362562.15 | 1518128.1075 | 20893449.98 | 0 | 1010142553 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 93 | 100 | 2009-07-25 | 2011-07-15 | 2022-08-24 | 2022-08-24 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | مسحوب | Yes
2100020090 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 4790975 | 239548.75 | 0 | 0 | 4030052981 | لا | 0 |  | ايقاف كلي | التكلفة المفوترة | 0 | 100 | 2015-03-22 | 2016-09-12 | 2022-06-05 | 2022-06-05 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | Failed | No
2100058122 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2700000 | 135000 | 576104 | 576104 | 5864037186 | لا | 0 |  | مسحوب | التكلفة المفوترة | 83 | 100 | 2014-11-02 | 2015-12-27 | 2022-08-02 | 2022-08-02 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0859 | 19.1571 | مسحوب | No
2100067281 | وزارة التعليم | تشييد | ذات اولوية عالية | 3448385 | 172419.25 | 318045 | 318045 | 4031059792 | لا | 0 | 191101281478 | مسحوب | التكلفة المفوترة | 10 | 100 | 2018-01-28 | 2019-04-23 | 2019-04-23 | 2019-04-23 |  |  | ضعف كفاءة المقاول الفنية |  | 42.6509 | 17.1567 | مسحوب | No
2100058321 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 5730245.6 | 286512.28 | 0 | 0 | 1010188602 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0 | 100 | 2009-10-10 | 2009-10-11 | 2023-02-08 | 2023-02-08 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.5429 | 16.8808 | مسحوب | No
2100098873 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 10995841.52 | 549792.076 | 6982433.64 | 6982433.64 | 4030140863 | لا | 0 | 190209015471 | جاري | التكلفة المفوترة | 86 | 100 | 2014-08-21 | 2016-08-10 | 2022-12-30 | 2022-12-30 |  |  | ضعف كفاءة المقاول الفنية |  | 40.2691 | 20.1489 | Failed | No
2100107004 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 61681381.16 | 3084069.058 | 44964850.03 | 41584196.48 | 4030130776 | لا | 0 | 180709022049 | ايقاف كلي | تكلفة العمل المنجز | 87 | 100 | 2014-10-20 | 2016-12-28 | 2025-12-31 | 2025-12-31 |  |  | تأخرصرف المستحقات المالية |  | 39.3545 | 21.4085 | Failed | No
2100047865 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية | 6339450 | 316972.5 | 5078584.3 | 5078584.3 | 2050007106 | نعم | 1601167.35 | 180709020364 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-04-21 | 2016-10-12 | 2023-02-01 | 2023-02-01 | 2016-10-12 |  | تأخرصرف المستحقات المالية |  | 50.1638 | 26.1829 | منجز | No
2100025911 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 45259915.81 | 2262995.7905 | 11314978.95 | 11314978.95 | 5950003603 | لا | 0 |  | مسحوب | التكلفة المفوترة | 24 | 100 | 2016-01-17 | 2018-07-05 | 2023-11-22 | 2023-11-22 |  |  | ضعف كفاءة المقاول الفنية |  | 44.2341 | 17.5757 | مسحوب | No
2100006392 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2637014.9 | 131850.745 | 0.01 | 0.01 | 5950005651 | لا | 0 | 190509027271 | جاري | التكلفة المفوترة | 76 | 100 | 2018-01-14 | 2019-04-09 | 2022-08-10 | 2022-08-10 |  |  | ضعف كفاءة المقاول الفنية |  | 44.2341 | 17.5757 | Failed | No
2100008820 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 13451627 | 672581.35 | 2889656.06 | 2889656.06 | 1010223860 | لا | 0 | 190209010072 | مسحوب | التكلفة المفوترة | 37 | 100 | 2012-09-02 | 2014-08-23 | 2023-02-01 | 2023-02-01 |  |  | ضعف كفاءة المقاول الفنية |  | 42.4987 | 18.2178 | مسحوب | No
2100067454 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2236215 | 111810.75 | 977026.14 | 977026.14 | 4030108097 | لا | 0 |  | مسحوب | التكلفة المفوترة | 61 | 100 | 2008-07-30 | 2009-07-18 | 2023-05-24 | 2023-05-24 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | مسحوب | No
2100086763 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2583146.5 | 129157.325 | 232000 | 232000 | 3550026844 | لا | 0 |  | مسحوب | التكلفة المفوترة | 9 | 100 | 2011-01-06 | 2012-03-30 | 2023-02-15 | 2023-02-15 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | مسحوب | No
2100038533 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 13989285.4 | 699464.27 | 12588415.11 | 12588415.11 | 2050041707 | لا | 0 | 181001157344 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-03-12 | 2021-03-13 | 2021-03-04 | 2021-03-04 | 2021-03-13 |  | لا يوجد تأخير |  | 49.5853 | 25.3806 | منجز | No
2100012445 | أمانة / عسير | تشييد | ذات اولوية عالية | 4199991 | 209999.55 | 1365180 | 0 | 5852001934 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 0 | 100 | 2018-11-30 | 2019-11-25 | 2020-01-13 | 2020-01-13 |  |  | ضعف كفاءة المقاول الفنية |  | 42.3206 | 18.1905 | مسحوب | Yes
2100006591 | وزارة التعليم | تشييد | لم تعد تحتاجها الجهة | 1994415 | 99720.75 | 791255.5 | 791255.5 | 1010069591 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 45 | 100 | 2009-12-18 | 2010-12-15 | 2019-08-01 | 2019-08-01 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 43.1379 | 18.0853 | مسحوب | No
2100022433 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1766015 | 88300.75 | 223500 | 223500 | 5850022317 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 14 | 100 | 2012-02-07 | 2012-12-23 | 2012-12-23 | 2012-12-23 |  |  | المشروع ليس ذو أولوية في الوقت الحالي |  | 41.4374 | 19.7864 | مسحوب | No
2100006300 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 18390512.5 | 919525.625 | 15996509.92 | 15996509.92 | 2051021070 | لا | 0 | 180909109379 | جاري | منهجية القيمة المكتسبة | 81 | 100 | 2018-03-19 | 2019-11-25 | 2023-11-12 | 2023-11-12 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 49.5648 | 27.1019 | متأخر | No
2100004874 | وزارة الدفاع / الإدارة الهندسية والاشغال بقوة الصواريخ الإستراتيجية | تشييد | ذات اولوية عالية | 229456169 | 11472808.45 | 112907699.57 | 112907699.57 | 1010154193 | لا | 0 | 181109344536 | جاري | الكميات التي تم تركيبها | 67 | 100 | 2014-12-16 | 2016-06-08 | 2022-06-03 | 2022-06-03 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال | مخطط لسحبه وإعادة ترسيته | 46.5096 | 23.6207 | Failed | No
2100087802 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 414420051.09 | 20721002.5545 | 319372544.89 | 319372544.89 | 2050034321 | لا | 0 | 180809058926 | جاري | منهجية القيمة المكتسبة | 96 | 100 | 2012-10-15 | 2015-10-12 | 2023-06-04 | 2023-06-04 |  |  | ضعف كفاءة المقاول الفنية |  | 49.6626 | 27.0037 | Failed | No
2100079251 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1815595 | 90779.75 | 0 | 0 | 5850022317 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 7 | 100 | 2012-02-29 | 2013-01-14 | 2013-01-14 | 2013-01-14 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 41.4374 | 19.7864 | مسحوب | No
2100001816 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 11573065.15 | 578653.2575 | 6258904.42 | 0 | 1010196220 | لا | 0 | 190909020010 | جاري | التكلفة المفوترة | 85 | 100 | 2012-11-19 | 2014-11-09 | 2022-12-30 | 2022-12-30 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0859 | 19.1571 | Failed | Yes
2100054386 | وزارة النقل والخدمات اللوجستية / منطقة جازان | تشييد | ذات اولوية متوسطة | 13334462.78 | 666723.139 | 340000 | 340000 | 1010080784 | لا | 0 | 0 | فسخ العقد | الكميات التي تم تركيبها | 2.45 | 100 | 2013-11-18 | 2015-10-27 | 2021-06-17 | 2021-06-17 |  |  | اخرى |  | 42.5363 | 17.374 | مسحوب | No
2100189954 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية عالية وعاجلة | 10994523.48 | 549726.174 | 10540644.02 | 10540644.02 | 1010008680 | لا | 0 | 190701166403 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-11-21 | 2020-11-19 | 2021-12-14 | 2021-12-14 | 2020-11-19 |  |  |  | 44.4234 | 24.5318 | منجز | No
2100088443 | وزارة الدفاع / الإدارة الهندسية والاشغال بالخدمات الصحية | تشييد | ذات اولوية متوسطة | 18678856 | 933942.8 | 4285700.37 | 4285700.37 | 1010213669 | لا | 0 | 180909090609 | جاري | الكميات التي تم تركيبها | 12.7 | 100 | 2018-06-28 | 2019-12-10 | 2021-03-27 | 2021-03-27 |  |  | تغيرات في نطاق المشروع |  | 39.1649 | 21.5502 | Failed | No
2100092724 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 689900 | 34495 | 722752.36 | 722752.36 | 4030237556 | لا | 0 | 181109267334 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 90 | 99 | 2018-10-23 | 2020-09-30 | 2020-10-01 | 2020-10-01 | 2020-09-30 |  | اخرى |  | 40.8637 | 20.4217 | منجز | No
2200210814 | المؤسسة العامة للحبوب | تصميم وتشييد | ذات اولوية عالية | 2209647 | 110482.35 | 0 | 0 | 1010211349 | لا | 0 |  | لم يبدأ | الكميات التي تم تركيبها | 1 | 1 | 2021-09-15 | 2023-12-01 | 2024-03-01 | 2024-03-01 |  |  |  |  | 43.5023 | 26.2119 | Failed | No
2100055856 | جامعة حائل | دراسة الجدوى | ذات اولوية عالية وعاجلة | 134430000 | 6721500 | 86839589.11 | 86839589.11 | 4030276223 | لا | 0 |  | جاري | التكلفة المفوترة | 98 | 100 | 2014-12-18 | 2022-07-05 | 2021-11-05 | 2021-11-05 |  |  | لا يوجد تأخير |  | 41.709 | 27.6646 | خدمات عامة | No
2100074200 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 24517752.75 | 1225887.6375 | 0.02 | 0.02 | 4031020518 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 92 | 100 | 2009-07-29 | 2011-09-17 | 2018-11-08 | 2018-11-08 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.836 | 21.4408 | مسحوب | No
2100092120 | وزارة التعليم | تشييد | ذات اولوية عالية | 3772897.3 | 188644.865 | 1738875 | 1738875 | 4031053163 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 44 | 100 | 2014-09-20 | 2015-12-20 | 2020-12-15 | 2020-12-15 |  |  | ضعف كفاءة المقاول الفنية |  | 43.9544 | 26.3504 | مسحوب | No
2100021114 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 8433227 | 421661.35 | 6672663.48 | 6514971.59 | 1010277276 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 83 | 100 | 2014-03-12 | 2018-03-15 | 2023-02-08 | 2023-02-08 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.5429 | 16.8808 | مسحوب | No
2100195871 | الهيئة العامة للزكاة والدخل | توريد وتركيب | ذات اولوية عالية وعاجلة | 95450 | 4772.5 | 95450 | 95450 | 1131007134 | لا | 0 |  | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2021-04-18 | 2021-05-13 | 2021-05-13 | 2021-05-13 |  | 2021-05-13 |  |  | 43.9474 | 26.3528 | منجز | No
2100095303 | وزارة الصحة / المدينة المنورة | تشييد | ذات اولوية منخفضة | 58608689.4 | 2930434.47 | 45169234 | 44003616 | 4030052981 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 81 | 100 | 2014-03-24 | 2016-03-01 | 2022-03-31 | 2022-03-31 |  |  | تأخرصرف المستحقات المالية |  | 39.36 | 24.28 | Failed | No
2200219671 | وزارة الداخلية / المديرية العامة لحرس الحدود | تشييد | ذات اولوية عالية | 624834 | 31241.7 | 624834 | 624834 | 3550024705 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2021-11-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 | 2022-05-17 |  |  |  | 36.5618 | 28.3865 | منجز | No
2100017625 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2470276.42 | 123513.821 | 2133542.08 | 902741.93 | 5860034369 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 90 | 100 | 2015-11-17 | 2016-11-11 | 2020-07-07 | 2020-07-07 | 2016-11-11 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.9381 | 17.7901 | منجز | No
2100190282 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية عالية وعاجلة | 1437040.55 | 71852.0275 | 1433008.98 | 1433008.98 | 5950018592 | لا | 0 | 200701098894 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2021-02-21 | 2021-11-15 | 2021-11-14 | 2021-11-14 | 2021-11-15 |  |  |  | 44.2326 | 17.5517 | منجز | No
2100080220 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية | 37089306 | 1854465.3 | 34247545.92 | 34247545.92 | 1010010466 | لا | 0 | 181009152957 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2015-07-26 | 2017-07-04 | 2020-04-13 | 2020-04-13 |  | 2017-07-04 | لا يوجد تأخير |  | 39.6005 | 24.4595 | منجز | No
2100095200 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 8121889 | 406094.45 | 8112603 | 8112603 | 2051021399 | لا | 0 | 180909109714 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-03-19 | 2019-03-19 | 2023-01-20 | 2023-01-20 | 2019-03-19 |  | اخرى |  | 38.4657 | 23.823 | منجز | No
2100094732 | وزارة الخارجية | إشراف | ذات اولوية عالية | 3824257.5 | 191212.875 | 501742.5 | 501742.5 | 1010433597 | لا | 0 | 200809013696 | ايقاف جزئي | مدفوعات ساعات العمل | 3 | 21 | 2020-02-09 | 2022-04-09 | 2022-09-02 | 2022-09-02 |  |  | عدم وجود مبالغ في البنود تغطي الأعمال المرصودة |  | -15.9544 | 18.0774 | متأخر | No
2100006613 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 14003818.79 | 700190.9395 | 5586550.79 | 4985820.85 | 1010183010 | لا | 0 |  | مسحوب | التكلفة المفوترة | 55 | 100 | 2017-01-28 | 2018-10-20 | 2022-12-16 | 2022-12-16 |  |  | تأخرصرف المستحقات المالية |  | 42.2211 | 18.0985 | مسحوب | No
2100102760 | وزارة الموارد البشرية والتنمية الإجتماعية | إشراف | ذات اولوية منخفضة | 1138500 | 56925 | 1061291.63 | 1061291.63 | 1010435790 | لا | 0 | 181109284709 | جاري | الكميات التي تم تركيبها | 95 | 100 | 2018-02-06 | 2020-01-25 | 2023-03-30 | 2023-03-30 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5077 | 18.2242 | خدمات عامة | No
2100020134 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 11394702.25 | 569735.1125 | 11394702.25 | 11394702.25 | 4030071125 | لا | 0 |  | جاري | اخرى | 100 | 100 | 2018-10-10 | 2020-03-01 | 2020-03-01 | 2020-03-01 | [6 empty] | Failed | No
2100005456 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 9405062.52 | 470253.126 | 8648773.12 | 6780704.77 | 1010060469 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2016-02-09 | 2019-07-27 | 2020-01-25 | 2020-01-25 | 2019-07-27 |  | اخرى |  | 42.5429 | 16.8808 | منجز | No
2100091571 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3069362 | 153468.1 | 41739 | 0 | 1116007006 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 74 | 100 | 2014-08-17 | 2015-10-11 | 2019-12-09 | 2019-12-09 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6672 | 24.7019 | مسحوب | Yes
2100062635 | هيئة الهلال الأحمر السعودي | تشييد | ذات اولوية عالية | 3202715.16 | 160135.758 | 222572.44 | 222572.44 | 4031050323 | لا | 0 | 181209452299 | مسحوب | الكميات التي تم تركيبها | 15 | 15 | 2019-03-31 | 2020-02-25 | 2019-05-14 | 2019-05-14 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.1883 | 21.4781 | مسحوب | No
2200219925 | وزارة الحرس الوطني / وكالة الشؤون الفنية | توريد وتركيب | ذات اولوية متوسطة | 1795840 | 89792 | 1589760 | 1589760 | 1010032177 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2022-03-08 | 2022-10-30 | 2022-10-30 | 2022-10-30 | 2022-10-30 |  |  |  | 46.6773 | 24.7038 | منجز | No
2200210906 | المؤسسة العامة للحبوب | تصميم وتشييد | ذات اولوية عالية وعاجلة | 399067224 | 19953361.2 | 0 | 0 | 1010185409 | لا | 0 | 210601109703 | ايقاف جزئي | الكميات التي تم تركيبها | 1 | 1 | 2021-08-13 | 2024-05-12 | 2025-01-01 | 2025-01-01 |  |  |  |  | 35.7305 | 27.3352 | منتظم | No
2100031533 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 11388500 | 569425 | 4608379.65 | 0 | 1010108475 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-05-20 | 2016-11-10 | 2019-11-08 | 2019-11-08 | 2016-11-10 |  | ضعف كفاءة المقاول الفنية |  | 46.6672 | 24.7094 | منجز | Yes
2100043352 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 759000 | 37950 | 203833.6 | 0 | 1010064540 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-01-16 | 2016-01-01 | 2019-09-04 | 2019-09-04 | 2016-01-01 |  | ضعف كفاءة المقاول الفنية |  | 46.6869 | 24.7028 | منجز | Yes
2100032653 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 17760600 | 888030 | 16040315.316 | 16040315.316 | 4650049563 | لا | 0 |  | جاري | تكلفة العمل المنجز | 90 | 95 | 2019-10-02 | 2023-05-02 | 2023-05-02 | 2023-05-02 |  |  | ضعف كفاءة المقاول الفنية |  | 39.5858 | 24.5353 | منتظم | No
2100018023 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 222079254.17 | 11103962.7085 | 199994178.44 | 199994178.44 | 2055014114 | لا | 0 | 180809058460 | جاري | منهجية القيمة المكتسبة | 90 | 99 | 2017-07-10 | 2020-06-08 | 2024-04-30 | 2024-04-30 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 49.2063 | 27.5138 | متأخر | No
2100004476 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 49405444.83 | 2470272.2415 | 42856329.67 | 42856329.67 | 1010185409 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-11-26 | 2020-05-19 | 2020-05-19 | 2020-05-19 | 2020-05-19 |  | أوامر تغيير | أخرى |  |  | منجز | No
2100194460 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 5314545 | 265727.25 | 253060.5 | 253060.5 | 5800010527 | نعم | 1 | 190801006121 | مسحوب | تكلفة العمل المنجز | 80 | 80 | 2021-07-26 | 2022-07-25 | 2022-07-25 | 2022-07-25 |  |  | ضعف كفاءة المقاول الفنية |  | 41.8582 | 19.3959 | مسحوب | No
2100036676 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 1650000 | 82500 | 1650000 | 1650000 | 4030071125 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2018-09-07 | 2018-10-04 | 2018-12-09 | 2018-12-09 | 2018-10-04 | [5 empty] | منجز | No
2100105560 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية | 27825000 | 1391250 | 26041813.91 | 26041813.91 | 1010044185 | لا | 0 | 180301001083 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 93.63 | 100 | 2018-09-05 | 2021-08-04 | 2021-10-14 | 2021-10-14 | 2021-08-04 |  | لا يوجد تأخير |  | 39.5111 | 24.4174 | منجز | No
2100065004 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 5249365 | 262468.25 | 2240593 | 0 | 1114000037 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 72 | 100 | 2014-12-18 | 2016-04-11 | 2020-01-13 | 2020-01-13 | 2016-04-11 |  | ضعف كفاءة المقاول الفنية |  | 46.6912 | 24.7113 | منجز | Yes
2100031006 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 899305 | 44965.25 | 244540 | 0 | 1115001965 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 100 | 2015-01-07 | 2016-04-01 | 2019-09-09 | 2019-09-09 | 2016-04-01 |  | ضعف كفاءة المقاول الفنية |  | 46.6706 | 24.7013 | منجز | Yes
2100047456 | أمانة / عسير | تشييد | ذات اولوية عالية | 15918014 | 795900.7 | 5437157 | 5437157 | 1010409973 | لا | 0 |  | جاري | تكلفة العمل المنجز | 65 | 100 | 2019-01-30 | 2020-01-26 | 2023-03-31 | 2023-03-31 |  |  | ضعف كفاءة المقاول الفنية |  | 42.4763 | 18.2608 | Failed | No
2100055145 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 64781972.43 | 3239098.6215 | 30860635.73 | 30860635.73 | 2050027937 | لا | 0 | 180101000029 | جاري | منهجية القيمة المكتسبة | 18 | 100 | 2018-11-27 | 2020-09-29 | 2023-05-07 | 2023-05-07 |  |  | عدم وجود كوادر كافية في الجهه لادارة المشروع |  | 49.5648 | 27.1019 | Failed | No
2100076823 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 1581650 | 79082.5 | 1581650 | 1581650 | 1010997845 | لا | 0 | 200101053819 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-07-16 | 2019-11-15 | 2021-01-05 | 2021-01-05 | 2019-11-15 |  | ضعف كفاءة المقاول الفنية |  | 36.6321 | 28.3451 | منجز | No
2100198343 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 21459232.46 | 1072961.623 | 7754134 | 7754134 | 1010205512 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 59 | 66.78 | 2020-04-24 | 2022-07-14 | 2023-06-15 | 2023-06-15 |  |  |  |  | 46.5657 | 24.6524 | متأخر | No
2100198881 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 49851998.18 | 2492599.909 | 0 | 0 | 1010066115 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 0 | 0 | 2021-01-06 | 2022-06-30 | 2021-12-03 | 2021-12-03 |  |  |  |  | 46.8974 | 24.3532 | مسحوب | No
2100075386 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1291400 | 64570 | 42149 | 0 | 1122003654 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 78 | 100 | 2015-09-30 | 2016-12-23 | 2019-09-08 | 2019-09-08 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6816 | 24.7088 | مسحوب | Yes
2100062926 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 6619666 | 330983.3 | 4635459.38 | 0 | 1116005202 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 94 | 100 | 2015-02-22 | 2017-02-11 | 2020-02-23 | 2020-02-23 | 2017-02-11 |  | ضعف كفاءة المقاول الفنية |  | 46.2685 | 24.4531 | منجز | Yes
2100027742 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 72000000 | 3600000 | 48465017.29 | 48465017.29 | 2051027499 | لا | 0 | 180701014907 | جاري | منهجية القيمة المكتسبة | 71 | 86 | 2018-10-14 | 2021-10-10 | 2023-09-23 | 2023-09-23 |  |  | اخرى |  | 49.6626 | 27.0037 | متأخر | No
2100033574 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 134738905.89 | 6736945.2945 | 121020940.76 | 119623144.51 | 1010210667 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-11-27 | 2020-05-20 | 2020-12-16 | 2020-12-16 | 2020-05-20 |  | أوامر تغيير |  |  |  | منجز | No
2100077534 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 2599753.28 | 129987.664 | 0 | 0 | 1010158786 | نعم | 92565000 | 180901080240 | فسخ العقد | الكميات التي تم تركيبها | 0 | 0 | 2019-12-11 | 2020-07-04 | 2021-09-21 | 2021-09-21 |  |  | اخرى |  | 47.1464 | 24.3244 | مسحوب | No
2100033235 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3296580 | 164829 | 655451.5 | 0 | 1116008805 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 26 | 100 | 2015-04-08 | 2017-03-28 | 2022-08-20 | 2022-08-20 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6624 | 24.6976 | مسحوب | Yes
2100090845 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 244000 | 12200 | 43083 | 0 | 1185000777 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 34 | 2018-02-24 | 2022-02-03 | 2022-02-04 | 2022-02-04 | 2022-02-03 |  |  |  | 43.2698 | 24.3499 | منجز | Yes
2100008094 | أمانة / عسير | تشييد | ذات اولوية عالية | 2751051 | 137552.55 | 217563 | 217563 | 5855041956 | لا | 0 | 190409134648 | فسخ العقد | تكلفة العمل المنجز | 50 | 100 | 2015-08-18 | 2016-08-18 | 2023-01-31 | 2023-01-31 |  |  | ضعف كفاءة المقاول الفنية |  | 41.9833 | 18.354 | مسحوب | No
2100060432 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية وعاجلة | 91863321.88 | 4593166.094 | 59845518.2 | 59845518.2 | 1010144393 | لا | 0 | 180709020923 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2012-05-19 | 2014-11-05 | 2021-06-10 | 2021-06-10 | 2014-11-05 |  | لا يوجد تأخير |  | 46.6286 | 24.4791 | منجز | No
2100014910 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية | 64522975.18 | 3226148.759 | 47410656.68 | 47204023.94 | 1010154943 | لا | 0 | 180709017690 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-09-10 | 2016-08-10 | 2022-02-01 | 2022-02-01 | 2016-08-10 |  | لا يوجد تأخير |  | 44.846 | 26.3149 | منجز | No
2100077560 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 57870000 | 2893500 | 30870823 | 30870823 | 1010017021 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 55.01 | 100 | 2014-08-14 | 2018-03-28 | 2018-03-28 | 2018-03-28 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6658 | 24.71 | مسحوب | No
2100201014 | الهيئة العامة للموانئ | تصميم | ذات اولوية عالية | 1955000 | 97750 | 587500 | 587500 | 2050099301 | لا | 0 |  | جاري | تكلفة العمل المنجز | 98 | 100 | 2021-10-12 | 2022-01-10 | 2022-01-10 | 2022-01-10 |  |  |  |  | 50.2148 | 26.4822 | Failed | No
2100064131 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1085500 | 54275 | 120400 | 0 | 1113001150 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 51 | 100 | 2019-02-13 | 2020-07-22 | 2020-07-22 | 2020-07-22 |  |  | تأخرصرف المستحقات المالية |  | 44.616 | 25.1772 | Failed | Yes
2100074966 | أمانة / عسير | تشييد | ذات اولوية عالية | 2991435 | 149571.75 | 1514046 | 1514046 | 5850016212 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 75 | 100 | 2014-09-21 | 2015-09-15 | 2022-02-02 | 2022-02-02 |  |  | ضعف كفاءة المقاول الفنية |  | 43.3251 | 17.5774 | مسحوب | No
2100002656 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 6649776.75 | 332488.8375 | 5541264.5 | 0 | 2050039353 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2011-05-02 | 2012-12-22 | 2020-09-27 | 2020-09-27 | 2012-12-22 |  | موافقات |  | 50.4819 | 26.4368 | منجز | Yes
2100003216 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 9930588.33 | 496529.4165 | 9930588.33 | 7324661.21 | 2251021202 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-08-03 | 2016-08-03 | 2019-11-26 | 2019-11-26 | 2016-08-03 |  | تأخرصرف المستحقات المالية |  | 50.0738 | 25.9241 | منجز | No
2100006311 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 31134962.41 | 1556748.1205 | 27353766.71 | 27130307.77 | 1010039430 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-12-10 | 2020-06-02 | 2021-05-05 | 2021-05-05 | 2020-06-02 |  | أوامر تغيير | أخرى |  |  | منجز | No
2100039896 | شركة الكهرباء | تشييد | ذات اولوية متوسطة | 51765392 | 2588269.6 | 39901393 | 39901393 | 1010063866 | لا | 0 |  | جاري | اخرى | 86.2 | 100 | 2018-05-28 | 2020-08-27 | 2023-08-03 | 2023-08-03 |  |  | اخرى |  | 46.683 | 24.8734 | Failed | No
2100047460 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2076550 | 103827.5 | 41457 | 0 | 1010309404 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 73 | 100 | 2014-07-16 | 2015-07-11 | 2022-11-07 | 2022-11-07 |  |  | ضعف كفاءة المقاول الفنية |  | 44.8454 | 20.4327 | Failed | Yes
2100013576 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 949050 | 47452.5 | 854144 | 0 | 1185000614 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 95 | 2014-11-24 | 2015-09-20 | 2015-09-20 | 2015-09-20 | 2015-09-20 |  | ضعف كفاءة المقاول الفنية |  | 46.6782 | 24.6957 | منجز | Yes
2100107052 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 12350732 | 617536.6 | 9332794.76 | 9332794.76 | 1010196220 | لا | 0 | 190309007763 | جاري | التكلفة المفوترة | 99 | 100 | 2012-03-11 | 2014-03-01 | 2022-06-15 | 2022-06-15 |  |  | ضعف كفاءة المقاول الفنية |  | 40.0549 | 29.8587 | Failed | No
2100001503 | المؤسسة العامة لتحلية المياه المالحة | تشييد | ذات اولوية عالية | 165720000 | 8286000 | 109082483.99 | 104982475.76 | 1010012911 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 95.9 | 100 | 2020-01-21 | 2021-12-31 | 2023-10-23 | 2023-10-23 |  |  | لا يوجد تأخير |  | 49.5476 | 26.777 | منتظم | No
2100192334 | وزارة الصحة / حفر الباطن | تشييد | ذات اولوية عالية | 5398077 | 269903.85 | 4008635.367 | 4008635.367 | 1010194943 | لا | 0 |  | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 95 | 100 | 2020-10-27 | 2021-04-26 | 2023-03-01 | 2023-03-01 |  |  |  | تم إنذار المقاول كتابيا | 45.9536 | 28.311 | Failed | No
2100006252 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 88958048.1 | 4447902.405 | 63469611 | 63469611 | 5855000147 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 90 | 100 | 2019-03-17 | 2020-09-07 | 2023-03-31 | 2023-03-31 |  |  | منازعات قائمة | أخرى |  |  | Failed | No
2100005014 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 25566476.43 | 1278323.8215 | 9735726.89 | 6799343.3 | 1010196220 | لا | 0 |  | مسحوب | التكلفة المفوترة | 39 | 100 | 2014-09-10 | 2018-02-12 | 2021-11-23 | 2021-11-23 |  |  | ضعف كفاءة المقاول الفنية |  | 40.4511 | 21.2747 | مسحوب | No
2100052404 | شركة المياه الوطنية / منطقة الرياض | إشراف | ذات اولوية عالية | 2712000 | 135600 | 286214.29 | 117000 | 7009104832 | لا | 0 | 181209476032 | جاري | التكلفة المفوترة | 52.6 | 52.6 | 2019-01-05 | 2023-01-06 | 2024-04-22 | 2024-04-22 |  |  | لا يوجد تأخير |  | 45.5789 | 20.4684 | خدمات عامة | No
2100102966 | شركة المياه الوطنية / منطقة حائل | إشراف | ذات اولوية عالية وعاجلة | 15609880 | 780494 | 15438615.45 | 13905184.99 | 2050101543 | لا | 0 | 180301000498 | منجز – استلام ابتدائي | التكلفة المفوترة | 99.9 | 100 | 2018-05-28 | 2020-07-27 | 2021-10-23 | 2021-10-23 | 2020-07-27 |  | لا يوجد تأخير |  | 41.7086 | 27.4912 | منجز | No
2100073146 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 94545931.25 | 4727296.5625 | 85817856 | 85817856 | 3550019957 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 97.5 | 100 | 2012-09-19 | 2016-10-03 | 2021-09-24 | 2021-09-24 |  |  | اخرى |  | 46.765 | 24.9428 | مسحوب | No
2100078341 | وزارة الصحة / الطائف | تشييد | ذات اولوية عالية | 2979000 | 148950 | 0 | 0 | 4035000741 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 95 | 100 | 2018-01-27 | 2019-01-17 | 2022-06-01 | 2022-06-01 | 2019-01-17 |  | تأخرصرف المستحقات المالية |  | 40.4167 | 21.2457 | منجز | No
2100080824 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2415800 | 120790 | 1250000 | 0 | 1010350630 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 96.5 | 100 | 2015-10-09 | 2016-10-03 | 2017-03-10 | 2017-03-10 | 2016-10-03 |  | ضعف كفاءة المقاول الفنية |  | 46.8068 | 23.4522 | منجز | Yes
2100091722 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2955700 | 147785 | 41862 | 0 | 1010150014 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 85 | 100 | 2014-12-31 | 2016-06-23 | 2016-06-23 | 2016-06-23 | 2016-06-23 |  | ضعف كفاءة المقاول الفنية |  | 45.5161 | 23.5419 | منجز | Yes
2100014055 | وزارة الصحة / تبوك | توريد وتركيب | ذات اولوية عالية | 1001500 | 50075 | 0 | 0 | 3550013161 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 0 | 100 | 2017-12-06 | 2018-06-02 | 2020-02-17 | 2020-02-17 |  |  | ضعف كفاءة المقاول الفنية |  | 37.2502 | 25.0543 | مسحوب | No
2100047025 | أمانة / عسير | تشييد | ذات اولوية عالية وعاجلة | 15960000 | 798000 | 8987601 | 8987601 | 5850010031 | لا | 0 |  | جاري | تكلفة العمل المنجز | 80 | 100 | 2019-06-10 | 2020-12-01 | 2023-03-31 | 2023-03-31 |  |  | ضعف كفاءة المقاول الفنية |  | 42.4999 | 18.1961 | Failed | No
2100065310 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 25000000 | 1250000 | 23970480 | 23970480 | 2050027937 | لا | 0 | 190309008537 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2012-10-06 | 2013-08-02 | 2013-11-30 | 2013-11-30 | 2013-08-02 |  |  |  | 50.2155 | 25.6481 | منجز | No
2100103143 | شركة المياه الوطنية / منطقة حائل | إشراف | لم تعد تحتاجها الجهة | 9984000 | 499200 | 7090665.74 | 6626399.07 | 1010314421 | لا | 0 | 200409108787 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2011-12-07 | 2014-12-07 | 2021-01-10 | 2021-01-10 | 2014-12-07 |  | لا يوجد تأخير |  | 41.71 | 27.5052 | منجز | No
2100007453 | المركز الوطني للأرصاد | تشييد | ذات اولوية متوسطة | 2201000 | 110050 | 1100000 | 1100000 | 4030000500 | لا | 0 | 180809054932 | مسحوب | تكلفة العمل المنجز | 50 | 100 | 2010-06-29 | 2012-06-30 | 2012-06-30 | 2012-06-30 |  |  | اخرى |  |  |  | مسحوب | No
2100078094 | وزارة الصحة / الطائف | تشييد | ذات اولوية عالية وعاجلة | 185280 | 9264 | 0 | 0 | 4031027316 | لا | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 55 | 100 | 2019-02-09 | 2019-04-09 | 2019-07-29 | 2019-07-29 |  |  | عدم اكتمال أو ضعف أعمال التصميم والدراسات |  | 40.4134 | 21.2407 | Failed | No
2100107450 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 9693832 | 484691.6 | 2040509.52 | 0 | 1010183010 | لا | 0 |  | جاري | التكلفة المفوترة | 60 | 64 | 2019-03-09 | 2020-12-28 | 2022-03-10 | 2022-03-10 |  |  | اخرى |  | 45.2591 | 25.2379 | Failed | Yes
2100100402 | أمانة / جازان | دراسة الجدوى | ذات اولوية متوسطة | 1342800 | 67140 | 1275615.24 | 1275615.24 | 5900031907 | لا | 0 |  | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2018-08-29 | 2020-08-28 | 2021-09-07 | 2021-09-07 | 2020-08-28 |  | ضعف كفاءة المقاول الفنية |  |  |  | منجز | No
2100059846 | المؤسسة العامة لتحلية المياه المالحة | إشراف | ذات اولوية عالية | 50428576 | 2521428.8 | 36581299.18 | 36581299.18 | 2051023736 | لا | 0 | 200101013786 | جاري | منهجية القيمة المكتسبة | 92 | 100 | 2019-03-08 | 2022-03-07 | 2022-03-07 | 2022-03-07 |  |  |  |  | 50.2056 | 26.1754 | خدمات عامة | No
2100029746 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 735600 | 36780 | 42017 | 0 | 4030065096 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 0 | 100 | 2015-08-11 | 2016-07-26 | 2020-08-01 | 2020-08-01 |  |  | ضعف كفاءة المقاول الفنية |  | 46.5665 | 24.7477 | مسحوب | Yes
2100033305 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2134929 | 106746.45 | 1662133 | 1662133 | 1155000117 | لا | 0 |  | جاري الاستلام الإبتدائي | التكلفة المفوترة | 100 | 100 | 2019-06-17 | 2020-06-11 | 2022-01-13 | 2022-01-13 |  |  | اخرى |  | 45.2591 | 25.2379 | Failed | No
2100052651 | الهيئة العامة للموانئ | تشييد | ذات اولوية عالية | 59954017.9 | 2997700.895 | 50895562.21 | 50895562.21 | 4030039641 | لا | 0 | 181101276583 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-06-30 | 2021-02-18 | 2021-11-07 | 2021-11-07 | 2021-02-18 |  | ضعف كفاءة المقاول الفنية |  | 49.6856 | 27.0232 | منجز | No
2100016284 | وزارة المالية | أخرى | ذات اولوية عالية | 5579907 | 278995.35 | 4439550.58 | 4439550.58 | 1010177619 | لا | 0 | 200909152478 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2020-10-06 | 2021-10-31 | 2022-04-30 | 2022-04-30 | 2021-10-31 |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | منجز | No
2100101636 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تصميم وتشييد | ذات اولوية عالية وعاجلة | 78751103.33 | 3937555.1665 | 64371010.33 | 64371010.33 | 1116000082 | لا | 0 | 180809058385 | جاري | منهجية القيمة المكتسبة | 96 | 100 | 2013-04-17 | 2014-10-11 | 2023-10-23 | 2023-10-23 |  |  | لا يوجد تأخير |  | 49.5648 | 27.1019 | Failed | No
2100009450 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية وعاجلة | 86587902.01 | 4329395.1005 | 62358956.88 | 60169110.74 | 1010034808 | لا | 0 | 181109360894 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2012-12-22 | 2015-06-10 | 2021-07-30 | 2021-07-30 | 2015-06-10 |  | لا يوجد تأخير |  | 46.6269 | 24.4799 | منجز | No
2100018734 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية وعاجلة | 38245089.4 | 1912254.47 | 33961435.04 | 33961435.04 | 1010219886 | لا | 0 | 180709020158 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-06-04 | 2017-05-04 | 2021-11-10 | 2021-11-10 | 2017-05-04 |  | تأخرصرف المستحقات المالية |  | 42.0102 | 21.9179 | منجز | No
2100048495 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 36351032 | 1817551.6 | 34550622 | 17512804 | 2051030949 | لا | 0 | 180901083012 | جاري | التكلفة المفوترة | 90 | 100 | 2019-01-15 | 2020-12-23 | 2021-11-02 | 2021-11-02 |  |  |  | أخرى | 50.0079 | 26.4197 | Failed | No
2100061585 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 71975000 | 3598750 | 57061926 | 57061926 | 2050018730 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 94.22 | 100 | 2014-05-25 | 2016-05-25 | 2020-09-07 | 2020-09-07 | 2016-05-25 |  | لا يوجد تأخير |  | 40.4495 | 21.3416 | منجز | No
2100102546 | شركة المياه الوطنية / منطقة الرياض | إشراف | ذات اولوية عالية | 4918000 | 245900 | 4893790 | 4893790 | 2050099301 | لا | 0 | 180809042634 | منجز – استلام نهائي | التكلفة المفوترة | 99.46 | 100 | 2016-03-03 | 2019-03-03 | 2019-03-03 | 2019-03-03 |  | 2019-03-03 | لا يوجد تأخير |  | 45.2878 | 24.0664 | منجز | No
2100080161 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية متوسطة | 38534495 | 1926724.75 | 23270989.18 | 23270989.18 | 1010262459 | لا | 0 | 190401080615 | جاري | منهجية القيمة المكتسبة | 71.77 | 100 | 2019-08-01 | 2022-08-01 | 2022-10-15 | 2022-10-15 |  |  | لا يوجد تأخير |  | 36.5033 | 28.4235 | Failed | No
2100102686 | أمانة / حائل | دراسة الجدوى | ذات اولوية متوسطة | 1098720 | 54936 | 929213 | 929213 | 1010433237 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 93 | 97 | 2018-10-10 | 2020-09-29 | 2020-09-28 | 2020-09-28 | 2020-09-29 |  | اخرى |  | 40.9385 | 28.0075 | منجز | No
2100001326 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية | 60084804.81 | 3004240.2405 | 48684829.79 | 48684829.79 | 1010154943 | لا | 0 | 180709020083 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-01-06 | 2016-12-26 | 2022-04-30 | 2022-04-30 | 2016-12-26 |  | لا يوجد تأخير |  | 37.9496 | 24.1471 | منجز | No
2100109605 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 45300924.52 | 2265046.226 | 40770830.85 | 30454176.17 | 1010209661 | لا | 0 | 180709022038 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-02-08 | 2017-01-08 | 2022-11-23 | 2022-11-23 | 2017-01-08 |  | تأخرصرف المستحقات المالية |  | 40.5428 | 21.3116 | منجز | No
2100056836 | وزارة الحرس الوطني / الشؤون الصحية | تشييد | ذات اولوية عالية | 122850000 | 6142500 | 99450000 | 99450000 | 1010057263 | لا | 0 | 180909092207 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-04-29 | 2020-04-28 | 2022-07-15 | 2022-07-15 | 2020-04-28 |  | تأخرصرف المستحقات المالية |  | 43.7886 | 26.3564 | منجز | No
2100191586 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية وعاجلة | 26346600 | 1317330 | 22016700 | 22016700 | 1131014852 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99.92 | 100 | 2020-06-10 | 2021-12-10 | 2022-02-27 | 2022-02-27 | 2021-12-10 |  |  |  | 46.6255 | 24.8526 | منجز | No
2100199006 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 12707190 | 635359.5 | 2438335.16 | 1650914.18 | 1010158780 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 28.57 | 37.18 | 2021-07-04 | 2023-07-04 | 2023-07-04 | 2023-07-04 |  |  |  |  | 40.4248 | 21.2841 | متأخر | No
2100000696 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 46999200 | 2349960 | 40970717.35 | 40970717.35 | 1010085982 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 99.34 | 100 | 2019-03-28 | 2021-03-28 | 2021-01-31 | 2021-01-31 |  | 2021-03-28 | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100008444 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2158286 | 107914.3 | 0 | 0 | 1010246941 | لا | 0 |  | مسحوب | التكلفة المفوترة | 1 | 100 | 2011-11-21 | 2014-08-12 | 2013-03-15 | 2013-03-15 |  |  | ضعف كفاءة المقاول الفنية |  | 44.4412 | 24.5406 | مسحوب | No
2100104160 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2898513 | 144925.65 | 625092 | 625092 | 5860024921 | لا | 0 |  | مسحوب | التكلفة المفوترة | 49 | 100 | 2019-08-18 | 2020-11-09 | 2022-05-18 | 2022-05-18 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.0529 | 18.5228 | مسحوب | No
2100006145 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 26435200 | 1321760 | 26147714.3 | 22735325.62 | 1010026934 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 99.73 | 100 | 2017-07-06 | 2019-01-06 | 2020-12-30 | 2020-12-30 |  | 2019-01-06 | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100107240 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 8470636.2 | 423531.81 | 5312617 | 5312617 | 1116004360 | لا | 0 |  | جاري | التكلفة المفوترة | 75 | 100 | 2013-01-07 | 2014-12-28 | 2022-01-19 | 2022-01-19 |  |  | ضعف كفاءة المقاول الفنية |  | 44.4412 | 24.5406 | Failed | No
2100028114 | وزارة التعليم | تشييد | ذات اولوية عالية | 12425281.75 | 621264.0875 | 0.01 | 0.01 | 1010192035 | لا | 0 |  | مسحوب | التكلفة المفوترة | 1 | 100 | 2015-01-28 | 2017-04-17 | 2017-04-17 | 2017-04-17 |  |  | ضعف كفاءة المقاول الفنية |  | 50.632 | 26.195 | مسحوب | No
2100061596 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية وعاجلة | 75245096.93 | 3762254.8465 | 58257144.93 | 58257144.93 | 1010065292 | لا | 0 | 180709016561 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-04-27 | 2016-10-13 | 2021-04-01 | 2021-04-01 | 2016-10-13 |  | تأخرصرف المستحقات المالية |  | 43.4991 | 25.9045 | منجز | No
2100092820 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 9283135.14 | 464156.757 | 0.01 | 0.01 | 5950011052 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-12-07 | 2019-06-18 | 2019-06-18 | 2019-06-18 | 2019-06-18 |  | ضعف كفاءة المقاول الفنية |  | 44.2341 | 17.5757 | منجز | No
2100007545 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 4983481.34 | 249174.067 | 4000439.29 | 4000439.29 | 1010211349 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-06-04 | 2016-11-25 | 2022-01-13 | 2022-01-13 | 2016-11-25 |  |  |  | 45.313 | 24.0763 | منجز | No
2100073102 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 42159736.8 | 2107986.84 | 27126269 | 27126269 | 1116001737 | لا | 0 |  | ايقاف جزئي | الكميات التي تم تركيبها | 69.44 | 82 | 2013-10-23 | 2020-02-11 | 2022-11-30 | 2022-11-30 |  |  |  |  | 46.6757 | 24.6885 | متأخر | No
2100032631 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3049801 | 152490.05 | 421496 | 0 | 1014000394 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 78 | 100 | 2015-07-29 | 2017-07-18 | 2021-06-09 | 2021-06-09 | 2017-07-18 |  | تأخرصرف المستحقات المالية |  | 46.7139 | 23.3519 | منجز | Yes
2100107660 | وزارة التعليم | تشييد | ذات اولوية عالية | 2273551.2 | 113677.56 | 2376183 | 2029896 | 4603004056 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-07-23 | 2016-09-15 | 2019-05-01 | 2019-05-01 | 2016-09-15 |  |  |  | 41.0859 | 19.1571 | منجز | No
2100035416 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 10722293.01 | 536114.6505 | 0 | 0 | 1010233305 | لا | 0 |  | ايقاف كلي | التكلفة المفوترة | 0 | 100 | 2017-01-29 | 2019-01-19 | 2022-05-11 | 2022-05-11 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | Failed | No
2100049302 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 9222349.18 | 461117.459 | 5558070.38 | 0 | 1010196220 | لا | 0 | 190209012730 | مسحوب | التكلفة المفوترة | 80 | 100 | 2013-11-04 | 2015-07-27 | 2022-05-04 | 2022-05-04 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | مسحوب | Yes
2100042674 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 4959436.05 | 247971.8025 | 0.01 | 0.01 | 4030298655 | لا | 0 |  | مسحوب | التكلفة المفوترة | 12 | 100 | 2011-09-11 | 2012-07-01 | 2023-05-10 | 2023-05-10 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 44.2341 | 17.5757 | مسحوب | No
2100058612 | وزارة التعليم | تشييد | ذات اولوية عالية | 10280046.39 | 514002.3195 | 507087.9 | 0 | 5950007285 | لا | 0 |  | مسحوب | التكلفة المفوترة | 8 | 100 | 2013-08-27 | 2015-08-17 | 2023-05-10 | 2023-05-10 |  |  | ضعف كفاءة المقاول الفنية |  | 42.6509 | 17.1567 | مسحوب | Yes
2100001551 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 43288268.8 | 2164413.44 | 38588358.47 | 24446458.53 | 1010060469 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-07-27 | 2018-01-12 | 2020-01-15 | 2020-01-15 | 2018-01-12 |  | ضعف كفاءة المقاول الفنية |  | 40.2691 | 20.1489 | منجز | No
2100002704 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 6738574.82 | 336928.741 | 0.02 | 0.02 | 4030173446 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-01-19 | 2015-07-05 | 2019-01-14 | 2019-01-14 | 2015-07-05 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.836 | 21.4408 | منجز | No
2100085024 | وزارة البيئة والمياة والزراعة | تشييد | لم تعد تحتاجها الجهة | 92020000 | 4601000 | 82900830 | 82900830 | 1010159432 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2011-11-16 | 2015-06-06 | 2015-08-05 | 2015-08-05 | 2015-06-06 |  | ضعف كفاءة المقاول الفنية |  | 41.584 | 19.8469 | منجز | No
2100016450 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 9394660.39 | 469733.0195 | 0.01 | 0.01 | 5950010876 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2016-10-16 | 2018-08-07 | 2020-11-04 | 2020-11-04 | 2018-08-07 |  | ضعف كفاءة المقاول الفنية |  | 44.2341 | 17.5757 | منجز | No
2100060524 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 3180000 | 159000 | 1821225 | 1821225 | 1010020047 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2020-03-09 | 2021-07-09 | 2022-03-31 | 2022-03-31 | 2021-07-09 |  | لا يوجد تأخير |  | 46.6928 | 24.8004 | منجز | No
2100105335 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية | 34621500 | 1731075 | 16556258.26 | 16556258.26 | 5850002600 | لا | 0 | 190201038178 | جاري | منهجية القيمة المكتسبة | 95 | 99 | 2019-05-01 | 2020-04-19 | 2022-05-01 | 2022-05-01 |  |  | لا يوجد تأخير |  | 42.7542 | 17.0999 | Failed | No
2100035431 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 102850000 | 5142500 | 92565000 | 92565000 | 1010108612 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 97 | 97 | 2011-06-01 | 2017-07-22 | 2017-07-22 | 2017-07-22 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7125 | 24.6942 | مسحوب | No
2100010765 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 10242951.47 | 512147.5735 | 1990518.13 | 1731307.95 | 1010090099 | لا | 0 | 190309007790 | مسحوب | التكلفة المفوترة | 28 | 100 | 2012-07-21 | 2014-07-11 | 2022-12-01 | 2022-12-01 |  |  | ضعف كفاءة المقاول الفنية |  | 42.6031 | 20.0028 | مسحوب | No
2100193395 | الجمارك السعودية | إشراف | ذات اولوية عالية | 8830702.54 | 441535.127 | 9622939.04 | 9622939.04 | 1010363372 | لا | 0 | 181209455456 | مسحوب | تكلفة العمل المنجز | 100 | 100 | 2014-01-14 | 2017-01-15 | 2021-11-30 | 2021-11-30 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 50.7585 | 24.7369 | مسحوب | No
2100087706 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 3590800 | 179540 | 3226454.5 | 3226454.5 | 1010227442 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2020-04-02 | 2021-08-02 | 2021-06-20 | 2021-06-20 | 2021-08-02 |  | لا يوجد تأخير |  | 46.6421 | 24.5157 | منجز | No
2100012143 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية عالية | 14890312.5 | 744515.625 | 14787181 | 14787181 | 5850017617 | لا | 0 | 190801122142 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-09-17 | 2020-09-06 | 2020-11-05 | 2020-11-05 |  | 2020-09-06 | لا يوجد تأخير |  | 42.4989 | 18.2169 | منجز | No
2100058741 | شركة المياه الوطنية / منطقة الرياض | إشراف | ذات اولوية عالية | 2856000 | 142800 | 1896679.83 | 1896679.83 | 1010426678 | لا | 0 |  | منجز – استلام نهائي | تكلفة العمل المنجز | 66.39 | 100 | 2017-03-01 | 2019-01-01 | 2020-01-30 | 2020-01-30 |  | 2019-01-01 | لا يوجد تأخير |  | 46.7942 | 24.6531 | منجز | No
2100016822 | أمانة / الرياض | تشييد | ذات اولوية عالية | 4173712 | 208685.6 | 0 | 0 | 1010171813 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-01-12 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 |  | ضعف كفاءة المقاول الفنية |  | 43.8175 | 25.0186 | منجز | No
2100077011 | أمانة / جازان | تشييد | ذات اولوية عالية | 8555000 | 427750 | 7009264.2 | 7009264.2 | 5900008127 | لا | 0 | 181209401251 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-09-24 | 2019-09-19 | 2021-10-20 | 2021-10-20 | 2019-09-19 |  | ضعف كفاءة المقاول الفنية |  | 42.5717 | 16.8804 | منجز | No
2100059264 | وزارة التعليم | تشييد | ذات اولوية عالية | 2595470.6 | 129773.53 | 782559 | 782559 | 2050018834 | لا | 0 |  | مسحوب | التكلفة المفوترة | 33 | 100 | 2015-08-29 | 2016-09-23 | 2024-02-01 | 2024-02-01 |  |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | مسحوب | No
2100036271 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 9953732.12 | 497686.606 | 0.01 | 0.01 | 5950011291 | لا | 0 | 190209016278 | جاري | التكلفة المفوترة | 83 | 99 | 2013-06-15 | 2015-03-07 | 2023-01-03 | 2023-01-03 |  |  | ضعف كفاءة المقاول الفنية |  | 44.2341 | 17.5757 | Failed | No
2100002306 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 11375838.74 | 568791.937 | 5783285.6 | 2892961.59 | 5855014881 | لا | 0 | 190709026775 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-11-18 | 2017-11-07 | 2020-12-09 | 2020-12-09 | 2017-11-07 |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | منجز | No
2100029035 | أمانة / تبوك | تشييد | ذات اولوية عالية | 582120 | 29106 | 489038 | 489038 | 3350017280 | لا | 0 | 200501038056 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-12-01 | 2020-11-19 | 2021-02-22 | 2021-02-22 | 2020-11-19 |  | ضعف كفاءة المقاول الفنية |  | 36.5108 | 27.4005 | منجز | No
2100091954 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 4817924.13 | 240896.2065 | 2554944.59 | 0 | 1010183010 | لا | 0 | 190209012575 | مسحوب | التكلفة المفوترة | 40 | 100 | 2016-12-06 | 2018-05-30 | 2022-08-10 | 2022-08-10 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | مسحوب | Yes
2100037424 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 16455150 | 822757.5 | 15780307 | 15780307 | 2252026598 | لا | 0 | 190309002099 | جاري | تكلفة العمل المنجز | 97 | 97 | 2015-09-13 | 2016-07-10 | 2022-11-29 | 2022-11-29 |  |  | تأخرصرف المستحقات المالية |  | 49.6712 | 25.4161 | منتظم | No
2100104366 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2255992 | 112799.6 | 0 | 0 | 5864031115 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0 | 100 | 2010-02-09 | 2011-04-29 | 2023-05-24 | 2023-05-24 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.0529 | 18.5228 | مسحوب | No
2100013160 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1369052 | 68452.6 | 1341241.2 | 0 | 1014000288 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 98 | 100 | 2014-12-31 | 2015-12-26 | 2021-06-20 | 2021-06-20 | 2015-12-26 |  | ضعف كفاءة المقاول الفنية |  | 46.8823 | 23.552 | منجز | Yes
2100068983 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 18037980 | 901899 | 18037980 | 18037980 | 2056001352 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-02-03 | 2021-11-06 | 2021-11-06 | 2021-11-06 | 2021-11-06 |  |  |  | 48.4822 | 27.4631 | منجز | No
2100007081 | الهيئة العامة للموانئ | توريد وتركيب | ذات اولوية عالية وعاجلة | 4540000 | 227000 | 4540000 | 4540000 | 2054001362 | لا | 0 | 181201484726 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-11-18 | 2019-07-16 | 2019-07-16 | 2019-07-16 | 2019-07-16 |  | عدم واقعية الجدول الزمني |  | 42.5362 | 16.8907 | منجز | No
2100020473 | وزارة الموارد البشرية والتنمية الإجتماعية | إشراف | ذات اولوية منخفضة | 1300300 | 65015 | 3483124 | 3483124 | 1010429789 | لا | 0 | 190209044347 | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2014-12-28 | 2016-12-05 | 2021-12-29 | 2021-12-29 | 2016-12-05 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 44.8293 | 26.3081 | منجز | No
2100087146 | وزارة الموارد البشرية والتنمية الإجتماعية | تشييد | ذات اولوية منخفضة | 16486713.68 | 824335.684 | 7423912.36 | 7423912.36 | 2511004823 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 85 | 100 | 2013-09-01 | 2015-08-10 | 2022-05-18 | 2022-05-18 |  |  | ضعف كفاءة المقاول الفنية |  | 48.4447 | 28.4623 | مسحوب | No
2100109340 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 4858832.94 | 242941.647 | 1415225.91 | 1415225.91 | 1010045486 | لا | 0 |  | مسحوب | التكلفة المفوترة | 35 | 100 | 2015-07-29 | 2017-04-19 | 2022-03-16 | 2022-03-16 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.1677 | 21.5008 | مسحوب | No
2100000674 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية | 7409797 | 370489.85 | 6229227.5 | 6229227.5 | 4030087384 | لا | 0 | 180809061830 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 98 | 2016-04-10 | 2018-03-20 | 2019-01-06 | 2019-01-06 |  | 2018-03-20 | لا يوجد تأخير |  | 39.5933 | 24.4518 | منجز | No
2100071492 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1770123.6 | 88506.18 | 1549190.5 | 0 | 1116008805 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 88 | 100 | 2015-03-17 | 2016-06-09 | 2019-10-22 | 2019-10-22 | 2016-06-09 |  | ضعف كفاءة المقاول الفنية |  | 44.5954 | 25.173 | منجز | Yes
2100028755 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3353300 | 167665 | 2648831 | 0 | 1017000207 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 92.41 | 100 | 2014-12-24 | 2016-12-13 | 2016-12-23 | 2016-12-23 | 2016-12-13 |  | ضعف كفاءة المقاول الفنية |  | 46.6713 | 24.7019 | منجز | Yes
2100045592 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3303825 | 165191.25 | 41714 | 0 | 1010171813 | لا | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 0 | 100 | 2015-04-01 | 2016-06-24 | 2016-06-24 | 2016-06-24 |  |  | تأخرصرف المستحقات المالية |  | 46.6617 | 24.7144 | Failed | Yes
2100108102 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | تشييد | ذات اولوية عالية | 16640032 | 832001.6 | 13007751.12 | 13007751.12 | 4030087384 | لا | 0 | 181201489361 | جاري | اخرى | 98 | 100 | 2019-04-15 | 2020-01-08 | 2023-03-31 | 2023-03-31 |  |  | تأخرصرف المستحقات المالية |  | 42.507 | 18.2194 | منتظم | No
2100087043 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية وعاجلة | 153254708 | 7662735.4 | 109044497 | 105129175.47 | 2050018730 | لا | 0 | 180709028695 | جاري | منهجية القيمة المكتسبة | 83.96 | 100 | 2013-09-01 | 2016-07-30 | 2022-10-30 | 2022-10-30 |  |  | لا يوجد تأخير |  | 42.5825 | 16.8917 | Failed | No
2100058730 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 7539700 | 376985 | 1066826.4 | 0 | 1185000614 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 26 | 100 | 2015-06-07 | 2017-01-27 | 2021-06-17 | 2021-06-17 |  |  | ضعف كفاءة المقاول الفنية |  | 44.8646 | 20.4441 | مسحوب | Yes
2100044752 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1100300 | 55015 | 126995.65 | 0 | 1116007586 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 6 | 100 | 2014-08-02 | 2015-10-26 | 2023-07-02 | 2023-07-02 |  |  | ضعف كفاءة المقاول الفنية |  | 45.3558 | 26.4975 | مسحوب | Yes
2100013296 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1415825 | 70791.25 | 453024.25 | 0 | 2511007879 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 32 | 100 | 2015-09-08 | 2017-03-01 | 2019-11-14 | 2019-11-14 | 2017-03-01 |  | ضعف كفاءة المقاول الفنية |  | 46.685 | 24.6932 | منجز | Yes
2100064234 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 26730 | 1336.5 | 0 | 0 | 1010249671 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 19 | 100 | 2019-07-27 | 2021-10-14 | 2020-07-16 | 2020-07-16 |  |  | ضعف كفاءة المقاول الفنية |  | 47.7127 | 27.5618 | مسحوب | No
2100045846 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 4044450 | 202222.5 | 4044450 | 4044450 | 2060016250 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-12-31 | 2019-12-18 | 2020-12-19 | 2020-12-19 | 2019-12-18 |  |  |  | 48.8694 | 25.977 | منجز | No
2100095874 | شركة المياه الوطنية / منطقة نجران | تشييد | ذات اولوية عالية | 11195810 | 559790.5 | 11195810 | 11195810 | 4030129066 | لا | 0 | 180709033413 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2013-03-30 | 2015-03-09 | 2019-12-30 | 2019-12-30 | 2015-03-09 | 2020-12-28 | لا يوجد تأخير |  | 44.2341 | 17.5757 | منجز | No
2100190901 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 8001000 | 400050 | 6400800 | 6400800 | 4031041927 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-12-19 | 2020-04-19 | 2020-12-21 | 2020-12-21 | 2020-04-19 |  |  |  | 39.995 | 21.3389 | منجز | No
2100010065 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 6900250 | 345012.5 | 3026707.26 | 0 | 1010242626 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 51 | 100 | 2014-01-11 | 2014-12-27 | 2015-10-05 | 2015-10-05 |  |  | ضعف كفاءة المقاول الفنية |  | 45.4635 | 25.069 | مسحوب | Yes
2100201445 | وزارة الحرس الوطني / الشؤون الفنية بالقطاع الغربي | تشييد | ذات اولوية عالية وعاجلة | 7761669.7 | 388083.485 | 0 | 0 | 4030009703 | لا | 0 | 220801237529 | جاري | تكلفة العمل المنجز | 8 | 11 | 2022-10-25 | 2024-04-07 | 2024-04-07 | 2024-04-07 |  |  |  |  | 40.4491 | 21.4337 | منتظم | No
2100089574 | شركة المياه الوطنية / منطقة نجران | تشييد | ذات اولوية عالية | 39709640 | 1985482 | 21477110.8 | 21477110.8 | 5950009827 | لا | 0 | 190501111280 | جاري | منهجية القيمة المكتسبة | 76.8 | 100 | 2018-04-24 | 2021-03-21 | 2022-03-08 | 2022-03-08 |  |  | تأخرصرف المستحقات المالية |  | 44.2336 | 17.5636 | متأخر | No
2100105291 | وزارة الموارد البشرية والتنمية الإجتماعية | تشييد | ذات اولوية منخفضة | 55888036.58 | 2794401.829 | 39485027.24 | 39485027.24 | 2051027988 | لا | 0 | 180909092682 | مسحوب | الكميات التي تم تركيبها | 88 | 100 | 2013-07-06 | 2018-07-27 | 2021-12-31 | 2021-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 43.9322 | 26.2958 | مسحوب | No
2100060222 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 7136254.36 | 356812.718 | 7136254.36 | 6752873.6 | 1010196414 | لا | 0 | 180401004194 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-04-08 | 2019-01-28 | 2022-12-31 | 2022-12-31 |  |  | تأخرصرف المستحقات المالية |  | 39.1677 | 21.5008 | متأخر | No
2100025336 | وزارة الصحة / تجمع الشرقية | تحديث وتوريد | ذات اولوية عالية | 9110601.15 | 455530.0575 | 2499581.12 | 2499581.12 | 1010057263 | لا | 0 | 211109304176 | جاري | تكلفة العمل المنجز | 90 | 100 | 2019-01-25 | 2021-09-27 | 2022-06-30 | 2022-06-30 |  |  | تصاريح أعمال التنفيذ |  | 50.1008 | 26.4129 | Failed | No
2100016892 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2772000 | 138600 | 2772000 | 0 | 1118001501 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-01-29 | 2019-02-25 | 2019-02-25 | 2019-02-25 | 2019-02-25 |  |  |  | 46.6742 | 24.7118 | منجز | Yes
2100075854 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2806202 | 140310.1 | 1379730 | 0 | 1010168247 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 41 | 2018-12-26 | 2020-03-20 | 2020-03-21 | 2020-03-21 | 2020-03-20 |  |  |  | 46.8483 | 23.513 | منجز | Yes
2100201471 | وزارة الصحة / الباحة | تحديث وتوريد | ذات اولوية عالية | 48000000 | 2400000 | 23795455.9 | 23795455.9 | 4030045393 | لا | 0 | 181009167082 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 99 | 100 | 2021-05-23 | 2022-09-28 | 2022-04-07 | 2022-04-07 | 2022-09-28 |  |  |  | 41.4382 | 20.0634 | منجز | No
2100105593 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية | 15999900 | 799995 | 15999900 | 15999900 | 2050003475 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-01-29 | 2021-01-07 | 2020-05-13 | 2020-05-13 |  | 2021-01-07 | لا يوجد تأخير |  | 41.7179 | 27.5215 | منجز | No
2100007803 | شركة المياه الوطنية / منطقة الرياض | إشراف | ذات اولوية عالية | 16794000 | 839700 | 16783870.38 | 16783870.38 | 1010314421 | لا | 0 |  | منجز – استلام نهائي | مدفوعات ساعات العمل | 100 | 100 | 2017-08-29 | 2020-08-29 | 2021-03-31 | 2021-03-31 |  | 2020-08-29 | لا يوجد تأخير |  | 46.7942 | 24.6524 | منجز | No
2100030166 | أمانة / الرياض | تشييد | ذات اولوية عالية | 328500 | 16425 | 2042.5 | 0 | 1010422547 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-07-25 | 2016-07-09 | 2019-12-28 | 2019-12-28 | 2016-07-09 |  | اخرى |  | 44.3924 | 23.4871 | منجز | Yes
2100075095 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2603220 | 130161 | 1828250 | 0 | 1010272521 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-10-05 | 2016-11-22 | 2019-08-23 | 2019-08-23 | 2016-11-22 |  | تأخرصرف المستحقات المالية |  | 47.2188 | 24.1662 | منجز | Yes
2100193373 | وزارة الحرس الوطني / وكالة الشؤون الفنية | تحديث وتوريد | ذات اولوية متوسطة | 3094236 | 154711.8 | 289800 | 289800 | 1010161812 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 38 | 85 | 2021-05-26 | 2022-05-15 | 2023-03-07 | 2023-03-07 |  |  |  |  | 46.6816 | 24.7038 | Failed | No
2100047961 | وزارة الموارد البشرية والتنمية الإجتماعية | إشراف | ذات اولوية منخفضة | 1648500 | 82425 | 2810460.5 | 2810460.5 | 1010435790 | لا | 0 | 181009179597 | مسحوب | مدفوعات ساعات العمل | 84 | 100 | 2015-01-06 | 2017-06-09 | 2022-06-08 | 2022-06-08 |  |  | ضعف كفاءة المقاول الفنية |  | 40.1898 | 29.9604 | مسحوب | No
2100074911 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2342890 | 117144.5 | 42093 | 0 | 1010194799 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 80 | 100 | 2015-10-14 | 2017-01-06 | 2022-07-18 | 2022-07-18 | 2017-01-06 |  | ضعف كفاءة المقاول الفنية |  | 43.692 | 24.6746 | منجز | Yes
2100023656 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 11849565 | 592478.25 | 5792737.5265 | 0 | 1010056094 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 49 | 100 | 2015-08-05 | 2017-07-25 | 2019-07-28 | 2019-07-28 | 2017-07-25 |  | ضعف كفاءة المقاول الفنية |  | 46.6775 | 24.6951 | منجز | Yes
2100198796 | وزارة الحرس الوطني / وكالة الشؤون الفنية | تحديث وتوريد | ذات اولوية متوسطة | 816500 | 40825 | 509726 | 509726 | 4030160669 | لا | 0 |  | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 100 | 100 | 2021-10-26 | 2022-04-20 | 2022-09-01 | 2022-09-01 |  |  |  |  | 46.6828 | 24.7063 | Failed | No
2100105103 | شركة المياه الوطنية | تشييد | ذات اولوية عالية وعاجلة | 123800000 | 6190000 | 75119051.68 | 64451051.68 | 1010011560 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 95.01 | 100 | 2018-04-19 | 2019-08-19 | 2021-12-11 | 2021-12-11 | 2019-08-19 |  | لا يوجد تأخير |  | 41.0165 | 30.9619 | منجز | No
2100053082 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1088172.75 | 54408.6375 | 0 | 0 | 1116005202 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 79 | 2018-12-23 | 2019-12-08 | 2019-12-08 | 2019-12-08 | 2019-12-08 |  | ضعف كفاءة المقاول الفنية |  | 46.6699 | 24.7157 | منجز | No
2100105895 | وزارة الموارد البشرية والتنمية الإجتماعية | تشييد | ذات اولوية منخفضة | 15600679 | 780033.95 | 10030994.08 | 10030994.08 | 1131022493 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 93 | 100 | 2015-02-09 | 2017-01-17 | 2021-12-31 | 2021-12-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 50.1045 | 26.3964 | مسحوب | No
2100061235 | شركة المياه الوطنية | تشييد | ذات اولوية عالية وعاجلة | 296000000 | 14800000 | 222897680.16 | 222897680.16 | 1010011560 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 95.1 | 100 | 2018-04-19 | 2019-08-19 | 2021-12-11 | 2021-12-11 | 2019-08-19 |  | اخرى |  | 41.0165 | 30.9619 | منجز | No
2100044962 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 6573166 | 328658.3 | 1745111.03 | 0 | 1010231660 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 74 | 100 | 2015-07-08 | 2017-06-27 | 2021-06-20 | 2021-06-20 |  |  | ضعف كفاءة المقاول الفنية |  | 45.303 | 24.0239 | Failed | Yes
2100178452 | وزارة الثقافة | ترميم | ذات اولوية عالية | 21573199.89 | 1078659.9945 | 21438526.53 | 19415879.87 | 1010208611 | لا | 0 | 201109074189 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-10-26 | 2020-04-10 | 2020-04-10 | 2020-04-10 |  | 2020-04-10 |  |  | 41.745 | 27.4609 | منجز | No
2100080301 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 932913 | 46645.65 | 43122 | 0 | 1010019983 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-04-09 | 2019-04-04 | 2018-12-03 | 2018-12-03 | 2019-04-04 |  |  |  | 47.1646 | 25.56 | منجز | Yes
2100011734 | وزارة الحرس الوطني / وكالة الشؤون الفنية | تشييد | ذات اولوية متوسطة | 17216185.35 | 860809.2675 | 17216185.35 | 17216185.35 | 1010243552 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-10-08 | 2020-03-22 | 2021-01-10 | 2021-01-10 | 2020-03-22 |  |  |  | 46.6857 | 24.7013 | منجز | No
2100010651 | جامعة الملك خالد | تشييد | ذات اولوية عالية وعاجلة | 2429055776 | 121452788.8 | 2307602778 | 2307602778 | 2051037631 | لا | 0 | 180909088079 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2009-12-06 | 2021-12-31 | 2021-12-24 | 2021-12-24 |  |  | تأخرصرف المستحقات المالية |  | 42.8114 | 18.1027 | متأخر | No
2100191542 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 3195210 | 159760.5 | 2880514.6 | 2880514.6 | 1010158780 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 90.15 | 100 | 2021-01-10 | 2021-11-10 | 2022-01-31 | 2022-01-31 | 2021-11-10 |  |  |  | 46.626 | 24.8055 | منجز | No
2100101872 | وزارة الصحة / القصيم | تشييد | ذات اولوية متوسطة | 1535870 | 76793.5 | 1535870 | 1535870 | 1131019987 | لا | 0 | 181009151277 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 0 | 2018-09-23 | 2020-08-30 | 2021-01-01 | 2021-01-01 | 2020-08-30 |  | اخرى |  | 43.9553 | 26.3508 | منجز | No
2100105232 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 17242104 | 862105.2 | 17240283.28 | 17240283.28 | 1010158780 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-09-25 | 2021-09-25 | 2020-12-18 | 2020-12-18 |  | 2021-09-25 | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100023763 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية وعاجلة | 3965250 | 198262.5 | 0 | 0 | 2054001362 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-08-08 | 2020-07-07 | 2020-07-21 | 2020-07-21 |  | 2020-07-07 | لا يوجد تأخير |  | 49.6696 | 26.9595 | منجز | No
2100102034 | وزارة الصحة / القصيم | تشييد | ذات اولوية عالية | 2740982 | 137049.1 | 0 | 0 | 1129103691 | لا | 0 |  | جاري | تكلفة العمل المنجز | 16 | 25 | 2020-03-08 | 2022-10-12 | 2023-12-21 | 2023-12-21 |  |  | اخرى |  | 43.9408 | 26.371 | متأخر | No
2100033062 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1097175 | 54858.75 | 1097175 | 0 | 1117001977 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 60 | 2018-04-25 | 2020-04-14 | 2020-04-15 | 2020-04-15 | 2020-04-14 |  |  |  | 46.6843 | 24.7001 | منجز | Yes
2100079015 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 5369722.23 | 268486.1115 | 1514302.52 | 0 | 3350007326 | لا | 0 |  | مسحوب | التكلفة المفوترة | 28 | 100 | 2013-09-09 | 2016-03-17 | 2019-10-24 | 2019-10-24 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.6968 | 27.506 | مسحوب | Yes
2100101360 | المؤسسة العامة لتحلية المياه المالحة | إشراف | ذات اولوية عالية | 24418000 | 1220900 | 23667492.83 | 23667492.83 | 1010348048 | لا | 0 | 180709019508 | جاري | منهجية القيمة المكتسبة | 98.1 | 100 | 2017-10-12 | 2023-01-11 | 2023-01-11 | 2023-01-11 |  |  |  |  | 40.3775 | 21.3008 | خدمات عامة | No
2100066216 | شركة الكهرباء | تشييد | ذات اولوية متوسطة | 133079008 | 6653950.4 | 99463683 | 99463683 | 4030074229 | لا | 0 |  | جاري | اخرى | 91 | 100 | 2015-10-15 | 2018-01-15 | 2023-09-30 | 2023-09-30 |  |  | اخرى |  | 47.4224 | 24.1502 | متأخر | No
2100034005 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 2698000 | 134900 | 1370213 | 1370213 | 3450010117 | لا | 0 | 200609030596 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-11-04 | 2020-06-01 | 2023-02-27 | 2023-02-27 | 2020-06-01 |  | ضعف كفاءة المقاول الفنية |  | 41.0689 | 30.9798 | منجز | No
2100092886 | أمانة / الحدود الشمالية | تشييد | ذات اولوية متوسطة | 3998400 | 199920 | 1887746 | 1887746 | 3451001152 | لا | 0 | 190801003673 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 96 | 100 | 2015-10-19 | 2019-05-29 | 2020-06-04 | 2020-06-04 | 2019-05-29 |  | ضعف كفاءة المقاول الفنية |  | 38.6686 | 31.6666 | منجز | No
2100007486 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 11181457.11 | 559072.8555 | 5486478.71 | 5283912 | 1010196220 | لا | 0 | 190709061075 | مسحوب | التكلفة المفوترة | 65 | 100 | 2013-01-05 | 2014-12-26 | 2022-08-24 | 2022-08-24 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0859 | 19.1571 | مسحوب | No
2100055322 | شركة الكهرباء | تشييد | ذات اولوية متوسطة | 202101000 | 10105050 | 180363554 | 180363554 | 1010090181 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 99.6 | 100 | 2018-04-10 | 2020-08-11 | 2023-02-28 | 2023-02-28 |  |  |  |  | 39.2442 | 21.4737 | Failed | No
2100078960 | شركة المياه الوطنية / منطقة مكة المكرمة | إشراف | ذات اولوية عالية | 5369760 | 268488 | 3201764.33 | 3201764.33 | 1010325732 | لا | 0 |  | جاري | التكلفة المفوترة | 99.36 | 100 | 2018-10-16 | 2020-09-25 | 2022-05-08 | 2022-05-08 |  |  | لا يوجد تأخير |  | 39.2017 | 21.7679 | خدمات عامة | No
2100046141 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 2111000 | 105550 | 1899973.27 | 1899973.27 | 1011010795 | لا | 0 | 190301052047 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-10-24 | 2020-04-16 | 2020-04-16 | 2020-04-16 | 2020-04-16 |  | تأخرصرف المستحقات المالية |  | 43.73 | 28.756 | منجز | No
2100066802 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 12678208 | 633910.4 | 9300204.85 | 9300204.85 | 3450006578 | لا | 0 | 190509082373 | جاري | تكلفة العمل المنجز | 77 | 80 | 2019-10-08 | 2022-03-31 | 2023-05-28 | 2023-05-28 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0192 | 30.9749 | منتظم | No
2100094872 | شركة الكهرباء | تشييد | ذات اولوية متوسطة | 412373285 | 20618664.25 | 403318401 | 403318401 | 1010011560 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-12-06 | 2019-08-31 | 2021-12-31 | 2021-12-31 | 2019-08-31 |  | لا يوجد تأخير |  | 49.9863 | 26.3898 | منجز | No
2100009240 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 8021924.47 | 401096.2235 | 8021924.47 | 8021924.47 | 1010030949 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2013-09-06 | 2015-08-27 | 2018-12-27 | 2018-12-27 | 2015-08-27 |  |  |  | 41.0859 | 19.1571 | منجز | No
2100032395 | المؤسسة العامة للحبوب | تشييد | ذات اولوية عالية | 1960176.89 | 98008.8445 | 1960176.89 | 1960176.89 | 1010895413 | نعم | 761173 | 191101063884 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-04-10 | 2020-03-29 | 2020-03-29 | 2020-03-29 | 2020-03-29 |  | لا يوجد تأخير |  | 40.1531 | 29.9945 | منجز | No
2100023726 | الهيئة العامة للموانئ | توريد وتركيب | ذات اولوية عالية وعاجلة | 9884088 | 494204.4 | 9884088 | 9884088 | 4030190266 | لا | 0 | 181101277294 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-01-16 | 2020-01-15 | 2021-06-16 | 2021-06-16 | 2020-01-15 |  | لا يوجد تأخير |  | 38.2045 | 23.9747 | منجز | No
2100095966 | المؤسسة العامة لتحلية المياه المالحة | تشييد | ذات اولوية عالية | 544570540 | 27228527 | 411827987.65 | 411827987.65 | 1010004739 | لا | 0 | 190901000325 | جاري | منهجية القيمة المكتسبة | 90.4 | 90.4 | 2020-01-13 | 2021-10-01 | 2023-04-25 | 2023-04-25 |  |  | ضعف كفاءة المقاول الفنية |  | 40.2664 | 20.1309 | منتظم | No
2100019552 | أمانة / حفر الباطن | تشييد | ذات اولوية متوسطة | 1794850 | 89742.5 | 1794850 | 1794850 | 1010203649 | لا | 0 | 180901094147 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-12-12 | 2019-11-03 | 2019-11-03 | 2019-11-03 | 2019-11-03 |  |  |  | 46.716 | 28.107 | منجز | No
2100032071 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 9519440.15 | 475972.0075 | 3568654.14 | 3568654.14 | 1010072637 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 73 | 100 | 2014-02-23 | 2017-11-29 | 2023-02-03 | 2023-02-03 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0859 | 19.1571 | مسحوب | No
2100021442 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 19961165.16 | 998058.258 | 4573412.72 | 3614178.9 | 1010072637 | لا | 0 |  | مسحوب | التكلفة المفوترة | 28 | 100 | 2015-10-29 | 2017-10-18 | 2023-02-03 | 2023-02-03 |  |  | ضعف كفاءة المقاول الفنية |  | 40.2691 | 20.1489 | مسحوب | No
2100058483 | وزارة التعليم | تشييد | ذات اولوية عالية | 6810150.21 | 340507.5105 | 5170000 | 0 | 1018746600 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2013-07-02 | 2015-03-14 | 2021-12-10 | 2021-12-10 | 2015-03-14 |  | ضعف كفاءة المقاول الفنية |  | 42.6509 | 17.1567 | منجز | Yes
2100201714 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 1200900 | 60045 | 1200900 | 1200900 | 2050003475 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 97.71 | 2021-06-01 | 2021-12-02 | 2021-11-14 | 2021-11-14 | 2021-12-02 |  |  |  | 39.1306 | 21.7899 | منجز | No
2100059765 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية وعاجلة | 41991125 | 2099556.25 | 23179645.85 | 20997394.86 | 5850022870 | لا | 0 | 180801048639 | جاري | الكميات التي تم تركيبها | 63.5 | 87.96 | 2018-11-27 | 2021-11-28 | 2023-01-18 | 2023-01-18 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 49.565 | 25.3332 | متأخر | No
2100048635 | وزارة التعليم | تشييد | لم تعد تحتاجها الجهة | 1992745 | 99637.25 | 679223 | 647148 | 1010069591 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 45 | 100 | 2009-10-17 | 2010-10-12 | 2023-05-24 | 2023-05-24 |  |  | ضعف كفاءة المقاول الفنية |  | 43.1379 | 18.0853 | مسحوب | No
2100066360 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 2553500 | 127675 | 1028219 | 1028219 | 3350020147 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 90 | 100 | 2018-09-04 | 2020-09-13 | 2022-07-01 | 2022-07-01 | 2020-09-13 |  | ضعف كفاءة المقاول الفنية |  | 38.6606 | 31.6571 | منجز | No
2100107041 | جامعة الجوف | تشييد | ذات اولوية عالية | 71803380.11 | 3590169.0055 | 36885296.11 | 32116675.26 | 1010005046 | لا | 0 | 181009121431 | جاري | تكلفة العمل المنجز | 70 | 94 | 2017-05-29 | 2021-01-14 | 2023-10-10 | 2023-10-10 |  |  | تأخرصرف المستحقات المالية |  | 40.0558 | 29.7961 | متأخر | No
2100059124 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 14532328 | 726616.4 | 11625862 | 11625862 | 4030065868 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 89 | 100 | 2009-06-11 | 2011-05-20 | 2023-02-10 | 2023-02-10 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.1677 | 21.5008 | مسحوب | No
2100023133 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 12438734.72 | 621936.736 | 1.01 | 0.01 | 1010178798 | لا | 0 |  | مسحوب | التكلفة المفوترة | 40 | 100 | 2015-10-16 | 2016-12-06 | 2024-02-01 | 2024-02-01 |  |  | ضعف كفاءة المقاول الفنية |  | 44.2341 | 17.5757 | مسحوب | No
2100020845 | وزارة الشـؤون الاسلامية والدعوة والارشاد | تشييد | ذات اولوية عالية | 487525.5 | 24376.275 | 464132.05 | 73005.39 | 5950008566 | لا | 0 | 180909070565 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-03-25 | 2019-06-25 | 2019-11-25 | 2019-11-25 | 2019-06-25 |  | تأخرصرف المستحقات المالية |  | 44.2479 | 17.5226 | منجز | No
2100023741 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية عالية | 76411459 | 3820572.95 | 68390804 | 68390804 | 5855000147 | لا | 0 | 181109352035 | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2012-09-17 | 2016-09-22 | 2017-12-31 | 2017-12-31 | 2016-09-22 | 2020-11-24 |  |  | 41.4126 | 18.5878 | منجز | No
2100076204 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 432300 | 21615 | 408896.99 | 408896.99 | 1011011290 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 95 | 100 | 2020-03-09 | 2020-12-21 | 2022-07-01 | 2022-07-01 | 2020-12-21 |  |  |  | 43.5461 | 29.6191 | منجز | No
2200220463 | وزارة التعليم | توريد وتركيب | ذات اولوية عالية | 2093000 | 104650 | 0 | 0 | 5950016618 | لا | 0 |  | لم يبدأ | الكميات التي تم تركيبها | 0 | 0 |  |  |  | 2023-02-01 |  |  |  |  | 42.2699 | 18.246 | منتظم | No
2100088410 | جامعة الملك خالد | تشييد | ذات اولوية عالية وعاجلة | 28544863.6 | 1427243.18 | 28544863.6 | 28544863.6 | 2051037631 | لا | 0 | 180809039017 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2017-04-12 | 2019-03-12 | 2021-09-23 | 2021-09-23 | 2019-03-12 |  | تأخرصرف المستحقات المالية |  | 42.8114 | 18.1027 | منجز | No
2100087872 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 11525622.64 | 576281.132 | 5509846.26 | 5509846.26 | 1010072637 | لا | 0 | 190209015523 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2016-01-19 | 2018-01-08 | 2021-08-11 | 2021-08-11 | 2018-01-08 |  | ضعف كفاءة المقاول الفنية |  | 42.0529 | 18.5228 | منجز | No
2100074524 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2521863.9 | 126093.195 | 1454445 | 1454445 | 4030181069 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 65 | 100 | 2010-10-01 | 2011-12-25 | 2023-03-09 | 2023-03-09 |  |  | ضعف كفاءة المقاول الفنية |  | 43.5194 | 17.9562 | مسحوب | No
2100103073 | شركة المياه الوطنية / منطقة مكة المكرمة | إشراف | ذات اولوية عالية | 4942080 | 247104 | 2527048.81 | 2527048.81 | 4030233884 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2018-06-07 | 2020-06-06 | 2020-06-06 | 2020-06-06 | 2020-06-06 |  | لا يوجد تأخير |  | 39.206 | 21.7325 | منجز | No
2100038732 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية متوسطة | 243049823.5 | 12152491.175 | 119536542.46 | 119536542.46 | 1116000094 | لا | 0 | 180709030781 | مسحوب | منهجية القيمة المكتسبة | 71.64 | 100 | 2011-03-08 | 2013-02-13 | 2022-12-31 | 2022-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 36.2361 | 28.8603 | مسحوب | No
2100025115 | صندوق تنمية الموارد البشرية | تشييد | ذات اولوية منخفضة | 31264209.14 | 1563210.457 | 23431914.22 | 23431914.22 | 1010094008 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 89.62 | 100 | 2015-02-12 | 2018-01-26 | 2022-12-31 | 2022-12-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 46.7222 | 22.2969 | مسحوب | No
2100107310 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 4460496.4 | 223024.82 | 4410542.06 | 4410542.06 | 1010010506 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-04-11 | 2019-10-08 | 2019-11-28 | 2019-11-28 | 2019-10-08 | [5 empty] | منجز | No
2100097930 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 5131134.41 | 256556.7205 | 4706649.7 | 3556361.68 | 5855014881 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-12-15 | 2017-06-07 | 2021-08-03 | 2021-08-03 | 2017-06-07 |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | منجز | No
2100092632 | وزارة الشـؤون الاسلامية والدعوة والارشاد | تشييد | ذات اولوية عالية | 8557172.95 | 427858.6475 | 0 | 0 | 1122001087 | لا | 0 | 180909103779 | جاري | الكميات التي تم تركيبها | 100 | 100 | 2017-07-13 | 2019-06-22 | 2022-01-05 | 2022-01-05 |  |  | تأخرصرف المستحقات المالية |  | 44.8249 | 26.2993 | Failed | No
2100190352 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية عالية | 984359.75 | 49217.9875 | 974387.68 | 974387.68 | 4031052907 | لا | 0 | 210201009611 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2021-04-13 | 2022-01-12 | 2021-12-05 | 2021-12-05 | 2022-01-12 |  |  |  | 39.8487 | 21.3769 | منجز | No
2100191461 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 27437236.38 | 1371861.819 | 24670373.31 | 24670373.31 | 2050007224 | لا | 0 | 200709052696 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2020-11-05 | 2022-02-04 | 2022-01-31 | 2022-01-31 | 2022-02-04 |  |  |  | 39.1693 | 21.6205 | منجز | No
2100055635 | وزارة الصحة / المدينة المنورة | تشييد | ذات اولوية عالية | 7879900 | 393995 | 7879900 | 5460050 | 4650007032 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-02-08 | 2015-11-30 | 2022-02-28 | 2022-02-28 | 2015-11-30 |  | تأخرصرف المستحقات المالية |  | 39.5614 | 24.4948 | منجز | No
2100011620 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2999890.19 | 149994.5095 | 0 | 0 | 1010051817 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0 | 100 | 2015-03-12 | 2019-03-27 | 2023-02-03 | 2023-02-03 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.5429 | 16.8808 | مسحوب | No
2100070210 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 25294234.06 | 1264711.703 | 22765320 | 22765320 | 5850016803 | لا | 0 | 180501005719 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-07-26 | 2020-12-27 | 2021-12-13 | 2021-12-13 | 2020-12-27 |  | اخرى |  | 42.5117 | 18.2465 | منجز | No
2100014836 | صندوق تنمية الموارد البشرية | تشييد | ذات اولوية منخفضة | 24609432.05 | 1230471.6025 | 14954448.6 | 14954448.6 | 1131022493 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 76 | 100 | 2015-05-24 | 2017-04-13 | 2021-09-01 | 2021-09-01 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 46.6716 | 24.7041 | مسحوب | No
2100012025 | وزارة التعليم | تشييد | ذات اولوية عالية | 2800000 | 140000 | 411896 | 411896 | 1010965788 | لا | 0 |  | مسحوب | التكلفة المفوترة | 90 | 100 | 2014-04-14 | 2015-06-08 | 2022-09-20 | 2022-09-20 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0859 | 19.1571 | مسحوب | No
2100001271 | وزارة الشـؤون الاسلامية والدعوة والارشاد | تشييد | ذات اولوية عالية | 4996710 | 249835.5 | 1552538 | 441897 | 3400011183 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 51 | 100 | 2015-06-01 | 2017-05-09 | 2017-04-10 | 2017-04-10 |  |  | تأخرصرف المستحقات المالية |  | 37.3638 | 31.3253 | Failed | No
2100012106 | وزارة التعليم | تشييد | ذات اولوية عالية | 27490646.77 | 1374532.3385 | 21809327.15 | 21809327.15 | 1010196220 | لا | 0 | 190209015498 | جاري | التكلفة المفوترة | 100 | 100 | 2013-10-30 | 2022-08-28 | 2022-05-11 | 2022-05-11 |  |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | متأخر | No
2100060502 | المؤسسة العامة للحبوب | تشييد | ذات اولوية عالية | 8032536 | 401626.8 | 7601336 | 7601336 | 2511006797 | لا | 0 | 190301007256 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-12-25 | 2020-06-08 | 2021-12-01 | 2021-12-01 | 2020-06-08 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.6885 | 21.6314 | منجز | No
2100003360 | وزارة التعليم | تشييد | ذات اولوية عالية | 2330414.74 | 116520.737 | 1058256 | 1058256 | 4030140863 | لا | 0 | 190409040475 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-07-29 | 2016-07-23 | 2022-02-23 | 2022-02-23 | 2016-07-23 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.1677 | 21.5008 | منجز | No
2100011642 | وزارة التعليم | تشييد | ذات اولوية عالية | 14989111.03 | 749455.5515 | 9343032.46 | 9343032.46 | 1010196220 | لا | 0 |  | مسحوب | التكلفة المفوترة | 66 | 100 | 2013-11-07 | 2015-10-28 | 2022-08-10 | 2022-08-10 |  |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | مسحوب | No
2100003883 | جامعة الأمير سطام بن عبدالعزيز | تشييد | ذات اولوية عالية | 951308.4 | 47565.42 | 536203.2 | 536203.2 | 1012001120 | لا | 0 | 191101101973 | ايقاف كلي | تكلفة العمل المنجز | 80 | 100 | 2019-11-17 | 2020-11-11 | 2023-01-03 | 2023-01-03 |  |  | اخرى |  | 47.2733 | 24.1626 | Failed | No
2100010124 | أمانة / نجران | تشييد | ذات اولوية عالية | 68348103 | 3417405.15 | 53454936.15 | 28138107.39 | 5950002027 | لا | 0 | 180709017298 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 91.26 | 96 | 2015-07-22 | 2021-07-25 | 2022-09-11 | 2022-09-11 | 2021-07-25 |  | ضعف كفاءة المقاول الفنية |  | 44.2289 | 17.5649 | منجز | No
2100192824 | جامعة القصيم | توريد وتركيب | ذات اولوية عالية وعاجلة | 1398562 | 69928.1 | 1398562 | 1398562 | 1010187766 | لا | 0 | 200509076789 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-09-14 | 2021-09-13 | 2021-05-27 | 2021-05-27 | 2021-09-13 |  |  |  | 43.7493 | 26.3489 | منجز | No
2100098921 | جامعة القصيم | تشييد | ذات اولوية عالية وعاجلة | 313318000 | 15665900 | 287546079.9 | 287546079.9 | 1010009593 | لا | 0 | 200409028419 | جاري | تكلفة العمل المنجز | 98 | 98 | 2020-02-16 | 2023-01-31 | 2023-01-31 | 2023-01-31 |  |  | تأخرصرف المستحقات المالية |  | 43.9553 | 26.3508 | منتظم | No
2100194471 | أمانة / جدة | تشييد | ذات اولوية عالية وعاجلة | 239497230 | 11974861.5 | 202359886.69 | 202359886.69 | 4030007856 | لا | 0 | 200201143627 | جاري | تكلفة العمل المنجز | 99.5 | 100 | 2020-06-15 | 2021-11-28 | 2022-12-20 | 2022-12-20 |  |  |  |  | 39.2349 | 21.5969 | منتظم | No
2100027145 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1912675.12 | 95633.756 | 1912675.12 | 1912675.12 | 4031079157 | لا | 0 | 181009124356 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-11-29 | 2016-09-24 | 2016-09-24 | 2016-09-24 | 2016-09-24 |  |  |  | 40.426 | 21.248 | منجز | No
2100013112 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2969201.7 | 148460.085 | 2969200.22 | 2969200.22 | 5800002551 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2017-10-12 | 2018-08-28 | 2019-01-11 | 2019-01-11 | 2018-08-28 |  |  |  | 41.3679 | 19.7623 | منجز | No
2100086306 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 3079218 | 153960.9 | 2553680.48 | 2553680.48 | 2066002992 | لا | 0 | 181101271322 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-07-03 | 2019-01-03 | 2020-09-07 | 2020-09-07 | 2019-01-03 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 49.7608 | 26.8763 | منجز | No
2100190831 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 69300000.1 | 3465000.005 | 3794878.5 | 3794878.5 | 1010122914 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 16.83 | 70.1 | 2021-03-29 | 2023-03-29 | 2023-03-29 | 2023-03-29 |  |  |  |  | 40.4723 | 21.4209 | Failed | No
2100077792 | أمانة / جازان | تشييد | ذات اولوية عالية | 2949000 | 147450 | 1581345.39 | 1581345.39 | 5900013452 | لا | 0 | 190201045370 | منجز – استلام ابتدائي | اخرى | 83 | 100 | 2018-11-25 | 2019-11-21 | 2021-08-05 | 2021-08-05 | 2019-11-21 |  | ضعف كفاءة المقاول الفنية |  | 42.8287 | 17.6161 | منجز | No
2100022923 | جامعة الأمير سطام بن عبدالعزيز | تشييد | ذات اولوية عالية | 136130603 | 6806530.15 | 7137481 | 7137481 | 2050022550 | لا | 0 |  | مسحوب | مدفوعات ساعات العمل | 5 | 100 | 2013-09-12 | 2016-08-27 | 2024-01-01 | 2024-01-01 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 45.5586 | 20.4465 | مسحوب | No
2200220500 | أمانة / الأحساء | دعم فني | ذات اولوية عالية | 368000 | 18400 | 240000 | 240000 | 1010570397 | لا | 0 |  | جاري | تكلفة العمل المنجز | 67 | 75 | 2021-12-13 | 2022-03-13 | 2022-03-15 | 2022-03-15 |  |  |  |  | 49.5604 | 25.3897 | خدمات عامة | No
2100001212 | المؤسسة العامة لتحلية المياه المالحة | تشييد | ذات اولوية عالية | 270000000 | 13500000 | 242949672.33 | 242949672.33 | 4030271192 | لا | 0 | 181109295333 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-05-08 | 2020-11-03 | 2020-11-03 | 2020-11-03 | 2020-11-03 |  | تأخرصرف المستحقات المالية |  | 50.2113 | 26.1826 | منجز | No
2200220533 | شركة المياه الوطنية / منطقة الرياض | تصميم | ذات اولوية عالية | 7750000 | 387500 | 1212067.61 | 1212067.61 | 2050101543 | لا | 0 |  | جاري | اخرى | 12.73 | 12.73 | 2022-01-17 | 2023-07-15 | 2023-07-15 | 2023-07-15 |  |  |  |  | 46.7942 | 24.6523 | منتظم | No
2100064875 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2262700 | 113135 | 41427 | 0 | 1113000219 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 0 | 100 | 2013-11-23 | 2015-05-17 | 2021-02-07 | 2021-02-07 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 45.2573 | 25.2571 | Failed | Yes
2100048985 | أمانة / نجران | تشييد | ذات اولوية عالية | 35825312.4 | 1791265.62 | 28660307.67 | 16559883.13 | 5950009827 | لا | 0 | 181009119454 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 99.83 | 100 | 2015-01-11 | 2021-06-29 | 2022-05-14 | 2022-05-14 | 2021-06-29 |  | ضعف كفاءة المقاول الفنية |  | 44.2228 | 17.5499 | منجز | No
2100193130 | جامعة القصيم | توريد وتركيب | ذات اولوية عالية وعاجلة | 2777968.75 | 138898.4375 | 2777968.75 | 2777968.75 | 4030193136 | لا | 0 | 210801105834 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2021-04-05 | 2022-04-05 | 2022-04-05 | 2022-04-05 | 2022-04-05 |  |  |  | 43.7668 | 26.3489 | منجز | No
2100091405 | وزارة التعليم | تشييد | ذات اولوية عالية | 10837247.86 | 541862.393 | 0 | 0 | 1010196220 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0 | 100 | 2013-09-02 | 2015-08-23 | 2023-02-03 | 2023-02-03 |  |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | مسحوب | No
2100009052 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 1856460.82 | 92823.041 | 1509583 | 1509583 | 1134000478 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 60 | 100 | 2012-04-10 | 2013-03-28 | 2019-04-14 | 2019-04-14 |  |  | ضعف كفاءة المقاول الفنية |  | 43.2646 | 26.4403 | مسحوب | No
2100024393 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 5119993.9 | 255999.695 | 4971430.17 | 4971430.17 | 1010010506 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-04-17 | 2019-10-14 | 2019-12-03 | 2019-12-03 | 2019-10-14 | [5 empty] | منجز | No
2100082025 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 4551469 | 227573.45 | 4791020 | 4300222.42 | 4030151374 | لا | 0 | 190909113186 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 99 | 99 | 2019-01-20 | 2020-12-28 | 2021-02-01 | 2021-02-01 | 2020-12-28 |  | اخرى |  | 41.0787 | 19.1281 | منجز | No
2100022665 | أمانة / الجوف | ترميم | ذات اولوية عالية | 5126682 | 256334.1 | 3274547 | 3274547 | 7003041394 | لا | 0 | 190901040531 | جاري | اخرى | 99 | 99 | 2019-12-08 | 2022-12-07 | 2023-01-31 | 2023-01-31 |  |  | اخرى |  | 40.1043 | 29.878 | منتظم | No
2100007630 | وزارة الصحة / المدينة المنورة | تشييد | ذات اولوية منخفضة | 4779730 | 238986.5 | 1855470 | 1350640 | 1132002394 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 50 | 100 | 2015-04-14 | 2016-04-02 | 2022-06-30 | 2022-06-30 |  |  | تأخرصرف المستحقات المالية |  | 39.9056 | 22.9984 | Failed | No
2100088631 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 50419700 | 2520985 | 40447257.89 | 40447257.89 | 5855000147 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-03-06 | 2020-03-05 | 2020-08-02 | 2020-08-02 | 2020-03-05 |  | أوامر تغيير | أخرى |  |  | منجز | No
2100052555 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 4984090 | 249204.5 | 4984090 | 4410918.5 | 5907024458 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-10-10 | 2020-09-29 | 2022-11-05 | 2022-11-05 | 2020-09-29 |  |  |  | 41.471 | 20.005 | منجز | No
2100089213 | وزارة الداخلية / ديوان وزارة الداخلية | تصميم وتشييد | ذات اولوية عالية وعاجلة | 2648130879 | 132406543.95 | 2565201716 | 2565201716 | 1010199246 | لا | 0 | 180909085140 | جاري | التكلفة المفوترة | 99.48 | 100 | 2014-03-09 | 2017-02-19 | 2023-05-16 | 2023-05-16 |  |  | تأخرصرف المستحقات المالية |  | 46.7098 | 24.6275 | منتظم | No
2100094533 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية منخفضة | 32360580 | 1618029 | 31433421.09 | 31433421.09 | 5855001146 | لا | 0 | 181109357995 | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2013-10-24 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2020-10-25 |  |  | 42.5276 | 18.461 | منجز | No
2100000195 | وزارة التعليم | تشييد | ذات اولوية عالية | 2774450.74 | 138722.537 | 2533435.64 | 2351765.89 | 3350026586 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-06-10 | 2015-09-03 | 2019-11-26 | 2019-11-26 | 2015-09-03 |  | ضعف كفاءة المقاول الفنية |  | 37.928 | 26.5737 | منجز | No
2100034414 | أمانة / جازان | تشييد | ذات اولوية عالية | 999750 | 49987.5 | 899735 | 899735 | 5907014307 | لا | 0 | 190309036360 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-12-10 | 2020-03-03 | 2020-03-03 | 2020-03-03 | 2020-03-03 |  | سوء التخطيط الاولي للمشروع |  | 42.7484 | 16.7701 | منجز | No
2100046620 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 65275980 | 3263799 | 65275980 | 65275980 | 2050018628 | لا | 0 | 190401064215 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-09-29 | 2022-11-15 | 2022-09-17 | 2022-09-17 | 2022-11-15 |  |  |  | 49.5936 | 27.0031 | منجز | No
2100035792 | أمانة / جازان | تشييد | ذات اولوية عالية وعاجلة | 848400 | 42420 | 759956 | 759956 | 5950007619 | لا | 0 | 200101024650 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-11-12 | 2020-05-10 | 2020-10-23 | 2020-10-23 | 2020-05-10 |  | ضعف كفاءة المقاول الفنية |  | 42.9378 | 16.6005 | منجز | No
2100066135 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 3000000 | 150000 | 572574 | 572574 | 4601000386 | لا | 0 | 200609061151 | مسحوب | تكلفة العمل المنجز | 24 | 24 | 2015-05-16 | 2020-02-04 | 2020-02-04 | 2020-02-04 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 40.7334 | 19.919 | مسحوب | No
2100043396 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 109483183 | 5474159.15 | 98528312.8 | 97951402.6 | 1010257051 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 98.82 | 100 | 2016-01-21 | 2018-01-21 | 2020-12-21 | 2020-12-21 | 2018-01-21 |  | لا يوجد تأخير |  | 47.6084 | 25.0403 | منجز | No
2100100940 | أمانة / نجران | تشييد | ذات اولوية عالية | 52379360 | 2618968 | 40783895.33 | 40783895.33 | 1010056094 | لا | 0 |  | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 99 | 100 | 2013-09-03 | 2015-11-09 | 2022-11-11 | 2022-11-11 |  |  | ضعف كفاءة المقاول الفنية |  | 44.1694 | 17.5579 | Failed | No
2100057396 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 3258654.45 | 162932.7225 | 1645669.85 | 1645669.85 | 1010237336 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 47 | 100 | 2013-05-24 | 2014-10-02 | 2023-02-01 | 2023-02-01 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 41.4779 | 20.0185 | مسحوب | No
2100191704 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 2650000 | 132500 | 2073500 | 834000 | 1010328073 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2021-04-14 | 2021-08-12 | 2021-10-17 | 2021-10-17 | 2021-08-12 |  |  |  | 47.5427 | 25.0997 | منجز | No
2100037704 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية منخفضة | 14823000 | 741150 | 8988417.28 | 8988417.28 | 5855029980 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2014-08-28 | 2016-10-02 | 2020-08-19 | 2020-08-19 | 2016-10-02 | 2022-08-31 |  |  | 42.5203 | 18.2431 | منجز | No
2100104392 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 39721005.75 | 1986050.2875 | 5215175 | 0 | 1010046644 | لا | 0 |  | مسحوب | التكلفة المفوترة | 16 | 100 | 2016-01-07 | 2018-12-17 | 2018-12-17 | 2018-12-17 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5604 | 25.3897 | مسحوب | Yes
2100051273 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 1253936 | 62696.8 | 1313647.22 | 1313647.22 | 4601002260 | لا | 0 | 181209506558 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-09-08 | 2020-08-17 | 2020-08-17 | 2020-08-17 | 2020-08-17 |  | ضعف كفاءة المقاول الفنية |  | 40.8602 | 20.4053 | منجز | No
2100011771 | وزارة الحرس الوطني / الشؤون الفنية بالقطاع الشرقي | ترميم | ذات اولوية عالية | 19691747.6 | 984587.38 | 17679601.8 | 16140683.3 | 1010188480 | لا | 0 | 180401004042 | جاري | تكلفة العمل المنجز | 98 | 100 | 2018-08-29 | 2021-12-31 | 2023-03-01 | 2023-03-01 |  |  | تأخرصرف المستحقات المالية |  | 49.5361 | 25.452 | Failed | No
2100104764 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 139925459 | 6996272.95 | 113446104.3 | 105282478.15 | 1010004249 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 92.63 | 100 | 2013-02-16 | 2016-08-16 | 2020-07-30 | 2020-07-30 |  | 2016-08-16 | لا يوجد تأخير |  | 46.6556 | 24.8194 | منجز | No
2100068773 | أمانة / جدة | تشييد | ذات اولوية عالية | 1771200 | 88560 | 1856748.35 | 1856748.35 | 4601002260 | لا | 0 | 181109353126 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-09-02 | 2020-02-16 | 2020-05-02 | 2020-05-02 | 2020-02-16 |  | اخرى |  | 39.1953 | 21.5339 | منجز | No
2100071934 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 1083009 | 54150.45 | 1083009.2 | 1083009.2 | 4030188853 | لا | 0 | 191101248955 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 95 | 100 | 2019-09-29 | 2020-09-18 | 2021-03-30 | 2021-03-30 | 2020-09-18 |  | ضعف كفاءة المقاول الفنية |  | 40.4605 | 20.305 | منجز | No
2100013204 | أمانة / عسير | تشييد | ذات اولوية عالية | 4888710 | 244435.5 | 1133900 | 1133900 | 5862004065 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 33 | 100 | 2014-12-10 | 2016-06-02 | 2023-01-01 | 2023-01-01 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | مسحوب | No
2100087813 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | تشييد | ذات اولوية متوسطة | 9453013 | 472650.65 | 9453013 | 8248217 | 1011873110 | لا | 0 | 181001178161 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-04-01 | 2020-09-13 | 2020-12-30 | 2020-12-30 | 2020-09-13 |  | تأخرصرف المستحقات المالية |  | 49.6626 | 27.0037 | منجز | No
2100059393 | جامعة الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 127413977 | 6370698.85 | 115194777 | 115194777 | 2050018887 | لا | 0 | 181109242651 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 97 | 100 | 2017-11-28 | 2021-05-28 | 2022-05-27 | 2022-05-27 |  |  | تأخرصرف المستحقات المالية |  | 43.5207 | 29.6323 | متأخر | No
2100190842 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية وعاجلة | 2025495.34 | 101274.767 | 688513.89 | 220618.71 | 1010147422 | لا | 0 | 201001077229 | جاري | منهجية القيمة المكتسبة | 79.64 | 100 | 2020-12-22 | 2021-12-12 | 2022-03-12 | 2022-03-12 |  |  |  |  | 41.563 | 20.1338 | Failed | No
2100006296 | وزارة التعليم | تشييد | ذات اولوية عالية | 4052965.85 | 202648.2925 | 1942684 | 1942684 | 4031053163 | لا | 0 |  | مسحوب | التكلفة المفوترة | 46 | 100 | 2013-11-14 | 2015-02-14 | 2023-05-15 | 2023-05-15 |  |  | ضعف كفاءة المقاول الفنية |  | 43.9544 | 26.3504 | مسحوب | No
2100076801 | أمانة / تبوك | تشييد | ذات اولوية عالية | 1005200 | 50260 | 1005200 | 282180 | 3554001218 | لا | 0 | 200101016926 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-03-15 | 2020-01-09 | 2021-09-05 | 2021-09-05 | 2020-01-09 |  | ضعف كفاءة المقاول الفنية |  | 38.5165 | 27.6122 | منجز | No
2100057702 | جامعة الملك عبدالعزيز | تشييد | لم تعد تحتاجها الجهة | 25161853.86 | 1258092.693 | 107789.39 | 107789.39 | 1010251358 | لا | 0 | 181101270735 | فسخ العقد | تكلفة العمل المنجز | 0 | 0 | 2018-11-18 | 2019-09-09 | 2021-12-31 | 2021-12-31 |  |  | أوامر سامية |  | 39.1677 | 21.5008 | مسحوب | No
2100192581 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 4916690.3 | 245834.515 | 2800339.05 | 2469736.51 | 1010212379 | لا | 0 | 181109279543 | جاري | تكلفة العمل المنجز | 61.6 | 100 | 2018-11-18 | 2019-02-19 | 2023-06-30 | 2023-06-30 |  |  |  |  | 38.9603 | 22.7892 | Failed | No
2100002542 | وزارة التعليم | تشييد | ذات اولوية عالية | 10526150.88 | 526307.544 | 4480604 | 4480604 | 1010051817 | لا | 0 |  | مسحوب | التكلفة المفوترة | 48 | 100 | 2014-05-08 | 2016-04-27 | 2021-06-18 | 2021-06-18 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 46.7098 | 24.6275 | مسحوب | No
2100100063 | جامعة الإمام محمد بن سعود الاسلامية | دراسة الجدوى | ذات اولوية متوسطة | 51981643 | 2599082.15 | 38496510 | 34764385.99 | 1010078921 | لا | 0 | 181009167875 | جاري | اخرى | 82 | 100 | 2014-09-16 | 2016-06-11 | 2023-12-31 | 2023-12-31 |  |  | تأخرصرف المستحقات المالية |  | 46.7021 | 24.8118 | خدمات عامة | No
2100109303 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 10056512.7 | 502825.635 | 3890371.48 | 3890371.48 | 2055002421 | لا | 0 |  | مسحوب | التكلفة المفوترة | 45 | 100 | 2015-01-12 | 2017-01-01 | 2018-03-27 | 2018-03-27 |  |  | ضعف كفاءة المقاول الفنية |  | 45.975 | 28.4334 | مسحوب | No
2200212855 | أمانة / الجوف | إشراف | ذات اولوية عالية وعاجلة | 10204857.24 | 510242.862 | 8506142.85 | 8506142.85 | 3400013323 | لا | 0 | 190801056545 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-10-22 | 2022-04-09 | 2022-04-24 | 2022-04-24 | 2022-04-09 |  |  |  | 40.1043 | 29.878 | منجز | No
2100053292 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 37737813 | 1886890.65 | 3341695 | 3341695 | 1010202447 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 15.25 | 100 | 2012-07-04 | 2016-05-20 | 2016-05-20 | 2016-05-20 |  |  | اخرى |  | 46.6826 | 24.7097 | مسحوب | No
2100083845 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 76799459 | 3839972.95 | 16269353 | 15692568 | 2051010618 | لا | 0 |  | ايقاف جزئي | الكميات التي تم تركيبها | 25.23 | 28.87 | 2018-06-09 | 2020-05-29 | 2023-03-22 | 2023-03-22 |  |  |  |  | 46.6235 | 24.7328 | منتظم | No
2100011804 | وزارة الحرس الوطني / وكالة الشؤون الفنية | تشييد | ذات اولوية متوسطة | 4494970.26 | 224748.513 | 2913442.41 | 2774697.65 | 1010495829 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 72 | 97 | 2020-02-17 | 2023-01-13 | 2023-04-12 | 2023-04-12 |  |  |  |  | 46.683 | 24.7113 | Failed | No
2200220780 | المؤسسة العامة للتأمينات الاجتماعية | ترميم | ذات اولوية متوسطة | 6016230 | 300811.5 | 1317950.55 | 1317950.55 | 2051040604 | لا | 0 |  | ايقاف كلي | منهجية القيمة المكتسبة | 45 | 100 | 2022-01-16 | 2022-07-15 | 2022-10-31 | 2022-10-31 |  |  |  |  | 50.218 | 26.3812 | Failed | No
2100004244 | شركة المياه الوطنية / منطقة حائل | إشراف | لم تعد تحتاجها الجهة | 4494000 | 224700 | 3577618.2 | 3577618.2 | 1131055230 | لا | 0 | 180901068960 | منجز – استلام ابتدائي | التكلفة المفوترة | 79.61 | 100 | 2018-05-16 | 2021-01-16 | 2021-01-16 | 2021-01-16 | 2021-01-16 |  | لا يوجد تأخير |  | 41.7188 | 27.4462 | منجز | No
2100096261 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 418454210 | 20922710.5 | 315794821.4 | 304115545.92 | 2050005846 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99.65 | 100 | 2015-10-01 | 2018-04-01 | 2021-03-18 | 2021-03-18 | 2018-04-01 |  | لا يوجد تأخير |  | 46.7309 | 24.5873 | منجز | No
2100088701 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 3075555.44 | 153777.772 | 1727980.85 | 1727980.85 | 1010164501 | لا | 0 |  | مسحوب | التكلفة المفوترة | 56 | 100 | 2015-02-24 | 2016-02-19 | 2021-04-02 | 2021-04-02 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.5973 | مسحوب | No
2100031905 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 11487939.35 | 574396.9675 | 8356974.12 | 8356974.12 | 4030221968 | لا | 0 | 180709016095 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2017-05-21 | 2018-03-12 | 2022-12-31 | 2022-12-31 |  |  | تأخرصرف المستحقات المالية |  | 39.1677 | 21.5008 | متأخر | No
2100095550 | الهيئة الملكية للجبيل وينبع / مدينة جازان للصناعات الأساسية والتحويلية | تشييد | ذات اولوية عالية | 17055051.51 | 852752.5755 | 16406623.85 | 15380373.05 | 5950004973 | لا | 0 | 200101028062 | جاري | الكميات التي تم تركيبها | 94.41 | 95.58 | 2020-03-15 | 2023-03-15 | 2023-04-18 | 2023-04-18 |  |  | عدم وجود كوادر كافية في الجهه لادارة المشروع |  | 42.335 | 17.3525 | منتظم | No
2100103493 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية | 630186174.22 | 31509308.711 | 119521.82 | 119521.82 | 1010609431 | لا | 0 |  | ايقاف كلي | منهجية القيمة المكتسبة | 0.02 | 0.02 | 2015-03-05 | 2019-02-11 | 2022-12-31 | 2022-12-31 |  |  | عدم وجود مبالغ في البنود تغطي الأعمال المرصودة |  | 39.6138 | 24.4632 | Failed | No
2100015551 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1985310 | 99265.5 | 333484.53 | 0 | 1186002013 | لا | 0 |  | مسحوب | التكلفة المفوترة | 1 | 100 | 2013-08-18 | 2014-07-16 | 2024-01-15 | 2024-01-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | Yes
2100016435 | وزارة التعليم | تشييد | ذات اولوية عالية | 13359455 | 667972.75 | 13046896 | 13046896 | 1010051817 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-11-27 | 2016-10-17 | 2019-08-23 | 2019-08-23 | 2016-10-17 |  |  |  | 46.7098 | 24.6275 | منجز | No
2100079553 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 4817017 | 240850.85 | 325018.75 | 0 | 4030025647 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 7 | 100 | 2008-10-28 | 2010-04-20 | 2024-01-15 | 2024-01-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | Yes
2100029540 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 9863835 | 493191.75 | 9863835 | 9863835 | 4032002354 | لا | 0 | 181109341125 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-10-07 | 2017-09-26 | 2019-09-25 | 2019-09-25 | 2017-09-26 |  |  |  | 41.7446 | 22.4285 | منجز | No
2100035184 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 29182969 | 1459148.45 | 29182969 | 29182969 | 2251032617 | لا | 0 | 190201040102 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-05-14 | 2021-05-03 | 2022-02-21 | 2022-02-21 | 2021-05-03 |  | ضعف كفاءة المقاول الفنية |  | 49.5871 | 25.3837 | منجز | No
2100037796 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 79991971.5 | 3999598.575 | 71994279.51 | 71994279.51 | 1116001737 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2011-05-31 | 2013-11-01 | 2020-02-09 | 2020-02-09 | 2013-11-01 | 2022-01-13 |  |  |  |  | منجز | No
2100035906 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 2408537 | 120426.85 | 2408537 | 2408537 | 5907014307 | لا | 0 | 1903090306340 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-12-10 | 2019-12-10 | 2020-02-20 | 2020-02-20 | 2019-12-10 |  | سوء التخطيط الاولي للمشروع |  | 42.7254 | 16.7715 | منجز | No
2100088826 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 8439812 | 421990.6 | 2911182.96 | 2911182.96 | 1010187466 | لا | 0 |  | جاري | التكلفة المفوترة | 84 | 100 | 2017-11-05 | 2019-10-26 | 2019-10-26 | 2019-10-26 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.5881 | Failed | No
2100002192 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 6548887.25 | 327444.3625 | 400884.22 | 0 | 4650020865 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 7 | 100 | 2012-09-16 | 2014-05-11 | 2024-01-15 | 2024-01-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | Yes
2100039756 | وزارة التعليم | تشييد | ذات اولوية عالية | 10572773.74 | 528638.687 | 9326975.14 | 9326975.14 | 1010081451 | لا | 0 |  | جاري | التكلفة المفوترة | 88 | 100 | 2014-11-05 | 2016-10-25 | 2020-03-13 | 2020-03-13 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6163 | 24.786 | Failed | No
2100080894 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2942030 | 147101.5 | 1154995 | 0 | 4031057760 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 99 | 100 | 2014-12-02 | 2016-05-25 | 2022-10-30 | 2022-10-30 |  |  | ضعف كفاءة المقاول الفنية |  | 45.4639 | 25.0699 | Failed | Yes
2100082725 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1714990 | 85749.5 | 997940 | 0 | 1116004922 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 92 | 100 | 2015-01-14 | 2017-01-25 | 2020-01-29 | 2020-01-29 | 2017-01-25 |  | ضعف كفاءة المقاول الفنية |  | 45.392 | 23.6208 | منجز | Yes
2100080511 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3945670 | 197283.5 | 41448 | 0 | 1010182773 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 78 | 100 | 2014-01-25 | 2015-04-20 | 2015-04-20 | 2015-04-20 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6706 | 24.6982 | مسحوب | Yes
2100081325 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 9998020 | 499901 | 41736 | 0 | 1010056094 | لا | 0 |  | جاري | تكلفة العمل المنجز | 38 | 100 | 2014-09-24 | 2016-09-13 | 2021-01-19 | 2021-01-19 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6682 | 24.7129 | Failed | Yes
2100060944 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 53875800 | 2693790 | 36082696.68 | 36082696.68 | 2051030949 | لا | 0 | 200709052696 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-05-29 | 2021-05-06 | 2021-10-05 | 2021-10-05 | 2021-05-06 |  | لا يوجد تأخير |  | 39.144 | 21.6182 | منجز | No
2100087194 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 39845782 | 1992289.1 | 34213376.2 | 34213376.2 | 2050001536 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-02-01 | 2020-01-10 | 2019-02-19 | 2019-02-19 | 2020-01-10 |  | لا يوجد تأخير |  | 39.3085 | 21.453 | منجز | No
2100042851 | هيئة المدن الصناعية ومناطق التقنية | تشييد | ذات اولوية عالية | 16213489 | 810674.45 | 9762179 | 9762179 | 1010302875 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 84 | 90 | 2019-11-17 | 2021-05-17 | 2023-01-31 | 2023-01-31 |  |  | اخرى |  | 26.2487 | 44.0174 | متأخر | No
2100019515 | وزارة التعليم | تشييد | ذات اولوية عالية | 7581013.65 | 379050.6825 | 3475623 | 3475623 | 1132002624 | لا | 0 |  | جاري | التكلفة المفوترة | 90 | 100 | 2016-04-24 | 2018-04-14 | 2022-10-18 | 2022-10-18 |  |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | Failed | No
2100060981 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 65280954 | 3264047.7 | 45773116.08 | 45773116.08 | 2050001536 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-02-01 | 2020-01-10 | 2020-08-09 | 2020-08-09 | 2020-01-10 |  | لا يوجد تأخير |  | 39.3103 | 21.4535 | منجز | No
2100191505 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 11388457.5 | 569422.875 | 10021357.5 | 10021357.5 | 2050007224 | نعم | 1 | 200709052696 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2021-02-15 | 2021-10-14 | 2021-09-30 | 2021-09-30 | 2021-10-14 |  |  |  | 39.2182 | 21.5324 | منجز | No
2100016623 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 38804301.92 | 1940215.096 | 9170902 | 8841463.37 | 4030157663 | لا | 0 | 181109279632 | جاري | تكلفة العمل المنجز | 30.54 | 30.45 | 2014-12-07 | 2016-05-16 | 2024-12-31 | 2024-12-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.1677 | 21.5008 | منتظم | No
2100064536 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 9457377.5 | 472868.875 | 9457376.89 | 9457376.89 | 1010135922 | لا | 0 | 200209113917 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-11-24 | 2019-06-04 | 2022-06-30 | 2022-06-30 |  |  | تأخرصرف المستحقات المالية |  | 39.1677 | 21.5008 | متأخر | No
2100085046 | المؤسسة العامة للتأمينات الاجتماعية | تشييد | ذات اولوية متوسطة | 398289418.07 | 19914470.9035 | 308113916.7405 | 308113916.7405 | 1010085518 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2017-01-15 | 2018-12-16 | 2022-03-31 | 2022-03-31 | 2018-12-16 |  | أوامر تغيير |  | 46.6753 | 24.7136 | منجز | No
2100091070 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 46449829 | 2322491.45 | 33445117.24 | 33445117.24 | 1010183025 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-04-13 | 2018-03-04 | 2019-10-29 | 2019-10-29 |  | 2018-03-04 | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100192964 | مدينة الملك فهد الطبية | توريد وتركيب | ذات اولوية عالية | 4948619 | 247430.95 | 1925238 | 792358 | 1010122816 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 80 | 80 | 2020-06-15 | 2023-06-15 | 2023-06-15 | 2023-06-15 |  |  |  |  | 46.7038 | 24.6873 | منتظم | No
2100078702 | جامعة الإمام محمد بن سعود الاسلامية | دراسة الجدوى | ذات اولوية عالية وعاجلة | 5544000 | 277200 | 4646990.9218 | 4646990.9218 | 1010078921 | لا | 0 | 180909094625 | جاري | اخرى | 88 | 100 | 2012-04-28 | 2014-06-04 | 2023-12-31 | 2023-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7004 | 24.8104 | خدمات عامة | No
2100016096 | هيئة المدن الصناعية ومناطق التقنية | تشييد | ذات اولوية عالية | 15108913 | 755445.65 | 6274824 | 5940458 | 1010206690 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 46 | 50 | 2019-12-04 | 2021-06-03 | 2023-05-02 | 2023-05-02 |  |  | لا يوجد تأخير |  | 17.0892 | 42.8966 | منتظم | No
2100178485 | وزارة الثقافة | إشراف | ذات اولوية عالية | 4899058.68 | 244952.934 | 4612374.22 | 3566681.3 | 1010435790 | لا | 0 | 201009164269 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-07-25 | 2020-11-30 | 2020-11-30 | 2020-11-30 |  | 2020-11-30 |  |  | 39.5672 | 24.4757 | منجز | No
2100042162 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 9310086.22 | 465504.311 | 8103141.61 | 8103141.61 | 1116002088 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-05-28 | 2018-05-17 | 2019-07-10 | 2019-07-10 |  | 2018-05-17 | لا يوجد تأخير |  | 48.5359 | 27.448 | منجز | No
2100178441 | وزارة الثقافة | تشييد | ذات اولوية عالية | 15235940.07 | 761797.0035 | 15312211.81 | 13624580.2 | 1010009971 | لا | 0 | 201109074238 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-11-26 | 2020-05-25 | 2020-08-25 | 2020-08-25 | 2020-05-25 |  |  |  | 46.5775 | 24.5746 | منجز | No
2100005806 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 75174000 | 3758700 | 67616344.6 | 67616344.6 | 1010026934 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 97.08 | 100 | 2015-05-31 | 2017-05-31 | 2020-04-30 | 2020-04-30 |  | 2017-05-31 | لا يوجد تأخير |  | 39.7936 | 21.3814 | منجز | No
2100055554 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 53976900 | 2698845 | 53502997.74 | 53502997.74 | 1010016228 | لا | 0 | 181009173954 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2015-06-07 | 2018-05-06 | 2019-12-26 | 2019-12-26 | 2018-05-06 |  | لا يوجد تأخير |  | 45.313 | 24.0763 | منجز | No
2100045883 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3708000 | 185400 | 42522 | 0 | 1131023927 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2016-12-26 | 2019-12-26 | 2021-06-27 | 2021-06-27 | 2019-12-26 |  |  |  | 47.2997 | 24.1789 | منجز | Yes
2100097672 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 24854197.35 | 1242709.8675 | 21051793.43 | 20990786.43 | 1010185409 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-12-25 | 2019-09-21 | 2020-01-19 | 2020-01-19 | 2019-09-21 | [5 empty] | منجز | No
2100042696 | هيئة المدن الصناعية ومناطق التقنية | تشييد | ذات اولوية عالية | 9691481 | 484574.05 | 5192237 | 5192237 | 1010055791 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 84 | 100 | 2019-11-11 | 2021-05-04 | 2023-01-31 | 2023-01-31 |  |  | اخرى |  | 29.7777 | 39.9826 | Failed | No
2100056965 | شركة المياه الوطنية / منطقة القصيم | إشراف | ذات اولوية عالية وعاجلة | 24858000 | 1242900 | 24594386.5 | 20788908 | 1010348048 | لا | 0 | 180901071004 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2019-01-13 | 2022-02-27 | 2021-02-28 | 2021-02-28 | 2022-02-27 |  | لا يوجد تأخير |  | 43.9892 | 26.349 | منجز | No
2100105744 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 5369400 | 268470 | 4544341.91 | 4544341.91 | 1134003368 | لا | 0 | 181009164092 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 84.9 | 100 | 2017-06-06 | 2019-05-16 | 2020-01-25 | 2020-01-25 |  | 2019-05-16 | لا يوجد تأخير |  | 44.8241 | 26.3046 | منجز | No
2100077475 | وزارة النقل والخدمات اللوجستية / منطقة القصيم | تشييد | ذات اولوية متوسطة | 33695568.8 | 1684778.44 | 21669926.71 | 21669926.71 | 1010203405 | لا | 0 | 180901069655 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2012-10-23 | 2016-07-16 | 2021-12-25 | 2021-12-25 | 2016-07-16 |  |  |  | 44.0633 | 26.2503 | منجز | No
2100100553 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4960630 | 248031.5 | 41710 | 0 | 1116004922 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 15 | 100 | 2014-09-14 | 2016-03-07 | 2021-09-24 | 2021-09-24 |  |  | تأخرصرف المستحقات المالية |  | 44.4147 | 24.509 | مسحوب | Yes
2100078481 | هيئة المدن الصناعية ومناطق التقنية | تصميم | ذات اولوية عالية | 9855456 | 492772.8 | 6463380 | 6463380 | 4030312817 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-08-19 | 2022-08-03 | 2022-08-03 | 2022-08-03 | 2022-08-03 |  | لا يوجد تأخير |  | 46.6857 | 24.7069 | منجز | No
2100057260 | شركة المياه الوطنية / منطقة القصيم | إشراف | ذات اولوية متوسطة | 8208000 | 410400 | 8193952.2 | 8193952.2 | 1131052029 | لا | 0 | 180709023251 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2017-12-11 | 2021-12-11 | 2021-03-31 | 2021-03-31 | 2021-12-11 |  | لا يوجد تأخير |  | 43.0581 | 25.8357 | منجز | No
2100061541 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 30929302.54 | 1546465.127 | 30708386.89 | 30708386.89 | 1010070634 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99.3 | 100 | 2019-12-05 | 2021-12-05 | 2021-08-10 | 2021-08-10 | 2021-12-05 |  | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100043385 | الهيئة الملكية لمدينة مكة المكرمة و المشاعر المقدسة | تشييد | ذات اولوية عالية وعاجلة | 276379637.48 | 13818981.874 | 149827165.6 | 144873618.326 | 4031008077 | لا | 0 | 200309019204 | جاري | منهجية القيمة المكتسبة | 56.72 | 90.61 | 2019-06-19 | 2021-06-18 | 2023-11-15 | 2023-11-15 |  |  | نزع الملكيات | العقد يسير حسب الخطة | 39.85 | 21.3944 | Failed | No
2100059905 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية وعاجلة | 38990000 | 1949500 | 32544568.14 | 28174808.31 | 1131023007 | لا | 0 | 180301000488 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-10-09 | 2021-09-06 | 2022-04-30 | 2022-04-30 | 2021-09-06 |  | ضعف كفاءة المقاول الفنية |  | 43.9544 | 26.3504 | منجز | No
2100070626 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 49754248.8 | 2487712.44 | 16596442.24 | 16596442.24 | 5950010109 | لا | 0 | 181109368511 | جاري | الكميات التي تم تركيبها | 40.79 | 88.36 | 2015-03-12 | 2017-02-17 | 2022-12-29 | 2022-12-29 |  |  | ضعف كفاءة المقاول الفنية |  | 39.9678 | 21.3354 | Failed | No
2100026353 | وزارة الحرس الوطني / وكالة الشؤون الفنية | تشييد | ذات اولوية متوسطة | 1943106 | 97155.3 | 1748906 | 1748906 | 1010062992 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-06-17 | 2021-04-22 | 2021-04-22 | 2021-04-22 | 2021-04-22 |  |  |  | 46.6761 | 24.7038 | منجز | No
2100001186 | وزارة التعليم | تشييد | ذات اولوية عالية | 6485823.43 | 324291.1715 | 2116847.36 | 0 | 4030065868 | لا | 0 |  | مسحوب | التكلفة المفوترة | 34 | 100 | 2010-10-08 | 2012-05-31 | 2023-01-15 | 2023-01-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | Yes
2100085175 | هيئة المدن الصناعية ومناطق التقنية | تصميم | ذات اولوية عالية | 29221080 | 1461054 | 3103870 | 3103870 | 1010213041 | لا | 0 |  | جاري | التكلفة المفوترة | 10 | 10 | 2019-12-22 | 2023-12-01 | 2023-12-01 | 2023-12-01 |  |  | لا يوجد تأخير |  | 46.6898 | 24.7094 | منتظم | No
2100028232 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تصميم | ذات اولوية عالية وعاجلة | 32648500 | 1632425 | 15991837.5 | 15991837.5 | 2251043785 | لا | 0 | 181109254890 | جاري | اخرى | 71.43 | 89.7 | 2017-08-21 | 2022-08-20 | 2023-08-15 | 2023-08-15 |  |  | ضعف كفاءة المقاول الفنية |  | 38.1931 | 24.0183 | متأخر | No
2100048031 | أمانة / نجران | تشييد | ذات اولوية عالية | 10352900 | 517645 | 0 | 0 | 5950018186 | لا | 0 | 180801065138 | ايقاف كلي | اخرى | 0 | 0 | 2018-10-28 | 2020-02-13 | 2022-06-15 | 2022-06-15 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 44.2067 | 17.5642 | Failed | No
2100010872 | جامعة أم القرى | تشييد | ذات اولوية عالية وعاجلة | 256735805.09 | 12836790.2545 | 155061823.49 | 151560020.84 | 4030008659 | لا | 0 | 181109246341 | مسحوب | تكلفة العمل المنجز | 65 | 65 | 2010-04-14 | 2013-04-13 | 2024-12-01 | 2024-12-01 |  |  |  | مخطط لسحبه وإعادة ترسيته | 39.9275 | 21.3499 | مسحوب | No
2100039944 | شركة الكهرباء | تشييد | ذات اولوية متوسطة | 22615363 | 1130768.15 | 17644414 | 17644414 | 1010157290 | لا | 0 |  | جاري الاستلام الإبتدائي | اخرى | 100 | 100 | 2015-09-17 | 2018-04-05 | 2022-12-31 | 2022-12-31 |  |  | لا يوجد تأخير |  | 39.208 | 21.4799 | Failed | No
2100079181 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 17647963 | 882398.15 | 13157959 | 11331116 | 1010001374 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0 | 100 | 2007-11-10 | 2009-10-10 | 2020-11-19 | 2020-11-19 |  |  | ضعف كفاءة المقاول الفنية |  | 50.4732 | 26.5156 | مسحوب | No
2100094813 | وزارة الداخلية / المديرية العامة للدفاع المدني | تشييد | ذات اولوية عالية | 14860350 | 743017.5 | 12872622.5 | 12872622.5 | 4031044308 | لا | 0 | 181109291177 | جاري | الكميات التي تم تركيبها | 97 | 100 | 2018-04-04 | 2020-03-13 | 2022-03-01 | 2022-03-01 |  |  | تأخرصرف المستحقات المالية |  | 39.7034 | 21.5969 | Failed | No
2100087216 | الهيئة الملكية لمدينة مكة المكرمة و المشاعر المقدسة | تشييد | ذات اولوية عالية وعاجلة | 185884572.7309 | 9294228.6365 | 118380483.9029 | 115170068.4349 | 1010066115 | لا | 0 | 190409052109 | جاري | منهجية القيمة المكتسبة | 67.1 | 89.43 | 2018-10-16 | 2020-10-15 | 2023-08-08 | 2023-08-08 |  |  | تصاريح أعمال التنفيذ | العقد يسير حسب الخطة | 39.846 | 21.4546 | متأخر | No
2100191041 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 764400 | 38220 | 672476 | 672476 | 4030155993 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 95 | 100 | 2020-08-16 | 2021-02-17 | 2021-02-13 | 2021-02-13 | 2021-02-17 |  |  |  | 39.7124 | 21.2584 | منجز | No
2100085315 | هيئة المدن الصناعية ومناطق التقنية | إشراف | ذات اولوية عالية | 72627639 | 3631381.95 | 38158760 | 38158760 | 7001444244 | لا | 0 |  | جاري | التكلفة المفوترة | 53 | 53 | 2023-01-12 | 2023-01-15 | 2023-07-17 | 2023-07-17 |  |  | لا يوجد تأخير |  | 39.173 | 21.5355 | خدمات عامة | No
2100096504 | وزارة المالية | مساحة | ذات اولوية متوسطة | 110000 | 5500 | 65000 | 65000 | 1010363372 | لا | 0 |  | جاري | تكلفة العمل المنجز | 96 | 98 | 2018-09-02 | 2019-06-25 | 2022-11-30 | 2022-11-30 |  |  | موافقات |  | 42.0666 | 18.5421 | خدمات عامة | No
2100073673 | شركة الكهرباء | تشييد | ذات اولوية متوسطة | 114145756 | 5707287.8 | 114145756 | 114145756 | 1010011560 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 98 | 98 | 2012-05-29 | 2014-05-30 | 2023-01-30 | 2023-01-30 |  |  | اخرى |  | 39.877 | 21.4343 | Failed | No
2100021965 | شركة الكهرباء | تشييد | ذات اولوية متوسطة | 109459626 | 5472981.3 | 108985941 | 108985941 | 1010011560 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 98 | 98 | 2012-05-29 | 2014-05-30 | 2023-01-10 | 2023-01-10 |  |  | اخرى |  | 39.8591 | 21.4103 | Failed | No
2100095126 | شركة الكهرباء | تشييد | ذات اولوية متوسطة | 94467041 | 4723352.05 | 71556460 | 71556460 | 4030019266 | لا | 0 |  | جاري | اخرى | 98 | 100 | 2015-12-20 | 2018-01-20 | 2023-01-31 | 2023-01-31 |  |  | اخرى |  | 39.2681 | 21.4806 | منتظم | No
2100178566 | وزارة الثقافة | تصميم | ذات اولوية عالية | 800000 | 40000 | 0 | 0 | 4030214246 | لا | 0 |  | جاري | تكلفة العمل المنجز | 30 | 60 | 2020-08-01 | 2021-07-01 | 2022-12-01 | 2022-12-01 |  |  |  |  | 39.1838 | 21.4867 | Failed | No
2100086855 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية | 17972190 | 898609.5 | 5813074.6 | 5813074.6 | 2054000121 | لا | 0 | 190801018694 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-10-09 | 2021-09-17 | 2022-02-28 | 2022-02-28 | 2021-09-17 |  | لا يوجد تأخير |  | 43.9544 | 26.3504 | منجز | No
2100090300 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البحرية | تشييد | ذات اولوية متوسطة | 10486793 | 524339.65 | 10312913 | 10312913 | 1010156182 | لا | 0 | 180901108522 | جاري | الكميات التي تم تركيبها | 67 | 100 | 2019-02-13 | 2022-09-25 | 2023-03-30 | 2023-03-30 |  |  |  |  | 39.1771 | 21.5257 | Failed | No
2100192124 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 387183149 | 19359157.45 | 278954801.72 | 278954801.72 | 1010152417 | لا | 0 | 210709145522 | جاري | تكلفة العمل المنجز | 92 | 100 | 2011-05-21 | 2014-12-03 | 2021-12-31 | 2021-12-31 |  |  |  |  | 39.2592 | 21.4977 | Failed | No
2100056442 | وزارة الموارد البشرية والتنمية الإجتماعية | إشراف | ذات اولوية منخفضة | 1409067 | 70453.35 | 4873361 | 4873361 | 1010429789 | لا | 0 | 190209044349 | مسحوب | الكميات التي تم تركيبها | 85 | 100 | 2015-02-17 | 2017-01-25 | 2022-08-17 | 2022-08-17 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 46.7098 | 22.3028 | مسحوب | No
2100084674 | شركة الكهرباء | تشييد | ذات اولوية متوسطة | 250233990 | 12511699.5 | 199563074 | 199563074 | 2051030681 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 92.5 | 93.5 | 2020-05-18 | 2022-06-15 | 2023-03-30 | 2023-03-30 |  |  |  |  | 39.5599 | 21.3739 | متأخر | No
2200221034 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 3098632.2 | 154931.61 | 0 | 0 | 4031040677 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 12 | 20.6 | 2022-01-28 | 2023-01-28 | 2023-01-28 | 2023-01-28 |  |  |  |  | 39.8194 | 21.3713 | متأخر | No
2100075283 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1200000 | 60000 | 41995 | 0 | 1111001884 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 72 | 100 | 2015-05-20 | 2016-05-04 | 2019-11-27 | 2019-11-27 |  |  | ضعف كفاءة المقاول الفنية |  | 44.628 | 23.9002 | مسحوب | Yes
2100202451 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 117297000 | 5864850 | 31956139.98 | 31956139.98 | 1134000444 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 41 | 46 | 2021-11-19 | 2023-10-19 | 2024-05-29 | 2024-05-29 |  |  |  |  | 49.5731 | 26.9796 | منتظم | No
2100105453 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية وعاجلة | 89880272 | 4494013.6 | 79955493.66 | 75628732.49 | 4030032844 | لا | 0 | 180709034450 | جاري | منهجية القيمة المكتسبة | 94.5 | 100 | 2018-02-04 | 2021-01-02 | 2022-11-30 | 2022-11-30 |  |  | اخرى |  | 43.9544 | 26.3504 | متأخر | No
2200220986 | شركة المياه الوطنية / منطقة الرياض | إشراف | ذات اولوية عالية | 11140440 | 557022 | 799302.15 | 799302.15 | 1010322448 | لا | 0 |  | جاري | تكلفة العمل المنجز | 4.46 | 4.46 | 2022-02-13 | 2024-02-14 | 2024-02-14 | 2024-02-14 |  |  |  |  | 46.7946 | 24.6525 | خدمات عامة | No
2100098350 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البحرية | تشييد | ذات اولوية متوسطة | 1998750 | 99937.5 | 879465 | 879465 | 1010106132 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 82 | 100 | 2012-08-28 | 2014-02-20 | 2021-12-31 | 2021-12-31 |  |  |  |  | 39.1811 | 21.446 | مسحوب | No
2100104786 | المؤسسة العامة للحبوب | تشييد | ذات اولوية عالية | 988411 | 49420.55 | 988411 | 988411 | 2511009902 | لا | 0 | 190309094374 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-11-04 | 2019-08-06 | 2019-07-27 | 2019-07-27 | 2019-08-06 |  | التنسيق مع أصحاب المصلحه (خدمات |  | 43.968 | 26.3285 | منجز | No
2100055064 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تصميم | ذات اولوية عالية وعاجلة | 18955750 | 947787.5 | 18428923.26 | 18428923.26 | 2051060068 | لا | 0 | 180809058646 | جاري | تكلفة العمل المنجز | 94 | 99 | 2018-01-30 | 2023-01-29 | 2023-01-29 | 2023-01-29 |  |  |  |  | 49.1787 | 27.5028 | منتظم | No
2100050223 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 12796705.86 | 639835.293 | 12796705.86 | 12796705.86 | 4030006066 | لا | 0 | 181009124790 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-05-12 | 2016-11-02 | 2020-01-02 | 2020-01-02 | 2016-11-02 |  |  |  | 42.8484 | 21.2515 | منجز | No
2100202484 | الرئاسة العامة لهيئة الأمر بالمعروف والنهي عن المنكر | ترميم | ذات اولوية عالية وعاجلة | 1132000 | 56600 | 62566 | 62566 | 2050039364 | لا | 0 | 200301037594 | جاري | الكميات التي تم تركيبها | 30 | 100 | 2021-09-15 | 2022-05-13 | 2022-05-13 | 2022-05-13 |  |  |  | أخرى | 49.9982 | 26.5765 | Failed | No
2200222202 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | دراسات هندسية | ذات اولوية عالية وعاجلة | 22823865.1 | 1141193.255 | 14131400.2 | 14131400.2 | 4030148218 | لا | 0 |  | جاري | تكلفة العمل المنجز | 68.18 | 75 | 2018-03-04 | 2023-05-04 | 2024-03-10 | 2024-03-10 |  |  |  |  | 38.22 | 23.99 | خدمات عامة | No
2100057864 | وزارة المالية - الحرمين | تشييد | ذات اولوية عالية وعاجلة | 50784000000 | 6564255366 | 13754062746 | 12738166754 | 4030068284 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 71.78 | 71.48 | 2012-11-21 | 2015-11-20 | 2025-06-30 | 2025-06-30 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.8257 | 21.4229 | منتظم | No
2100021733 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 7985716 | 399285.8 | 3463641.79 | 3463641.79 | 5950005816 | لا | 0 | 180601012180 | مسحوب | منهجية القيمة المكتسبة | 63.39 | 100 | 2018-08-27 | 2020-02-10 | 2021-12-31 | 2021-12-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 50.2181 | 26.2736 | مسحوب | No
2100103390 | وزارة المالية - الحرمين | تشييد | ذات اولوية منخفضة | 20000000000 | 4500000000 | 1389804735.77 | 1389804735.77 | 4030068284 | لا | 0 |  | ايقاف كلي | منهجية القيمة المكتسبة | 8.77 | 100 | 2012-12-15 | 2015-12-14 | 2015-12-14 | 2015-12-14 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.836 | 21.4408 | Failed | No
2100085654 | شركة المياه الوطنية / منطقة الباحة | إشراف | ذات اولوية عالية | 770000 | 38500 | 706881.73 | 610225 | 1010326770 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 92.57 | 100 | 2018-12-02 | 2020-02-02 | 2020-02-05 | 2020-02-05 | 2020-02-02 |  | لا يوجد تأخير |  | 41.6622 | 20.2659 | منجز | No
2200211470 | وزارة الصحة / القصيم | تشييد | ذات اولوية متوسطة | 2786553 | 139327.65 | 1003159.08 | 1003159.08 | 1131038024 | لا | 0 |  | جاري | تكلفة العمل المنجز | 99 | 100 | 2018-10-25 | 2022-01-11 | 2022-06-30 | 2022-06-30 |  |  |  |  | 43.9803 | 26.327 | Failed | No
2100031791 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1520037 | 76001.85 | 0.01 | 0.01 | 2066002210 | لا | 0 |  | جاري | التكلفة المفوترة | 0 | 60 | 2019-03-05 | 2020-05-28 | 2021-06-01 | 2021-06-01 |  |  | ضعف كفاءة المقاول الفنية |  | 49.0362 | 26.9388 | Failed | No
2100101533 | المؤسسة العامة لتحلية المياه المالحة | إشراف | ذات اولوية عالية | 79103736 | 3955186.8 | 75854620.84 | 75854620.84 | 1010241121 | لا | 0 | 190401052609 | جاري | منهجية القيمة المكتسبة | 100 | 100 | 2019-02-14 | 2022-12-31 | 2022-12-31 | 2022-12-31 |  |  |  |  | 34.9297 | 29.2906 | خدمات عامة | No
2100194176 | أمانة / جدة | تشييد | ذات اولوية عالية | 15777397 | 788869.85 | 9403772.77 | 2669472 | 4030149957 | لا | 0 | 190201036789 | جاري | تكلفة العمل المنجز | 94 | 100 | 2019-05-16 | 2021-04-23 | 2023-01-30 | 2023-01-30 |  |  |  |  | 39.2425 | 21.5491 | Failed | No
2100059673 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1283816.24 | 64190.812 | 429342.22 | 429342.22 | 4031045075 | لا | 0 | 191001198399 | ايقاف كلي | تكلفة العمل المنجز | 36 | 45 | 2019-02-07 | 2019-09-05 | 2022-01-01 | 2022-01-01 |  |  | اخرى |  | 40.4113 | 21.2648 | Failed | No
2100194095 | أمانة / جدة | تشييد | ذات اولوية عالية | 618975 | 30948.75 | 618975 | 618975 | 4030152625 | لا | 0 | 200609049277 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-10-25 | 2021-04-08 | 2021-04-08 | 2021-04-08 | 2021-04-08 |  |  |  | 40.8826 | 20.3302 | منجز | No
2100091302 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تصميم | ذات اولوية عالية وعاجلة | 51533200 | 2576660 | 44199823.91 | 44199823.91 | 2051060090 | لا | 0 | 180809058981 | جاري | تكلفة العمل المنجز | 83 | 99 | 2018-01-23 | 2023-01-22 | 2023-01-22 | 2023-01-22 |  |  |  | أخرى | 49.5737 | 27.0367 | متأخر | No
2100193340 | المؤسسة العامة للتقاعد | تشييد | ذات اولوية عالية | 1083236.6 | 54161.83 | 412214.17 | 412214.17 | 1010273357 | لا | 0 |  | ايقاف جزئي | الكميات التي تم تركيبها | 78 | 100 | 2020-10-10 | 2021-05-12 | 2021-11-30 | 2021-11-30 |  |  |  |  | 39.7086 | 24.483 | Failed | No
2100067970 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 12981807.5 | 649090.375 | 7351265 | 7351265 | 1010255485 | لا | 0 | 180909094781 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-08-30 | 2015-12-30 | 2021-04-21 | 2021-04-21 | 2015-12-30 |  | ضعف كفاءة المقاول الفنية |  | 37.261 | 25.0346 | منجز | No
2100076882 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | دراسات هندسية | ذات اولوية عالية وعاجلة | 43974375 | 2198718.75 | 22766377.35 | 22766377.35 | 2051047662 | لا | 0 | 190201000576 | جاري | تكلفة العمل المنجز | 51 | 86 | 2019-04-24 | 2024-04-23 | 2024-04-23 | 2024-04-23 |  |  |  | أخرى | 49.582 | 26.9671 | خدمات عامة | No
2100063700 | وزارة الداخلية / ديوان وزارة الداخلية | إشراف | ذات اولوية عالية | 625090300 | 31254515 | 543686282.05 | 540681776 | 1010277276 | لا | 0 |  | جاري | مدفوعات ساعات العمل | 100 | 100 | 2014-11-25 | 2021-12-31 | 2024-12-31 | 2024-12-31 |  |  | لا يوجد تأخير |  | 46.6898 | 24.7275 | خدمات عامة | No
2100200244 | البريد السعودي | إشراف | ذات اولوية عالية وعاجلة | 3895050 | 194752.5 | 844784.91 | 844784.91 | 1010326770 | لا | 0 |  | جاري | اخرى | 22 | 22 | 2022-04-16 | 2023-02-16 | 2023-06-05 | 2023-06-05 |  |  |  |  | 39.6632 | 24.4615 | خدمات عامة | No
2200221841 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 74005838.39 | 3700291.9195 | 41713913.87 | 41713913.87 | 2051034972 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 81 | 95 | 2019-06-30 | 2020-06-29 | 2023-09-30 | 2023-09-30 |  |  |  | أخرى | 49.3653 | 21.9113 | متأخر | No
2100115205 | المؤسسة العامة للحبوب | ترميم | ذات اولوية عالية وعاجلة | 2052610 | 102630.5 | 2052610 | 2052610 | 1010895413 | لا | 0 | 190401057163 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-03-17 | 2019-03-27 | 2020-06-18 | 2020-06-18 | 2019-03-27 |  |  |  | 44.9479 | 20.4904 | منجز | No
2200222865 | أمانة / جدة | تشييد | ذات اولوية عالية | 17995775 | 899788.75 | 5034041.6 | 5034041.6 | 4030141919 | لا | 0 | 210901142997 | جاري | الكميات التي تم تركيبها | 73 | 100 | 2022-01-01 | 2022-12-21 | 2022-12-21 | 2022-12-21 |  |  |  |  | 39.2979 | 21.4214 | Failed | No
2200221863 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 160000000.25 | 8000000.0125 | 22295941.81 | 22295941.81 | 1010210667 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 22.35 | 78 | 2021-12-04 | 2022-11-04 | 2023-08-31 | 2023-08-31 |  |  |  | أخرى | 39.1429 | 21.6897 | Failed | No
2200222563 | رئاسة أمن الدولة / المديرية العامة للمباحث | تشييد | ذات اولوية عالية | 5957700 | 297885 | 5957700 | 0 | 1010301264 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 80 | 100 | 2021-10-18 | 2022-02-12 | 2023-02-01 | 2023-02-01 |  |  |  |  | 46.6992 | 24.6719 | Failed | Yes
2200222596 | رئاسة أمن الدولة / المديرية العامة للمباحث | ترميم | ذات اولوية عالية | 2537802.75 | 126890.1375 | 0.1 | 0.1 | 1010203140 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 85 | 100 | 2021-06-15 | 2022-02-24 | 2023-02-21 | 2023-02-21 |  |  |  |  | 46.6992 | 24.6719 | Failed | No
2200221874 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 154873210 | 7743660.5 | 49573050.94 | 49573050.94 | 2051017029 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 63 | 100 | 2020-09-20 | 2022-05-13 | 2023-03-31 | 2023-03-31 |  |  |  | أخرى | 39.298 | 21.4281 | Failed | No
2100043223 | وزارة الشـؤون الاسلامية والدعوة والارشاد | تشييد | ذات اولوية عالية | 1663848 | 83192.4 | 0 | 0 | 1010232948 | لا | 0 | 200701204580 | ايقاف كلي | الكميات التي تم تركيبها | 100 | 100 | 2019-02-05 | 2019-09-28 | 2021-09-12 | 2021-09-12 |  |  | اخرى |  | 46.7544 | 24.6227 | Failed | No
2100079295 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 3021260 | 151063 | 579600 | 579600 | 1131021347 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 65 | 100 | 2019-07-22 | 2020-10-14 | 2022-11-11 | 2022-11-11 | 2020-10-14 |  |  |  | 43.9544 | 26.3504 | منجز | No
2100026666 | أمانة / الرياض | تشييد | ذات اولوية عالية | 1199945 | 59997.25 | 1107745 | 0 | 1116007885 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 97.98 | 100 | 2014-09-07 | 2015-08-23 | 2020-02-08 | 2020-02-08 | 2015-08-23 |  | ضعف كفاءة المقاول الفنية |  | 44.6213 | 23.9011 | منجز | Yes
2100201541 | رئاسة أمن الدولة / المديرية العامة للمباحث | تشييد | ذات اولوية عالية | 599000 | 29950 | 0 | 0 | 4030246330 | لا | 0 |  | ايقاف كلي | منهجية القيمة المكتسبة | 0.01 | 100 | 2019-02-06 | 2019-06-03 | 2019-06-03 | 2019-06-03 |  |  |  |  | 46.6992 | 24.6719 | Failed | No
2100201552 | رئاسة أمن الدولة / المديرية العامة للمباحث | تشييد | ذات اولوية عالية | 2968537.8 | 148426.89 | 0 | 0 | 4031068952 | لا | 0 |  | مسحوب | منهجية القيمة المكتسبة | 5 | 100 | 2020-11-30 | 2021-08-01 | 2022-11-24 | 2022-11-24 |  |  |  |  | 46.6992 | 24.6719 | مسحوب | No
2100108080 | جامعة طيبة | تشييد | ذات اولوية عالية | 19106946.12 | 955347.306 | 18173274.88 | 18173274.88 | 2050022550 | لا | 0 | 181109376964 | جاري | تكلفة العمل المنجز | 92 | 100 | 2013-02-25 | 2013-05-12 | 2018-03-29 | 2018-03-29 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال | أخرى | 39.6005 | 24.4595 | Failed | No
2100036746 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية عالية | 41425450 | 2071272.5 | 4749470 | 4749470 | 4031036822 | لا | 0 | 3046209 | منجز – استلام نهائي | تكلفة العمل المنجز | 99.01 | 99.01 | 2014-12-07 | 2017-11-03 | 2018-12-16 | 2018-12-16 | 2017-11-03 | 2022-06-08 |  |  | 39.8775 | 21.3636 | منجز | No
2100052533 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 2797474.7 | 139873.735 | 483795.36 | 483795.36 | 4031057370 | لا | 0 | 2046362 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 99.27 | 99.27 | 2014-12-11 | 2017-12-10 | 2018-09-24 | 2018-09-24 |  |  |  |  | 39.8805 | 21.3561 | Failed | No
2100066474 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 2564031 | 128201.55 | 2297231 | 2297231 | 1010158252 | لا | 0 | 190309073403 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-09-16 | 2019-09-11 | 2019-09-11 | 2019-09-11 | 2019-09-11 |  |  |  | 43.5365 | 29.6192 | منجز | No
2100048543 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية عالية | 13735050 | 686752.5 | 13033512 | 13033512 | 4031046580 | لا | 0 | 190909000323 | منجز – استلام ابتدائي | التكلفة المفوترة | 94.89 | 94.89 | 2019-06-02 | 2021-12-13 | 2021-12-13 | 2021-12-13 | 2021-12-13 |  |  |  | 39.8573 | 21.3894 | منجز | No
2100019375 | جامعة أم القرى | تشييد | ذات اولوية عالية وعاجلة | 232662483.11 | 11633124.1555 | 155742673.23 | 122499037.68 | 4030138280 | لا | 0 | 181109245848 | ايقاف كلي | الكميات التي تم تركيبها | 61 | 86 | 2012-11-20 | 2015-10-19 | 2024-12-30 | 2024-12-30 |  |  | اخرى |  | 39.9309 | 21.3444 | Failed | No
2100193620 | وزارة الحرس الوطني / الشؤون الفنية بالقطاع الشرقي | تشييد | ذات اولوية عالية | 6330397.52 | 316519.876 | 2729812.5 | 2729812.5 | 1010150014 | لا | 0 | 200101046788 | جاري | تكلفة العمل المنجز | 60 | 100 | 2020-10-13 | 2022-09-08 | 2023-03-01 | 2023-03-01 |  |  |  |  | 49.5201 | 25.4494 | Failed | No
2100013274 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 1950775 | 97538.75 | 197000 | 197000 | 4031055169 | لا | 0 |  | جاري الاستلام الإبتدائي | التكلفة المفوترة | 100 | 100 | 2015-05-06 | 2017-05-05 | 2017-04-12 | 2017-04-12 |  |  |  |  | 39.7038 | 21.6114 | Failed | No
2100108931 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 8435498.2 | 421774.91 | 8452443.54 | 8452443.54 | 1010096983 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2020-10-07 | 2022-01-10 | 2022-01-10 | 2022-01-10 | 2022-01-10 |  |  |  | 26.3204 | 50.1431 | منجز | No
2100195425 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 893529.22 | 44676.461 | 893529.22 | 893529.22 | 1010364056 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2021-01-12 | 2021-09-12 | 2021-09-12 | 2021-09-12 | 2021-09-12 |  |  |  | 50.0031 | 26.5696 | منجز | No
2100058763 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية وعاجلة | 34454900 | 1722745 | 29637785.23 | 29637785.23 | 1010257755 | لا | 0 | 181001145773 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 96.82 | 100 | 2018-12-31 | 2020-12-09 | 2021-08-31 | 2021-08-31 | 2020-12-09 |  | لا يوجد تأخير |  | 41.3205 | 26.7868 | منجز | No
2100104775 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية وعاجلة | 19786500 | 989325 | 17808157.7 | 17808157.7 | 2050003475 | لا | 0 | 190409036939 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-04-29 | 2020-04-06 | 2021-07-06 | 2021-07-06 | 2020-04-06 |  | أوامر تغيير |  | 41.7183 | 27.5313 | منجز | No
2100022363 | وزارة الصحة / الحدود الشمالية | تشييد | لم تعد تحتاجها الجهة | 3224980 | 161249 | 3224980 | 3224980 | 3453004545 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-02-11 | 2019-08-21 | 2019-07-09 | 2019-07-09 | 2019-08-21 |  | أوامر تغيير |  | 44.739 | 28.8922 | منجز | No
2100083764 | معهد الإدارة العامة | تشييد | ذات اولوية عالية وعاجلة | 23620545 | 1181027.25 | 5478426.78 | 4054587.56 | 1010171914 | لا | 0 | 191101133795 | جاري | التكلفة المفوترة | 19 | 40 | 2019-12-24 | 2020-06-24 | 2023-01-24 | 2023-01-24 |  |  |  |  | 46.6843 | 24.8266 | متأخر | No
2100047762 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 5238800 | 261940 | 3799780 | 3799780 | 3450009076 | لا | 0 | 181201506964 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 74 | 84 | 2019-04-22 | 2020-10-14 | 2022-05-12 | 2022-05-12 | 2020-10-14 |  | ضعف كفاءة المقاول الفنية |  | 41.0327 | 30.9755 | منجز | No
2100202926 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 7239221.44 | 361961.072 | 7210087.3 | 7210087.3 | 4030146704 | لا | 0 | 181101270646 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-10-29 | 2019-04-25 | 2022-06-30 | 2022-06-30 | 2019-04-25 |  |  |  | 39.239 | 21.4933 | منجز | No
2100062436 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1878020 | 93901 | 1878020 | 0 | 1155100235 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-07-21 | 2019-04-17 | 2019-04-17 | 2019-04-17 | 2019-04-17 |  |  |  | 43.8201 | 25.0106 | منجز | Yes
2100090871 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 985000 | 49250 | 232263 | 0 | 1017001594 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 23.58 | 100 | 2015-08-09 | 2017-01-30 | 2021-07-05 | 2021-07-05 |  |  | ضعف كفاءة المقاول الفنية |  | 45.5673 | 20.4494 | مسحوب | Yes
2100029621 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 13089003 | 654450.15 | 12728492.58 | 0 | 1116005202 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 99 | 100 | 2013-05-21 | 2015-05-11 | 2019-08-30 | 2019-08-30 | 2015-05-11 |  | ضعف كفاءة المقاول الفنية |  | 46.6837 | 24.7144 | منجز | Yes
2100047670 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 5397052 | 269852.6 | 5002230 | 5002230 | 1010127437 | لا | 0 | 191101360345 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2015-08-30 | 2020-02-06 | 2020-06-06 | 2020-06-06 | 2020-02-06 |  | ضعف كفاءة المقاول الفنية |  | 42.2469 | 30.3572 | منجز | No
2100028700 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 8108557 | 405427.85 | 2663787.95 | 0 | 1010195208 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 37 | 100 | 2015-07-03 | 2019-03-24 | 2021-06-23 | 2021-06-23 |  |  | ضعف كفاءة المقاول الفنية |  | 44.8725 | 26.3196 | مسحوب | Yes
2100063405 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 16612423.8 | 830621.19 | 5315975.616 | 5315975.616 | 4650021867 | لا | 0 |  | جاري | تكلفة العمل المنجز | 32 | 40 | 2019-01-15 | 2024-02-11 | 2024-02-11 | 2024-02-11 |  |  | ضعف كفاءة المقاول الفنية |  | 40.1503 | 24.7076 | متأخر | No
2100036481 | أمانة / الجوف | تشييد | ذات اولوية عالية وعاجلة | 22442290 | 1122114.5 | 20426938.31 | 20426938.31 | 1010043648 | لا | 0 | 180901069721 | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-02-06 | 2021-07-25 | 2023-01-24 | 2023-01-24 |  |  |  |  | 40.121 | 29.8687 | Failed | No
2100082176 | أمانة / جازان | تشييد | ذات اولوية عالية | 24889334 | 1244466.7 | 323994 | 323994 | 5900008127 | لا | 0 | 181009129736 | جاري | الكميات التي تم تركيبها | 15 | 100 | 2018-01-17 | 2019-12-18 | 2022-06-28 | 2022-06-28 |  |  | اخرى |  | 42.6281 | 17.1508 | Failed | No
2100093133 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 6836470 | 341823.5 | 331870 | 331870 | 5911014153 | لا | 0 | 181101227467 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-11-19 | 2020-12-01 | 2021-08-05 | 2021-08-05 | 2020-12-01 |  | ضعف كفاءة المقاول الفنية |  | 42.5508 | 16.8806 | منجز | No
2100067303 | أمانة / الجوف | تشييد | ذات اولوية عالية وعاجلة | 26255615 | 1312780.75 | 16678529.24 | 16678529.24 | 3450009076 | لا | 0 | 180801052323 | جاري | الكميات التي تم تركيبها | 70 | 78 | 2019-05-19 | 2021-11-04 | 2023-11-13 | 2023-11-13 |  |  |  |  | 40.114 | 29.8882 | متأخر | No
2100072391 | أمانة / جازان | تشييد | ذات اولوية عالية | 1170658 | 58532.9 | 1170658 | 1170658 | 5950008178 | لا | 0 | 180909109885 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2012-12-04 | 2013-11-19 | 2019-02-14 | 2019-02-14 | 2013-11-19 |  | اخرى |  | 42.6229 | 17.1481 | منجز | No
2100065612 | أمانة / الجوف | تشييد | ذات اولوية عالية | 1256165 | 62808.25 | 1256165 | 1256165 | 3400017086 | لا | 0 | 191101202430 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-11-06 | 2020-03-06 | 2020-05-07 | 2020-05-07 | 2020-03-06 |  |  |  | 40.087 | 29.8581 | منجز | No
2100037074 | أمانة / الجوف | تشييد | ذات اولوية عالية وعاجلة | 15949240 | 797462 | 15949240 | 15949240 | 3450009076 | لا | 0 | 190401032627 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-05-27 | 2021-03-18 | 2022-09-22 | 2022-09-22 | 2021-03-18 |  |  |  | 40.1194 | 29.8735 | منجز | No
2100099540 | أمانة / جازان | دراسة الجدوى | ذات اولوية متوسطة | 2628000 | 131400 | 2263000 | 2263000 | 5801010135 | لا | 0 | 181009185888 | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2018-09-02 | 2021-09-01 | 2021-10-01 | 2021-10-01 | 2021-09-01 |  | اخرى |  | 42.5846 | 16.8785 | منجز | No
2100092993 | أمانة / جازان | تشييد | ذات اولوية عالية | 27923320 | 1396166 | 10061296 | 10061296 | 5950008178 | لا | 0 | 180809060071 | جاري | الكميات التي تم تركيبها | 40 | 100 | 2016-11-09 | 2018-10-10 | 2022-03-20 | 2022-03-20 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5574 | 16.7973 | Failed | No
2100092676 | أمانة / جازان | تشييد | ذات اولوية عالية | 13477629.59 | 673881.4795 | 11185675.91 | 11185675.91 | 5850021111 | لا | 0 | 180809060036 | جاري | الكميات التي تم تركيبها | 76 | 100 | 2011-07-19 | 2012-07-03 | 2021-11-11 | 2021-11-11 |  |  | اخرى |  | 42.6691 | 16.9103 | Failed | No
2100006602 | أمانة / الباحة | تصميم | ذات اولوية متوسطة | 342000 | 17100 | 342000 | 342000 | 5801010135 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-04-03 | 2019-09-26 | 2019-09-26 | 2019-09-26 | 2019-09-26 |  | اخرى |  |  |  | منجز | No
2100076274 | أمانة / جازان | تشييد | ذات اولوية عالية | 32984638.14 | 1649231.907 | 32984638.14 | 32984638.14 | 1010152168 | لا | 0 | 180909098713 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-04-07 | 2018-06-01 | 2020-04-12 | 2020-04-12 | 2018-06-01 |  | اخرى |  | 42.6252 | 17.1531 | منجز | No
2100039211 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 103400000 | 5170000 | 91715556.83 | 91715556.83 | 1010008118 | لا | 0 |  | جاري | تكلفة العمل المنجز | 89.62 | 89.62 | 2011-02-12 | 2013-08-15 | 2015-09-19 | 2015-09-19 |  |  |  |  | 39.8845 | 21.3188 | Failed | No
2100092514 | أمانة / جازان | تشييد | ذات اولوية عالية | 9220672 | 461033.6 | 9128583.88 | 9128583.88 | 5855021000 | لا | 0 | 180909109884 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 99 | 100 | 2010-07-02 | 2018-09-25 | 2020-04-27 | 2020-04-27 | 2018-09-25 |  | اخرى |  | 42.564 | 16.8867 | منجز | No
2100067701 | أمانة / جازان | تشييد | ذات اولوية عالية وعاجلة | 12330956 | 616547.8 | 10457992 | 10457992 | 5950010447 | لا | 0 | 180909110067 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 87 | 100 | 2015-10-19 | 2021-10-07 | 2021-11-11 | 2021-11-11 | 2021-10-07 |  | ضعف كفاءة المقاول الفنية |  | 42.6272 | 17.1502 | منجز | No
2100146311 | وزارة المالية | إشراف | ذات اولوية متوسطة | 2318400 | 115920 | 2387155 | 2387155 | 1010007606 | لا | 0 | 190501123973 | ايقاف كلي | تكلفة العمل المنجز | 64 | 64 | 2019-07-16 | 2020-02-02 | 2023-11-30 | 2023-11-30 |  |  | ضعف كفاءة المقاول الفنية |  | 42.0451 | 18.5329 | Failed | No
2100018863 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 3205320 | 160266 | 2153480 | 2153480 | 4650020357 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 67 | 100 | 2015-01-31 | 2016-03-19 | 2016-03-19 | 2016-03-19 |  |  | ضعف كفاءة المقاول الفنية |  | 39.5356 | 24.5391 | مسحوب | No
2100084475 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية عالية | 72738745.67 | 3636937.2835 | 66800889.89 | 66800889.89 | 1010187733 | لا | 0 |  | منجز – استلام نهائي | تكلفة العمل المنجز | 91.84 | 91.84 | 2014-02-02 | 2015-02-02 | 2020-12-25 | 2020-12-25 | 2015-02-02 | 2022-01-30 | اخرى |  | 39.8676 | 21.3641 | منجز | No
2100094673 | أمانة / العاصمة المقدسة | أخرى | ذات اولوية متوسطة | 8411500 | 420575 | 1890000 | 1890000 | 4030013052 | لا | 0 |  | مسحوب | اخرى | 22.47 | 22.47 | 2017-09-21 | 2018-09-21 | 2022-08-31 | 2022-08-31 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.8604 | 21.3457 | مسحوب | No
2100087710 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 17940085 | 897004.25 | 17669895.92 | 17669895.92 | 1010210566 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99.44 | 100 | 2018-09-17 | 2019-05-17 | 2020-10-01 | 2020-10-01 | 2019-05-17 |  | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100004325 | جامعة جازان | تشييد | ذات اولوية منخفضة | 135312731.29 | 6765636.5645 | 64415489.28 | 60326265.85 | 1010277276 | لا | 0 | 181109360936 | جاري | الكميات التي تم تركيبها | 55 | 82 | 2014-10-25 | 2017-10-25 | 2024-01-03 | 2024-01-03 |  |  | المشروع ليس ذو أولوية في الوقت الحالي |  | 42.9186 | 16.6238 | Failed | No
2100032502 | أمانة / عسير | تشييد | ذات اولوية عالية | 16323636 | 816181.8 | 11510142 | 11510142 | 5850031232 | لا | 0 |  | جاري | تكلفة العمل المنجز | 88 | 100 | 2018-12-24 | 2019-12-15 | 2023-03-31 | 2023-03-31 |  |  | ضعف كفاءة المقاول الفنية |  | 42.7874 | 18.3103 | Failed | No
2100041134 | وزارة التعليم | تشييد | ذات اولوية عالية | 10598550.29 | 529927.5145 | 9113428.68 | 9113428.68 | 1010081451 | لا | 0 |  | جاري | التكلفة المفوترة | 85 | 100 | 2014-11-05 | 2016-10-25 | 2019-05-08 | 2019-05-08 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6212 | 24.7756 | Failed | No
2100081480 | أمانة / عسير | تشييد | ذات اولوية عالية | 25932950 | 1296647.5 | 10650423 | 10650423 | 5950009415 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 50 | 100 | 2014-04-05 | 2016-06-04 | 2023-03-31 | 2023-03-31 |  |  | ضعف كفاءة المقاول الفنية |  | 42.8068 | 18.2543 | مسحوب | No
2100063324 | أمانة / عسير | تشييد | ذات اولوية عالية | 680000 | 34000 | 340000 | 340000 | 5855025894 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 50 | 100 | 2014-12-03 | 2015-06-01 | 2023-03-31 | 2023-03-31 |  |  | ضعف كفاءة المقاول الفنية |  | 42.7602 | 18.2865 | مسحوب | No
2100002085 | أمانة / الجوف | تشييد | ذات اولوية عالية وعاجلة | 3855900 | 192795 | 3741329.5 | 3741329.5 | 1010108475 | نعم | 381455 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-10-12 | 2020-08-12 | 2022-09-15 | 2022-09-15 | 2020-08-12 |  | أوامر تغيير |  | 37.3614 | 31.3296 | منجز | No
2100069075 | أمانة / عسير | تشييد | ذات اولوية عالية | 24918780 | 1245939 | 15216202.92 | 15216202.92 | 4032019436 | لا | 0 |  | جاري | تكلفة العمل المنجز | 98 | 100 | 2019-03-16 | 2020-11-06 | 2023-03-31 | 2023-03-31 |  |  |  |  | 42.7439 | 18.3049 | Failed | No
2100093601 | وزارة المالية - الحرمين | إشراف | ذات اولوية عالية وعاجلة | 44357142.98 | 0 | 25433275.38 | 25433275.38 | 1010076578 | لا | 0 |  | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 98.85 | 100 | 2013-10-14 | 2015-06-30 | 2022-07-30 | 2022-07-30 | 2015-06-30 |  | اخرى |  | 39.5639 | 24.4942 | منجز | No
2100071573 | أمانة / عسير | تشييد | ذات اولوية عالية | 6150120 | 307506 | 3517659.5 | 3517659.5 | 5855026400 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 61 | 100 | 2019-01-05 | 2019-12-22 | 2021-09-22 | 2021-09-22 |  |  | ضعف كفاءة المقاول الفنية |  | 42.7809 | 18.3054 | مسحوب | No
2100011616 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية متوسطة | 11731271 | 586563.55 | 11731247.82 | 11731247.82 | 5855029073 | لا | 0 | 180701015719 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-08-12 | 2020-07-22 | 2020-07-22 | 2020-07-22 |  | 2020-07-22 | لا يوجد تأخير |  | 42.4989 | 18.2169 | منجز | No
2100041521 | جامعة الإمام عبدالرحمن بن فيصل | تشييد | ذات اولوية عالية وعاجلة | 83057521.14 | 4152876.057 | 30222548.48 | 30222548.48 | 2055002293 | لا | 0 | 180809037781 | ايقاف كلي | تكلفة العمل المنجز | 52 | 96.8 | 2014-01-20 | 2016-12-17 | 2022-12-29 | 2022-12-29 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 50.1918 | 26.3967 | Failed | No
2100012283 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 132271759.17 | 6613587.9585 | 49625231.26 | 49625231.26 | 1010185409 | لا | 0 |  | ايقاف جزئي | منهجية القيمة المكتسبة | 75 | 100 | 2020-01-28 | 2021-07-21 | 2022-12-31 | 2022-12-31 |  |  | أوامر تغيير | أخرى |  |  | Failed | No
2100073640 | جامعة بيشة | تشييد | ذات اولوية متوسطة | 3881978 | 194098.9 | 821472 | 821472 | 5851003348 | لا | 0 | 190501071771 | جاري | الكميات التي تم تركيبها | 22 | 40 | 2021-09-21 | 2023-04-14 | 2023-04-14 | 2023-04-14 |  |  | ضعف كفاءة المقاول الفنية |  | 42.613 | 20.0279 | متأخر | No
2100018384 | وكالة / الإسكان | تشييد | ذات اولوية متوسطة | 79862019.25 | 3993100.9625 | 54219762.75 | 54219762.75 | 1010054406 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2013-07-26 | 2015-07-16 | 2022-12-31 | 2022-12-31 | 2015-07-16 |  | ضعف كفاءة المقاول الفنية | أخرى | 49.5604 | 25.3897 | منجز | No
2100014221 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 53841835 | 2692091.75 | 40054597 | 37671437 | 3350000106 | لا | 0 | 180401001768 | جاري | الكميات التي تم تركيبها | 61 | 74 | 2018-09-27 | 2020-08-04 | 2023-07-05 | 2023-07-05 |  |  | سوء التخطيط الاولي للمشروع |  | 41.7131 | 27.5332 | متأخر | No
2100090215 | وزارة التعليم | تشييد | ذات اولوية عالية | 8353665 | 417683.25 | 7452589 | 6994941 | 4032034978 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2019-02-11 | 2019-10-09 | 2019-10-31 | 2019-10-31 | 2019-10-09 |  |  |  | 40.4511 | 21.2747 | منجز | No
2100088782 | وزارة الحرس الوطني / وكالة الشؤون الفنية | تصميم وتشييد | ذات اولوية عالية وعاجلة | 4400000000 | 220000000 | 0 | 0 | 4030068284 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 2 | 100 | 2014-11-11 | 2017-11-10 | 2022-06-03 | 2022-06-03 |  |  | اخرى |  |  |  | مسحوب | No
2100193546 | وزارة الحرس الوطني / وكالة الشؤون الفنية | إشراف | ذات اولوية عالية | 104642464 | 5232123.2 | 42240604 | 42240604 | 1010902667 | لا | 0 |  | ايقاف كلي | التكلفة المفوترة | 42 | 42 | 2015-06-01 | 2018-06-01 | 2024-01-31 | 2024-01-31 |  |  | اخرى |  |  |  | Failed | No
2100052415 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 9053377.85 | 452668.8925 | 9053377.85 | 7201845 | 1010168033 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-08-06 | 2016-04-27 | 2018-07-21 | 2018-07-21 | 2016-04-27 |  |  |  | 41.0859 | 19.1571 | منجز | No
2100030354 | أمانة / الجوف | تشييد | ذات اولوية عالية | 987750 | 49387.5 | 592162 | 592162 | 1010234790 | لا | 0 | 180909091089 | مسحوب | تكلفة العمل المنجز | 60 | 100 | 2018-07-14 | 2019-03-08 | 2019-03-10 | 2019-03-10 |  |  | ضعف كفاءة المقاول الفنية |  | 39.3051 | 29.888 | مسحوب | No
2100042405 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2972004 | 148600.2 | 1744985.03 | 1744985.03 | 1010233819 | لا | 0 |  | جاري | التكلفة المفوترة | 88 | 100 | 2014-06-18 | 2015-08-12 | 2022-05-17 | 2022-05-17 |  |  | ضعف كفاءة المقاول الفنية |  | 45.3525 | 25.8912 | Failed | No
2100073916 | أمانة / جدة | دراسات هندسية | ذات اولوية عالية | 1278900 | 63945 | 1365900 | 1365900 | 1010373041 | لا | 0 | 200101001903 | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2019-07-02 | 2019-12-26 | 2019-12-26 | 2019-12-26 | 2019-12-26 | 2019-12-27 | اخرى |  |  |  | منجز | No
2100036713 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 1536700 | 76835 | 1536700 | 1536700 | 4031050860 | لا | 0 | 191001190697 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-03-05 | 2019-10-28 | 2020-08-12 | 2020-08-12 | 2019-10-28 |  | ضعف كفاءة المقاول الفنية |  | 40.2778 | 20.1408 | منجز | No
2100018266 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 4481049 | 224052.45 | 0 | 0 | 1010277276 | لا | 0 |  | ايقاف كلي | التكلفة المفوترة | 0 | 100 | 2014-05-08 | 2015-10-30 | 2023-05-10 | 2023-05-10 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | Failed | No
2100076215 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 2999250 | 149962.5 | 1639612 | 1639612 | 4030050024 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 78 | 100 | 2014-12-31 | 2016-06-14 | 2018-04-21 | 2018-04-21 |  |  | ضعف كفاءة المقاول الفنية |  | 40.282 | 20.1402 | مسحوب | No
2100033961 | أمانة / جدة | تشييد | ذات اولوية عالية | 7764150 | 388207.5 | 0 | 0 | 1010064626 | لا | 0 | 210309109182 | مسحوب | تكلفة العمل المنجز | 30 | 100 | 2015-07-08 | 2017-06-16 | 2019-01-11 | 2019-01-11 |  |  | ضعف كفاءة المقاول الفنية |  | 40.2782 | 20.144 | مسحوب | No
2100100774 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 6996675 | 349833.75 | 6538350 | 6538350 | 4605002907 | لا | 0 | 181209507904 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-02-07 | 2019-08-06 | 2019-08-06 | 2019-08-06 | 2019-08-06 |  |  |  | 40.4036 | 21.2597 | منجز | No
2100020764 | وزارة الشـؤون الاسلامية والدعوة والارشاد | تشييد | ذات اولوية عالية | 294710 | 14735.5 | 0 | 0 | 3357003880 | نعم | 452060 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2017-11-30 | 2018-05-30 | 2021-02-25 | 2021-02-25 | 2018-05-30 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.528 | 26.6769 | منجز | No
2100043046 | وزارة التجارة | تشييد | ذات اولوية عالية وعاجلة | 56014493 | 2800724.65 | 7920410 | 7920410 | 2051030201 | لا | 0 | 180709021876 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2015-11-26 | 2017-11-25 | 2021-02-28 | 2021-02-28 |  | 2017-11-25 | اخرى |  | 39.2173 | 21.4795 | منجز | No
2100010220 | وزارة الصحة / ديوان الوزارة | تشييد | ذات اولوية عالية | 126799627 | 6339981.35 | 94855707.2 | 94855707.2 | 5855017763 | نعم | 110155705 | 200309067783 | مسحوب | تكلفة العمل المنجز | 97 | 100 | 2008-04-14 | 2010-03-23 | 2018-01-06 | 2018-01-06 |  |  | ضعف كفاءة المقاول الفنية |  | 40.2891 | 20.1137 | مسحوب | No
2100081793 | أمانة / جازان | تشييد | ذات اولوية عالية وعاجلة | 1784212.5 | 89210.625 | 0.01 | 0.01 | 5901009718 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 89 | 100 | 2019-10-23 | 2020-10-22 | 2020-10-23 | 2020-10-23 | 2020-10-22 |  | ضعف كفاءة المقاول الفنية |  | 42.6981 | 16.9757 | منجز | No
2100088454 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البحرية | تشييد | ذات اولوية متوسطة | 6981870 | 349093.5 | 6981870 | 6981870 | 1010242781 | لا | 0 | 180801052901 | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 100 | 100 | 2017-01-11 | 2020-02-15 | 2021-09-21 | 2021-09-21 |  |  |  |  | 49.5931 | 26.9306 | Failed | No
2100073942 | أمانة / جازان | دراسة الجدوى | ذات اولوية متوسطة | 3420000 | 171000 | 3135000 | 3135000 | 5900020940 | لا | 0 | 181001203952 | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2018-10-22 | 2021-10-21 | 2021-10-21 | 2021-10-21 | 2021-10-21 |  | اخرى |  | 42.5681 | 16.9388 | منجز | No
2100072262 | أمانة / جازان | تشييد | ذات اولوية عالية وعاجلة | 2524603 | 126230.15 | 1627366.69 | 1627366.69 | 4030165513 | لا | 0 | 191101132251 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 99 | 100 | 2019-10-13 | 2020-10-07 | 2021-09-05 | 2021-09-05 | 2020-10-07 |  | ضعف كفاءة المقاول الفنية |  | 42.6988 | 16.9762 | منجز | No
2100036190 | أمانة / جازان | تشييد | ذات اولوية عالية | 499030 | 24951.5 | 499030 | 499030 | 5900011363 | لا | 0 | 180601013859 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-08-17 | 2019-08-12 | 2019-08-13 | 2019-08-13 | 2019-08-12 |  | اخرى |  | 42.9405 | 16.6011 | منجز | No
2100029256 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 58398300 | 2919915 | 47302623 | 47302623 | 4030044382 | لا | 0 |  | جاري | تكلفة العمل المنجز | 81 | 78 | 2018-11-13 | 2024-09-18 | 2024-09-18 | 2024-09-18 |  |  | ضعف كفاءة المقاول الفنية |  | 39.5687 | 24.5168 | منتظم | No
2100058914 | المركز الوطني للأرصاد | تشييد | ذات اولوية متوسطة | 225290050 | 11264502.5 | 213467008 | 213467008 | 4030000500 | لا | 0 | 181009165234 | مسحوب | تكلفة العمل المنجز | 98 | 100 | 2008-05-06 | 2010-10-09 | 2010-10-09 | 2010-10-09 |  |  | اخرى |  | 39.2097 | 21.5235 | مسحوب | No
2100018826 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2203825.5 | 110191.275 | 131272 | 131272 | 3350009773 | لا | 0 |  | مسحوب | التكلفة المفوترة | 12 | 100 | 2016-02-28 | 2017-02-22 | 2023-01-24 | 2023-01-24 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | مسحوب | No
2100101076 | وزارة الصحة / المدينة المنورة | تشييد | ذات اولوية منخفضة | 22911215 | 1145560.75 | 6036136 | 5102352 | 1010215793 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 41 | 100 | 2013-09-09 | 2015-08-18 | 2022-06-30 | 2022-06-30 |  |  | تأخرصرف المستحقات المالية |  | 39.36 | 24.28 | Failed | No
2100019456 | أمانة / تبوك | دراسة الجدوى | ذات اولوية متوسطة | 375000 | 18750 | 216000 | 216000 | 3550025925 | لا | 0 |  | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2018-11-09 | 2019-08-06 | 2019-08-06 | 2019-08-06 | 2019-08-06 |  | اخرى |  |  |  | منجز | No
2100026180 | وزارة الموارد البشرية والتنمية الإجتماعية | تشييد | ذات اولوية منخفضة | 6884648.25 | 344232.4125 | 6884648.25 | 6884648.25 | 1010274632 | لا | 0 | 181109264771 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-01-14 | 2017-10-11 | 2021-12-21 | 2021-12-21 | 2017-10-11 |  | لا يوجد تأخير |  | 37.2664 | 25.0399 | منجز | No
2100090090 | أمانة / العاصمة المقدسة | تحديث وتوريد | ذات اولوية متوسطة | 3034500 | 151725 | 3034500 | 3034500 | 1010464778 | لا | 0 | 190609005336 | منجز – استلام نهائي | مدفوعات ساعات العمل | 100 | 100 | 2019-04-25 | 2021-04-24 | 2021-04-24 | 2021-04-24 | 2021-04-24 | 2021-06-24 | اخرى |  |  |  | منجز | No
2100019320 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية وعاجلة | 45101423.72 | 2255071.186 | 35592564.36 | 35592564.36 | 1010045581 | لا | 0 | 180709024862 | ايقاف كلي | تكلفة العمل المنجز | 98 | 100 | 2014-06-10 | 2016-05-10 | 2023-12-31 | 2023-12-31 |  |  | تأخرصرف المستحقات المالية |  | 46.1005 | 24.4572 | Failed | No
2100073124 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 84999800 | 4249990 | 59188505.36 | 59188505.36 | 5855028046 | لا | 0 | 181001218863 | مسحوب | الكميات التي تم تركيبها | 80.6 | 100 | 2019-01-17 | 2022-01-04 | 2022-01-03 | 2022-01-03 |  |  |  |  | 42.1227 | 19.7955 | مسحوب | No
2100004616 | وزارة الصحة / المدينة المنورة | تشييد | ذات اولوية منخفضة | 26792446 | 1339622.3 | 10853678 | 9927113 | 1010215793 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 54 | 100 | 2013-09-09 | 2015-08-18 | 2022-03-31 | 2022-03-31 |  |  | تأخرصرف المستحقات المالية |  | 39.36 | 24.28 | Failed | No
2100080496 | أمانة / عسير | تشييد | ذات اولوية عالية | 948975 | 47448.75 | 181500 | 181500 | 5856005112 | لا | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 12 | 100 | 2014-12-16 | 2023-04-04 | 2023-04-04 | 2023-04-04 |  |  | أوامر سامية |  | 42.6712 | 18.5807 | Failed | No
2100081841 | أمانة / عسير | تشييد | ذات اولوية عالية | 4984205 | 249210.25 | 3251841 | 3251841 | 5858014051 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 73 | 100 | 2015-10-18 | 2016-10-18 | 2020-09-01 | 2020-09-01 |  |  | تأخرصرف المستحقات المالية |  | 43.5129 | 17.6651 | مسحوب | No
2100104591 | وزارة الموارد البشرية والتنمية الإجتماعية | تشييد | ذات اولوية منخفضة | 41780841.6 | 2089042.08 | 41780841.6 | 41780841.6 | 1115001461 | لا | 0 | 180809053328 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-11-30 | 2017-10-27 | 2018-11-06 | 2018-11-06 | 2017-10-27 |  | ضعف كفاءة المقاول الفنية |  | 46.7373 | 24.6324 | منجز | No
2100203873 | جامعة الملك سعود | تشييد | ذات اولوية متوسطة | 11758713 | 587935.65 | 0 | 0 | 4030052524 | لا | 0 | 211109081708 | مسحوب | تكلفة العمل المنجز | 5 | 100 | 2020-11-29 | 2021-10-31 | 2022-05-31 | 2022-05-31 |  |  | ضعف كفاءة المقاول الفنية | مخطط لإعادة طرحه | 46.6234 | 24.7117 | مسحوب | No
2100091044 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 4887822 | 244391.1 | 0 | 0 | 4030052981 | لا | 0 |  | مسحوب | التكلفة المفوترة | 0 | 100 | 2015-03-22 | 2016-09-12 | 2023-11-15 | 2023-11-15 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | مسحوب | No
2100043330 | جامعة الإمام محمد بن سعود الاسلامية | تشييد | ذات اولوية عالية | 193215199.91 | 9660759.9955 | 175099294.22 | 171029084.22 | 1010016736 | لا | 0 | 190909020111 | جاري | اخرى | 97 | 100 | 2012-08-25 | 2013-08-14 | 2023-02-28 | 2023-02-28 |  |  | أوامر تغيير |  | 46.7098 | 24.6275 | Failed | No
2100039410 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية عالية | 144330145 | 7216507.25 | 122407736 | 122407736 | 2050024197 | لا | 0 | 181109327901 | ايقاف جزئي | تكلفة العمل المنجز | 88 | 100 | 2014-04-15 | 2015-09-28 | 2022-03-19 | 2022-03-19 |  |  |  |  | 50.0402 | 26.2344 | متأخر | No
2100044866 | أمانة / عسير | تشييد | ذات اولوية عالية | 7811700 | 390585 | 4686800 | 4686800 | 5859000601 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 63 | 100 | 2014-04-27 | 2016-04-16 | 2020-10-14 | 2020-10-14 |  |  | ضعف كفاءة المقاول الفنية |  | 42.179 | 18.9518 | مسحوب | No
2100043912 | أمانة / عسير | تشييد | ذات اولوية عالية | 5379798 | 268989.9 | 0 | 0 | 2051035036 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 30 | 100 | 2019-01-13 | 2020-04-16 | 2020-03-15 | 2020-03-15 |  |  | ضعف كفاءة المقاول الفنية |  | 42.1351 | 19.1263 | مسحوب | No
2100043271 | وزارة الموارد البشرية والتنمية الإجتماعية | تشييد | ذات اولوية منخفضة | 17164761.65 | 858238.0825 | 10063760.97 | 10063760.97 | 1010219247 | لا | 0 | 190209042471 | مسحوب | الكميات التي تم تركيبها | 84 | 100 | 2015-12-27 | 2017-12-26 | 2022-04-20 | 2022-04-20 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 47.3741 | 24.1947 | مسحوب | No
2100194530 | أمانة / جدة | إشراف | ذات اولوية عالية وعاجلة | 142433150 | 7121657.5 | 94192539 | 76864239 | 1010403954 | لا | 0 | 180401004299 | جاري | اخرى | 68 | 68 | 2018-09-09 | 2021-09-09 | 2024-04-15 | 2024-04-15 |  |  |  |  | 39.1677 | 21.5008 | خدمات عامة | No
2100002785 | أمانة / عسير | تشييد | ذات اولوية عالية وعاجلة | 34284476 | 1714223.8 | 31502977 | 31502977 | 5850016183 | لا | 0 | 181001157092 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-08-29 | 2021-08-19 | 2023-03-31 | 2023-03-31 | 2021-08-19 |  | ضعف كفاءة المقاول الفنية |  | 42.5165 | 18.2431 | منجز | No
2100099573 | أمانة / عسير | تشييد | ذات اولوية عالية | 8545408 | 427270.4 | 7214932.9 | 7214932.9 | 5850031232 | لا | 0 | 190701124493 | جاري | تكلفة العمل المنجز | 87 | 100 | 2019-09-09 | 2022-12-22 | 2022-12-22 | 2022-12-22 |  |  |  |  | 42.6819 | 18.5774 | متأخر | No
2100017006 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | تشييد | ذات اولوية عالية | 50652705.47 | 2532635.2735 | 45200476.7 | 45200476.7 | 5855010714 | لا | 0 | 180709032284 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2016-06-14 | 2018-06-02 | 2022-03-31 | 2022-03-31 | 2018-06-02 |  | تأخرصرف المستحقات المالية |  | 42.5429 | 16.8808 | منجز | No
2100044251 | أمانة / عسير | تشييد | ذات اولوية عالية وعاجلة | 884580.66 | 44229.033 | 799083.9 | 799083.9 | 5856665842 | لا | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 33 | 100 | 2013-12-07 | 2023-04-04 | 2023-04-04 | 2023-04-04 |  |  | أوامر سامية |  | 42.6767 | 18.5902 | Failed | No
2100032896 | أمانة / عسير | تشييد | ذات اولوية عالية وعاجلة | 1999351 | 99967.55 | 276898 | 276898 | 5857024318 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 15 | 100 | 2019-04-08 | 2020-04-03 | 2020-05-14 | 2020-05-14 |  |  | ضعف كفاءة المقاول الفنية |  | 42.2418 | 18.7828 | مسحوب | No
2100057256 | وزارة الموارد البشرية والتنمية الإجتماعية | تشييد | ذات اولوية منخفضة | 28815401.68 | 1440770.084 | 11726566 | 11506690.78 | 1010145283 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 77 | 100 | 2015-02-02 | 2017-01-10 | 2022-02-09 | 2022-02-09 |  |  | ضعف كفاءة المقاول الفنية |  | 39.2147 | 21.5458 | مسحوب | No
2100054725 | وزارة الخارجية | تشييد | ذات اولوية عالية | 130237500 | 6511875 | 1312935.52 | 1312935.52 | 2051027499 | لا | 0 | 191101348404 | ايقاف جزئي | تكلفة العمل المنجز | 1 | 50 | 2019-12-02 | 2020-12-31 | 2022-03-01 | 2022-03-01 |  |  | عدم وجود مبالغ في البنود تغطي الأعمال المرصودة |  | 9.4445 | 0.4201 | Failed | No
2100018933 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4139972.4 | 206998.62 | 3352142.52 | 0 | 1010171813 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 87.85 | 100 | 2013-10-17 | 2015-01-10 | 2020-02-12 | 2020-02-12 | 2015-01-10 |  | ضعف كفاءة المقاول الفنية |  | 45.433 | 25.0781 | منجز | Yes
2100069005 | أمانة / عسير | تشييد | ذات اولوية عالية | 5457740 | 272887 | 1381295 | 500000 | 5859000601 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 50 | 100 | 2015-04-11 | 2016-04-05 | 2019-10-22 | 2019-10-22 |  |  | تأخرصرف المستحقات المالية |  | 42.1351 | 19.1263 | مسحوب | No
2100106013 | وزارة الموارد البشرية والتنمية الإجتماعية | تشييد | ذات اولوية منخفضة | 42315731 | 2115786.55 | 19270186.83 | 19270186.83 | 2051030201 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 78 | 100 | 2012-06-11 | 2015-05-09 | 2021-11-16 | 2021-11-16 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.1952 | 21.5308 | مسحوب | No
2100059485 | وزارة التعليم | تشييد | لم تعد تحتاجها الجهة | 4888721.5 | 244436.075 | 961902.82 | 961902.82 | 1010142553 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 20 | 100 | 2015-06-03 | 2016-11-24 | 2016-11-24 | 2016-11-24 |  |  | المشروع ليس ذو أولوية في الوقت الحالي |  | 46.7098 | 24.6275 | مسحوب | No
2100052824 | أمانة / عسير | تشييد | ذات اولوية عالية | 1902575 | 95128.75 | 156541 | 156541 | 5855041956 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 50 | 100 | 2015-11-29 | 2016-11-29 | 2023-01-31 | 2023-01-31 |  |  | ضعف كفاءة المقاول الفنية |  | 41.9929 | 18.3397 | مسحوب | No
2100033526 | أمانة / عسير | تشييد | ذات اولوية عالية | 2339905 | 116995.25 | 1728848 | 1728848 | 5857024318 | لا | 0 | 191101290238 | مسحوب | تكلفة العمل المنجز | 87 | 100 | 2018-10-01 | 2019-09-27 | 2020-01-25 | 2020-01-25 |  |  | ضعف كفاءة المقاول الفنية |  | 42.2496 | 18.7748 | مسحوب | No
2100077814 | وزارة الخارجية | تشييد | ذات اولوية عالية | 104798019 | 5239900.95 | 2136523.5 | 2136523.5 | 2051027499 | لا | 0 |  | ايقاف جزئي | تكلفة العمل المنجز | 3 | 21 | 2020-02-09 | 2021-10-11 | 2023-07-01 | 2023-07-01 |  |  | عدم وجود مبالغ في البنود تغطي الأعمال المرصودة |  | -15.9653 | 18.0711 | متأخر | No
2100077523 | وزارة النقل والخدمات اللوجستية / منطقة جازان | تشييد | ذات اولوية متوسطة | 34151484.5 | 1707574.225 | 23879182.56 | 23879182.56 | 1010066115 | لا | 0 | 180901069401 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-12-09 | 2016-05-23 | 2022-01-22 | 2022-01-22 | 2016-05-23 |  |  |  | 42.6269 | 17.1548 | منجز | No
2100061375 | وزارة النقل والخدمات اللوجستية / منطقة جازان | تشييد | ذات اولوية متوسطة | 109054471.96 | 5452723.598 | 71381115.2 | 71381115.2 | 1010210667 | لا | 0 | 180701033287 | جاري | الكميات التي تم تركيبها | 89.6 | 100 | 2012-09-27 | 2016-08-13 | 2022-12-30 | 2022-12-30 |  |  |  |  | 42.8872 | 17.6547 | متأخر | No
2100081756 | أمانة / عسير | تشييد | ذات اولوية عالية | 9048398 | 452419.9 | 3347907 | 3347907 | 5858014051 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 37 | 100 | 2015-03-07 | 2017-03-03 | 2022-05-25 | 2022-05-25 |  |  | تأخرصرف المستحقات المالية |  | 43.518 | 17.6649 | مسحوب | No
2100051995 | أمانة / عسير | تشييد | ذات اولوية عالية | 4954700 | 247735 | 854472 | 732683 | 2051035036 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 40 | 100 | 2014-12-26 | 2015-12-22 | 2019-10-22 | 2019-10-22 |  |  | تأخرصرف المستحقات المالية |  | 42.1351 | 19.1263 | مسحوب | No
2100018896 | أمانة / عسير | تشييد | ذات اولوية عالية | 7776132 | 388806.6 | 0 | 0 | 5857007966 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 12 | 100 | 2019-10-09 | 2020-10-03 | 2021-07-09 | 2021-07-09 |  |  |  |  | 42.4957 | 18.2499 | مسحوب | No
2100040670 | وزارة الصحة / ديوان الوزارة | تشييد | ذات اولوية عالية | 326686471 | 16334323.55 | 30373981 | 0 | 1010009593 | نعم | 62634355 | 190709036289 | ايقاف كلي | تكلفة العمل المنجز | 13.39 | 0 | 2019-04-10 | 2022-04-10 | 2024-12-31 | 2024-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 43.5768 | 25.9016 | Failed | Yes
2100071842 | أمانة / عسير | تشييد | ذات اولوية عالية | 1218395 | 60919.75 | 0 | 0 | 5858014051 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 5 | 100 | 2015-08-31 | 2016-09-01 | 2022-09-25 | 2022-09-25 |  |  | تأخرصرف المستحقات المالية |  | 43.5201 | 17.6578 | مسحوب | No
2100010393 | وزارة الموارد البشرية والتنمية الإجتماعية | تشييد | ذات اولوية منخفضة | 9482788.71 | 474139.4355 | 175963.49 | 175963.49 | 4031034191 | لا | 0 | 181109278639 | فسخ العقد | الكميات التي تم تركيبها | 2 | 100 | 2015-08-06 | 2017-07-14 | 2021-01-13 | 2021-01-13 |  |  | عدم وجود مبالغ في البنود تغطي الأعمال المرصودة |  | 39.8642 | 21.3595 | مسحوب | No
2100003776 | وزارة الصحة / القريات | ترميم | ذات اولوية متوسطة | 2999950 | 149997.5 | 2065025.48 | 1613300 | 2050068940 | لا | 0 | 190709007299 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-03-04 | 2019-06-01 | 2021-04-07 | 2021-04-07 | 2019-06-01 |  | ضعف كفاءة المقاول الفنية |  | 37.3648 | 31.331 | منجز | No
2100102384 | وزارة التجارة | دراسة الجدوى | ذات اولوية عالية | 2491768 | 124588.4 | 1900937.63 | 1900937.63 | 1010348048 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 70 | 80 | 2019-02-20 | 2021-02-20 | 2022-02-02 | 2022-02-02 |  |  | اخرى |  |  |  | خدمات عامة | No
2100083473 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 33774470 | 1688723.5 | 29509950.88 | 29509950.88 | 1010069549 | لا | 0 | 181101369602 | جاري | الكميات التي تم تركيبها | 90 | 98 | 2018-06-24 | 2020-06-13 | 2022-12-31 | 2022-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 41.7622 | 27.5436 | متأخر | No
2100078680 | أمانة / الرياض | دراسات هندسية | ذات اولوية متوسطة | 7884000 | 394200 | 7884000 | 7884000 | 1010326466 | لا | 0 |  | منجز – استلام نهائي | التكلفة المفوترة | 100 | 100 | 2018-03-22 | 2020-03-11 | 2020-03-11 | 2020-03-11 |  | 2020-03-11 | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  |  |  | منجز | No
2100108732 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | تشييد | ذات اولوية عالية | 187476983.37 | 9373849.1685 | 157355161.96 | 157355161.96 | 1010233574 | لا | 0 | 180063764037 | جاري | تكلفة العمل المنجز | 90.7 | 100 | 2013-07-15 | 2015-12-31 | 2023-08-21 | 2023-08-21 |  |  | ضعف كفاءة المقاول الفنية |  | 42.7302 | 18.3003 | Failed | No
2100078190 | جامعة شقراء | تشييد | ذات اولوية عالية | 84323641.46 | 4216182.073 | 57481340.61 | 57481340.61 | 1010003091 | لا | 0 | 200309003858 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2011-06-08 | 2013-05-28 | 2018-07-13 | 2018-07-13 |  |  |  |  | 45.1448 | 25.1748 | Failed | No
2100023181 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 7759132.92 | 387956.646 | 631304.49 | 0 | 5950007285 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 8 | 100 | 2013-09-17 | 2015-09-07 | 2023-02-01 | 2023-02-01 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.5429 | 16.8808 | مسحوب | Yes
2100023262 | وزارة التعليم | تشييد | ذات اولوية عالية | 2570898.968 | 128544.9484 | 1491287.5 | 1481689.14 | 2050018834 | لا | 0 |  | مسحوب | التكلفة المفوترة | 65.38 | 100 | 2015-04-05 | 2016-03-30 | 2023-02-03 | 2023-02-03 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.1677 | 21.5008 | مسحوب | No
2100100203 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البرية | تشييد | ذات اولوية متوسطة | 1469117 | 73455.85 | 1445849 | 1445849 | 2511102993 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2020-08-16 | 2021-05-15 | 2022-01-31 | 2022-01-31 | 2021-05-15 |  | لا يوجد تأخير |  | 50.0481 | 26.4406 | منجز | No
2100079796 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية عالية | 29787185 | 1489359.25 | 29787135.8 | 29787135.8 | 5855015373 | لا | 0 | 190201003397 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-04-10 | 2021-09-12 | 2021-04-14 | 2021-04-14 | 2021-09-12 |  | لا يوجد تأخير |  | 42.7302 | 18.3003 | منجز | No
2100055720 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية متوسطة | 67178050.44 | 3358902.522 | 67178050.44 | 54827973.71 | 4030159937 | لا | 0 | 180709034972 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2013-10-29 | 2015-10-07 | 2020-02-16 | 2020-02-16 | 2015-10-07 |  | لا يوجد تأخير |  | 42.4989 | 18.2169 | منجز | No
2100059603 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية عالية | 21390303 | 1069515.15 | 21390303 | 21390303 | 5850022870 | لا | 0 | 181201479571 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 99.92 | 2019-02-11 | 2021-01-19 | 2021-04-08 | 2021-04-08 | 2021-01-19 |  | لا يوجد تأخير |  | 42.4989 | 18.2169 | منجز | No
2100100026 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 24133536 | 1206676.8 | 24061113.43 | 24061113.43 | 2050060197 | لا | 0 | 180201000198 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99.7 | 100 | 2018-10-01 | 2020-09-09 | 2021-05-10 | 2021-05-10 | 2020-09-09 |  | لا يوجد تأخير |  | 48.5068 | 27.4649 | منجز | No
2100024614 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2500778 | 125038.9 | 2238605.772 | 0 | 1116001509 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 94.24 | 100 | 2015-09-29 | 2017-02-07 | 2017-02-08 | 2017-02-08 | 2017-02-07 |  |  |  | 44.3253 | 24.4947 | منجز | Yes
2100001540 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية عالية | 203884859.9 | 10194242.995 | 112429426.86 | 110324291.84 | 1010014477 | لا | 0 | 180909072514 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 98.5 | 100 | 2014-04-28 | 2017-03-27 | 2022-08-30 | 2022-08-30 |  |  | لا يوجد تأخير |  | 36.0922 | 28.9155 | Failed | No
2100079354 | جامعة الملك سعود | تشييد | ذات اولوية عالية | 30929860 | 1546493 | 3973767.15 | 3973767.15 | 1010090071 | لا | 0 | 200709016598 | جاري | تكلفة العمل المنجز | 28 | 96 | 2018-01-25 | 2022-01-25 | 2023-04-13 | 2023-04-13 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 46.7098 | 24.6275 | Failed | No
2100040736 | وزارة الصحة / ديوان الوزارة | تشييد | ذات اولوية عالية | 312043145.29 | 15602157.2645 | 63095490.59 | 63095490.59 | 1010032384 | لا | 0 | 181109241937 | جاري | تكلفة العمل المنجز | 43.1 | 89.27 | 2015-03-11 | 2019-01-25 | 2023-12-06 | 2023-12-06 |  |  | ضعف كفاءة المقاول الفنية |  | 44.0064 | 26.0134 | Failed | No
2100024382 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 6453297 | 322664.85 | 0 | 0 | 1010183010 | لا | 0 | 190309008237 | ايقاف كلي | التكلفة المفوترة | 0 | 100 | 2015-01-21 | 2016-10-12 | 2023-02-02 | 2023-02-02 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.0529 | 18.5228 | Failed | No
2100004071 | وزارة المالية | تصميم | ذات اولوية متوسطة | 3328000 | 166400 | 2496000 | 2496000 | 1010304791 | لا | 0 | 181109353543 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-10-24 | 2019-01-19 | 2022-12-25 | 2022-12-25 |  |  | التنسيق مع أصحاب المصلحه (خدمات |  | 46.7063 | 24.7013 | منتظم | No
2100004001 | جامعة الجوف | تشييد | ذات اولوية عالية | 130000000 | 6500000 | 94284699.4 | 94284699.4 | 1010122914 | لا | 0 | 181209452145 | جاري | تكلفة العمل المنجز | 100 | 100 | 2012-09-18 | 2021-03-22 | 2021-12-05 | 2021-12-05 |  |  | تأخرصرف المستحقات المالية |  | 40.0614 | 29.8014 | متأخر | No
2100061725 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 50859715 | 2542985.75 | 36851270.2 | 36851270.2 | 1010090968 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 87.33 | 100 | 2015-09-30 | 2016-09-18 | 2022-06-10 | 2022-06-10 |  |  | اخرى |  | 39.142 | 21.7403 | Failed | No
2100004255 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 88150807.08 | 4407540.354 | 88359597.41 | 88359597.41 | 1010120626 | لا | 0 | 180809049192 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-02-19 | 2020-08-17 | 2022-07-31 | 2022-07-31 | 2020-08-17 |  | لا يوجد تأخير |  | 49.6626 | 27.0037 | منجز | No
2100015901 | وزارة الصحة / جازان | تشييد | ذات اولوية متوسطة | 10863952 | 543197.6 | 12077351.55 | 2399685.29 | 1010172403 | لا | 0 | 181009139628 | جاري | تكلفة العمل المنجز | 95 | 100 | 2015-05-03 | 2017-05-03 | 2021-11-08 | 2021-11-08 |  |  | تأخرصرف المستحقات المالية |  | 43.0541 | 17.1283 | Failed | No
2100004782 | وكالة / الإسكان | تشييد | ذات اولوية متوسطة | 90673581.76 | 4533679.088 | 41398578.7 | 31919664.7 | 5855000147 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 77 | 100 | 2019-09-18 | 2020-12-11 | 2023-03-31 | 2023-03-31 |  |  | أوامر تغيير | أخرى |  |  | متأخر | No
2100077781 | الهيئة العامة للموانئ | تشييد | ذات اولوية عالية | 1447085 | 72354.25 | 1352404.47 | 1180836.9 | 2050048843 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 98 | 100 | 2019-12-02 | 2021-01-27 | 2021-12-10 | 2021-12-10 | 2017-03-01 |  | اخرى |  | 49.6575 | 27.0764 | منجز | No
2100079170 | وزارة التعليم | تشييد | ذات اولوية عالية | 2906273.25 | 145313.6625 | 143355 | 143355 | 1010229957 | لا | 0 |  | جاري | التكلفة المفوترة | 5 | 100 | 2012-12-18 | 2014-02-12 | 2022-12-01 | 2022-12-01 |  |  | ضعف كفاءة المقاول الفنية |  | 45.313 | 24.0763 | Failed | No
2100040574 | وزارة الموارد البشرية والتنمية الإجتماعية | إشراف | ذات اولوية منخفضة | 919749.69 | 45987.4845 | 919749.69 | 919749.69 | 1010328167 | لا | 0 | 190309006754 | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2015-04-20 | 2017-10-25 | 2021-12-22 | 2021-12-22 | 2017-10-25 |  | ضعف كفاءة المقاول الفنية |  | 44.4516 | 17.6376 | منجز | No
2100005213 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 10169236.61 | 508461.8305 | 8067066.71 | 8067066.71 | 1013000078 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-04-03 | 2019-12-29 | 2020-02-12 | 2020-02-12 | 2019-12-29 |  | أوامر تغيير | أخرى |  |  | منجز | No
2100107376 | وزارة التعليم | تشييد | ذات اولوية عالية | 13832395.08 | 691619.754 | 9953771 | 8988782 | 1132002624 | لا | 0 | 190309000201 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2013-08-20 | 2015-08-10 | 2023-02-08 | 2023-02-08 | 2015-08-10 |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | منجز | No
2100001584 | جامعة الإمام محمد بن سعود الاسلامية | تشييد | ذات اولوية متوسطة | 35816568 | 1790828.4 | 26287789.4062 | 13789035.59 | 1010020305 | لا | 0 | 180709033680 | جاري | اخرى | 90 | 97 | 2017-11-26 | 2021-05-26 | 2023-12-31 | 2023-12-31 |  |  | تأخرصرف المستحقات المالية |  | 46.7098 | 24.812 | متأخر | No
2100101905 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 182194559.95 | 9109727.9975 | 108822113.07 | 108822113.07 | 2055002293 | لا | 0 | 180809058638 | جاري | منهجية القيمة المكتسبة | 58 | 100 | 2015-03-12 | 2017-09-07 | 2024-12-26 | 2024-12-26 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 49.5648 | 27.1019 | Failed | No
2100045942 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 4994850 | 249742.5 | 3170855.38 | 3170855.38 | 4031045075 | لا | 0 | 191101177856 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-10-15 | 2020-10-09 | 2020-10-09 | 2020-10-09 | 2020-10-09 |  |  |  | 40.4086 | 21.2883 | منجز | No
2100023380 | رئاسة أمن الدولة / قوات الأمن الخاصة | تشييد | ذات اولوية عالية وعاجلة | 49409440.08 | 2470472.004 | 50373797.25 | 50373797.25 | 1010188861 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-10-15 | 2021-09-24 | 2022-08-25 | 2022-08-25 | 2021-09-24 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 46.5681 | 24.8782 | منجز | No
2100050326 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 1444123 | 72206.15 | 0 | 0 | 4030181480 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 0 | 0 | 2015-12-05 | 2016-11-29 | 2021-04-03 | 2021-04-03 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5882 | 28.3958 | مسحوب | No
2100055101 | وزارة الخارجية | تشييد | ذات اولوية عالية | 124004355.825 | 6200217.7913 | 4474827.6 | 4474827.6 | 0 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 4 | 99 | 2017-10-25 | 2020-01-23 | 2020-01-25 | 2020-01-25 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 15.0432 | 12.115 | مسحوب | No
2100007173 | وزارة الخارجية | تشييد | ذات اولوية عالية | 75108499.5375 | 3755424.9769 | 6688500 | 6688500 | 1010308838 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 9 | 100 | 2015-06-01 | 2017-06-30 | 2020-04-14 | 2020-04-14 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | -15.9503 | 18.029 | مسحوب | No
2100048171 | شركة المياه الوطنية / منطقة جازان | إشراف | ذات اولوية عالية وعاجلة | 3480000 | 174000 | 3480000 | 3480000 | 4650061777 | لا | 0 |  | جاري | التكلفة المفوترة | 100 | 100 | 2014-12-31 | 2016-12-30 | 2022-03-30 | 2022-03-30 |  |  | لا يوجد تأخير |  | 43.2184 | 16.7812 | خدمات عامة | No
2100082563 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 1069100 | 53455 | 870350 | 870350 | 3350014288 | لا | 0 | 200501033493 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 81 | 100 | 2019-01-27 | 2019-09-24 | 2021-04-26 | 2021-04-26 | 2019-09-24 |  | ضعف كفاءة المقاول الفنية |  | 42.4135 | 27.8869 | منجز | No
2100085934 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 22514590.07 | 1125729.5035 | 0 | 0 | 1010142553 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 1 | 100 | 2015-08-17 | 2018-02-13 | 2018-02-13 | 2018-02-13 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 46.7098 | 24.6275 | مسحوب | No
2100073264 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 28100000 | 1405000 | 23364036.93 | 23364036.93 | 1010074764 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 95.04 | 100 | 2014-06-23 | 2017-05-21 | 2017-05-17 | 2017-05-17 | 2017-05-21 |  | لا يوجد تأخير |  | 49.6627 | 26.9912 | منجز | No
2100040132 | هيئة الهلال الأحمر السعودي | تشييد | ذات اولوية عالية | 12528192.6 | 626409.63 | 10165469.12 | 10165469.12 | 1010239020 | لا | 0 | 190709064775 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 100 | 2019-09-15 | 2022-05-25 | 2022-09-01 | 2022-09-01 | 2022-05-25 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.1374 | 21.7614 | منجز | No
2100084825 | هيئة الهلال الأحمر السعودي | تشييد | ذات اولوية عالية | 10699700 | 534985 | 7678339.31 | 7678339.31 | 5858023576 | لا | 0 | 190401000256 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 100 | 2020-02-23 | 2022-07-07 | 2022-10-01 | 2022-10-01 | 2022-07-07 |  | تصاريح أعمال التنفيذ |  | 39.7035 | 24.5215 | منجز | No
2100090683 | جامعة جازان | تشييد | ذات اولوية عالية وعاجلة | 18286000 | 914300 | 16456200 | 16456200 | 1010185891 | لا | 0 | 181109298272 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-12-29 | 2016-06-29 | 2018-09-16 | 2018-09-16 | 2016-06-29 |  | لا يوجد تأخير |  | 42.6189 | 16.9323 | منجز | No
2100052673 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 1823393 | 91169.65 | 690759 | 690759 | 7008415775 | لا | 0 | 191001266626 | مسحوب | الكميات التي تم تركيبها | 38.8 | 80 | 2018-12-29 | 2019-12-25 | 2021-06-13 | 2021-06-13 |  |  | ضعف كفاءة المقاول الفنية |  | 42.4181 | 27.8836 | مسحوب | No
2100007125 | وزارة الخارجية | تشييد | لم تعد تحتاجها الجهة | 82295874 | 4114793.7 | 58486069.13 | 58486069.13 | 0 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 85 | 100 | 2015-02-16 | 2017-02-15 | 2017-08-09 | 2017-08-09 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | -0.19272 | 5.6104 | مسحوب | No
2100067911 | وزارة الخارجية | تشييد | ذات اولوية عالية وعاجلة | 51907428 | 2595371.4 | 37817799.2 | 37817799.2 | 0 | لا | 0 |  | جاري | تكلفة العمل المنجز | 85 | 100 | 2019-01-08 | 2020-09-08 | 2021-08-03 | 2021-08-03 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 32.5867 | 0.3154 | Failed | No
2100093063 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 1298810 | 64940.5 | 1079540 | 1079540 | 3357011509 | لا | 0 | 181209460228 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 98 | 100 | 2018-06-24 | 2019-06-19 | 2020-07-12 | 2020-07-12 | 2019-06-19 |  | ضعف كفاءة المقاول الفنية |  | 42.4135 | 27.8869 | منجز | No
2100021755 | جامعة الإمام محمد بن سعود الاسلامية | دراسة الجدوى | ذات اولوية عالية | 8694683.996 | 434734.1998 | 7887139.9248 | 7841939.5749 | 1010078921 | لا | 0 | 180909094731 | جاري | اخرى | 97 | 100 | 2012-08-25 | 2013-08-14 | 2023-02-28 | 2023-02-28 |  |  | تغيرات في نطاق المشروع |  | 46.705 | 24.8105 | خدمات عامة | No
2200223392 | وزارة البيئة والمياة والزراعة | تحديث وتوريد | ذات اولوية متوسطة | 963915 | 48195.75 | 963915 | 963915 | 1010246223 | لا | 0 | 190601057612 | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2019-08-20 | 2020-04-21 | 2020-04-21 | 2020-04-21 | 2020-04-21 |  |  |  | 46.7777 | 25.2963 | منجز | No
2100038975 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 19398750 | 969937.5 | 17458875 | 17458875 | 4031019772 | لا | 0 |  | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2019-06-16 | 2019-12-10 | 2020-01-24 | 2020-01-24 |  | 2019-12-10 |  |  | 39.8616 | 21.3968 | منجز | No
2100088244 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1972397 | 98619.85 | 1582425 | 1582425 | 1155000117 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 93 | 2019-06-17 | 2020-06-11 | 2022-02-25 | 2022-02-25 | 2020-06-11 |  | اخرى |  | 45.2591 | 25.2379 | منجز | No
2100025653 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 10282000 | 514100 | 4696529 | 4696529 | 1010082460 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-09-17 | 2020-09-17 | 2023-02-20 | 2023-02-20 | 2020-09-17 |  | ضعف كفاءة المقاول الفنية |  | 43.5207 | 29.6315 | منجز | No
2100028814 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 425453 | 21272.65 | 398050 | 398050 | 3550032522 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-12-02 | 2016-11-26 | 2021-01-17 | 2021-01-17 | 2016-11-26 |  | ضعف كفاءة المقاول الفنية |  | 36.5899 | 28.3921 | منجز | No
2100030100 | أمانة / تبوك | تشييد | لم تعد تحتاجها الجهة | 1450333.7 | 72516.685 | 1261444 | 1261444 | 1010167015 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-11-18 | 2015-11-18 | 2016-08-20 | 2016-08-20 | 2015-11-18 |  | اخرى |  | 37.6847 | 28.3938 | منجز | No
2100026913 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 6996605.4 | 349830.27 | 0 | 0 | 2251033167 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 22 | 100 | 2008-05-10 | 2009-12-20 | 2023-02-01 | 2023-02-01 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.5429 | 16.8808 | مسحوب | No
2100034661 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 10260328 | 513016.4 | 10260328 | 10260328 | 2251032617 | لا | 0 | 190209008692 | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2015-11-02 | 2017-10-22 | 2017-10-21 | 2017-10-21 | 2017-10-22 | 2021-08-29 |  |  | 49.7215 | 25.3769 | منجز | No
2100061504 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية وعاجلة | 70152298.68 | 3507614.934 | 13976509.49 | 8100707.33 | 1010219753 | لا | 0 | 190901085212 | جاري | منهجية القيمة المكتسبة | 41.31 | 47.96 | 2020-03-15 | 2022-08-18 | 2023-12-31 | 2023-12-31 |  |  | اخرى |  | 43.9821 | 26.3067 | متأخر | No
2100076510 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 1285250 | 64262.5 | 1285250 | 1285250 | 3555000942 | لا | 0 | 190309004536 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-12-02 | 2019-09-24 | 2019-09-24 | 2019-09-24 | 2019-09-24 |  | اخرى |  | 35.7243 | 27.3457 | منجز | No
2100031452 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 299259 | 14962.95 | 299259 | 299259 | 4700010229 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-12-10 | 2019-12-05 | 2019-12-01 | 2019-12-01 | 2019-12-05 |  |  |  | 36.5182 | 28.4328 | منجز | No
2100098910 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 12769699.64 | 638484.982 | 0.02 | 0.02 | 4031020518 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 68 | 100 | 2010-01-10 | 2012-01-10 | 2018-11-07 | 2018-11-07 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.836 | 21.4408 | مسحوب | No
2200223230 | أمانة / جدة | تشييد | ذات اولوية عالية | 362337925 | 18116896.25 | 19346480.9 | 19346480.9 | 1010026934 | لا | 0 | 220101010136 | جاري | الكميات التي تم تركيبها | 16 | 20 | 2022-03-13 | 2025-02-07 | 2025-02-07 | 2025-02-07 |  |  |  |  | 39.137 | 21.7964 | منتظم | No
2100034602 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 2749706.3 | 137485.315 | 1703090 | 1703090 | 3550027826 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 62 | 62 | 2014-08-16 | 2015-08-16 | 2020-05-02 | 2020-05-02 |  |  | اخرى |  | 37.715 | 28.3858 | مسحوب | No
2100030881 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 4347980 | 217399 | 0 | 0 | 1010156220 | نعم | 1 |  | مسحوب | تكلفة العمل المنجز | 1 | 100 | 2015-10-17 | 2016-10-11 | 2020-09-20 | 2020-09-20 |  |  | ضعف كفاءة المقاول الفنية |  | 35.0215 | 28.4937 | مسحوب | No
2100062392 | أمانة / تبوك | تشييد | ذات اولوية عالية | 499850 | 24992.5 | 256553 | 256553 | 3550027826 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 74 | 100 | 2013-02-04 | 2014-01-04 | 2020-06-15 | 2020-06-15 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5228 | 28.4275 | مسحوب | No
2100062882 | أمانة / تبوك | تشييد | ذات اولوية عالية | 1790700 | 89535 | 385625 | 385625 | 4030212516 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 50 | 100 | 2018-12-08 | 2019-12-03 | 2021-06-01 | 2021-06-01 |  |  | ضعف كفاءة المقاول الفنية |  | 36.4689 | 26.2366 | مسحوب | No
2100030310 | أمانة / تبوك | تشييد | ذات اولوية عالية | 1270000 | 63500 | 1270000 | 1270000 | 4650020357 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 66 | 66 | 2014-09-12 | 2015-09-11 | 2015-11-20 | 2015-11-20 |  |  | ضعف كفاءة المقاول الفنية |  | 37.187 | 27.0479 | مسحوب | No
2100035442 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 500000 | 25000 | 234281.46 | 234281.46 | 3555000942 | لا | 0 | 191001217502 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-08-03 | 2019-12-01 | 2019-12-02 | 2019-12-02 | 2019-12-01 |  | التنسيق مع أصحاب المصلحه (خدمات |  | 35.6976 | 27.3441 | منجز | No
2100054961 | أمانة / تبوك | تشييد | ذات اولوية عالية | 29414997.72 | 1470749.886 | 23287798 | 21371571 | 3555000709 | لا | 0 | 181009135030 | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 98 | 100 | 2014-09-19 | 2019-01-04 | 2021-09-01 | 2021-09-01 |  |  |  |  | 36.5682 | 28.3911 | متأخر | No
2100068261 | أمانة / تبوك | تشييد | ذات اولوية عالية | 28500000 | 1425000 | 28275912.87 | 25649309.98 | 1010006004 | لا | 0 | 190309095708 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-10-18 | 2017-08-07 | 2021-05-30 | 2021-05-30 | 2017-08-07 |  | ضعف كفاءة المقاول الفنية |  | 36.5777 | 28.4145 | منجز | No
2100068784 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 430950 | 21547.5 | 430950 | 430950 | 3550023552 | لا | 0 | 190509000533 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-02-24 | 2019-10-22 | 2019-12-21 | 2019-12-21 | 2019-10-22 |  | اخرى |  | 36.5593 | 28.3964 | منجز | No
2100067071 | أمانة / تبوك | تشييد | ذات اولوية عالية | 20999640 | 1049982 | 17263804 | 17263804 | 4030131706 | لا | 0 | 181201397800 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-01-27 | 2021-05-16 | 2021-05-16 | 2021-05-16 | 2021-05-16 |  | ضعف كفاءة المقاول الفنية |  | 36.5352 | 28.4108 | منجز | No
2100091431 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 4655000 | 232750 | 4189499.6 | 4189499.6 | 1010064626 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-10-14 | 2020-12-30 | 2020-12-01 | 2020-12-01 | 2020-12-30 |  | اخرى |  | 37.2627 | 25.0292 | منجز | No
2100063663 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 30981073.23 | 1549053.6615 | 26600349 | 25595014 | 3555000709 | لا | 0 |  | جاري | تكلفة العمل المنجز | 83 | 91 | 2019-01-28 | 2022-07-05 | 2022-07-05 | 2022-07-05 |  |  | التنسيق مع أصحاب المصلحه (خدمات |  | 39.5352 | 24.5202 | متأخر | No
2200223241 | أمانة / جدة | تشييد | ذات اولوية عالية | 114292313 | 5714615.65 | 13571900 | 10225628.9 | 1010026934 | لا | 0 | 211101101637 | جاري | الكميات التي تم تركيبها | 36 | 36 | 2022-03-13 | 2024-08-14 | 2024-08-14 | 2024-08-14 |  |  |  |  | 39.2958 | 21.4068 | منتظم | No
2100043050 | وزارة التعليم | تشييد | ذات اولوية عالية | 9001622.7 | 450081.135 | 460290.6 | 0 | 1010223860 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 6.41 | 100 | 2013-11-26 | 2015-08-18 | 2018-08-12 | 2018-08-12 |  |  | ضعف كفاءة المقاول الفنية |  | 42.6509 | 17.1567 | مسحوب | Yes
2100028615 | وزارة الثقافة | مساحة |  | 7387200 | 369360 | 4924800 | 4924800 | 0 |  | 0 |  | جاري | مدفوعات ساعات العمل | 75 | 75 | 2017-09-10 00:59 | 2021-09-09 00:59 | 2021-09-09 | 2021-09-09 | [6 empty] | خدمات عامة | No
2100101953 | مدينة الملك سعود الطبية | تشييد |  | 60208251 | 3010412.55 | 0 | 0 | 1010219933 |  | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 0 | 100 | 2020-04-29 00:59 | 2022-04-29 00:59 |  |  |  |  | اخرى |  | 46.6906 | 24.6282 | Failed | No
2100005666 | أمانة / العاصمة المقدسة | دراسة بيئية | ذات اولوية متوسطة | 982800 | 49140 | 928746 | 928746 | 4031085958 | لا | 0 | 181209459395 | منجز – استلام نهائي | مدفوعات ساعات العمل | 93.33 | 93.33 | 2018-06-03 | 2020-06-02 | 2020-06-02 | 2020-06-02 | 2020-06-02 | 2020-12-09 | اخرى |  |  |  | منجز | No
2100107586 | جامعة الأمير سطام بن عبدالعزيز | تشييد | ذات اولوية عالية | 978075 | 48903.75 | 380363 | 380363 | 1011008904 | لا | 0 | 200101044763 | ايقاف كلي | تكلفة العمل المنجز | 50 | 100 | 2019-12-15 | 2020-06-12 | 2023-01-01 | 2023-01-01 |  |  | اخرى |  | 47.2733 | 24.1626 | Failed | No
2100066463 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 1132200 | 56610 | 442500 | 442500 | 5901028271 | لا | 0 | 180909111240 | مسحوب | اخرى | 39 | 100 | 2015-07-21 | 2016-05-16 | 2019-07-28 | 2019-07-28 |  |  | تأخرصرف المستحقات المالية |  | 43.058 | 17.0391 | مسحوب | No
2100106363 | وزارة التعليم | تشييد | ذات اولوية عالية | 26002264.85 | 1300113.2425 | 20252758.19 | 20252758.19 | 1010099661 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 98 | 100 | 2013-12-01 | 2016-05-19 | 2021-05-26 | 2021-05-26 | 2016-05-19 |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | منجز | No
2100052183 | أمانة / تبوك | تشييد | ذات اولوية عالية | 39914656.71 | 1995732.8355 | 39914656.71 | 35879284 | 1010262459 | لا | 0 | 18100132020 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-07-07 | 2016-12-28 | 2019-11-30 | 2019-11-30 | 2016-12-28 |  | اخرى |  | 36.5911 | 28.4019 | منجز | No
2100027904 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 16620152 | 831007.6 | 0 | 0 | 4653000436 | لا | 0 | 190601015253 | جاري | الكميات التي تم تركيبها | 8 | 100 | 2022-11-01 | 2024-10-10 | 2024-10-10 | 2024-10-10 |  |  | اخرى |  | 40.8787 | 25.9809 | Failed | No
2100006672 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية وعاجلة | 39680500 | 1984025 | 35864934.76 | 34093535 | 1131009235 | لا | 0 | 180801053848 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-12-11 | 2020-11-19 | 2022-01-30 | 2022-01-30 | 2020-11-19 |  | لا يوجد تأخير |  | 43.9553 | 26.3508 | منجز | No
2100106525 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 15951861.06 | 797593.053 | 0 | 0 | 1010142553 | لا | 0 |  | مسحوب | التكلفة المفوترة | 8 | 100 | 2016-05-26 | 2018-02-15 | 2021-01-31 | 2021-01-31 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | مسحوب | No
2100011480 | أمانة / تبوك | تشييد | ذات اولوية عالية | 18981119.23 | 949055.9615 | 13386000 | 13386000 | 1010214056 | لا | 0 | 181209445289 | جاري | تكلفة العمل المنجز | 83 | 100 | 2015-09-06 | 2017-03-07 | 2023-05-09 | 2023-05-09 |  |  | ضعف كفاءة المقاول الفنية |  | 38.5165 | 27.6122 | متأخر | No
2100069414 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 5253600 | 262680 | 4255198.5 | 1954136.36 | 5800000059 | لا | 0 | 181109320160 | جاري | تكلفة العمل المنجز | 92 | 96.12 | 2014-05-25 | 2015-11-08 | 2023-05-20 | 2023-05-20 |  |  | ضعف كفاءة المقاول الفنية |  | 41.4543 | 20.0033 | منتظم | No
2100090742 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 52529988 | 2626499.4 | 52529988 | 52529988 | 4030150094 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-11-27 | 2025-08-21 | 2025-08-21 | 2025-08-21 | 2025-08-21 |  | ضعف كفاءة المقاول الفنية |  | 39.5758 | 24.4479 | منجز | No
2100076506 | أمانة / تبوك | تشييد | ذات اولوية عالية | 1757682 | 87884.1 | 1581914 | 1580092.2 | 1010055791 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-10-21 | 2016-10-21 | 2018-03-12 | 2018-03-12 | 2016-10-21 |  | اخرى |  | 36.5739 | 28.4338 | منجز | No
2100084442 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 2856470.63 | 142823.5315 | 2856470.63 | 0 | 5806007439 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2016-02-01 | 2017-01-20 | 2020-03-15 | 2020-03-15 | 2017-01-20 |  | ضعف كفاءة المقاول الفنية |  | 41.4672 | 20.007 | منجز | Yes
2100060056 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية وعاجلة | 80359142.78 | 4017957.139 | 43923431.33 | 27592881.87 | 1128000011 | لا | 0 | 180701029303 | جاري | منهجية القيمة المكتسبة | 68.5 | 88 | 2018-09-18 | 2021-08-16 | 2023-01-31 | 2023-01-31 |  |  | اخرى |  | 44.0054 | 26.2857 | متأخر | No
2100073334 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية وعاجلة | 54042062.99 | 2702103.1495 | 44992477.4 | 38833312.4 | 4030159937 | لا | 0 | 180709021048 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2015-02-12 | 2018-01-10 | 2021-08-01 | 2021-08-01 | 2018-01-10 |  | ضعف كفاءة المقاول الفنية |  | 41.4374 | 19.7864 | منجز | No
2100109200 | وزارة التعليم | تشييد | ذات اولوية عالية | 12181568 | 609078.4 | 6412262.97 | 5755041.58 | 1123000700 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2012-11-09 | 2014-10-30 | 2019-07-15 | 2019-07-15 | 2014-10-30 |  | ضعف كفاءة المقاول الفنية |  | 45.3525 | 25.8912 | منجز | No
2100003485 | هيئة الهلال الأحمر السعودي | تشييد | ذات اولوية عالية | 823725 | 41186.25 | 376649.47 | 376649.47 | 1010175017 | لا | 0 | 181009157539 | مسحوب | الكميات التي تم تركيبها | 35 | 100 | 2017-08-20 | 2017-09-20 | 2020-03-09 | 2020-03-09 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 40.3189 | 28.7014 | مسحوب | No
2100090521 | أمانة / تبوك | تشييد | ذات اولوية عالية وعاجلة | 6347500 | 317375 | 344990 | 344990 | 3450009076 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 6 | 6 | 2014-11-12 | 2015-07-06 | 2021-04-20 | 2021-04-20 |  |  | ضعف كفاءة المقاول الفنية |  | 36.533 | 28.3951 | مسحوب | No
2100005504 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 56803403 | 2840170.15 | 2348000 | 2348000 | 1116002219 | لا | 0 | 190501071765 | جاري | منهجية القيمة المكتسبة | 68.6 | 90.98 | 2019-10-20 | 2022-09-17 | 2023-02-23 | 2023-02-23 |  |  | اخرى |  | 41.0886 | 19.1437 | متأخر | No
2100005390 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية وعاجلة | 157555451 | 7877772.55 | 0 | 0 | 4030004451 | لا | 0 |  | مسحوب | منهجية القيمة المكتسبة | 0 | 100 | 2011-11-20 | 2014-10-15 | 2014-10-18 | 2014-10-18 |  |  | ضعف كفاءة المقاول الفنية |  | 42.8338 | 16.9633 | مسحوب | No
2100030181 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 1977295 | 98864.75 | 1500000 | 1500000 | 5950024761 | لا | 0 | 181209477572 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 86 | 91 | 2014-08-30 | 2016-08-08 | 2022-11-20 | 2022-11-20 | 2016-08-08 |  | ضعف كفاءة المقاول الفنية |  | 44.2441 | 17.5445 | منجز | No
2100097646 | وزارة السياحة | تشييد |  | 14603919.75 | 730195.9875 | 1091944.15 | 1091944.15 | 1010039430 |  | 0 |  | جاري | منهجية القيمة المكتسبة | 48 | 100 | 2019-04-08 00:59 | 2020-04-07 00:59 | 2020-04-07 | 2020-04-07 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  |  |  | Failed | No
2100022223 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 26754100 | 1337705 | 18354988.7 | 18354988.7 | 5855021168 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 80.85 | 100 | 2020-06-21 | 2022-05-30 | 2022-07-31 | 2022-07-31 |  |  | اخرى |  | 41.0506 | 19.5338 | متأخر | No
2100090263 | شركة المياه الوطنية / منطقة نجران | تشييد | ذات اولوية عالية | 19130131.35 | 956506.5675 | 17863574.67 | 17863574.67 | 5950004276 | لا | 0 | 180201000119 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-04-23 | 2020-03-31 | 2021-01-11 | 2021-01-11 | 2020-03-31 |  | لا يوجد تأخير |  | 44.2341 | 17.5757 | منجز | No
2100031172 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 4055144 | 202757.2 | 3513998.7 | 3158184 | 5857031865 | لا | 0 | 190909006115 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-07-22 | 2017-01-12 | 2021-12-15 | 2021-12-15 | 2017-01-12 |  | ضعف كفاءة المقاول الفنية |  | 41.0859 | 19.1571 | منجز | No
2100046686 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | تشييد | ذات اولوية متوسطة | 49682614.68 | 2484130.734 | 27201671.33 | 27201671.33 | 1010191039 | لا | 0 | 180601011990 | جاري | تكلفة العمل المنجز | 60 | 100 | 2018-11-07 | 2022-08-20 | 2022-08-20 | 2022-08-20 |  |  | تأخرصرف المستحقات المالية |  | 46.7098 | 24.6275 | Failed | No
2100083856 | معهد الإدارة العامة | تشييد | ذات اولوية عالية وعاجلة | 128403537 | 6420176.85 | 6486891 | 6486891 | 1010006362 | نعم | 6486891 | 181009120932 | ايقاف كلي | التكلفة المفوترة | 5 | 99 | 2014-08-17 | 2017-01-18 | 2025-09-30 | 2025-09-30 |  |  | اخرى |  | 50.1173 | 26.4273 | Failed | No
2100192544 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 8335338.76 | 416766.938 | 7075155.85 | 7075155.85 | 4030164404 | لا | 0 | 190801094217 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-01-19 | 2020-07-15 | 2022-12-31 | 2022-12-31 |  |  |  |  | 39.2391 | 21.4933 | متأخر | No
2100192496 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 5581632.52 | 279081.626 | 4697535.13 | 4697535.13 | 1010168729 | لا | 0 | 191001158134 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 99.3 | 100 | 2019-07-30 | 2019-09-13 | 2022-12-31 | 2022-12-31 |  |  |  |  | 39.2391 | 21.4933 | Failed | No
2100087743 | شركة المياه الوطنية | تشييد | ذات اولوية عالية وعاجلة | 173468899 | 8673444.95 | 117853942.13 | 117853942.13 | 1010157933 | لا | 0 | 191101147845 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2012-10-01 | 2015-08-30 | 2020-03-15 | 2020-03-15 | 2015-08-30 |  | لا يوجد تأخير |  | 41.0859 | 19.1571 | منجز | No
2100049416 | جامعة الملك سعود | تشييد | ذات اولوية عالية | 4750000 | 237500 | 1386066 | 842419 | 1010015734 | لا | 0 | 181109295199 | جاري | تكلفة العمل المنجز | 78 | 100 | 2015-05-22 | 2016-05-21 | 2023-03-31 | 2023-03-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 46.7098 | 24.6275 | متأخر | No
2100008562 | وزارة المالية | تشييد | ذات اولوية متوسطة | 18151804.47 | 907590.2235 | 5050304.84 | 5050304.84 | 1010099661 | لا | 0 | 190901171804 | جاري | التكلفة المفوترة | 44 | 90.8 | 2020-08-16 | 2023-04-17 | 2023-04-17 | 2023-04-17 |  |  | لا يوجد تأخير |  | 44.44 | 24.5389 | Failed | No
2100009096 | رئاسة أمن الدولة / المديرية العامة للمباحث | تشييد | ذات اولوية متوسطة | 764137 | 38206.85 | 0 | 0 | 1010413981 | لا | 0 |  | فسخ العقد | منهجية القيمة المكتسبة | 10 | 100 | 2020-03-18 | 2020-06-04 | 2020-06-04 | 2020-06-04 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  |  |  | مسحوب | No
2100069204 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 501800 | 25090 | 501800 | 501800 | 4605002907 | لا | 0 | 181009114808 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-07-02 | 2019-06-12 | 2019-06-12 | 2019-06-12 | 2019-06-12 |  |  |  | 40.988 | 21.0595 | منجز | No
2100069355 | شركة المياه الوطنية / منطقة القصيم | تصميم | ذات اولوية عالية وعاجلة | 23047500 | 1152375 | 1975449.16 | 1975449.16 | 1010282788 | لا | 0 | 191201125163 | مسحوب | تكلفة العمل المنجز | 51 | 100 | 2020-03-02 | 2021-08-15 | 2021-08-15 | 2021-08-15 |  |  | عدم اكتمال أو ضعف أعمال التصميم والدراسات |  | 43.9918 | 26.3566 | مسحوب | No
2100086704 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 103351283 | 5167564.15 | 77638152.26 | 67306220.92 | 1010014477 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 99.9 | 100 | 2013-02-10 | 2016-02-10 | 2020-09-29 | 2020-09-29 |  | 2016-02-10 | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100083602 | معهد الإدارة العامة | تشييد | ذات اولوية عالية وعاجلة | 23548037 | 1177401.85 | 4666918.61 | 4666918.61 | 1010171914 | لا | 0 | 191101193737 | جاري | التكلفة المفوترة | 19 | 40 | 2020-01-02 | 2020-07-02 | 2023-02-02 | 2023-02-02 |  |  |  |  | 39.1554 | 21.601 | متأخر | No
2100096095 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 164440746 | 8222037.3 | 126904960.49 | 126904960.49 | 1010010506 | لا | 0 | 180809058634 | جاري | منهجية القيمة المكتسبة | 98 | 100 | 2014-09-01 | 2016-08-29 | 2023-03-25 | 2023-03-25 |  |  | اخرى |  | 49.5648 | 27.1019 | متأخر | No
2100034075 | المؤسسة العامة للتقاعد | تشييد | ذات اولوية عالية | 5554000 | 277700 | 4221441 | 4221441 | 4030021112 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 95 | 100 | 2019-05-29 | 2021-09-30 | 2021-11-30 | 2021-11-30 |  |  | ضعف كفاءة المقاول الفنية |  | 39.126 | 21.7254 | Failed | No
2100105361 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 26165946.5 | 1308297.325 | 21840081.14 | 21840081.14 | 1010085982 | لا | 0 |  | ايقاف كلي | منهجية القيمة المكتسبة | 92.9 | 100 | 2019-03-04 | 2020-09-04 | 2022-12-25 | 2022-12-25 |  |  | لا يوجد تأخير |  | 46.743 | 24.7283 | Failed | No
2100105254 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 131801195 | 6590059.75 | 73928914 | 73928914 | 5810001890 | لا | 0 | 181101294756 | جاري | منهجية القيمة المكتسبة | 79.7 | 100 | 2019-04-15 | 2022-03-13 | 2023-01-07 | 2023-01-07 |  |  | اخرى |  | 39.0411 | 22.7986 | متأخر | No
2100097252 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية وعاجلة | 50317108.94 | 2515855.447 | 37452757.42 | 36310382.32 | 4650049275 | لا | 0 | 180709028142 | مسحوب | منهجية القيمة المكتسبة | 88.48 | 100 | 2014-08-13 | 2017-07-11 | 2022-05-01 | 2022-05-01 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6695 | 19.8881 | مسحوب | No
2100095900 | مدينة الملك عبدالله الطبية بالعاصمة المقدسة | تشييد | ذات اولوية عالية | 1839033 | 91951.65 | 912534 | 591948 | 4031072592 | لا | 0 | 210309167448 | جاري | الكميات التي تم تركيبها | 33 | 66 | 2019-07-23 | 2022-06-20 | 2024-05-28 | 2024-05-28 |  |  | اخرى |  | 39.8811 | 21.382 | Failed | No
2100104576 | هيئة المدن الصناعية ومناطق التقنية | تشييد | ذات اولوية عالية | 477001136 | 23850056.8 | 327351875 | 327351875 | 2051007339 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 72 | 100 | 2013-07-01 | 2015-06-08 | 2023-09-14 | 2023-09-14 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  |  |  | Failed | No
2100107472 | الهيئة الملكية لمدينة الرياض | تشييد | ذات اولوية عالية | 1381380456.87 | 69069022.8435 | 1336201159.07 | 1336201159.07 | 1010006315 | لا | 0 | 190109010614 | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2017-03-01 | 2018-10-10 | 2021-02-26 | 2021-02-26 | 2018-10-10 |  |  |  | 46.7774 | 24.6053 | منجز | No
2100087463 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 42149548 | 2107477.4 | 35940693.08 | 35940693.08 | 1010090968 | لا | 0 | 200709052696 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 91.665 | 100 | 2018-10-25 | 2020-10-03 | 2021-06-28 | 2021-06-28 | 2020-10-03 |  | اخرى |  | 39.2981 | 21.4294 | منجز | No
2100191483 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 6755712 | 337785.6 | 3746581.7 | 3746581.7 | 2050003475 | لا | 0 | 200709052696 | جاري | منهجية القيمة المكتسبة | 81.97 | 100 | 2021-04-20 | 2022-05-08 | 2022-05-08 | 2022-05-08 |  |  |  |  | 39.3207 | 21.4575 | متأخر | No
2100041580 | وزارة الموارد البشرية والتنمية الإجتماعية | تشييد | ذات اولوية منخفضة | 31960965.9 | 1598048.295 | 31960965.9 | 31960965.9 | 1010188847 | لا | 0 | 180909066685 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2011-09-14 | 2014-08-11 | 2019-03-26 | 2019-03-26 | 2014-08-11 |  | ضعف كفاءة المقاول الفنية |  | 45.996 | 28.382 | منجز | No
2100090672 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 8190315 | 409515.75 | 2795878.2 | 2795878.2 | 5950027418 | لا | 0 | 181209477572 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 53 | 100 | 2019-09-15 | 2020-09-02 | 2022-09-11 | 2022-09-11 | 2020-09-02 |  |  |  | 44.2358 | 17.549 | منجز | No
2100018115 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | دراسات هندسية | ذات اولوية عالية وعاجلة | 14984983 | 749249.15 | 3689144 | 3689144 | 2050107656 | لا | 0 | 180201000203 | جاري | مدفوعات ساعات العمل | 27 | 58 | 2018-10-14 | 2023-10-13 | 2025-12-30 | 2025-12-30 |  |  |  |  | 38.2189 | 24.0104 | خدمات عامة | No
2100054515 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تصميم | ذات اولوية عالية وعاجلة | 65875205 | 3293760.25 | 66185354.61 | 66185354.61 | 1010412691 | لا | 0 | 190509121159 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2010-07-05 | 2015-07-04 | 2020-12-31 | 2020-12-31 | 2015-07-04 |  |  |  | 49.1672 | 27.5093 | منجز | No
2100094883 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 7241814 | 362090.7 | 6372806 | 6372806 | 5857024964 | لا | 0 | 181201394436 | جاري | منهجية القيمة المكتسبة | 81 | 100 | 2018-02-12 | 2020-02-12 | 2023-04-20 | 2023-04-20 |  |  | أوامر تغيير |  | 38.268 | 23.8632 | متأخر | No
2100193314 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 63312368.84 | 3165618.442 | 61380937.67 | 55625267.67 | 4030096631 | لا | 0 | 200209116417 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2011-06-07 | 2013-04-03 | 2021-12-31 | 2021-12-31 |  |  |  |  | 39.239 | 21.4933 | Failed | No
2100053174 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 309000000 | 15450000 | 156233813.7 | 156233813.7 | 1010166751 | نعم | 218033813.7 | 180809059273 | مسحوب | منهجية القيمة المكتسبة | 63 | 100 | 2014-12-02 | 2018-05-29 | 2023-09-27 | 2023-09-27 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 49.6626 | 27.0037 | مسحوب | No
2100202440 | شركة المياه الوطنية / منطقة عسير | تصميم | ذات اولوية عالية | 2835000 | 141750 | 2835000 | 2835000 | 1010348048 | لا | 0 | 190901068781 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2019-11-11 | 2020-09-06 | 2020-09-06 | 2020-09-06 | 2020-09-06 |  |  |  | 42.4888 | 18.2116 | منجز | No
2100022713 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية عالية | 81950000 | 4097500 | 81949020 | 81949020 | 4030082735 | لا | 0 | 180809048443 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-07-16 | 2019-06-25 | 2019-08-26 | 2019-08-26 | 2019-06-25 |  | لا يوجد تأخير |  | 42.4989 | 18.2169 | منجز | No
2100063420 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 97700000 | 4885000 | 59067891.7 | 52184230.9 | 1010012911 | لا | 0 |  | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 85.08 | 100 | 2013-11-25 | 2015-11-03 | 2022-05-17 | 2022-05-17 |  |  | اخرى |  | 40.5891 | 21.3623 | متأخر | No
2100098884 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1392410.24 | 69620.512 | 1205485.95 | 1205485.95 | 5801011161 | لا | 0 | 190709102913 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2018-09-26 | 2019-04-14 | 2022-12-31 | 2022-12-31 | 2019-04-14 |  | ضعف كفاءة المقاول الفنية |  | 41.4779 | 20.0185 | منجز | No
2100031695 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 10304372.17 | 515218.6085 | 5269196 | 5269196 | 5950007285 | لا | 0 | 180809042358 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 72 | 100 | 2014-03-23 | 2022-12-13 | 2021-10-20 | 2021-10-20 | 2022-12-13 |  |  |  | 44.2235 | 17.5757 | منجز | No
2100088082 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 9847021.12 | 492351.056 | 6785032.23 | 6785032.23 | 1010023313 | لا | 0 | 190409063962 | مسحوب | التكلفة المفوترة | 82 | 100 | 2013-07-09 | 2015-06-29 | 2019-12-22 | 2019-12-22 |  |  | ضعف كفاءة المقاول الفنية |  | 41.3268 | 19.6363 | مسحوب | No
2100106551 | وزارة الثقافة | تشييد |  | 349165 | 17458.25 | 366623.3 | 366623.3 | 1010298707 |  | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-01-27 00:59 | 2019-11-26 00:59 | 2019-11-26 | 2019-11-26 | 2019-11-26 00:59 |  | لا يوجد تأخير |  |  |  | منجز | No
2100001713 | وزارة الثقافة | تشييد |  | 2886943.2 | 144347.16 | 460404 | 460404 | 1010149030 |  | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-12-06 00:59 | 2019-10-06 00:59 | 2020-02-02 | 2020-02-02 | 2019-10-06 00:59 |  | لا يوجد تأخير |  |  |  | منجز | No
2100190820 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 18378621.12 | 918931.056 | 2425865.97 | 438473.3 | 1010219753 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 19.28 | 49.9 | 2021-04-27 | 2023-04-27 | 2023-04-27 | 2023-04-27 |  |  |  |  | 40.4055 | 21.2641 | Failed | No
2100042000 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 5741669 | 287083.45 | 2213202.96 | 2213202.96 | 5801005451 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2009-02-10 | 2011-02-01 | 2011-04-05 | 2011-04-05 | 2011-02-01 |  | اخرى |  | 41.4779 | 20.0185 | منجز | No
2100079273 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية عالية | 9954173.9 | 497708.695 | 7616877.4 | 7616877.4 | 1131022276 | نعم | 1 | 191009088037 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-01-01 | 2020-06-16 | 2020-11-03 | 2020-11-03 | 2020-06-16 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 44.945 | 26.0268 | منجز | No
2100088966 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 4795999.2 | 239799.96 | 4413851.319 | 4413851.319 | 1010060469 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2017-08-07 | 2019-01-29 | 2021-01-20 | 2021-01-20 | 2019-01-29 |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | منجز | No
2100195392 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 666201.9 | 33310.095 | 503366.5 | 0 | 5951126918 | لا | 0 |  | جاري | تكلفة العمل المنجز | 80 | 100 | 2020-10-20 | 2021-06-20 | 2021-09-10 | 2021-09-10 |  |  |  |  | 42.6271 | 17.0375 | Failed | Yes
2100008750 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 4979540 | 248977 | 4971605.6 | 4971605.6 | 2050018730 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-12-19 | 2020-03-19 | 2020-03-18 | 2020-03-18 | 2020-03-19 |  | لا يوجد تأخير |  | 40.4852 | 21.3541 | منجز | No
2100191413 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 7569300 | 378465 | 6694305.4 | 6694305.4 | 1010224518 | لا | 0 | 200709052696 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 99.98 | 2020-09-06 | 2022-02-19 | 2022-03-31 | 2022-03-31 | 2022-02-19 |  |  |  | 39.1205 | 21.6775 | منجز | No
2100069786 | وزارة الخارجية | تشييد | ذات اولوية عالية وعاجلة | 143375622.52 | 7168781.126 | 123412629.5 | 123412629.5 | 0 | لا | 0 |  | جاري | تكلفة العمل المنجز | 81 | 81 | 2014-12-30 | 2016-12-30 | 2016-12-30 | 2016-12-30 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 8.5375 | 11.9906 | Failed | No
2100062285 | المؤسسة العامة لتحلية المياه المالحة | إشراف | ذات اولوية عالية | 189337800 | 9466890 | 188001382.97 | 188001382.97 | 2051023736 | لا | 0 | 180709019498 | جاري | تكلفة العمل المنجز | 94.9 | 100 | 2013-05-20 | 2022-05-18 | 2022-05-18 | 2022-05-18 |  |  |  |  | 38.1851 | 23.9905 | خدمات عامة | No
2100190444 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية عالية وعاجلة | 918551 | 45927.55 | 918551 | 918551 | 1128016238 | لا | 0 | 201201134213 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2021-06-06 | 2022-01-27 | 2022-02-07 | 2022-02-07 | 2022-01-27 |  |  |  | 49.6595 | 25.4406 | منجز | No
2100025174 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية عالية | 43216915 | 2160845.75 | 24532315 | 24532315 | 4031033277 | لا | 0 | 180909110006 | جاري | تكلفة العمل المنجز | 89.99 | 89.99 | 2013-01-05 | 2020-12-11 | 2020-12-11 | 2020-12-11 |  |  |  |  | 39.8473 | 21.3229 | Failed | No
2100069462 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 4197837 | 209891.85 | 4121958 | 4121958 | 5855036170 | لا | 0 | 190801085487 | منجز – استلام ابتدائي | التكلفة المفوترة | 94.43 | 94.43 | 2019-09-09 | 2020-08-28 | 2021-02-02 | 2021-02-02 | 2020-08-28 |  |  |  | 39.8554 | 21.3956 | منجز | No
2100055005 | وزارة الخارجية | تشييد | لم تعد تحتاجها الجهة | 126380566.38 | 6319028.319 | 92219531.25 | 92219531.25 | 0 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 73 | 100 | 2015-01-29 | 2018-05-16 | 2018-04-29 | 2018-04-29 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 2.0844 | 13.4861 | مسحوب | No
2100095524 | جامعة القصيم | تشييد | ذات اولوية عالية | 13727424.2 | 686371.21 | 11706203.82 | 11706203.82 | 4031053163 | لا | 0 | 180709026232 | مسحوب | تكلفة العمل المنجز | 86 | 100 | 2014-06-01 | 2015-07-26 | 2022-12-31 | 2022-12-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 43.9875 | 26.0873 | مسحوب | No
2100037542 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 17837500 | 891875 | 16013451 | 16013451 | 4031036822 | لا | 0 | 180909110852 | منجز – استلام ابتدائي | التكلفة المفوترة | 85.5 | 85.5 | 2015-04-06 | 2022-07-04 | 2021-10-07 | 2021-10-07 | 2022-07-04 |  |  |  | 39.8401 | 21.3889 | منجز | No
2100019902 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية عالية | 23853250 | 1192662.5 | 21466790 | 21466790 | 4031033277 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-03-26 | 2016-08-29 | 2017-06-06 | 2017-06-06 | 2016-08-29 |  | التنسيق مع أصحاب المصلحه (خدمات |  | 39.8559 | 21.3307 | منجز | No
2100041020 | الرئاسة العامة لهيئة الأمر بالمعروف والنهي عن المنكر | تشييد | ذات اولوية متوسطة | 26799780 | 1339989 | 13030317.6 | 13030317.6 | 1010349346 | لا | 0 | 180909079292 | مسحوب | الكميات التي تم تركيبها | 72 | 80 | 2012-02-15 | 2013-10-07 | 2022-01-01 | 2022-01-01 |  |  | ضعف كفاءة المقاول الفنية | تم إعادة ترسيته | 45.5749 | 20.472 | مسحوب | No
2100055226 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية متوسطة | 168200249.43 | 8410012.4715 | 159783368.2 | 159783368.2 | 1010004249 | لا | 0 | 180909067009 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-07-12 | 2019-12-15 | 2020-05-12 | 2020-05-12 |  | 2019-12-15 | لا يوجد تأخير |  | 42.4989 | 18.2169 | منجز | No
2100049545 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية عالية | 44126490.3 | 2206324.515 | 33612974.8 | 33612974.8 | 4031047880 | لا | 0 | 3046202 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 91.56 | 91.56 | 2015-09-30 | 2018-12-14 | 2018-12-14 | 2018-12-14 |  |  | ضعف كفاءة المقاول الفنية |  | 39.8775 | 21.3482 | Failed | No
2100068740 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية عالية | 39756193 | 1987809.65 | 34705903.01 | 34705903.01 | 4031041258 | لا | 0 | 1046200 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 91.56 | 91.56 | 2015-10-06 | 2018-10-05 | 2019-09-16 | 2019-09-16 |  |  | التنسيق مع أصحاب المصلحه (خدمات |  | 39.8513 | 21.3529 | Failed | No
2100052861 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية عالية | 21786300 | 1089315 | 14358152.5 | 14358152.5 | 4031033277 | لا | 0 | 7046192 | جاري | تكلفة العمل المنجز | 65.9 | 65.9 | 2018-11-01 | 2022-01-03 | 2022-05-30 | 2022-05-30 |  |  | التنسيق مع أصحاب المصلحه (خدمات |  | 39.8682 | 21.3769 | متأخر | No
2100049361 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية عالية | 28680776 | 1434038.8 | 7851087 | 7851087 | 4031041258 | لا | 0 | 180709028293 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 89.97 | 89.97 | 2014-04-01 | 2017-02-28 | 2020-01-17 | 2020-01-17 | 2017-02-28 |  | التنسيق مع أصحاب المصلحه (خدمات |  | 39.8845 | 21.3754 | منجز | No
2100033541 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 22987000 | 1149350 | 2126339.6 | 2126339.6 | 4031041927 | لا | 0 | 190501025514 | جاري | التكلفة المفوترة | 13.95 | 13.95 | 2019-09-05 | 2022-12-03 | 2022-12-03 | 2022-12-03 |  |  |  |  | 39.8557 | 21.3601 | منتظم | No
2100022772 | شركة المياه الوطنية / منطقة عسير | تصميم وإشراف | ذات اولوية عالية | 1880000 | 94000 | 1974000 | 1974000 | 1010314421 | لا | 0 | 190901068781 | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2018-05-03 | 2018-11-02 | 2022-01-07 | 2022-01-07 |  | 2018-11-02 | لا يوجد تأخير |  | 42.1462 | 19.1088 | منجز | No
2100089751 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 55434535.05 | 2771726.7525 | 37487013.16 | 37487013.16 | 1010297995 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 95.43 | 100 | 2013-11-03 | 2015-11-03 | 2020-06-30 | 2020-06-30 | 2015-11-03 |  | لا يوجد تأخير |  | 40.4198 | 21.3601 | منجز | No
2100191332 | شركة المياه الوطنية / منطقة الحدود الشمالية | تشييد | ذات اولوية عالية | 6050928.45 | 302546.4225 | 6050928.45 | 3279880 | 1010220848 | نعم | 3898065.5 | 200201078721 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2020-09-14 | 2021-09-03 | 2021-09-02 | 2021-09-02 | 2021-09-03 |  |  |  | 41.0986 | 31.0278 | منجز | No
2100083145 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 13373640 | 668682 | 11950429 | 11950429 | 4031008077 | لا | 0 | 190301037132 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 89.36 | 89.36 | 2022-08-25 | 2023-08-24 | 2023-08-24 | 2023-08-24 | 2022-06-16 |  |  |  | 39.8721 | 21.3698 | منجز | No
2100035534 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 11801930 | 590096.5 | 1590868 | 1590868 | 4031057259 | لا | 0 | 180909065795 | منجز – استلام نهائي | تكلفة العمل المنجز | 99.74 | 99.74 | 2014-02-23 | 2015-02-23 | 2017-11-17 | 2017-11-17 | 2015-02-23 | 2021-09-24 |  |  | 39.87 | 21.3912 | منجز | No
2100010426 | شركة المياه الوطنية | إشراف | ذات اولوية عالية | 10656000 | 532800 | 13025303 | 12818128 | 1010415802 | لا | 0 | 181109273795 | جاري | تكلفة العمل المنجز | 100 | 100 | 2015-01-01 | 2016-12-31 | 2022-12-16 | 2022-12-16 |  |  | لا يوجد تأخير |  | 39.861 | 21.3687 | خدمات عامة | No
2100058704 | وزارة الثقافة | تشييد |  | 46075832.59 | 2303791.6295 | 4562380.96 | 4562380.96 | 3350012131 |  | 0 |  | مسحوب | منهجية القيمة المكتسبة | 14 | 100 | 2018-03-21 00:59 | 2020-03-20 00:59 | 2020-07-16 | 2020-07-16 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  |  |  | مسحوب | No
2100084884 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 72912327 | 3645616.35 | 40651260 | 40651260 | 2051020158 | لا | 0 | 181209546913 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 99.8 | 100 | 2012-02-20 | 2014-02-19 | 2023-11-28 | 2023-11-28 |  |  | ضعف كفاءة المقاول الفنية |  | 38.1942 | 24.0204 | Failed | No
2100065262 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 136469462 | 6823473.1 | 129645988 | 129645988 | 4030198340 | لا | 0 | 180709032398 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 98 | 100 | 2012-05-19 | 2015-05-19 | 2023-01-31 | 2023-01-31 |  |  | ضعف كفاءة المقاول الفنية |  | 38.1914 | 24.0213 | منتظم | No
2100194891 | هيئة المدن الصناعية ومناطق التقنية | تشييد | ذات اولوية عالية | 20474332 | 1023716.6 | 17370363 | 17370363 | 1011009116 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2020-08-26 | 2022-02-25 | 2022-10-25 | 2022-10-25 | 2022-02-25 |  |  |  | 44.1319 | 26.2095 | منجز | No
2100107354 | وزارة الموارد البشرية والتنمية الإجتماعية | تشييد | ذات اولوية منخفضة | 7324841.66 | 366242.083 | 7324841.66 | 7324841.66 | 1131001849 | لا | 0 | 180909083349 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-03-25 | 2017-03-02 | 2018-02-11 | 2018-02-11 | 2017-03-02 |  | ضعف كفاءة المقاول الفنية |  | 41.693 | 27.517 | منجز | No
2100049125 | وزارة الموارد البشرية والتنمية الإجتماعية | تشييد | ذات اولوية منخفضة | 8338813.04 | 416940.652 | 6990147.31 | 6990147.31 | 1010028451 | لا | 0 | 180809038347 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-12-30 | 2016-12-07 | 2020-10-27 | 2020-10-27 | 2016-12-07 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.9129 | 16.6313 | منجز | No
2200223661 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 31315378 | 1565768.9 | 20825336.75 | 19861308.25 | 1010082898 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 90 | 100 | 2018-09-05 | 2019-09-05 | 2023-03-31 | 2023-03-31 |  |  |  | أخرى | 44.2363 | 26.3098 | متأخر | No
2200223672 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 74016106 | 3700805.3 | 63241896.23 | 63241896.23 | 1010219247 | لا | 0 |  | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-07-25 | 2019-07-15 | 2022-12-31 | 2022-12-31 |  |  |  |  | 43.544 | 25.8945 | منتظم | No
2100105490 | جامعة الحدود الشمالية | تشييد | ذات اولوية متوسطة | 125549975.27 | 6277498.7635 | 32094548.99 | 32094548.99 | 1010219886 | لا | 0 | 181109236428 | جاري | تكلفة العمل المنجز | 27 | 50 | 2015-10-12 | 2018-09-26 | 2025-06-01 | 2025-06-01 |  |  | التنسيق مع أصحاب المصلحه (خدمات |  | 43.5207 | 29.6323 | متأخر | No
2100000604 | جامعة نجران | تشييد | ذات اولوية عالية | 45000000 | 2250000 | 22489644 | 22489644 | 1001032384 | لا | 0 | 180709021995 | جاري | الكميات التي تم تركيبها | 58 | 100 | 2017-07-20 | 2017-12-22 | 2024-02-20 | 2024-02-20 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 44.2341 | 17.5757 | Failed | No
2100194983 | هيئة المدن الصناعية ومناطق التقنية | تشييد | ذات اولوية عالية | 12921975 | 646098.75 | 10524139 | 10524139 | 1131014852 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2021-06-22 | 2023-06-21 | 2023-06-22 | 2023-06-22 | 2023-06-21 |  |  |  | 41.7582 | 27.4862 | منجز | No
2100034860 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية عالية | 8862000 | 443100 | 5381954.18 | 5381954.18 | 4031059045 | لا | 0 |  | جاري | تكلفة العمل المنجز | 60.79 | 60.79 | 2019-10-17 | 2022-01-14 | 2022-01-14 | 2022-01-14 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.868 | 21.3762 | Failed | No
2100059323 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 6690200 | 334510 | 3686294 | 3686294 | 4030057371 | لا | 0 |  | مسحوب | التكلفة المفوترة | 55.1 | 55.1 | 2013-02-02 | 2015-02-02 | 2017-12-11 | 2017-12-11 |  |  | ضعف كفاءة المقاول الفنية |  | 39.3774 | 21.8957 | مسحوب | No
2100084571 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 262388258 | 13119412.9 | 193313721 | 193313721 | 1010224378 | لا | 0 | 180709036688 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99.98 | 100 | 2014-09-21 | 2016-09-20 | 2022-11-10 | 2022-11-10 | 2016-09-20 |  | أوامر تغيير |  | 38.3047 | 23.962 | منجز | No
2100003150 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2352569 | 117628.45 | 0 | 0 | 4031052955 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 13 | 100 | 2011-02-16 | 2012-05-11 | 2012-05-11 | 2012-05-11 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.836 | 21.4408 | مسحوب | No
2100199323 | جامعة جدة | ترميم | ذات اولوية متوسطة | 381143.35 | 19057.1675 | 0 | 0 | 4030343095 | لا | 0 |  | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2021-11-04 | 2022-02-01 | 2022-09-14 | 2022-09-14 |  |  |  |  | 39.1886 | 21.5269 | Failed | No
2100105836 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 21147282 | 1057364.1 | 16891311.7 | 16891311.7 | 2050053367 | لا | 0 | 190401128192 | جاري | منهجية القيمة المكتسبة | 93.44 | 100 | 2019-10-16 | 2021-09-24 | 2022-06-30 | 2022-06-30 |  |  | اخرى |  | 41.6715 | 19.5815 | متأخر | No
2100007361 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1778007 | 88900.35 | 730985 | 730985 | 1010026700 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 56 | 100 | 2006-09-16 | 2015-10-18 | 2019-02-13 | 2019-02-13 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 41.6968 | 27.506 | مسحوب | No
2100011163 | الهيئة العامة للموانئ | توريد وتركيب | ذات اولوية عالية وعاجلة | 136206145.48 | 6810307.274 | 135510680.72 | 135510680.72 | 4030218491 | لا | 0 | 190509076394 | جاري | تكلفة العمل المنجز | 100 | 100 | 2018-05-06 | 2021-04-20 | 2022-10-28 | 2022-10-28 |  |  | اخرى |  | 39.1719 | 21.4758 | متأخر | No
2100059850 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية | 112561131 | 5628056.55 | 12496067.19 | 12496067.19 | 2051003203 | لا | 0 | 180709022461 | مسحوب | تكلفة العمل المنجز | 22 | 86 | 2014-05-29 | 2016-04-28 | 2025-12-31 | 2025-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5232 | 25.3008 | مسحوب | No
2100085050 | وزارة الصحة / جدة | تشييد | ذات اولوية عالية وعاجلة | 84000000 | 4200000 | 69455000 | 69455000 | 1010136286 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-03-18 | 2017-11-25 | 2018-01-02 | 2018-01-02 | 2017-11-25 |  |  |  | 39.0342 | 22.7741 | منجز | No
2100073721 | شركة المياه الوطنية / منطقة نجران | تشييد | ذات اولوية عالية | 44052960 | 2202648 | 37419137.7 | 37419137.7 | 5950005891 | لا | 0 | 181001198277 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 90.97 | 100 | 2018-04-05 | 2021-03-03 | 2021-06-20 | 2021-06-20 | 2021-03-03 |  | لا يوجد تأخير |  | 44.2341 | 17.5757 | منجز | No
2100088594 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 11020527.37 | 551026.3685 | 6533492.565 | 6533492.565 | 1011008214 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-03-29 | 2020-05-23 | 2021-09-05 | 2021-09-05 | 2020-05-23 |  | تأخرصرف المستحقات المالية |  | 47.3078 | 24.1522 | منجز | No
2100036120 | أمانة / تبوك | تشييد | ذات اولوية عالية وعاجلة | 3149641 | 157482.05 | 2162305 | 2162305 | 4030210663 | لا | 0 | 191201096898 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-09-24 | 2020-09-18 | 2021-08-01 | 2021-08-01 | 2020-09-18 |  | ضعف كفاءة المقاول الفنية |  | 36.5626 | 28.4722 | منجز | No
2200223694 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 497481354.25 | 24874067.7125 | 353183685.94 | 353183685.94 | 1010039430 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 81 | 100 | 2018-04-02 | 2020-03-22 | 2023-06-29 | 2023-06-29 |  |  |  | تم تمديد الجدول الزمني | 42.599 | 16.9861 | متأخر | No
2200223716 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 28388998 | 1419449.9 | 721940 | 721940 | 1010082898 | لا | 0 |  | ايقاف كلي | منهجية القيمة المكتسبة | 2 | 100 | 2018-09-05 | 2019-09-05 | 2023-12-31 | 2023-12-31 |  |  |  | أخرى | 43.6133 | 26.1769 | Failed | No
2100058682 | شركة المياه الوطنية / منطقة الحدود الشمالية | تشييد | ذات اولوية عالية | 28906803 | 1445340.15 | 17891873.65 | 14585061.7 | 1011011290 | لا | 0 | 180201000112 | مسحوب | منهجية القيمة المكتسبة | 69.02 | 100 | 2018-04-08 | 2020-09-10 | 2023-05-15 | 2023-05-15 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.0998 | 31.0228 | مسحوب | No
2100079785 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 12381746.3 | 619087.315 | 11632726.38 | 10422141.2 | 1010249593 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 95.66 | 100 | 2020-02-13 | 2020-12-13 | 2021-02-23 | 2021-02-23 |  | 2020-12-13 | لا يوجد تأخير |  | 46.5239 | 24.4936 | منجز | No
2100097086 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 11367210 | 568360.5 | 8161195.5 | 8161195.5 | 1010276827 | نعم | 27968065.4 |  | جاري | منهجية القيمة المكتسبة | 86.02 | 100 | 2020-02-03 | 2021-04-03 | 2022-08-30 | 2022-08-30 |  |  | لا يوجد تأخير |  | 46.5951 | 24.7397 | Failed | No
2200223705 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 57844977.27 | 2892248.8635 | 16519740.03 | 15067972.72 | 1010082898 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 58 | 75 | 2018-09-04 | 2020-02-26 | 2023-06-29 | 2023-06-29 |  |  |  | أخرى | 42.9548 | 16.8676 | متأخر | No
2200223731 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 133130844.94 | 6656542.247 | 70519410.56 | 70519410.56 | 2050022550 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 92 | 100 | 2013-05-19 | 2015-05-09 | 2023-03-31 | 2023-03-31 |  |  |  | أخرى | 43.8584 | 26.374 | متأخر | No
2100078713 | مستشفى الملك فيصل التخصصي ومركز الأبحاث | الخدمات الاستشارية | ذات اولوية عالية | 5344000 | 267200 | 5343988.56 | 5217380.42 | 4030276223 | لا | 0 | 191201123719 | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2020-01-05 | 2022-01-03 | 2022-03-31 | 2022-03-31 | 2022-01-03 |  | لا يوجد تأخير |  | 46.6767 | 24.6711 | منجز | No
2100103773 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية وعاجلة | 59716900 | 2985845 | 16032972.62 | 12826378.1 | 2050022550 | لا | 0 | 210109010458 | مسحوب | منهجية القيمة المكتسبة | 34.14 | 100 | 2011-03-12 | 2015-01-27 | 2026-08-22 | 2026-08-22 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 44.4236 | 24.5207 | مسحوب | No
2100100295 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية وعاجلة | 9729837 | 486491.85 | 9729836.66 | 9729836.66 | 1010208942 | لا | 0 | 180909066208 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-05-21 | 2019-11-03 | 2019-10-31 | 2019-10-31 |  | 2019-11-03 | لا يوجد تأخير |  | 45.3525 | 25.8912 | منجز | No
2100042873 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية وعاجلة | 350119275 | 17505963.75 | 167672890.31 | 163547298.72 | 1010157933 | لا | 0 | 190701123831 | جاري | منهجية القيمة المكتسبة | 56.67 | 68.67 | 2019-09-09 | 2022-08-07 | 2023-08-15 | 2023-08-15 |  |  | اخرى |  | 46.5769 | 24.6389 | متأخر | No
2100199334 | جامعة جدة | ترميم | ذات اولوية متوسطة | 1320030 | 66001.5 | 0 | 0 | 4030343095 | لا | 0 |  | جاري | تكلفة العمل المنجز | 98 | 100 | 2021-11-14 | 2022-02-14 | 2022-02-14 | 2022-02-14 |  |  |  |  | 39.1886 | 21.5269 | Failed | No
2100060362 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 10130232 | 506511.6 | 6164003.16 | 6104003.16 | 5950004276 | لا | 0 | 181009175289 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 85.84 | 100 | 2018-03-08 | 2021-02-02 | 2021-04-18 | 2021-04-18 |  | 2021-02-02 | لا يوجد تأخير |  | 46.7271 | 22.2863 | منجز | No
2100074605 | جامعة الملك فيصل | توريد وتركيب | ذات اولوية عالية وعاجلة | 448280 | 22414 | 448280 | 448280 | 2257029825 | لا | 0 | 180809055509 | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2016-05-28 | 2017-05-23 | 2017-05-23 | 2017-05-23 |  | 2017-05-23 | تأخرصرف المستحقات المالية |  | 49.5604 | 25.3897 | منجز | No
2100086730 | رئاسة أمن الدولة / قوات الأمن الخاصة | تشييد | ذات اولوية متوسطة | 3820485 | 191024.25 | 1614235.1 | 1614235.1 | 1010224892 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 40 | 100 | 2018-01-04 | 2019-07-01 | 2022-06-08 | 2022-06-08 |  |  | ضعف كفاءة المقاول الفنية |  | 46.557 | 24.8758 | مسحوب | No
2100101441 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 61379905 | 3068995.25 | 52164463 | 52164463 | 4700004138 | لا | 0 | 181009214562 | جاري | منهجية القيمة المكتسبة | 97.48 | 100 | 2018-02-04 | 2020-02-04 | 2023-01-31 | 2023-01-31 |  |  | موافقات |  | 38.3339 | 23.823 | Failed | No
2100037365 | وزارة التعليم | تشييد | ذات اولوية عالية | 4191679 | 209583.95 | 4191679 | 4191679 | 5810009404 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-09-14 | 2016-07-09 | 2018-03-09 | 2018-03-09 | 2016-07-09 |  | اخرى |  | 41.4779 | 20.0185 | منجز | No
2100104952 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 34317063.75 | 1715853.1875 | 34249464.62 | 34249464.62 | 2050002732 | لا | 0 | 180709031902 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-07-26 | 2019-07-06 | 2020-07-05 | 2020-07-05 |  | 2019-07-06 | لا يوجد تأخير |  | 50.0627 | 26.4366 | منجز | No
2100199183 | وزارة الحرس الوطني / الشؤون الصحية | توريد وتركيب | ذات اولوية عالية | 1074487.5 | 53724.375 | 256576.5 | 256576.5 | 1010183991 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 65 | 100 | 2021-08-22 | 2022-02-15 | 2023-07-31 | 2023-07-31 |  |  |  |  | 49.5175 | 25.4533 | Failed | No
2100029702 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 469000 | 23450 | 0 | 0 | 1010198470 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 49 | 2019-01-02 | 2020-06-25 | 2021-06-21 | 2021-06-21 | 2020-06-25 |  |  |  | 45.9384 | 25.2819 | منجز | No
2100061132 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية عالية | 49753159.05 | 2487657.9525 | 49698333.45 | 49698333.45 | 1132002415 | لا | 0 | 181109287562 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2017-12-10 | 2022-06-15 | 2022-06-16 | 2022-06-16 | 2022-06-15 |  |  |  | 45.3236 | 23.8511 | منجز | No
2100036422 | أمانة / جازان | تشييد | ذات اولوية عالية | 319985 | 15999.25 | 0 | 0 | 5906018493 | لا | 0 | 181109346366 | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2018-09-25 | 2019-09-20 | 2020-02-20 | 2020-02-20 | 2019-09-20 |  | ضعف كفاءة المقاول الفنية |  | 42.9401 | 17.238 | منجز | No
2100055565 | جامعة القصيم | تشييد | ذات اولوية عالية | 10971950 | 548597.5 | 8760428.9 | 8760428.9 | 1010092552 | لا | 0 | 200409028667 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-01-20 | 2020-01-05 | 2020-01-05 | 2020-01-05 | 2020-01-05 |  | تأخرصرف المستحقات المالية |  | 43.9376 | 26.3939 | منجز | No
2100038710 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 231319895 | 11565994.75 | 135319896 | 113037466 | 4700004138 | لا | 0 | 180809059054 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2013-10-20 | 2015-10-20 | 2022-10-16 | 2022-10-16 | 2015-10-20 |  | أوامر تغيير |  | 38.3031 | 23.9613 | منجز | No
2100011373 | مستشفى الملك فيصل التخصصي ومركز الأبحاث | تشييد | ذات اولوية عالية | 4171496.75 | 208574.8375 | 4112189.23 | 3411432.98 | 1010170470 | لا | 0 | 200101062113 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2020-02-06 | 2020-08-03 | 2021-08-17 | 2021-08-17 | 2020-08-03 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 46.673 | 24.6707 | منجز | No
2100061891 | شركة المياه الوطنية / منطقة مكة المكرمة | إشراف | ذات اولوية عالية وعاجلة | 7425600 | 371280 | 5577755.12 | 4635209.6 | 1010421976 | لا | 0 |  | جاري | التكلفة المفوترة | 23.68 | 51 | 2020-02-09 | 2022-01-18 | 2022-02-08 | 2022-02-08 |  |  | لا يوجد تأخير |  | 39.1696 | 21.5709 | خدمات عامة | No
2100086870 | جامعة القصيم | تشييد | ذات اولوية عالية وعاجلة | 80600554.98 | 4030027.749 | 62072181.38 | 62072181.38 | 2051027134 | لا | 0 | 190401066502 | جاري | تكلفة العمل المنجز | 81 | 81 | 2018-09-25 | 2019-09-10 | 2023-06-30 | 2023-06-30 |  |  | تأخرصرف المستحقات المالية |  | 43.9544 | 26.3504 | متأخر | No
2100039616 | أمانة / جازان | تشييد | ذات اولوية عالية | 1613790 | 80689.5 | 1477590 | 1477590 | 5903025849 | لا | 0 | 181201541336 | منجز – استلام ابتدائي | اخرى | 92 | 100 | 2018-08-27 | 2019-08-22 | 2020-10-11 | 2020-10-11 | 2019-08-22 |  | ضعف كفاءة المقاول الفنية |  | 42.9415 | 17.2382 | منجز | No
2100082036 | أمانة / الجوف | تشييد | ذات اولوية عالية | 3474500 | 173725 | 3474050 | 3474050 | 3350021023 | لا | 0 | 191101110300 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-10-21 | 2020-10-20 | 2020-10-20 | 2020-10-20 | 2020-10-20 |  |  |  | 37.9756 | 30.7139 | منجز | No
2100039804 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 45600000 | 2280000 | 45554400 | 45554400 | 3550021826 | لا | 0 | 181109231771 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-01-18 | 2015-04-13 | 2019-08-20 | 2019-08-20 | 2015-04-13 |  | اخرى |  | 36.5797 | 28.3816 | منجز | No
2100076926 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 61658847.54 | 3082942.377 | 54803988.67 | 54803988.67 | 1010004737 | لا | 0 | 180809052025 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 91 | 100 | 2014-09-24 | 2020-12-31 | 2022-06-30 | 2022-06-30 | 2020-12-31 |  |  |  | 40.4042 | 21.2944 | منجز | No
2100027322 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 2468832 | 123441.6 | 3086040 | 1157175.7 | 4032030443 | لا | 0 | 210301237624 | جاري | تكلفة العمل المنجز | 56 | 100 | 2019-10-20 | 2020-10-14 | 2023-07-10 | 2023-07-10 |  |  |  |  | 40.4039 | 21.2948 | Failed | No
2100072332 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 24229333.53 | 1211466.6765 | 20323444.43 | 20323444.43 | 4032005285 | لا | 0 | 181009158455 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2013-01-19 | 2014-01-14 | 2021-10-31 | 2021-10-31 | 2014-01-14 |  |  |  | 40.418 | 21.2768 | منجز | No
2100194865 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 17065330 | 853266.5 | 14095962.58 | 14095962.58 | 4032042137 | لا | 0 | 190309000349 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-10-04 | 2016-12-27 | 2020-12-30 | 2020-12-30 | 2016-12-27 |  |  |  | 40.4511 | 21.2747 | منجز | No
2100030413 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 6333463.5 | 316673.175 | 6333463.5 | 6333463.5 | 4032000581 | لا | 0 | 180901070960 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-09-03 | 2020-09-02 | 2021-09-02 | 2021-09-02 | 2020-09-02 |  | ضعف كفاءة المقاول الفنية |  | 40.4312 | 21.2741 | منجز | No
2100082375 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 47361583.04 | 2368079.152 | 41002098.36 | 41002098.36 | 1010004737 | لا | 0 | 180809052028 | مسحوب | تكلفة العمل المنجز | 94 | 100 | 2014-10-12 | 2016-10-01 | 2022-06-30 | 2022-06-30 |  |  |  |  | 40.4176 | 21.248 | مسحوب | No
2100194644 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1099455 | 54972.75 | 704579.4 | 704579.4 | 4032024289 | لا | 0 | 191001037477 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 85 | 100 | 2019-09-01 | 2020-08-26 | 2020-01-01 | 2020-01-01 | 2020-08-26 |  |  |  | 40.4511 | 21.2747 | منجز | No
2100068025 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 2056425 | 102821.25 | 1344819.01 | 1344819.01 | 4032024289 | لا | 0 | 191001036460 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 85 | 100 | 2018-02-25 | 2020-08-28 | 2022-01-01 | 2022-01-01 | 2020-08-28 |  |  |  | 40.4127 | 21.2929 | منجز | No
2100047261 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 19453286.79 | 972664.3395 | 17317427.43 | 17317427.43 | 4032005285 | لا | 0 | 181001192427 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-06-25 | 2021-06-14 | 2021-06-14 | 2021-06-14 | 2021-06-14 |  |  |  | 40.4108 | 21.2562 | منجز | No
2100044166 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 39269790 | 1963489.5 | 25555190.64 | 25555190.64 | 1116001737 | لا | 0 | 180501011216 | ايقاف كلي | تكلفة العمل المنجز | 77 | 100 | 2019-04-18 | 2020-10-09 | 2022-06-30 | 2022-06-30 |  |  |  |  | 40.4156 | 21.255 | Failed | No
2100017286 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 149951227.06 | 7497561.353 | 83159447.92 | 83159447.92 | 1010178838 | لا | 0 | 180709036952 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 98 | 100 | 2016-10-14 | 2018-04-07 | 2022-12-21 | 2022-12-21 | 2018-04-07 |  | ضعف كفاءة المقاول الفنية |  | 40.4186 | 21.2933 | منجز | No
2100093704 | جامعة الملك سعود | تشييد | ذات اولوية متوسطة | 4788728 | 239436.4 | 3529748.38 | 3529748.38 | 1010122914 | لا | 0 | 201309035909 | جاري | الكميات التي تم تركيبها | 95 | 100 | 2017-04-24 | 2018-02-24 | 2021-04-30 | 2021-04-30 |  |  | لا يوجد تأخير |  | 62.7127 | 27.0663 | Failed | No
2100074804 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 20857709.01 | 1042885.4505 | 20857709.01 | 20857709.01 | 4031045075 | لا | 0 | 180809055701 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2017-09-21 | 2018-09-21 | 2018-09-21 | 2018-09-21 | 2018-09-21 |  |  |  | 40.4177 | 21.2676 | منجز | No
2100032056 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية منخفضة | 29970759 | 1498537.95 | 24874950 | 24874950 | 4031036822 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 91.21 | 100 | 2019-05-26 | 2021-05-25 | 2021-08-18 | 2021-08-18 | 2021-05-25 |  |  |  | 39.8532 | 21.3673 | منجز | No
2100106816 | مستشفى الملك فيصل التخصصي ومركز الأبحاث | تشييد | ذات اولوية عالية | 23374327.5 | 1168716.375 | 18778231.05 | 17908512.45 | 1010146750 | لا | 0 | 191001215754 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-11-19 | 2020-11-17 | 2022-08-13 | 2022-08-13 |  |  | تصاريح أعمال التنفيذ |  | 46.6937 | 24.8294 | متأخر | No
2100009645 | الهيئة الملكية لمدينة مكة المكرمة و المشاعر المقدسة | تصميم |  | 9900000 | 495000 | 0 | 0 | 0 |  | 0 |  | جاري | اخرى | 93 | 100 | 2019-06-10 00:59 | 2019-05-12 00:59 |  |  |  |  | موافقات |  |  |  | متأخر | No
2100096600 | وزارة الحج والعمرة | تشييد | ذات اولوية عالية | 37202818.26 | 1860140.913 | 32445584.81 | 32445584.81 | 1010178838 | لا | 0 | 180709017806 | ايقاف كلي | الكميات التي تم تركيبها | 92.5 | 92.5 | 2017-09-21 | 2021-06-24 | 2021-06-24 | 2021-06-24 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.7679 | 21.4155 | Failed | No
2100040806 | هيئة المدن الصناعية ومناطق التقنية | دراسات هندسية | ذات اولوية عالية | 45519640 | 2275982 | 45519640 | 45519640 | 1010902667 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2018-01-16 | 2021-01-16 | 2022-07-31 | 2022-07-31 | 2021-01-16 | 2022-09-30 | لا يوجد تأخير |  |  |  | منجز | No
2100026176 | وزارة الموارد البشرية والتنمية الإجتماعية | تشييد | ذات اولوية منخفضة | 28805103.55 | 1440255.1775 | 28805103.55 | 28805103.55 | 1010224427 | لا | 0 | 180709022210 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-07-06 | 2017-06-02 | 2019-10-09 | 2019-10-09 | 2017-06-02 |  | ضعف كفاءة المقاول الفنية |  | 46.6988 | 24.6577 | منجز | No
2100041112 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 14922688 | 746134.4 | 9253092.9 | 9253092.9 | 1010185409 | لا | 0 |  | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2020-02-02 | 2021-02-01 | 2022-09-30 | 2022-09-30 |  |  | أوامر تغيير |  |  |  | Failed | No
2100105081 | المؤسسة العامة للحبوب | تشييد | ذات اولوية عالية | 1994150 | 99707.5 | 1994150 | 1994150 | 1010287256 | لا | 0 | 190309094388 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-01-16 | 2020-06-30 | 2020-06-30 | 2020-06-30 | 2020-06-30 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 44.6359 | 20.4472 | منجز | No
2100001256 | وزارة المالية | تشييد | ذات اولوية عالية | 42845732.16 | 2142286.608 | 35307011.89 | 35307011.89 | 1010228607 | لا | 0 | 191001239033 | منجز – استلام ابتدائي | التكلفة المفوترة | 99 | 100 | 2020-01-07 | 2021-09-01 | 2022-05-31 | 2022-05-31 | 2021-09-01 |  | التنسيق مع أصحاب المصلحه (خدمات |  | 46.7098 | 24.6275 | منجز | No
2100190595 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية | 7063864.89 | 353193.2445 | 2856760.02 | 2856760.02 | 1010439305 | لا | 0 | 200301137029 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 76.26 | 2020-10-14 | 2022-09-23 | 2022-09-23 | 2022-09-23 | 2022-09-23 |  |  |  | 43.512 | 25.8657 | منجز | No
2100040036 | جامعة حائل | تشييد | ذات اولوية عالية وعاجلة | 134430000 | 6721500 | 105620839.61 | 105620839.61 | 1128000011 | لا | 0 |  | جاري | تكلفة العمل المنجز | 78.57 | 78 | 2014-12-18 | 2018-11-27 | 2022-07-05 | 2022-07-05 |  |  | تأخرصرف المستحقات المالية |  | 41.7093 | 27.665 | منتظم | No
2100042394 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 3730483.72 | 186524.186 | 2317637 | 2317637 | 4031053163 | لا | 0 |  | مسحوب | التكلفة المفوترة | 61 | 100 | 2013-10-26 | 2015-01-26 | 2015-03-15 | 2015-03-15 |  |  | ضعف كفاءة المقاول الفنية |  | 43.9544 | 26.3504 | مسحوب | No
2100106470 | المؤسسة العامة للحبوب | تشييد | ذات اولوية عالية | 2625000 | 131250 | 2625000 | 2625000 | 1010125419 | لا | 0 | 200701088759 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-10-29 | 2020-12-01 | 2020-12-01 | 2020-12-01 | 2020-12-01 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 46.6656 | 24.7229 | منجز | No
2100107704 | جامعة حائل | تشييد | ذات اولوية عالية وعاجلة | 30941490.8 | 1547074.54 | 13891335.49 | 13891335.49 | 1010012687 | لا | 0 |  | جاري | تكلفة العمل المنجز | 45.77 | 95 | 2013-11-13 | 2020-08-15 | 2022-03-31 | 2022-03-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.7116 | 27.6678 | Failed | No
2100021512 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 51735658.41 | 2586782.9205 | 32097036.25 | 32097036.25 | 1010276314 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 70 | 100 | 2013-01-18 | 2015-06-22 | 2021-03-05 | 2021-03-05 |  |  | اخرى |  | 46.6814 | 24.7044 | مسحوب | No
2100080986 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 256401012 | 12820050.6 | 6433625.01 | 6433625.01 | 1010018152 | لا | 0 | 190401103214 | جاري | الكميات التي تم تركيبها | 3 | 3 | 2019-07-10 | 2022-11-04 | 2022-11-05 | 2022-11-05 |  |  |  |  | 46.6786 | 24.7131 | منتظم | No
2100042442 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 8666810.61 | 433340.5305 | 0 | 0 | 1010046644 | لا | 0 |  | مسحوب | التكلفة المفوترة | 0 | 100 | 2017-04-30 | 2019-01-20 | 2019-06-27 | 2019-06-27 |  |  | ضعف كفاءة المقاول الفنية |  | 50.4488 | 26.4699 | مسحوب | No
2100008680 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 114000218 | 5700010.9 | 60512284.91 | 60512284.91 | 4030028078 | لا | 0 | 190509035676 | جاري | تكلفة العمل المنجز | 50.5 | 100 | 2013-02-23 | 2015-02-03 | 2023-12-31 | 2023-12-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.1677 | 21.5008 | Failed | No
2100192636 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 97158800.76 | 4857940.038 | 15860197.08 | 15860197.08 | 4031036822 | لا | 0 | 190901112435 | جاري | تكلفة العمل المنجز | 16.95 | 25 | 2020-06-16 | 2020-11-06 | 2024-12-31 | 2024-12-31 |  |  |  |  | 39.2391 | 21.4933 | متأخر | No
2100192662 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 14855202.25 | 742760.1125 | 0 | 0 | 4030123131 | لا | 0 | 191001169844 | لم يبدأ | تكلفة العمل المنجز | 0 | 0 | 2018-10-28 | 2019-08-20 | 2023-12-31 | 2023-12-31 |  |  |  |  | 39.239 | 21.4933 | منتظم | No
2100005902 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 80747802.96 | 4037390.148 | 72580185.08 | 72580185.08 | 1010136405 | لا | 0 | 180709020610 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-09-03 | 2016-08-13 | 2022-12-31 | 2022-12-31 |  |  | تأخرصرف المستحقات المالية |  | 39.1677 | 21.5008 | متأخر | No
2100043035 | وزارة التعليم | تشييد | ذات اولوية عالية | 4866897.6 | 243344.88 | 0 | 0 | 1010183010 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0 | 100 | 2008-04-26 | 2009-10-18 | 2023-05-03 | 2023-05-03 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.6509 | 17.1567 | مسحوب | No
2100013241 | أمانة / الجوف | تشييد | ذات اولوية عالية وعاجلة | 23372870 | 1168643.5 | 16119049 | 14919049 | 3350000106 | لا | 0 | 190709006420 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-02-10 | 2021-02-09 | 2022-05-24 | 2022-05-24 | 2021-02-09 |  |  |  | 37.3647 | 31.3181 | منجز | No
2100096331 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 76826790 | 3841339.5 | 40027215.3 | 40024935.8 | 1010010466 | لا | 0 | 180909067472 | جاري | منهجية القيمة المكتسبة | 72.66 | 73.96 | 2013-04-03 | 2017-02-19 | 2022-11-27 | 2022-11-27 |  |  | تصاريح أعمال التنفيذ |  | 46.2928 | 24.4781 | منتظم | No
2100097952 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 55134955.2 | 2756747.76 | 41213827.2 | 39398317.97 | 1010188861 | لا | 0 | 180701036096 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 97.15 | 100 | 2018-11-15 | 2021-10-13 | 2022-04-30 | 2022-04-30 |  |  | اخرى |  | 44.7813 | 20.4716 | متأخر | No
2100189814 | الهيئة الملكية لمحافظة العلا | تصميم وتشييد | ذات اولوية متوسطة | 11787843 | 589392.15 | 7721036.95 | 7721036.95 | 4030288802 | لا | 0 |  | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 100 | 100 | 2020-02-20 | 2021-12-02 | 2022-02-28 | 2022-02-28 |  |  |  |  | 38.1167 | 26.4779 | Failed | No
2100191634 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 36500000 | 1825000 | 31091833.99 | 21482089.54 | 2050003475 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 100 | 78.99 | 2020-11-25 | 2022-11-26 | 2022-11-25 | 2022-11-25 |  |  |  |  | 46.6314 | 24.8525 | منتظم | No
2100080242 | المؤسسة العامة للتقاعد | تشييد | ذات اولوية عالية | 444174087.49 | 22208704.3745 | 267313311 | 267313311 | 1010054406 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2013-06-12 | 2020-11-11 | 2021-12-31 | 2021-12-31 | 2020-11-11 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.1269 | 21.7261 | منجز | No
2100056976 | شركة المياه الوطنية / منطقة مكة المكرمة | إشراف | ذات اولوية عالية | 10375200 | 518760 | 9910246.71 | 9429816.6 | 1131035992 | لا | 0 |  | منجز – استلام نهائي | مدفوعات ساعات العمل | 100 | 100 | 2014-08-14 | 2017-08-13 | 2019-08-25 | 2019-08-25 |  | 2017-08-13 | لا يوجد تأخير |  | 39.8317 | 21.3577 | منجز | No
2100091280 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 3194465 | 159723.25 | 1626397 | 1626397 | 1010061463 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99.97 | 100 | 2020-03-09 | 2021-07-09 | 2022-04-30 | 2022-04-30 | 2021-07-09 |  | لا يوجد تأخير |  | 46.621 | 24.7529 | منجز | No
2100096692 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1369038 | 68451.9 | 829371.6 | 829371.6 | 1010261195 | لا | 0 |  | مسحوب | التكلفة المفوترة | 75 | 100 | 2012-11-16 | 2014-07-01 | 2019-11-18 | 2019-11-18 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | مسحوب | No
2100002273 | وزارة التعليم | تشييد | لم تعد تحتاجها الجهة | 10147006.55 | 507350.3275 | 5111943.35 | 5111943.35 | 1010051817 | لا | 0 |  | مسحوب | التكلفة المفوترة | 56 | 100 | 2013-06-14 | 2015-06-04 | 2018-09-26 | 2018-09-26 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 46.7098 | 24.6275 | مسحوب | No
2100096762 | وزارة التعليم | تشييد | لم تعد تحتاجها الجهة | 3676886 | 183844.3 | 1272496 | 1272496 | 1010213832 | لا | 0 |  | مسحوب | التكلفة المفوترة | 76 | 100 | 2013-01-21 | 2014-07-16 | 2018-11-19 | 2018-11-19 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | مسحوب | No
2100041016 | وزارة التعليم | تشييد | ذات اولوية عالية | 2742008.75 | 137100.4375 | 1616197 | 1616197 | 1010240933 | لا | 0 |  | مسحوب | التكلفة المفوترة | 90 | 100 | 2014-11-05 | 2016-07-27 | 2020-03-22 | 2020-03-22 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | مسحوب | No
2100041101 | وزارة التعليم | تشييد | لم تعد تحتاجها الجهة | 11920094.33 | 596004.7165 | 10519836.11 | 8455184 | 1010300402 | لا | 0 |  | ايقاف جزئي | التكلفة المفوترة | 100 | 100 | 2019-03-03 | 2020-04-26 | 2022-06-06 | 2022-06-06 |  |  | اخرى |  | 46.6561 | 24.7709 | Failed | No
2100063173 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 4960881 | 248044.05 | 4145726 | 4145726 | 1010300402 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-08-25 | 2017-09-14 | 2017-09-14 | 2017-09-14 | 2017-09-14 |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | منجز | No
2100056910 | شركة المياه الوطنية / منطقة مكة المكرمة | إشراف | ذات اولوية متوسطة | 11000000 | 550000 | 10611396.71 | 10611396.71 | 1010358934 | لا | 0 |  | منجز – استلام نهائي | مدفوعات ساعات العمل | 100 | 100 | 2015-08-06 | 2018-08-05 | 2018-08-06 | 2018-08-06 |  | 2018-08-05 | لا يوجد تأخير |  | 39.8104 | 21.3729 | منجز | No
2100191343 | شركة المياه الوطنية / منطقة مكة المكرمة | إشراف | ذات اولوية عالية | 14367311 | 718365.55 | 18200763.06 | 17509367.89 | 1010314421 | لا | 0 | 200709052696 | جاري | مدفوعات ساعات العمل | 100 | 100 | 2014-08-14 | 2017-08-14 | 2023-01-31 | 2023-01-31 |  |  |  |  | 39.2284 | 21.5933 | خدمات عامة | No
2100087323 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 34111750 | 1705587.5 | 34110521.6 | 30694099.3 | 1131014852 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-02-03 | 2021-02-03 | 2020-12-27 | 2020-12-27 | 2021-02-03 |  | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100062521 | الهيئة الملكية للجبيل وينبع / مدينة جازان للصناعات الأساسية والتحويلية | تشييد | ذات اولوية عالية | 105177911.74 | 5258895.587 | 51455093.09 | 51455093.09 | 1010127437 | لا | 0 | 190901007220 | جاري | الكميات التي تم تركيبها | 39.76 | 84.23 | 2020-02-27 | 2022-08-28 | 2024-12-23 | 2024-12-23 |  |  | اخرى | أخرى | 42.3474 | 17.3552 | Failed | No
2100045334 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4498400 | 224920 | 42093 | 0 | 1010225233 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 1 | 100 | 2015-09-23 | 2016-12-16 | 2023-12-06 | 2023-12-06 |  |  | تأخرصرف المستحقات المالية |  |  |  | مسحوب | Yes
2100105092 | الهيئة العامة للموانئ | تشييد | ذات اولوية عالية وعاجلة | 55888269.15 | 2794413.4575 | 0 | 0 | 1010231383 | لا | 0 | 181001192511 | مسحوب | تكلفة العمل المنجز | 5 | 95 | 2019-06-30 | 2021-06-20 | 2021-10-25 | 2021-10-25 |  |  | ضعف كفاءة المقاول الفنية |  | 49.6743 | 27.0199 | مسحوب | No
2100015680 | وزارة الصحة/ الاحساء | تشييد | ذات اولوية متوسطة | 2938980 | 146949 | 213980 | 213980 | 2051038453 | لا | 0 | 191201009038 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 17 | 83 | 2020-02-08 | 2021-01-27 | 2021-01-28 | 2021-01-28 | 2021-01-27 |  | اخرى |  | 49.5598 | 25.4093 | منجز | No
2100090565 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 3196050 | 159802.5 | 2807956 | 2807956 | 1010018153 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-05-19 | 2017-07-17 | 2017-07-17 | 2017-07-17 | 2017-07-17 |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | منجز | No
2100046314 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 3165372 | 158268.6 | 3097122 | 3097122 | 5950014853 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 97.84 | 97.48 | 2018-12-21 | 2020-12-20 | 2020-12-20 | 2020-12-20 | 2020-12-20 |  |  |  | 44.2224 | 17.5552 | منجز | No
2100057956 | وزارة الموارد البشرية والتنمية الإجتماعية | تشييد | ذات اولوية منخفضة | 16511250.4 | 825562.52 | 7173127.98 | 7173127.98 | 1010145283 | لا | 0 | 190209044359 | مسحوب | الكميات التي تم تركيبها | 75 | 100 | 2015-02-02 | 2017-01-10 | 2022-10-12 | 2022-10-12 |  |  | ضعف كفاءة المقاول الفنية |  | 39.7968 | 21.392 | مسحوب | No
2100103806 | وزارة الموارد البشرية والتنمية الإجتماعية | تشييد | ذات اولوية منخفضة | 16116900.27 | 805845.0135 | 6330395 | 6330395 | 1010145283 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 83 | 100 | 2015-02-02 | 2017-01-10 | 2021-08-05 | 2021-08-05 |  |  | ضعف كفاءة المقاول الفنية |  | 39.3555 | 21.4076 | مسحوب | No
2100019202 | وزارة التعليم | تشييد | لم تعد تحتاجها الجهة | 1865843 | 93292.15 | 1303675 | 1303675 | 1118001885 | لا | 0 |  | مسحوب | التكلفة المفوترة | 88 | 100 | 2011-05-14 | 2012-08-05 | 2022-09-14 | 2022-09-14 |  |  | ضعف كفاءة المقاول الفنية |  | 42.9095 | 23.8972 | مسحوب | No
2100074034 | شركة المياه الوطنية / منطقة القصيم | إشراف | ذات اولوية عالية | 20588150 | 1029407.5 | 20588131.19 | 20588131.19 | 1010949106 | لا | 0 | 181009132336 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-09-22 | 2018-01-22 | 2019-11-01 | 2019-11-01 | 2018-01-22 |  | لا يوجد تأخير |  | 43.967 | 26.3343 | منجز | No
2100191111 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 5800000 | 290000 | 2348000 | 2348000 | 4030087384 | لا | 0 |  | ايقاف كلي | منهجية القيمة المكتسبة | 80 | 100 | 2020-07-19 | 2021-06-18 | 2022-01-30 | 2022-01-30 |  |  |  |  | 39.8764 | 21.4237 | Failed | No
2100015842 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1743735 | 87186.75 | 1192002 | 1192002 | 1010165941 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2008-04-29 | 2009-04-14 | 2019-11-15 | 2019-11-15 | 2009-04-14 |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | منجز | No
2100012320 | رئاسة أمن الدولة / المديرية العامة للمباحث | تشييد | ذات اولوية متوسطة | 1542056 | 77102.8 | 0.01 | 0.01 | 1010413981 | لا | 0 |  | مسحوب | منهجية القيمة المكتسبة | 10 | 100 | 2020-02-20 | 2020-06-21 | 2021-12-31 | 2021-12-31 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | مسحوب | No
2100028265 | جامعة الملك سعود | إشراف | ذات اولوية متوسطة | 4422322.27 | 221116.1135 | 4205512.87 | 4205512.87 | 1010423257 | لا | 0 | 190909068950 | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2019-03-28 | 2022-03-28 | 2022-03-28 | 2022-03-28 | 2022-03-28 | [5 empty] | منجز | No
2100090904 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 4290307.83 | 214515.3915 | 3537560.6 | 3537560.6 | 2057001038 | لا | 0 | 190709120762 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2012-11-11 | 2014-05-05 | 2021-12-08 | 2021-12-08 | 2014-05-05 |  | ضعف كفاءة المقاول الفنية |  | 41.0859 | 19.1571 | منجز | No
2100108850 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 1593900 | 79695 | 1593900 | 1593900 | 2050093648 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2019-05-09 | 2020-03-05 | 2020-03-02 | 2020-03-02 | 2020-03-05 |  |  |  | 46.8595 | 24.7664 | منجز | No
2100057190 | شركة المياه الوطنية / منطقة مكة المكرمة | إشراف | ذات اولوية عالية وعاجلة | 7819200 | 390960 | 5973236 | 5703836 | 4030267376 | لا | 0 |  | جاري | التكلفة المفوترة | 73 | 90.2 | 2019-04-15 | 2022-03-13 | 2022-03-13 | 2022-03-13 |  |  | لا يوجد تأخير |  | 39.1925 | 21.5634 | خدمات عامة | No
2100071875 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية عالية | 20000000 | 1000000 | 17438198 | 17438198 | 1010213394 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2012-12-05 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2016-10-21 | 2021-11-08 |  |  | 42.5117 | 18.2465 | منجز | No
2100046631 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 394107 | 19705.35 | 319039.2 | 309766.47 | 4046001694 | لا | 0 | 190701037833 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-10-10 | 2020-02-21 | 2020-02-21 | 2020-02-21 | 2020-02-21 |  | ضعف كفاءة المقاول الفنية |  | 42.8512 | 21.2617 | منجز | No
2100106923 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 3285872.51 | 164293.6255 | 2626465.97 | 2078663.93 | 5850009271 | لا | 0 | 190309049065 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-12-03 | 2016-05-26 | 2021-11-21 | 2021-11-21 | 2016-05-26 |  | تأخرصرف المستحقات المالية |  | 42.2352 | 18.1939 | منجز | No
2100017544 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية وعاجلة | 51307777.5 | 2565388.875 | 33999326.3 | 33999326.3 | 2051063410 | لا | 0 | 180701014821 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 88.82 | 100 | 2018-08-09 | 2021-01-11 | 2022-01-11 | 2022-01-11 | 2021-01-11 |  | لا يوجد تأخير |  | 43.9553 | 26.3508 | منجز | No
2100071164 | شركة المياه الوطنية / منطقة الباحة | إشراف | ذات اولوية عالية وعاجلة | 2000000 | 100000 | 1216638.42 | 1093450.03 | 5801018549 | لا | 0 | 19031012660 | جاري | التكلفة المفوترة | 60.83 | 72.45 | 2020-03-18 | 2023-03-18 | 2023-03-18 | 2023-03-18 |  |  | لا يوجد تأخير |  | 41.2542 | 19.9462 | خدمات عامة | No
2100043444 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية وعاجلة | 71365771 | 3568288.55 | 30125946.72 | 19892582.13 | 1128000011 | لا | 0 | 181001213250 | جاري | منهجية القيمة المكتسبة | 74.9 | 98.6 | 2018-12-26 | 2021-11-24 | 2023-07-31 | 2023-07-31 |  |  | اخرى |  | 43.8463 | 26.3786 | متأخر | No
2100032745 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية وعاجلة | 45874568.25 | 2293728.4125 | 7871477.26 | 7871477.26 | 1010009590 | نعم | 0.01 | 190801107186 | جاري | منهجية القيمة المكتسبة | 47 | 39.51 | 2020-03-15 | 2023-02-11 | 2023-11-02 | 2023-11-02 |  |  | لا يوجد تأخير |  | 44.0094 | 26.3916 | منتظم | No
2100086623 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 3911805 | 195590.25 | 929819 | 929819 | 2057001038 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 28 | 100 | 2013-08-24 | 2015-02-16 | 2023-02-01 | 2023-02-01 |  |  | تغيرات في نطاق المشروع |  | 42.0529 | 18.5228 | مسحوب | No
2100022805 | شركة المياه الوطنية / منطقة الباحة | إشراف | ذات اولوية عالية وعاجلة | 13680000 | 684000 | 11803287.88 | 10290867.88 | 4031087359 | لا | 0 | 180801041291 | جاري | التكلفة المفوترة | 86.28 | 86.28 | 2018-10-18 | 2022-10-19 | 2022-10-19 | 2022-10-19 |  |  | لا يوجد تأخير |  | 41.4712 | 20.0089 | خدمات عامة | No
2100012014 | وزارة التجارة | تشييد | ذات اولوية عالية | 16376317.55 | 818815.8775 | 5903652 | 5903652 | 4601000417 | لا | 0 | 181109373724 | جاري | منهجية القيمة المكتسبة | 75 | 90 | 2018-03-26 | 2021-09-30 | 2022-06-09 | 2022-06-09 |  |  | اخرى |  | 41.4807 | 20.0075 | متأخر | No
2100086866 | وزارة التجارة | تشييد | ذات اولوية عالية وعاجلة | 17003666 | 850183.3 | 12898513 | 12898513 | 1010114475 | لا | 0 | 180301000637 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-11-14 | 2020-11-13 | 2021-07-18 | 2021-07-18 |  | 2020-11-13 | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 49.5574 | 25.3855 | منجز | No
2100041090 | أمانة / جازان | تحديث وتوريد | ذات اولوية متوسطة | 7950000 | 397500 | 4000000 | 4000000 | 1010348048 | لا | 0 | 180401004051 | جاري | تكلفة العمل المنجز | 96 | 100 | 2018-07-17 | 2020-01-08 | 2020-05-12 | 2020-05-12 |  |  | اخرى |  | 42.6856 | 16.9294 | Failed | No
2100089972 | وزارة التعليم | تشييد | ذات اولوية عالية | 10906964.43 | 545348.2215 | 4661288.55 | 4661288.55 | 4030174393 | لا | 0 | 190901074838 | جاري الاستلام الإبتدائي | التكلفة المفوترة | 95 | 100 | 2014-01-12 | 2016-01-02 | 2022-08-03 | 2022-08-03 |  |  | ضعف كفاءة المقاول الفنية |  | 39.836 | 21.4408 | Failed | No
2100091626 | أمانة / عسير | تشييد | ذات اولوية عالية | 1673033 | 83651.65 | 1498751 | 1498751 | 1010191831 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 85 | 100 | 2009-06-13 | 2010-06-09 | 2020-06-09 | 2020-06-09 |  |  | ضعف كفاءة المقاول الفنية |  | 42.1788 | 18.9252 | مسحوب | No
2100076285 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 13332000 | 666600 | 8447560.87 | 8447560.87 | 5950005816 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 91.51 | 100 | 2019-04-07 | 2021-10-22 | 2022-09-11 | 2022-09-11 | 2021-10-22 |  |  |  | 44.2337 | 17.589 | منجز | No
2100199415 | جامعة جدة | تصميم وتشييد | ذات اولوية متوسطة | 2242672.5 | 112133.625 | 1325035.75 | 1325035.75 | 4605000749 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2021-01-04 | 2021-02-04 | 2021-11-11 | 2021-11-11 | 2021-02-04 |  |  |  | 39.1808 | 21.579 | منجز | No
2100013355 | أمانة / الجوف | تشييد | ذات اولوية عالية | 8159420 | 407971 | 3202663 | 3202663 | 5859000601 | لا | 0 |  | جاري | تكلفة العمل المنجز | 98 | 100 | 2015-11-07 | 2017-10-27 | 2022-09-07 | 2022-09-07 |  |  | ضعف كفاءة المقاول الفنية |  | 42.1791 | 18.9518 | منتظم | No
2100191446 | شركة المياه الوطنية / منطقة الباحة | إشراف | ذات اولوية عالية وعاجلة | 10000000 | 500000 | 3745765.32 | 3745765.32 | 1131052239 | لا | 0 | 190601010683 | جاري | منهجية القيمة المكتسبة | 39.74 | 39.74 | 2020-12-01 | 2023-12-01 | 2023-12-02 | 2023-12-02 |  |  |  |  | 41.4742 | 20.0154 | خدمات عامة | No
2100090580 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 5565210 | 278260.5 | 3678272.16 | 3678272.16 | 5950016273 | لا | 0 | 200509001711 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 80 | 85 | 2019-12-31 | 2021-12-29 | 2021-12-07 | 2021-12-07 | 2021-12-29 |  |  |  | 44.2439 | 17.5537 | منجز | No
2100084195 | أمانة / نجران | تشييد | ذات اولوية عالية | 45630517 | 2281525.85 | 39493569.16 | 39493569.16 | 1010180651 | لا | 0 | 180709033561 | مسحوب | تكلفة العمل المنجز | 87.45 | 87.45 | 2014-04-02 | 2021-06-29 | 2021-04-27 | 2021-04-27 |  |  | اخرى |  | 44.2122 | 17.5722 | مسحوب | No
2100050466 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 6876274 | 343813.7 | 6244956 | 6244956 | 1010255485 | لا | 0 | 190309098645 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 100 | 2013-11-19 | 2015-05-13 | 2021-04-14 | 2021-04-14 | 2015-05-13 |  | ضعف كفاءة المقاول الفنية |  | 37.2651 | 25.05 | منجز | No
2100058962 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 3751300 | 187565 | 2322040 | 2322040 | 5802004740 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 78 | 100 | 2016-05-19 | 2017-04-28 | 2021-02-02 | 2021-02-02 |  |  | تأخرصرف المستحقات المالية |  | 41.6519 | 20.2518 | مسحوب | No
2100061445 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 15181331.52 | 759066.576 | 12923040.62 | 11567972.11 | 5950009685 | لا | 0 | 181209410911 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 91.23 | 100 | 2016-12-06 | 2019-05-12 | 2020-06-13 | 2020-06-13 |  | 2019-05-12 | لا يوجد تأخير |  | 46.7271 | 22.2863 | منجز | No
2100060734 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 39200000 | 1960000 | 35257152.58 | 35257152.58 | 2050001536 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2020-01-16 | 2020-09-16 | 2020-07-19 | 2020-07-19 | 2020-09-16 |  | لا يوجد تأخير |  | 39.1463 | 21.533 | منجز | No
2100000453 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 20778423.75 | 1038921.1875 | 20711404.72 | 20711404.72 | 1010278841 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 99.99 | 96.97 | 2019-01-17 | 2021-01-17 | 2020-01-28 | 2020-01-28 |  | 2021-01-17 | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100190816 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية وعاجلة | 105000000 | 5250000 | 8878232.51 | 8878232.51 | 1010011560 | لا | 0 | 180301001391 | جاري | منهجية القيمة المكتسبة | 71.81 | 81.61 | 2020-07-27 | 2022-12-29 | 2022-12-29 | 2022-12-29 |  |  |  |  | 44.2574 | 26.3151 | متأخر | No
2100087614 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 105680007 | 5284000.35 | 65557967.86 | 65557967.86 | 2050003475 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-02-01 | 2020-01-10 | 2020-06-17 | 2020-06-17 | 2020-01-10 |  | لا يوجد تأخير |  | 39.3113 | 21.4628 | منجز | No
2100086111 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية عالية | 64929981.45 | 3246499.0725 | 62436937.63 | 62436937.63 | 1010066115 | لا | 0 | 190309013101 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 86.81 | 100 | 2017-12-04 | 2019-11-13 | 2021-03-02 | 2021-03-02 |  | 2019-11-13 | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.0529 | 18.5228 | منجز | No
2100191435 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 68952381 | 3447619.05 | 18453911.77 | 17506922.2 | 4030032844 | لا | 0 | 200709052696 | جاري | منهجية القيمة المكتسبة | 67.15 | 100 | 2020-09-08 | 2022-02-21 | 2022-05-31 | 2022-05-31 |  |  |  |  | 39.2012 | 21.6307 | Failed | No
2100078072 | وزارة الصحة / القصيم | تشييد | ذات اولوية متوسطة | 2223783.1 | 111189.155 | 2223783.1 | 2223783.1 | 1131030754 | لا | 0 | 181009159488 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2017-05-10 | 2020-11-18 | 2022-03-30 | 2022-03-30 | 2020-11-18 |  | موافقات |  | 44.2476 | 26.3177 | منجز | No
2100059021 | أمانة / جازان | دراسة الجدوى | ذات اولوية متوسطة | 7930000 | 396500 | 7930000 | 7930000 | 5900018330 | لا | 0 | 180709032167 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-06-24 | 2020-06-24 | 2020-11-11 | 2020-11-11 | 2020-06-24 |  | اخرى |  | 42.6225 | 16.8967 | منجز | No
2100072166 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 17851315 | 892565.75 | 6622402 | 6622402 | 1131020873 | لا | 0 | 190309018977 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 99 | 100 | 2014-04-09 | 2015-10-02 | 2022-03-30 | 2022-03-30 | 2015-10-02 |  | التنسيق مع أصحاب المصلحه (خدمات |  | 42.5747 | 16.9123 | منجز | No
2100194246 | أمانة / جدة | تشييد | ذات اولوية عالية | 229330605 | 11466530.25 | 107834131.38 | 89978450 | 4030140033 | لا | 0 | 200201131584 | جاري | الكميات التي تم تركيبها | 69 | 73 | 2020-05-21 | 2022-10-23 | 2023-06-23 | 2023-06-23 |  |  |  |  | 39.1677 | 21.5008 | منتظم | No
2100194213 | أمانة / جدة | تشييد | ذات اولوية عالية وعاجلة | 12912900 | 645645 | 10540236 | 10540236 | 1010009804 | لا | 0 | 191101281146 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 82 | 86 | 2020-01-15 | 2021-01-03 | 2020-01-03 | 2020-01-03 | 2021-01-03 |  |  |  | 39.1677 | 21.5008 | منجز | No
2100049954 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 13933218 | 696660.9 | 12712209 | 12712209 | 4650007032 | لا | 0 | 181209454467 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 84 | 85 | 2015-05-03 | 2017-04-10 | 2020-11-15 | 2020-11-15 | 2017-04-10 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.2259 | 21.5633 | منجز | No
2100009306 | أمانة / جدة | دراسات هندسية | ذات اولوية متوسطة | 33458805 | 1672940.25 | 31618546 | 31618546 | 1010433483 | لا | 0 | 190409002739 | جاري | تكلفة العمل المنجز | 100 | 100 | 2018-02-18 | 2021-01-15 | 2021-07-02 | 2021-07-02 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.1907 | 21.4856 | خدمات عامة | No
2100194191 | أمانة / جدة | تشييد | ذات اولوية عالية | 10992466 | 549623.3 | 4892579.33 | 4892579.33 | 4030038043 | لا | 0 | 200909139940 | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2020-07-02 | 2020-10-28 | 2021-05-02 | 2021-05-02 | 2020-10-28 | 2021-01-29 |  |  | 39.1677 | 21.5008 | منجز | No
2100082460 | أمانة / جدة | تشييد | ذات اولوية عالية | 64004977 | 3200248.85 | 58814596 | 58814596 | 4650037043 | لا | 0 | 181109283081 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 86 | 100 | 2015-02-10 | 2017-01-18 | 2020-05-13 | 2020-05-13 | 2017-01-18 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.1922 | 21.5969 | منجز | No
2100194224 | أمانة / جدة | تشييد | ذات اولوية عالية وعاجلة | 41997973 | 2099898.65 | 0 | 0 | 4030113058 | لا | 0 | 200801029741 | مسحوب | الكميات التي تم تركيبها | 2.5 | 19.5 | 2021-01-18 | 2022-12-27 | 2022-12-27 | 2022-12-27 |  |  |  |  | 39.1677 | 21.5008 | مسحوب | No
2100027672 | أمانة / جدة | تشييد | ذات اولوية عالية وعاجلة | 75470275 | 3773513.75 | 53047381 | 53047381 | 4030013052 | لا | 0 | 180909095133 | جاري | تكلفة العمل المنجز | 85 | 100 | 2019-03-07 | 2021-02-12 | 2022-11-11 | 2022-11-11 |  |  | اخرى |  | 39.1811 | 21.4631 | Failed | No
2100191166 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية وعاجلة | 3770000 | 188500 | 2778930 | 2778930 | 7013364158 | لا | 0 | 180901078879 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2020-09-06 | 2021-09-06 | 2021-08-09 | 2021-08-09 | 2021-09-06 |  |  |  | 41.2563 | 19.9286 | منجز | No
2100097753 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية عالية | 35822584 | 1791129.2 | 32240323.83 | 32240323.83 | 5950009827 | لا | 0 | 190301039387 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 99.51 | 2019-05-12 | 2021-04-19 | 2021-11-04 | 2021-11-04 | 2021-04-19 |  | لا يوجد تأخير |  | 42.7302 | 18.3003 | منجز | No
2100059695 | أمانة / جازان | تشييد | ذات اولوية عالية | 63659300 | 3182965 | 36194975 | 36194975 | 5900008127 | لا | 0 | 180809052701 | جاري | تكلفة العمل المنجز | 74 | 100 | 2012-12-01 | 2014-11-21 | 2021-12-05 | 2021-12-05 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.5685 | 16.8762 | Failed | No
2100051763 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 671886 | 33594.3 | 604698 | 604698 | 4035000741 | لا | 0 | 191101245182 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-12-02 | 2016-11-21 | 2021-11-21 | 2021-11-21 | 2016-11-21 |  | ضعف كفاءة المقاول الفنية |  | 41.0719 | 20.4625 | منجز | No
2100091766 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 12912616 | 645630.8 | 10442876.15 | 7788582.04 | 1010060469 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2013-04-15 | 2015-04-05 | 2020-07-20 | 2020-07-20 | 2015-04-05 |  | ضعف كفاءة المقاول الفنية |  | 42.4987 | 18.2178 | منجز | No
2100178382 | وزارة الثقافة | ترميم | ذات اولوية عالية | 57004736 | 2850236.8 | 57004736 | 48206768.53 | 1010070634 | لا | 0 | 201009164261 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2013-07-14 | 2019-06-05 | 2019-07-05 | 2019-07-05 | 2019-06-05 | 2019-07-10 |  |  | 44.2239 | 17.5415 | منجز | No
2100051936 | أمانة / الجوف | تشييد | ذات اولوية عالية | 941190 | 47059.5 | 941190 | 941190 | 3452007751 | لا | 0 | 180909094034 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-06-20 | 2016-06-09 | 2016-09-15 | 2016-09-15 | 2016-06-09 |  | ضعف كفاءة المقاول الفنية |  | 37.3661 | 31.3337 | منجز | No
2100086822 | وزارة التجارة | تشييد | ذات اولوية عالية | 11446000 | 572300 | 1265427.22 | 1265427.22 | 4030144266 | لا | 0 | 181001166441 | جاري | منهجية القيمة المكتسبة | 75 | 80 | 2018-12-26 | 2020-12-25 | 2022-11-07 | 2022-11-07 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 37.994 | 24.1475 | منتظم | No
2100046815 | المؤسسة العامة للري | إشراف | ذات اولوية عالية | 192150 | 9607.5 | 192150 | 192150 | 2251047903 | لا | 0 | 181101269888 | جاري الاستلام الإبتدائي | مدفوعات ساعات العمل | 99.83 | 100 | 2018-11-28 | 2019-02-08 | 2022-07-14 | 2022-07-14 |  |  | ضعف كفاءة المقاول الفنية |  | 49.6386 | 25.3661 | متأخر | No
2100053362 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2103494 | 105174.7 | 0 | 0 | 5855005104 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0 | 100 | 2015-12-24 | 2018-06-17 | 2023-08-10 | 2023-08-10 |  |  | ضعف كفاءة المقاول الفنية |  | 42.4987 | 18.2178 | مسحوب | No
2100018336 | أمانة / تبوك | دراسة الجدوى | ذات اولوية عالية | 8895600 | 444780 | 7234234.85 | 4583902.68 | 1010326466 | لا | 0 |  | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2020-03-25 | 2022-03-25 | 2022-09-23 | 2022-09-23 | 2022-03-25 |  | اخرى |  |  |  | منجز | No
2100021744 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 81531915 | 4076595.75 | 51270490 | 51270490 | 1010136405 | لا | 0 | 181209546932 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2012-11-27 | 2015-11-27 | 2022-12-31 | 2022-12-31 | 2015-11-27 |  |  |  | 38.2677 | 23.9883 | منجز | No
2100085094 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 93258236.34 | 4662911.817 | 83756123.04 | 83756123.04 | 2051002267 | لا | 0 | 180101000053 | جاري | منهجية القيمة المكتسبة | 91 | 100 | 2018-10-23 | 2021-10-19 | 2023-03-15 | 2023-03-15 |  |  | اخرى |  | 49.6626 | 27.0037 | متأخر | No
2100062484 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 16909971.6 | 845498.58 | 14895254.4 | 11888717.4 | 5800004732 | لا | 0 | 190509035653 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 88 | 100 | 2018-09-26 | 2020-03-10 | 2022-05-07 | 2022-05-07 |  |  |  |  | 41.5812 | 19.8649 | متأخر | No
2100010920 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 291309876 | 14565493.8 | 205599792.97 | 205599792.97 | 1010008118 | لا | 0 | 180809058704 | مسحوب | منهجية القيمة المكتسبة | 87 | 100 | 2013-12-04 | 2015-12-02 | 2023-03-30 | 2023-03-30 |  |  | أوامر تغيير |  | 49.6626 | 27.0037 | مسحوب | No
2100106584 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية منخفضة | 1533485 | 76674.25 | 1126121.68 | 1126121.68 | 1163002582 | لا | 0 | 181101343285 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 81.233 | 100 | 2019-01-27 | 2021-12-25 | 2022-02-28 | 2022-02-28 | 2021-12-25 |  | لا يوجد تأخير |  | 35.6899 | 27.3494 | منجز | No
2100054574 | أمانة / جازان | تشييد | ذات اولوية عالية | 18806916.63 | 940345.8315 | 5378929.05 | 5378929.05 | 1010193433 | لا | 0 | 180909111482 | جاري | الكميات التي تم تركيبها | 27 | 100 | 2014-09-23 | 2016-09-16 | 2022-03-30 | 2022-03-30 |  |  | ضعف كفاءة المقاول الفنية |  | 43.1044 | 17.2416 | Failed | No
2100092260 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية متوسطة | 36794659 | 1839732.95 | 24049225.73 | 24049225.73 | 4030450094 | لا | 0 | 180701032331 | جاري | منهجية القيمة المكتسبة | 90.92 | 98.04 | 2018-10-29 | 2021-09-27 | 2022-08-30 | 2022-08-30 |  |  | اخرى |  | 36.472 | 28.4346 | متأخر | No
2100006226 | وزارة التعليم | تشييد | ذات اولوية عالية | 6384531.3 | 319226.565 | 904754.34 | 904754.34 | 4030085763 | لا | 0 |  | مسحوب | التكلفة المفوترة | 18 | 39 | 2010-11-07 | 2012-06-29 | 2014-07-09 | 2014-07-09 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | مسحوب | No
2100002321 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 63168700 | 3158435 | 47778372.034 | 47778372.034 | 2060002548 | لا | 0 | 180809058488 | جاري | منهجية القيمة المكتسبة | 87 | 100 | 2011-09-27 | 2014-03-26 | 2023-03-28 | 2023-03-28 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 49.5648 | 27.1019 | Failed | No
2100055871 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 122656293.78 | 6132814.689 | 113161077.2 | 113161077.2 | 1123000085 | لا | 0 | 180301001028 | جاري | منهجية القيمة المكتسبة | 89 | 99 | 2018-11-11 | 2020-11-10 | 2024-04-30 | 2024-04-30 |  |  | أوامر تغيير |  | 49.5648 | 27.1019 | متأخر | No
2100001643 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 43623828.92 | 2181191.446 | 0 | 0 | 4030017054 | لا | 0 | 190801068061 | جاري | منهجية القيمة المكتسبة | 0 | 0 | 2020-12-13 | 2023-09-24 | 2025-10-08 | 2025-10-08 |  |  | لا يوجد تأخير |  | 49.6626 | 27.0037 | منتظم | No
2100003135 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 6399984 | 319999.2 | 2305313.244 | 2305313.244 | 1010466292 | لا | 0 |  | مسحوب | التكلفة المفوترة | 40 | 100 | 2011-03-05 | 2012-08-26 | 2023-12-15 | 2023-12-15 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | مسحوب | No
2100011874 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 19007665 | 950383.25 | 6228096.8 | 6228096.8 | 4030085763 | لا | 0 |  | مسحوب | التكلفة المفوترة | 36 | 100 | 2010-11-07 | 2012-06-20 | 2014-04-15 | 2014-04-15 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | مسحوب | No
2100057094 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 15299643 | 764982.15 | 4569629.04 | 4569629.04 | 1010466292 | لا | 0 |  | مسحوب | التكلفة المفوترة | 40 | 49 | 2012-04-22 | 2014-04-02 | 2016-06-26 | 2016-06-26 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | مسحوب | No
2100107262 | شركة المياه الوطنية / منطقة نجران | تشييد | ذات اولوية عالية | 29732670 | 1486633.5 | 14969592 | 14969592 | 5950006794 | لا | 0 | 181101278982 | ايقاف كلي | منهجية القيمة المكتسبة | 80.91 | 100 | 2018-12-17 | 2021-05-22 | 2022-10-02 | 2022-10-02 |  |  | لا يوجد تأخير |  | 44.2341 | 17.5757 | Failed | No
2100068051 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 2620818 | 131040.9 | 1158075 | 1158075 | 3550032557 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 44 | 100 | 2016-07-10 | 2021-03-16 | 2021-03-16 | 2021-03-16 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | مسحوب | No
2100056825 | أمانة / الرياض | دراسات هندسية | ذات اولوية متوسطة | 12346020 | 617301 | 12346020 | 11688040 | 1010322156 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-04-09 | 2016-12-20 | 2016-12-20 | 2016-12-20 | 2016-12-20 |  | اخرى |  |  |  | منجز | No
2100065085 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 715000 | 35750 | 715000 | 715000 | 2057002075 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 95 | 2019-06-08 | 2020-05-10 | 2020-05-10 | 2020-05-10 | 2020-05-10 |  |  |  | 48.3789 | 26.9882 | منجز | No
2100095012 | أمانة / تبوك | تصميم | ذات اولوية متوسطة | 5187000 | 259350 | 5187000 | 0 | 1010323435 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-08-03 | 2020-02-03 | 2020-02-03 | 2020-02-03 | 2020-02-03 |  | اخرى |  |  |  | منجز | Yes
2100094441 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية منخفضة | 10379000 | 518950 | 0 | 0 | 1010033701 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2007-09-01 | 2013-10-08 | 2009-09-01 | 2009-09-01 | 2013-10-08 | 2021-11-24 |  |  | 42.4784 | 18.3229 | منجز | No
2100034495 | أمانة / نجران | تشييد | ذات اولوية عالية | 2359450 | 117972.5 | 186226 | 0 | 5950002997 | لا | 0 | 230109005179 | ايقاف كلي | تكلفة العمل المنجز | 16 | 100 | 2020-01-09 | 2020-07-04 | 2023-01-11 | 2023-01-11 |  |  | اخرى |  | 44.2039 | 17.6093 | Failed | Yes
2100015632 | جامعة القصيم | تشييد | ذات اولوية عالية وعاجلة | 108693750 | 5434687.5 | 83071888.05 | 78918293.63 | 1131013992 | لا | 0 | 200409030344 | جاري | تكلفة العمل المنجز | 98 | 92 | 2018-04-01 | 2021-03-01 | 2023-02-19 | 2023-02-19 |  |  | تأخرصرف المستحقات المالية |  | 43.7556 | 26.3629 | منتظم | No
2100032384 | أمانة / الجوف | تشييد | ذات اولوية عالية وعاجلة | 2855950 | 142797.5 | 171357 | 171357 | 3450009076 | لا | 171750 |  | مسحوب | الكميات التي تم تركيبها | 10 | 100 | 2012-12-27 | 2013-12-30 | 2013-12-30 | 2013-12-30 |  |  | سوء التخطيط الاولي للمشروع |  | 37.1459 | 31.4681 | مسحوب | No
2100057282 | وزارة الثقافة | تصميم |  | 556000 | 27800 | 0 | 0 | 0 |  | 0 |  | جاري | اخرى | 20 | 85 | 2019-05-12 00:59 | 2020-05-11 00:59 | 2020-10-23 | 2020-10-23 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | Failed | No
2100038220 | الهيئة الملكية لمدينة مكة المكرمة و المشاعر المقدسة | تشييد | ذات اولوية عالية وعاجلة | 20916000 | 1045800 | 10259213 | 10256661 | 4031040412 |  | 0 | 190509071681 | جاري | الكميات التي تم تركيبها | 80 | 100 | 2018-08-30 | 2020-02-11 | 2021-10-01 | 2021-10-01 |  |  | تأخرصرف المستحقات المالية |  | 21.3914 | 39.9014 | Failed | No
2100004336 | الجامعة الاسلامية بالمدينة المنورة | تشييد | ذات اولوية متوسطة | 64368306.2 | 3218415.31 | 31705798 | 31705798 | 4030068284 | لا | 0 | 180709022086 | مسحوب | الكميات التي تم تركيبها | 68 | 100 | 2013-05-18 | 2016-08-30 | 2021-06-05 | 2021-06-05 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.5654 | 24.4807 | مسحوب | No
2100009892 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | تشييد | ذات اولوية عالية وعاجلة | 551374663.59 | 27568733.1795 | 396989754.3 | 374199864.67 | 1010074952 | لا | 0 | 180909090968 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-04-01 | 2015-06-21 | 2022-04-30 | 2022-04-30 | 2015-06-21 |  | تأخرصرف المستحقات المالية |  | 47.1167 | 17.485 | منجز | No
2100022046 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 52165996 | 2608299.8 | 44351644.66 | 44351644.66 | 1010305951 | لا | 0 | 181209546873 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 99.98 | 100 | 2013-02-10 | 2015-02-10 | 2023-01-01 | 2023-01-01 |  |  | أوامر تغيير |  | 38.268 | 23.9436 | Failed | No
2100042630 | جامعة القصيم | تشييد | ذات اولوية عالية وعاجلة | 119624963 | 5981248.15 | 120056372.41 | 120056372.41 | 1010006362 | لا | 0 | 200409030314 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-10-12 | 2017-09-26 | 2022-02-27 | 2022-02-27 | 2017-09-26 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 43.7653 | 26.3604 | منجز | No
2100033902 | أمانة / الجوف | تشييد | ذات اولوية عالية | 1886280 | 94314 | 517180 | 517180 | 3400011214 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 27 | 100 | 2014-02-23 | 2016-01-08 | 2016-01-08 | 2016-01-08 |  |  | سوء التخطيط الاولي للمشروع |  | 37.1461 | 31.4598 | مسحوب | No
2100096342 | شركة المياه الوطنية / منطقة الحدود الشمالية | إشراف | ذات اولوية عالية | 7945200 | 397260 | 7915278.59 | 6882356.01 | 1010406370 | لا | 0 | 180301001274 | جاري | التكلفة المفوترة | 99.62 | 100 | 2018-05-07 | 2021-05-07 | 2023-02-20 | 2023-02-20 |  |  | لا يوجد تأخير |  | 41.0206 | 30.9726 | خدمات عامة | No
2100191870 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 94804760 | 4740238 | 11700560.87 | 11700560.87 | 5850022870 | لا | 0 | 200101054657 | جاري | منهجية القيمة المكتسبة | 23.4 | 37.12 | 2021-02-07 | 2024-01-07 | 2024-01-07 | 2024-01-07 |  |  |  |  | 40.286 | 20.1383 | متأخر | No
2100057761 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية متوسطة | 25116750 | 1255837.5 | 12058624.92 | 12058624.92 | 1010178884 | لا | 0 | 180909093698 | مسحوب | منهجية القيمة المكتسبة | 50.29 | 100 | 2013-11-04 | 2016-04-08 | 2022-12-31 | 2022-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 36.4552 | 26.2524 | مسحوب | No
2100108356 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | تشييد | ذات اولوية عالية | 14732061.75 | 736603.0875 | 11513403.51 | 10057148.2 | 1010176525 | لا | 0 | 190501015204 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-10-17 | 2022-03-13 | 2023-02-28 | 2023-02-28 |  |  | تأخرصرف المستحقات المالية |  | 36.5638 | 28.4092 | Failed | No
2100022035 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 53862307 | 2693115.35 | 29993665 | 29993665 | 1010305951 | لا | 0 | 181209546859 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 99.96 | 100 | 2013-02-10 | 2015-02-10 | 2023-01-12 | 2023-01-12 |  |  |  |  | 38.2601 | 23.9834 | Failed | No
2100003581 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | تشييد | ذات اولوية متوسطة | 13935903.88 | 696795.194 | 12124235.6 | 12124235.6 | 1010296235 | لا | 0 | 181201445355 | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 90 | 100 | 2019-02-05 | 2020-10-31 | 2023-11-30 | 2023-11-30 |  |  | تأخرصرف المستحقات المالية |  | 47.1167 | 17.485 | متأخر | No
2100194913 | هيئة المدن الصناعية ومناطق التقنية | تشييد | ذات اولوية عالية | 79188153 | 3959407.65 | 58777517 | 58777517 | 1010063866 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 73 | 78 | 2020-04-01 | 2021-11-22 | 2023-04-15 | 2023-04-15 |  |  |  |  | 49.9865 | 26.2444 | منتظم | No
2100065170 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 3000000 | 150000 | 3000000 | 3000000 | 4650046008 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 100 | 100 | 2017-12-31 | 2018-06-26 | 2018-06-26 | 2018-06-26 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.5555 | 24.5115 | مسحوب | No
2100057363 | وزارة الدفاع / الإدارة الهندسية والاشغال بقوات الدفاع الجوي | تشييد | ذات اولوية متوسطة | 11990614.7 | 599530.735 | 11990614.7 | 11990614.7 | 1010245185 | لا | 0 | 181101278881 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-04-02 | 2020-09-23 | 2021-06-27 | 2021-06-27 | 2020-09-23 |  | أوامر سامية |  | 39.2244 | 21.4006 | منجز | No
2100109292 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية منخفضة | 29189483 | 1459474.15 | 23071320.17 | 20175927.54 | 3450002829 | لا | 0 | 180909079000 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 97.99 | 100 | 2013-02-11 | 2015-01-21 | 2019-12-19 | 2019-12-19 |  | 2015-01-21 | لا يوجد تأخير |  | 36.498 | 28.461 | منجز | No
2100042276 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 5294444 | 264722.2 | 1265990.4 | 1265990.4 | 1010466292 | لا | 0 |  | مسحوب | التكلفة المفوترة | 1 | 46 | 2012-05-27 | 2013-11-18 | 2016-07-18 | 2016-07-18 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | مسحوب | No
2100049033 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 11076823 | 553841.15 | 4333938 | 4333938 | 4030139128 | لا | 0 | 181009135049 | مسحوب | تكلفة العمل المنجز | 48.72 | 100 | 2014-12-27 | 2015-12-17 | 2021-12-01 | 2021-12-01 |  |  | ضعف كفاءة المقاول الفنية |  | 36.4731 | 26.2265 | مسحوب | No
2100036326 | أمانة / تبوك | تشييد | لم تعد تحتاجها الجهة | 7171586.4 | 358579.32 | 5107202.74 | 5107202.74 | 4030139128 | لا | 0 | 180709031161 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-10-08 | 2021-11-02 | 2020-10-25 | 2020-10-25 | 2021-11-02 |  | ضعف كفاءة المقاول الفنية |  | 36.5701 | 28.3532 | منجز | No
2100009520 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 69993260 | 3499663 | 69993260 | 69993260 | 3555000709 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-05-29 | 2022-08-14 | 2022-08-14 | 2022-08-14 | 2022-08-14 |  | ضعف كفاءة المقاول الفنية |  | 39.6082 | 24.4853 | منجز | No
2100099746 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 99888084.8 | 4994404.24 | 69354611.11 | 69354611.11 | 4031019848 | لا | 0 |  | جاري | تكلفة العمل المنجز | 69.43 | 69.43 | 2017-09-10 | 2020-09-09 | 2023-06-29 | 2023-06-29 |  |  |  | أخرى | 39.8797 | 21.3348 | Failed | No
2100000840 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية متوسطة | 11248268.4 | 562413.42 | 526424.37 | 526424.37 | 3550025982 | لا | 0 | 200309034163 | ايقاف كلي | منهجية القيمة المكتسبة | 13.59 | 100 | 2018-04-11 | 2019-09-24 | 2022-12-31 | 2022-12-31 |  |  | لا يوجد تأخير |  | 36.469 | 26.2554 | Failed | No
2100091814 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية متوسطة | 73503587 | 3675179.35 | 60510053.53 | 58582702.33 | 1010014082 | لا | 0 | 180909078981 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99.02 | 100 | 2017-11-16 | 2019-10-26 | 2021-07-11 | 2021-07-11 | 2019-10-26 |  | لا يوجد تأخير |  | 36.09 | 28.9062 | منجز | No
2100038835 | وزارة النقل والخدمات اللوجستية / منطقة حائل | تشييد | ذات اولوية متوسطة | 43769999.23 | 2188499.9615 | 39392999 | 39392999 | 3350000631 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2010-08-17 | 2018-07-25 | 2018-07-25 | 2018-07-25 | 2018-07-25 | [5 empty] | منجز | No
2100037973 | وزارة النقل والخدمات اللوجستية / منطقة القصيم | تشييد | ذات اولوية عالية | 48677500 | 2433875 | 42895027.82 | 42895027.82 | 1010095105 | لا | 0 | 181109353288 | جاري | الكميات التي تم تركيبها | 97.4 | 100 | 2012-08-27 | 2016-07-14 | 2022-10-15 | 2022-10-15 |  |  | ضعف كفاءة المقاول الفنية |  | 43.3643 | 26.0278 | Failed | No
2100039200 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية منخفضة | 5999997 | 299999.85 | 5277850 | 5277850 | 5856021642 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2012-09-05 | 2019-09-16 | 2012-09-04 | 2012-09-04 | 2019-09-16 | 2021-07-26 |  |  | 42.4735 | 18.4032 | منجز | No
2100053815 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية عالية | 66991473 | 3349573.65 | 66251318 | 66251318 | 5855000147 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2013-10-26 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2020-02-11 |  |  | 42.0267 | 18.5459 | منجز | No
2100060675 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية وعاجلة | 81134089.05 | 4056704.4525 | 54922440 | 38700731.75 | 2050003475 | لا | 0 | 180901097206 | جاري | منهجية القيمة المكتسبة | 94.5 | 100 | 2018-12-06 | 2021-11-03 | 2022-09-30 | 2022-09-30 |  |  | اخرى |  | 43.5862 | 26.4875 | متأخر | No
2100015120 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 54959245 | 2747962.25 | 15886152.5 | 15886152.5 | 5860007938 | لا | 0 | 180701022985 | جاري | الكميات التي تم تركيبها | 48.7 | 59.39 | 2018-09-20 | 2021-02-21 | 2023-09-13 | 2023-09-13 |  |  |  |  | 42.5117 | 18.2465 | متأخر | No
2100038522 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | لم تعد تحتاجها الجهة | 5160001 | 258000.05 | 0 | 0 | 4031046917 | لا | 0 | 12800108 | فسخ العقد | الكميات التي تم تركيبها | 0 | 0 | 2012-05-27 | 2015-08-20 | 2017-06-01 | 2017-06-01 |  |  | اخرى |  | 39.834 | 21.3116 | مسحوب | No
2100054401 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 159520000 | 7976000 | 143733801.46 | 143733801.46 | 1010008118 | لا | 0 | 181109333755 | مسحوب | الكميات التي تم تركيبها | 89.83 | 100 | 2010-08-17 | 2014-01-04 | 2014-01-04 | 2014-01-04 |  |  | اخرى |  | 42.4695 | 18.3091 | مسحوب | No
2100083985 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 52230121.47 | 2611506.0735 | 35690964.96 | 35690964.96 | 1010009590 | لا | 0 | 191201121934 | ايقاف كلي | الكميات التي تم تركيبها | 78.08 | 90.06 | 2020-04-06 | 2021-11-26 | 2021-11-27 | 2021-11-27 |  |  | اخرى |  | 42.5924 | 18.2623 | Failed | No
2100066500 | أمانة / حفر الباطن | تشييد | ذات اولوية متوسطة | 9305217 | 465260.85 | 5412844 | 5412844 | 1010008188 | لا | 0 |  | جاري | تكلفة العمل المنجز | 79 | 100 | 2019-01-09 | 2022-01-11 | 2023-01-01 | 2023-01-01 |  |  | ضعف كفاءة المقاول الفنية |  | 46.0207 | 28.3793 | Failed | No
2100059581 | أمانة / جازان | تشييد | ذات اولوية عالية وعاجلة | 1493540 | 74677 | 829108.94 | 829108.94 | 5905009914 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 58 | 100 | 2018-09-17 | 2019-09-12 | 2022-02-01 | 2022-02-01 |  |  | ضعف كفاءة المقاول الفنية |  | 42.6981 | 16.9799 | مسحوب | No
2100061342 | وزارة الثقافة | تشييد |  | 4982250 | 249112.5 | 3402876.75 | 3402876.75 | 1010156756 |  | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-02-25 00:59 | 2020-04-24 00:59 | 2020-04-24 | 2020-04-24 | 2020-04-24 00:59 |  | موافقات |  |  |  | منجز | No
2100070744 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 122018283.9 | 6100914.195 | 104131644 | 104131644 | 5855021000 | لا | 0 | 190509108068 | مسحوب | الكميات التي تم تركيبها | 85.88 | 100 | 2009-10-06 | 2012-09-03 | 2021-12-05 | 2021-12-05 |  |  |  |  | 42.6783 | 18.2886 | مسحوب | No
2100084000 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 73355250 | 3667762.5 | 26249414 | 26249414 | 1010247052 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 34.93 | 100 | 2011-12-12 | 2016-04-23 | 2016-04-23 | 2016-04-23 |  |  | اخرى |  | 42.5531 | 18.3377 | Failed | No
2100060535 | جامعة الإمام محمد بن سعود الاسلامية | تشييد | ذات اولوية عالية وعاجلة | 971009270 | 48550463.5 | 825284441.55 | 825284441.55 | 1010053925 | لا | 0 |  | جاري | اخرى | 86 | 100 | 2012-05-01 | 2015-03-30 | 2023-02-28 | 2023-02-28 |  |  | أوامر تغيير |  | 46.7098 | 24.6275 | Failed | No
2100005891 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية وعاجلة | 317273736.12 | 15863686.806 | 57779599.63 | 57779599.63 | 1010014578 | لا | 0 | 180909089093 | جاري | مدفوعات ساعات العمل | 41.18 | 96.1 | 2010-06-28 | 2013-06-11 | 2024-12-31 | 2024-12-31 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | Failed | No
2100014873 | وزارة النقل والخدمات اللوجستية / منطقة حائل | تشييد | ذات اولوية متوسطة | 44561747 | 2228087.35 | 1876408 | 1876408 | 4650050716 | لا | 0 | 181109364720 | فسخ العقد | تكلفة العمل المنجز | 4.2 | 4.2 | 2015-08-11 | 2018-04-11 | 2018-04-11 | 2018-04-11 |  |  | اخرى |  | 41.7264 | 27.4396 | مسحوب | No
2100027635 | وزارة النقل والخدمات اللوجستية / منطقة حائل | تشييد | ذات اولوية عالية | 308389485 | 15419474.25 | 18330917 | 16255814 | 2060002548 | لا | 0 | 180701029998 | فسخ العقد | الكميات التي تم تركيبها | 7.8 | 22 | 2014-08-20 | 2020-04-08 | 2020-04-08 | 2020-04-08 |  |  | اخرى |  | 41.7208 | 27.5114 | مسحوب | No
2100006926 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 16425963 | 821298.15 | 8212981 | 0 | 4030142833 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 60 | 100 | 2007-08-08 | 2009-07-29 | 2023-01-15 | 2023-01-15 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | مسحوب | Yes
2100105884 | الرئاسة العامة لهيئة الأمر بالمعروف والنهي عن المنكر | تشييد | ذات اولوية عالية | 15889529 | 794476.45 | 6035510.07 | 6035510.07 | 1010120564 | لا | 0 | 190509110761 | جاري | الكميات التي تم تركيبها | 60 | 100 | 2013-09-10 | 2021-05-20 | 2022-03-31 | 2022-03-31 |  |  | تأخرصرف المستحقات المالية | مخطط لسحبه وإعادة ترسيته | 44.2365 | 17.601 | Failed | No
2100001761 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 11358305 | 567915.25 | 5218555 | 0 | 3350003498 | لا | 0 |  | جاري | التكلفة المفوترة | 57 | 100 | 2013-02-05 | 2015-01-26 | 2022-03-30 | 2022-03-30 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | Failed | Yes
2100083952 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 4198387 | 209919.35 | 4198387 | 2243519 | 1010335103 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2014-01-08 | 2014-12-28 | 2014-12-28 | 2014-12-28 | 2014-12-28 | 2018-08-18 |  |  | 42.5117 | 18.2465 | منجز | No
2100022352 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 165821764 | 8291088.2 | 129501090 | 82642237.84 | 1010054406 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2013-06-08 | 2015-05-29 | 2020-05-30 | 2020-05-30 | 2015-05-29 |  | ضعف كفاءة المقاول الفنية | أخرى | 36.5638 | 28.4092 | منجز | No
2100008676 | جامعة الحدود الشمالية | تشييد | ذات اولوية متوسطة | 161401248 | 8070062.4 | 49909217 | 49909217 | 1010142553 | لا | 0 | 181109304286 | ايقاف كلي | التكلفة المفوترة | 50 | 100 | 2011-09-20 | 2017-10-30 | 2024-12-30 | 2024-12-30 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال | مخطط لسحبه وإعادة ترسيته | 41.0346 | 30.951 | Failed | No
2100061224 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 4710075 | 235503.75 | 4824142.81 | 3512363 | 5805000328 | لا | 0 | 190309005517 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 65 | 84 | 2018-11-25 | 2019-11-15 | 2019-11-14 | 2019-11-14 | 2019-11-15 |  |  |  | 41.4693 | 19.9992 | منجز | No
2100058192 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 160000000 | 8000000 | 144000000 | 144000000 | 1010008118 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 85.86 | 100 | 2009-09-14 | 2012-08-11 | 2015-03-14 | 2015-03-14 |  |  | اخرى |  | 42.4766 | 18.3171 | مسحوب | No
2100053944 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 84185056.95 | 4209252.8475 | 75766622.89 | 75766622.89 | 5950010121 | لا | 0 | 181001218975 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-01-22 | 2020-12-30 | 2021-08-24 | 2021-08-24 | 2020-12-30 |  |  |  | 42.1785 | 19.9112 | منجز | No
2100077394 | وزارة النقل والخدمات اللوجستية / منطقة حائل | تشييد | ذات اولوية متوسطة | 27543760 | 1377188 | 4369854 | 4369854 | 1010184457 | لا | 0 | 180901072252 | مسحوب | تكلفة العمل المنجز | 29.5 | 63 | 2014-02-06 | 2016-01-15 | 2016-01-15 | 2016-01-15 |  |  | اخرى |  | 42.3359 | 27.9336 | مسحوب | No
2100081351 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 6774641 | 338732.05 | 4869477.74 | 0 | 1010242793 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 93.71 | 100 | 2014-09-24 | 2016-03-17 | 2020-11-15 | 2020-11-15 | 2016-03-17 |  | ضعف كفاءة المقاول الفنية |  | 44.7993 | 26.2798 | منجز | Yes
2100037461 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 14887995 | 744399.75 | 13124855 | 13124855 | 1010202928 | لا | 0 | 200509031917 | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2013-11-17 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2017-05-16 | 2019-09-15 |  |  | 42.5066 | 18.2205 | منجز | No
2100008960 | وزارة التجارة | تشييد | ذات اولوية عالية وعاجلة | 12696612.8 | 634830.64 | 8867177.16 | 8867177.16 | 1010156182 | لا | 0 | 180401001541 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-07-11 | 2021-07-15 | 2021-09-05 | 2021-09-05 |  | 2021-07-15 | أوامر تغيير |  | 36.5037 | 28.4304 | منجز | No
2100021405 | وزارة النقل والخدمات اللوجستية / المنطقة الشرقية | تشييد | ذات اولوية منخفضة | 40387280 | 2019364 | 25888173.84 | 25888173.84 | 1010202447 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 64.55 | 100 | 2012-09-05 | 2020-11-17 | 2021-11-17 | 2021-11-17 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 48.4423 | 28.3706 | مسحوب | No
2100070512 | وزارة النقل والخدمات اللوجستية / منطقة حائل | تشييد | ذات اولوية متوسطة | 52397708 | 2619885.4 | 3517823.33 | 0 | 3350000631 | لا | 0 | 181101221544 | فسخ العقد | الكميات التي تم تركيبها | 9.64 | 100 | 2019-01-20 | 2021-12-17 | 2021-12-18 | 2021-12-18 |  |  | اخرى |  | 41.7058 | 27.4805 | مسحوب | Yes
2100077556 | وزارة النقل والخدمات اللوجستية / منطقة تبوك | تشييد | لم تعد تحتاجها الجهة | 712500 | 35625 | 0 | 0 | 2051010618 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 0 | 0 | 2015-07-06 | 2015-12-29 | 2015-12-29 | 2015-12-29 |  |  | ضعف كفاءة المقاول الفنية |  | 37.6643 | 25.004 | مسحوب | No
2100094113 | وزارة النقل والخدمات اللوجستية / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 69999999.5 | 3499999.975 | 53228793.95 | 53228793.95 | 2060024520 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 93.6 | 100 | 2018-06-28 | 2020-11-23 | 2022-06-22 | 2022-06-22 |  |  |  |  | 50.0137 | 26.2576 | متأخر | No
2100084291 | وزارة النقل والخدمات اللوجستية / منطقة حائل | تشييد | ذات اولوية عالية | 83654951 | 4182747.55 | 58120950 | 0 | 2059001422 | لا | 0 |  | جاري | تكلفة العمل المنجز | 88.7 | 100 | 2019-01-17 | 2020-12-25 | 2022-11-15 | 2022-11-15 |  |  |  |  | 42.9185 | 28.1009 | متأخر | Yes
2100070291 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 19782031 | 989101.55 | 17865235 | 17865235 | 1010152168 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2011-12-10 | 2014-02-04 | 2014-02-24 | 2014-02-24 | 2014-02-04 | 2020-11-16 |  |  | 42.5408 | 18.1893 | منجز | No
2100070556 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 39166722 | 1958336.1 | 35250320 | 35250320 | 1123000085 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2014-07-21 | 2018-12-06 | 2018-12-16 | 2018-12-16 | 2018-12-06 | 2017-10-27 |  |  | 42.6889 | 18.0993 | منجز | No
2100001875 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 3421546 | 171077.3 | 3071545 | 3071545 | 1010436567 | لا | 0 | 200709052696 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-03-10 | 2020-04-26 | 2020-04-18 | 2020-04-18 | 2020-04-26 |  | لا يوجد تأخير |  | 39.8997 | 21.0785 | منجز | No
2100073032 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 72175945 | 3608797.25 | 64958350.75 | 64958350.75 | 7000646831 | لا | 0 | 181001218925 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-01-17 | 2020-12-25 | 2022-04-11 | 2022-04-11 | 2020-12-25 |  |  |  | 42.5006 | 18.4782 | منجز | No
2100084055 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 53065060 | 2653253 | 47133707 | 47133707 | 5860007938 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2011-07-06 | 2013-12-07 | 2021-07-15 | 2021-07-15 | 2013-12-07 | 2021-07-14 |  |  | 42.5265 | 18.2383 | منجز | No
2100204385 | جامعة أم القرى | تشييد | ذات اولوية عالية وعاجلة | 98121575.07 | 4906078.7535 | 78155121.51 | 78155121.51 | 4030138280 | لا | 0 | 211009013680 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2012-12-03 | 2015-11-03 | 2021-12-31 | 2021-12-31 | 2015-11-03 |  |  |  | 39.9389 | 21.323 | منجز | No
2100079085 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 32173472.42 | 1608673.621 | 28827842.16 | 28827842.16 | 1010136405 | لا | 0 |  | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 89 | 100 | 2019-09-18 | 2020-12-11 | 2022-07-16 | 2022-07-16 |  |  | تصاريح أعمال التنفيذ | أخرى |  |  | متأخر | No
2100074340 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 383383000.01 | 19169150.0005 | 254752568.81 | 254752568.81 | 1010008948 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2012-05-15 | 2015-04-29 | 2020-09-29 | 2020-09-29 | 2015-04-29 |  | موافقات | أخرى | 38.5466 | 27.6109 | منجز | No
2100094710 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 56433135 | 2821656.75 | 47278114 | 47278114 | 1010108612 | لا | 0 | 181109339024 | مسحوب | الكميات التي تم تركيبها | 77.66 | 100 | 2012-10-20 | 2016-01-13 | 2023-02-13 | 2023-02-13 |  |  | ضعف كفاءة المقاول الفنية |  | 39.7905 | 21.3959 | مسحوب | No
2100071035 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية عالية | 81871630.5 | 4093581.525 | 44333798.74 | 44333798.74 | 5855001146 | لا | 0 | 180301000824 | جاري | الكميات التي تم تركيبها | 66.47 | 81.78 | 2018-06-05 | 2020-11-06 | 2022-07-03 | 2022-07-03 |  |  |  |  | 42.6325 | 20.3808 | Failed | No
2100083871 | وزارة النقل والخدمات اللوجستية / منطقة حائل | تشييد | ذات اولوية متوسطة | 32653253.5 | 1632662.675 | 29370702 | 29370702 | 1123000085 | لا | 0 | 181101221411 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-01-17 | 2020-12-25 | 2021-12-21 | 2021-12-21 | 2020-12-25 |  |  |  | 41.6768 | 27.4717 | منجز | No
2100062801 | أمانة / الجوف | تشييد | ذات اولوية عالية وعاجلة | 72612288.17 | 3630614.4085 | 67552016.17 | 67552016.17 | 1134000444 | لا | 0 | 190709092898 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-06-23 | 2021-06-12 | 2023-02-05 | 2023-02-05 | 2021-06-12 |  |  |  | 40.1998 | 29.9401 | منجز | No
2100079531 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 4904511 | 245225.55 | 1417353 | 0 | 1116002399 | لا | 0 |  | مسحوب | التكلفة المفوترة | 25 | 100 | 2013-08-18 | 2015-02-10 | 2023-12-15 | 2023-12-15 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | مسحوب | Yes
2100096143 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 2097320 | 104866 | 0 | 0 | 3550025589 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 1 | 100 | 2015-08-08 | 2016-08-08 | 2021-04-06 | 2021-04-06 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | مسحوب | No
2100053874 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية منخفضة | 36735240 | 1836762 | 33061716 | 33061716 | 1010247052 | لا | 0 | 181109334221 | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2011-07-06 | 2013-12-22 | 2015-12-15 | 2015-12-15 | 2013-12-22 | 2021-04-24 |  |  | 42.4765 | 18.2613 | منجز | No
2100102561 | أمانة / تبوك | دراسة الجدوى | ذات اولوية متوسطة | 12981600 | 649080 | 12981600 | 12981600 | 1131052059 | لا | 0 |  | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2019-06-19 | 2021-06-08 | 2021-06-08 | 2021-06-08 | 2021-06-08 |  | اخرى |  |  |  | منجز | No
2100053130 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 81000000 | 4050000 | 79564235 | 79564235 | 5855005058 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2008-08-05 | 2012-09-19 | 2012-09-19 | 2012-09-19 | 2012-09-19 | 2017-04-11 |  |  | 42.7869 | 18.2312 | منجز | No
2100077350 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 90487998 | 4524399.9 | 9897436 | 9897436 | 1010247052 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 11.38 | 100 | 2014-11-16 | 2017-04-19 | 2017-04-19 | 2017-04-19 |  |  | اخرى |  | 42.5503 | 18.056 | مسحوب | No
2100053690 | وزارة النقل والخدمات اللوجستية / منطقة حائل | تشييد | ذات اولوية متوسطة | 11385865 | 569293.25 | 0 | 0 | 3350002763 | لا | 0 | 181109364499 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-01-09 | 2015-06-24 | 2015-06-24 | 2015-06-24 | 2015-06-24 |  |  |  | 41.5999 | 27.4212 | منجز | No
2100058170 | وزارة الحرس الوطني / الشؤون الصحية | تشييد | ذات اولوية عالية | 7804694 | 390234.7 | 1101863 | 0 | 4650007352 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 14 | 100 | 2015-04-19 | 2016-10-09 | 2022-12-31 | 2022-12-31 |  |  | عدم وجود مبالغ في البنود تغطي الأعمال المرصودة |  | 39.6368 | 24.5336 | Failed | Yes
2100063711 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 5148864 | 257443.2 | 1004077.04 | 512809.92 | 1010213931 | لا | 0 |  | مسحوب | التكلفة المفوترة | 20 | 100 | 2015-08-25 | 2017-02-15 | 2019-04-30 | 2019-04-30 |  |  | ضعف كفاءة المقاول الفنية |  | 39.836 | 21.4408 | مسحوب | No
2100063582 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 13287367 | 664368.35 | 1529958 | 1529958 | 7013469452 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2013-06-10 | 2015-05-31 | 2021-10-20 | 2021-10-20 | 2015-05-31 |  | ضعف كفاءة المقاول الفنية |  | 41.0859 | 19.1571 | منجز | No
2100079601 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية متوسطة | 77841334.22 | 3892066.711 | 39671967.65 | 39671967.65 | 1010014477 | لا | 0 | 180909074914 | جاري | منهجية القيمة المكتسبة | 86.9 | 100 | 2012-06-18 | 2014-05-27 | 2022-09-30 | 2022-09-30 |  |  | لا يوجد تأخير |  | 36.5743 | 28.3691 | Failed | No
2100020123 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية منخفضة | 6936750 | 346837.5 | 977472.5 | 977472.5 | 1010168729 | لا | 0 | 180909070700 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 15.07 | 92.47 | 2017-12-20 | 2018-08-13 | 2021-01-10 | 2021-01-10 | 2018-08-13 |  | لا يوجد تأخير |  | 36.5117 | 26.193 | منجز | No
2100015013 | وزارة النقل والخدمات اللوجستية / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 70560323.39 | 3528016.1695 | 63504291.05 | 63504291.05 | 1123000085 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2012-07-30 | 2022-03-22 | 2021-08-24 | 2021-08-24 | 2022-03-22 |  |  |  | 49.4457 | 25.3822 | منجز | No
2100192220 | جامعة جازان | دعم فني | ذات اولوية عالية وعاجلة | 13860000 | 693000 | 13828106.83 | 13828106.83 | 5900028256 | لا | 0 | 191001170695 | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 100 | 100 | 2020-02-05 | 2022-02-05 | 2022-06-04 | 2022-06-04 |  |  |  |  | 42.5418 | 16.9655 | متأخر | No
2100039012 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 39800000 | 1990000 | 31652349.75 | 31652349.75 | 1010066115 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2012-10-15 | 2015-03-18 | 2017-02-25 | 2017-02-25 | 2015-03-18 | 2020-02-23 |  |  | 39.2926 | 21.0642 | منجز | No
2100007976 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 4456863 | 222843.15 | 4456647.92 | 4376501.58 | 1010136405 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-11-28 | 2020-05-26 | 2022-02-01 | 2022-02-01 | 2020-05-26 |  | أوامر تغيير |  |  |  | منجز | No
2100012331 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية منخفضة | 3725000 | 186250 | 2987562.56 | 2463173.93 | 3550022094 | لا | 0 | 180909071515 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 97 | 100 | 2015-05-17 | 2017-10-18 | 2019-12-07 | 2019-12-07 | 2017-10-18 |  | لا يوجد تأخير |  | 36.5477 | 28.4063 | منجز | No
2100070766 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | لم تعد تحتاجها الجهة | 46319996.23 | 2315999.8115 | 41330765 | 41330765 | 1010184457 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 92.3 | 100 | 2008-07-07 | 2010-12-09 | 2023-02-07 | 2023-02-07 |  |  | ضعف كفاءة المقاول الفنية |  | 40.4248 | 21.2841 | مسحوب | No
2100063954 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 1326000 | 66300 | 208900 | 208900 | 3550025589 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 28 | 100 | 2015-09-14 | 2017-03-04 | 2020-12-15 | 2020-12-15 |  |  | ضعف كفاءة المقاول الفنية |  | 36.6457 | 28.5018 | مسحوب | No
2100055985 | أمانة / تبوك | دراسة الجدوى | لم تعد تحتاجها الجهة | 7824000 | 391200 | 1592400 | 1592400 | 1010323435 | لا | 0 | 180709015729 | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2017-10-01 | 2019-09-21 | 2019-09-21 | 2019-09-21 | 2019-09-21 |  | اخرى |  |  |  | منجز | No
2100005795 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | تشييد | ذات اولوية متوسطة | 1161901102.26 | 58095055.113 | 814115864.02 | 814115864.02 | 1010230789 | لا | 0 | 180709031347 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-04-10 | 2018-03-24 | 2021-09-19 | 2021-09-19 | 2018-03-24 |  | لا يوجد تأخير |  | 36.5638 | 28.4092 | منجز | No
2100063906 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 1180557 | 59027.85 | 405835 | 0 | 5950026666 | لا | 0 | 210601172735 | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2019-03-18 | 2020-04-28 | 2020-04-28 | 2020-04-28 | 2020-04-28 |  |  |  | 44.2382 | 17.6001 | منجز | Yes
2100108916 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 39995000 | 1999750 | 22665714.16 | 22665714.16 | 1010140330 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99.591 | 100 | 2016-09-29 | 2018-09-29 | 2020-08-09 | 2020-08-09 | 2018-09-29 |  | لا يوجد تأخير |  | 39.1971 | 21.567 | منجز | No
2100054541 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 107043994.36 | 5352199.718 | 78837441.71 | 78837441.71 | 4030170755 | لا | 0 | 181109340560 | جاري | الكميات التي تم تركيبها | 78.95 | 79.73 | 2011-10-03 | 2014-03-05 | 2023-03-07 | 2023-03-07 |  |  | اخرى |  | 39.1977 | 21.4749 | منتظم | No
2100086004 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 175848606.92 | 8792430.346 | 74263629.26 | 73152500.74 | 1010036045 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 84 | 100 | 2011-09-20 | 2013-09-09 | 2023-03-31 | 2023-03-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال | مخطط لسحبه وإعادة ترسيته | 37.2633 | 25.0313 | Failed | No
2100054445 | وزارة النقل والخدمات اللوجستية / منطقة الباحة | تشييد | ذات اولوية عالية | 189774803.05 | 9488740.1525 | 42490578.4 | 42490578.4 | 1010247052 | لا | 0 | 180701035774 | فسخ العقد | الكميات التي تم تركيبها | 22.39 | 100 | 2014-07-29 | 2019-12-26 | 2019-12-26 | 2019-12-26 |  |  | ضعف كفاءة المقاول الفنية |  | 41.4498 | 20.0284 | مسحوب | No
2100195974 | وزارة النقل والخدمات اللوجستية / منطقة تبوك | تشييد | ذات اولوية متوسطة | 72975000 | 3648750 | 228600 | 228600 | 3550021826 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 23 | 51.53 | 2018-11-04 | 2023-04-20 | 2023-04-20 | 2023-04-20 |  |  |  |  | 35.362 | 28.8755 | Failed | No
2100085411 | أمانة / تبوك | تصميم | لم تعد تحتاجها الجهة | 78750 | 3937.5 | 78750 | 0 | 3350029913 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-06-18 | 2019-09-29 | 2019-09-16 | 2019-09-16 | 2019-09-29 |  | اخرى |  |  |  | منجز | Yes
2100059986 | أمانة / جدة | تشييد | ذات اولوية عالية | 17466388 | 873319.4 | 6982931.34 | 4712824.75 | 4031036822 | لا | 0 | 190701080299 | جاري | الكميات التي تم تركيبها | 84 | 100 | 2019-09-16 | 2021-08-24 | 2023-01-30 | 2023-01-30 |  |  | اخرى |  | 39.2213 | 21.4967 | متأخر | No
2100087382 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية منخفضة | 20945476 | 1047273.8 | 15908417.82 | 14753785.05 | 1010194943 | لا | 0 | 180909081980 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 95.5 | 97.65 | 2015-04-19 | 2017-03-29 | 2020-10-07 | 2020-10-07 | 2017-03-29 |  | لا يوجد تأخير |  | 36.2522 | 28.8737 | منجز | No
2100097856 | وزارة الثقافة | تشييد |  | 1569477 | 78473.85 | 365280.3 | 365280.3 | 3556000251 |  | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-04-03 00:59 | 2020-01-22 00:59 | 2020-02-02 | 2020-02-02 | 2020-01-22 00:59 |  | لا يوجد تأخير |  |  |  | منجز | No
2100200185 | وزارة الداخلية / المديرية العامة للسجون | تشييد | ذات اولوية عالية وعاجلة | 51321994.75 | 2566099.7375 | 46120859.17 | 40709611.66 | 1010271361 | لا | 0 |  | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-11-06 | 2022-04-10 | 2022-11-05 | 2022-11-05 |  |  |  |  | 40.1847 | 29.904 | Failed | No
2100096832 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 7956982 | 397849.1 | 0 | 0 | 4030085763 | لا | 0 |  | مسحوب | التكلفة المفوترة | 59 | 28 | 2008-02-16 | 2010-02-06 | 2019-04-08 | 2019-04-08 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | مسحوب | No
2100078761 | أمانة / حائل | إشراف | ذات اولوية متوسطة | 585000 | 29250 | 585000 | 585000 | 1010537228 | لا | 0 | 190509053963 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-01-13 | 2020-07-06 | 2020-07-20 | 2020-07-20 | 2020-07-06 |  | اخرى |  | 42.1277 | 26.5033 | منجز | No
2100103283 | وزارة الدفاع / الإدارة الهندسية والاشغال بقوات الدفاع الجوي | تشييد | ذات اولوية متوسطة | 6722285.85 | 336114.2925 | 6722285.85 | 6722285.85 | 2050019840 | لا | 0 | 190101001964 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-02-17 | 2020-02-06 | 2020-02-05 | 2020-02-05 | 2020-02-06 |  | أوامر سامية |  | 50.1028 | 26.4535 | منجز | No
2100095060 | شركة الكهرباء | تشييد | ذات اولوية متوسطة | 37570375 | 1878518.75 | 30913586 | 30913586 | 2055002293 | نعم | 849600 |  | جاري | الكميات التي تم تركيبها | 99.6 | 100 | 2020-01-27 | 2020-12-31 | 2023-03-30 | 2023-03-30 |  |  | ضعف كفاءة المقاول الفنية |  | 49.566 | 25.424 | متأخر | No
2100022503 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 14987470 | 749373.5 | 14987469.9 | 14987469.9 | 4030028078 | لا | 0 | 180709022336 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2016-10-18 | 2017-07-11 | 2021-12-31 | 2021-12-31 | 2017-07-11 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.1677 | 21.5008 | منجز | No
2100040692 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 178248184.95 | 8912409.2475 | 157053344.95 | 157053344.95 | 1010066115 | لا | 0 | 180709034146 | جاري | منهجية القيمة المكتسبة | 89 | 94 | 2017-07-10 | 2019-07-08 | 2023-06-15 | 2023-06-15 |  |  | ضعف كفاءة المقاول الفنية |  | 49.6626 | 27.0037 | منتظم | No
2100068946 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1685323.5 | 84266.175 | 1685323.5 | 1685323.5 | 4046001694 | لا | 0 | 190301010438 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-02-24 | 2020-02-19 | 2020-02-19 | 2020-02-19 | 2020-02-19 |  | ضعف كفاءة المقاول الفنية |  | 41.3512 | 22.6212 | منجز | No
2100089946 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 493266289.53 | 24663314.4765 | 385480187.17 | 385480187.17 | 2051002267 | لا | 0 | 180701014906 | جاري | منهجية القيمة المكتسبة | 81 | 100 | 2018-09-06 | 2022-03-03 | 2023-03-28 | 2023-03-28 |  |  | اخرى |  | 49.6626 | 27.0037 | متأخر | No
2100055764 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تصميم وتشييد | ذات اولوية عالية وعاجلة | 101675402.86 | 5083770.143 | 66166781.5 | 66166781.5 | 1010140330 | لا | 0 | 180809049248 | جاري | منهجية القيمة المكتسبة | 82 | 100 | 2013-10-02 | 2016-02-03 | 2024-01-29 | 2024-01-29 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 49.5648 | 27.1019 | متأخر | No
2100016192 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 149279698.75 | 7463984.9375 | 116960938.07 | 116960938.07 | 2050004953 | لا | 0 | 180809049328 | جاري | منهجية القيمة المكتسبة | 78 | 100 | 2017-07-18 | 2020-03-24 | 2023-07-31 | 2023-07-31 |  |  | التنسيق مع أصحاب المصلحه (خدمات |  | 49.6626 | 27.0037 | متأخر | No
2100071422 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | دراسات هندسية | ذات اولوية عالية وعاجلة | 49711608 | 2485580.4 | 50563129.76 | 50563129.76 | 1010408393 | لا | 0 | 180809056961 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 95 | 100 | 2015-05-24 | 2020-05-23 | 2023-05-24 | 2023-05-24 | 2020-05-23 |  |  | أخرى | 49.5603 | 26.9931 | منجز | No
2100101010 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | دراسات هندسية | ذات اولوية عالية وعاجلة | 35062384.5 | 1753119.225 | 26016657.83 | 26016657.83 | 2251043785 | لا | 0 | 180809059449 | جاري | تكلفة العمل المنجز | 71 | 92 | 2014-09-28 | 2019-09-27 | 2023-09-28 | 2023-09-28 |  |  |  | أخرى | 49.5715 | 26.9602 | خدمات عامة | No
2100077932 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | دراسات هندسية | ذات اولوية عالية وعاجلة | 13499500 | 674975 | 10937061.64 | 10937061.64 | 2050087924 | لا | 0 | 180401001794 | جاري | تكلفة العمل المنجز | 78 | 92 | 2018-06-09 | 2023-06-08 | 2023-06-08 | 2023-06-08 |  |  |  | أخرى | 49.5681 | 26.9938 | خدمات عامة | No
2100097554 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 129850189.49 | 6492509.4745 | 57782826.7 | 57782826.7 | 1010076961 | لا | 0 | 180809057280 | مسحوب | منهجية القيمة المكتسبة | 56 | 100 | 2013-08-28 | 2016-02-24 | 2023-06-16 | 2023-06-16 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 49.6626 | 27.0037 | مسحوب | No
2100054563 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 120351635.55 | 6017581.7775 | 68309948.81 | 68309948.81 | 1010066115 | لا | 0 |  | جاري | تكلفة العمل المنجز | 56.9 | 100 | 2013-12-18 | 2014-12-18 | 2019-06-25 | 2019-06-25 |  |  | التنسيق مع أصحاب المصلحه (خدمات |  | 39.8723 | 21.3811 | Failed | No
2100058435 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 19180707 | 959035.35 | 0 | 0 | 2057001038 | لا | 0 |  | مسحوب | التكلفة المفوترة | 29 | 100 | 2015-01-17 | 2016-07-13 | 2023-06-15 | 2023-06-15 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | مسحوب | No
2100015875 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 13102582.4 | 655129.12 | 3359945.8 | 0 | 1010174503 | نعم | 3359946 |  | مسحوب | التكلفة المفوترة | 26 | 100 | 2010-03-19 | 2012-01-09 | 2012-01-09 | 2012-01-09 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5604 | 25.3897 | مسحوب | Yes
2100091206 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | دراسة بيئية | ذات اولوية عالية وعاجلة | 41243620 | 2062181 | 30839263.8 | 30839263.8 | 1010320728 | لا | 0 | 180809058515 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 93 | 100 | 2011-07-11 | 2016-07-10 | 2022-12-31 | 2022-12-31 | 2016-07-10 |  |  |  | 49.1922 | 27.4995 | منجز | No
2100101544 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 589921069.54 | 29496053.477 | 448497727.93 | 448497727.93 | 2055003728 | لا | 0 | 180809049358 | جاري | منهجية القيمة المكتسبة | 94 | 100 | 2014-07-08 | 2017-07-04 | 2023-06-14 | 2023-06-14 |  |  | اخرى |  | 49.1594 | 27.5133 | متأخر | No
2100073802 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 87325192.27 | 4366259.6135 | 72985212.69 | 72985212.69 | 2050004953 | لا | 0 | 181109323420 | جاري | منهجية القيمة المكتسبة | 84 | 100 | 2018-04-09 | 2020-04-06 | 2023-10-28 | 2023-10-28 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 49.5648 | 27.1019 | متأخر | No
2100040224 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 77944311.73 | 3897215.5865 | 68048333.66 | 68048333.66 | 2050027937 | لا | 0 | 180809058608 | جاري | منهجية القيمة المكتسبة | 59 | 100 | 2017-02-12 | 2019-02-10 | 2023-05-30 | 2023-05-30 |  |  | عدم وجود كوادر كافية في الجهه لادارة المشروع |  | 49.5648 | 27.1019 | Failed | No
2100095841 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 64500000 | 3225000 | 50187037.67 | 50187037.67 | 2050027937 | لا | 0 | 180809058554 | جاري | منهجية القيمة المكتسبة | 33 | 100 | 2017-11-06 | 2019-09-09 | 2023-10-24 | 2023-10-24 |  |  | عدم وجود كوادر كافية في الجهه لادارة المشروع |  | 49.5648 | 27.1019 | Failed | No
2100067130 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 7337458 | 366872.9 | 5796855 | 5796855 | 4030113058 | لا | 0 | 180709025428 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 99 | 100 | 2017-11-06 | 2019-11-05 | 2023-01-14 | 2023-01-14 |  |  | عدم وجود كوادر كافية في الجهه لادارة المشروع |  | 38.1914 | 24.0066 | Failed | No
2100055160 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 82112952 | 4105647.6 | 82112952 | 82112952 | 4030056662 | لا | 0 | 180809057732 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2015-03-17 | 2017-03-16 | 2022-07-18 | 2022-07-18 | 2017-03-16 |  | أوامر تغيير |  | 38.3339 | 23.8833 | منجز | No
2100069753 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 3949200 | 197460 | 3826059.25 | 3826059.25 | 5808013465 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 82.24 | 100 | 2014-02-19 | 2016-01-30 | 2016-01-30 | 2016-01-30 | 2016-01-30 |  |  |  | 41.467 | 20.003 | منجز | No
2100034764 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 16149755 | 807487.75 | 4873307 | 4873307 | 1010312806 | لا | 0 | 180909087656 | مسحوب | منهجية القيمة المكتسبة | 63.25 | 100 | 2015-02-22 | 2017-02-21 | 2022-07-18 | 2022-07-18 |  |  | اخرى |  | 38.3156 | 23.9555 | مسحوب | No
2100042560 | الجمارك السعودية | تشييد | ذات اولوية عالية | 4853240 | 242662 | 2762270.5 | 2762270.5 | 5854000232 | نعم | 2885982.45 | 180901097732 | مسحوب | تكلفة العمل المنجز | 79 | 100 | 2017-09-13 | 2018-03-14 | 2019-06-17 | 2019-06-17 |  |  | ضعف كفاءة المقاول الفنية |  | 51.5226 | 24.1624 | مسحوب | No
2100001886 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية عالية | 19595338 | 979766.9 | 17562507 | 17562507 | 1118000259 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-11-20 | 2016-10-17 | 2021-09-30 | 2021-09-30 | 2016-10-17 |  |  |  | 36.5753 | 28.2608 | منجز | No
2100078061 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 47940728 | 2397036.4 | 38708075 | 38708075 | 1010168729 | لا | 0 | 180201000191 | جاري | منهجية القيمة المكتسبة | 97 | 98.99 | 2018-10-03 | 2020-10-01 | 2023-01-26 | 2023-01-26 |  |  | أوامر تغيير |  | 38.1848 | 24.0283 | منتظم | No
2100041311 | أمانة / العاصمة المقدسة | تصميم | ذات اولوية متوسطة | 1275750 | 63787.5 | 1129000 | 1129000 | 1010326466 | لا | 0 | 200309117600 | منجز – استلام نهائي | مدفوعات ساعات العمل | 88.5 | 88.5 | 2019-10-21 | 2020-10-09 | 2022-08-10 | 2022-08-10 | 2020-10-09 | 2022-09-04 | عدم اكتمال أو ضعف أعمال التصميم والدراسات |  |  |  | منجز | No
2100018712 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 933579 | 46678.95 | 0 | 0 | 2057001038 | لا | 0 |  | جاري | التكلفة المفوترة | 40 | 100 | 2013-02-02 | 2013-10-29 | 2022-11-16 | 2022-11-16 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | Failed | No
2100003275 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 933579 | 46678.95 | 392040 | 392040 | 2057001038 | لا | 0 |  | مسحوب | التكلفة المفوترة | 38 | 100 | 2012-07-13 | 2013-04-09 | 2017-05-24 | 2017-05-24 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | مسحوب | No
2100003780 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 3280084 | 164004.2 | 3053868.93 | 3053868.93 | 3550024033 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2016-01-03 | 2017-03-28 | 2022-10-11 | 2022-10-11 | 2017-03-28 |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | منجز | No
2100021000 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 29930939.85 | 1496546.9925 | 19277386.62 | 19277386.62 | 1010257051 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 94.02 | 99.46 | 2020-01-01 | 2020-07-01 | 2022-04-30 | 2022-04-30 | 2020-07-01 |  | اخرى |  | 49.5131 | 26.7886 | منجز | No
2100042346 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 3766693 | 188334.65 | 260514.24 | 260514.24 | 1010052618 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 6 | 100 | 2013-08-21 | 2015-02-12 | 2021-01-10 | 2021-01-10 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | مسحوب | No
2100056394 | أمانة / تبوك | تصميم | ذات اولوية متوسطة | 94185 | 4709.25 | 94185 | 94185 | 4030282813 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-07-01 | 2019-10-29 | 2019-10-29 | 2019-10-29 | 2019-10-29 |  | اخرى |  |  |  | منجز | No
2100042453 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2855707 | 142785.35 | 0 | 0 | 1010188764 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 1 | 100 | 2012-01-02 | 2013-03-20 | 2023-08-16 | 2023-08-16 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | مسحوب | No
2100021210 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 6408413 | 320420.65 | 2085627.5 | 2085627.5 | 4030085763 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 39 | 100 | 2010-11-07 | 2010-11-08 | 2021-01-10 | 2021-01-10 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | مسحوب | No
2100026692 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 7585738.58 | 379286.929 | 1338025.1 | 1338025.1 | 1010052618 | لا | 0 |  | مسحوب | التكلفة المفوترة | 17 | 100 | 2013-09-29 | 2015-09-19 | 2023-02-08 | 2023-02-08 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | مسحوب | No
2100079472 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 4793838 | 239691.9 | 1283285.82 | 1283285.82 | 1010142553 | لا | 0 |  | مسحوب | التكلفة المفوترة | 46 | 100 | 2015-04-05 | 2016-09-26 | 2019-10-26 | 2019-10-26 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | مسحوب | No
2100076915 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 106400 | 5320 | 95760 | 95760 | 3550023679 | لا | 0 | 190509000087 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-11-01 | 2019-08-24 | 2021-09-01 | 2021-09-01 | 2019-08-24 |  | اخرى |  | 38.5165 | 27.6122 | منجز | No
2100097031 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية متوسطة | 6721186.87 | 336059.3435 | 300894.21 | 300894.21 | 1010264550 | لا | 0 | 180909078847 | مسحوب | منهجية القيمة المكتسبة | 54.63 | 100 | 2013-11-04 | 2016-04-08 | 2022-12-31 | 2022-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 38.5173 | 27.6119 | مسحوب | No
2100007674 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 28543176 | 1427158.8 | 5523249.69 | 5523249.69 | 3550019326 | لا | 0 |  | مسحوب | التكلفة المفوترة | 18 | 48 | 2014-03-17 | 2016-03-05 | 2023-06-14 | 2023-06-14 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | مسحوب | No
2100086505 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2016866 | 100843.3 | 34807.79 | 34807.79 | 1010026700 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 7 | 100 | 2006-07-10 | 2007-05-25 | 2019-03-12 | 2019-03-12 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 36.5638 | 28.4092 | مسحوب | No
2100009726 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | تشييد | ذات اولوية متوسطة | 15800874.6 | 790043.73 | 13479622.25 | 5451268.47 | 1010404410 | لا | 0 | 190401114531 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-07-15 | 2021-10-10 | 2021-10-10 | 2021-10-10 | 2021-10-10 |  | لا يوجد تأخير |  | 42.7302 | 18.3003 | منجز | No
2100106783 | وزارة الدفاع / الإدارة الهندسية والاشغال بالخدمات الصحية | تشييد | ذات اولوية متوسطة | 7918662.5 | 395933.125 | 7268006.85 | 7268006.85 | 4030130776 | لا | 0 | 180909090530 | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 100 | 100 | 2017-07-17 | 2018-12-28 | 2022-11-15 | 2022-11-15 |  |  | اخرى |  | 39.583 | 24.6158 | Failed | No
2100096622 | أمانة / تبوك | دراسة الجدوى | ذات اولوية متوسطة | 10524000 | 526200 | 10455438 | 10164792 | 1010326466 | لا | 0 |  | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2018-03-24 | 2020-03-23 | 2020-03-23 | 2020-03-23 | 2020-03-23 |  | اخرى |  |  |  | منجز | No
2100086601 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 9588880.06 | 479444.003 | 7764779.92 | 7764779.92 | 1166003901 | لا | 0 |  | مسحوب | التكلفة المفوترة | 85 | 100 | 2010-04-30 | 2012-01-23 | 2023-01-15 | 2023-01-15 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | مسحوب | No
2100010662 | وزارة الدفاع / الإدارة الهندسية والاشغال بالخدمات الصحية | تشييد | ذات اولوية عالية | 2929290 | 146464.5 | 1763831.64 | 1763831.64 | 1010216372 | لا | 0 | 200309132778 | جاري | الكميات التي تم تركيبها | 76 | 95.83 | 2020-01-22 | 2021-06-25 | 2022-10-21 | 2022-10-21 |  |  | اخرى |  | 44.1106 | 26.1862 | متأخر | No
2100002520 | وزارة الدفاع / الإدارة الهندسية والاشغال بالخدمات الصحية | تشييد | ذات اولوية متوسطة | 40436143 | 2021807.15 | 31218215.87 | 31218215.87 | 2050026979 | لا | 0 | 181101307326 | جاري | الكميات التي تم تركيبها | 81 | 90 | 2019-04-09 | 2021-09-04 | 2023-08-24 | 2023-08-24 |  |  | تغيرات في نطاق المشروع |  | 50.0619 | 26.4189 | متأخر | No
2100108533 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 10140020.52 | 507001.026 | 1578573.78 | 0 | 1132000522 | لا | 0 |  | مسحوب | التكلفة المفوترة | 23 | 100 | 2013-09-24 | 2015-09-02 | 2021-10-15 | 2021-10-15 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5264 | 28.3676 | مسحوب | Yes
2100016052 | وزارة الدفاع / الإدارة الهندسية والاشغال بالخدمات الصحية | تشييد | ذات اولوية متوسطة | 4808979 | 240448.95 | 198750 | 198750 | 4030173390 | لا | 0 |  | لم يبدأ | الكميات التي تم تركيبها | 0 | 0 | 2020-05-04 | 2021-07-09 | 2022-07-19 | 2022-07-19 |  |  | اخرى |  | 39.2694 | 21.6518 | متأخر | No
2100059791 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البحرية | تشييد | ذات اولوية متوسطة | 16499590 | 824979.5 | 7293901 | 7293901 | 2251012432 | لا | 0 | 190201002797 | جاري | الكميات التي تم تركيبها | 74 | 100 | 2019-06-27 | 2021-10-27 | 2021-12-31 | 2021-12-31 |  |  |  |  | 50.1237 | 26.3077 | Failed | No
2100106956 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البحرية | تشييد | ذات اولوية متوسطة | 12345550 | 617277.5 | 7355400 | 7355400 | 1010156182 | لا | 0 | 190101004151 | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-07-04 | 2022-06-10 | 2023-03-30 | 2023-03-30 |  |  |  |  | 50.0518 | 26.4904 | منتظم | No
2100108393 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البرية | تشييد | ذات اولوية متوسطة | 3969000 | 198450 | 3969000 | 3969000 | 3550023851 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-10-06 | 2020-09-25 | 2021-09-19 | 2021-09-19 | 2020-09-25 |  | تأخرصرف المستحقات المالية |  | 36.6054 | 28.309 | منجز | No
2100205590 | وزارة الثقافة | تصميم وتشييد | ذات اولوية متوسطة | 13795685.2 | 689784.26 | 3931770.39 | 3931770.39 | 4030138444 | لا | 0 |  | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2021-08-02 | 2022-07-13 | 2022-02-11 | 2022-02-11 | 2022-07-13 | 2022-07-14 |  |  | 46.6249 | 24.6822 | منجز | No
2100004675 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البرية | تشييد | ذات اولوية متوسطة | 1018500 | 50925 | 1018500 | 1018500 | 1010056094 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-09-15 | 2018-12-23 | 2020-11-01 | 2020-11-01 | 2018-12-23 |  | تأخرصرف المستحقات المالية |  | 36.6093 | 28.3406 | منجز | No
2100026950 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 14684312.47 | 734215.6235 | 14684312.47 | 14684312.47 | 5810001890 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 97 | 97 | 2015-01-29 | 2017-01-17 | 2021-03-30 | 2021-03-30 | 2017-01-17 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 41.7053 | 20.3191 | منجز | No
2100011675 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البرية | تشييد | ذات اولوية متوسطة | 2645818.88 | 132290.944 | 2485130.24 | 2485130.24 | 1011012750 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-12-27 | 2019-12-18 | 2021-12-31 | 2021-12-31 | 2019-12-18 |  | تأخرصرف المستحقات المالية |  | 36.5836 | 28.3733 | منجز | No
2100108426 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البرية | تشييد | ذات اولوية متوسطة | 1596000 | 79800 | 1100000 | 1100000 | 1010056094 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-11-25 | 2019-02-25 | 2021-12-31 | 2021-12-31 | 2019-02-25 |  | تأخرصرف المستحقات المالية |  | 36.6019 | 28.4049 | منجز | No
2100108220 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات الجوية | تشييد | ذات اولوية عالية | 16323049.66 | 816152.483 | 14822406.43 | 14822406.43 | 1010310655 | لا | 0 | 200509016675 | جاري | الكميات التي تم تركيبها | 88 | 100 | 2020-04-02 | 2021-04-01 | 2022-08-31 | 2022-08-31 |  |  | تصاريح أعمال التنفيذ |  | 39.1131 | 21.5553 | متأخر | No
2100022492 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات الجوية | دراسات هندسية | ذات اولوية متوسطة | 2021250 | 101062.5 | 2021250 | 2021250 | 1010326073 | لا | 0 | 191001018290 | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2019-10-27 | 2020-01-06 | 2021-05-31 | 2021-05-31 | 2020-01-06 |  |  |  | 50.0644 | 26.4197 | منجز | No
2100002881 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات الجوية | تشييد | ذات اولوية عالية | 2802518.25 | 140125.9125 | 2802518.25 | 2802518.25 | 1010286523 | لا | 0 | 200201097565 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2020-05-31 | 2021-10-02 | 2021-02-11 | 2021-02-11 | 2021-10-02 |  | لا يوجد تأخير |  | 46.6758 | 24.7031 | منجز | No
2100073581 | هيئة تطوير بوابة الدرعية | تشييد | ذات اولوية عالية | 99780009 | 4989000.45 | 60030314.37 | 60030314.37 | 1010085518 | لا | 0 | 200501046630 | جاري | اخرى | 99 | 100 | 2020-01-03 | 2020-09-20 | 2021-09-30 | 2021-09-30 |  |  |  |  | 46.5742 | 24.7368 | منتظم | No
2100100133 | الهيئة العامة للطيران المدني | تشييد | ذات اولوية عالية | 223910797.03 | 11195539.8515 | 139399515 | 139399515 | 1010034600 | لا | 0 | 190301094289 | ايقاف كلي | منهجية القيمة المكتسبة | 66.23 | 66.23 | 2019-04-08 | 2020-09-29 | 2023-11-18 | 2023-11-18 |  |  | اخرى |  | 42.5565 | 16.8965 | Failed | No
2100042022 | وزارة الدفاع / الإدارة الهندسية والاشغال بقوات الدفاع الجوي | تشييد | ذات اولوية متوسطة | 7502709.24 | 375135.462 | 7502709.24 | 6691666.37 | 5857020213 | لا | 0 | 190501060809 | جاري | الكميات التي تم تركيبها | 98 | 100 | 2019-09-15 | 2022-02-01 | 2022-05-09 | 2022-05-09 |  |  | أوامر سامية |  | 42.633 | 16.974 | Failed | No
2100026725 | وزارة الدفاع / الإدارة الهندسية والاشغال بقوات الدفاع الجوي | تشييد | ذات اولوية متوسطة | 7378275.2 | 368913.76 | 7378275.2 | 7378275.2 | 2052001709 | لا | 0 | 190601030791 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-09-15 | 2021-06-06 | 2021-11-16 | 2021-11-16 | 2021-06-06 |  | أوامر سامية |  | 50.0926 | 26.4129 | منجز | No
2100057341 | وزارة الدفاع / الإدارة الهندسية والاشغال بقوات الدفاع الجوي | تشييد | ذات اولوية متوسطة | 10956897 | 547844.85 | 10956897 | 5466319.22 | 1010177619 | لا | 0 | 190901184913 | جاري | الكميات التي تم تركيبها | 68 | 100 | 2020-01-02 | 2021-12-14 | 2022-05-10 | 2022-05-10 |  |  | أوامر سامية |  | 46.6869 | 24.7082 | Failed | No
2100079973 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية | 50200890 | 2510044.5 | 36901912.2747 | 36901912.2747 | 1010014477 | لا | 0 | 180709019593 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2013-06-15 | 2016-05-13 | 2020-11-19 | 2020-11-19 |  | 2016-05-13 | لا يوجد تأخير |  | 43.9875 | 26.0873 | منجز | No
2100013963 | أمانة / حفر الباطن | تشييد | ذات اولوية متوسطة | 156000 | 7800 | 156000 | 156000 | 2511016672 | لا | 0 | 0 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-01-27 | 2019-07-01 | 2019-07-01 | 2019-07-01 | 2019-07-01 |  |  |  | 46.7125 | 28.103 | منجز | No
2100025642 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 8177707 | 408885.35 | 1880347.54 | 111697.62 | 1010052618 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 15 | 100 | 2013-09-29 | 2015-06-23 | 2020-12-15 | 2020-12-15 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5087 | 28.4381 | مسحوب | No
2100074955 | أمانة / تبوك | تشييد | لم تعد تحتاجها الجهة | 909628 | 45481.4 | 261940 | 261940 | 4701000456 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 45 | 45 | 2012-11-09 | 2013-07-27 | 2013-07-27 | 2013-07-27 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5237 | 28.4012 | مسحوب | No
2100190083 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية متوسطة | 1062090.96 | 53104.548 | 920412.76 | 920412.76 | 1010381316 | لا | 0 | 201001073551 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2021-03-28 | 2021-09-21 | 2021-10-21 | 2021-10-21 | 2021-09-21 |  |  |  | 45.4336 | 25.0684 | منجز | No
2100048123 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية عالية | 49959052 | 2497952.6 | 50094368.57 | 45082293.06 | 2050018628 | لا | 0 | 180801055965 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2018-12-02 | 2020-08-13 | 2021-02-02 | 2021-02-02 | 2020-08-13 |  |  |  | 50.0873 | 26.3894 | منجز | No
2100043245 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 3240530.2 | 162026.51 | 2849193.25 | 2849193.25 | 4030113058 | لا | 0 | 180809037604 | جاري | تكلفة العمل المنجز | 100 | 100 | 2017-10-29 | 2017-11-20 | 2021-12-31 | 2021-12-31 |  |  | تأخرصرف المستحقات المالية |  | 39.1677 | 21.5008 | Failed | No
2100039760 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 19738161 | 986908.05 | 15518088 | 15518088 | 2051041139 | نعم | 3493657 | 180809046711 | مسحوب | منهجية القيمة المكتسبة | 85 | 100 | 2017-11-08 | 2019-11-08 | 2022-10-04 | 2022-10-04 |  |  | ضعف كفاءة المقاول الفنية |  | 38.268 | 23.9436 | مسحوب | No
2100072741 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 6083957 | 304197.85 | 6083957 | 6083957 | 4030151374 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-12-11 | 2020-06-10 | 2020-09-05 | 2020-09-05 | 2020-06-10 |  | اخرى |  | 41.3073 | 18.9782 | منجز | No
2100063232 | جامعة الملك فيصل | دراسة الجدوى | ذات اولوية عالية | 8280090 | 414004.5 | 2028582 | 2028582 | 1010135922 | لا | 0 | 190201014817 | جاري | تكلفة العمل المنجز | 95 | 95 | 2018-01-28 | 2022-01-27 | 2022-01-27 | 2022-01-27 |  |  | تأخرصرف المستحقات المالية |  | 49.6054 | 25.3169 | خدمات عامة | No
2100051774 | أمانة / عسير | تشييد | ذات اولوية عالية | 11253700 | 562685 | 4286550 | 4286550 | 5859000601 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 61 | 100 | 2015-03-18 | 2017-02-14 | 2022-03-01 | 2022-03-01 |  |  | تأخرصرف المستحقات المالية |  | 42.1664 | 19.1177 | مسحوب | No
2100050890 | أمانة / الأحساء | تشييد | ذات اولوية عالية وعاجلة | 7862762 | 393138.1 | 7862762 | 7862762 | 1010381941 | لا | 0 | 180701031096 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-11-04 | 2020-04-27 | 2021-03-03 | 2021-03-03 | 2020-04-27 |  | ضعف كفاءة المقاول الفنية |  | 49.5907 | 25.3906 | منجز | No
2100092831 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 24536097.108 | 1226804.8554 | 24140567 | 24140567 | 2050018628 | لا | 0 | 190501069527 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-09-07 | 2021-08-27 | 2022-03-16 | 2022-03-16 | 2021-08-27 |  |  |  | 49.5952 | 25.3793 | منجز | No
2100077184 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية عالية | 55765020.6 | 2788251.03 | 25112138 | 25112138 | 4031041927 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 48.06 | 48.06 | 2015-02-16 | 2016-07-31 | 2020-06-07 | 2020-06-07 |  |  | ضعف اداء الاستشاري |  | 39.8665 | 21.3636 | مسحوب | No
2100053804 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 108522067.3 | 5426103.365 | 108084165.32 | 108084165.32 | 1010185409 | لا | 0 | 181109350645 | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2012-06-27 | 2016-05-13 | 2020-10-26 | 2020-10-26 | 2016-05-13 | 2021-07-08 |  |  | 39.8531 | 21.4055 | منجز | No
2100093391 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 18988000 | 949400 | 11355913.91 | 11355913.91 | 4030006066 | لا | 0 | 180401003757 | ايقاف كلي | تكلفة العمل المنجز | 79 | 100 | 2018-06-24 | 2020-06-13 | 2022-06-30 | 2022-06-30 |  |  | تأخرصرف المستحقات المالية |  | 41.627 | 21.2116 | Failed | No
2100189560 | الهيئة العامة للزكاة والدخل | تشييد | ذات اولوية عالية | 39233096.69 | 1961654.8345 | 39233096.69 | 39233096.69 | 3350012131 | لا | 0 |  | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2015-10-28 | 2020-03-01 | 2021-03-01 | 2021-03-01 |  | 2020-03-01 |  |  | 36.5339 | 28.4208 | منجز | No
2100095863 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 7653028 | 382651.4 | 3746035.99 | 0 | 4650026784 | لا | 0 |  | مسحوب | التكلفة المفوترة | 65 | 100 | 2011-01-30 | 2013-01-20 | 2023-01-15 | 2023-01-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | Yes
2100043164 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية عالية | 6265990 | 313299.5 | 5803059 | 5803059 | 1010014501 | لا | 0 | 180709030049 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-10-13 | 2017-03-17 | 2014-12-13 | 2014-12-13 | 2017-03-17 |  |  |  | 44.8672 | 22.7661 | منجز | No
2100002660 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية عالية | 54390897.59 | 2719544.8795 | 40191001.05 | 40191001.05 | 5855000147 | لا | 0 | 181109316648 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2007-01-09 | 2010-02-02 | 2014-08-26 | 2014-08-26 | 2010-02-02 |  |  |  | 42.8778 | 17.1917 | منجز | No
2100190315 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية عالية وعاجلة | 1108860 | 55443 | 129489.97 | 129489.97 | 4032034406 | لا | 0 | 190701046968 | مسحوب | الكميات التي تم تركيبها | 32 | 100 | 2019-09-01 | 2020-05-23 | 2020-10-12 | 2020-10-12 |  |  | ضعف كفاءة المقاول الفنية |  | 39.8736 | 21.384 | مسحوب | No
2100200233 | البريد السعودي | تصميم وتشييد | ذات اولوية عالية وعاجلة | 2273042 | 113652.1 | 437045.29 | 0 | 1010180090 | لا | 0 |  | جاري | اخرى | 87 | 94 | 2022-01-30 | 2023-02-18 | 2023-02-18 | 2023-02-18 |  |  |  |  | 39.1625 | 21.553 | متأخر | Yes
2100033692 | مدينة الملك عبدالعزيز للعلوم والتقنية | تشييد | ذات اولوية عالية | 836196.38 | 41809.819 | 0 | 0 | 4030064711 |  | 0 | 190409047769 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-04-11 | 2019-07-10 | 2019-07-10 | 2019-07-10 | 2019-07-10 |  |  |  | 39.222 | 21.4961 | منجز | No
2100080102 | وزارة الثقافة | تشييد |  | 32950119.02 | 1647505.951 | 23020541.57 | 23020541.57 | 1010070634 |  | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-04-09 00:59 | 2018-10-08 00:59 | 2020-03-12 | 2020-03-12 | 2018-10-08 00:59 |  | لا يوجد تأخير |  |  |  | منجز | No
2100012412 | أمانة / عسير | تشييد | ذات اولوية عالية | 1690022 | 84501.1 | 248128 | 248128 | 5856032758 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 14 | 100 | 2009-12-06 | 2010-12-08 | 2022-09-20 | 2022-09-20 |  |  | ضعف كفاءة المقاول الفنية |  | 43.1421 | 18.0895 | مسحوب | No
2100080345 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 6836370 | 341818.5 | 5810915 | 5810915 | 4650032795 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 85 | 100 | 2018-11-20 | 2022-01-11 | 2021-09-09 | 2021-09-09 | 2022-01-11 |  | ضعف كفاءة المقاول الفنية |  | 38.7906 | 23.7576 | منجز | No
2100081266 | أمانة / عسير | تشييد | ذات اولوية عالية | 3981946 | 199097.3 | 3566496 | 3566496 | 5852001934 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 89 | 100 | 2011-01-07 | 2012-01-02 | 2020-10-14 | 2020-10-14 |  |  | ضعف كفاءة المقاول الفنية |  | 42.2147 | 18.9051 | مسحوب | No
2100018804 | أمانة / عسير | تشييد | ذات اولوية عالية وعاجلة | 4796528 | 239826.4 | 600115 | 600115 | 5858031419 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 13 | 100 | 2015-03-14 | 2016-03-09 | 2022-09-20 | 2022-09-20 |  |  | ضعف كفاءة المقاول الفنية |  | 43.3259 | 17.5776 | مسحوب | No
2100039340 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 71522437 | 3576121.85 | 42935074 | 42935074 | 2051000654 | لا | 0 | 180709030378 | مسحوب | تكلفة العمل المنجز | 65 | 100 | 2014-06-28 | 2015-12-20 | 2019-03-31 | 2019-03-31 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5752 | 25.3825 | مسحوب | No
2100080415 | أمانة / عسير | تشييد | ذات اولوية عالية | 987600 | 49380 | 344143 | 344143 | 5859002286 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 40 | 100 | 2015-10-24 | 2016-10-17 | 2019-07-02 | 2019-07-02 |  |  | تأخرصرف المستحقات المالية |  |  |  | مسحوب | No
2100199872 | الجامعة الاسلامية بالمدينة المنورة | ترميم | ذات اولوية عالية | 2638887.75 | 131944.3875 | 0 | 0 | 5901005893 | لا | 0 | 210839393636 | جاري | الكميات التي تم تركيبها | 50 | 60 | 2022-06-06 | 2023-05-08 | 2023-05-08 | 2023-05-08 |  |  |  |  | 39.5654 | 24.4807 | متأخر | No
2100106562 | الهيئة العامة للموانئ | ترميم | ذات اولوية متوسطة | 27612668 | 1380633.4 | 16995407.4 | 16995407.4 | 1010187466 | لا | 0 | 181009170561 | جاري | تكلفة العمل المنجز | 69 | 100 | 2017-11-06 | 2021-09-24 | 2023-08-16 | 2023-08-16 |  |  | ضعف كفاءة المقاول الفنية | تم إشعار المقاول كتابيا بالتأخير | 49.6725 | 27.0191 | Failed | No
2100052732 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 7926268 | 396313.4 | 7926268 | 6760896 | 1010149050 | لا | 0 | 180909103090 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2016-03-01 | 2018-02-19 | 2022-10-31 | 2022-10-31 | 2018-02-19 |  | اخرى |  | 51.5732 | 24.1262 | منجز | No
2100083204 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 2485350 | 124267.5 | 2485349.99 | 2485349.99 | 4605000749 | لا | 0 | 200101001125 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 85 | 75 | 2019-12-22 | 2020-12-10 | 2020-12-10 | 2020-12-10 | 2020-12-10 |  | اخرى |  | 39.7876 | 22.2691 | منجز | No
2100029046 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2104800 | 105240 | 41897 | 0 | 1116004307 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 8.68 | 100 | 2015-02-11 | 2016-05-06 | 2016-05-06 | 2016-05-06 |  |  | ضعف كفاءة المقاول الفنية |  | 45.2672 | 24.1137 | مسحوب | Yes
2100084545 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 418110256 | 20905512.8 | 248926865 | 244627306 | 2051020158 | لا | 0 | 180709020814 | مسحوب | التكلفة المفوترة | 60 | 100 | 2012-03-10 | 2014-02-16 | 2021-07-19 | 2021-07-19 |  |  | ضعف كفاءة المقاول الفنية |  | 50.1141 | 26.3623 | مسحوب | No
2100059183 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 1318500 | 65925 | 373410 | 373410 | 2250029534 | لا | 0 | 181109286980 | فسخ العقد | تكلفة العمل المنجز | 28 | 100 | 2011-06-03 | 2011-11-30 | 2011-12-01 | 2011-12-01 |  |  | التنسيق مع أصحاب المصلحه (خدمات |  | 49.595 | 25.3711 | مسحوب | No
2100072973 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية وعاجلة | 11399450 | 569972.5 | 9357764.27 | 9357764.27 | 1010239020 | لا | 0 | 181109360565 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-05-06 | 2021-04-02 | 2022-06-30 | 2022-06-30 | 2021-04-02 |  | لا يوجد تأخير |  | 39.553 | 24.4194 | منجز | No
2100096810 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 4174920 | 208746 | 342250 | 342250 | 3550017480 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 10 | 54 | 2015-03-16 | 2016-12-21 | 2023-12-15 | 2023-12-15 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | مسحوب | No
2100091394 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 996480 | 49824 | 0 | 0 | 1117002145 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 1 | 100 | 2015-06-17 | 2016-06-11 | 2021-04-06 | 2021-04-06 |  |  | تأخرصرف المستحقات المالية | مخطط لفسخ العقد | 51.5767 | 24.1282 | مسحوب | No
2100084044 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية منخفضة | 19999996.51 | 999999.8255 | 17906860 | 17906860 | 5855000147 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2006-07-15 | 2008-06-23 | 2008-06-23 | 2008-06-23 | 2008-06-23 | 2013-11-17 |  |  | 42.6006 | 18.2272 | منجز | No
2100080194 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية | 12861619 | 643080.95 | 10932931 | 10932931 | 4650007352 | لا | 0 | 181009158822 | جاري | منهجية القيمة المكتسبة | 87.7 | 100 | 2014-12-18 | 2016-06-02 | 2022-06-30 | 2022-06-30 |  |  | لا يوجد تأخير |  | 40.5104 | 24.9027 | Failed | No
2100085805 | شركة المياه الوطنية / منطقة مكة المكرمة | إشراف | ذات اولوية عالية وعاجلة | 2526000 | 126300 | 2236712 | 2236712 | 1010413771 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2018-03-04 | 2020-03-03 | 2020-03-03 | 2020-03-03 | 2020-03-03 |  | لا يوجد تأخير |  | 39.1929 | 21.5279 | منجز | No
2100063980 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 16255422.48 | 812771.124 | 16255422.48 | 16255422.48 | 2060024520 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-01-08 | 2020-09-07 | 2020-09-08 | 2020-09-08 | 2020-09-07 |  |  |  | 49.5957 | 26.9916 | منجز | No
2100084770 | هيئة الهلال الأحمر السعودي | تشييد | ذات اولوية عالية | 1081639.75 | 54081.9875 | 1073059.81 | 1073059.81 | 1010277656 | لا | 0 | 190401001122 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-03-28 | 2019-06-26 | 2021-11-30 | 2021-11-30 | 2019-06-26 |  | اخرى |  | 39.9822 | 21.3477 | منجز | No
2100061003 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 63597550 | 3179877.5 | 57225240 | 57225240 | 5850016803 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2012-02-29 | 2015-08-31 | 2020-10-08 | 2020-10-08 | 2015-08-31 | 2020-10-08 |  |  | 42.5192 | 18.1729 | منجز | No
2100061902 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية | 6608732 | 330436.6 | 5100810.75 | 5100810.75 | 4650009299 | لا | 0 | 181009158456 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 96.71 | 100 | 2014-11-26 | 2016-11-04 | 2022-03-31 | 2022-03-31 | 2016-11-04 |  | لا يوجد تأخير |  | 39.6457 | 24.2586 | منجز | No
2100086612 | وزارة التعليم | تشييد | ذات اولوية عالية | 4872256 | 243612.8 | 0 | 0 | 1010245520 | لا | 0 |  | مسحوب | التكلفة المفوترة | 32 | 100 | 2005-07-13 | 2007-04-03 | 2012-07-14 | 2012-07-14 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | مسحوب | No
2100193594 | وزارة الحرس الوطني / الشؤون الفنية بالقطاع الشرقي | تشييد | ذات اولوية عالية | 16745041.95 | 837252.0975 | 12964163.37 | 11053049.13 | 2051027134 | لا | 0 | 190901066188 | جاري | تكلفة العمل المنجز | 97 | 100 | 2019-09-17 | 2020-03-16 | 2023-03-01 | 2023-03-01 |  |  |  |  | 50.1625 | 26.3628 | Failed | No
2100000313 | وزارة الشـؤون الاسلامية والدعوة والارشاد | تشييد | ذات اولوية عالية | 900000 | 45000 | 0 | 0 | 5855031154 | لا | 0 | 201009177293 | فسخ العقد | الكميات التي تم تركيبها | 65 | 100 | 2018-06-30 | 2018-12-30 | 2019-04-30 | 2019-04-30 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.7626 | 18.299 | مسحوب | No
2100059942 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية | 50000000 | 2500000 | 49939507.34 | 24332408.98 | 1010188861 | لا | 0 | 180201000173 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 94.8 | 100 | 2018-10-04 | 2021-09-01 | 2021-08-31 | 2021-08-31 | 2021-09-01 |  | لا يوجد تأخير |  | 39.6421 | 24.3945 | منجز | No
2100086494 | وزارة التعليم | تشييد | لم تعد تحتاجها الجهة | 19907865 | 995393.25 | 1182358.05 | 1182358.05 | 1010142553 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 6 | 100 | 2014-12-11 | 2017-02-28 | 2017-06-05 | 2017-06-05 |  |  | تغيرات في نطاق المشروع |  | 46.7098 | 24.6275 | مسحوب | No
2100087334 | وزارة المالية | تشييد | ذات اولوية متوسطة | 266285967.55 | 13314298.3775 | 203068648.1 | 197337832.76 | 1010047800 | لا | 0 | 181109317489 | جاري | التكلفة المفوترة | 89 | 93 | 2015-12-08 | 2022-12-30 | 2022-12-30 | 2022-12-30 |  |  | التنسيق مع أصحاب المصلحه (خدمات |  | 39.1677 | 21.5008 | منتظم | No
2100032340 | وزارة الموارد البشرية والتنمية الإجتماعية | تشييد | ذات اولوية منخفضة | 12395275 | 619763.75 | 675793.54 | 675793.54 | 4030140863 | لا | 0 | 181109265844 | مسحوب | الكميات التي تم تركيبها | 66 | 100 | 2014-10-15 | 2020-06-21 | 2021-12-31 | 2021-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 44.4537 | 17.6554 | مسحوب | No
2100086553 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1653087.8 | 82654.39 | 0 | 0 | 4030458624 | لا | 0 |  | مسحوب | التكلفة المفوترة | 0 | 100 | 2006-06-12 | 2007-04-28 | 2023-02-03 | 2023-02-03 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | مسحوب | No
2100207804 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 5572095 | 278604.75 | 5572095 | 5572095 | 4030271639 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2021-11-07 | 2022-11-02 | 2022-11-02 | 2022-11-02 | 2022-11-02 |  |  |  | 49.6058 | 25.313 | منجز | No
2100078735 | شركة المياه الوطنية / منطقة القصيم | إشراف | ذات اولوية عالية | 9871200 | 493560 | 9639924.51 | 9639924.51 | 1131049510 | لا | 0 | 180709023190 | منجز – استلام ابتدائي | التكلفة المفوترة | 99.97 | 100 | 2018-02-01 | 2020-02-01 | 2020-03-31 | 2020-03-31 | 2020-02-01 |  | لا يوجد تأخير |  | 43.992 | 26.0839 | منجز | No
2100029212 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 2550000 | 127500 | 2550000 | 2550000 | 2252054447 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-09-17 | 2019-09-04 | 2019-09-03 | 2019-09-03 | 2019-09-04 |  |  |  | 49.5918 | 27.0216 | منجز | No
2100020716 | وزارة الموارد البشرية والتنمية الإجتماعية | تشييد | ذات اولوية منخفضة | 41039813.1 | 2051990.655 | 24149766.32 | 24149766.32 | 3350012618 | لا | 0 | 180809055261 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-02-21 | 2019-01-04 | 2021-12-31 | 2021-12-31 | 2019-01-04 |  | ضعف كفاءة المقاول الفنية |  | 41.6734 | 27.5371 | منجز | No
2100089983 | وزارة المالية | إشراف | ذات اولوية عالية | 1128960 | 56448 | 1234676 | 1234676 | 1010099661 | لا | 0 |  | جاري | تكلفة العمل المنجز | 79.35 | 100 | 2020-01-28 | 2021-12-09 | 2022-12-09 | 2022-12-09 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.5706 | 16.8894 | خدمات عامة | No
2100092201 | المؤسسة العامة لتحلية المياه المالحة | إشراف | ذات اولوية عالية | 51835132 | 2591756.6 | 32425485.77 | 32425485.77 | 7000220330 | لا | 0 | 200101013761 | جاري | منهجية القيمة المكتسبة | 71.2 | 100 | 2019-04-01 | 2022-03-31 | 2022-03-31 | 2022-03-31 |  |  |  |  | 49.7891 | 26.888 | خدمات عامة | No
2100090016 | أمانة / العاصمة المقدسة | دراسة بيئية | ذات اولوية متوسطة | 2350600 | 117530 | 312018 | 312018 | 1010336184 | لا | 0 | 200309117737 | جاري | تكلفة العمل المنجز | 13.27 | 13.27 | 2022-05-08 | 2024-05-07 | 2024-05-07 | 2024-05-07 |  |  | اخرى |  |  |  | خدمات عامة | No
2100102955 | شركة المياه الوطنية / المنطقة الشرقية | إشراف | ذات اولوية عالية | 19887025 | 994351.25 | 19885400 | 19885400 | 2050101543 | لا | 0 | 180709035737 | منجز – استلام ابتدائي | التكلفة المفوترة | 99.99 | 100 | 2016-10-19 | 2019-10-19 | 2019-09-30 | 2019-09-30 | 2019-10-19 |  | لا يوجد تأخير |  | 50.1078 | 26.4285 | منجز | No
2100102734 | جامعة الملك فيصل | دراسة الجدوى | ذات اولوية عالية | 4404479.62 | 220223.981 | 10790011 | 10790011 | 1010321932 | لا | 0 | 200201054887 | جاري | تكلفة العمل المنجز | 83 | 83 | 2014-04-20 | 2017-04-29 | 2022-02-28 | 2022-02-28 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5946 | 25.341 | خدمات عامة | No
2100075305 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 1497000 | 74850 | 1497000 | 1497000 | 2511010804 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 34 | 100 | 2015-09-09 | 2019-02-25 | 2019-02-25 | 2019-02-25 |  |  | ضعف كفاءة المقاول الفنية |  | 47.0607 | 26.9914 | مسحوب | No
2100096482 | أمانة / الأحساء | دراسات هندسية | ذات اولوية متوسطة | 1206250 | 60312.5 | 687500 | 687500 | 1010227162 | لا | 0 | 190309010720 | فسخ العقد | تكلفة العمل المنجز | 57 | 100 | 2015-04-21 | 2016-02-19 | 2016-02-19 | 2016-02-19 |  |  | أوامر سامية |  | 49.6417 | 25.4185 | مسحوب | No
2100099282 | وزارة الصحة / حفر الباطن | تشييد | ذات اولوية عالية وعاجلة | 4150000 | 207500 | 285600 | 285600 | 2050018622 | لا | 0 | 180901113551 | جاري | الكميات التي تم تركيبها | 45 | 100 | 2018-05-13 | 2019-05-12 | 2024-03-01 | 2024-03-01 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ | مخطط لسحبه وإعادة ترسيته | 45.9855 | 28.4232 | Failed | No
2100022411 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 63680274 | 3184013.7 | 45846774.98 | 45846774.98 | 1010054406 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2013-06-16 | 2015-06-06 | 2018-04-26 | 2018-04-26 | 2015-06-06 |  | ضعف كفاءة المقاول الفنية |  | 50.0711 | 26.4321 | منجز | No
2100100586 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 34814041.27 | 1740702.0635 | 27716565.1 | 27716565.1 | 2050018628 | لا | 0 | 190701055827 | جاري | منهجية القيمة المكتسبة | 76 | 88 | 2019-11-12 | 2023-06-27 | 2023-06-27 | 2023-06-27 |  |  |  |  | 50 | 26.5546 | متأخر | No
2100029886 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 1810320 | 90516 | 1273942.42 | 1273942.42 | 1010432584 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-10-01 | 2021-09-29 | 2021-10-06 | 2021-10-06 | 2021-09-29 |  |  |  | 47.0717 | 26.9785 | منجز | No
2100026865 | أمانة / حفر الباطن | تشييد | ذات اولوية متوسطة | 882000 | 44100 | 882000 | 829080 | 1010077408 | لا | 0 | 0 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-06-16 | 2019-08-16 | 2019-09-21 | 2019-09-21 | 2019-08-16 |  |  |  | 50.0782 | 26.4229 | منجز | No
2100094861 | أمانة / المدينة المنورة | دراسة الجدوى | ذات اولوية عالية | 3450000 | 172500 | 3450000 | 3450000 | 1010323435 | لا | 0 |  | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-06-07 | 2022-09-10 | 2022-10-22 | 2022-10-22 |  |  | اخرى |  |  |  | متأخر | No
2100056921 | أمانة / الأحساء | دراسات هندسية | ذات اولوية متوسطة | 20000000 | 1000000 | 19667000 | 19667000 | 1010322156 | لا | 0 | 181109339455 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2017-11-09 | 2019-05-11 | 2021-12-31 | 2021-12-31 | 2019-05-11 |  | ضعف كفاءة المقاول الفنية |  | 49.6664 | 25.4557 | منجز | No
2100180471 | جامعة حائل | تشييد | ذات اولوية عالية وعاجلة | 149000000 | 7450000 | 120621901.201 | 120621901.201 | 1128000011 | لا | 0 | 200209139141 | جاري | تكلفة العمل المنجز | 84.01 | 100 | 2014-12-18 | 2023-04-01 | 2023-04-01 | 2023-04-01 |  |  |  |  | 41.709 | 27.6646 | متأخر | No
2100094765 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1001950 | 50097.5 | 1001950 | 1001950 | 4032029266 | لا | 0 | 181009122367 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-04-25 | 2020-02-19 | 2020-04-19 | 2020-04-19 | 2020-02-19 |  | ضعف كفاءة المقاول الفنية |  | 40.4105 | 22.4751 | منجز | No
2100076005 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 1399171 | 69958.55 | 1399171 | 1399171 | 2056002346 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-12-24 | 2020-12-12 | 2021-06-30 | 2021-06-30 | 2020-12-12 |  |  |  | 48.2882 | 26.7611 | منجز | No
2100096725 | هيئة المدن الصناعية ومناطق التقنية | تشييد | ذات اولوية عالية | 64430500 | 3221525 | 62956520 | 61494946 | 4030159937 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2015-08-31 | 2017-02-28 | 2019-06-30 | 2019-06-30 | 2017-02-28 |  | ضعف كفاءة المقاول الفنية |  | 25.9314 | 49.9532 | منجز | No
2100047294 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 47787038 | 2389351.9 | 33693837 | 33693837 | 4030091877 | لا | 0 | 200209140636 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 99.62 | 100 | 2012-03-05 | 2014-03-05 | 2023-05-23 | 2023-05-23 |  |  | ضعف كفاءة المقاول الفنية |  | 38.2058 | 24.0184 | Failed | No
2100067605 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 31754200 | 1587710 | 30126419 | 30126419 | 2251032617 | لا | 0 | 180801043072 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-12-17 | 2020-12-06 | 2022-06-15 | 2022-06-15 | 2020-12-06 |  |  |  | 49.5842 | 25.3416 | منجز | No
2100075703 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 12401500 | 620075 | 59529880 | 0 | 2050048409 | لا | 0 |  | مسحوب | منهجية القيمة المكتسبة | 50 | 100 | 2015-03-13 | 2018-12-09 | 2021-06-27 | 2021-06-27 |  |  | ضعف كفاءة المقاول الفنية |  | 49.8073 | 26.6589 | مسحوب | Yes
2100087032 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 142744682 | 7137234.1 | 141604612.19 | 126878706.7 | 1131014852 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 99.77 | 100 | 2015-05-03 | 2018-05-03 | 2021-04-26 | 2021-04-26 |  | 2018-05-03 | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100084910 | جامعة القصيم | تشييد | ذات اولوية عالية | 140273996 | 7013699.8 | 97676046.75 | 97676046.75 | 1010034600 | لا | 0 | 181109312345 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 90 | 100 | 2012-05-30 | 2015-11-11 | 2023-01-30 | 2023-01-30 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 44.0896 | 26.1114 | Failed | No
2100097764 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 4609931.5 | 230496.575 | 1102475.2 | 1102475.2 | 1010151477 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 29 | 100 | 2005-04-17 | 2007-01-23 | 2007-01-23 | 2007-01-23 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | مسحوب | No
2100098534 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 1089950 | 54497.5 | 1089950 | 1089950 | 2251032226 | لا | 0 | 190309011218 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-10-07 | 2020-03-30 | 2020-03-30 | 2020-03-30 | 2020-03-30 |  |  |  | 49.5431 | 25.6775 | منجز | No
2100190223 | جامعة الملك فيصل | تشييد | ذات اولوية عالية | 70395153 | 3519757.65 | 27663261 | 27663261 | 1010208002 | لا | 0 | 180501009155 | جاري | الكميات التي تم تركيبها | 40 | 70.15 | 2018-11-21 | 2022-02-02 | 2023-02-02 | 2023-02-02 |  |  |  |  | 49.6448 | 25.9322 | Failed | No
2100057481 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 17409315 | 870465.75 | 2139517.75 | 2139517.75 | 5950010534 | لا | 0 | 181101271198 | ايقاف كلي | تكلفة العمل المنجز | 15 | 100 | 2018-06-05 | 2019-05-26 | 2021-12-31 | 2021-12-31 |  |  | أوامر سامية |  | 39.1677 | 21.5008 | Failed | No
2100100236 | وزارة الدفاع / الإدارة الهندسية والاشغال بالخدمات الصحية | تشييد | ذات اولوية متوسطة | 14042640 | 702132 | 5375126.77 | 5375126.77 | 1010106132 | لا | 0 | 181009149731 | ايقاف كلي | الكميات التي تم تركيبها | 40 | 100 | 2014-12-24 | 2016-06-03 | 2020-02-25 | 2020-02-25 |  |  | اخرى |  | 46.6745 | 24.7119 | Failed | No
2100048926 | وزارة الصحة / تجمع الشرقية | توريد وتركيب | ذات اولوية عالية | 6310347.75 | 315517.3875 | 1150993.2 | 1150993.2 | 1010287690 | لا | 0 | 190909196757 | جاري | تكلفة العمل المنجز | 60 | 40 | 2019-02-28 | 2022-08-28 | 2022-08-28 | 2022-08-28 |  |  | تصاريح أعمال التنفيذ |  | 50.1026 | 26.41 | متأخر | No
2100099901 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2187063 | 109353.15 | 0 | 0 | 1010246941 | لا | 0 |  | مسحوب | التكلفة المفوترة | 1 | 100 | 2011-10-02 | 2013-01-02 | 2013-03-16 | 2013-03-16 |  |  | ضعف كفاءة المقاول الفنية |  | 44.4412 | 24.5406 | مسحوب | No
2100100461 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3826180 | 191309 | 2859960 | 0 | 1115001431 | لا | 0 |  | جاري | تكلفة العمل المنجز | 96 | 100 | 2014-01-07 | 2016-12-22 | 2018-07-30 | 2018-07-30 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6713 | 24.7082 | Failed | Yes
2100099842 | أمانة / العاصمة المقدسة | تحديث وتوريد | ذات اولوية متوسطة | 5998608 | 299930.4 | 6023050 | 6023050 | 1010336184 | لا | 0 | 200101014566 | جاري الاستلام الإبتدائي | مدفوعات ساعات العمل | 93.07 | 93.07 | 2019-10-20 | 2021-09-27 | 2021-12-31 | 2021-12-31 |  |  | اخرى |  | 39.1974 | 21.486 | Failed | No
2100099481 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 6423191.44 | 321159.572 | 6205818.91 | 6205818.91 | 5950002943 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2013-07-13 | 2015-01-13 | 2016-01-30 | 2016-01-30 | 2015-01-13 |  |  |  | 46.5188 | 23.6202 | منجز | No
2100099713 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1034690 | 51734.5 | 776017.5 | 776017.5 | 1010173192 | لا | 0 |  | مسحوب | التكلفة المفوترة | 75 | 100 | 2008-08-16 | 2009-04-12 | 2009-04-12 | 2009-04-12 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | مسحوب | No
2100196486 | أمانة / المنطقة الشرقية | الخدمات الاستشارية | ذات اولوية متوسطة | 9216428 | 460821.4 | 7959643 | 7959643 | 4030276223 | لا | 0 | 200601085109 | جاري | التكلفة المفوترة | 85 | 100 | 2020-10-04 | 2022-10-04 | 2022-10-04 | 2022-10-04 |  |  |  |  | 50.0888 | 26.4207 | خدمات عامة | No
2100101146 | شركة الكهرباء | تشييد | ذات اولوية متوسطة | 80374243 | 4018712.15 | 71915424 | 71915424 | 1010154437 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2016-02-07 | 2018-05-06 | 2022-03-31 | 2022-03-31 | 2018-05-06 |  | لا يوجد تأخير |  | 41.7358 | 27.5379 | منجز | No
2100073625 | المؤسسة العامة لتحلية المياه المالحة | إشراف | ذات اولوية عالية | 30413794 | 1520689.7 | 26910474.73 | 26910474.73 | 1010440438 | لا | 0 | 190701089764 | جاري | تكلفة العمل المنجز | 89.8 | 89.8 | 2019-10-31 | 2023-11-09 | 2023-11-09 | 2023-11-09 |  |  |  |  | 46.0391 | 28.3419 | خدمات عامة | No
2100101463 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 498000 | 24900 | 498000 | 498000 | 1010219753 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-06-09 | 2019-12-09 | 2019-12-09 | 2019-12-09 |  | 2019-12-09 | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100106396 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 36499374 | 1824968.7 | 32896010.99 | 32896010.99 | 1010074413 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 98.99 | 100 | 2018-01-01 | 2020-01-01 | 2021-02-03 | 2021-02-03 |  | 2020-01-01 | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100008201 | أمانة / حفر الباطن | تشييد | ذات اولوية متوسطة | 541098166.4 | 27054908.32 | 351503257 | 351503257 | 1010090968 | لا | 0 | 190201034487 | جاري | تكلفة العمل المنجز | 72 | 83 | 2019-07-30 | 2021-07-07 | 2023-10-01 | 2023-10-01 |  |  |  |  | 45.9833 | 28.3681 | متأخر | No
2100105383 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 11638140 | 581907 | 11254040.41 | 10322044.31 | 1010249593 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 97.94 | 100 | 2019-02-25 | 2020-02-25 | 2020-12-03 | 2020-12-03 |  | 2020-02-25 | أوامر تغيير |  | 46.5373 | 24.7528 | منجز | No
2100064190 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية عالية | 6927300 | 346365 | 4330911.89 | 4330911.89 | 2051003698 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-11-26 | 2021-12-09 | 2021-04-16 | 2021-04-16 | 2021-12-09 |  |  |  | 49.6707 | 25.9168 | منجز | No
2100091873 | أمانة / حفر الباطن | تشييد | ذات اولوية متوسطة | 9196228 | 459811.4 | 9196228 | 9196228 | 1010008188 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 70 | 2018-09-16 | 2020-03-06 | 2020-03-11 | 2020-03-11 | 2020-03-06 |  |  |  | 45.9885 | 28.35 | منجز | No
2100052161 | أمانة / حفر الباطن | تشييد | ذات اولوية متوسطة | 10999618 | 549980.9 | 9901896.52 | 9901896.52 | 1010136405 | لا | 0 | 181101373742 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-03-06 | 2021-09-23 | 2022-11-30 | 2022-11-30 | 2021-09-23 |  | ضعف كفاءة المقاول الفنية |  | 45.9802 | 28.3873 | منجز | No
2100023321 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 34172274.12 | 1708613.706 | 34172274.12 | 34172274.12 | 1010224518 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 96.89 | 2018-03-22 | 2020-02-29 | 2020-01-28 | 2020-01-28 |  | 2020-02-29 | لا يوجد تأخير |  | 39.193 | 21.7846 | منجز | No
2100048204 | أمانة / حفر الباطن | تشييد | ذات اولوية متوسطة | 97518461 | 4875923.05 | 97518461 | 92154946.73 | 1010136405 | لا | 0 | 190809101508 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-10-07 | 2022-05-10 | 2022-12-04 | 2022-12-04 | 2022-05-10 |  | ضعف كفاءة المقاول الفنية |  | 45.9798 | 28.3782 | منجز | No
2100066415 | أمانة / حفر الباطن | تشييد | ذات اولوية متوسطة | 3994975 | 199748.75 | 3736387.34 | 3736387.34 | 2511022954 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-02-24 | 2020-08-17 | 2021-05-28 | 2021-05-28 | 2020-08-17 |  |  |  | 45.9736 | 28.4052 | منجز | No
2100016726 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 6678100 | 333905 | 6344216.26 | 6344216.26 | 1010092552 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 95 | 100 | 2019-01-09 | 2020-07-09 | 2020-07-09 | 2020-07-09 |  | 2020-07-09 | لا يوجد تأخير |  | 47.7225 | 27.5463 | منجز | No
2100076145 | وزارة الصحة / تجمع الشرقية | تحديث وتوريد | ذات اولوية متوسطة | 3596009 | 179800.45 | 3196159 | 3196159 | 2051033753 | لا | 0 | 200909032728 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-10-05 | 2016-02-19 | 2021-09-12 | 2021-09-12 | 2016-02-19 |  | تصاريح أعمال التنفيذ |  | 50.1031 | 26.4078 | منجز | No
2100058306 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 10136322 | 506816.1 | 10136322 | 10136322 | 2050048409 | لا | 0 |  | مسحوب | منهجية القيمة المكتسبة | 6 | 100 | 2017-08-13 | 2019-09-02 | 2019-09-02 | 2019-09-02 |  |  | ضعف كفاءة المقاول الفنية |  | 50.0537 | 26.5632 | مسحوب | No
2100085551 | وزارة الموارد البشرية والتنمية الإجتماعية | إشراف | ذات اولوية منخفضة | 723600 | 36180 | 2284229.99 | 2284229.99 | 1010328167 | لا | 0 | 190309006765 | مسحوب | الكميات التي تم تركيبها | 97 | 100 | 2014-05-30 | 2016-05-06 | 2021-12-30 | 2021-12-30 |  |  | ضعف كفاءة المقاول الفنية |  | 45.9471 | 28.4408 | مسحوب | No
2100066883 | أمانة / حفر الباطن | تشييد | ذات اولوية متوسطة | 2388920 | 119446 | 2358186.44 | 2358186.44 | 1010008188 | لا | 0 | 0 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-03-27 | 2019-03-22 | 2019-03-25 | 2019-03-25 | 2019-03-22 |  |  |  | 45.9735 | 28.4306 | منجز | No
2100096073 | وزارة الموارد البشرية والتنمية الإجتماعية | إشراف | ذات اولوية منخفضة | 830800 | 41540 | 1874522.5 | 1874522.5 | 1010328167 | لا | 0 | 190309017872 | مسحوب | الكميات التي تم تركيبها | 84 | 100 | 2013-09-01 | 2015-08-10 | 2022-03-24 | 2022-03-24 |  |  | ضعف كفاءة المقاول الفنية |  | 48.4922 | 28.4562 | مسحوب | No
2100078573 | أمانة / حفر الباطن | ترميم | ذات اولوية متوسطة | 945000 | 47250 | 945000 | 945000 | 4030282813 | لا | 0 | 200309068153 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-10-23 | 2020-10-23 | 2020-10-29 | 2020-10-29 | 2020-10-23 |  | اخرى |  | 45.9692 | 28.331 | منجز | No
2100081966 | أمانة / حفر الباطن | تشييد | ذات اولوية متوسطة | 18006038 | 900301.9 | 15960631 | 15960631 | 1010136405 | لا | 0 | 0 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-10-18 | 2019-04-16 | 2019-04-15 | 2019-04-15 | 2019-04-16 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 45.9849 | 28.3922 | منجز | No
2100072833 | أمانة / حفر الباطن | تشييد | ذات اولوية متوسطة | 13582915.5 | 679145.775 | 13581452.47 | 13581452.47 | 2511006133 | لا | 0 | 181001169506 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-01-16 | 2021-01-05 | 2021-03-29 | 2021-03-29 | 2021-01-05 |  |  |  | 45.9856 | 28.3889 | منجز | No
2100106234 | وزارة الثقافة | تشييد |  | 73196265.85 | 3659813.2925 | 55028244.77 | 55028244.77 | 1010044893 |  | 0 |  | جاري | منهجية القيمة المكتسبة | 95 | 100 | 2017-04-26 00:59 | 2019-04-25 00:59 | 2020-03-25 | 2020-03-25 |  |  | أوامر تغيير |  |  |  | Failed | No
2100041473 | جامعة الملك فيصل | دراسة الجدوى | ذات اولوية متوسطة | 2265000 | 113250 | 1847803 | 1847803 | 1010359384 | لا | 0 | 180809054453 | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2013-01-07 | 2016-06-29 | 2020-09-10 | 2020-09-10 |  | 2016-06-29 | تأخرصرف المستحقات المالية |  | 49.5999 | 25.3427 | منجز | No
2100078875 | وزارة الموارد البشرية والتنمية الإجتماعية | تشييد | ذات اولوية منخفضة | 2727050 | 136352.5 | 4515033.33 | 4515033.33 | 1010406370 | لا | 0 | 180909066210 | مسحوب | مدفوعات ساعات العمل | 82 | 100 | 2013-06-28 | 2016-02-27 | 2021-10-13 | 2021-10-13 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 50.0855 | 26.4393 | مسحوب | No
2100097171 | أمانة / حفر الباطن | تشييد | ذات اولوية متوسطة | 92600 | 4630 | 92600 | 0 | 1010343431 | لا | 0 | 200201008753 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-04-16 | 2018-10-16 | 2018-10-16 | 2018-10-16 | 2018-10-16 |  |  |  | 46.7133 | 28.0989 | منجز | Yes
2100034753 | أمانة / حفر الباطن | تشييد | ذات اولوية متوسطة | 19895380 | 994769 | 7203620 | 0 | 2511005876 | نعم | 7203620 | 0 | مسحوب | تكلفة العمل المنجز | 36 | 36 | 2014-01-09 | 2016-07-28 | 2017-03-28 | 2017-03-28 |  |  | ضعف كفاءة المقاول الفنية |  | 46.002 | 28.3423 | مسحوب | Yes
2100101603 | وزارة الصحة / حفر الباطن | تشييد | ذات اولوية عالية | 59327113 | 2966355.65 | 15629198 | 15629198 | 2111005876 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 45 | 100 | 2014-04-30 | 2016-04-08 | 2025-01-01 | 2025-01-01 |  |  | ضعف كفاءة المقاول الفنية | مخطط لإعادة طرحه | 45.9547 | 28.314 | مسحوب | No
2100190466 | جامعة الملك فيصل | تشييد | ذات اولوية عالية | 322744723.33 | 16137236.1665 | 98445386.32 | 98445386.32 | 2055002293 | لا | 0 | 181009122304 | جاري | الكميات التي تم تركيبها | 32 | 69.5 | 2014-04-30 | 2022-02-28 | 2023-02-28 | 2023-02-28 |  |  |  |  | 49.5933 | 25.3399 | Failed | No
2100107295 | جامعة طيبة | تشييد | ذات اولوية عالية | 167773177 | 8388658.85 | 66280654.02 | 64479836.36 | 4030068284 | لا | 0 | 181009161414 | جاري | تكلفة العمل المنجز | 36.49 | 90 | 2013-01-13 | 2015-01-03 | 2024-12-01 | 2024-12-01 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال | تم إنذار المقاول كتابيا | 39.6005 | 24.4595 | Failed | No
2100192942 | وزارة الحرس الوطني / الشؤون الصحية | توريد وتركيب | ذات اولوية عالية وعاجلة | 284625 | 14231.25 | 0 | 0 | 1010327804 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2021-06-21 | 2022-01-23 | 2022-10-31 | 2022-10-31 | 2022-01-23 |  |  |  | 49.5339 | 25.4601 | منجز | No
2100116292 | المؤسسة العامة للحبوب | ترميم | ذات اولوية عالية وعاجلة | 956445 | 47822.25 | 956445 | 956445 | 1131014504 | نعم | 188158 | 190309093885 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2020-11-20 | 2021-08-12 | 2021-08-12 | 2021-08-12 | 2021-08-12 |  |  |  | 43.9932 | 26.3491 | منجز | No
2100006344 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 24828000 | 1241400 | 22342200 | 22342200 | 5855037099 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-02-07 | 2019-07-24 | 2020-11-18 | 2020-11-18 | 2019-07-24 |  | لا يوجد تأخير |  | 39.1242 | 22.2875 | منجز | No
2100054331 | وزارة النقل والخدمات اللوجستية / منطقة الباحة | تشييد | ذات اولوية عالية وعاجلة | 143828829 | 7191441.45 | 0 | 0 | 1010009590 | نعم | 38405732.33 | 181009170021 | جاري | الكميات التي تم تركيبها | 0 | 0 | 2022-09-14 | 2025-09-14 | 2025-09-14 | 2025-09-14 |  |  | ضعف كفاءة المقاول الفنية |  | 41.4978 | 20.1158 | منتظم | No
2100026143 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 14290796 | 714539.8 | 14290796 | 14290796 | 2251032617 | لا | 0 | 180801054422 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-11-05 | 2020-10-25 | 2021-04-04 | 2021-04-04 | 2020-10-25 |  |  |  | 49.5567 | 25.3973 | منجز | No
2100067524 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 3038105.48 | 151905.274 | 2262654 | 2262654 | 2251036876 | لا | 0 | 190309013625 | مسحوب | تكلفة العمل المنجز | 75 | 100 | 2012-12-04 | 2013-11-29 | 2019-12-04 | 2019-12-04 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 48.9812 | 23.2387 | مسحوب | No
2100053314 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 11133240 | 556662 | 10020284 | 8725897 | 2251031375 | لا | 0 | 200109043754 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-03-07 | 2016-03-01 | 2022-04-08 | 2022-04-08 | 2016-03-01 |  | تأخرصرف المستحقات المالية |  | 49.5376 | 25.4132 | منجز | No
2100194611 | الهيئة العامة للطيران المدني | تصميم وتشييد | ذات اولوية عالية وعاجلة | 55502958 | 2775147.9 | 38587770.8 | 38587770.8 | 4030288802 | لا | 0 | 191201138503 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2021-02-19 | 2021-08-29 | 2021-12-31 | 2021-12-31 | 2021-08-29 |  |  |  | 52.0814 | 20.2555 | منجز | No
2100056652 | جامعة الملك فيصل | دراسة الجدوى | ذات اولوية عالية | 3474168 | 173708.4 | 2744933 | 2744933 | 4030276223 | لا | 0 | 180809056125 | جاري | تكلفة العمل المنجز | 100 | 100 | 2018-01-02 | 2018-10-31 | 2019-04-30 | 2019-04-30 |  |  | تأخرصرف المستحقات المالية |  | 49.7891 | 25.3777 | خدمات عامة | No
2100093715 | وزارة الحرس الوطني / الشؤون الفنية بالقطاع الشرقي | ترميم | ذات اولوية عالية | 6287472.45 | 314373.6225 | 5357441.25 | 5357441.25 | 2050018622 | لا | 0 | 180501009330 | مسحوب | تكلفة العمل المنجز | 87 | 100 | 2018-08-12 | 2019-08-01 | 2022-06-30 | 2022-06-30 |  |  | تأخرصرف المستحقات المالية |  | 49.5356 | 25.4519 | مسحوب | No
2100032970 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 6316335.71 | 315816.7855 | 4937913 | 4937913 | 1010197183 | لا | 0 | 190601007193 | مسحوب | منهجية القيمة المكتسبة | 83.47 | 100 | 2019-08-30 | 2022-03-25 | 2022-03-25 | 2022-03-25 |  |  |  |  | 50.0019 | 26.5722 | مسحوب | No
2100195436 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 1821460 | 91073 | 728558.74 | 728558.74 | 2511105361 | لا | 0 |  | جاري | تكلفة العمل المنجز | 48 | 100 | 2020-12-01 | 2021-08-01 | 2021-07-28 | 2021-07-28 |  |  |  |  | 45.969 | 28.3734 | Failed | No
2100108500 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 20752510 | 1037625.5 | 18498119.42 | 18498119.42 | 1010199480 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-01-29 | 2017-04-18 | 2020-01-26 | 2020-01-26 | 2017-04-18 |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.5485 | منجز | No
2100022525 | وزارة الصحة / حفر الباطن | تشييد | ذات اولوية متوسطة | 1377060 | 68853 | 795712.65 | 795712.65 | 2514000363 | لا | 0 | 181109297886 | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 96 | 100 | 2018-04-12 | 2018-12-03 | 2023-03-01 | 2023-03-01 |  |  | تأخرصرف المستحقات المالية | تم تمديد الجدول الزمني | 45.9835 | 28.4148 | Failed | No
2100109395 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 25040777.64 | 1252038.882 | 21967141.6 | 21967141.6 | 1010060469 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2017-07-26 | 2019-10-15 | 2020-12-29 | 2020-12-29 | 2019-10-15 |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | منجز | No
2100108710 | وزارة التعليم | تشييد | ذات اولوية عالية | 11044700 | 552235 | 4009893 | 3884276 | 4650020435 | لا | 0 |  | مسحوب | التكلفة المفوترة | 58 | 100 | 2014-11-15 | 2017-02-03 | 2023-06-15 | 2023-06-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | No
2100025126 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 40101600 | 2005080 | 40094500 | 36456000 | 2050018628 | لا | 0 | 180801062386 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2019-03-30 | 2020-09-12 | 2020-09-12 | 2020-09-12 | 2020-09-12 |  |  |  | 50.0014 | 26.423 | منجز | No
2100031220 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 9977300 | 498865 | 9977300 | 9977300 | 2051043445 | لا | 0 | 190401014149 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 90 | 100 | 2019-07-09 | 2019-07-10 | 2021-04-23 | 2021-04-23 | 2019-07-10 |  |  |  | 50.0277 | 26.4921 | منجز | No
2100092094 | أمانة / حفر الباطن | تشييد | ذات اولوية متوسطة | 2488900 | 124445 | 2478360 | 2478360 | 1010161638 | لا | 0 | 0 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-01-20 | 2019-07-17 | 2020-05-06 | 2020-05-06 | 2019-07-17 |  | ضعف كفاءة المقاول الفنية |  | 45.6777 | 28.1132 | منجز | No
2100051483 | أمانة / حفر الباطن | تشييد | ذات اولوية متوسطة | 9111638 | 455581.9 | 4143275 | 4143275 | 2511005876 | لا | 0 | 0 | مسحوب | تكلفة العمل المنجز | 46 | 46 | 2014-08-10 | 2016-01-24 | 2016-08-30 | 2016-08-30 |  |  | ضعف كفاءة المقاول الفنية |  | 45.9849 | 28.3862 | مسحوب | No
2100051833 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3762283 | 188114.15 | 3254497.65 | 0 | 1116005202 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 100 | 2015-04-08 | 2016-09-27 | 2016-09-27 | 2016-09-27 | 2016-09-27 |  | ضعف كفاءة المقاول الفنية |  | 43.7421 | 24.2982 | منجز | Yes
2100062532 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 2090170 | 104508.5 | 2090170 | 2090170 | 2511004823 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2013-11-10 | 2016-01-13 | 2021-06-24 | 2021-06-24 | 2016-01-13 |  |  |  | 47.0619 | 27.0051 | منجز | No
2100045231 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 1747305 | 87365.25 | 1747305 | 1747305 | 2251007095 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-09-03 | 2020-08-22 | 2020-08-23 | 2020-08-23 | 2020-08-22 |  |  |  | 49.4491 | 26.0752 | منجز | No
2100064853 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 2599945 | 129997.25 | 2575645 | 2575645 | 2050069357 | لا | 0 | 4005700003111319 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-08-19 | 2020-08-07 | 2020-01-11 | 2020-01-11 | 2020-08-07 |  |  |  | 47.6985 | 27.5398 | منجز | No
2100066791 | أمانة / حفر الباطن | تشييد | ذات اولوية متوسطة | 2108000 | 105400 | 2107500 | 2107500 | 1010350726 | لا | 0 | 0 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-05-08 | 2020-04-26 | 2020-04-26 | 2020-04-26 | 2020-04-26 |  |  |  | 45.6688 | 28.1072 | منجز | No
2100035162 | أمانة / حفر الباطن | تشييد | ذات اولوية متوسطة | 732270 | 36613.5 | 732270 | 732270 | 1010203649 | لا | 0 | 190609106373 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-06-30 | 2019-11-03 | 2020-12-26 | 2020-12-26 | 2019-11-03 |  |  |  | 46.7246 | 28.0994 | منجز | No
2100078643 | أمانة / حفر الباطن | دراسات هندسية | ذات اولوية متوسطة | 51210000 | 2560500 | 50974476 | 50974476 | 1010322156 | لا | 0 |  | جاري | تكلفة العمل المنجز | 95 | 98 | 2019-07-30 | 2023-06-13 | 2022-11-13 | 2022-11-13 |  |  | اخرى |  | 45.961 | 28.363 | خدمات عامة | No
2100056840 | جامعة الملك فيصل | دراسات هندسية | ذات اولوية عالية | 330000 | 16500 | 115500 | 115500 | 1010423886 | لا | 0 | 180809056321 | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2015-06-17 | 2015-12-10 | 2015-11-10 | 2015-11-10 |  | 2015-12-10 | تأخرصرف المستحقات المالية |  | 49.5946 | 25.3381 | منجز | No
2100093553 | وزارة الصحة / حفر الباطن | تشييد | ذات اولوية عالية | 9949982 | 497499.1 | 6468132 | 6468132 | 2111005876 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-03-29 | 2016-03-17 | 2017-04-05 | 2017-04-05 | 2016-03-17 |  | ضعف كفاءة المقاول الفنية |  | 46.0068 | 28.4435 | منجز | No
2100102001 | أمانة / حفر الباطن | ترميم | ذات اولوية متوسطة | 4935000 | 246750 | 4935000 | 4935000 | 1010315853 | لا | 0 | 190909145477 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-06-17 | 2021-06-16 | 2021-06-16 | 2021-06-16 | 2021-06-16 |  | اخرى |  | 45.9804 | 28.3793 | منجز | No
2100003021 | وزارة الشـؤون الاسلامية والدعوة والارشاد | تشييد | ذات اولوية عالية | 399244.8 | 19962.24 | 225545 | 0 | 3357003880 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 65 | 65 | 2017-07-26 | 2018-07-26 | 2021-02-25 | 2021-02-25 | 2018-07-26 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.7013 | 26.687 | منجز | Yes
2100093284 | وزارة الشـؤون الاسلامية والدعوة والارشاد | تشييد | ذات اولوية عالية | 1513895 | 75694.75 | 0 | 0 | 1010253720 | لا | 0 | 180901070781 | جاري | الكميات التي تم تركيبها | 100 | 100 | 2018-11-12 | 2019-07-07 | 2021-02-28 | 2021-02-28 |  |  | اخرى |  | 39.8309 | 21.3719 | Failed | No
2100107284 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البرية | تشييد | ذات اولوية متوسطة | 4497155 | 224857.75 | 500000 | 500000 | 1010063483 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 60 | 100 | 2019-10-14 | 2020-04-13 | 2022-12-31 | 2022-12-31 |  |  | لا يوجد تأخير |  | 50.2134 | 26.4441 | Failed | No
2100077173 | وزارة الموارد البشرية والتنمية الإجتماعية | تشييد | ذات اولوية منخفضة | 22588494 | 1129424.7 | 14287981.7 | 14287981.7 | 2051027988 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 82 | 100 | 2013-06-28 | 2016-02-27 | 2021-02-03 | 2021-02-03 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 50.0694 | 26.4334 | مسحوب | No
2100019191 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 4989758 | 249487.9 | 4752150 | 4686821 | 4030023505 | لا | 0 | 190809095721 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-07-06 | 2020-06-30 | 2022-06-13 | 2022-06-13 | 2020-06-30 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 49.5516 | 25.4051 | منجز | No
2100095572 | جامعة القصيم | تشييد | ذات اولوية عالية وعاجلة | 3833565.75 | 191678.2875 | 2765856.91 | 2751082.65 | 1131028904 | لا | 0 | 200409100771 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-04-08 | 2021-02-02 | 2021-06-22 | 2021-06-22 | 2021-02-02 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 43.7604 | 26.3451 | منجز | No
2100091534 | المؤسسة العامة للري | إشراف | ذات اولوية عالية | 7148800 | 357440 | 7148800 | 7148800 | 1010120626 | لا | 0 |  | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2013-11-12 | 2016-05-09 | 2022-03-15 | 2022-03-15 | 2016-05-09 |  | ضعف كفاءة المقاول الفنية |  | 49.6225 | 25.4259 | منجز | No
2100193491 | الجمارك السعودية | إشراف | ذات اولوية عالية | 11235456.52 | 561772.826 | 9574454 | 9574454 | 1010093247 | لا | 0 | 200901155460 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-12-13 | 2021-06-11 | 2021-08-14 | 2021-08-14 | 2021-06-11 |  |  |  | 51.5752 | 24.1295 | منجز | No
2100047434 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 53925000 | 2696250 | 41759141.64 | 0 | 1010056094 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 85 | 100 | 2014-08-06 | 2016-07-26 | 2020-01-13 | 2020-01-13 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6788 | 24.7038 | Failed | Yes
2100073931 | الجمارك السعودية | دراسة الجدوى | ذات اولوية عالية | 3234560 | 161728 | 3181142.9 | 3181142.9 | 1010250667 | لا | 0 | 181209455249 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-11-03 | 2016-12-26 | 2021-11-18 | 2021-11-18 | 2016-12-26 |  | اخرى |  | 50.746 | 24.731 | منجز | No
2100070405 | صندوق تنمية الموارد البشرية | تشييد | ذات اولوية منخفضة | 35434014.3 | 1771700.715 | 31890612.87 | 31890612.87 | 2050007518 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2015-01-05 | 2017-01-04 | 2021-11-08 | 2021-11-08 | 2017-01-04 | 2022-12-07 | سوء التخطيط الاولي للمشروع |  | 50.0012 | 26.7734 | منجز | No
2100064901 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 2983304 | 149165.2 | 0 | 0 | 1117002145 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 27 | 100 | 2015-06-17 | 2016-06-11 | 2021-04-06 | 2021-04-06 |  |  | تأخرصرف المستحقات المالية |  | 51.5696 | 24.1345 | مسحوب | No
2100100914 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 437000 | 21850 | 437000 | 437000 | 2056001462 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 86.85 | 2019-12-07 | 2020-11-25 | 2020-10-20 | 2020-10-20 | 2020-11-25 |  |  |  | 49.4718 | 25.9952 | منجز | No
2100035232 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 327600 | 16380 | 183000 | 183000 | 2066002549 | لا | 0 | 191101089426 | فسخ العقد | تكلفة العمل المنجز | 75 | 100 | 2019-09-14 | 2020-03-12 | 2020-12-21 | 2020-12-21 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5486 | 25.6538 | مسحوب | No
2100075434 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 997025 | 49851.25 | 427500 | 427500 | 2251044279 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 43 | 100 | 2015-06-09 | 2016-05-24 | 2016-05-25 | 2016-05-25 |  |  | تأخرصرف المستحقات المالية |  | 51.576 | 24.1264 | مسحوب | No
2100079590 | جامعة الحدود الشمالية | تشييد | ذات اولوية متوسطة | 72275267.47 | 3613763.3735 | 28118030.99 | 28118030.99 | 1010034600 | لا | 0 | 181109330241 | ايقاف جزئي | تكلفة العمل المنجز | 41 | 100 | 2013-11-12 | 2019-10-09 | 2024-10-31 | 2024-10-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.0346 | 30.951 | Failed | No
2100034285 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 1189131 | 59456.55 | 1189131 | 1189131 | 3453002609 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-10-17 | 2020-07-13 | 2020-07-26 | 2020-07-26 | 2020-07-13 |  | ضعف كفاءة المقاول الفنية |  | 43.3742 | 29.9513 | منجز | No
2100052754 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 11478980 | 573949 | 8215480 | 8215480 | 3450007800 | لا | 0 | 190301057870 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 97 | 100 | 2018-09-30 | 2019-07-30 | 2023-05-31 | 2023-05-31 |  |  |  |  | 41.0224 | 30.9755 | منتظم | No
2100084173 | وزارة النقل والخدمات اللوجستية / منطقة الحدود الشمالية | تشييد | ذات اولوية عالية | 105037828.72 | 5251891.436 | 94959117 | 94959117 | 1010213394 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 93.49 | 100 | 2009-08-12 | 2014-01-18 | 2014-01-18 | 2014-01-18 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 43.1217 | 29.3421 | مسحوب | No
2100067756 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 7946200 | 397310 | 1618650 | 1618650 | 3453001773 | لا | 0 | 181009183067 | مسحوب | منهجية القيمة المكتسبة | 20 | 100 | 2014-12-10 | 2016-06-10 | 2021-12-30 | 2021-12-30 |  |  | ضعف كفاءة المقاول الفنية |  | 43.51 | 29.6333 | مسحوب | No
2100051030 | أمانة / الحدود الشمالية | تشييد | ذات اولوية متوسطة | 3572960 | 178648 | 3446960 | 3446960 | 3452007733 | لا | 0 | 181209488050 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2015-03-05 | 2016-02-28 | 2021-03-01 | 2021-03-01 | 2016-02-28 |  | ضعف كفاءة المقاول الفنية |  | 38.676 | 31.6672 | منجز | No
2100072030 | أمانة / الحدود الشمالية | تشييد | ذات اولوية متوسطة | 515000 | 25750 | 0 | 0 | 3450009680 | لا | 0 | 200309011292 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-01-02 | 2019-07-01 | 2020-11-15 | 2020-11-15 | 2019-07-01 |  | ضعف كفاءة المقاول الفنية |  | 38.6692 | 31.6601 | منجز | No
2100013801 | أمانة / الحدود الشمالية | تشييد | ذات اولوية متوسطة | 2796286.6 | 139814.33 | 2354722.45 | 2354722.45 | 3450012620 | لا | 0 | 181009128867 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2015-09-02 | 2016-08-27 | 2019-03-08 | 2019-03-08 | 2016-08-27 |  | ضعف كفاءة المقاول الفنية |  | 41.5964 | 30.6944 | منجز | No
2100077630 | أمانة / جدة | تشييد | ذات اولوية عالية وعاجلة | 46058073 | 2302903.65 | 45980784 | 39713073 | 1010044185 | لا | 0 | 181109314250 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-09-16 | 2019-06-08 | 2020-06-05 | 2020-06-05 | 2019-06-08 |  | التنسيق مع أصحاب المصلحه (خدمات |  | 39.1901 | 21.519 | منجز | No
2100057783 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 1604313.44 | 80215.672 | 1333275 | 1333275 | 3450010904 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 85 | 91 | 2018-06-04 | 2019-05-30 | 2023-05-28 | 2023-05-28 |  |  | اخرى |  | 44.319 | 29.15 | متأخر | No
2100012051 | جامعة الملك سعود | تشييد | ذات اولوية عالية | 115500 | 5775 | 0 | 0 | 1010210567 | لا | 0 | 200601168527 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-12-19 | 2020-02-01 | 2020-12-01 | 2020-12-01 | 2020-02-01 |  | تغيرات في نطاق المشروع |  | 46.7098 | 24.6275 | منجز | No
2100178345 | وزارة الثقافة | تشييد | ذات اولوية عالية | 96895260.37 | 4844763.0185 | 53090199.97 | 49328634.84 | 1010154344 | لا | 0 | 201009139976 | جاري | منهجية القيمة المكتسبة | 75 | 100 | 2017-12-06 | 2020-09-20 | 2021-09-01 | 2021-09-01 |  |  |  |  | 41.1149 | 30.8313 | Failed | No
2100033681 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 825995 | 41299.75 | 281695 | 281695 | 3450010575 | لا | 0 | 181001187296 | مسحوب | منهجية القيمة المكتسبة | 34 | 34 | 2018-09-06 | 2019-05-04 | 2021-01-01 | 2021-01-01 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6002 | 30.6955 | مسحوب | No
2100082390 | أمانة / الحدود الشمالية | تشييد | ذات اولوية متوسطة | 847795 | 42389.75 | 847795 | 847795 | 5856009437 | لا | 0 | 181001143909 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-07-18 | 2019-04-14 | 2019-03-07 | 2019-03-07 | 2019-04-14 |  |  |  | 41.0144 | 30.9714 | منجز | No
2100072354 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 1950250 | 97512.5 | 1950250 | 1950250 | 1010158252 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-09-18 | 2019-09-13 | 2020-09-10 | 2020-09-10 | 2019-09-13 |  | ضعف كفاءة المقاول الفنية |  | 41.0136 | 30.9628 | منجز | No
2100067056 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 1965750 | 98287.5 | 1699000 | 1699000 | 3450011559 | لا | 0 | 200201014381 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 89 | 100 | 2018-11-26 | 2019-07-24 | 2020-10-29 | 2020-10-29 | 2019-07-24 |  | ضعف كفاءة المقاول الفنية |  | 41.01 | 30.9758 | منجز | No
2100072203 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 4996250 | 249812.5 | 4702395 | 4702395 | 3450009076 | لا | 0 | 200201023207 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-02-20 | 2020-02-15 | 2021-10-25 | 2021-10-25 | 2020-02-15 |  | ضعف كفاءة المقاول الفنية |  | 41.0147 | 30.975 | منجز | No
2100025233 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 5419000 | 270950 | 5419000 | 5419000 | 3450007800 | لا | 0 | 190401035739 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-11-05 | 2019-11-04 | 2019-11-03 | 2019-11-03 | 2019-11-04 |  | ضعف كفاءة المقاول الفنية |  | 41.0245 | 30.9837 | منجز | No
2100005622 | أمانة / الحدود الشمالية | دراسات هندسية | ذات اولوية متوسطة | 2879880 | 143994 | 2879880 | 2563155 | 1010933222 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-12-02 | 2021-11-21 | 2022-02-12 | 2022-02-12 | 2021-11-21 |  | اخرى |  | 41.0543 | 30.9539 | منجز | No
2100064013 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 286999946.7 | 14349997.335 | 201776511.91 | 201776511.91 | 1010090181 | لا | 0 | 180809050240 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-12-09 | 2016-05-24 | 2021-12-31 | 2021-12-31 |  |  | تأخرصرف المستحقات المالية |  | 39.1677 | 21.5008 | Failed | No
2100047773 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 2421847.1 | 121092.355 | 1245040 | 1245040 | 3450011720 | لا | 0 |  | مسحوب | منهجية القيمة المكتسبة | 55 | 55 | 2015-06-21 | 2016-06-15 | 2021-12-01 | 2021-12-01 |  |  | ضعف كفاءة المقاول الفنية |  | 43.7376 | 28.766 | مسحوب | No
2100013764 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 726894 | 36344.7 | 160000 | 160000 | 3450010543 | لا | 0 |  | مسحوب | منهجية القيمة المكتسبة | 21 | 21 | 2015-09-06 | 2016-08-31 | 2020-09-15 | 2020-09-15 |  |  | ضعف كفاءة المقاول الفنية |  | 42.2374 | 30.3627 | مسحوب | No
2100024754 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 1329800 | 66490 | 1003627 | 1003627 | 2511003200 | لا | 0 | 190309094055 | مسحوب | تكلفة العمل المنجز | 62 | 62 | 2013-03-30 | 2015-03-20 | 2022-01-01 | 2022-01-01 |  |  | ضعف كفاءة المقاول الفنية |  | 44.3216 | 29.1537 | مسحوب | No
2100019471 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 560630 | 28031.5 | 454110 | 454110 | 1122002403 | لا | 0 | 200309020385 | جاري | منهجية القيمة المكتسبة | 93 | 100 | 2014-08-07 | 2015-08-07 | 2023-03-31 | 2023-03-31 |  |  | اخرى |  | 44.3067 | 29.1531 | متأخر | No
2100076650 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 10444000 | 522200 | 9367278 | 9367278 | 1010179017 | لا | 0 | 181001211805 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-01-01 | 2020-12-23 | 2022-03-27 | 2022-03-27 | 2020-12-23 |  | ضعف كفاءة المقاول الفنية |  | 43.5211 | 29.6298 | منجز | No
2100019526 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 398340 | 19917 | 0 | 0 | 1010288150 | لا | 0 | 190409118863 | مسحوب | منهجية القيمة المكتسبة | 37 | 100 | 2018-08-28 | 2019-11-21 | 2021-09-15 | 2021-09-15 |  |  | ضعف كفاءة المقاول الفنية |  | 43.7462 | 28.7696 | مسحوب | No
2100020241 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 11986002 | 599300.1 | 0 | 0 | 1010161026 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0 | 100 | 2018-07-31 | 2020-07-20 | 2023-02-01 | 2023-02-01 |  |  | اخرى |  | 42.6509 | 17.1567 | مسحوب | No
2100027436 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 3622750 | 181137.5 | 1862530 | 1862530 | 3451001742 | لا | 0 | 190701017319 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 96 | 100 | 2019-06-20 | 2020-07-01 | 2021-01-15 | 2021-01-15 | 2020-07-01 |  | ضعف كفاءة المقاول الفنية |  | 38.6645 | 31.6718 | منجز | No
2100014210 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 887150 | 44357.5 | 887150 | 887150 | 5856009437 | لا | 0 | 200209122587 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2020-01-12 | 2021-01-12 | 2021-04-22 | 2021-04-22 | 2021-01-12 |  | ضعف كفاءة المقاول الفنية |  | 43.5447 | 29.6119 | منجز | No
2100034020 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 6410000 | 320500 | 0 | 0 | 1131029336 | لا | 0 |  | مسحوب | منهجية القيمة المكتسبة | 55 | 55 | 2015-10-04 | 2017-03-26 | 2021-07-18 | 2021-07-18 |  |  | تأخرصرف المستحقات المالية |  | 41.0145 | 30.9668 | مسحوب | No
2100048565 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 971500 | 48575 | 0 | 0 | 3357007585 | لا | 0 |  | مسحوب | منهجية القيمة المكتسبة | 1 | 100 | 2019-11-14 | 2020-11-13 | 2021-06-15 | 2021-06-15 |  |  | ضعف كفاءة المقاول الفنية |  | 43.1426 | 29.8472 | مسحوب | No
2100024791 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 387200 | 19360 | 276900 | 276900 | 1010288150 | لا | 0 |  | مسحوب | منهجية القيمة المكتسبة | 90 | 90 | 2018-08-28 | 2019-08-23 | 2021-12-01 | 2021-12-01 |  |  | ضعف كفاءة المقاول الفنية |  | 43.737 | 28.7605 | مسحوب | No
2100036702 | أمانة / الحدود الشمالية | تشييد | ذات اولوية متوسطة | 4597526.8 | 229876.34 | 4137918 | 4137918 | 3451001215 | لا | 0 | 200209128208 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2015-08-27 | 2019-10-05 | 2020-12-01 | 2020-12-01 | 2019-10-05 |  | ضعف كفاءة المقاول الفنية |  | 38.6771 | 31.6693 | منجز | No
2100025524 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 1359750 | 67987.5 | 1359750 | 1359750 | 1010179017 | لا | 0 | 191001198845 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-07-30 | 2020-05-25 | 2020-05-29 | 2020-05-29 | 2020-05-25 |  | ضعف كفاءة المقاول الفنية |  | 43.5419 | 29.6106 | منجز | No
2100034370 | أمانة / الحدود الشمالية | تشييد | ذات اولوية متوسطة | 1631999.04 | 81599.952 | 641424 | 641424 | 3450011349 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2015-08-10 | 2019-12-12 | 2020-11-15 | 2020-11-15 | 2019-12-12 |  | أوامر سامية |  | 42.2478 | 30.3531 | منجز | No
2100071901 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 8294984 | 414749.2 | 6559272 | 6559272 | 3453001773 | لا | 0 | 181001133595 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-11-05 | 2020-05-11 | 2020-11-08 | 2020-11-08 | 2020-05-11 |  |  |  | 44.7311 | 28.8952 | منجز | No
2100065903 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 3233420 | 161671 | 2345340 | 2345340 | 3450009076 | لا | 0 | 181001144460 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 89 | 100 | 2019-02-19 | 2020-02-14 | 2022-07-01 | 2022-07-01 | 2020-02-14 |  |  |  | 44.7353 | 28.8854 | منجز | No
2100048484 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 4702900 | 235145 | 3026500 | 3026500 | 3450006687 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 94 | 94 | 2011-04-30 | 2012-04-24 | 2020-01-09 | 2020-01-09 | 2012-04-24 |  |  |  | 41.0195 | 30.9714 | منجز | No
2100093052 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 817802 | 40890.1 | 735896 | 735896 | 3450010379 | لا | 0 | 190301092379 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-03-07 | 2020-03-02 | 2021-03-15 | 2021-03-15 | 2020-03-02 |  | ضعف كفاءة المقاول الفنية |  | 41.0052 | 30.9754 | منجز | No
2100082902 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 39371149.25 | 1968557.4625 | 30807473.67 | 30807473.67 | 3450007800 | لا | 0 | 181201477847 | جاري | منهجية القيمة المكتسبة | 83 | 85 | 2015-11-11 | 2017-10-31 | 2024-01-29 | 2024-01-29 |  |  | ضعف كفاءة المقاول الفنية | تم إنذار المقاول كتابيا | 41.0012 | 30.9757 | منتظم | No
2100068456 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 2530190 | 126509.5 | 2421940 | 2421940 | 3450008799 | لا | 0 |  | فسخ العقد | منهجية القيمة المكتسبة | 72 | 100 | 2018-05-02 | 2019-04-28 | 2021-12-15 | 2021-12-15 |  |  | ضعف كفاءة المقاول الفنية |  | 42.2565 | 30.3479 | مسحوب | No
2100025034 | أمانة / الحدود الشمالية | تشييد | ذات اولوية متوسطة | 6922900 | 346145 | 5713400 | 5713400 | 3450009076 | لا | 0 | 180709020980 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2015-03-17 | 2016-10-17 | 2019-12-01 | 2019-12-01 | 2016-10-17 |  |  |  | 43.5364 | 29.6271 | منجز | No
2100010846 | أمانة / الحدود الشمالية | دراسة الجدوى | ذات اولوية متوسطة | 1099956 | 54997.8 | 907200 | 865200 | 3400014764 | لا | 0 | 181209471077 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-10-14 | 2020-10-14 | 2022-02-16 | 2022-02-16 | 2020-10-14 |  | اخرى |  | 41.0383 | 30.9638 | منجز | No
2100024975 | أمانة / الحدود الشمالية | تشييد | ذات اولوية متوسطة | 572800 | 28640 | 0 | 0 | 3450009089 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-06-15 | 2021-06-14 | 2021-06-13 | 2021-06-13 | 2021-06-14 |  | اخرى |  | 43.1377 | 29.8515 | منجز | No
2100013742 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 2437425 | 121871.25 | 0 | 0 | 3451001742 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 0 | 0 | 2018-11-09 | 2020-09-28 | 2020-09-28 | 2020-09-28 |  |  | ضعف كفاءة المقاول الفنية |  | 38.6742 | 31.6682 | مسحوب | No
2100050164 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 5794790 | 289739.5 | 5794790 | 5794790 | 1010127437 | لا | 0 | 181001143407 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-01-30 | 2020-07-21 | 2020-11-15 | 2020-11-15 | 2020-07-21 |  | ضعف كفاءة المقاول الفنية |  | 42.2437 | 30.353 | منجز | No
2100019596 | أمانة / الحدود الشمالية | تشييد | ذات اولوية متوسطة | 112500 | 5625 | 112500 | 112500 | 3453003284 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-05-27 | 2019-10-25 | 2019-10-25 | 2019-10-25 | 2019-10-25 |  |  |  | 41.0234 | 30.9816 | منجز | No
2100033843 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 3271150 | 163557.5 | 2741602 | 2741602 | 3450007439 | لا | 0 | 190201036747 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 95 | 100 | 2018-12-24 | 2019-12-19 | 2023-05-28 | 2023-05-28 |  |  | ضعف كفاءة المقاول الفنية | تم إشعار المقاول كتابيا بالتأخير | 41.0588 | 30.9678 | منتظم | No
2100019666 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 7668022.225 | 383401.1113 | 6972277 | 6972277 | 1011010795 | لا | 0 | 181109224146 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-02-04 | 2016-01-30 | 2019-03-11 | 2019-03-11 | 2016-01-30 |  |  |  | 43.5112 | 29.6256 | منجز | No
2100010076 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 1301000 | 65050 | 1300999 | 1300999 | 3453003284 | لا | 0 | 200201079874 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-09-25 | 2019-09-20 | 2019-09-09 | 2019-09-09 | 2019-09-20 |  | ضعف كفاءة المقاول الفنية |  | 41.048 | 30.9591 | منجز | No
2100036923 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 461433 | 23071.65 | 461433 | 461433 | 3450172337 | لا | 0 | 200201039941 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 92 | 100 | 2019-10-21 | 2020-04-18 | 2020-04-18 | 2020-04-18 | 2020-04-18 |  | ضعف كفاءة المقاول الفنية |  | 41.055 | 30.9722 | منجز | No
2100019386 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 19268071 | 963403.55 | 14506905 | 14506905 | 3450007800 | لا | 0 | 181101362873 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2015-11-08 | 2018-04-26 | 2020-05-15 | 2020-05-15 | 2018-04-26 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 41.0375 | 30.9573 | منجز | No
2100014070 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 5000000 | 250000 | 2737565 | 2737565 | 1010240630 | لا | 2261933 |  | مسحوب | منهجية القيمة المكتسبة | 55 | 55 | 2013-07-29 | 2015-07-20 | 2022-01-01 | 2022-01-01 |  |  | تغيرات في نطاق المشروع |  | 41.0377 | 30.9571 | مسحوب | No
2100069871 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 11478980 | 573949 | 8215480 | 8215480 | 3450007800 | لا | 0 | 190301057870 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 97 | 100 | 2018-09-29 | 2019-05-27 | 2023-05-31 | 2023-05-31 |  |  |  |  | 40.9982 | 30.9824 | منتظم | No
2100024802 | أمانة / الحدود الشمالية | تشييد | ذات اولوية متوسطة | 1724060 | 86203 | 1040059 | 1040059 | 3452007733 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2014-11-12 | 2015-11-08 | 2020-12-01 | 2020-12-01 | 2015-11-08 |  | ضعف كفاءة المقاول الفنية |  | 38.6589 | 31.6645 | منجز | No
2100050676 | أمانة / الحدود الشمالية | تشييد | ذات اولوية متوسطة | 2709530 | 135476.5 | 2709530 | 2709530 | 3450006303 | لا | 0 | 181201389593 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-11-08 | 2019-11-03 | 2019-11-05 | 2019-11-05 | 2019-11-03 |  | تأخرصرف المستحقات المالية |  | 41.0175 | 30.9759 | منجز | No
2100067664 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 1045000 | 52250 | 1045000 | 1045000 | 1010179017 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-12-20 | 2020-10-15 | 2021-01-15 | 2021-01-15 | 2020-10-15 |  | ضعف كفاءة المقاول الفنية |  | 43.5159 | 29.6288 | منجز | No
2100050212 | أمانة / الحدود الشمالية | تشييد | ذات اولوية متوسطة | 2978500 | 148925 | 2978500 | 2978500 | 3453002609 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-07-16 | 2020-07-05 | 2020-04-11 | 2020-04-11 | 2020-07-05 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 43.5336 | 29.6748 | منجز | No
2100059382 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 2958050 | 147902.5 | 1656780 | 1656780 | 3450006578 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 58 | 70 | 2018-09-16 | 2021-08-25 | 2023-05-31 | 2023-05-31 |  |  |  | مخطط لسحبه وإعادة ترسيته | 43.5423 | 29.6229 | متأخر | No
2100051656 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 7905295 | 395264.75 | 3677867 | 3677867 | 3453001722 | لا | 0 |  | مسحوب | منهجية القيمة المكتسبة | 47 | 100 | 2015-02-05 | 2016-03-04 | 2016-03-04 | 2016-03-04 |  |  | ضعف كفاءة المقاول الفنية |  | 42.2439 | 30.359 | مسحوب | No
2100076300 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 1001000 | 50050 | 800798 | 800798 | 3450010379 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 90 | 100 | 2019-10-02 | 2020-09-26 | 2021-05-30 | 2021-05-30 | 2020-09-26 |  | ضعف كفاءة المقاول الفنية |  | 44.7431 | 28.8782 | منجز | No
2100027930 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 9670623.9 | 483531.195 | 6048898 | 6048898 | 3450007800 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 85 | 100 | 2015-10-11 | 2017-04-02 | 2022-07-01 | 2022-07-01 | 2017-04-02 |  | تأخرصرف المستحقات المالية |  | 41.0298 | 30.9828 | منجز | No
2100033471 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 13855850 | 692792.5 | 13855850 | 13855850 | 3450009076 | لا | 0 | 181109315248 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-09-02 | 2019-08-24 | 2019-08-28 | 2019-08-28 | 2019-08-24 |  |  |  | 41.0056 | 30.9755 | منجز | No
2100033810 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 690300 | 34515 | 690300 | 690300 | 1010181249 | لا | 0 | 190509037647 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-09-05 | 2019-08-30 | 2020-03-12 | 2020-03-12 | 2019-08-30 |  | ضعف كفاءة المقاول الفنية |  | 42.2515 | 30.3589 | منجز | No
2100050805 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 4527116 | 226355.8 | 1713000 | 1713000 | 3453002609 | لا | 0 | 190309093918 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-07-16 | 2020-01-08 | 2021-11-21 | 2021-11-21 | 2020-01-08 |  | أوامر سامية |  | 43.5294 | 29.6306 | منجز | No
2100081981 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 687382 | 34369.1 | 407507 | 407507 | 3450010575 | لا | 0 |  | مسحوب | منهجية القيمة المكتسبة | 59 | 59 | 2015-06-11 | 2016-06-05 | 2020-09-15 | 2020-09-15 |  |  | اخرى |  | 42.2406 | 30.3559 | مسحوب | No
2100050735 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 7314286 | 365714.3 | 5461182.6 | 5271310.46 | 1011010795 | لا | 0 | 180801041068 | جاري | منهجية القيمة المكتسبة | 97 | 100 | 2019-06-21 | 2021-01-21 | 2023-05-31 | 2023-05-31 |  |  | ضعف كفاءة المقاول الفنية |  | 44.3222 | 29.1478 | منتظم | No
2100071923 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 227700 | 11385 | 227700 | 227700 | 1010179017 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-11-14 | 2020-05-14 | 2020-05-09 | 2020-05-09 | 2020-05-14 |  | اخرى |  | 43.1454 | 29.8476 | منجز | No
2100069930 | البريد السعودي | تشييد | ذات اولوية متوسطة | 4011868.8 | 200593.44 | 182241.89 | 182241.89 | 3400000500 | لا | 0 | 190309057613 | مسحوب | منهجية القيمة المكتسبة | 23 | 100 | 2018-12-12 | 2020-05-28 | 2020-03-23 | 2020-03-23 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.1435 | 31.0206 | مسحوب | No
2100070604 | هيئة تطوير بوابة الدرعية | تشييد | ذات اولوية متوسطة | 16087634 | 804381.7 | 14800623.28 | 14800623.28 | 4030246002 | لا | 0 | 200509087004 | جاري | اخرى | 92 | 100 | 2019-10-10 | 2020-11-30 | 2020-11-30 | 2020-11-30 |  |  |  |  | 46.5752 | 24.7374 | Failed | No
2100012235 | أمانة / الرياض | تشييد | ذات اولوية عالية | 9991735 | 499586.75 | 6654613.74 | 0 | 1116005202 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 71.24 | 100 | 2015-01-13 | 2016-07-06 | 2020-04-24 | 2020-04-24 | 2016-07-06 |  | ضعف كفاءة المقاول الفنية |  | 44.422 | 24.5358 | منجز | Yes
2100029632 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3898670 | 194933.5 | 2800608.5 | 0 | 1116005202 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 90.9 | 100 | 2014-09-03 | 2016-08-23 | 2020-10-22 | 2020-10-22 | 2016-08-23 |  | ضعف كفاءة المقاول الفنية |  | 45.301 | 24.0731 | منجز | Yes
2100067992 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 2091750 | 104587.5 | 2091750 | 2091750 | 3450013972 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-09-16 | 2019-09-11 | 2019-09-11 | 2019-09-11 | 2019-09-11 |  |  |  | 42.2477 | 30.3507 | منجز | No
2100066021 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 2601400 | 130070 | 950494 | 950494 | 1010181249 | لا | 0 | 190509002084 | مسحوب | منهجية القيمة المكتسبة | 61 | 100 | 2018-09-18 | 2020-03-09 | 2021-12-30 | 2021-12-30 |  |  | ضعف كفاءة المقاول الفنية |  | 43.525 | 29.6266 | مسحوب | No
2100104720 | وزارة الموارد البشرية والتنمية الإجتماعية | تشييد | ذات اولوية منخفضة | 15585027.5 | 779251.375 | 8943032 | 8943032 | 1010224892 | لا | 0 | 180809064461 | مسحوب | الكميات التي تم تركيبها | 63 | 100 | 2014-10-27 | 2017-09-24 | 2023-12-31 | 2023-12-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 46.5345 | 24.751 | مسحوب | No
2100039701 | وزارة الموارد البشرية والتنمية الإجتماعية | تشييد | ذات اولوية منخفضة | 13622916 | 681145.8 | 5846642.09 | 5846642.09 | 1131022493 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 76 | 100 | 2015-04-25 | 2017-04-02 | 2021-11-25 | 2021-11-25 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 46.6236 | 24.4805 | مسحوب | No
2100064514 | أمانة / الرياض | تشييد | ذات اولوية عالية | 45954064 | 2297703.2 | 27275218 | 27275218 | 1116000094 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 62 | 100 | 2014-10-12 | 2017-04-06 | 2017-10-10 | 2017-10-10 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6745 | 24.7082 | مسحوب | No
2100091372 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 11907927 | 595396.35 | 10214409.0225 | 0 | 1017000207 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 93.69 | 100 | 2014-11-09 | 2016-02-02 | 2019-11-28 | 2019-11-28 | 2016-02-02 |  | ضعف كفاءة المقاول الفنية |  | 44.8233 | 20.4589 | منجز | Yes
2100099761 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 231153202.44 | 11557660.122 | 228613733.77 | 210527168.16 | 1010012911 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-04-23 | 2015-04-01 | 2020-11-02 | 2020-11-02 | 2015-04-01 |  |  |  | 46.6814 | 24.7069 | منجز | No
2100082574 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 328057257 | 16402862.85 | 328057257 | 328057257 | 1010054806 | لا | 0 | 181101358920 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-09-01 | 2022-08-16 | 2022-08-17 | 2022-08-17 | 2022-08-16 |  |  |  | 46.6827 | 24.7032 | منجز | No
2100015201 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 121936092.56 | 6096804.628 | 58475721.56 | 45922461.4 | 2050022550 | نعم | 459224614 |  | مسحوب | الكميات التي تم تركيبها | 53 | 100 | 2013-08-25 | 2016-01-28 | 2016-11-24 | 2016-11-24 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6731 | 24.7007 | مسحوب | No
2100000851 | الهيئة الملكية لمدينة الرياض | تشييد | ذات اولوية عالية | 35401791116 | 1770089555.8 | 32684404893.7 | 32684404893.7 | 1010307848 | لا | 0 | 190209017632 | جاري | اخرى | 96.75 | 100 | 2013-10-30 | 2018-10-29 | 2022-06-30 | 2022-06-30 |  |  | تغيرات في نطاق المشروع |  | 46.7177 | 24.6991 | Failed | No
2100039362 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3792890 | 189644.5 | 410.37 | 0 | 1116004922 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 66 | 100 | 2013-02-13 | 2014-11-08 | 2020-03-21 | 2020-03-21 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6837 | 24.7032 | مسحوب | Yes
2100081476 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2655880 | 132794 | 225750 | 0 | 1010293549 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 8.5 | 100 | 2015-05-26 | 2016-08-18 | 2023-03-25 | 2023-03-25 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6775 | 24.7025 | Failed | Yes
2100109572 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية | 2899817909.85 | 144990895.4925 | 419390776.97 | 419390776.97 | 1010609431 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 20.11 | 99.77 | 2015-01-08 | 2018-12-17 | 2026-12-31 | 2026-12-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 46.6953 | 24.7387 | Failed | No
2100054740 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 76233080.36 | 3811654.018 | 68498162.94 | 68498162.94 | 1010014477 | لا | 0 | 180809057596 | جاري | الكميات التي تم تركيبها | 94 | 100 | 2013-03-24 | 2015-08-27 | 2023-03-31 | 2023-03-31 |  |  | التنسيق مع أصحاب المصلحه (خدمات |  | 46.6759 | 24.7082 | Failed | No
2100095141 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 142771891 | 7138594.55 | 142740776.68 | 142740776.68 | 1010044185 | لا | 0 | 180809057593 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-08-24 | 2016-08-23 | 2018-12-21 | 2018-12-21 | 2016-08-23 |  |  |  | 46.6718 | 24.7057 | منجز | No
2100100671 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 157017543 | 7850877.15 | 77733172.07 | 77733172.07 | 1010142553 | لا | 0 | 180809057434 | مسحوب | الكميات التي تم تركيبها | 53 | 100 | 2013-02-23 | 2017-03-15 | 2017-03-14 | 2017-03-14 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6786 | 24.7057 | مسحوب | No
2100068574 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 156309688.46 | 7815484.423 | 114582371.07 | 114582371.07 | 1116000082 | لا | 0 | 180809048034 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2015-06-07 | 2019-04-25 | 2021-03-17 | 2021-03-17 | 2019-04-25 |  | لا يوجد تأخير |  | 45.2815 | 24.0637 | منجز | No
2100191693 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 11875896.61 | 593794.8305 | 11875896.61 | 10686681.65 | 1010012911 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2020-06-23 | 2021-12-23 | 2021-10-31 | 2021-10-31 | 2021-12-23 |  |  |  | 47.5679 | 24.2033 | منجز | No
2100004852 | المؤسسة العامة للتقاعد | تشييد | ذات اولوية عالية | 222891028.16 | 11144551.408 | 187133624.46 | 187133624.46 | 1010083181 | نعم | 187133624.41 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2013-05-25 | 2014-05-25 | 2021-12-31 | 2021-12-31 |  | 2014-05-25 | اخرى |  | 46.6363 | 24.7413 | منجز | No
2100038920 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 304991102.45 | 15249555.1225 | 97944368.69 | 47944368.69 | 1010271502 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 29 | 100 | 2014-06-07 | 2017-06-06 | 2017-12-19 | 2017-12-19 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6786 | 24.6994 | مسحوب | No
2100047471 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1195845 | 59792.25 | 932380 | 0 | 1015000676 | لا | 0 |  | جاري | تكلفة العمل المنجز | 85 | 100 | 2015-08-13 | 2016-11-05 | 2019-02-05 | 2019-02-05 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6933 | 24.6957 | Failed | Yes
2100068353 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 5948200 | 297410 | 5292664.18 | 0 | 1010194943 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 91.11 | 100 | 2015-07-30 | 2017-07-19 | 2020-04-02 | 2020-04-02 | 2017-07-19 |  | ضعف كفاءة المقاول الفنية |  | 45.3882 | 23.6167 | منجز | Yes
2100004115 | وزارة المالية | إشراف | ذات اولوية متوسطة | 2608200 | 130410 | 2263728.93 | 2263728.93 | 1010099661 | لا | 0 | 191001263240 | جاري | مدفوعات ساعات العمل | 44 | 90.8 | 2020-08-16 | 2023-04-17 | 2023-04-17 | 2023-04-17 |  |  | لا يوجد تأخير |  | 44.4096 | 24.5046 | خدمات عامة | No
2100191763 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 1721538 | 86076.9 | 510831.89 | 510831.89 | 1017000955 | لا | 0 | 200301068419 | جاري | منهجية القيمة المكتسبة | 61.35 | 100 | 2020-08-20 | 2021-08-09 | 2022-07-31 | 2022-07-31 |  |  |  |  | 46.7762 | 22.2491 | Failed | No
2100191623 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 7097530 | 354876.5 | 6099503.03 | 6099503.03 | 1010061463 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99.07 | 100 | 2020-06-15 | 2021-06-15 | 2021-06-01 | 2021-06-01 | 2021-06-15 |  |  |  | 46.6919 | 24.534 | منجز | No
2100075762 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 191093389.5 | 9554669.475 | 69912722 | 69912722 | 1010142553 | نعم | 69912722 | 180809058142 | مسحوب | الكميات التي تم تركيبها | 44 | 100 | 2014-01-28 | 2017-05-01 | 2017-05-02 | 2017-05-02 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6786 | 24.7107 | مسحوب | No
2100064761 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4939151.65 | 246957.5825 | 0 | 0 | 1010243840 | لا | 0 | 200101047411 | جاري | الكميات التي تم تركيبها | 21 | 22 | 2019-10-08 | 2020-08-29 | 2020-08-30 | 2020-08-30 |  |  |  |  | 46.6759 | 24.7094 | Failed | No
2100100881 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1016077.25 | 50803.8625 | 606991 | 0 | 1017000694 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 40 | 95 | 2015-07-29 | 2016-10-21 | 2019-09-21 | 2019-09-21 |  |  | ضعف كفاءة المقاول الفنية |  | 45.6139 | 20.4314 | Failed | Yes
2100080430 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 31110620 | 1555531 | 5722177.79 | 5722177.79 | 1010216462 | لا | 0 | 180809057371 | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 94.69 | 100 | 2015-06-03 | 2021-07-28 | 2023-02-15 | 2023-02-15 |  |  |  | أخرى | 46.7324 | 24.6679 | متأخر | No
2100025001 | أمانة / الرياض | تشييد | ذات اولوية عالية | 51447807 | 2572390.35 | 2793357.05 | 2793357.05 | 1010010506 | لا | 0 | 190201046640 | ايقاف جزئي | تكلفة العمل المنجز | 15.97 | 100 | 2019-05-29 | 2021-05-27 | 2021-05-27 | 2021-05-27 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 46.6759 | 24.7107 | Failed | No
2100081583 | أمانة / الرياض | تشييد | ذات اولوية عالية | 117399100 | 5869955 | 114815330.22 | 114815330.2 | 1010048595 | لا | 0 | 190301022933 | جاري | الكميات التي تم تركيبها | 99 | 100 | 2019-10-05 | 2021-11-12 | 2021-11-11 | 2021-11-11 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6745 | 24.7069 | Failed | No
2100044380 | أمانة / الرياض | تشييد | ذات اولوية عالية | 67382228.55 | 3369111.4275 | 56736021.58 | 56736021.58 | 1010009804 | لا | 0 | 180901068367 | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 94 | 94 | 2018-12-27 | 2021-05-29 | 2021-05-30 | 2021-05-30 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6786 | 24.7057 | Failed | No
2100043525 | أمانة / الرياض | تشييد | ذات اولوية عالية | 144880703.03 | 7244035.1515 | 132907948.02 | 132907948.02 | 1010030427 | لا | 0 | 181101306978 | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 100 | 10 | 2019-01-02 | 2021-08-30 | 2021-08-30 | 2021-08-30 |  |  |  |  | 46.6773 | 24.7069 | Failed | No
2100070965 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 37272925.01 | 1863646.2505 | 34410979 | 34410979 | 1010149483 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2010-08-16 | 2014-12-14 | 2022-08-31 | 2022-08-31 | 2014-12-14 |  | اخرى |  | 42.8679 | 23.9265 | منجز | No
2100037240 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 54070695 | 2703534.75 | 35104616 | 35104616 | 1185000614 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 69.7 | 100 | 2013-12-04 | 2018-02-12 | 2022-06-30 | 2022-06-30 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال | تم إنذار المقاول كتابيا | 44.8866 | 20.4606 | مسحوب | No
2100038463 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 20416070 | 1020803.5 | 4510937 | 4510937 | 1010270823 | نعم | 1540989.9 |  | جاري | الكميات التي تم تركيبها | 70 | 97 | 2019-01-16 | 2021-12-14 | 2022-11-30 | 2022-11-30 |  |  |  |  | 45.9735 | 24.4207 | Failed | No
2100080544 | أمانة / الرياض | تشييد | ذات اولوية عالية | 30398563.99 | 1519928.1995 | 27995057.82 | 27995057.82 | 1010161812 | لا | 0 | 180901076807 | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 83.5 | 100 | 2019-07-02 | 2021-05-09 | 2021-05-09 | 2021-05-09 |  |  |  |  | 46.6731 | 24.7069 | Failed | No
2100069160 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 214808475 | 10740423.75 | 186946379 | 186946379 | 1010044185 | لا | 0 | 190409118830 | جاري | الكميات التي تم تركيبها | 87.13 | 91.88 | 2019-07-01 | 2021-06-10 | 2023-07-10 | 2023-07-10 |  |  |  |  | 46.6841 | 24.7082 | منتظم | No
2100080802 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1387045 | 69352.25 | 1015045 | 0 | 1123002388 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 75 | 2018-01-04 | 2019-12-25 | 2019-12-25 | 2019-12-25 | 2019-12-25 |  |  |  | 46.6699 | 24.7169 | منجز | Yes
2100075025 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1248255 | 62412.75 | 42079 | 0 | 1010237871 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 96 | 100 | 2015-08-29 | 2016-11-21 | 2016-11-21 | 2016-11-21 | 2016-11-21 |  | ضعف كفاءة المقاول الفنية |  | 45.5253 | 23.5321 | منجز | Yes
2100019950 | معهد الإدارة العامة | تصميم | ذات اولوية عالية وعاجلة | 1100000 | 55000 | 693000 | 693000 | 1010322156 | لا | 0 | 181009216817 | جاري | التكلفة المفوترة | 63 | 100 | 2018-06-10 | 2018-10-27 | 2023-03-01 | 2023-03-01 |  |  |  |  | 46.687 | 24.8218 | Failed | No
2100201891 | الجمارك السعودية | تشييد | ذات اولوية عالية | 328085039.08 | 16404251.954 | 103318309.67 | 103318309.67 | 1010132551 | لا | 0 |  | جاري | تكلفة العمل المنجز | 53 | 100 | 2021-09-22 | 2023-03-22 | 2023-03-22 | 2023-03-22 |  |  |  |  | 48.719 | 21.0953 | Failed | No
2100011513 | وزارة الدفاع / الإدارة الهندسية والاشغال بالخدمات الصحية | تشييد | ذات اولوية عالية | 30326000 | 1516300 | 30326000 | 30326000 | 4030056662 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-01-26 | 2016-09-05 | 2021-12-31 | 2021-12-31 | 2016-09-05 |  | تغيرات في نطاق المشروع |  | 44.8014 | 20.4203 | منجز | No
2100081465 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 555950 | 27797.5 | 39811 | 0 | 1118001997 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 30 | 34 | 2018-02-24 | 2022-02-03 | 2022-02-03 | 2022-02-03 |  |  |  |  | 42.9103 | 24.1315 | متأخر | Yes
2100083005 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 5363882 | 268194.1 | 4052751.4 | 0 | 1010171813 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 94 | 100 | 2015-02-24 | 2016-02-09 | 2020-01-19 | 2020-01-19 | 2016-02-09 |  | ضعف كفاءة المقاول الفنية |  | 46.6992 | 24.6965 | منجز | Yes
2100191531 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 14801550 | 740077.5 | 11809968.09 | 5871496.14 | 1010227442 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 91.77 | 64.24 | 2021-05-27 | 2022-11-27 | 2022-11-26 | 2022-11-26 |  |  |  |  | 46.524 | 24.5636 | منتظم | No
2100026670 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1950362 | 97518.1 | 41659 | 0 | 1010279126 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 80 | 100 | 2014-06-04 | 2015-08-28 | 2015-08-28 | 2015-08-28 | 2015-08-28 |  | ضعف كفاءة المقاول الفنية |  | 46.6782 | 24.7069 | منجز | Yes
2100029816 | أمانة / الرياض | تشييد | ذات اولوية عالية | 1887540 | 94377 | 41378 | 0 | 1010150014 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 100 | 2013-12-09 | 2014-12-04 | 2014-12-04 | 2014-12-04 | 2014-12-04 |  |  |  | 44.8708 | 22.8448 | منجز | Yes
2100009936 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1116000 | 55800 | 1054000 | 1054000 | 1010108088 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 94 | 94 | 2017-01-31 | 2021-01-16 | 2021-01-17 | 2021-01-17 |  |  |  |  | 46.6775 | 24.7075 | Failed | No
2100012935 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 5472800 | 273640 | 3129797.55 | 0 | 1010010305 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 90 | 100 | 2015-10-03 | 2017-09-22 | 2020-06-06 | 2020-06-06 | 2017-09-22 |  | ضعف كفاءة المقاول الفنية |  | 44.3995 | 24.5067 | منجز | Yes
2100100741 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2674994 | 133749.7 | 190039.55 | 0 | 1118001997 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 13.5 | 26 | 2018-11-07 | 2021-04-25 | 2021-04-25 | 2021-04-25 |  |  |  |  | 46.674 | 24.7082 | مسحوب | Yes
2100012740 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2021000 | 101050 | 1576400 | 0 | 1010015152 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 78 | 78 | 2013-02-23 | 2016-05-13 | 2016-05-13 | 2016-05-13 | 2016-05-13 |  |  |  | 46.6737 | 24.706 | منجز | Yes
2100062451 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1350000 | 67500 | 829000 | 0 | 1131031806 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 61 | 100 | 2015-10-03 | 2016-09-27 | 2020-02-07 | 2020-02-07 |  |  | ضعف كفاءة المقاول الفنية |  | 46.0999 | 25.115 | Failed | Yes
2100006860 | الهيئة الملكية لمدينة الرياض | تشييد | ذات اولوية عالية | 18227962 | 911398.1 | 16405129.3 | 16405129.3 | 1010079992 | لا | 0 | 190209009617 | منجز – استلام نهائي | اخرى | 100 | 100 | 2018-06-24 | 2020-11-29 | 2020-10-01 | 2020-10-01 | 2020-11-29 | 2021-11-19 |  |  | 46.8811 | 24.3903 | منجز | No
2100013134 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3557640 | 177882 | 981650 | 0 | 1010197183 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-09-21 | 2016-09-10 | 2016-09-10 | 2016-09-10 | 2016-09-10 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 46.6823 | 24.7068 | منجز | Yes
2100043514 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4045000 | 202250 | 865862.5 | 0 | 1017000207 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 92 | 100 | 2014-12-26 | 2016-06-18 | 2020-10-15 | 2020-10-15 | 2016-06-18 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 46.6857 | 24.715 | منجز | Yes
2100013694 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4187865 | 209393.25 | 41640 | 0 | 1116007126 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 69 | 100 | 2014-10-15 | 2016-07-21 | 2021-06-19 | 2021-06-19 | 2016-07-21 |  |  |  | 44.4727 | 24.5516 | منجز | Yes
2100016925 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2180619.9995 | 109031 | 42133 | 0 | 1116007038 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 96 | 100 | 2015-10-13 | 2017-01-05 | 2017-01-05 | 2017-01-05 | 2017-01-05 |  | ضعف كفاءة المقاول الفنية |  | 46.6864 | 24.7169 | منجز | Yes
2100012386 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3360000 | 168000 | 42057 | 0 | 1010231660 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 0 | 100 | 2015-07-01 | 2016-09-22 | 2016-09-22 | 2016-09-22 |  |  | تأخرصرف المستحقات المالية |  | 45.3731 | 25.8759 | مسحوب | Yes
2100080990 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2236340 | 111817 | 522385.23 | 0 | 1185002666 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 55.41 | 100 | 2015-10-28 | 2016-10-22 | 2019-08-22 | 2019-08-22 | 2016-10-22 |  | ضعف كفاءة المقاول الفنية |  | 44.854 | 20.453 | منجز | Yes
2100030483 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 10902682 | 545134.1 | 40708 | 0 | 1010056094 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 89 | 100 | 2012-06-08 | 2013-09-01 | 2021-01-30 | 2021-01-30 | 2013-09-01 |  | ضعف كفاءة المقاول الفنية |  | 44.8781 | 20.4279 | منجز | Yes
2100013145 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2563060.5 | 128153.025 | 0 | 0 | 1118001684 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 99 | 80 | 2018-12-21 | 2019-12-10 | 2019-12-10 | 2019-12-10 | 2019-12-10 |  |  |  | 46.7094 | 24.731 | منجز | No
2100024592 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 628900 | 31445 | 628900 | 0 | 1123002131 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2017-12-04 | 2018-11-19 | 2018-11-19 | 2018-11-19 | 2018-11-19 |  |  |  | 46.6754 | 24.7181 | منجز | Yes
2100031592 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 734000 | 36700 | 432150 | 0 | 1115001965 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-10-28 | 2019-10-13 | 2019-10-13 | 2019-10-13 | 2019-10-13 |  |  |  | 46.6617 | 24.7107 | منجز | Yes
2100045835 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1943200 | 97160 | 42079 | 0 | 1117001757 | لا | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 0 | 100 | 2015-08-20 | 2017-02-10 | 2017-02-09 | 2017-02-09 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6795 | 24.7107 | Failed | Yes
2100029315 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 750875 | 37543.75 | 41504 | 0 | 1010225108 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 54 | 100 | 2014-01-07 | 2015-01-02 | 2015-01-03 | 2015-01-03 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6727 | 24.7094 | مسحوب | Yes
2100032900 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 6559750 | 327987.5 | 5359127.96 | 0 | 1010056094 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 82 | 100 | 2014-11-03 | 2016-10-23 | 2020-07-08 | 2020-07-08 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6857 | 24.7038 | Failed | Yes
2100032550 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1411950 | 70597.5 | 733048.6 | 0 | 1130003142 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 86 | 100 | 2014-10-27 | 2016-01-20 | 2020-04-12 | 2020-04-12 | 2016-01-20 |  | ضعف كفاءة المقاول الفنية |  | 46.6939 | 24.7001 | منجز | Yes
2100027263 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 28570125 | 1428506.25 | 22607953.7479 | 0 | 1010168999 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-04-15 | 2017-04-04 | 2020-04-22 | 2020-04-22 | 2017-04-04 |  | ضعف كفاءة المقاول الفنية |  | 45.7674 | 25.5574 | منجز | Yes
2100043923 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1260000 | 63000 | 1092529.5 | 0 | 1010350311 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 44 | 2019-01-23 | 2020-01-18 | 2020-01-18 | 2020-01-18 | 2020-01-18 |  |  |  | 46.674 | 24.7269 | منجز | Yes
2100044516 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1898000 | 94900 | 41640 | 0 | 1010341087 | لا | 0 |  | جاري | تكلفة العمل المنجز | 82 | 100 | 2014-10-22 | 2016-01-15 | 2021-02-14 | 2021-02-14 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6768 | 24.6994 | Failed | Yes
2100046701 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2699400 | 134970 | 2699400 | 0 | 1010056094 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-11-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 | 2017-03-22 |  |  |  | 46.6459 | 24.6976 | منجز | Yes
2100029993 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 9049676 | 452483.8 | 3598947.2 | 0 | 1010171813 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 80 | 100 | 2014-09-22 | 2016-03-15 | 2020-06-13 | 2020-06-13 | 2016-03-15 |  | ضعف كفاءة المقاول الفنية |  | 46.6672 | 24.7082 | منجز | Yes
2100080533 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4349900 | 217495 | 0.01 | 0.01 | 1010154770 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 58.95 | 100 | 2007-12-03 | 2009-05-26 | 2020-03-31 | 2020-03-31 |  |  | ضعف كفاءة المقاول الفنية |  | 46.4489 | 24.9007 | مسحوب | No
2100045625 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2999999 | 149999.95 | 0 | 0 | 1010064540 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 99.06 | 100 | 2015-01-20 | 2016-07-30 | 2016-07-30 | 2016-07-30 | 2016-07-30 |  | ضعف كفاءة المقاول الفنية |  | 44.4934 | 25.3645 | منجز | No
2100042136 | جامعة الإمام محمد بن سعود الاسلامية | تصميم | ذات اولوية متوسطة | 934500 | 46725 | 934500 | 0 | 1010078921 | لا | 0 | 181209456341 | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2018-07-08 | 2018-10-29 | 2018-10-29 | 2018-10-29 | 2018-10-29 |  | لا يوجد تأخير |  | 46.7024 | 24.8109 | منجز | Yes
2100062311 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 7061207.06 | 353060.353 | 3735110 | 0 | 1010231660 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 52.9 | 100 | 2015-06-30 | 2017-02-19 | 2020-11-24 | 2020-11-24 |  |  | ضعف كفاءة المقاول الفنية |  | 44.4107 | 24.513 | Failed | Yes
2100063280 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 9499477 | 474973.85 | 6790782 | 6790740.9 | 1010168999 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 91 | 100 | 2014-10-19 | 2016-01-12 | 2020-01-19 | 2020-01-19 | 2016-01-12 |  | ضعف كفاءة المقاول الفنية |  | 46.6857 | 24.7063 | منجز | No
2100033530 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 870962 | 43548.1 | 39665 | 0 | 1116003379 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 55 | 100 | 2010-05-28 | 2011-08-21 | 2020-03-07 | 2020-03-07 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6733 | 24.7063 | مسحوب | Yes
2100072380 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 716394 | 35819.7 | 400757 | 0 | 1010346646 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 62 | 100 | 2015-07-04 | 2019-05-08 | 2019-05-07 | 2019-05-07 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6878 | 24.7094 | مسحوب | Yes
2100071326 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 6765300 | 338265 | 42073 | 0 | 1010010305 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 100 | 94 | 2015-08-04 | 2016-07-19 | 2019-12-16 | 2019-12-16 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 46.6981 | 24.71 | مسحوب | Yes
2100062462 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 318465 | 15923.25 | 0 | 0 | 1010290069 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 96 | 100 | 2019-05-29 | 2019-11-25 | 2019-11-19 | 2019-11-19 | 2019-11-25 |  | تأخرصرف المستحقات المالية |  | 44.6174 | 25.1795 | منجز | No
2100045404 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2441155 | 122057.75 | 41029 | 0 | 1010327811 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 49 | 100 | 2013-03-31 | 2014-06-24 | 2014-06-24 | 2014-06-24 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6864 | 24.7119 | مسحوب | Yes
2100071212 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2185600 | 109280 | 41991 | 0 | 2051047076 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 100 | 2015-04-28 | 2016-10-19 | 2017-04-19 | 2017-04-19 | 2016-10-19 |  |  |  | 46.7171 | 24.6965 | منجز | Yes
2100056151 | جامعة الإمام محمد بن سعود الاسلامية | دراسة الجدوى | ذات اولوية عالية | 43695417.15 | 2184770.8575 | 37137799.8648 | 37137799.8648 | 1010078921 | لا | 0 | 180909094689 | جاري | اخرى | 86 | 100 | 2012-04-24 | 2015-03-30 | 2023-12-31 | 2023-12-31 |  |  | تغيرات في نطاق المشروع |  | 46.6928 | 24.8173 | خدمات عامة | No
2100075526 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 739740 | 36987 | 41405 | 0 | 1116005842 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 61 | 100 | 2013-11-28 | 2019-03-24 | 2019-03-24 | 2019-03-24 |  |  | ضعف كفاءة المقاول الفنية |  | 43.6205 | 24.299 | مسحوب | Yes
2100074830 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3144770 | 157238.5 | 2982380 | 0 | 1010165175 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 94.84 | 100 | 2014-01-22 | 2015-11-20 | 2015-11-21 | 2015-11-21 | 2015-11-20 |  |  |  | 45.8768 | 25.2616 | منجز | Yes
2100080942 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 755885 | 37794.25 | 639015 | 0 | 1131000697 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-08-01 | 2016-01-28 | 2016-01-02 | 2016-01-02 | 2016-01-28 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 46.6871 | 24.7038 | منجز | Yes
2100075633 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 7999520 | 399976 | 5553392.95 | 0 | 1010178884 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 77 | 100 | 2014-03-05 | 2016-02-23 | 2022-12-12 | 2022-12-12 |  |  | ضعف كفاءة المقاول الفنية |  | 46.683 | 24.6951 | Failed | Yes
2100080592 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1742250 | 87112.5 | 1527250 | 0 | 1013001518 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 88 | 67 | 2018-10-31 | 2019-10-26 | 2019-10-27 | 2019-10-27 | 2019-10-26 |  | ضعف كفاءة المقاول الفنية |  | 46.7837 | 23.4384 | منجز | Yes
2100091335 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2254490.19 | 112724.5095 | 42058 | 0 | 1010299555 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 67 | 100 | 2015-06-18 | 2016-12-09 | 2016-12-09 | 2016-12-09 |  |  | تأخرصرف المستحقات المالية |  | 46.6837 | 24.7032 | Failed | Yes
2100078831 | جامعة الإمام محمد بن سعود الاسلامية | تصميم | ذات اولوية منخفضة | 892500 | 44625 | 892500 | 0 | 1010078921 | لا | 0 | 181209447610 | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2018-04-16 | 2018-07-01 | 2018-07-01 | 2018-07-01 | 2018-07-01 |  | لا يوجد تأخير |  | 46.7017 | 24.8102 | منجز | Yes
2100030586 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 6094440 | 304722 | 0 | 0 | 1010056094 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 50 | 1 | 2014-11-03 | 2016-11-03 | 2021-06-23 | 2021-06-23 | 2016-11-03 |  | ضعف كفاءة المقاول الفنية |  | 46.8832 | 23.4312 | منجز | No
2100075482 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2983277 | 149163.85 | 2068755.12 | 0 | 1017001454 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 71 | 100 | 2015-08-17 | 2017-08-06 | 2017-10-19 | 2017-10-19 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7033 | 24.704 | Failed | Yes
2100073544 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 19289707.15 | 964485.3575 | 12708842.26 | 12708842.26 | 1010185409 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 78 | 92 | 2019-11-27 | 2021-05-20 | 2023-03-31 | 2023-03-31 |  |  | التنسيق مع أصحاب المصلحه (خدمات | أخرى | 46.6635 | 24.6803 | متأخر | No
2100081340 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 20319438 | 1015971.9 | 7413222.71 | 0 | 1116001737 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 93.26 | 100 | 2015-08-05 | 2017-01-26 | 2020-03-23 | 2020-03-23 | 2017-01-26 |  | ضعف كفاءة المقاول الفنية |  | 42.9329 | 23.9116 | منجز | Yes
2100081572 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 10440194.7 | 522009.735 | 10440194.7841 | 0 | 1010127437 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-05-12 | 2018-08-11 | 2018-08-11 | 2018-08-11 | 2018-08-11 |  |  |  | 46.6809 | 24.7219 | منجز | Yes
2100091840 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 7183155.5 | 359157.775 | 1960204.15 | 0 | 1010178884 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 27.29 | 100 | 2015-01-10 | 2016-07-03 | 2016-07-03 | 2016-07-03 |  |  | ضعف كفاءة المقاول الفنية |  | 45.2867 | 24.0722 | مسحوب | Yes
2100047051 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3136955 | 156847.75 | 41308 | 0 | 1018000156 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 92 | 100 | 2013-08-24 | 2014-11-17 | 2019-07-01 | 2019-07-01 |  |  | ضعف كفاءة المقاول الفنية |  | 45.8664 | 25.2691 | مسحوب | Yes
2100091652 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 750000 | 37500 | 42022 | 0 | 1010178890 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 100 | 2015-07-04 | 2019-03-13 | 2019-03-13 | 2019-03-13 | 2019-03-13 |  |  |  | 46.3887 | 24.897 | منجز | Yes
2100099514 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1811958 | 90597.9 | 41807 | 0 | 1010265080 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 17 | 100 | 2015-01-10 | 2016-04-04 | 2018-12-18 | 2018-12-18 |  |  | ضعف كفاءة المقاول الفنية |  | 43.2687 | 24.3575 | مسحوب | Yes
2100081255 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2315191.4 | 115759.57 | 2311905.4 | 0 | 1131026032 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-12-19 | 2018-12-03 | 2018-03-03 | 2018-03-03 | 2018-12-03 |  |  |  | 44.8014 | 26.2973 | منجز | Yes
2100178511 | وزارة الثقافة | تصميم وتشييد | ذات اولوية عالية | 6808575 | 340428.75 | 6808575 | 5243425 | 4030330535 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2020-10-29 | 2021-02-24 | 2021-07-01 | 2021-07-01 |  | 2021-02-24 |  |  | 46.6237 | 24.6829 | منجز | No
2100095701 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1874360 | 93718 | 267922 | 0 | 1117002453 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 64 | 100 | 2015-02-07 | 2016-01-23 | 2018-12-13 | 2018-12-13 |  |  | ضعف كفاءة المقاول الفنية |  | 44.3834 | 23.4881 | Failed | Yes
2100028711 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1079150 | 53957.5 | 40688 | 0 | 4030197963 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 85 | 100 | 2012-01-23 | 2013-04-17 | 2021-06-23 | 2021-06-23 | 2013-04-17 |  |  |  | 45.8935 | 25.2864 | منجز | Yes
2100044660 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 798083 | 39904.15 | 0 | 0 | 1017000718 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2019-01-24 | 2021-01-12 | 2021-07-04 | 2021-07-04 | 2021-01-12 |  |  |  | 46.6824 | 24.711 | منجز | No
2100075924 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 650600 | 32530 | 41533 | 0 | 4030065096 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 0 | 100 | 2014-08-27 | 2015-08-12 | 2015-08-12 | 2015-08-12 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 43.6634 | 24.669 | Failed | Yes
2100093273 | أمانة / الرياض | تشييد | ذات اولوية عالية | 833670 | 41683.5 | 744190 | 744190 | 1136000392 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-10-20 | 2019-10-14 | 2019-11-14 | 2019-11-14 | 2019-10-14 |  | ضعف كفاءة المقاول الفنية |  | 45.2974 | 25.7158 | منجز | No
2100027381 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 5188000 | 259400 | 41196 | 0 | 1010255485 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 81 | 100 | 2014-05-07 | 2015-10-29 | 2015-10-29 | 2015-10-29 | 2015-10-29 |  |  |  | 46.6686 | 24.7057 | منجز | Yes
2100026121 | شركة الكهرباء | تشييد | ذات اولوية متوسطة | 375732375 | 18786618.75 | 328150237 | 328150237 | 1010011560 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2017-03-05 | 2019-07-26 | 2022-02-20 | 2022-02-20 | 2019-07-26 | 2019-08-01 | لا يوجد تأخير |  | 46.6761 | 24.7088 | منجز | No
2100083786 | وزارة الدفاع / الإدارة الهندسية والاشغال بالخدمات الصحية | تشييد | ذات اولوية عالية | 9623390.16 | 481169.508 | 9623390.16 | 4105121 | 1010146750 | لا | 0 | 190309038031 | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-07-17 | 2020-07-08 | 2022-11-08 | 2022-11-08 |  |  |  |  | 46.6803 | 24.7006 | منتظم | No
2100054600 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 220204542.14 | 11010227.107 | 127036000.3606 | 127036000.3606 | 1010008118 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 62 | 100 | 2011-10-02 | 2013-09-09 | 2019-07-07 | 2019-07-07 |  |  | ضعف كفاءة المقاول الفنية |  | 46.8343 | 24.6553 | مسحوب | No
2100029724 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 7366000 | 368300 | 415.17 | 0 | 1010168999 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 88 | 100 | 2013-12-26 | 2015-12-16 | 2019-12-23 | 2019-12-23 | 2015-12-16 |  | ضعف كفاءة المقاول الفنية |  | 46.6898 | 24.6976 | منجز | Yes
2100010275 | صندوق تنمية الموارد البشرية | تشييد | ذات اولوية منخفضة | 31421335.32 | 1571066.766 | 27026205.75 | 27026205.75 | 1010094008 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 98.8 | 100 | 2014-12-29 | 2016-12-07 | 2022-02-28 | 2022-02-28 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 44.8211 | 26.3053 | مسحوب | No
2100037041 | صندوق تنمية الموارد البشرية | تشييد | ذات اولوية منخفضة | 31334717.1 | 1566735.855 | 24100737.46 | 24100737.46 | 1010094008 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 90.65 | 100 | 2014-12-29 | 2017-12-18 | 2022-08-31 | 2022-08-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 45.2521 | 25.2451 | مسحوب | No
2100178544 | وزارة الثقافة | تصميم وإشراف | ذات اولوية عالية | 28000000 | 1400000 | 0 | 0 | 1010596943 | لا | 0 |  | لم يبدأ | اخرى | 50 | 50 | 2021-03-01 | 2023-03-01 | 2023-03-01 | 2023-03-01 |  |  |  |  | 46.7415 | 24.9356 | منتظم | No
2100190551 | شركة المياه الوطنية / منطقة الرياض | إشراف | ذات اولوية عالية | 18337000 | 916850 | 11436686.72 | 9833422.21 | 1010314421 | لا | 0 |  | جاري | التكلفة المفوترة | 71.6 | 71.6 | 2020-06-04 | 2022-06-04 | 2022-06-04 | 2022-06-04 |  |  |  |  | 46.7948 | 24.6527 | خدمات عامة | No
2100043610 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3969000 | 198450 | 291600.01 | 291600.01 | 1010250396 | لا | 0 | 200209125926 | جاري | الكميات التي تم تركيبها | 5 | 5 | 2019-09-19 | 2021-04-03 | 2021-04-03 | 2021-04-03 |  |  |  |  | 46.6704 | 24.7094 | Failed | No
2100047876 | شركة المياه الوطنية / منطقة الرياض | إشراف | ذات اولوية عالية | 6876144 | 343807.2 | 6104587.36 | 6104587.36 | 1010326770 | لا | 0 |  | منجز – استلام نهائي | التكلفة المفوترة | 89.48 | 100 | 2019-02-21 | 2021-02-22 | 2021-02-22 | 2021-02-22 |  | 2021-02-22 | لا يوجد تأخير |  | 46.7947 | 24.6527 | منجز | No
2100191726 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 2284000 | 114200 | 1954730 | 1954730 | 1010219753 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 95 | 100 | 2020-04-23 | 2020-07-23 | 2021-03-23 | 2021-03-23 | 2020-07-23 |  |  |  | 47.5433 | 25.0992 | منجز | No
2100090952 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1737000 | 86850 | 1737000 | 0 | 1123002152 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-02-06 | 2019-04-09 | 2019-04-09 | 2019-04-09 | 2019-04-09 |  |  |  | 44.8238 | 26.2967 | منجز | Yes
2100044763 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2770455 | 138522.75 | 41392 | 0 | 1117002921 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 46 | 47 | 2014-01-15 | 2014-12-31 | 2019-03-24 | 2019-03-24 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6764 | 24.7125 | مسحوب | Yes
2100191785 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 70680141 | 3534007.05 | 17202694.99 | 17202694.99 | 7001378517 | لا | 0 | 191101175746 | جاري | منهجية القيمة المكتسبة | 34.59 | 37.67 | 2020-09-06 | 2023-08-04 | 2023-08-06 | 2023-08-06 |  |  |  |  | 45.5868 | 20.4514 | منتظم | No
2100022400 | المؤسسة العامة للتقاعد | تشييد | ذات اولوية عالية | 2112500740.19 | 105625037.0095 | 1780948257.27 | 1780948257.27 | 2055002293 | نعم | 1984048257.27 |  | مسحوب | الكميات التي تم تركيبها | 99 | 100 | 2012-08-12 | 2022-04-20 | 2023-11-09 | 2023-11-09 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6349 | 24.7401 | مسحوب | No
2100058634 | جامعة الأميرة نورة بنت عبدالرحمن | تشييد | ذات اولوية عالية | 3475122 | 173756.1 | 3433903.42 | 3433903.42 | 1010366443 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-10-27 | 2021-11-20 | 2021-11-22 | 2021-11-22 | 2021-11-20 |  | لا يوجد تأخير |  | 46.7164 | 24.8493 | منجز | No
2100033180 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 22023829 | 1101191.45 | 10881693.085 | 0 | 1116001737 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2011-02-19 | 2013-02-08 | 2019-10-15 | 2019-10-15 | 2013-02-08 |  | ضعف كفاءة المقاول الفنية |  | 46.6761 | 24.7013 | منجز | Yes
2100029956 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 5261218 | 263060.9 | 1171014.585 | 0 | 1116001737 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-08-09 | 2017-01-30 | 2020-04-10 | 2020-04-10 | 2017-01-30 |  | ضعف كفاءة المقاول الفنية |  | 46.6576 | 24.7194 | منجز | Yes
2100064691 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 5828525 | 291426.25 | 5091417 | 0 | 1118000832 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 89 | 100 | 2011-02-13 | 2012-05-08 | 2012-05-08 | 2012-05-08 |  |  | ضعف كفاءة المقاول الفنية |  | 42.9287 | 23.8962 | مسحوب | Yes
2100045673 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2990802 | 149540.1 | 2118088.25 | 0 | 1010225108 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 82 | 100 | 2013-08-31 | 2015-06-22 | 2020-01-05 | 2020-01-05 | 2015-06-22 |  | ضعف كفاءة المقاول الفنية |  | 46.6878 | 24.7269 | منجز | Yes
2100070722 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1061775710 | 53088785.5 | 851544119.42 | 851544119.42 | 1010202928 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 80 | 100 | 2013-04-05 | 2016-04-04 | 2019-11-19 | 2019-11-19 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 46.7313 | 24.7651 | مسحوب | No
2100096423 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 12265795 | 613289.75 | 0 | 0 | 1010171813 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 82 | 100 | 2013-11-05 | 2015-10-26 | 2016-01-03 | 2016-01-03 | 2015-10-26 |  | ضعف كفاءة المقاول الفنية |  | 45.5072 | 23.5433 | منجز | No
2100011395 | الهيئة العامة للطيران المدني | تشييد | ذات اولوية متوسطة | 112295506.98 | 5614775.349 | 56833260 | 56833260 | 4030008021 | لا | 0 | 200909115002 | جاري | منهجية القيمة المكتسبة | 54 | 100 | 2015-02-05 | 2017-01-25 | 2023-10-30 | 2023-10-30 |  |  | ضعف كفاءة المقاول الفنية |  | 44.9222 | 20.3147 | Failed | No
2100064120 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 510600 | 25530 | 0 | 0 | 1010010466 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-01-14 | 2020-01-09 | 2019-12-31 | 2019-12-31 | 2020-01-09 |  |  |  | 45.3213 | 24.0828 | منجز | No
2100090576 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1094830 | 54741.5 | 42064 | 0 | 1116005407 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 1 | 100 | 2015-08-01 | 2016-10-24 | 2016-10-24 | 2016-10-24 |  |  | ضعف كفاءة المقاول الفنية |  | 45.6929 | 25.5844 | مسحوب | Yes
2100030262 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4193100 | 209655 | 42007 | 0 | 1010188984 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 66 | 100 | 2015-06-27 | 2016-09-19 | 2019-07-19 | 2019-07-19 |  |  | ضعف كفاءة المقاول الفنية |  | 46.663 | 24.7019 | مسحوب | Yes
2100030656 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 8918700 | 445935 | 41791 | 0 | 1185000614 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 23 | 100 | 2015-02-17 | 2017-02-06 | 2021-06-01 | 2021-06-01 |  |  | تأخرصرف المستحقات المالية |  | 44.8224 | 20.4507 | Failed | Yes
2100064573 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2846082.5 | 142304.125 | 2099303.57 | 0 | 1117002589 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-04-15 | 2019-05-31 | 2019-05-31 | 2019-05-31 | 2019-05-31 |  |  |  | 45.2948 | 24.0717 | منجز | Yes
2100080931 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 24434343.45 | 1221717.1725 | 229805 | 0 | 1010056094 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 94 | 100 | 2013-09-05 | 2016-05-06 | 2017-01-20 | 2017-01-20 | 2016-05-06 |  | ضعف كفاءة المقاول الفنية |  | 46.6946 | 24.7169 | منجز | Yes
2100014976 | هيئة تطوير بوابة الدرعية | تشييد | ذات اولوية متوسطة | 11685097 | 584254.85 | 11685097 | 11685097 | 1010401459 | لا | 0 | 200501102916 | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2020-01-03 | 2020-04-30 | 2020-04-30 | 2020-04-30 |  | 2020-04-30 |  |  | 46.5738 | 24.7369 | منجز | No
2100045780 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1474000 | 73700 | 1179937.05 | 0 | 1010418752 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 88 | 100 | 2015-07-04 | 2019-07-16 | 2019-07-16 | 2019-07-16 | 2019-07-16 |  |  |  | 46.6644 | 24.7119 | منجز | Yes
2100075213 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1881225 | 94061.25 | 1688647.5 | 0 | 1126000984 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 100 | 2018-04-22 | 2019-06-16 | 2019-06-16 | 2019-06-16 | 2019-06-16 |  | ضعف كفاءة المقاول الفنية |  | 45.4547 | 25.5763 | منجز | Yes
2100013215 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 8011955 | 400597.75 | 1404270 | 0 | 1010015152 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 76 | 100 | 2014-10-17 | 2016-10-06 | 2022-12-14 | 2022-12-14 | 2016-10-06 |  | ضعف كفاءة المقاول الفنية |  | 46.6891 | 24.7082 | منجز | Yes
2100098114 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية | 383343444.02 | 19167172.201 | 352504353.08 | 352504353.08 | 1010199246 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 98 | 100 | 2017-03-26 | 2019-03-26 | 2023-06-09 | 2023-06-09 |  |  | تأخرصرف المستحقات المالية |  | 46.6243 | 24.6834 | متأخر | No
2100003264 | وزارة الدفاع / الإدارة الهندسية والاشغال بالخدمات الصحية | تشييد | ذات اولوية متوسطة | 9401283.17 | 470064.1585 | 9401283.17 | 9401283.17 | 1010223860 | لا | 0 | 181009118514 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-12-29 | 2016-04-18 | 2021-12-31 | 2021-12-31 | 2016-04-18 |  | تأخرصرف المستحقات المالية |  | 46.684 | 24.6994 | منجز | No
2100178522 | وزارة الثقافة | ترميم | ذات اولوية عالية وعاجلة | 1994766.15 | 99738.3075 | 1052684.75 | 0 | 1010145607 | لا | 0 |  | جاري | تكلفة العمل المنجز | 25 | 100 | 2021-01-18 | 2022-01-17 | 2022-01-18 | 2022-01-18 |  |  |  |  | 46.7077 | 24.6294 | Failed | Yes
2100017651 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 18299210 | 914960.5 | 9512057.23 | 0 | 1010056094 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 90 | 100 | 2013-07-06 | 2015-06-26 | 2019-10-29 | 2019-10-29 | 2015-06-26 |  | ضعف كفاءة المقاول الفنية |  | 46.6878 | 24.7069 | منجز | Yes
2100043901 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 47857141.6 | 2392857.08 | 27825738.693 | 0 | 1116001737 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 92 | 100 | 2013-10-19 | 2015-10-09 | 2020-01-07 | 2020-01-07 | 2015-10-09 |  | ضعف كفاءة المقاول الفنية |  | 46.6679 | 24.7063 | منجز | Yes
2100045290 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 39759504 | 1987975.2 | 24244041.23 | 0 | 1010101252 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2011-03-14 | 2013-03-03 | 2019-10-04 | 2019-10-04 | 2013-03-03 |  | ضعف كفاءة المقاول الفنية |  | 46.5456 | 24.74 | منجز | Yes
2100018900 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3658703.5 | 182935.175 | 1859707.1 | 0 | 1010168999 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 94 | 51 | 2015-04-16 | 2018-01-27 | 2019-12-31 | 2019-12-31 | 2018-01-27 |  |  |  | 46.6809 | 24.7157 | منجز | Yes
2100016693 | جامعة الإمام محمد بن سعود الاسلامية | تشييد | ذات اولوية متوسطة | 39384037.84 | 1969201.892 | 39384037.84 | 39384037.84 | 1010181431 | لا | 0 | 180809052712 | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2014-04-30 | 2016-04-08 | 2017-11-19 | 2017-11-19 | 2016-04-08 |  | لا يوجد تأخير |  | 47.3608 | 24.1724 | منجز | No
2100013075 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 219999200 | 10999960 | 190309022.28 | 190309022.28 | 1010092796 | لا | 0 | 200409084509 | منجز – استلام نهائي | الكميات التي تم تركيبها | 0.9 | 0.94 | 2014-03-06 | 2019-04-27 | 2020-04-28 | 2020-04-28 | 2019-04-27 | 2021-11-15 |  |  | 46.68 | 24.7107 | منجز | No
2100092665 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 8389032 | 419451.6 | 0 | 0 | 1010171813 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 25 | 76 | 2019-10-22 | 2021-10-08 | 2022-05-10 | 2022-05-10 |  |  |  |  | 43.7405 | 24.2958 | Failed | No
2100029164 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2148950 | 107447.5 | 1728094 | 1728094 | 1010168999 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-02-18 | 2014-08-12 | 2019-11-16 | 2019-11-16 | 2014-08-12 |  | ضعف كفاءة المقاول الفنية |  | 46.6981 | 24.7038 | منجز | No
2100046966 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4833486 | 241674.3 | 1610044 | 0 | 1010129381 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 90 | 50 | 2019-06-16 | 2020-06-11 | 2020-06-11 | 2020-06-11 | 2020-06-11 |  |  |  | 46.5269 | 23.6205 | منجز | Yes
2100026574 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 797850 | 39892.5 | 42094 | 0 | 1186001580 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 37 | 100 | 2015-08-02 | 2016-07-17 | 2016-07-16 | 2016-07-16 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6672 | 24.7057 | مسحوب | Yes
2100026364 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 5493755 | 274687.75 | 41632 | 0 | 1116007586 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 0 | 100 | 2015-04-20 | 2016-12-10 | 2016-12-10 | 2016-12-10 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 46.6713 | 24.7044 | Failed | Yes
2100030435 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3600000 | 180000 | 41196 | 0.01 | 1010154770 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 19 | 30 | 2019-05-17 | 2020-05-18 | 2020-05-18 | 2020-05-18 |  |  |  |  | 46.2732 | 24.4714 | Failed | No
2100026294 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4574952.5 | 228747.625 | 4574952.5 | 0 | 1114000037 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2013-12-29 | 2016-03-27 | 2016-03-27 | 2016-03-27 | 2016-03-27 |  |  |  | 46.6699 | 24.7069 | منجز | Yes
2100029190 | أمانة / الرياض | تشييد | ذات اولوية عالية | 28995100 | 1449755 | 6481736 | 0 | 1011012161 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 83 | 100 | 2019-01-02 | 2020-12-22 | 2022-05-24 | 2022-05-24 |  |  |  |  | 46.6682 | 24.7172 | Failed | Yes
2100046933 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3761500 | 188075 | 0 | 0 | 1010160688 | لا | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 1 | 1 | 2019-03-24 | 2021-03-13 | 2021-03-13 | 2021-03-13 |  |  | اخرى |  | 46.6672 | 24.7069 | Failed | No
2100029971 | أمانة / الرياض | تشييد | ذات اولوية عالية | 3483460 | 174173 | 41888 | 0 | 1010019983 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-02-23 | 2016-08-16 | 2019-11-14 | 2019-11-14 | 2016-08-16 |  | ضعف كفاءة المقاول الفنية |  | 47.164 | 25.5612 | منجز | Yes
2100031301 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2609937 | 130496.85 | 2348817.12 | 0 | 1010031436 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-01-09 | 2020-07-02 | 2020-07-02 | 2020-07-02 | 2020-07-02 |  |  |  | 46.6706 | 24.6963 | منجز | Yes
2100030914 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3416700 | 170835 | 0 | 0 | 1010158786 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 36 | 2019-06-13 | 2021-05-27 | 2021-05-21 | 2021-05-21 | 2021-05-27 |  |  |  | 46.6809 | 24.7206 | منجز | No
2100030796 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3464874 | 173243.7 | 41902 | 0 | 1116008805 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 84 | 100 | 2015-02-17 | 2016-05-12 | 2020-01-21 | 2020-01-21 | 2016-05-12 |  | ضعف كفاءة المقاول الفنية |  | 46.7056 | 24.7244 | منجز | Yes
2100029934 | أمانة / الرياض | تشييد | ذات اولوية عالية | 9754350 | 487717.5 | 41934 | 0 | 4031044308 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 4 | 100 | 2015-05-10 | 2017-04-29 | 2017-04-29 | 2017-04-29 |  |  | ضعف كفاءة المقاول الفنية |  | 44.4093 | 24.5244 | Failed | Yes
2100030026 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3566158 | 178307.9 | 3048600 | 0 | 1010127437 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-08-18 | 2017-02-08 | 2020-11-24 | 2020-11-24 | 2017-02-08 |  | ضعف كفاءة المقاول الفنية |  | 46.672 | 24.705 | منجز | Yes
2100032686 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4041585 | 202079.25 | 400000 | 0 | 1010290949 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 9 | 100 | 2015-10-13 | 2017-11-01 | 2021-06-30 | 2021-06-30 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6775 | 24.7025 | مسحوب | Yes
2100033154 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 13373500 | 668675 | 6824375 | 0 | 1010108475 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 23 | 100 | 2014-08-21 | 2016-08-10 | 2016-08-10 | 2016-08-10 | 2016-08-10 |  | ضعف كفاءة المقاول الفنية |  | 46.6809 | 24.7131 | منجز | Yes
2100031242 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 395518.86 | 19775.943 | 0 | 0 | 1112000174 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 97 | 100 | 2019-05-23 | 2020-11-09 | 2020-11-09 | 2020-11-09 | 2020-11-09 | 2023-01-17 |  |  | 45.2595 | 24.6151 | منجز | No
2100033165 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 24830243 | 1241512.15 | 17408866.36 | 0 | 1010154882 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 85 | 100 | 2014-05-07 | 2015-07-31 | 2019-10-23 | 2019-10-23 | 2015-07-31 |  | ضعف كفاءة المقاول الفنية |  | 46.6885 | 24.71 | منجز | Yes
2100044225 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 18537195 | 926859.75 | 16177200 | 0 | 1010101252 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-06-03 | 2018-11-30 | 2020-05-22 | 2020-05-22 | 2018-11-30 |  | ضعف كفاءة المقاول الفنية |  | 46.6891 | 24.7194 | منجز | Yes
2100032944 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3085000 | 154250 | 40097 | 0 | 1115001461 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 85 | 100 | 2010-06-22 | 2016-08-07 | 2021-06-21 | 2021-06-21 | 2016-08-07 |  |  |  | 45.8877 | 25.2433 | منجز | Yes
2100032325 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2442000 | 122100 | 0 | 0 | 1010194943 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-03-15 | 2016-10-25 | 2016-10-24 | 2016-10-24 | 2016-10-25 |  |  |  | 46.6782 | 24.7069 | منجز | No
2100034230 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1967960 | 98398 | 1296740 | 0 | 1113002421 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 90 | 100 | 2015-02-15 | 2016-05-10 | 2019-12-30 | 2019-12-30 | 2016-05-10 |  | ضعف كفاءة المقاول الفنية |  | 46.6837 | 24.7107 | منجز | Yes
2100030973 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2201140 | 110057 | 1887330 | 0 | 1010009217 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 86 | 100 | 2015-01-16 | 2016-04-09 | 2016-04-09 | 2016-04-09 | 2016-04-09 |  |  |  | 45.7172 | 25.5945 | منجز | Yes
2100044306 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 6165250 | 308262.5 | 41815 | 0 | 1010015152 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 76 | 100 | 2014-12-24 | 2016-06-16 | 2019-09-18 | 2019-09-18 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6802 | 24.7088 | Failed | Yes
2100033331 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4468300 | 223415 | 4244846.5 | 0 | 1017000207 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 100 | 2014-05-27 | 2015-11-18 | 2019-09-14 | 2019-09-14 | 2015-11-18 |  | ضعف كفاءة المقاول الفنية |  | 46.6939 | 24.71 | منجز | Yes
2100047342 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1887450 | 94372.5 | 363364.67 | 0 | 1118002055 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 25 | 100 | 2014-02-22 | 2015-05-18 | 2018-11-28 | 2018-11-28 |  |  | ضعف كفاءة المقاول الفنية |  | 43.2802 | 24.3432 | مسحوب | Yes
2100046023 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 11768920 | 588446 | 9057823.08 | 0 | 1010015152 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2012-05-27 | 2014-05-17 | 2022-11-23 | 2022-11-23 | 2014-05-17 |  |  |  | 46.6857 | 24.6838 | منجز | Yes
2100063630 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3850150 | 192507.5 | 42106 | 0 | 1010056094 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 60 | 100 | 2015-10-14 | 2017-04-06 | 2020-03-06 | 2020-03-06 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6775 | 24.6976 | Failed | Yes
2100045916 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3833250 | 191662.5 | 751357 | 0 | 1010171813 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 94.99 | 100 | 2015-04-14 | 2017-04-03 | 2021-06-11 | 2021-06-11 | 2017-04-03 |  | ضعف كفاءة المقاول الفنية |  | 46.0969 | 25.117 | منجز | Yes
2100043886 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 31753450 | 1587672.5 | 27690479.1 | 0 | 1010056094 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 94 | 100 | 2013-09-04 | 2015-08-25 | 2019-11-13 | 2019-11-13 | 2015-08-25 |  | ضعف كفاءة المقاول الفنية |  | 46.6706 | 24.7088 | منجز | Yes
2100031054 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3869175 | 193458.75 | 3000923.47 | 0 | 1116005202 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 78 | 100 | 2015-06-14 | 2016-06-08 | 2019-09-22 | 2019-09-22 | 2016-06-08 |  | ضعف كفاءة المقاول الفنية |  | 46.6686 | 24.7032 | منجز | Yes
2100045905 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 21796851.8 | 1089842.59 | 19177447.8 | 0 | 1012001538 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 100 | 2015-04-07 | 2017-03-27 | 2021-04-11 | 2021-04-11 | 2017-03-27 |  | ضعف كفاءة المقاول الفنية |  | 47.3135 | 24.1587 | منجز | Yes
2100033191 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 899999 | 44999.95 | 41995 | 0 | 1010076344 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 86 | 100 | 2015-08-11 | 2016-07-26 | 2016-07-25 | 2016-07-25 | 2016-07-26 |  | ضعف كفاءة المقاول الفنية |  | 46.6754 | 24.7131 | منجز | Yes
2100065962 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1016077.25 | 50803.8625 | 606991 | 0 | 1017000694 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 41 | 95 | 2015-07-29 | 2016-10-21 | 2019-07-06 | 2019-07-06 |  |  | ضعف كفاءة المقاول الفنية |  | 45.584 | 20.4612 | Failed | Yes
2100070560 | هيئة تطوير بوابة الدرعية | تشييد | ذات اولوية عالية | 88293472 | 4414673.6 | 86275424.12 | 86275424.12 | 1010135922 | لا | 0 | 200509098094 | جاري | اخرى | 100 | 100 | 2019-07-07 | 2021-03-23 | 2021-03-05 | 2021-03-05 |  |  |  |  | 46.5903 | 24.7291 | Failed | No
2100047364 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 6597207 | 329860.35 | 41722 | 0 | 1010157240 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 26 | 100 | 2015-05-20 | 2017-05-09 | 2016-05-09 | 2016-05-09 |  |  | ضعف كفاءة المقاول الفنية |  | 46.5148 | 23.6178 | مسحوب | Yes
2100075110 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2452000 | 122600 | 1427944 | 0 | 1010108475 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 73 | 2018-01-21 | 2020-01-11 | 2020-01-11 | 2020-01-11 | 2020-01-11 |  |  |  | 44.8284 | 26.295 | منجز | Yes
2100063523 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 8999990 | 449999.5 | 8219552 | 0 | 1010056094 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-03-29 | 2015-03-19 | 2019-10-10 | 2019-10-10 | 2015-03-19 |  | ضعف كفاءة المقاول الفنية |  | 46.6843 | 24.715 | منجز | Yes
2100063350 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 5554500 | 277725 | 3838965 | 0 | 1010010305 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-10-13 | 2016-02-05 | 2019-09-26 | 2019-09-26 | 2016-02-05 |  | ضعف كفاءة المقاول الفنية |  | 46.6816 | 24.7038 | منجز | Yes
2100065225 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3783375 | 189168.75 | 3305200 | 0 | 3350018863 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-10-14 | 2017-01-06 | 2022-12-22 | 2022-12-22 | 2017-01-06 |  | ضعف كفاءة المقاول الفنية |  | 43.6981 | 24.6724 | منجز | Yes
2100063011 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3878305.2 | 193915.26 | 595069.3 | 0 | 1010279126 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 30 | 21 | 2019-02-24 | 2020-10-16 | 2020-10-17 | 2020-10-17 |  |  |  |  | 46.6802 | 24.6976 | مسحوب | Yes
2100065041 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2848760 | 142438 | 2118177.65 | 0 | 1010272521 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-10-06 | 2017-07-22 | 2019-12-19 | 2019-12-19 | 2017-07-22 |  | تأخرصرف المستحقات المالية |  | 46.6891 | 24.7107 | منجز | Yes
2100047880 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1139900 | 56995 | 0 | 0 | 1010019983 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-10-12 | 2019-11-13 | 2019-11-15 | 2019-11-15 | 2019-11-13 |  |  |  | 47.1593 | 25.5602 | منجز | No
2100083683 | وزارة الدفاع / الإدارة الهندسية والاشغال بالخدمات الصحية | تشييد | ذات اولوية عالية | 44429784 | 2221489.2 | 38776473.75 | 38776473.75 | 1010146750 | لا | 0 | 180801062073 | جاري | الكميات التي تم تركيبها | 85 | 87 | 2018-10-01 | 2020-10-01 | 2022-10-01 | 2022-10-01 |  |  |  |  | 46.6827 | 24.6957 | متأخر | No
2100039476 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 19355000 | 967750 | 5212882.24 | 5212882.24 | 1116000094 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 27 | 100 | 2011-03-11 | 2013-02-16 | 2016-12-22 | 2016-12-22 |  |  | ضعف كفاءة المقاول الفنية |  | 46.8398 | 24.6603 | مسحوب | No
2100065586 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 6994700 | 349735 | 919006.39 | 0 | 1010203405 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2011-03-29 | 2019-03-23 | 2019-03-23 | 2019-03-23 | 2019-03-23 |  | ضعف كفاءة المقاول الفنية |  | 45.2807 | 24.0663 | منجز | Yes
2100083016 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 688850 | 34442.5 | 41995 | 0 | 1116006456 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 28 | 100 | 2015-05-02 | 2016-04-16 | 2016-04-16 | 2016-04-16 |  |  | ضعف كفاءة المقاول الفنية |  | 44.6415 | 23.8995 | مسحوب | Yes
2100080393 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 5966020 | 298301 | 39971 | 0 | 1122001367 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 82 | 100 | 2010-05-28 | 2011-11-19 | 2012-08-09 | 2012-08-09 | 2011-11-19 |  | ضعف كفاءة المقاول الفنية |  | 46.6992 | 24.6728 | منجز | Yes
2100063103 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3426264 | 171313.2 | 2911369 | 0 | 1010318776 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-03-04 | 2016-06-26 | 2016-06-26 | 2016-06-26 | 2016-06-26 |  | ضعف كفاءة المقاول الفنية |  | 46.6754 | 24.6994 | منجز | Yes
2100080905 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3250000 | 162500 | 3250000 | 0 | 1113001362 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-10-12 | 2016-04-04 | 2020-01-19 | 2020-01-19 | 2016-04-04 |  |  |  | 46.6754 | 24.7082 | منجز | Yes
2100080695 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2435150 | 121757.5 | 1718359.9 | 0 | 1010010466 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-08-26 | 2015-10-20 | 2019-08-24 | 2019-08-24 | 2015-10-20 |  | ضعف كفاءة المقاول الفنية |  | 45.2754 | 24.0676 | منجز | Yes
2100074944 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 11397813 | 569890.65 | 5404219.96 | 0 | 1010164501 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 92 | 100 | 2014-10-22 | 2016-04-14 | 2021-07-04 | 2021-07-04 | 2016-04-14 |  | ضعف كفاءة المقاول الفنية |  | 46.6704 | 24.6765 | منجز | Yes
2100075250 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1935150 | 96757.5 | 0 | 0 | 1113000448 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 33 | 100 | 2019-04-27 | 2022-01-19 | 2023-08-27 | 2023-08-27 |  |  |  |  | 46.6912 | 24.7013 | Failed | No
2100091313 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 8465520.76 | 423276.038 | 2091979.368 | 0 | 1114000037 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 43 | 100 | 2014-08-03 | 2016-03-25 | 2016-11-25 | 2016-11-25 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6521 | 24.7119 | مسحوب | Yes
2100058295 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 989248 | 49462.4 | 41779 | 0 | 1015001443 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 90 | 100 | 2014-08-20 | 2016-02-11 | 2016-05-22 | 2016-05-22 | 2016-02-11 |  |  |  | 46.1028 | 22.9718 | منجز | Yes
2100008245 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 201600 | 10080 | 201600 | 0 | 1010258205 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-08-15 | 2018-12-11 | 2021-06-14 | 2021-06-14 | 2018-12-11 |  |  |  | 46.7022 | 24.72 | منجز | Yes
2100062602 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1285000 | 64250 | 42141 | 0 | 1113001088 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 0 | 100 | 2015-12-13 | 2016-12-07 | 2021-07-04 | 2021-07-04 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 46.1406 | 24.6322 | Failed | Yes
2100099632 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 21793240 | 1089662 | 3725905.27 | 0 | 1010193266 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 96 | 100 | 2014-09-22 | 2016-09-11 | 2019-09-22 | 2019-09-22 | 2016-09-11 |  | ضعف كفاءة المقاول الفنية |  | 47.231 | 24.1724 | منجز | Yes
2100091243 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1999953.6 | 99997.68 | 42066 | 0 | 1010263223 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 0 | 1 | 2015-07-25 | 2017-01-15 | 2018-01-16 | 2018-01-16 |  |  | تأخرصرف المستحقات المالية |  | 46.5099 | 24.8117 | مسحوب | Yes
2100081664 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3700000 | 185000 | 41890 | 0 | 1124000200 | لا | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 9 | 100 | 2015-02-18 | 2017-02-07 | 2021-07-16 | 2021-07-16 |  |  | تأخرصرف المستحقات المالية |  | 46.6823 | 24.7119 | Failed | Yes
2100081421 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 899820 | 44991 | 41752 | 0 | 1116002296 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 33 | 100 | 2014-10-21 | 2018-12-26 | 2018-12-26 | 2018-12-26 |  |  | ضعف كفاءة المقاول الفنية |  | 45.4626 | 25.0648 | مسحوب | Yes
2100031415 | أمانة / الرياض | تشييد | ذات اولوية عالية | 1907690 | 95384.5 | 0 | 0 | 1010056094 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 50 | 1 | 2015-08-06 | 2017-07-26 | 2019-10-12 | 2019-10-12 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7936 | 23.412 | Failed | No
2100090731 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3661100 | 183055 | 42103 | 0 | 1113000219 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 16 | 100 | 2015-12-16 | 2017-06-08 | 2023-01-19 | 2023-01-19 |  |  | تأخرصرف المستحقات المالية |  | 45.249 | 25.2337 | Failed | Yes
2100091560 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2946370 | 147318.5 | 39971 | 0 | 1013000078 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 82 | 100 | 2010-05-29 | 2019-01-15 | 2019-01-15 | 2019-01-15 | 2019-01-15 |  | ضعف كفاءة المقاول الفنية |  | 46.506 | 23.619 | منجز | Yes
2100107085 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات الجوية | تشييد | ذات اولوية عالية | 4936603 | 246830.15 | 3578564.5 | 3578564.5 | 1011008354 | لا | 0 | 190401013292 | جاري | الكميات التي تم تركيبها | 80 | 100 | 2018-08-19 | 2019-08-08 | 2022-10-31 | 2022-10-31 |  |  | ضعف كفاءة المقاول الفنية |  | 47.3255 | 24.1429 | Failed | No
2100031872 | الرئاسة العامة للبحوث العلمية والإفتاء | تشييد | ذات اولوية عالية وعاجلة | 47696716.24 | 2384835.812 | 12488032.05 | 12488032.05 | 1010087411 | لا | 0 |  | مسحوب | اخرى | 28 | 100 | 2012-09-02 | 2014-08-11 | 2015-02-04 | 2015-02-04 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7041 | 24.616 | مسحوب | No
2100065973 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1016077.25 | 50803.8625 | 606991 | 0 | 1017000694 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 40 | 95 | 2015-07-29 | 2016-10-21 | 2022-11-08 | 2022-11-08 |  |  | ضعف كفاءة المقاول الفنية |  | 45.583 | 20.4571 | Failed | Yes
2100100645 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3492722 | 174636.1 | 3492722 | 0 | 1010252537 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-10-19 | 2016-10-08 | 2018-04-07 | 2018-04-07 | 2016-10-08 |  |  |  | 46.6823 | 24.7094 | منجز | Yes
2100100601 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 11634280 | 581714 | 11203140.8845 | 0 | 1010010466 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-08-02 | 2016-07-22 | 2019-09-13 | 2019-09-13 | 2016-07-22 |  | ضعف كفاءة المقاول الفنية |  | 44.7893 | 23.7618 | منجز | Yes
2100038544 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 126445181 | 6322259.05 | 107333456 | 105573448 | 1116001737 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 92.1 | 100 | 2013-07-06 | 2020-10-31 | 2022-09-30 | 2022-09-30 |  |  |  |  | 46.6892 | 24.7116 | متأخر | No
2100074163 | وزارة المالية | إشراف | ذات اولوية عالية | 13046506.2 | 652325.31 | 9509680.21 | 9509680.21 | 4030216250 | لا | 0 | 190501003886 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 98 | 100 | 2019-07-04 | 2021-12-06 | 2022-08-18 | 2022-08-18 | 2021-12-06 |  | لا يوجد تأخير |  | 46.7181 | 24.6528 | منجز | No
2100189755 | وزارة الاعلام | تحديث وتوريد | ذات اولوية عالية وعاجلة | 64510245 | 3225512.25 | 57621052 | 57621052 | 1010171914 | لا | 0 |  | منجز – استلام نهائي | تكلفة العمل المنجز | 90 | 100 | 2013-12-25 | 2018-06-03 | 2021-12-31 | 2021-12-31 |  | 2018-06-03 |  |  | 46.6981 | 24.6826 | منجز | No
2100091173 | شركة المياه الوطنية | دراسات هندسية | ذات اولوية عالية | 45000000 | 2250000 | 19589169 | 10819530 | 1010945566 | لا | 10819530 |  | مسحوب | تكلفة العمل المنجز | 51.31 | 100 | 2017-10-18 | 2020-10-17 | 2020-10-17 | 2020-10-17 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6759 | 24.7056 | مسحوب | No
2100064551 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 8787535 | 439376.75 | 41736 | 0 | 1010178884 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 20 | 100 | 2014-11-06 | 2016-10-26 | 2016-10-25 | 2016-10-25 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6672 | 24.7107 | مسحوب | Yes
2100073404 | وزارة الداخلية / المديرية العامة للدفاع المدني | تشييد | ذات اولوية عالية | 6354212 | 317710.6 | 6354212 | 6354212 | 1010231492 | لا | 0 | 180701025606 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-10-19 | 2020-05-31 | 2022-07-01 | 2022-07-01 | 2020-05-31 |  | تأخرصرف المستحقات المالية |  | 46.6611 | 24.5413 | منجز | No
2100053454 | صندوق تنمية الموارد البشرية | تشييد | ذات اولوية منخفضة | 31233165.66 | 1561658.283 | 23616484.17 | 23616484.17 | 1010094008 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 94.15 | 100 | 2015-12-27 | 2017-12-13 | 2022-06-30 | 2022-06-30 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 47.3241 | 24.1571 | مسحوب | No
2100083510 | وزارة الدفاع / الإدارة الهندسية والاشغال بالخدمات الصحية | تشييد | ذات اولوية متوسطة | 18375714 | 918785.7 | 12216414 | 5215350 | 5855027944 | لا | 0 | 190401098689 | جاري | الكميات التي تم تركيبها | 75 | 85 | 2018-12-20 | 2020-12-11 | 2023-12-11 | 2023-12-11 |  |  |  |  | 46.68 | 24.6957 | متأخر | No
2100190584 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 18098115 | 904905.75 | 16258302.99 | 15086883.84 | 1010149483 | نعم | 192267482 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99.35 | 100 | 2020-08-17 | 2021-10-17 | 2021-10-27 | 2021-10-27 | 2021-10-17 |  |  |  | 46.7948 | 24.6526 | منجز | No
2100021766 | شركة المياه الوطنية / منطقة الرياض | إشراف | ذات اولوية عالية | 4640000 | 232000 | 4618973 | 4618973 | 4031072810 | لا | 0 | 180809056665 | منجز – استلام نهائي | تكلفة العمل المنجز | 99.55 | 100 | 2014-10-25 | 2017-10-25 | 2018-11-03 | 2018-11-03 |  | 2017-10-25 | لا يوجد تأخير |  | 46.1487 | 24.5941 | منجز | No
2100191590 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 4619972.5 | 230998.625 | 4539754.2 | 4539754.2 | 1010311911 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 98.26 | 100 | 2020-04-08 | 2020-12-08 | 2021-01-05 | 2021-01-05 |  | 2020-12-08 |  |  | 46.6146 | 24.6935 | منجز | No
2100191715 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 5125210.4 | 256260.52 | 4973298.91 | 4438251.71 | 1010249593 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 98.51 | 100 | 2020-03-03 | 2020-12-03 | 2020-12-02 | 2020-12-02 | 2020-12-03 |  |  |  | 46.6679 | 24.675 | منجز | No
2100054250 | شركة الكهرباء | تشييد | ذات اولوية متوسطة | 74716771 | 3735838.55 | 62082490 | 62082490 | 7001445233 | لا | 0 |  | جاري | تكلفة العمل المنجز | 84.8 | 100 | 2016-02-07 | 2020-02-13 | 2023-03-30 | 2023-03-30 |  |  | اخرى |  | 46.3887 | 24.8982 | متأخر | No
2100012600 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 191305728.42 | 9565286.421 | 61113399.41 | 61113399.41 | 1010015350 | لا | 0 | 180909090105 | مسحوب | الكميات التي تم تركيبها | 39 | 100 | 2014-01-28 | 2017-06-04 | 2017-05-04 | 2017-05-04 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6773 | 24.7069 | مسحوب | No
2100064455 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 5202540 | 260127 | 2219383.56 | 0 | 1114000037 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-02-24 | 2015-08-18 | 2019-05-11 | 2019-05-11 | 2015-08-18 |  | ضعف كفاءة المقاول الفنية |  | 46.683 | 24.6976 | منجز | Yes
2100061143 | الهيئة الملكية لمدينة الرياض | تشييد | ذات اولوية عالية | 1260039203.19 | 63001960.1595 | 1195845429 | 1195845429 | 1010006315 | لا | 0 | 190109010663 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2017-03-01 | 2019-02-06 | 2021-02-26 | 2021-02-26 | 2019-02-06 |  |  |  | 46.7251 | 24.6844 | منجز | No
2100178533 | وزارة الثقافة | تصميم وتشييد | ذات اولوية عالية | 17500000 | 875000 | 16018500 | 16018500 | 1010074797 | لا | 0 | 201101427533 | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2020-07-28 | 2021-02-28 | 2021-06-30 | 2021-06-30 |  | 2021-02-28 |  |  | 46.6786 | 24.6969 | منجز | No
2100013322 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1714990 | 85749.5 | 41902 | 0 | 1116004922 | لا | 0 | 1040208 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 92 | 100 | 2015-01-13 | 2016-04-07 | 2020-04-07 | 2020-04-07 | 2016-04-07 |  | ضعف كفاءة المقاول الفنية |  | 46.663 | 24.7069 | منجز | Yes
2100010006 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 17448190 | 872409.5 | 3624000 | 36240 | 1011012161 | لا | 0 |  | جاري | تكلفة العمل المنجز | 91 | 100 | 2018-11-17 | 2019-11-12 | 2021-08-21 | 2021-08-21 |  |  |  |  | 46.6782 | 24.7025 | Failed | No
2100064245 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1292800 | 64640 | 42079 | 0 | 1117002589 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 80 | 100 | 2015-09-05 | 2017-08-25 | 2020-01-08 | 2020-01-08 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 45.5093 | 23.5415 | Failed | Yes
2100064680 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4942825 | 247141.25 | 3074900 | 0 | 1113000219 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-08-02 | 2015-09-26 | 2019-12-05 | 2019-12-05 | 2015-09-26 |  | ضعف كفاءة المقاول الفنية |  | 45.2588 | 25.2371 | منجز | Yes
2100029396 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 13106050 | 655302.5 | 40840 | 0 | 1010030427 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 59 | 100 | 2013-04-04 | 2015-03-10 | 2021-06-21 | 2021-06-21 |  |  | ضعف كفاءة المقاول الفنية |  | 47.3447 | 24.1743 | مسحوب | Yes
2100029842 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3919035 | 195951.75 | 3447905 | 0 | 1111000356 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 88 | 100 | 2013-11-16 | 2015-05-10 | 2015-12-04 | 2015-12-04 | 2015-05-10 |  |  |  | 46.6699 | 24.7169 | منجز | Yes
2100009612 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 10995000 | 549750 | 41545 | 0 | 1124000200 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-10-01 | 2016-09-20 | 2021-06-14 | 2021-06-14 | 2016-09-20 |  | ضعف كفاءة المقاول الفنية |  | 47.1556 | 23.9748 | منجز | Yes
2100100715 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 850780 | 42539 | 0 | 0 | 1111000356 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2013-12-26 | 2014-12-11 | 2014-12-11 | 2014-12-11 | 2014-12-11 |  | ضعف كفاءة المقاول الفنية |  | 46.6837 | 24.7019 | منجز | No
2100076064 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 10996700 | 549835 | 0 | 0 | 1010226183 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 75 | 100 | 2019-05-04 | 2021-04-23 | 2022-10-30 | 2022-10-30 |  |  |  |  | 47.1697 | 25.5565 | Failed | No
2100033983 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1713250 | 85662.5 | 42103 | 0 | 1113000601 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 0 | 100 | 2015-09-30 | 2017-01-22 | 2020-12-09 | 2020-12-09 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 45.2525 | 25.2476 | Failed | Yes
2100029201 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4024010 | 201200.5 | 41701 | 0 | 1010258205 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 83 | 100 | 2014-10-26 | 2016-02-18 | 2020-11-07 | 2020-11-07 | 2016-02-18 |  | ضعف كفاءة المقاول الفنية |  | 46.6782 | 24.7119 | منجز | Yes
2100017990 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2427840 | 121392 | 0 | 0 | 1010290949 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 8 | 100 | 2015-04-25 | 2016-07-18 | 2016-07-18 | 2016-07-18 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6974 | 24.7069 | مسحوب | No
2100031275 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1246458 | 62322.9 | 1057880.67 | 0 | 1113000490 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2013-09-10 | 2014-12-04 | 2019-10-28 | 2019-10-28 | 2014-12-04 |  |  |  | 46.685 | 24.7057 | منجز | Yes
2100008691 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1162885 | 58144.25 | 854925 | 0 | 1111000356 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 87 | 100 | 2014-05-14 | 2015-05-09 | 2015-05-09 | 2015-05-09 | 2015-05-09 |  | ضعف كفاءة المقاول الفنية |  | 46.1431 | 24.6002 | منجز | Yes
2100057886 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 494700 | 24735 | 43177 | 0 | 1010258205 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 92 | 100 | 2018-09-15 | 2019-02-12 | 2019-08-31 | 2019-08-31 | 2019-02-12 |  | ضعف كفاءة المقاول الفنية |  | 45.253 | 25.2467 | منجز | Yes
2100043934 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 949050 | 47452.5 | 854144 | 0 | 1185000614 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-11-24 | 2015-09-20 | 2021-11-26 | 2021-11-26 | 2015-09-20 |  | ضعف كفاءة المقاول الفنية |  | 45.5846 | 20.4651 | منجز | Yes
2100045275 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 14988366 | 749418.3 | 11869273.45 | 0 | 1010255485 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 90 | 100 | 2013-11-06 | 2015-10-27 | 2015-10-27 | 2015-10-27 | 2015-10-27 |  | ضعف كفاءة المقاول الفنية |  | 44.8347 | 26.3069 | منجز | Yes
2100044870 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1149000 | 57450 | 42101 | 0 | 1187001520 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 80 | 100 | 2015-08-10 | 2016-11-02 | 2017-01-28 | 2017-01-28 | 2016-11-02 |  | ضعف كفاءة المقاول الفنية |  | 46.6713 | 24.7131 | منجز | Yes
2100031485 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1300000 | 65000 | 42101 | 0 | 1116002385 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 1 | 100 | 2015-07-05 | 2016-12-26 | 2016-12-26 | 2016-12-26 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 46.6727 | 24.7044 | مسحوب | Yes
2100080290 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1511685 | 75584.25 | 829740 | 0 | 1010258205 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-11-03 | 2019-10-29 | 2019-10-29 | 2019-10-29 | 2019-10-29 |  |  |  | 46.8728 | 23.4919 | منجز | Yes
2100076123 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1590300 | 79515 | 1362744.32 | 0 | 1010299555 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 86 | 100 | 2015-09-12 | 2016-12-05 | 2019-03-01 | 2019-03-01 | 2016-12-05 |  |  |  | 45.5133 | 25.6209 | منجز | Yes
2100090812 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2129220 | 106461 | 2129220 | 0 | 1113001886 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-11-07 | 2018-06-25 | 2018-06-25 | 2018-06-25 | 2018-06-25 |  |  |  | 46.6761 | 24.705 | منجز | Yes
2100074815 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1421375 | 71068.75 | 43349 | 0 | 1010258205 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-09-15 | 2018-12-07 | 2018-12-07 | 2018-12-07 | 2018-12-07 |  |  |  | 45.2531 | 25.2443 | منجز | Yes
2100046082 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1146150 | 57307.5 | 0 | 0 | 1010355556 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 1 | 1 | 2015-10-03 | 2016-09-17 | 2016-09-17 | 2016-09-17 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7008 | 24.7013 | مسحوب | No
2100074896 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 663840 | 33192 | 0 | 0 | 1010299555 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 31 | 2019-01-14 | 2020-04-08 | 2020-07-07 | 2020-07-07 | 2020-04-08 |  | ضعف كفاءة المقاول الفنية |  | 45.35 | 26.4966 | منجز | No
2100043864 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2021081 | 101054.05 | 41807 | 0 | 1010252432 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 32 | 100 | 2015-01-11 | 2016-04-05 | 2019-02-05 | 2019-02-05 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6727 | 24.7144 | مسحوب | Yes
2100065052 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2634250 | 131712.5 | 0 | 0 | 1010188984 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 27 | 40 | 2018-10-18 | 2020-09-18 | 2020-09-19 | 2020-09-19 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6951 | 24.6965 | Failed | No
2100028976 | أمانة / الرياض | تشييد | ذات اولوية عالية | 2593000 | 129650 | 41926 | 0 | 4031057760 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 0 | 100 | 2015-03-21 | 2016-06-13 | 2016-06-13 | 2016-06-13 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 45.4778 | 25.0632 | Failed | Yes
2100013672 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 7853790 | 392689.5 | 6283071.078 | 0 | 1010171813 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-09-22 | 2016-03-15 | 2019-11-18 | 2019-11-18 | 2016-03-15 |  | ضعف كفاءة المقاول الفنية |  | 46.6768 | 24.7119 | منجز | Yes
2100025082 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1938600 | 96930 | 1841670 | 0 | 1118003899 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 95 | 100 | 2015-10-17 | 2017-03-11 | 2017-03-11 | 2017-03-11 | 2017-03-11 |  |  |  | 46.6768 | 24.7057 | منجز | Yes
2100013005 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4112910 | 205645.5 | 3717675.78 | 0 | 1116005311 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-05-20 | 2016-08-12 | 2019-09-20 | 2019-09-20 | 2016-08-12 |  | ضعف كفاءة المقاول الفنية |  | 46.6768 | 24.7144 | منجز | Yes
2100046406 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 864460 | 43223 | 41252 | 0 | 1010291687 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 61 | 100 | 2013-05-17 | 2014-05-02 | 2019-03-24 | 2019-03-24 |  |  | ضعف كفاءة المقاول الفنية |  | 46.1054 | 25.1108 | مسحوب | Yes
2100076112 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1458060 | 72903 | 762558.44 | 0 | 4031057760 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 86 | 100 | 2014-05-04 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2023-01-17 | ضعف كفاءة المقاول الفنية |  | 45.4975 | 25.1166 | منجز | Yes
2100017183 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 14635024 | 731751.2 | 9826986.5 | 0 | 1010242793 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 92.65 | 100 | 2014-08-24 | 2016-02-15 | 2020-12-03 | 2020-12-03 | 2016-02-15 |  | ضعف كفاءة المقاول الفنية |  | 44.837 | 26.3254 | منجز | Yes
2100024275 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 19498721 | 974936.05 | 41888 | 0 | 1010043654 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-04-11 | 2017-03-31 | 2020-05-30 | 2020-05-30 | 2017-03-31 |  | ضعف كفاءة المقاول الفنية |  | 45.3869 | 25.8324 | منجز | Yes
2100017673 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 8329362 | 416468.1 | 7800890 | 0 | 1010006004 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 100 | 2014-09-28 | 2017-02-18 | 2017-02-18 | 2017-02-18 | 2017-02-18 |  |  |  | 46.685 | 24.6994 | منجز | Yes
2100026541 | أمانة / الرياض | تشييد | ذات اولوية عالية | 6573382 | 328669.1 | 6414319 | 0 | 1010252537 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 97.58 | 100 | 2014-06-03 | 2019-01-06 | 2019-01-06 | 2019-01-06 | 2019-01-06 |  |  |  | 44.7654 | 23.7642 | منجز | Yes
2100042114 | أمانة / الرياض | دراسة الجدوى | ذات اولوية متوسطة | 7992000 | 399600 | 7992000 | 0 | 1010372072 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-01-28 | 2020-01-06 | 2020-01-06 | 2020-01-06 | 2020-01-06 |  | اخرى |  | 46.6786 | 24.7065 | منجز | Yes
2100025351 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1599886 | 79994.3 | 0 | 0 | 1186002145 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 87 | 100 | 2015-07-21 | 2016-07-15 | 2022-06-20 | 2022-06-20 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6843 | 24.7028 | متأخر | No
2100013016 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1200000.77 | 60000.0385 | 0 | 0 | 1010129611 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 5 | 53 | 2018-11-17 | 2020-01-11 | 2021-06-17 | 2021-06-17 |  |  |  |  | 46.5511 | 23.6429 | مسحوب | No
2100008853 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 726330 | 36316.5 | 101387.268 | 0 | 1116007434 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 47 | 100 | 2014-08-26 | 2015-08-11 | 2015-08-11 | 2015-08-11 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6939 | 24.72 | Failed | Yes
2100012482 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3934357 | 196717.85 | 2842642.8 | 0 | 1010015152 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2013-11-24 | 2015-02-17 | 2020-02-27 | 2020-02-27 | 2015-02-17 |  | ضعف كفاءة المقاول الفنية |  | 46.6823 | 24.7044 | منجز | Yes
2100044052 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1077300 | 53865 | 1023435.28 | 0 | 1010150014 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 100 | 2015-02-11 | 2016-04-19 | 2016-04-19 | 2016-04-19 | 2016-04-19 |  |  |  | 46.674 | 24.7069 | منجز | Yes
2100038102 | هيئة تطوير بوابة الدرعية | تشييد | ذات اولوية متوسطة | 16226182 | 811309.1 | 16226182 | 16226182 | 1010079992 | لا | 0 | 200501087964 | جاري | اخرى | 100 | 100 | 2020-02-25 | 2021-05-24 | 2021-10-31 | 2021-10-31 |  |  |  |  | 46.5908 | 24.7279 | منتظم | No
2100031021 | أمانة / الرياض | تشييد | ذات اولوية عالية | 8716110 | 435805.5 | 4530393.82 | 0 | 1010177200 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 80 | 100 | 2015-04-15 | 2017-04-04 | 2020-11-17 | 2020-11-17 |  |  | ضعف كفاءة المقاول الفنية |  | 45.8992 | 24.3806 | Failed | Yes
2100026751 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 6653458 | 332672.9 | 42548 | 0 | 1010186180 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 93 | 92 | 2016-09-19 | 2019-09-22 | 2019-09-23 | 2019-09-23 | 2019-09-22 |  |  |  | 46.6882 | 24.6932 | منجز | Yes
2100031043 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 11188320 | 559416 | 41708 | 0 | 1010015734 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 5 | 100 | 2015-08-04 | 2017-07-24 | 2021-06-22 | 2021-06-22 |  |  | ضعف كفاءة المقاول الفنية |  | 46.0922 | 25.098 | مسحوب | Yes
2100017452 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2707200 | 135360 | 42859 | 0 | 1010348103 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 99 | 55 | 2017-10-30 | 2020-10-29 | 2020-10-29 | 2020-10-29 | 2020-10-29 |  |  |  | 42.9136 | 23.9021 | منجز | Yes
2100026493 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1980000 | 99000 | 42113 | 0 | 1010182773 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 5 | 100 | 2015-08-20 | 2016-08-04 | 2020-08-01 | 2020-08-01 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6939 | 24.705 | مسحوب | Yes
2100018034 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3988290 | 199414.5 | 3567840 | 0 | 1116007885 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 90 | 100 | 2015-06-20 | 2016-09-12 | 2019-10-04 | 2019-10-04 | 2016-09-12 |  | ضعف كفاءة المقاول الفنية |  | 46.674 | 24.7169 | منجز | Yes
2100031570 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1190040 | 59502 | 41995 | 0 | 1116002385 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 11 | 100 | 2015-06-03 | 2016-05-18 | 2016-05-18 | 2016-05-18 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6939 | 24.7138 | مسحوب | Yes
2100030866 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1366176 | 68308.8 | 905120 | 0 | 2051034938 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 45 | 2019-01-21 | 2021-04-10 | 2020-01-06 | 2020-01-06 | 2021-04-10 |  |  |  | 46.6706 | 24.7013 | منجز | Yes
2100028744 | أمانة / الرياض | تشييد | ذات اولوية عالية | 8258929 | 412946.45 | 458178.99 | 0 | 1116005202 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 82 | 100 | 2013-01-12 | 2015-01-02 | 2020-01-07 | 2020-01-07 | 2015-01-02 |  | ضعف كفاءة المقاول الفنية |  | 43.2738 | 24.3499 | منجز | Yes
2100034786 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2445850 | 122292.5 | 41896 | 0 | 1010240630 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 2 | 100 | 2015-01-25 | 2016-03-20 | 2020-10-10 | 2020-10-10 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6814 | 24.7215 | مسحوب | Yes
2100032793 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3993802 | 199690.1 | 3357761.9 | 0 | 1113001886 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-10-31 | 2016-04-23 | 2020-04-20 | 2020-04-20 | 2016-04-23 |  | ضعف كفاءة المقاول الفنية |  | 46.6809 | 24.7119 | منجز | Yes
2100023903 | أمانة / الرياض | تشييد | ذات اولوية عالية | 2498400 | 124920 | 2396800 | 0 | 1010209661 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 84 | 2017-11-04 | 2019-10-25 | 2019-10-26 | 2019-10-26 | 2019-10-25 |  |  |  | 46.6861 | 24.7035 | منجز | Yes
2100044435 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 786985 | 39349.25 | 786985 | 0 | 1010283691 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-06-21 | 2015-11-24 | 2015-11-24 | 2015-11-24 | 2015-11-24 |  |  |  | 45.3314 | 26.5689 | منجز | Yes
2100031124 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1601367 | 80068.35 | 1078952.5 | 0 | 1116008805 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 87 | 100 | 2015-05-30 | 2016-08-22 | 2020-05-23 | 2020-05-23 | 2016-08-22 |  | ضعف كفاءة المقاول الفنية |  | 46.6788 | 24.7063 | منجز | Yes
2100033202 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1016077.25 | 50803.8625 | 606991 | 0 | 1017000694 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 41 | 100 | 2015-07-29 | 2016-10-21 | 2021-07-04 | 2021-07-04 |  |  | ضعف كفاءة المقاول الفنية |  | 45.5708 | 20.4566 | Failed | Yes
2100031264 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 27156560 | 1357828 | 9690914.5 | 0 | 1010010466 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 80 | 100 | 2014-10-22 | 2016-10-11 | 2020-04-06 | 2020-04-06 |  |  | ضعف كفاءة المقاول الفنية |  | 45.5141 | 23.5423 | Failed | Yes
2100045636 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 799500 | 39975 | 0 | 0 | 1112000662 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 22 | 100 | 2018-02-19 | 2019-02-04 | 2019-02-04 | 2019-02-04 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6933 | 24.7069 | مسحوب | No
2100044531 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 866898 | 43344.9 | 41532 | 0 | 1010015152 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-09-21 | 2015-09-16 | 2019-12-13 | 2019-12-13 | 2015-09-16 |  | ضعف كفاءة المقاول الفنية |  | 46.6788 | 24.71 | منجز | Yes
2100043761 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2999870 | 149993.5 | 41533 | 0 | 1131041489 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 82 | 100 | 2014-05-07 | 2017-07-15 | 2017-07-15 | 2017-07-15 | 2017-07-15 |  |  |  | 46.6731 | 24.6965 | منجز | Yes
2100046104 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 12968350 | 648417.5 | 4905490 | 0 | 1010056094 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 80 | 100 | 2011-07-30 | 2013-07-19 | 2020-01-10 | 2020-01-10 | 2013-07-19 |  | ضعف كفاءة المقاول الفنية |  | 46.6775 | 24.7025 | منجز | Yes
2100044925 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 13373500 | 668675 | 6824375 | 0 | 1010108475 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-08-20 | 2016-08-09 | 2021-06-21 | 2021-06-21 | 2016-08-09 |  | ضعف كفاءة المقاول الفنية |  | 44.9579 | 26.3659 | منجز | Yes
2100033073 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 949050 | 47452.5 | 854144 | 0 | 1185000614 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-11-24 | 2015-09-20 | 2019-09-11 | 2019-09-11 | 2015-09-20 |  | ضعف كفاءة المقاول الفنية |  | 45.5956 | 20.4552 | منجز | Yes
2100012821 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2934040 | 146702 | 2934040 | 0 | 1117001926 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-07-16 | 2018-11-02 | 2018-11-02 | 2018-11-02 | 2018-11-02 |  |  |  | 46.6686 | 24.7032 | منجز | Yes
2100045684 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1454270 | 72713.5 | 195735 | 0 | 1010448883 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 26 | 2019-02-06 | 2020-07-30 | 2020-07-30 | 2020-07-30 | 2020-07-30 |  |  |  | 46.6686 | 24.7219 | منجز | Yes
2100032266 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1212300 | 60615 | 42058 | 0 | 1010300507 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-05-30 | 2016-11-20 | 2020-02-22 | 2020-02-22 | 2016-11-20 |  | تأخرصرف المستحقات المالية |  | 46.6898 | 24.71 | منجز | Yes
2100043993 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4991200 | 249560 | 41709 | 0 | 1010178884 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-09-22 | 2016-01-15 | 2021-06-30 | 2021-06-30 | 2016-01-15 |  |  |  | 46.6814 | 24.684 | منجز | Yes
2100096471 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 29537000 | 1476850 | 0 | 0 | 1010276314 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 80 | 100 | 2019-04-08 | 2022-03-23 | 2023-05-01 | 2023-05-01 |  |  |  |  | 44.8971 | 20.4417 | Failed | No
2100044321 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4921374 | 246068.7 | 2652740.4 | 0 | 1114000037 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 90 | 100 | 2014-11-15 | 2018-12-17 | 2018-12-18 | 2018-12-18 | 2018-12-17 |  | ضعف كفاءة المقاول الفنية |  | 46.6747 | 24.7075 | منجز | Yes
2100058343 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 11404412.5 | 570220.625 | 8154124.25 | 0 | 1111000356 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 97 | 100 | 2012-11-11 | 2014-11-01 | 2020-03-01 | 2020-03-01 | 2014-11-01 |  | ضعف كفاءة المقاول الفنية |  | 46.6905 | 24.7157 | منجز | Yes
2100057901 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 799500 | 39975 | 0 | 0 | 1112000662 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 22 | 100 | 2018-02-19 | 2019-02-04 | 2019-02-03 | 2019-02-03 |  |  | ضعف كفاءة المقاول الفنية |  | 44.8316 | 26.3092 | مسحوب | No
2100057842 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1016077.25 | 50803.8625 | 606991 | 0 | 1017000694 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 40 | 95 | 2015-07-29 | 2016-10-21 | 2019-07-07 | 2019-07-07 |  |  | ضعف كفاءة المقاول الفنية |  | 45.5744 | 20.4529 | Failed | Yes
2100032524 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 8733294 | 436664.7 | 0 | 0 | 1010043654 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 50 | 2019-04-24 | 2022-03-09 | 2022-03-09 | 2022-03-09 | 2022-03-09 |  |  |  | 45.7686 | 25.573 | منجز | No
2100051505 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 41068292.1 | 2053414.605 | 31652295.23 | 30699847.41 | 5950009261 | لا | 0 | 181109284919 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 98 | 100 | 2015-07-22 | 2022-04-27 | 2022-09-11 | 2022-09-11 | 2022-04-27 |  | تأخرصرف المستحقات المالية |  | 44.2617 | 17.5776 | منجز | No
2100056092 | وزارة الموارد البشرية والتنمية الإجتماعية | إشراف | ذات اولوية منخفضة | 808000 | 40400 | 1792677.5 | 1792677.5 | 1010328167 | لا | 0 | 190309005035 | مسحوب | الكميات التي تم تركيبها | 77 | 100 | 2015-04-25 | 2017-04-02 | 2022-06-16 | 2022-06-16 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 46.6236 | 24.4806 | مسحوب | No
2100076370 | الهيئة الملكية لمدينة الرياض | تشييد | ذات اولوية عالية | 137143008.63 | 6857150.4315 | 137143008.63 | 137143008.63 | 1010070634 | لا | 0 | 190109010710 | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2013-11-05 | 2015-11-05 | 2019-07-15 | 2019-07-15 | 2015-11-05 |  |  |  | 46.6242 | 24.6824 | منجز | No
2100058446 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1953815 | 97690.75 | 0 | 0 | 1010182773 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 64 | 100 | 2014-03-24 | 2015-09-15 | 2015-09-15 | 2015-09-15 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6939 | 24.7001 | مسحوب | No
2100058181 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 985000 | 49250 | 232263 | 0 | 1017001594 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 24 | 100 | 2015-08-09 | 2017-01-30 | 2017-01-31 | 2017-01-31 |  |  | ضعف كفاءة المقاول الفنية |  | 45.5783 | 20.4369 | مسحوب | Yes
2100063803 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3541170 | 177058.5 | 466936 | 0 | 1010171813 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 80 | 100 | 2015-02-17 | 2016-05-12 | 2020-09-11 | 2020-09-11 | 2016-05-12 |  | ضعف كفاءة المقاول الفنية |  | 46.6809 | 24.7044 | منجز | Yes
2100071724 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1463200 | 73160 | 0 | 0 | 1115001965 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 14 | 2019-04-17 | 2020-10-08 | 2020-10-09 | 2020-10-09 | 2020-10-08 |  |  |  | 46.6939 | 24.7025 | منجز | No
2100082224 | أمانة / نجران | تشييد | ذات اولوية عالية | 7286543 | 364327.15 | 4216600.26 | 4216600.26 | 5950007223 | لا | 0 | 200409059861 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 98 | 100 | 2019-12-15 | 2021-06-02 | 2022-09-10 | 2022-09-10 | 2021-06-02 |  |  |  | 44.2455 | 17.5136 | منجز | No
2100075014 | أمانة / الرياض | تشييد | ذات اولوية عالية | 257915911.55 | 12895795.5775 | 50034447.23 | 50034447.23 | 1010044185 | لا | 0 | 190509130984 | جاري | الكميات التي تم تركيبها | 83 | 100 | 2019-06-04 | 2021-08-09 | 2021-08-10 | 2021-08-10 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6814 | 24.7082 | Failed | No
2100064820 | أمانة / الرياض | تشييد | ذات اولوية عالية | 7203200 | 360160 | 184440.42 | 0 | 1118001076 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-06-02 | 2017-05-22 | 2020-02-05 | 2020-02-05 | 2017-05-22 |  | ضعف كفاءة المقاول الفنية |  | 42.8976 | 23.8951 | منجز | Yes
2100045894 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4387551 | 219377.55 | 41380 | 0 | 1010231660 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 81 | 100 | 2014-09-21 | 2016-03-14 | 2016-03-14 | 2016-03-14 | 2016-03-14 |  | ضعف كفاءة المقاول الفنية |  | 46.535 | 24.7422 | منجز | Yes
2100075154 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1403060 | 70153 | 875389 | 0 | 1010024386 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 72 | 100 | 2014-03-01 | 2015-04-25 | 2021-07-04 | 2021-07-04 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6731 | 24.684 | Failed | Yes
2100080474 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2886980 | 144349 | 42149 | 0 | 1122002698 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 1 | 100 | 2015-09-29 | 2016-12-22 | 2020-11-09 | 2020-11-09 |  |  | تأخرصرف المستحقات المالية |  | 45.3604 | 25.8978 | مسحوب | Yes
2100074885 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3788000 | 189400 | 41448 | 0 | 1010252537 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 56 | 100 | 2014-06-03 | 2015-05-29 | 2020-01-30 | 2020-01-30 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6429 | 24.7988 | مسحوب | Yes
2100029444 | أمانة / الرياض | تشييد | ذات اولوية عالية | 1694325 | 84716.25 | 265710 | 0 | 1010318776 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 26 | 100 | 2014-06-28 | 2015-09-21 | 2015-09-21 | 2015-09-21 |  |  | ضعف كفاءة المقاول الفنية |  | 44.4283 | 24.4962 | مسحوب | Yes
2100091221 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4994355 | 249717.75 | 795301 | 0 | 1010195827 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 15 | 15 | 2015-01-14 | 2016-04-08 | 2019-10-01 | 2019-10-01 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6775 | 24.7075 | مسحوب | Yes
2100080441 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2999550 | 149977.5 | 2154487.32 | 0 | 1116005202 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 83 | 100 | 2015-10-19 | 2017-04-11 | 2020-01-15 | 2020-01-15 | 2017-04-11 |  | ضعف كفاءة المقاول الفنية |  | 44.3017 | 24.2514 | منجز | Yes
2100080964 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 5282828 | 264141.4 | 1525820.4 | 0 | 1010056094 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 29 | 100 | 2015-10-18 | 2017-01-10 | 2020-07-03 | 2020-07-03 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6493 | 24.7069 | مسحوب | Yes
2100080426 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4192410 | 209620.5 | 856800 | 0 | 1010211585 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 99 | 100 | 2019-02-10 | 2019-08-09 | 2021-01-30 | 2021-01-30 | 2019-08-09 |  |  |  | 46.6896 | 24.694 | منجز | Yes
2100068810 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 12187200 | 609360 | 10135253.17 | 10135253.17 | 5950018186 | لا | 0 | 181209477572 | جاري | تكلفة العمل المنجز | 95.01 | 100 | 2015-10-25 | 2017-11-30 | 2023-03-31 | 2023-03-31 |  |  | أوامر تغيير |  | 44.2265 | 17.5381 | منتظم | No
2100067126 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 2988942.6 | 149447.13 | 1428620 | 1428620 | 5950010293 | لا | 0 | 210501030518 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-07-08 | 2020-12-20 | 2020-12-20 | 2020-12-20 | 2020-12-20 |  | اخرى |  | 44.3381 | 17.8038 | منجز | No
2100080975 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 18065488 | 903274.4 | 12797281 | 0 | 1010006004 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 77 | 100 | 2015-04-22 | 2017-02-10 | 2018-12-11 | 2018-12-11 |  |  | ضعف كفاءة المقاول الفنية |  | 45.2581 | 25.2276 | Failed | Yes
2100100413 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2498725 | 124936.25 | 41418 | 0 | 1010216996 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2017-02-06 | 2018-01-22 | 2019-11-04 | 2019-11-04 | 2018-01-22 |  | ضعف كفاءة المقاول الفنية |  | 46.5167 | 23.6238 | منجز | Yes
2100081432 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1807485 | 90374.25 | 354605.01 | 0 | 1116007586 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 50 | 100 | 2014-08-12 | 2016-04-03 | 2023-01-31 | 2023-01-31 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6754 | 24.7119 | مسحوب | Yes
2100081826 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2327410 | 116370.5 | 2327409.9998 | 0 | 1113000219 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-03-18 | 2016-09-08 | 2018-12-24 | 2018-12-24 | 2016-09-08 |  |  |  | 45.5239 | 25.2996 | منجز | Yes
2100090370 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1467814 | 73390.7 | 1236491.35 | 0 | 1116007006 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 84 | 100 | 2015-04-29 | 2018-09-04 | 2021-06-30 | 2021-06-30 | 2018-09-04 |  |  |  | 46.6869 | 24.6753 | منجز | Yes
2100081620 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3566158 | 178307.9 | 0 | 0 | 1010127437 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-11-07 | 2019-06-05 | 2019-06-05 | 2019-06-05 | 2019-06-05 |  |  |  | 46.6347 | 24.6691 | منجز | No
2100083521 | وزارة الدفاع / الإدارة الهندسية والاشغال بالخدمات الصحية | تشييد | ذات اولوية متوسطة | 13436667.11 | 671833.3555 | 11621002.31 | 7507902.41 | 1010146750 | لا | 0 | 190309038031 | جاري | الكميات التي تم تركيبها | 100 | 100 | 2019-01-07 | 2021-12-21 | 2022-06-21 | 2022-06-21 |  |  |  |  | 46.6798 | 24.713 | متأخر | No
2100092175 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 388900123.5 | 19445006.175 | 97225.0309 | 97225.0309 | 1010202928 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 0.74 | 100 | 2019-08-26 | 2022-02-11 | 2022-02-11 | 2022-02-11 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 46.8384 | 24.6591 | مسحوب | No
2100090915 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 6774641 | 338732.05 | 4869477.74 | 0 | 1010242793 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 93 | 100 | 2014-09-25 | 2016-03-18 | 2020-11-15 | 2020-11-15 | 2016-03-18 |  | ضعف كفاءة المقاول الفنية |  | 46.663 | 24.7082 | منجز | Yes
2100090860 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 571200 | 28560 | 0 | 0 | 1010106132 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 1 | 100 | 2018-03-19 | 2019-03-14 | 2021-07-04 | 2021-07-04 |  |  | ضعف كفاءة المقاول الفنية |  | 46.8005 | 23.4162 | مسحوب | No
2100090753 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 6631315 | 331565.75 | 4494324.15 | 0 | 1010178884 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 68 | 100 | 2014-08-20 | 2016-04-11 | 2020-03-31 | 2020-03-31 |  |  | ضعف كفاءة المقاول الفنية |  | 45.2944 | 24.0635 | مسحوب | Yes
2100090661 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2134100 | 106705 | 1096638.75 | 0 | 1010015152 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-05-19 | 2016-08-11 | 2019-08-25 | 2019-08-25 | 2016-08-11 |  | ضعف كفاءة المقاول الفنية |  | 46.672 | 24.7038 | منجز | Yes
2100052850 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 634742 | 31737.1 | 634742 | 0 | 1115001965 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-01-22 | 2019-03-17 | 2019-03-17 | 2019-03-17 | 2019-03-17 |  |  |  | 46.6933 | 24.7032 | منجز | Yes
2100030402 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2413950 | 120697.5 | 1129260 | 0 | 1010056094 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 49 | 100 | 2015-07-25 | 2016-10-17 | 2020-04-12 | 2020-04-12 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7041 | 22.2796 | مسحوب | Yes
2100033795 | وزارة المالية | تصميم | ذات اولوية متوسطة | 997000 | 49850 | 299100 | 299100 | 1010304791 | لا | 0 | 181109353335 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-11-10 | 2020-12-01 | 2022-11-02 | 2022-11-02 |  |  | التنسيق مع أصحاب المصلحه (خدمات |  | 46.7063 | 24.6976 | منتظم | No
2100189486 | الهيئة العامة للزكاة والدخل | ترميم | ذات اولوية متوسطة | 1489561.5 | 74478.075 | 1489561.5 | 1489561.5 | 1010174562 | لا | 0 |  | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2020-05-10 | 2020-07-06 | 2020-07-06 | 2020-07-06 |  | 2020-07-06 |  |  | 46.7137 | 24.6559 | منجز | No
2100189545 | الهيئة العامة للزكاة والدخل | توريد وتركيب | ذات اولوية عالية | 45438.8 | 2271.94 | 45438.8 | 45438.8 | 1010612558 | لا | 0 |  | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2020-09-28 | 2020-10-15 | 2020-10-15 | 2020-10-15 |  | 2020-10-15 |  |  | 46.7567 | 24.5626 | منجز | No
2100062753 | هيئة تطوير بوابة الدرعية | تشييد | ذات اولوية متوسطة | 453083287 | 22654164.35 | 321689133.77 | 321689133.77 | 2050001536 | لا | 0 | 200501046626 | جاري | اخرى | 80 | 75 | 2020-03-26 | 2021-03-25 | 2022-03-08 | 2022-03-08 |  |  |  |  | 46.5837 | 24.7317 | منتظم | No
2100085514 | شركة المياه الوطنية / منطقة الرياض | إشراف | ذات اولوية عالية | 2908000 | 145400 | 2782515.11 | 2782515.11 | 2050099301 | لا | 0 | 190401041221 | منجز – استلام نهائي | التكلفة المفوترة | 99.53 | 99.53 | 2019-05-01 | 2022-05-02 | 2022-05-02 | 2022-05-02 |  | 2022-05-02 | لا يوجد تأخير |  | 45.5771 | 20.4689 | منجز | No
2100084350 | شركة الكهرباء | تشييد | ذات اولوية متوسطة | 51000000 | 2550000 | 44726921 | 44726921 | 1010127329 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-08-25 | 2021-09-24 | 2021-11-24 | 2021-11-24 | 2021-09-24 |  |  |  | 46.6352 | 24.9762 | منجز | No
2100000346 | وزارة الشـؤون الاسلامية والدعوة والارشاد | تشييد | ذات اولوية عالية | 900000 | 45000 | 0 | 0 | 1155000177 | لا | 0 | 181101311288 | جاري | الكميات التي تم تركيبها | 100 | 100 | 2019-07-16 | 2022-03-01 | 2022-03-01 | 2022-03-01 |  |  | ضعف كفاءة المقاول الفنية |  | 44.4301 | 24.5121 | Failed | No
2100144233 | وزارة المالية | ترميم | ذات اولوية متوسطة | 2807120.01 | 140356.0005 | 2105082 | 2105082 | 1010349609 | لا | 0 | 180701028455 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-06-24 | 2020-12-24 | 2022-04-10 | 2022-04-10 | 2020-12-24 |  |  |  | 47.3463 | 24.1405 | منجز | No
2100003301 | رئاسة أمن الدولة / ديوان رئاسة أمن الدولة | تشييد | ذات اولوية عالية وعاجلة | 39952682.7 | 1997634.135 | 39952682.7 | 39952682.7 | 1010243700 | لا | 0 | 200201135484 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2020-03-12 | 2022-02-19 | 2022-02-19 | 2022-02-19 | 2022-02-19 |  | اخرى |  | 44.8209 | 24.4196 | منجز | No
2100020296 | وزارة التجارة | دراسة بيئية | ذات اولوية عالية | 6472800 | 323640 | 5889600 | 5889600 | 1010322156 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-01-21 | 2021-01-20 | 2021-01-20 | 2021-01-20 |  | 2021-01-20 | لا يوجد تأخير |  | 46.7157 | 24.6564 | منجز | No
2100103110 | شركة المياه الوطنية / منطقة الرياض | إشراف | ذات اولوية عالية | 1900000 | 95000 | 1596666.67 | 1596666.67 | 1010469290 | لا | 0 |  | منجز – استلام نهائي | مدفوعات ساعات العمل | 84.09 | 100 | 2019-09-11 | 2020-12-10 | 2020-12-11 | 2020-12-11 |  | 2020-12-10 | لا يوجد تأخير |  | 46.7942 | 24.6528 | منجز | No
2100026644 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3675600 | 183780 | 1531500 | 1531500 | 1010374734 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 44 | 44 | 2018-06-07 | 2021-05-07 | 2021-05-08 | 2021-05-08 |  |  |  |  | 46.6594 | 24.7206 | Failed | No
2100029002 | أمانة / الرياض | تشييد | ذات اولوية عالية | 29280741 | 1464037.05 | 20107221.76 | 0 | 1115001486 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 100 | 100 | 2010-10-21 | 2012-08-11 | 2019-11-01 | 2019-11-01 |  |  | ضعف كفاءة المقاول الفنية |  | 46.4265 | 24.9017 | مسحوب | Yes
2100029654 | أمانة / الرياض | تشييد | ذات اولوية عالية | 7147240 | 357362 | 6140954.6 | 0 | 1010193266 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 97 | 100 | 2015-02-24 | 2017-02-13 | 2020-09-16 | 2020-09-16 | 2017-02-13 |  | ضعف كفاءة المقاول الفنية |  | 47.212 | 24.1513 | منجز | Yes
2100056604 | وزارة الموارد البشرية والتنمية الإجتماعية | إشراف | ذات اولوية منخفضة | 1409067 | 70453.35 | 2579336.33 | 2579336.33 | 1010429789 | لا | 0 | 190501072893 | مسحوب | الكميات التي تم تركيبها | 85 | 100 | 2014-12-28 | 2016-12-05 | 2022-06-14 | 2022-06-14 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 45.1516 | 25.1808 | مسحوب | No
2100001175 | الهيئة الملكية لمدينة الرياض | تشييد | ذات اولوية عالية | 24081788167 | 1204089408.35 | 23177108982.7 | 23177108982.7 | 2051025367 | لا | 0 | 190209017629 | جاري | منهجية القيمة المكتسبة | 93 | 100 | 2013-10-30 | 2018-10-29 | 2022-06-30 | 2022-06-30 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 46.7792 | 24.6801 | Failed | No
2100031286 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4136400 | 206820 | 1613992 | 1613992 | 1010108088 | لا | 0 | 181109354973 | جاري | الكميات التي تم تركيبها | 44 | 44 | 2015-08-15 | 2018-08-14 | 2018-08-15 | 2018-08-15 |  |  |  |  | 46.6786 | 24.7032 | Failed | No
2100191682 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 6566581 | 328329.05 | 5813466.41 | 5813466.41 | 1010227442 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 98.46 | 100 | 2020-12-24 | 2021-10-23 | 2022-04-30 | 2022-04-30 | 2021-10-23 |  |  |  | 46.822 | 24.8391 | منجز | No
2100013370 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2452000 | 122600 | 1427944 | 0 | 1010108475 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 73 | 2018-01-21 | 2020-01-11 | 2020-01-11 | 2020-01-11 | 2020-01-11 |  |  |  | 46.6782 | 24.7069 | منجز | Yes
2100026994 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 10225688 | 511284.4 | 41363 | 0 | 1010219010 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 73 | 100 | 2013-09-06 | 2015-08-27 | 2020-02-16 | 2020-02-16 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6795 | 24.7082 | مسحوب | Yes
2100028593 | شركة الكهرباء | تشييد | ذات اولوية متوسطة | 48067304 | 2403365.2 | 24032963 | 24032963 | 1010063866 | لا | 0 |  | ايقاف كلي | اخرى | 47.3 | 100 | 2018-05-28 | 2020-08-27 | 2020-08-27 | 2020-08-27 |  |  | اخرى |  | 46.6857 | 24.897 | Failed | No
2100063744 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 54102087.91 | 2705104.3955 | 25842752.52 | 25842752.52 | 1010193266 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 64.32 | 100 | 2017-11-16 | 2019-12-18 | 2020-04-24 | 2020-04-24 |  |  |  |  | 46.6786 | 24.7032 | Failed | No
2100043422 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 664050 | 33202.5 | 41928 | 0 | 1010232227 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 96 | 100 | 2015-04-14 | 2016-04-08 | 2019-09-03 | 2019-09-03 | 2016-04-08 |  | ضعف كفاءة المقاول الفنية |  | 46.6882 | 24.6853 | منجز | Yes
2100075961 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 8429869.8 | 421493.49 | 1658638.215 | 0 | 1116001737 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 85 | 100 | 2013-01-17 | 2014-09-09 | 2022-12-06 | 2022-12-06 | 2014-09-09 |  | ضعف كفاءة المقاول الفنية |  | 46.6843 | 24.71 | منجز | Yes
2100088583 | الهيئة الملكية لمدينة الرياض | تشييد | ذات اولوية عالية | 183996711.49 | 9199835.5745 | 164963495.82 | 164963495.82 | 1010307848 | لا | 0 | 190309041451 | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2016-08-04 | 2019-01-06 | 2020-08-31 | 2020-08-31 | 2019-01-06 |  |  |  | 46.7139 | 24.6289 | منجز | No
2100023516 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2181068 | 109053.4 | 42102 | 0 | 1113001362 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 5 | 100 | 2015-09-13 | 2017-03-06 | 2021-02-07 | 2021-02-07 |  |  | تأخرصرف المستحقات المالية |  | 46.685 | 24.7082 | مسحوب | Yes
2100046292 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4189975 | 209498.75 | 41724 | 0 | 1113000601 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 47 | 100 | 2014-11-01 | 2016-04-24 | 2020-05-30 | 2020-05-30 |  |  | تأخرصرف المستحقات المالية |  | 46.6727 | 24.7231 | مسحوب | Yes
2100046244 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4886570 | 244328.5 | 290399.2 | 0 | 1124000200 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 95 | 100 | 2014-09-22 | 2018-12-25 | 2018-12-25 | 2018-12-25 | 2018-12-25 |  |  |  | 46.6727 | 24.7181 | منجز | Yes
2100063464 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2633818 | 131690.9 | 2215030 | 0 | 1010242510 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 87 | 100 | 2015-01-15 | 2019-01-12 | 2019-01-13 | 2019-01-13 | 2019-01-12 |  |  |  | 46.6692 | 24.6963 | منجز | Yes
2100044181 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 9944450 | 497222.5 | 5148244 | 0 | 1011000444 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 72 | 2018-06-04 | 2019-11-26 | 2021-06-30 | 2021-06-30 | 2019-11-26 |  | ضعف كفاءة المقاول الفنية |  | 46.6731 | 24.6965 | منجز | Yes
2100013646 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3500000 | 175000 | 2678179.6 | 0 | 1113000601 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 93 | 89 | 2018-03-07 | 2019-08-29 | 2019-08-30 | 2019-08-30 | 2019-08-29 |  |  |  | 46.6905 | 24.7069 | منجز | Yes
2100063976 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3486975 | 174348.75 | 250800 | 0 | 1010422547 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 9 | 100 | 2015-07-02 | 2016-12-23 | 2022-09-08 | 2022-09-08 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6768 | 24.7007 | مسحوب | Yes
2100017570 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 904800 | 45240 | 154000 | 0 | 2051047076 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 80.54 | 100 | 2015-05-20 | 2016-05-04 | 2020-05-23 | 2020-05-23 | 2016-05-04 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 46.685 | 24.6982 | منجز | Yes
2100013543 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1216806.4516 | 60840.3226 | 1216806.4516 | 0 | 1010290069 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-11-03 | 2018-09-30 | 2018-10-01 | 2018-10-01 | 2018-09-30 |  |  |  | 46.685 | 24.705 | منجز | Yes
2100028836 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1456007 | 72800.35 | 758600 | 0 | 1018000156 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 52 | 100 | 2014-03-01 | 2015-04-25 | 2021-06-29 | 2021-06-29 |  |  | ضعف كفاءة المقاول الفنية |  | 46.1187 | 25.1224 | مسحوب | Yes
2100075342 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1599320 | 79966 | 41251 | 0 | 1010291687 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 55 | 100 | 2013-06-01 | 2014-08-25 | 2021-07-01 | 2021-07-01 |  |  | ضعف كفاءة المقاول الفنية |  | 46.1132 | 25.1324 | Failed | Yes
2100013064 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 40674953 | 2033747.65 | 14595841.92 | 0 | 1010154882 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 89 | 100 | 2013-03-28 | 2015-03-18 | 2020-04-09 | 2020-04-09 | 2015-03-18 |  | ضعف كفاءة المقاول الفنية |  | 45.5119 | 23.5757 | منجز | Yes
2100069333 | وزارة الدفاع / الإدارة الهندسية والاشغال بالخدمات الصحية | تشييد | ذات اولوية متوسطة | 13493181.8 | 674659.09 | 6725497.59 | 4073144.04 | 1010179829 | لا | 0 | 190801048194 | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-11-03 | 2020-12-22 | 2022-06-22 | 2022-06-22 |  |  |  |  | 46.6869 | 24.6957 | متأخر | No
2100203195 | جامعة الملك سعود | تشييد | ذات اولوية متوسطة | 5762982.26 | 288149.113 | 5762982.26 | 5762982.26 | 1010104084 | لا | 0 | 210309062896 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-11-29 | 2021-05-25 | 2022-04-06 | 2022-04-06 | 2021-05-25 |  |  |  | 46.6236 | 24.7253 | منجز | No
2100046561 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1377653 | 68882.65 | 41461 | 0 | 1010290949 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 72 | 100 | 2014-03-04 | 2019-03-23 | 2019-03-25 | 2019-03-25 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6761 | 24.7025 | مسحوب | Yes
2100017883 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4879324 | 243966.2 | 1271990 | 0 | 1114000037 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-08-29 | 2016-02-20 | 2020-04-17 | 2020-04-17 | 2016-02-20 |  | ضعف كفاءة المقاول الفنية |  | 46.6637 | 24.7075 | منجز | Yes
2100029374 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1466500 | 73325 | 0 | 0 | 1010168999 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 2 | 40 | 2014-08-28 | 2016-06-08 | 2016-06-07 | 2016-06-07 | 2016-06-08 |  | ضعف كفاءة المقاول الفنية |  | 46.6878 | 24.7107 | منجز | No
2100026342 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 658100 | 32905 | 42094 | 0 | 1010158466 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-08-24 | 2016-08-18 | 2016-08-18 | 2016-08-18 | 2016-08-18 |  | ضعف كفاءة المقاول الفنية |  | 46.685 | 24.7082 | منجز | Yes
2100045426 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 174760 | 8738 | 0 | 0 | 1010331376 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 73 | 2018-10-09 | 2019-09-24 | 2019-10-05 | 2019-10-05 | 2019-09-24 |  |  |  | 47.1687 | 25.5601 | منجز | No
2100012622 | أمانة / الرياض | تشييد | ذات اولوية عالية | 395728.5 | 19786.425 | 395728.5 | 0 | 1010203405 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-01-01 | 2018-12-12 | 2018-12-12 | 2018-12-12 | 2018-12-12 |  |  |  | 46.7328 | 24.7359 | منجز | Yes
2100047246 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2074905.4015 | 103745.2701 | 1556207.784 | 0 | 1010244941 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-07-01 | 2019-07-01 | 2019-07-02 | 2019-07-02 | 2019-07-01 |  |  |  | 46.7209 | 22.3058 | منجز | Yes
2100071271 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2040200 | 102010 | 41119 | 0 | 1116002329 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-10-21 | 2016-04-13 | 2021-06-21 | 2021-06-21 | 2016-04-13 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 46.1581 | 24.6295 | منجز | Yes
2100012460 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 949050 | 47452.5 | 854144 | 0 | 1185000614 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 95 | 2014-11-24 | 2015-09-20 | 2015-09-20 | 2015-09-20 | 2015-09-20 |  | ضعف كفاءة المقاول الفنية |  | 46.6699 | 24.7281 | منجز | Yes
2100030553 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 5511580 | 275579 | 1552610 | 0 | 1010015152 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 74.26 | 100 | 2014-08-09 | 2016-01-31 | 2020-06-11 | 2020-06-11 | 2016-01-31 |  | ضعف كفاءة المقاول الفنية |  | 46.6706 | 24.6951 | منجز | Yes
2100055296 | شركة الكهرباء | تشييد | ذات اولوية متوسطة | 177356950 | 8867847.5 | 176406055 | 176406055 | 2051001976 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2017-07-30 | 2019-09-16 | 2020-12-02 | 2020-12-02 | 2019-09-16 |  | لا يوجد تأخير |  | 46.704 | 24.87 | منجز | No
2100054913 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 21236.05 | 1061.8025 | 412.67 | 0 | 1010318776 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 56 | 100 | 2013-11-27 | 2015-05-21 | 2020-04-11 | 2020-04-11 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6871 | 24.7013 | مسحوب | Yes
2100045205 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 9323214.0002 | 466160.7 | 7333561.5 | 0 | 1010056094 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 86 | 100 | 2015-01-07 | 2016-12-27 | 2021-06-21 | 2021-06-21 |  |  | ضعف كفاءة المقاول الفنية |  | 44.7647 | 20.3608 | Failed | Yes
2100013053 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2475030 | 123751.5 | 1746890 | 0 | 1010129611 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-01-30 | 2019-04-25 | 2019-04-25 | 2019-04-25 | 2019-04-25 |  |  |  | 46.6905 | 24.7119 | منجز | Yes
2100046723 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 11994800 | 599740 | 8892784.98 | 0 | 1010101252 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2013-07-22 | 2015-07-12 | 2019-12-01 | 2019-12-01 | 2015-07-12 |  | ضعف كفاءة المقاول الفنية |  | 46.6782 | 24.7032 | منجز | Yes
2100045323 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4708681 | 235434.05 | 41414 | 0 | 1010010466 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95.47 | 100 | 2014-02-01 | 2015-07-26 | 2019-11-11 | 2019-11-11 | 2015-07-26 |  | ضعف كفاءة المقاول الفنية |  | 45.2573 | 24.064 | منجز | Yes
2100063394 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3799903.5 | 189995.175 | 3799757.75 | 0 | 1010056094 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-01-12 | 2016-04-02 | 2016-04-02 | 2016-04-02 | 2016-04-02 |  |  |  | 46.6747 | 24.7038 | منجز | Yes
2100064783 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3585020 | 179251 | 41722 | 0 | 1010300884 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 0 | 100 | 2014-09-21 | 2016-03-14 | 2021-06-04 | 2021-06-04 |  |  | تأخرصرف المستحقات المالية |  | 46.6857 | 24.7038 | Failed | Yes
2100083823 | وزارة الدفاع / الإدارة الهندسية والاشغال بالخدمات الصحية | تشييد | ذات اولوية متوسطة | 49267101 | 2463355.05 | 3480054.85 | 3480054.85 | 1010195593 | لا | 0 | 190801047738 | ايقاف كلي | الكميات التي تم تركيبها | 12 | 100 | 2019-05-16 | 2020-05-03 | 2021-12-31 | 2021-12-31 |  |  |  |  | 46.6894 | 24.702 | Failed | No
2100070136 | وزارة الدفاع / الإدارة الهندسية والاشغال بالخدمات الصحية | تشييد | ذات اولوية متوسطة | 49998675 | 2499933.75 | 17862189 | 11941660 | 1010033701 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 35 | 53 | 2019-01-14 | 2022-01-02 | 2023-01-02 | 2023-01-02 |  |  |  |  | 46.6773 | 24.7144 | متأخر | No
2100082854 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 8392680 | 419634 | 41511 | 0 | 1010276314 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 6 | 100 | 2014-10-18 | 2016-01-11 | 2021-09-18 | 2021-09-18 |  |  | ضعف كفاءة المقاول الفنية |  | 42.9222 | 23.9 | مسحوب | Yes
2100064153 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 36932642 | 1846632.1 | 35267415.19 | 0 | 1010056094 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 99.98 | 100 | 2014-08-06 | 2016-07-26 | 2019-09-13 | 2019-09-13 | 2016-07-26 |  | ضعف كفاءة المقاول الفنية |  | 46.6775 | 24.7088 | منجز | Yes
2100081524 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 44374960 | 2218748 | 31877765.62 | 0 | 1116005202 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 100 | 2014-09-21 | 2016-09-10 | 2019-10-04 | 2019-10-04 | 2016-09-10 |  | ضعف كفاءة المقاول الفنية |  | 44.4042 | 24.5266 | منجز | Yes
2100091630 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 514656.45 | 25732.8225 | 0 | 0 | 1010043654 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-10-15 | 2020-10-10 | 2020-10-10 | 2020-10-10 | 2020-10-10 |  | اخرى |  | 45.5484 | 25.6155 | منجز | No
2100080776 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 7507000 | 375350 | 41187 | 0 | 1010211704 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 91 | 100 | 2013-06-28 | 2015-06-18 | 2021-07-04 | 2021-07-04 | 2015-06-18 |  | ضعف كفاءة المقاول الفنية |  | 46.6951 | 24.704 | منجز | Yes
2100051041 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 409750 | 20487.5 | 409750 | 0 | 1112000662 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-02-01 | 2019-01-27 | 2019-01-27 | 2019-01-27 | 2019-01-27 |  |  |  | 46.6686 | 24.7219 | منجز | Yes
2100203335 | وزارة الصحة/ الاحساء | تشييد | ذات اولوية عالية | 7936000 | 396800 | 7936000 | 2429651 | 1010209661 | لا | 0 | 190809103631 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 0 | 2021-05-30 | 2022-05-29 | 2022-05-29 | 2022-05-29 | 2022-05-29 |  |  |  | 49.5607 | 25.3583 | منجز | No
2100081513 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 540194 | 27009.7 | 40685 | 0 | 4030197963 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 40 | 100 | 2012-02-13 | 2018-02-03 | 2018-02-03 | 2018-02-03 |  |  | ضعف كفاءة المقاول الفنية |  | 43.8191 | 25.0119 | مسحوب | Yes
2100090462 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 12478186.9999 | 623909.35 | 11773075 | 0 | 1010170119 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-08-31 | 2015-02-17 | 2015-02-07 | 2015-02-07 | 2015-02-17 |  | ضعف كفاءة المقاول الفنية |  | 47.3548 | 24.1372 | منجز | Yes
2100071536 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 5243232.96 | 262161.648 | 292219.2 | 292219.2 | 1010094443 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 24 | 21 | 2019-07-15 | 2020-12-27 | 2020-12-27 | 2020-12-27 |  |  |  |  | 46.7093 | 24.6295 | Failed | No
2100071470 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3250431 | 162521.55 | 40846 | 0 | 1010163813 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 78 | 100 | 2012-06-16 | 2019-03-23 | 2019-03-24 | 2019-03-24 |  |  | ضعف كفاءة المقاول الفنية |  | 45.5164 | 23.5402 | مسحوب | Yes
2100062650 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1891000 | 94550 | 42015 | 0 | 1118001565 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 72 | 100 | 2015-05-22 | 2016-08-14 | 2016-08-14 | 2016-08-14 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6782 | 24.7144 | مسحوب | Yes
2100064466 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 397755.5 | 19887.775 | 0 | 0 | 1011004277 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 97 | 21 | 2019-04-15 | 2020-04-09 | 2020-04-10 | 2020-04-10 | 2020-04-09 |  | ضعف كفاءة المقاول الفنية |  | 46.7918 | 23.4145 | منجز | No
2100081071 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 6669565 | 333478.25 | 39684 | 0 | 1010147656 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 80 | 100 | 2009-08-09 | 2011-01-31 | 2019-03-25 | 2019-03-25 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7289 | 22.3043 | مسحوب | Yes
2100014991 | شركة الكهرباء | تشييد | ذات اولوية متوسطة | 62281656 | 3114082.8 | 59414000 | 59414000 | 2050004063 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-07-17 | 2021-04-16 | 2021-06-17 | 2021-06-17 | 2021-04-16 |  |  |  | 46.683 | 24.7107 | منجز | No
2100080684 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 548100 | 27405 | 398638.4 | 0 | 1010346143 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 94 | 100 | 2018-03-27 | 2019-06-20 | 2019-06-21 | 2019-06-21 | 2019-06-20 |  | ضعف كفاءة المقاول الفنية |  | 46.2733 | 24.471 | منجز | Yes
2100026316 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 921750 | 46087.5 | 42101 | 0 | 1116001737 | لا | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 68 | 100 | 2015-12-09 | 2017-03-03 | 2019-11-16 | 2019-11-16 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6878 | 24.7119 | Failed | Yes
2100093472 | أمانة / الرياض | دراسة الجدوى | ذات اولوية متوسطة | 4245120 | 212256 | 3455128 | 0 | 4030192494 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-04-02 | 2018-11-12 | 2018-11-12 | 2018-11-12 | 2018-11-12 |  | اخرى |  | 45.3715 | 25.8722 | منجز | Yes
2100040854 | هيئة المدن الصناعية ومناطق التقنية | تصميم | ذات اولوية عالية | 29966000 | 1498300 | 11738795 | 11738795 | 1010610727 | لا | 0 |  | جاري | التكلفة المفوترة | 39 | 43 | 2019-11-14 | 2023-10-24 | 2023-10-24 | 2023-10-24 |  |  | لا يوجد تأخير |  | 46.6786 | 24.7107 | منتظم | No
2100190562 | شركة المياه الوطنية / منطقة الرياض | إشراف | ذات اولوية عالية | 9999000 | 499950 | 2485025.97 | 2485025.97 | 1010322448 | لا | 0 |  | جاري | التكلفة المفوترة | 28.49 | 28.49 | 2021-04-01 | 2023-10-01 | 2023-10-01 | 2023-10-01 |  |  |  |  | 46.7949 | 24.6526 | خدمات عامة | No
2100033972 | شركة المياه الوطنية / منطقة الرياض | إشراف | ذات اولوية عالية | 16495000 | 824750 | 16486871.94 | 16486871.94 | 1010314421 | لا | 0 |  | منجز – استلام نهائي | التكلفة المفوترة | 99.95 | 99.95 | 2018-12-16 | 2020-12-17 | 2021-10-31 | 2021-10-31 |  | 2020-12-17 | لا يوجد تأخير |  | 46.7942 | 24.6531 | منجز | No
2100020613 | شركة المياه الوطنية / منطقة الرياض | إشراف | ذات اولوية عالية | 21575700 | 1078785 | 20913310.54 | 20913310.54 | 1010321646 | لا | 0 | 180809055498 | منجز – استلام نهائي | التكلفة المفوترة | 100 | 100 | 2016-06-28 | 2019-06-27 | 2020-06-02 | 2020-06-02 |  | 2019-06-27 | لا يوجد تأخير |  | 44.8553 | 20.4423 | منجز | No
2100070910 | وزارة الداخلية / مديرية الأمن العام | تشييد | ذات اولوية متوسطة | 1636583.3 | 81829.165 | 1565954.85 | 1565954.85 | 1010134168 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-02-29 | 2021-08-29 | 2021-11-29 | 2021-11-29 | 2021-08-29 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 46.3242 | 22.6087 | منجز | No
2100015352 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 372582402 | 18629120.1 | 335106685 | 320020430 | 1010057263 | لا | 0 | 180709026269 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 99.6 | 99.84 | 2017-06-15 | 2020-06-14 | 2023-03-30 | 2023-03-30 |  |  |  |  | 38.216 | 24.002 | منتظم | No
2100039266 | وزارة الثقافة | تصميم | لم تعد تحتاجها الجهة | 11212500 | 560625 | 0 | 0 | 2051011487 | لا | 0 |  | ايقاف كلي | منهجية القيمة المكتسبة | 25 | 30 |  | 2020-08-19 | 2021-01-01 | 2021-01-01 |  |  | اخرى |  | 46.3726 | 24.6925 | Failed | No
2100178496 | وزارة الثقافة | إشراف | ذات اولوية عالية | 4920168.75 | 246008.4375 | 2499802.25 | 2499802.25 | 1010322156 | لا | 0 |  | جاري | مدفوعات ساعات العمل | 100 | 100 | 2019-10-03 | 2021-10-05 | 2021-10-05 | 2021-10-05 |  |  |  |  | 46.6827 | 24.7057 | خدمات عامة | No
2100191601 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 18874425 | 943721.25 | 13125951.85 | 13125951.85 | 1010039430 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 92.61 | 100 | 2020-06-08 | 2020-12-08 | 2021-04-15 | 2021-04-15 | 2020-12-08 |  |  |  | 46.7169 | 24.6003 | منجز | No
2100030063 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 56901458.2 | 2845072.91 | 42252591.52 | 42252591.52 | 1010200098 | لا | 0 | 180809057460 | جاري | الكميات التي تم تركيبها | 85 | 100 | 2014-02-06 | 2019-08-19 | 2020-02-12 | 2020-02-12 |  |  |  |  | 46.6731 | 24.7057 | Failed | No
2100002763 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 949050 | 47452.5 | 854144 | 0 | 1185000614 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 95 | 2014-11-24 | 2015-09-20 | 2021-06-13 | 2021-06-13 | 2015-09-20 |  | ضعف كفاءة المقاول الفنية |  | 46.6827 | 24.7065 | منجز | Yes
2100030505 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2119500 | 105975 | 1906750 | 0 | 1010043654 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 32 | 2019-01-07 | 2020-06-30 | 2020-06-30 | 2020-06-30 | 2020-06-30 |  |  |  | 46.685 | 24.7094 | منجز | Yes
2100017430 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1798452 | 89922.6 | 41896 | 0 | 1113000601 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 79 | 100 | 2015-03-16 | 2016-03-10 | 2016-03-11 | 2016-03-11 | 2016-03-10 |  | ضعف كفاءة المقاول الفنية |  | 45.2042 | 25.3316 | منجز | Yes
2100013580 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3972900 | 198645 | 2866723.95 | 0 | 1185002656 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 96.99 | 100 | 2014-12-14 | 2016-02-07 | 2019-09-07 | 2019-09-07 | 2016-02-07 |  | ضعف كفاءة المقاول الفنية |  | 44.9844 | 20.4553 | منجز | Yes
2100023995 | أمانة / الرياض | تشييد | ذات اولوية عالية | 247031022 | 12351551.1 | 32364874.64 | 32364874.64 | 2050001536 | لا | 0 | 190701101492 | ايقاف جزئي | الكميات التي تم تركيبها | 64.41 | 74.2 | 2019-09-26 | 2021-03-09 | 2021-03-10 | 2021-03-10 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6814 | 24.7069 | Failed | No
2100075106 | أمانة / الرياض | تشييد | ذات اولوية عالية | 46200000 | 2310000 | 39748583.57 | 39748583.57 | 1010168729 | لا | 0 | 180901072188 | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 90.21 | 93 | 2018-12-27 | 2021-05-29 | 2021-05-29 | 2021-05-29 |  |  |  |  | 46.6773 | 24.7082 | Failed | No
2100041160 | البريد السعودي | تشييد | ذات اولوية متوسطة | 24980837 | 1249041.85 | 3107198.78 | 3107198.78 | 1010142553 | نعم | 2672947 |  | مسحوب | منهجية القيمة المكتسبة | 33 | 100 | 2016-04-17 | 2017-07-03 | 2018-04-25 | 2018-04-25 |  |  | ضعف كفاءة المقاول الفنية |  | 44.8196 | 26.3033 | مسحوب | No
2100189512 | الهيئة العامة للزكاة والدخل | ترميم | ذات اولوية متوسطة | 521850 | 26092.5 | 521850 | 521850 | 1010194614 | لا | 0 |  | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2020-05-31 | 2020-07-08 | 2020-07-08 | 2020-07-08 |  | 2020-07-08 |  |  | 46.7137 | 24.6559 | منجز | No
2100193222 | وزارة الحرس الوطني / الشؤون الفنية بالقطاع الغربي | ترميم | ذات اولوية متوسطة | 10972667.5 | 548633.375 | 2393293.06 | 2393293.06 | 1010092552 | لا | 0 | 200501049404 | جاري | الكميات التي تم تركيبها | 26 | 43 | 2021-02-22 | 2024-01-21 | 2024-01-20 | 2024-01-20 |  |  |  |  | 46.6816 | 24.7088 | متأخر | No
2100016343 | جامعة الأميرة نورة بنت عبدالرحمن | تشييد | ذات اولوية متوسطة | 1753710 | 87685.5 | 1753710 | 1753710 | 3452005783 | لا | 0 |  | جاري الاستلام الإبتدائي | التكلفة المفوترة | 100 | 100 | 2019-10-13 | 2020-11-02 | 2020-11-02 | 2020-11-02 | 2020-11-02 |  | لا يوجد تأخير |  | 46.719 | 24.862 | Failed | No
2100039513 | مدينة الملك عبدالعزيز للعلوم والتقنية | تشييد | ذات اولوية عالية | 64699462.47 | 3234973.1235 | 58249928.75 | 58249928.75 | 1010046693 | لا | 0 | 181001150767 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 98 | 100 | 2019-02-06 | 2020-06-28 | 2022-07-31 | 2022-07-31 | 2020-06-28 |  |  |  | 46.6433 | 24.717 | منجز | No
2100021582 | مدينة الملك عبدالعزيز للعلوم والتقنية | تشييد | ذات اولوية عالية وعاجلة | 49494214.61 | 2474710.7305 | 46648091.53 | 40014009.48 | 4030129407 | لا | 0 | 180701028148 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-04-15 | 2019-04-10 | 2021-03-25 | 2021-03-25 | 2019-04-10 |  | أوامر تغيير |  | 46.6433 | 24.717 | منجز | No
2100192695 | البريد السعودي | تصميم | ذات اولوية عالية | 19579897.35 | 978994.8675 | 15455361 | 0 | 1010179411 | لا | 0 | 200209127034 | ايقاف جزئي | منهجية القيمة المكتسبة | 70 | 70 | 2020-02-02 | 2020-10-31 | 2022-12-31 | 2022-12-31 |  |  | اخرى |  | 46.702 | 24.9334 | Failed | Yes
2100066124 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 187953316.77 | 9397665.8385 | 61575057.74 | 61575057.74 | 1010142553 | لا | 0 | 180809058169 | مسحوب | الكميات التي تم تركيبها | 42 | 100 | 2014-01-28 | 2017-09-30 | 2017-01-06 | 2017-01-06 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6759 | 24.7094 | مسحوب | No
2100033213 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 658300 | 32915 | 658300 | 0 | 1010214210 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 33 | 2019-03-04 | 2020-02-27 | 2020-02-28 | 2020-02-28 | 2020-02-27 |  |  |  | 46.6745 | 24.7015 | منجز | Yes
2100028825 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2488990 | 124449.5 | 42073 | 0 | 1116004302 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 8 | 100 | 2015-08-13 | 2017-02-03 | 2017-03-02 | 2017-03-02 |  |  | تأخرصرف المستحقات المالية |  | 46.6809 | 24.7082 | مسحوب | Yes
2100032815 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 515545.8 | 25777.29 | 54450 | 0 | 1010256208 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 21 | 2019-01-26 | 2021-01-15 | 2021-01-16 | 2021-01-16 | 2021-01-15 |  |  |  | 44.9469 | 26.03 | منجز | Yes
2100090635 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 199690 | 9984.5 | 0 | 0 | 1010256208 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 99.31 | 50 | 2018-11-04 | 2020-10-24 | 2020-10-25 | 2020-10-25 | 2020-10-24 |  | ضعف كفاءة المقاول الفنية |  | 45.8759 | 25.7021 | منجز | No
2100012401 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4199100 | 209955 | 41898 | 0 | 1010425198 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 1 | 100 | 2015-03-17 | 2016-06-09 | 2020-11-09 | 2020-11-09 |  |  | ضعف كفاءة المقاول الفنية |  | 46.0812 | 25.1179 | مسحوب | Yes
2100046642 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3699000 | 184950 | 3295000 | 0 | 3350032016 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-09-03 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 |  |  |  | 45.8607 | 25.2736 | منجز | Yes
2100071621 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 6629225 | 331461.25 | 1006050 | 0 | 1010056094 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 32 | 100 | 2015-04-15 | 2016-07-08 | 2020-09-15 | 2020-09-15 |  |  | ضعف كفاءة المقاول الفنية |  | 45.9632 | 21.9856 | Failed | Yes
2100046804 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 7272635 | 363631.75 | 41933 | 0 | 1116005202 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 0 | 100 | 2015-04-22 | 2017-04-11 | 2021-08-06 | 2021-08-06 |  |  | تأخرصرف المستحقات المالية |  | 46.6837 | 24.7107 | مسحوب | Yes
2100047423 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 339660 | 16983 | 339660 | 0 | 5951001795 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-07-18 | 2019-01-26 | 2019-01-26 | 2019-01-26 | 2019-01-26 |  |  |  | 46.6786 | 24.7065 | منجز | Yes
2100062694 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3439822 | 171991.1 | 3267822 | 0 | 1113000219 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 95 | 100 | 2014-08-04 | 2016-01-26 | 2019-09-08 | 2019-09-08 | 2016-01-26 |  | ضعف كفاءة المقاول الفنية |  | 46.6658 | 24.7094 | منجز | Yes
2100012681 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3939020 | 196951 | 42000 | 0 | 1010350630 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-06-06 | 2016-11-27 | 2020-02-06 | 2020-02-06 | 2016-11-27 |  | ضعف كفاءة المقاول الفنية |  | 46.6919 | 24.7057 | منجز | Yes
2100014965 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 49848165.84 | 2492408.292 | 22677143.1 | 22677143.1 | 1131013992 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 43 | 94 | 2019-11-27 | 2021-05-20 | 2023-04-30 | 2023-04-30 |  |  | التنسيق مع أصحاب المصلحه (خدمات | أخرى | 46.7038 | 24.9471 | Failed | No
2100203862 | جامعة الملك سعود | ترميم | ذات اولوية متوسطة | 9360367.8 | 468018.39 | 2707479.5 | 2707479.5 | 1010194970 | لا | 0 | 211009133423 | ايقاف كلي | تكلفة العمل المنجز | 78 | 95 | 2020-08-17 | 2021-08-02 | 2023-03-09 | 2023-03-09 |  |  |  |  | 46.6234 | 24.7117 | Failed | No
2100000512 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية متوسطة | 61999857 | 3099992.85 | 58589864.52 | 58589864.52 | 1010012911 | لا | 0 | 180709032709 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-02-11 | 2021-01-09 | 2021-04-12 | 2021-04-12 |  | 2021-01-09 | لا يوجد تأخير |  | 43.9544 | 26.3504 | منجز | No
2100060826 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 16079160 | 803958 | 10753180 | 10753180 | 4031041927 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 88.56 | 100 | 2017-12-20 | 2020-05-25 | 2021-04-24 | 2021-04-24 | 2020-05-25 |  | لا يوجد تأخير |  | 40.4471 | 21.6132 | منجز | No
2100103084 | جامعة الإمام محمد بن سعود الاسلامية | تصميم | ذات اولوية منخفضة | 525000 | 26250 | 525000 | 0 | 1010078921 | لا | 0 | 181209447428 | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2018-10-16 | 2018-11-11 | 2018-11-11 | 2018-11-11 | 2018-11-11 |  | لا يوجد تأخير |  | 46.706 | 24.8101 | منجز | Yes
2100009273 | جامعة الإمام محمد بن سعود الاسلامية | تصميم | ذات اولوية منخفضة | 945000 | 47250 | 945000 | 0 | 1010078921 | لا | 0 | 181209447558 | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2018-03-06 | 2018-08-15 | 2018-08-15 | 2018-08-15 | 2018-08-15 |  | لا يوجد تأخير |  | 46.6953 | 24.8082 | منجز | Yes
2100073592 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تصميم | ذات اولوية عالية وعاجلة | 17584254 | 879212.7 | 17584231 | 17584231 | 1010320575 | لا | 0 | 191101247642 | منجز – استلام ابتدائي | اخرى | 99.99 | 100 | 2012-05-23 | 2015-05-23 | 2022-03-31 | 2022-03-31 | 2015-05-23 |  |  |  | 38.1866 | 24.0022 | منجز | No
2100012305 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية وعاجلة | 58237525 | 2911876.25 | 12735676.35 | 12735676.35 | 1131055582 | لا | 0 | 180901083934 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 98.2 | 100 | 2018-12-06 | 2021-11-03 | 2022-06-30 | 2022-06-30 | 2021-11-03 |  | لا يوجد تأخير |  | 43.9597 | 26.325 | منجز | No
2100027720 | رئاسة أمن الدولة / ديوان رئاسة أمن الدولة | تشييد | ذات اولوية عالية وعاجلة | 9238741.05 | 461937.0525 | 7858956.53 | 5688938.39 | 5950010363 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-08-29 | 2020-07-14 | 2022-11-17 | 2022-11-17 | 2020-07-14 |  | تغيرات في نطاق المشروع |  | 45.4549 | 24.5673 | منجز | No
2100059721 | الهيئة الملكية لمدينة مكة المكرمة و المشاعر المقدسة | تشييد | ذات اولوية عالية وعاجلة | 21840000 | 1092000 | 10764762 | 9455113 | 4031040412 | لا | 0 | 190509071326 | جاري | الكميات التي تم تركيبها | 80 | 100 | 2018-08-31 | 2020-02-12 | 2021-10-01 | 2021-10-01 |  |  | تأخرصرف المستحقات المالية |  | 21.4198 | 39.8682 | Failed | No
2100015433 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 37990988 | 1899549.4 | 35965680 | 35965680 | 3555000709 | لا | 0 | 180909093583 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 97.81 | 100 | 2017-08-21 | 2019-10-21 | 2023-06-28 | 2023-06-28 |  |  |  |  | 38.2547 | 23.9481 | منتظم | No
2100055311 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 26766666 | 1338333.3 | 24058215 | 24058215 | 4032019436 | لا | 0 | 180909114001 | جاري | منهجية القيمة المكتسبة | 95 | 100 | 2017-03-15 | 2018-03-15 | 2023-04-18 | 2023-04-18 |  |  | ضعف كفاءة المقاول الفنية |  | 38.2055 | 24.0107 | Failed | No
2100084604 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 65000000 | 3250000 | 56041665 | 56041665 | 3555000709 | لا | 0 | 180301000912 | جاري | منهجية القيمة المكتسبة | 84.31 | 100 | 2018-07-18 | 2021-07-16 | 2023-07-01 | 2023-07-01 |  |  |  |  | 38.1984 | 24.0177 | Failed | No
2100032115 | وزارة الموارد البشرية والتنمية الإجتماعية | تشييد | ذات اولوية منخفضة | 29850630.2 | 1492531.51 | 710498.53 | 710498.53 | 3400000500 | لا | 0 | 181109251636 | مسحوب | الكميات التي تم تركيبها | 5 | 100 | 2015-07-29 | 2018-06-25 | 2019-01-09 | 2019-01-09 |  |  | عدم وجود مبالغ في البنود تغطي الأعمال المرصودة |  | 41.0258 | 30.9783 | مسحوب | No
2100019353 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 67004346.72 | 3350217.336 | 59536199.39 | 59536199.39 | 2055014114 | لا | 0 | 180301000737 | جاري | منهجية القيمة المكتسبة | 90 | 100 | 2018-10-24 | 2021-08-31 | 2023-10-25 | 2023-10-25 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 49.6626 | 27.0037 | متأخر | No
2100105066 | وزارة الموارد البشرية والتنمية الإجتماعية | تشييد | ذات اولوية منخفضة | 16659133.81 | 832956.6905 | 12081773.15 | 12081773.15 | 5855010714 | لا | 0 | 190209043759 | جاري | الكميات التي تم تركيبها | 88 | 100 | 2016-02-01 | 2018-07-04 | 2023-05-03 | 2023-05-03 |  |  | ضعف كفاءة المقاول الفنية |  | 42.6032 | 16.8432 | Failed | No
2100037015 | أمانة / الباحة | تشييد | ذات اولوية عالية | 9390708 | 469535.4 | 8397378 | 8397378 | 4030159820 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-12-29 | 2022-05-26 | 2022-05-26 | 2022-05-26 | 2022-05-26 |  | ضعف كفاءة المقاول الفنية |  | 41.4825 | 19.6019 | منجز | No
2100094835 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 41939800 | 2096990 | 41939800 | 41489502 | 3555000709 | لا | 0 | 190409096455 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-03-14 | 2019-09-15 | 2022-12-31 | 2022-12-31 | 2019-09-15 |  | عدم وجود كوادر كافية في الجهه لادارة المشروع |  | 38.3629 | 23.9381 | منجز | No
2100007475 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 55748848.77 | 2787442.4385 | 51380565.28 | 51380565.28 | 2055006347 | لا | 0 | 180809049188 | جاري | منهجية القيمة المكتسبة | 93 | 100 | 2018-03-08 | 2020-03-05 | 2023-02-05 | 2023-02-05 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 49.6626 | 27.0037 | Failed | No
2100040320 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 490262000 | 24513100 | 379392133.17 | 379392133.17 | 2051001349 | لا | 0 | 180809058465 | جاري | منهجية القيمة المكتسبة | 98 | 100 | 2012-01-14 | 2014-12-13 | 2023-05-31 | 2023-05-31 |  |  | لا يوجد تأخير |  | 49.5648 | 27.1019 | Failed | No
2100204153 | جامعة الملك سعود | تشييد | ذات اولوية متوسطة | 990239.25 | 49511.9625 | 0 | 0 | 1010153678 | لا | 0 |  | جاري | تكلفة العمل المنجز | 84 | 100 | 2020-10-15 | 2021-07-15 | 2022-08-30 | 2022-08-30 |  |  |  |  | 46.6234 | 24.7117 | Failed | No
2100037262 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية | 96124085 | 4806204.25 | 37900210.76 | 37900210.76 | 5855002736 | لا | 0 | 181109301851 | جاري | منهجية القيمة المكتسبة | 46.37 | 100 | 2011-11-15 | 2013-10-24 | 2023-12-31 | 2023-12-31 |  |  | لا يوجد تأخير |  | 42.894 | 17.4395 | Failed | No
2100074712 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية عالية | 36978000 | 1848900 | 36978000 | 36978000 | 5850002600 | لا | 0 | 181101290881 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-10-30 | 2020-10-08 | 2020-12-30 | 2020-12-30 | 2020-10-08 |  | لا يوجد تأخير |  | 42.4989 | 18.2169 | منجز | No
2100059522 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 51655135 | 2582756.75 | 16254227.8 | 16254227.8 | 4030151328 | لا | 0 | 190501019049 | جاري | منهجية القيمة المكتسبة | 44.27 | 100 | 2019-10-17 | 2021-09-25 | 2022-09-25 | 2022-09-25 |  |  | لا يوجد تأخير |  | 41.3009 | 18.9873 | Failed | No
2100099433 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 3984995 | 199249.75 | 4113414.75 | 4113414.75 | 5950024761 | لا | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 98 | 100 | 2019-01-08 | 2020-08-01 | 2020-08-01 | 2020-08-01 |  |  | اخرى |  |  |  | Failed | No
2100106201 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 182304000 | 9115200 | 126605694.02 | 126605694.02 | 1010074413 | لا | 0 |  | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 99.5 | 100 | 2014-07-09 | 2017-07-09 | 2022-05-31 | 2022-05-31 |  |  | اخرى |  | 39.8921 | 21.3732 | متأخر | No
2100191074 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية وعاجلة | 19999358 | 999967.9 | 12401659 | 8883182.45 | 2050018730 | لا | 0 | 1912010180139 | جاري | منهجية القيمة المكتسبة | 75 | 99.96 | 2020-01-05 | 2021-01-04 | 2022-08-31 | 2022-08-31 |  |  |  |  | 42.5589 | 16.8984 | Failed | No
2100056232 | وزارة الصحة / حائل | تشييد | ذات اولوية عالية | 349990 | 17499.5 | 349990 | 349990 | 3350026255 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-12-24 | 2020-03-21 | 2020-06-10 | 2020-06-10 | 2020-03-21 |  | التنسيق مع أصحاب المصلحه (خدمات |  | 41.6983 | 27.5161 | منجز | No
2100084766 | الهيئة الملكية للجبيل وينبع / مدينة جازان للصناعات الأساسية والتحويلية | تشييد | ذات اولوية متوسطة | 37041752.81 | 1852087.6405 | 37013702.6 | 37013702.6 | 4700004138 | لا | 0 | 191001206649 | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 100 | 100 | 2020-03-11 | 2021-09-02 | 2022-03-14 | 2022-03-14 |  |  | اخرى |  | 42.3383 | 17.3349 | Failed | No
2100092131 | أمانة / نجران | تشييد | ذات اولوية عالية | 10886230 | 544311.5 | 170453.22 | 170453.22 | 5950018186 | لا | 0 | 200309019738 | جاري | تكلفة العمل المنجز | 9.13 | 14 | 2019-04-25 | 2023-10-09 | 2023-10-09 | 2023-10-09 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 44.2457 | 17.5953 | منتظم | No
2100045183 | أمانة / حائل | تشييد | ذات اولوية عالية وعاجلة | 22070025 | 1103501.25 | 22070025 | 22070025 | 1010069549 | لا | 0 | 190101007327 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-10-25 | 2021-08-17 | 2021-08-17 | 2021-08-17 | 2021-08-17 |  |  |  | 41.7025 | 27.4875 | منجز | No
2100042700 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 13999960 | 699998 | 517973 | 517973 | 4650034676 | لا | 0 | 4650034676 | مسحوب | منهجية القيمة المكتسبة | 13.49 | 100 | 2017-12-27 | 2019-06-12 | 2023-08-19 | 2023-08-19 |  |  | ضعف كفاءة المقاول الفنية |  | 39.0444 | 22.8072 | مسحوب | No
2100190212 | جامعة الملك فيصل | تشييد | ذات اولوية عالية وعاجلة | 47306428.52 | 2365321.426 | 32235126.44 | 16231997 | 1010208002 | لا | 0 | 180301000585 | جاري | الكميات التي تم تركيبها | 95 | 95 | 2018-10-11 | 2021-12-23 | 2021-12-24 | 2021-12-24 |  |  |  |  | 49.6026 | 25.3225 | منتظم | No
2100097484 | جامعة الملك فيصل | تشييد | ذات اولوية عالية | 1830000 | 91500 | 1830000 | 1830000 | 1010281596 | لا | 0 | 180909099629 | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2015-08-28 | 2016-06-27 | 2016-11-19 | 2016-11-19 |  | 2016-06-27 | تأخرصرف المستحقات المالية |  | 49.5604 | 25.3897 | منجز | No
2100106035 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية عالية | 18286270 | 914313.5 | 15374649 | 15374649 | 1010122914 | لا | 0 | 190201003356 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 99.85 | 2019-04-10 | 2021-09-12 | 2021-11-01 | 2021-11-01 | 2021-09-12 |  | لا يوجد تأخير |  | 42.7302 | 18.3003 | منجز | No
2100041720 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 17980310 | 899015.5 | 14041728 | 14041728 | 4030163532 | لا | 0 | 180909109612 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-02-07 | 2020-02-06 | 2022-12-29 | 2022-12-29 | 2020-02-06 |  | أوامر تغيير |  | 38.2253 | 24.0243 | منجز | No
2100040773 | وزارة الصحة/ الاحساء | تشييد | ذات اولوية عالية | 19683568 | 984178.4 | 19683568 | 19683568 | 7007567790 | لا | 0 | 180301001309 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 0 | 2019-10-22 | 2021-04-04 | 2021-08-03 | 2021-08-03 | 2021-04-04 |  | اخرى |  | 49.56 | 25.4095 | منجز | No
2100040062 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 46914144 | 2345707.2 | 44929402 | 44929402 | 1010136405 | لا | 0 | 180809056087 | جاري | منهجية القيمة المكتسبة | 99.82 | 100 | 2017-04-10 | 2019-03-29 | 2023-03-02 | 2023-03-02 |  |  | ضعف كفاءة المقاول الفنية |  | 38.291 | 23.9811 | متأخر | No
2100055646 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 439709000 | 21985450 | 385364853 | 373730882 | 1010157290 | لا | 0 | 180909088339 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 97 | 96.59 | 2017-10-16 | 2020-10-14 | 2023-04-25 | 2023-04-25 |  |  |  |  | 38.2469 | 24.0283 | منتظم | No
2100085912 | البريد السعودي | تشييد | ذات اولوية متوسطة | 95208663 | 4760433.15 | 35479137.2 | 35479137.2 | 1010153346 | لا | 0 |  | مسحوب | منهجية القيمة المكتسبة | 52 | 100 | 2013-05-11 | 2015-12-03 | 2018-05-31 | 2018-05-31 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6941 | 24.7559 | مسحوب | No
2100099304 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 12329174 | 616458.7 | 0 | 0 | 1010233904 | لا | 0 | 190309036022 | مسحوب | منهجية القيمة المكتسبة | 33 | 100 | 2012-12-15 | 2014-12-15 | 2023-09-17 | 2023-09-17 |  |  | ضعف كفاءة المقاول الفنية |  | 42.011 | 21.9079 | مسحوب | No
2100204326 | شركة المياه الوطنية / المنطقة الشرقية | إشراف | ذات اولوية عالية وعاجلة | 20445997.2 | 1022299.86 | 4649176.01 | 67321.9 | 7009104832 | لا | 0 | 210601036078 | جاري | التكلفة المفوترة | 32.6 | 44.17 | 2021-09-20 | 2022-09-19 | 2022-09-19 | 2022-09-19 |  |  |  |  | 50.1181 | 26.426 | خدمات عامة | No
2100094986 | وزارة الصحة / القريات | ترميم | ذات اولوية متوسطة | 2970303 | 148515.15 | 2051184.61 | 0 | 2050068940 | لا | 0 | 200509012975 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-07-13 | 2019-09-11 | 2021-04-07 | 2021-04-07 | 2019-09-11 |  | ضعف كفاءة المقاول الفنية |  | 37.9435 | 30.7389 | منجز | Yes
2100014766 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 1978679 | 98933.95 | 2079951.77 | 2079951.77 | 4603001574 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 95 | 90 | 2019-04-18 | 2021-03-26 | 2021-06-17 | 2021-06-17 | 2021-03-26 |  | ضعف كفاءة المقاول الفنية |  | 41.3868 | 18.755 | منجز | No
2100034274 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 4958006 | 247900.3 | 5194101.51 | 5194101.51 | 4030006066 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-05-29 | 2021-05-06 | 2021-05-05 | 2021-05-05 | 2021-05-06 |  | ضعف كفاءة المقاول الفنية |  | 41.3872 | 18.7702 | منجز | No
2100030295 | أمانة / تبوك | تشييد | ذات اولوية عالية وعاجلة | 496650 | 24832.5 | 496650 | 496650 | 4650050668 | لا | 0 | 200309001528 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2020-02-24 | 2020-06-23 | 2020-06-24 | 2020-06-24 | 2020-06-23 |  | ضعف كفاءة المقاول الفنية |  | 36.5499 | 28.3759 | منجز | No
2100101426 | أمانة / تبوك | تشييد | ذات اولوية عالية وعاجلة | 104047000 | 5202350 | 98176286.76 | 98176286.76 | 3550021826 | لا | 0 | 181109263246 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-10-28 | 2020-12-17 | 2020-02-25 | 2020-02-25 | 2020-12-17 |  | ضعف كفاءة المقاول الفنية |  | 36.5467 | 28.3821 | منجز | No
2100071330 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 873332 | 43666.6 | 349382.25 | 349382.25 | 4650032626 | لا | 0 | 191101167880 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 91.5 | 100 | 2019-06-30 | 2020-06-24 | 2021-06-25 | 2021-06-25 | 2020-06-24 |  | ضعف كفاءة المقاول الفنية |  | 37.2651 | 25.05 | منجز | No
2100017986 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 686490 | 34324.5 | 584500 | 584500 | 4700010229 | لا | 0 | 190409036685 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-12-19 | 2020-03-18 | 2020-03-19 | 2020-03-19 | 2020-03-18 |  | ضعف كفاءة المقاول الفنية |  | 37.2651 | 25.05 | منجز | No
2100018270 | أمانة / جدة | إشراف | ذات اولوية عالية | 67879538 | 3393976.9 | 55000968.27 | 51184922 | 1010427119 | لا | 0 | 190701042902 | جاري | مدفوعات ساعات العمل | 93.5 | 96.7 | 2019-10-07 | 2022-10-06 | 2023-02-09 | 2023-02-09 |  |  | اخرى |  | 39.1985 | 21.4866 | خدمات عامة | No
2100085772 | وزارة المالية - الحرمين | تشييد | ذات اولوية عالية | 915731465 | 176522219 | 708985542.49 | 708985542.49 | 1010340672 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 98.85 | 100 | 2014-05-01 | 2015-06-30 | 2022-07-30 | 2022-07-30 | 2015-06-30 |  | اخرى |  | 39.5639 | 24.4942 | منجز | No
2100047353 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 2185950 | 109297.5 | 2142952.5 | 2142952.5 | 3552000023 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-12-30 | 2016-12-24 | 2016-12-25 | 2016-12-25 | 2016-12-24 |  | اخرى |  | 36.4689 | 26.2366 | منجز | No
2100032130 | أمانة / جدة | تشييد | ذات اولوية عالية | 65440672 | 3272033.6 | 53260962.27 | 47676155.36 | 4030141919 | لا | 0 | 190701167385 | جاري | تكلفة العمل المنجز | 94.02 | 100 | 2019-11-03 | 2021-10-11 | 2022-05-21 | 2022-05-21 |  |  | اخرى |  | 39.2264 | 21.5085 | متأخر | No
2100054880 | أمانة / جدة | تشييد | ذات اولوية عالية | 67833150 | 3391657.5 | 57894646.62 | 50064962.16 | 4030141919 | لا | 0 | 190801131230 | جاري | تكلفة العمل المنجز | 95 | 100 | 2019-11-05 | 2021-10-13 | 2022-06-13 | 2022-06-13 |  |  | اخرى |  | 39.1782 | 21.5265 | متأخر | No
2100082294 | أمانة / جدة | تشييد | ذات اولوية عالية | 62984549 | 3149227.45 | 56015382.59 | 53287910.11 | 4030148791 | لا | 0 | 190701167754 | ايقاف جزئي | تكلفة العمل المنجز | 95.5 | 100 | 2019-11-03 | 2021-10-11 | 2022-02-23 | 2022-02-23 |  |  | أوامر تغيير |  | 39.1566 | 21.5452 | Failed | No
2100082213 | أمانة / جدة | تشييد | ذات اولوية عالية وعاجلة | 28874396 | 1443719.8 | 22001343.85 | 18329968.85 | 1010346559 | لا | 0 | 190401098206 | جاري | اخرى | 86 | 86 | 2019-07-15 | 2022-06-11 | 2022-06-11 | 2022-06-11 |  |  | اخرى |  | 39.1735 | 21.573 | متأخر | No
2100086063 | وزارة المالية - الحرمين | تشييد | ذات اولوية عالية وعاجلة | 30750000000 | 26250000000 | 4527024589 | 4527024589 | 4030068284 | لا | 0 |  | ايقاف جزئي | تكلفة العمل المنجز | 11 | 100 | 2014-01-21 | 2018-01-20 | 2027-12-31 | 2027-12-31 |  |  | اخرى |  | 39.6005 | 24.4595 | Failed | No
2100093310 | أمانة / جدة | تشييد | ذات اولوية عالية | 14241743 | 712087.15 | 8227949 | 8222230 | 4030176726 | لا | 0 | 190801065923 | جاري | الكميات التي تم تركيبها | 85 | 87 | 2019-10-27 | 2021-10-04 | 2023-05-12 | 2023-05-12 |  |  | اخرى |  | 39.1902 | 21.5316 | منتظم | No
2100021626 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 1034775.21 | 51738.7605 | 1034775.21 | 1034775.21 | 4030237556 | لا | 0 | 181109339991 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-09-27 | 2020-03-11 | 2020-03-10 | 2020-03-10 | 2020-03-11 |  | ضعف كفاءة المقاول الفنية |  | 41.4279 | 19.2858 | منجز | No
2100207966 | الهيئة العامة للطيران المدني | تشييد | ذات اولوية عالية وعاجلة | 22968855 | 1148442.75 | 7336819.84 | 7336819.84 | 4030276223 | لا | 0 | 190601025531 | جاري | تكلفة العمل المنجز | 1.47 | 28.54 | 2020-06-03 | 2022-06-02 | 2022-06-02 | 2022-06-02 |  |  |  |  | 41.64 | 20.2942 | Failed | No
2100006064 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية وعاجلة | 72537979 | 3626898.95 | 51049066.11 | 51049066.11 | 2050022550 | لا | 0 | 181109337692 | مسحوب | منهجية القيمة المكتسبة | 72.48 | 100 | 2012-01-07 | 2014-12-05 | 2024-12-31 | 2024-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 41.2405 | 19.951 | مسحوب | No
2100087264 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية وعاجلة | 30000000 | 1500000 | 25948747.63 | 25948747.63 | 4031045263 | لا | 0 | 181001213164 | جاري | منهجية القيمة المكتسبة | 95.93 | 99.99 | 2019-07-04 | 2022-05-31 | 2022-09-29 | 2022-09-29 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0776 | 20.2043 | منتظم | No
2100092680 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 2055565 | 102778.25 | 2055565 | 1942052.59 | 5864048850 | لا | 0 | 190909192263 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-06-16 | 2020-11-27 | 2021-02-26 | 2021-02-26 | 2020-11-27 |  | ضعف كفاءة المقاول الفنية |  | 41.8402 | 19.266 | منجز | No
2100008794 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية وعاجلة | 373141215.85 | 18657060.7925 | 330070987.86 | 330070987.86 | 1010004739 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 99.9 | 100 | 2016-10-20 | 2018-10-30 | 2021-04-30 | 2021-04-30 | 2018-10-30 | [5 empty] | منجز | No
2100078013 | شركة الكهرباء | تشييد | ذات اولوية متوسطة | 48091341 | 2404567.05 | 24124239 | 24124239 | 1010063866 | لا | 0 |  | ايقاف كلي | اخرى | 49.1 | 100 | 2018-05-28 | 2020-08-27 | 2020-08-27 | 2020-08-27 |  |  | اخرى |  | 46.6843 | 24.9095 | Failed | No
2100066710 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 5261230 | 263061.5 | 4586264 | 2889296 | 4030170755 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 57 | 100 | 2014-12-23 | 2016-11-28 | 2021-10-02 | 2021-10-02 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.1811 | 21.4913 | مسحوب | No
2100207970 | الهيئة العامة للطيران المدني | إشراف | ذات اولوية عالية | 385742571 | 19287128.55 | 313610659.19 | 292751694.96 | 2051011487 | لا | 0 | 190409080422 | جاري | تكلفة العمل المنجز | 89.2 | 94.9 | 2013-03-31 | 2022-02-28 | 2023-12-31 | 2023-12-31 |  |  |  |  | 46.7011 | 24.9611 | خدمات عامة | No
2100031743 | وزارة الداخلية / المديرية العامة للدفاع المدني | تشييد | ذات اولوية عالية | 1532216.57 | 76610.8285 | 1130577.59 | 1130577.59 | 3350009542 | لا | 0 | 200309064043 | جاري | الكميات التي تم تركيبها | 74 | 100 | 2019-12-31 | 2021-02-16 | 2023-02-17 | 2023-02-17 |  |  | تأخرصرف المستحقات المالية |  | 41.7341 | 27.4498 | Failed | No
2100011270 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | تشييد | ذات اولوية عالية | 72273097.52 | 3613654.876 | 0 | 0 | 1010006362 | لا | 0 | 180533315033 | مسحوب | تكلفة العمل المنجز | 36.05 | 100 | 2015-05-17 | 2015-05-27 | 2025-05-31 | 2025-05-31 |  |  | ضعف كفاءة المقاول الفنية |  | 42.7302 | 18.3003 | مسحوب | No
2100208014 | الهيئة العامة للطيران المدني | إشراف | ذات اولوية عالية وعاجلة | 22049509.06 | 1102475.453 | 21006473.71 | 21006473.71 | 4030233884 | لا | 0 | 190909121831 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-06-25 | 2019-04-12 | 2019-04-12 | 2019-04-12 |  |  |  |  | 41.1369 | 30.9034 | Failed | No
2100060852 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية عالية | 22962465 | 1148123.25 | 22863668.93 | 22863668.93 | 5855015373 | لا | 0 | 181201450757 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 98.46 | 2019-02-24 | 2021-07-29 | 2021-04-14 | 2021-04-14 |  | 2021-07-29 | لا يوجد تأخير |  | 42.7302 | 18.3003 | منجز | No
2100006554 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 25657132.2 | 1282856.61 | 24271498.9 | 24271498.9 | 2050056172 | لا | 0 | 181201390158 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 99.33 | 100 | 2019-03-03 | 2021-03-04 | 2021-02-24 | 2021-02-24 |  | 2021-03-04 | لا يوجد تأخير |  | 48.4909 | 28.4458 | منجز | No
2100001595 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية وعاجلة | 244727684 | 12236384.2 | 75382122.52 | 75382122.52 | 1010076961 | لا | 0 | 180901104414 | جاري | منهجية القيمة المكتسبة | 45.35 | 100 | 2019-01-23 | 2021-12-21 | 2022-06-30 | 2022-06-30 |  |  | لا يوجد تأخير |  | 49.6363 | 25.3631 | Failed | No
2100089880 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 13696928 | 684846.4 | 13484955.72 | 11829542.26 | 1010166750 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-06-12 | 2020-06-12 | 2020-08-16 | 2020-08-16 |  | 2020-06-12 | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100191553 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية وعاجلة | 172800000 | 8640000 | 106945935.09 | 81282670.97 | 1010012911 | نعم | 153645089 |  | جاري | منهجية القيمة المكتسبة | 75.85 | 89.33 | 2021-03-18 | 2022-05-19 | 2022-12-30 | 2022-12-30 |  |  |  |  | 46.4794 | 25.0648 | متأخر | No
2100087275 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 129177126.5 | 6458856.325 | 100086381.05 | 100086381.05 | 4030235564 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 92.78 | 100 | 2010-12-07 | 2013-03-07 | 2020-02-27 | 2020-02-27 |  | 2013-03-07 | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100080113 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 2694900 | 134745 | 2481846.5 | 2212161.2 | 1010249593 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 92.65 | 100 | 2019-12-17 | 2020-06-17 | 2020-08-19 | 2020-08-19 |  | 2020-06-17 | أوامر تغيير |  | 46.7098 | 24.6275 | منجز | No
2100087253 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 4200000 | 210000 | 4174991.75 | 4174991.75 | 1010244536 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-09-25 | 2019-09-04 | 2019-09-04 | 2019-09-04 |  | 2019-09-04 | لا يوجد تأخير |  | 48.4478 | 27.5085 | منجز | No
2100096983 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 28628000 | 1431400 | 28589792.1 | 25715121.35 | 1010227442 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 99.87 | 68.42 | 2019-05-05 | 2021-05-05 | 2020-08-26 | 2020-08-26 |  | 2021-05-05 | لا يوجد تأخير |  | 46.3543 | 24.4828 | منجز | No
2100023391 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 27145643.14 | 1357282.157 | 24047604.95 | 24047604.95 | 2050003475 | لا | 0 | 180709030736 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 97.84 | 100 | 2016-05-24 | 2017-11-06 | 2021-08-19 | 2021-08-19 | 2017-11-06 |  | لا يوجد تأخير |  | 49.9891 | 26.5396 | منجز | No
2100039045 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 69999907 | 3499995.35 | 62871002.67 | 62871002.67 | 1010085982 | لا | 0 | 181101244513 | جاري | منهجية القيمة المكتسبة | 93.01 | 100 | 2019-01-17 | 2022-01-18 | 2022-02-28 | 2022-02-28 |  |  | اخرى |  | 50.1504 | 26.3457 | متأخر | No
2100087581 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 16805962.95 | 840298.1475 | 12349638.57 | 12349638.57 | 1010327797 | لا | 0 | 180809053045 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 93.56 | 100 | 2015-05-07 | 2018-04-04 | 2020-07-22 | 2020-07-22 | 2018-04-04 |  | لا يوجد تأخير |  | 44.9488 | 26.0491 | منجز | No
2100089913 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات الجوية | تشييد | ذات اولوية متوسطة | 4980066 | 249003.3 | 332138 | 332138 | 1010214056 | لا | 0 |  | ايقاف جزئي | الكميات التي تم تركيبها | 36 | 100 | 2018-06-27 | 2020-01-08 | 2022-06-30 | 2022-06-30 |  |  | ضعف كفاءة المقاول الفنية |  | 45.9734 | 28.3641 | Failed | No
2100047913 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 3724000 | 186200 | 2836240 | 2836240 | 5950011531 | لا | 0 | 200309041522 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 90 | 95 | 2019-06-23 | 2020-02-13 | 2021-03-23 | 2021-03-23 | 2020-02-13 |  | اخرى |  | 44.1884 | 17.6087 | منجز | No
2100194390 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 2654080 | 132704 | 2460217.51 | 2460217.51 | 4030152625 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-01-16 | 2021-06-30 | 2021-10-26 | 2021-10-26 | 2021-06-30 |  |  |  | 41.8346 | 19.4414 | منجز | No
2100205612 | وزارة الثقافة | تصميم وإشراف | ذات اولوية عالية | 18947368.42 | 947368.421 | 0 | 0 | 0 | لا | 0 |  | جاري | تكلفة العمل المنجز | 80 | 80 | 2021-04-08 | 2022-02-08 | 2022-02-08 | 2022-02-08 |  |  |  |  | 46.6534 | 24.6382 | منتظم | No
2100064676 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 10000 | 500 | 0 | 0 | 1117002589 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 67 | 28 | 2019-06-13 | 2020-11-25 | 2020-11-26 | 2020-11-26 |  |  |  |  | 46.1418 | 24.6003 | Failed | No
2100100096 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 9287394 | 464369.7 | 5179413.65 | 5179413.65 | 1010183010 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2013-03-29 | 2015-03-20 | 2020-01-09 | 2020-01-09 | 2015-03-20 |  | ضعف كفاءة المقاول الفنية |  | 41.0165 | 30.9619 | منجز | No
2100087986 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 20547776 | 1027388.8 | 12873379.92 | 12873379.92 | 1010142553 | لا | 0 |  | جاري | التكلفة المفوترة | 88 | 100 | 2012-02-28 | 2013-10-10 | 2023-05-24 | 2023-05-24 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | Failed | No
2100205623 | وزارة الثقافة | تصميم وتشييد | ذات اولوية عالية | 22886610 | 1144330.5 | 22886610 | 22886610 | 1010298707 | لا | 0 |  | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2021-09-01 | 2022-01-30 | 2022-04-15 | 2022-04-15 | 2022-01-30 | 2022-04-15 |  |  | 39.1633 | 21.4981 | منجز | No
2100047084 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 3844089 | 192204.45 | 3844089 | 3844089 | 4031046917 | لا | 0 | 190509061520 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-12-03 | 2019-05-24 | 2019-05-24 | 2019-05-24 | 2019-05-24 |  | ضعف كفاءة المقاول الفنية |  | 42.0197 | 21.9158 | منجز | No
2100034300 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية عالية | 80318001.75 | 4015900.0875 | 72478200.04 | 72478200.04 | 4031032312 | لا | 0 |  | جاري | تكلفة العمل المنجز | 90 | 90 | 2016-01-17 | 2019-01-16 | 2022-12-29 | 2022-12-29 |  |  | اخرى |  | 39.8716 | 21.363 | منتظم | No
2100205660 | وزارة الثقافة | تصميم وتشييد | ذات اولوية عالية | 22433840.98 | 1121692.049 | 22433840.98 | 22433840.98 | 1010402149 | لا | 0 |  | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2021-08-25 | 2021-11-14 | 2022-01-30 | 2022-01-30 | 2021-11-14 | 2021-11-14 |  |  | 46.6745 | 24.693 | منجز | No
2100023833 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3637490 | 181874.5 | 0 | 0 | 1010261575 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 1 | 36 | 2019-02-17 | 2021-02-06 | 2020-02-16 | 2020-02-16 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6878 | 24.7094 | مسحوب | No
2100047526 | أمانة / عسير | تشييد | ذات اولوية عالية | 999900 | 49995 | 888390 | 888390 | 5859004244 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 88 | 100 | 2013-01-19 | 2016-02-28 | 2017-12-31 | 2017-12-31 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | مسحوب | No
2100016391 | جامعة الملك خالد | تشييد | ذات اولوية عالية وعاجلة | 99368763.12 | 4968438.156 | 85612012.43 | 78987234.13 | 1010219886 | لا | 0 | 180801037549 | جاري | تكلفة العمل المنجز | 100 | 100 | 2019-01-24 | 2021-01-13 | 2023-04-23 | 2023-04-23 |  |  | تأخرصرف المستحقات المالية |  | 42.8114 | 18.1027 | منتظم | No
2100044785 | أمانة / عسير | تشييد | ذات اولوية عالية | 8699665 | 434983.25 | 1509676.6 | 0 | 5852002774 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 37 | 100 | 2018-04-29 | 2019-04-24 | 2021-05-06 | 2021-05-06 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | مسحوب | Yes
2100026784 | أمانة / عسير | تشييد | ذات اولوية عالية | 1548654 | 77432.7 | 1316190 | 1316190 | 5855035453 | لا | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 42 | 100 | 2012-08-31 | 2023-04-04 | 2023-04-04 | 2023-04-04 |  |  | أوامر سامية |  | 42.673 | 18.5826 | Failed | No
2100027226 | أمانة / عسير | تشييد | ذات اولوية عالية | 6171660 | 308583 | 0 | 0 | 5852002774 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 30 | 100 | 2019-01-06 | 2020-01-01 | 2022-01-01 | 2022-01-01 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | مسحوب | No
2100052452 | أمانة / عسير | تشييد | ذات اولوية عالية | 1042216 | 52110.8 | 410095 | 388765 | 5859002286 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 40 | 100 | 2015-10-24 | 2016-10-17 | 2021-05-01 | 2021-05-01 |  |  | تأخرصرف المستحقات المالية |  |  |  | مسحوب | No
2100065656 | أمانة / عسير | تشييد | ذات اولوية عالية | 6447300 | 322365 | 967095 | 967095 | 5851002846 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 20 | 100 | 2011-06-25 | 2012-12-16 | 2021-09-15 | 2021-09-15 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | مسحوب | No
2100013344 | أمانة / عسير | تشييد | ذات اولوية عالية | 3994046 | 199702.3 | 0 | 0 | 5855039650 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 60 | 100 | 2015-01-17 | 2016-01-12 | 2022-12-31 | 2022-12-31 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | مسحوب | No
2100019143 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 15113935.56 | 755696.778 | 12741233.56 | 12741233.56 | 7001681225 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2012-06-08 | 2014-05-29 | 2017-12-28 | 2017-12-28 | 2014-05-29 |  | ضعف كفاءة المقاول الفنية |  | 42.4987 | 18.2178 | منجز | No
2100049405 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 750435.4 | 37521.77 | 0 | 0 | 5852002001 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0 | 100 | 2010-04-30 | 2010-12-26 | 2023-03-08 | 2023-03-08 |  |  | ضعف كفاءة المقاول الفنية |  | 42.4987 | 18.2178 | مسحوب | No
2100071433 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 14512495.7 | 725624.785 | 8654110.38 | 8654110.38 | 7001681225 | لا | 0 | 190209028123 | فسخ العقد | التكلفة المفوترة | 65 | 100 | 2012-04-13 | 2014-01-03 | 2022-08-18 | 2022-08-18 |  |  | ضعف كفاءة المقاول الفنية |  | 42.4987 | 18.2178 | مسحوب | No
2100009785 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | تشييد | ذات اولوية عالية وعاجلة | 151608021.69 | 7580401.0845 | 132344210.67 | 95526536 | 1010318930 | لا | 0 | 190101004905 | جاري | تكلفة العمل المنجز | 93.85 | 100 | 2019-03-10 | 2022-12-23 | 2023-06-25 | 2023-06-25 |  |  | اخرى |  | 42.7302 | 18.3003 | متأخر | No
2100107332 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1831040.58 | 91552.029 | 1674181.25 | 1130643.74 | 5851003033 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2019-03-18 | 2020-05-11 | 2020-05-11 | 2020-05-11 | 2020-05-11 |  | ضعف كفاءة المقاول الفنية |  | 42.1351 | 19.1255 | منجز | No
2100107671 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 4986799 | 249339.95 | 370303.4 | 370303.4 | 5855018218 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 10 | 100 | 2015-11-22 | 2017-08-13 | 2022-06-14 | 2022-06-14 |  |  | ضعف كفاءة المقاول الفنية |  | 42.0529 | 18.5228 | مسحوب | No
2100107026 | وزارة التعليم | تشييد | ذات اولوية عالية | 1767505 | 88375.25 | 114580 | 114580 | 5855018218 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 11.5 | 100 | 2015-07-28 | 2016-06-12 | 2022-12-30 | 2022-12-30 |  |  | ضعف كفاءة المقاول الفنية |  | 42.0529 | 18.5228 | مسحوب | No
2100018793 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2150652.38 | 107532.619 | 1029239 | 1029039 | 5864037186 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-04-21 | 2016-04-15 | 2021-09-21 | 2021-09-21 | 2016-04-15 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.0529 | 18.5228 | منجز | No
2100103213 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 4098960.39 | 204948.0195 | 846182.48 | 539954.97 | 1010237336 | لا | 0 |  | مسحوب | التكلفة المفوترة | 21 | 100 | 2014-06-12 | 2015-09-04 | 2023-02-03 | 2023-02-03 |  |  | ضعف كفاءة المقاول الفنية |  | 41.4779 | 20.0185 | مسحوب | No
2100041296 | أمانة / جدة | دراسات هندسية | ذات اولوية عالية | 13749950 | 687497.5 | 13749950 | 13749950 | 1010308543 | لا | 0 | 181001179458 | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2019-01-22 | 2020-07-06 | 2020-07-06 | 2020-07-06 | 2020-07-06 | 2022-04-04 | اخرى |  | 39.1715 | 21.5049 | منجز | No
2100105313 | جامعة الباحة | تشييد | ذات اولوية متوسطة | 3145500 | 157275 | 1519643 | 1519643 | 1010212242 | لا | 0 | 190409056636 | جاري | الكميات التي تم تركيبها | 100 | 100 | 2016-04-06 | 2016-07-13 | 2021-12-31 | 2021-12-31 |  |  |  |  | 21.9422 | 60.1881 | Failed | No
2100107693 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 16361834.38 | 818091.719 | 14680912.62 | 0 | 5800000826 | لا | 0 | 190209015819 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2013-04-13 | 2015-04-03 | 2021-12-08 | 2021-12-08 | 2015-04-03 |  | ضعف كفاءة المقاول الفنية |  | 41.4779 | 20.0185 | منجز | Yes
2100195462 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 900000 | 45000 | 900000 | 900000 | 1010335499 | لا | 0 |  | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-12-21 | 2021-06-21 | 2021-06-21 | 2021-06-21 |  |  |  |  | 45.9675 | 28.4019 | Failed | No
2100013451 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 2597845 | 129892.25 | 498028 | 0 | 4032029329 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 30 | 100 | 2015-06-14 | 2020-06-13 | 2022-06-30 | 2022-06-30 |  |  | تأخرصرف المستحقات المالية |  | 40.8308 | 20.7251 | مسحوب | Yes
2100001783 | جامعة الملك فيصل | دراسات هندسية | ذات اولوية عالية | 383500 | 19175 | 325975 | 325975 | 1010423886 | لا | 0 | 180809056141 | ايقاف جزئي | تكلفة العمل المنجز | 95 | 5 | 2013-06-12 | 2015-05-21 | 2023-05-21 | 2023-05-21 |  |  | تأخرصرف المستحقات المالية |  | 49.5995 | 25.3404 | Failed | No
2100193631 | وزارة الحرس الوطني / الشؤون الفنية بالقطاع الشرقي | توريد وتركيب | ذات اولوية عالية | 39989060.88 | 1999453.044 | 35188798.84 | 30226794.91 | 1010277064 | لا | 0 | 180501005815 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-12-25 | 2022-02-28 | 2022-05-15 | 2022-05-15 | 2022-02-28 |  |  |  | 50.1576 | 26.3775 | منجز | No
2100093936 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية وعاجلة | 13798500 | 689925 | 12158632 | 12158632 | 2060010281 | لا | 0 | 180809053989 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 98.87 | 100 | 2017-12-11 | 2019-12-11 | 2021-01-21 | 2021-01-21 | 2019-12-11 |  | لا يوجد تأخير |  | 49.5635 | 25.6096 | منجز | No
2100055576 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 300348218.47 | 15017410.9235 | 164481824.89 | 164481824.89 | 2050027415 | لا | 0 | 180809049251 | جاري | منهجية القيمة المكتسبة | 51 | 93 | 2017-06-06 | 2020-06-02 | 2024-06-30 | 2024-06-30 |  |  | عدم وجود كوادر كافية في الجهه لادارة المشروع |  | 49.5648 | 27.1019 | Failed | No
2100001794 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 244228931.53 | 12211446.5765 | 193476559.514 | 193476559.514 | 1010008118 | لا | 0 | 180809058645 | جاري | منهجية القيمة المكتسبة | 94 | 100 | 2013-11-06 | 2016-05-04 | 2023-07-14 | 2023-07-14 |  |  | أوامر تغيير |  | 49.5648 | 27.1019 | متأخر | No
2100004233 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 49662799 | 2483139.95 | 45780324.12 | 45780324.12 | 2062006978 | لا | 0 | 181001178102 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-01-16 | 2022-01-12 | 2023-10-26 | 2023-10-26 |  |  | لا يوجد تأخير |  | 49.6626 | 27.0037 | منتظم | No
2100049136 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 173747366.58 | 8687368.329 | 154698644.65 | 154698644.65 | 1010135922 | لا | 0 | 180809049511 | جاري | منهجية القيمة المكتسبة | 91 | 93 | 2018-01-10 | 2020-08-19 | 2023-09-03 | 2023-09-03 |  |  | عدم وجود كوادر كافية في الجهه لادارة المشروع |  | 49.6626 | 27.0037 | متأخر | No
2100010404 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 155410731 | 7770536.55 | 146206965.95 | 146206965.95 | 2060024520 | لا | 0 | 181201462203 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-02-11 | 2022-02-07 | 2023-12-15 | 2023-12-15 |  |  | لا يوجد تأخير |  | 49.6626 | 27.0037 | منتظم | No
2100086833 | جامعة الملك فيصل | تشييد | ذات اولوية متوسطة | 50001144.15 | 2500057.2075 | 40546340.38 | 40546340 | 4030032844 | لا | 0 | 180809040384 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2017-01-15 | 2017-10-14 | 2018-11-24 | 2018-11-24 |  |  | تأخرصرف المستحقات المالية |  | 49.5604 | 25.3897 | Failed | No
2100007954 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 19237310.4 | 961865.52 | 3436308.81 | 0.01 | 2050010484 | لا | 0 |  | مسحوب | التكلفة المفوترة | 27 | 100 | 2013-07-02 | 2015-09-20 | 2015-09-20 | 2015-09-20 |  |  | ضعف كفاءة المقاول الفنية |  | 50.5 | 26.3646 | مسحوب | No
2100079365 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 3434678.5 | 171733.925 | 1474736 | 1474735.5 | 2050052248 | لا | 0 |  | مسحوب | التكلفة المفوترة | 47 | 98 | 2016-09-29 | 2017-09-24 | 2019-10-27 | 2019-10-27 |  |  | ضعف كفاءة المقاول الفنية |  | 48.7241 | 27.8719 | مسحوب | No
2100012073 | وزارة التعليم | تشييد | ذات اولوية عالية | 43998647.88 | 2199932.394 | 48357505.73 | 0 | 1010219247 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-04-20 | 2017-01-29 | 2019-11-06 | 2019-11-06 | 2017-01-29 |  |  |  | 50.5481 | 26.3765 | منجز | Yes
2100008540 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 10187883.03 | 509394.1515 | 10187883.03 | 7284602.69 | 2251021202 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-08-03 | 2016-08-03 | 2019-03-10 | 2019-03-10 | 2016-08-03 |  | تأخرصرف المستحقات المالية |  | 50.0738 | 25.9241 | منجز | No
2100020333 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 2097960 | 104898 | 2097960 | 2097960 | 2511104587 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2019-11-13 | 2020-06-13 | 2020-09-01 | 2020-09-01 | 2020-06-13 |  |  |  | 26.3204 | 50.1431 | منجز | No
2100104580 | جامعة الملك فيصل | تشييد | ذات اولوية عالية | 339455077.36 | 16972753.868 | 96207079.03 | 96207079.03 | 2055002293 | لا | 0 | 181009122304 | جاري | تكلفة العمل المنجز | 32 | 68 | 2014-05-01 | 2017-04-29 | 2023-08-29 | 2023-08-29 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5604 | 25.3897 | Failed | No
2100103854 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 20000000 | 1000000 | 2823786.61 | 2823786.61 | 2050010484 | لا | 0 |  | مسحوب | التكلفة المفوترة | 23 | 100 | 2013-07-02 | 2015-09-20 | 2017-06-21 | 2017-06-21 |  |  | ضعف كفاءة المقاول الفنية |  | 50.5058 | 26.3619 | مسحوب | No
2100104101 | وزارة التعليم | تشييد | ذات اولوية عالية | 10198933 | 509946.65 | 1826249.2 | 1826249.2 | 2055002421 | لا | 0 |  | مسحوب | التكلفة المفوترة | 20 | 100 | 2015-01-26 | 2017-01-15 | 2018-08-07 | 2018-08-07 |  |  | ضعف كفاءة المقاول الفنية |  | 45.975 | 28.4334 | مسحوب | No
2100005526 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2806810 | 140340.5 | 1961003.34 | 1961003.34 | 2050031834 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-12-31 | 2016-03-24 | 2019-04-03 | 2019-04-03 | 2016-03-24 |  |  |  | 49.5604 | 25.3897 | منجز | No
2100000980 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 7531608.23 | 376580.4115 | 3145804.27 | 3145804.27 | 2031040463 | لا | 0 |  | مسحوب | التكلفة المفوترة | 49 | 100 | 2012-09-23 | 2014-09-13 | 2014-09-13 | 2014-09-13 |  |  | ضعف كفاءة المقاول الفنية |  | 45.975 | 28.4334 | مسحوب | No
2100090311 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 15029225.43 | 751461.2715 | 15029225.43 | 11204154 | 2050237610 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2016-11-30 | 2018-11-20 | 2020-02-13 | 2020-02-13 | 2018-11-20 |  | ضعف كفاءة المقاول الفنية |  | 50.4933 | 26.5657 | منجز | No
2100005950 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 6500000 | 325000 | 402345.1 | 0.01 | 1010836770 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 6 | 100 | 2011-03-28 | 2012-11-16 | 2012-11-06 | 2012-11-06 |  |  | ضعف كفاءة المقاول الفنية |  | 47.5107 | 27.0157 | مسحوب | No
2100009284 | الجمارك السعودية | تشييد | ذات اولوية عالية | 9600000 | 480000 | 7064439.89 | 7064439.89 | 1010093247 | لا | 0 | 200701115505 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-02-25 | 2020-06-22 | 2020-06-22 | 2020-06-22 | 2020-06-22 |  | تصاريح أعمال التنفيذ |  | 51.5226 | 24.1624 | منجز | No
2100096935 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 8865666.6 | 443283.33 | 6019771.95 | 0 | 1010090099 | لا | 0 |  | مسحوب | التكلفة المفوترة | 75 | 100 | 2013-12-22 | 2015-12-18 | 2015-09-13 | 2015-09-13 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5604 | 25.3897 | مسحوب | Yes
2100091383 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 1677317 | 83865.85 | 1333060.34 | 1333060.34 | 2511482400 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2013-06-11 | 2014-05-07 | 2020-10-21 | 2020-10-21 | 2014-05-07 |  | ضعف كفاءة المقاول الفنية |  | 45.975 | 28.4334 | منجز | No
2100088616 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 9191307 | 459565.35 | 1676542.502 | 3398.681 | 2050030703 | لا | 0 |  | جاري | التكلفة المفوترة | 69 | 100 | 2019-03-30 | 2021-03-19 | 2022-05-15 | 2022-05-15 |  |  | ضعف كفاءة المقاول الفنية |  | 50.3999 | 26.3618 | Failed | No
2100059113 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 14021537.78 | 701076.889 | 2260123.2 | 0.01 | 1116004360 | لا | 0 |  | مسحوب | التكلفة المفوترة | 35 | 100 | 2012-11-19 | 2015-04-16 | 2020-12-01 | 2020-12-01 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5604 | 25.3897 | مسحوب | No
2100029013 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 9847416.21 | 492370.8105 | 9847416.21 | 9847416.21 | 4031045075 | لا | 0 | 180809055704 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2017-10-21 | 2018-10-21 | 2018-10-21 | 2018-10-21 | 2018-10-21 |  |  |  | 40.4236 | 21.2354 | منجز | No
2100097230 | جامعة الملك فيصل | تشييد | ذات اولوية عالية | 286402989.95 | 14320149.4975 | 69064766.93 | 69064766.93 | 2055002293 | لا | 0 | 181009122389 | مسحوب | تكلفة العمل المنجز | 25 | 75 | 2014-05-13 | 2017-04-09 | 2020-11-21 | 2020-11-21 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5604 | 25.3897 | مسحوب | No
2100092256 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 1659650.15 | 82982.5075 | 829651.44 | 0.01 | 2511482400 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2013-06-11 | 2014-05-07 | 2021-10-11 | 2021-10-11 | 2014-05-07 |  | ضعف كفاءة المقاول الفنية |  | 45.975 | 28.4334 | منجز | No
2100002376 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1662098.25 | 83104.9125 | 926358 | 926358 | 2511482400 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 60 | 100 | 2013-06-11 | 2014-04-30 | 2020-08-15 | 2020-08-15 | 2014-04-30 |  | ضعف كفاءة المقاول الفنية |  | 45.975 | 28.4334 | منجز | No
2100103902 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 19842230 | 992111.5 | 9977748 | 9638133 | 2050017509 | لا | 0 |  | مسحوب | التكلفة المفوترة | 39 | 100 | 2011-02-09 | 2013-01-19 | 2013-01-29 | 2013-01-29 |  |  | ضعف كفاءة المقاول الفنية |  | 48.962 | 27.4688 | مسحوب | No
2100106400 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 394386192.85 | 19719309.6425 | 313416435.85 | 313416435.85 | 2055002293 | لا | 0 | 180809058925 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2013-12-17 | 2017-04-04 | 2020-06-30 | 2020-06-30 | 2017-04-04 |  | لا يوجد تأخير |  | 49.6626 | 27.0037 | منجز | No
2100006204 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 114190991.22 | 5709549.561 | 51860928.09 | 51860928.09 | 1010008948 | لا | 0 | 190501118157 | جاري | منهجية القيمة المكتسبة | 44 | 56 | 2019-11-24 | 2022-05-22 | 2023-12-26 | 2023-12-26 |  |  | اخرى |  | 49.6626 | 27.0037 | متأخر | No
2100104860 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 9872476 | 493623.8 | 22558217.45 | 0.01 | 1010046644 | لا | 0 |  | مسحوب | التكلفة المفوترة | 86 | 100 | 2013-03-18 | 2015-03-08 | 2015-03-09 | 2015-03-09 |  |  | ضعف كفاءة المقاول الفنية |  | 50.5995 | 26.3403 | مسحوب | No
2100002074 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 29687154 | 1484357.7 | 28304066.18 | 28304066.18 | 2250001372 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-08-11 | 2017-10-29 | 2020-11-22 | 2020-11-22 | 2017-10-29 |  |  |  | 49.5604 | 25.3897 | منجز | No
2100042221 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 10922712.11 | 546135.6055 | 2348153 | 0.01 | 1010046644 | لا | 0 |  | مسحوب | التكلفة المفوترة | 31 | 100 | 2015-11-18 | 2017-11-07 | 2017-11-07 | 2017-11-07 |  |  | ضعف كفاءة المقاول الفنية |  | 50.5993 | 26.3395 | مسحوب | No
2100107446 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 970420 | 48521 | 620000 | 620000 | 2053002108 | لا | 0 |  | جاري | التكلفة المفوترة | 90 | 100 | 2008-11-29 | 2008-11-30 | 2020-12-01 | 2020-12-01 |  |  | ضعف كفاءة المقاول الفنية |  | 50.105 | 26.444 | Failed | No
2100097414 | هيئة المدن الصناعية ومناطق التقنية | تشييد | ذات اولوية عالية | 11865068 | 593253.4 | 10241353 | 10241353 | 1010199022 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-10-30 | 2021-04-22 | 2021-12-13 | 2021-12-13 | 2021-04-22 |  | عدم اكتمال أو ضعف أعمال التصميم والدراسات |  | 25.2683 | 49.5514 | منجز | No
2100104241 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 14274900.4 | 713745.02 | 5760990.71 | 5760990.71 | 1010046644 | لا | 0 |  | مسحوب | التكلفة المفوترة | 54 | 100 | 2014-01-26 | 2016-01-16 | 2019-04-22 | 2019-04-22 |  |  | ضعف كفاءة المقاول الفنية |  | 50.6413 | 26.2903 | مسحوب | No
2100044085 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1150000 | 57500 | 1150000 | 1150000 | 4034005467 | لا | 0 | 190409133866 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-08-27 | 2019-08-22 | 2019-08-22 | 2019-08-22 | 2019-08-22 |  |  |  | 41.6277 | 21.1998 | منجز | No
2100033644 | وزارة التجارة | تشييد | ذات اولوية عالية | 15812630 | 790631.5 | 10210029 | 10210029 | 3350009207 | لا | 0 | 180501011383 | جاري | منهجية القيمة المكتسبة | 95 | 99 | 2018-10-10 | 2020-10-09 | 2022-05-12 | 2022-05-12 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 41.6679 | 27.563 | منتظم | No
2100041963 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 5756392.66 | 287819.633 | 3749371.08 | 0 | 1128003208 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 90 | 67 | 2015-04-22 | 2018-02-24 | 2021-07-06 | 2021-07-06 | 2018-02-24 |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | منجز | Yes
2100055823 | هيئة تطوير منطقة حائل | تشييد | ذات اولوية عالية وعاجلة | 127000000 | 6350000 | 77088171.61 | 77088171.61 | 1010052129 | لا | 0 | 190809031113 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 77 | 100 | 2009-08-03 | 2011-12-07 | 2023-03-31 | 2023-03-31 |  |  | اخرى |  | 41.8561 | 27.443 | Failed | No
2100195720 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 9825742.5 | 491287.125 | 8782739 | 8782739 | 3350000631 | لا | 0 | 190701130484 | جاري | الكميات التي تم تركيبها | 90 | 100 | 2020-11-19 | 2022-05-13 | 2022-05-13 | 2022-05-13 |  |  |  |  | 41.6113 | 27.4726 | Failed | No
2100034473 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 2624310 | 131215.5 | 2815352 | 2307654 | 4601002260 | لا | 0 | 200609023320 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-12-18 | 2021-11-24 | 2022-02-23 | 2022-02-23 | 2021-11-24 |  | اخرى |  | 39.2079 | 21.502 | منجز | No
2100086575 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية متوسطة | 22682435 | 1134121.75 | 1219576.25 | 1219576.25 | 5950007285 | لا | 0 |  | مسحوب | منهجية القيمة المكتسبة | 6.6 | 100 | 2013-04-20 | 2015-09-23 | 2024-08-20 | 2024-08-20 |  |  | ضعف كفاءة المقاول الفنية |  | 41.2993 | 27.6283 | مسحوب | No
2100079052 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 7012261.77 | 350613.0885 | 1982407.02 | 0 | 3350007326 | لا | 0 |  | مسحوب | التكلفة المفوترة | 29.4 | 100 | 2015-01-08 | 2015-10-18 | 2019-01-11 | 2019-01-11 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | مسحوب | Yes
2100106761 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 11385432.01 | 569271.6005 | 2769399 | 0 | 3350003498 | لا | 0 |  | جاري | التكلفة المفوترة | 85 | 100 | 2011-10-15 | 2013-10-04 | 2022-12-24 | 2022-12-24 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | متأخر | Yes
2100001960 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 9251678.58 | 462583.929 | 4763523.66 | 0 | 3350003498 | لا | 0 |  | جاري | التكلفة المفوترة | 69 | 100 | 2013-02-18 | 2015-02-08 | 2021-12-15 | 2021-12-15 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | Failed | Yes
2100002435 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 11405313.55 | 570265.6775 | 9421967.26 | 0 | 1131012642 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2012-04-28 | 2014-04-18 | 2020-12-24 | 2020-12-24 | 2014-04-18 |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | منجز | Yes
2100104893 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 3368530.44 | 168426.522 | 1656195 | 1656195 | 3350018571 | لا | 0 |  | مسحوب | التكلفة المفوترة | 78 | 100 | 2010-04-21 | 2011-10-04 | 2015-10-26 | 2015-10-26 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.6968 | 27.506 | مسحوب | No
2100011465 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2111587.5 | 105579.375 | 0 | 0 | 1131533159 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0 | 100 | 2011-05-15 | 2012-08-07 | 2020-10-27 | 2020-10-27 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | مسحوب | No
2100035490 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2203825.5 | 110191.275 | 166702.84 | 166702.84 | 3350009773 | لا | 0 |  | مسحوب | التكلفة المفوترة | 16 | 100 | 2016-01-21 | 2017-01-15 | 2021-12-21 | 2021-12-21 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | مسحوب | No
2100040316 | وزارة الصحة / حائل | تشييد | ذات اولوية عالية | 83903279.22 | 4195163.961 | 37391942.45 | 28838284.13 | 1018000245 | لا | 0 | 181209418344 | مسحوب | تكلفة العمل المنجز | 45 | 100 | 2012-10-08 | 2016-11-23 | 2023-01-01 | 2023-01-01 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6922 | 27.5705 | مسحوب | No
2100103736 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 7825745.83 | 391287.2915 | 478823.39 | 0 | 3350007326 | لا | 0 |  | مسحوب | التكلفة المفوترة | 6 | 100 | 2015-03-05 | 2016-05-08 | 2019-02-21 | 2019-02-21 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | مسحوب | Yes
2100091604 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1847245 | 92362.25 | 191861 | 191861 | 1131034009 | لا | 0 |  | جاري | التكلفة المفوترة | 35 | 100 | 2018-10-08 | 2019-06-05 | 2021-12-15 | 2021-12-15 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | Failed | No
2100001735 | وزارة التعليم | تشييد | ذات اولوية عالية | 11670102.18 | 583505.109 | 10198938.87 | 0 | 3350003498 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2013-02-16 | 2016-12-31 | 2019-01-17 | 2019-01-17 | 2016-12-31 |  | اخرى |  | 41.6968 | 27.506 | منجز | Yes
2100000615 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 10706427 | 535321.35 | 6631191.7 | 0 | 1132005270 | لا | 0 |  | جاري | التكلفة المفوترة | 75 | 100 | 2012-06-25 | 2014-06-15 | 2021-12-15 | 2021-12-15 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | Failed | Yes
2100027941 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1466163 | 73308.15 | 0 | 0 | 3350010360 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0 | 100 | 2006-05-29 | 2007-04-14 | 2021-11-04 | 2021-11-04 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | مسحوب | No
2100011174 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 4466834.27 | 223341.7135 | 2828362.52 | 2828362.52 | 3350017007 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2017-11-27 | 2018-11-17 | 2021-12-15 | 2021-12-15 | 2018-11-17 |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | منجز | No
2100039561 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1399648 | 69982.4 | 1032314 | 1032314 | 3350027223 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2017-11-20 | 2018-07-28 | 2019-01-17 | 2019-01-17 | 2018-07-28 |  | اخرى |  | 41.6968 | 27.506 | منجز | No
2100098066 | جامعة حائل | تشييد | ذات اولوية عالية وعاجلة | 296487890 | 14824394.5 | 217256384.1 | 217256384.1 | 1010247052 | لا | 0 | 210909073001 | جاري | تكلفة العمل المنجز | 73.28 | 100 | 2010-10-31 | 2019-05-12 | 2023-12-31 | 2023-12-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.7104 | 27.6746 | Failed | No
2100079763 | المؤسسة العامة للحبوب | تشييد | ذات اولوية عالية وعاجلة | 58511409 | 2925570.45 | 58511409 | 58511409 | 1010085518 | لا | 0 | 190301030063 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-03-18 | 2021-02-23 | 2022-02-14 | 2022-02-14 | 2021-02-23 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 41.7216 | 27.647 | منجز | No
2100053196 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2203825.5 | 110191.275 | 182164.29 | 182164.29 | 3350009773 | لا | 0 |  | مسحوب | التكلفة المفوترة | 16 | 100 | 2016-01-04 | 2016-12-29 | 2021-12-15 | 2021-12-15 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | مسحوب | No
2100052544 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 9730289 | 486514.45 | 4814683.97 | 0 | 3350005675 | لا | 0 |  | جاري | التكلفة المفوترة | 70 | 100 | 2013-09-02 | 2015-02-27 | 2022-12-29 | 2022-12-29 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | Failed | Yes
2100088771 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 8837782.66 | 441889.133 | 6371122.02 | 6371122.02 | 1010196220 | لا | 0 | 190309008416 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2012-03-06 | 2013-08-28 | 2019-09-10 | 2019-09-10 | 2013-08-28 |  |  |  | 39.3206 | 29.8874 | منجز | No
2100088384 | جامعة الجوف | تشييد | ذات اولوية عالية | 95538362 | 4776918.1 | 37023695.48 | 37023695.48 | 1010122914 | لا | 0 | 180909067550 | جاري | تكلفة العمل المنجز | 65 | 89 | 2014-12-11 | 2021-12-03 | 2023-03-22 | 2023-03-22 |  |  | تأخرصرف المستحقات المالية |  | 40.0347 | 29.7747 | Failed | No
2100002590 | جامعة الجوف | تشييد | ذات اولوية عالية | 71935464.6 | 3596773.23 | 25670304.24 | 25670304.24 | 3450008383 | لا | 0 | 180809053032 | جاري | تكلفة العمل المنجز | 67 | 91 | 2017-02-21 | 2021-05-13 | 2023-02-07 | 2023-02-07 |  |  | تأخرصرف المستحقات المالية |  | 40.0347 | 29.7747 | متأخر | No
2100007114 | جامعة الجوف | تشييد | ذات اولوية متوسطة | 46419961 | 2320998.05 | 46040056.21 | 46040056.21 | 3452004161 | لا | 0 | 181009144881 | جاري | تكلفة العمل المنجز | 100 | 100 | 2017-12-04 | 2021-01-04 | 2021-11-04 | 2021-11-04 |  |  | تأخرصرف المستحقات المالية |  | 37.5464 | 52.1419 | Failed | No
2100088804 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 4379580.7 | 218979.035 | 3477425.6 | 3477425.6 | 1013000078 | لا | 0 | 190309008096 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2010-03-07 | 2011-08-29 | 2019-04-28 | 2019-04-28 | 2011-08-29 |  |  |  | 40.0549 | 29.8587 | منجز | No
2100003113 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 10751407.59 | 537570.3795 | 6544299 | 6544299 | 1010170640 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 73 | 100 | 2014-12-02 | 2016-11-21 | 2021-12-15 | 2021-12-15 | 2016-11-21 |  | ضعف كفاءة المقاول الفنية |  | 40.0549 | 29.8587 | منجز | No
2100006790 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2023115.9 | 101155.795 | 948834.42 | 948834.42 | 3452007733 | لا | 0 |  | مسحوب | التكلفة المفوترة | 87 | 100 | 2013-11-07 | 2014-11-02 | 2019-01-01 | 2019-01-01 |  |  | ضعف كفاءة المقاول الفنية |  | 40.0549 | 29.8587 | مسحوب | No
2100059091 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 7307922.04 | 365396.102 | 2239408.72 | 2239408.72 | 1010213931 | لا | 0 |  | مسحوب | التكلفة المفوترة | 40 | 100 | 2014-03-17 | 2016-03-06 | 2018-12-06 | 2018-12-06 |  |  | ضعف كفاءة المقاول الفنية |  | 40.0549 | 29.8587 | مسحوب | No
2100021033 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 8857620.14 | 442881.007 | 0 | 0 | 1010213931 | لا | 0 |  | مسحوب | التكلفة المفوترة | 1 | 100 | 2016-08-07 | 2018-05-26 | 2019-01-22 | 2019-01-22 |  |  | ضعف كفاءة المقاول الفنية |  | 40.0549 | 29.8587 | مسحوب | No
2100101754 | أمانة / الجوف | دراسة الجدوى | ذات اولوية عالية | 577800 | 28890 | 566244 | 557095.5 | 1010250667 | لا | 0 | 181209531871 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-12-16 | 2019-12-15 | 2019-12-15 | 2019-12-15 | 2019-12-15 |  | اخرى |  | 39.8888 | 29.8108 | منجز | No
2100061961 | وزارة التجارة | تشييد | ذات اولوية عالية | 9964928 | 498246.4 | 1790652.5794 | 1790652.5794 | 1010195593 | لا | 0 | 180901066327 | جاري | منهجية القيمة المكتسبة | 70 | 80 | 2018-11-07 | 2020-11-06 | 2022-08-09 | 2022-08-09 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 37.3393 | 31.346 | متأخر | No
2100090941 | جامعة جازان | تشييد | ذات اولوية عالية | 36781440 | 1839072 | 11024270 | 11024270 | 1010185891 | لا | 0 | 181101298446 | جاري | الكميات التي تم تركيبها | 30 | 80 | 2018-11-11 | 2019-11-11 | 2024-06-30 | 2024-06-30 |  |  | تأخرصرف المستحقات المالية |  | 42.8928 | 17.0103 | Failed | No
2100042243 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 8997859.28 | 449892.964 | 4429674.27 | 4429674.27 | 1010213931 | لا | 0 |  | مسحوب | التكلفة المفوترة | 86 | 100 | 2014-03-17 | 2015-12-08 | 2022-02-01 | 2022-02-01 |  |  | ضعف كفاءة المقاول الفنية |  | 40.0549 | 29.8587 | مسحوب | No
2100096132 | وزارة التجارة | دراسة الجدوى | ذات اولوية عالية وعاجلة | 3069572 | 153478.6 | 2512442 | 2512442 | 1010348048 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-07-22 | 2020-07-21 | 2021-03-28 | 2021-03-28 |  | 2020-07-21 | أوامر تغيير |  |  |  | منجز | No
2100003065 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 11186659.11 | 559332.9555 | 0 | 0 | 4030052981 | لا | 0 |  | مسحوب | التكلفة المفوترة | 1 | 29 | 2019-11-17 | 2021-11-06 | 2022-05-18 | 2022-05-18 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | مسحوب | No
2100006930 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 9062256 | 453112.8 | 702220 | 0 | 1010006362 | لا | 0 |  | مسحوب | التكلفة المفوترة | 7 | 100 | 2013-05-25 | 2015-02-14 | 2023-05-10 | 2023-05-10 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | مسحوب | Yes
2100006182 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 3000031.5 | 150001.575 | 2485396.13 | 2485396.13 | 4030052981 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-12-06 | 2016-11-30 | 2019-12-02 | 2019-12-02 | 2016-11-30 |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | منجز | No
2100006160 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 6601517.95 | 330075.8975 | 43716 | 0 | 1010006362 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 20 | 100 | 2013-05-25 | 2016-06-10 | 2023-05-10 | 2023-05-10 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.5429 | 16.8808 | مسحوب | Yes
2100002214 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 8460359.42 | 423017.971 | 6844156.5 | 0 | 5950004973 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2013-07-08 | 2015-03-30 | 2016-12-31 | 2016-12-31 | 2015-03-30 |  | تأخرصرف المستحقات المالية |  | 42.6509 | 17.1567 | منجز | Yes
2100036175 | وزارة التعليم | تشييد | ذات اولوية عالية | 2768116.9 | 138405.845 | 2637432 | 2637432 | 5901014389 | لا | 0 |  | جاري | التكلفة المفوترة | 93 | 100 | 2013-01-06 | 2014-03-02 | 2022-11-09 | 2022-11-09 |  |  | ضعف كفاءة المقاول الفنية |  | 42.6509 | 17.1567 | Failed | No
2100006845 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 12397278 | 619863.9 | 8338403 | 0 | 1116004627 | لا | 0 | 190309005107 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2013-02-20 | 2015-02-10 | 2022-11-30 | 2022-11-30 | 2015-02-10 |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | منجز | Yes
2100009671 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 1088085 | 54404.25 | 93164 | 93164 | 4031002336 | لا | 0 |  | مسحوب | التكلفة المفوترة | 15 | 100 | 2009-07-03 | 2010-06-27 | 2023-05-13 | 2023-05-13 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | مسحوب | No
2100010091 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 9794813.83 | 489740.6915 | 1221030.72 | 122030.72 | 4030052981 | لا | 0 | 190509016339 | مسحوب | التكلفة المفوترة | 16 | 100 | 2018-10-29 | 2020-07-20 | 2022-12-28 | 2022-12-28 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | مسحوب | No
2100041985 | وزارة التعليم | تشييد | ذات اولوية عالية | 9398086.46 | 469904.323 | 7220672.78 | 0 | 5950004973 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2013-09-29 | 2015-09-19 | 2020-08-19 | 2020-08-19 | 2015-09-19 |  | تأخرصرف المستحقات المالية |  | 42.6509 | 17.1567 | منجز | Yes
2100108570 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 8319688 | 415984.4 | 0 | 0 | 1010277276 | لا | 0 |  | ايقاف كلي | التكلفة المفوترة | 0 | 100 | 2014-05-08 | 2016-04-27 | 2023-05-09 | 2023-05-09 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | Failed | No
2100079542 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 6177742.8 | 308887.14 | 0 | 0 | 2251033167 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 9 | 100 | 2008-04-19 | 2010-01-09 | 2022-05-13 | 2022-05-13 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.5429 | 16.8808 | مسحوب | No
2100002833 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 1987295 | 99364.75 | 644613 | 644613 | 1010678591 | لا | 0 |  | مسحوب | التكلفة المفوترة | 65 | 100 | 2008-06-02 | 2009-05-20 | 2021-08-18 | 2021-08-18 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | مسحوب | No
2100057116 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 6894151.44 | 344707.572 | 506469.4 | 0 | 1010006362 | لا | 0 |  | مسحوب | التكلفة المفوترة | 7 | 100 | 2013-06-01 | 2015-02-21 | 2022-02-03 | 2022-02-03 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | مسحوب | Yes
2100058774 | وزارة التعليم | تشييد | ذات اولوية عالية | 5066791.29 | 253339.5645 | 554749.47 | 0 | 5950007285 | لا | 0 | 190309000715 | مسحوب | التكلفة المفوترة | 19 | 100 | 2013-08-28 | 2015-02-19 | 2022-05-11 | 2022-05-11 |  |  | ضعف كفاءة المقاول الفنية |  | 42.6509 | 17.1567 | مسحوب | Yes
2100005434 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 10396874 | 519843.7 | 3772829.87 | 3573489.27 | 4030052981 | لا | 0 | 190709025274 | مسحوب | التكلفة المفوترة | 39 | 100 | 2015-11-22 | 2017-11-11 | 2023-02-09 | 2023-02-09 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | مسحوب | No
2100096854 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 16866580.5 | 843329.025 | 0 | 0 | 1010157933 | لا | 0 |  | مسحوب | التكلفة المفوترة | 2 | 100 | 2009-12-18 | 2010-10-15 | 2023-02-10 | 2023-02-10 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | مسحوب | No
2100010721 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 19792778.91 | 989638.9455 | 19546884.37 | 19546884.37 | 1010039430 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-07-10 | 2020-07-04 | 2020-04-05 | 2020-04-05 | 2020-07-04 |  | أوامر تغيير | أخرى |  |  | منجز | No
2100042770 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1979605.1 | 98980.255 | 889631.135 | 889631.135 | 4030209079 | لا | 0 |  | مسحوب | التكلفة المفوترة | 57 | 100 | 2008-03-31 | 2009-03-26 | 2022-05-11 | 2022-05-11 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | مسحوب | No
2100010861 | وزارة التعليم | تشييد | ذات اولوية عالية | 1371310 | 68565.5 | 1371240 | 1211024.59 | 1010272551 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-02-18 | 2015-02-07 | 2022-08-19 | 2022-08-19 | 2015-02-07 |  | ضعف كفاءة المقاول الفنية |  | 42.6509 | 17.1567 | منجز | No
2100104635 | وزارة التعليم | تشييد | ذات اولوية عالية | 8744965.2 | 437248.26 | 1521720 | 0 | 1010223860 | لا | 0 |  | مسحوب | التكلفة المفوترة | 17 | 100 | 2013-09-07 | 2015-05-31 | 2023-02-09 | 2023-02-09 |  |  | ضعف كفاءة المقاول الفنية |  | 42.6509 | 17.1567 | مسحوب | Yes
2100033375 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 1575200 | 78760 | 1575200 | 1575200 | 3350027223 | لا | 0 | 200501044103 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-12-07 | 2020-12-07 | 2020-12-07 | 2020-12-07 | 2020-12-07 |  |  |  | 43.0094 | 27.4621 | منجز | No
2100058575 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 6840709.25 | 342035.4625 | 0 | 0 | 1010188602 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0 | 100 | 2008-01-28 | 2010-01-17 | 2024-02-21 | 2024-02-21 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.5429 | 16.8808 | مسحوب | No
2100091055 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 7291601.79 | 364580.0895 | 279526.54 | 279526.54 | 4030052981 | لا | 0 | 190409115080 | مسحوب | التكلفة المفوترة | 4 | 83 | 2018-10-29 | 2020-07-20 | 2022-08-24 | 2022-08-24 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | مسحوب | No
2100023472 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2292185 | 114609.25 | 1028323 | 1028323 | 2050031305 | لا | 0 |  | مسحوب | التكلفة المفوترة | 55 | 100 | 2008-07-30 | 2009-07-19 | 2023-02-21 | 2023-02-21 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | مسحوب | No
2100008061 | وزارة التعليم | تشييد | ذات اولوية عالية | 4705414.75 | 235270.7375 | 228714.62 | 0 | 1010223860 | لا | 0 |  | مسحوب | التكلفة المفوترة | 14 | 100 | 2013-12-22 | 2015-06-15 | 2023-03-07 | 2023-03-07 |  |  | ضعف كفاءة المقاول الفنية |  | 42.6509 | 17.1567 | مسحوب | Yes
2100041742 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 7802420.66 | 390121.033 | 7021337.64 | 4828805.09 | 1010060469 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2017-07-24 | 2019-07-14 | 2020-06-03 | 2020-06-03 | 2019-07-14 |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | منجز | No
2100057562 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 10613563 | 530678.15 | 2919889.6 | 1828932.18 | 1010277276 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 47 | 100 | 2014-05-08 | 2017-11-23 | 2024-02-22 | 2024-02-22 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.5429 | 16.8808 | مسحوب | No
2100196000 | الهيئة العامة للزكاة والدخل | توريد وتركيب | ذات اولوية عالية وعاجلة | 6305335 | 315266.75 | 3800000 | 1800000 | 1010168776 | لا | 0 |  | منجز – استلام نهائي | تكلفة العمل المنجز | 88 | 100 | 2021-02-28 | 2021-08-29 | 2021-09-25 | 2021-09-25 |  | 2021-08-29 |  |  | 46.7137 | 24.6559 | منجز | No
2100088513 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 8649088.93 | 432454.4465 | 1613764.3 | 0 | 4030161492 | لا | 0 |  | ايقاف كلي | التكلفة المفوترة | 22 | 100 | 2010-04-24 | 2012-04-13 | 2022-11-16 | 2022-11-16 |  |  | منازعات قائمة |  | 42.6509 | 17.1567 | Failed | Yes
2100035265 | وزارة الشـؤون الاسلامية والدعوة والارشاد | تشييد | ذات اولوية عالية | 2724950 | 136247.5 | 1678110 | 1678110 | 5906021695 | نعم | 1678110 |  | مسحوب | الكميات التي تم تركيبها | 65 | 100 | 2013-05-01 | 2014-04-20 | 2022-10-31 | 2022-10-31 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | مسحوب | No
2100088233 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1074667.33 | 53733.3665 | 0 | 0 | 4030137344 | لا | 0 |  | مسحوب | التكلفة المفوترة | 0 | 100 | 2008-06-08 | 2009-05-26 | 2024-03-20 | 2024-03-20 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | مسحوب | No
2100006090 | وزارة التعليم | تشييد | ذات اولوية عالية | 21361841 | 1068092.05 | 10752491 | 526420 | 4031033277 | لا | 0 |  | مسحوب | التكلفة المفوترة | 80 | 100 | 2015-04-19 | 2017-07-08 | 2024-01-15 | 2024-01-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | No
2100011546 | وزارة التعليم | تشييد | ذات اولوية عالية | 2493968 | 124698.4 | 355024.11 | 355024.11 | 5905030969 | لا | 0 | 190909018409 | ايقاف كلي | التكلفة المفوترة | 25.5 | 100 | 2018-03-31 | 2019-01-25 | 2023-02-01 | 2023-02-01 |  |  | ضعف كفاءة المقاول الفنية |  | 42.6509 | 17.1567 | Failed | No
2100016413 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 4112291.88 | 205614.594 | 1013680 | 1013680 | 1010197699 | لا | 0 |  | مسحوب | التكلفة المفوترة | 25 | 100 | 2014-04-01 | 2015-05-25 | 2023-12-13 | 2023-12-13 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | مسحوب | No
2100063162 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2638065 | 131903.25 | 3325147.2 | 0 | 5907012497 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 28 | 100 | 2012-02-20 | 2013-02-08 | 2023-08-10 | 2023-08-10 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.5429 | 16.8808 | مسحوب | Yes
2100023122 | وزارة التعليم | تشييد | ذات اولوية عالية | 7535508.24 | 376775.412 | 3875000 | 0 | 1018746600 | لا | 0 | 190309008338 | مسحوب | التكلفة المفوترة | 75 | 100 | 2014-08-10 | 2016-07-20 | 2023-06-13 | 2023-06-13 |  |  | ضعف كفاءة المقاول الفنية |  | 42.6509 | 17.1567 | مسحوب | Yes
2100100225 | وزارة التعليم | تشييد | ذات اولوية عالية | 5189980.95 | 259499.0475 | 0 | 0 | 1010322431 | لا | 0 |  | مسحوب | التكلفة المفوترة | 0 | 100 | 2013-09-08 | 2015-03-02 | 2023-03-02 | 2023-03-02 |  |  | ضعف كفاءة المقاول الفنية |  | 42.6509 | 17.1567 | مسحوب | No
2100041996 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2999859 | 149992.95 | 2546981.49 | 2247222.85 | 4030052981 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-12-06 | 2016-11-30 | 2019-11-02 | 2019-11-02 | 2016-11-30 |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | منجز | No
2100035932 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 6532863.48 | 326643.174 | 0 | 0 | 1010233305 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0 | 100 | 2015-02-15 | 2017-02-17 | 2024-06-06 | 2024-06-06 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.5429 | 16.8808 | مسحوب | No
2100003651 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 11192326.82 | 559616.341 | 4075437.12 | 3861014.62 | 4030052981 | لا | 0 | 190409114273 | مسحوب | التكلفة المفوترة | 40 | 100 | 2015-12-06 | 2017-11-25 | 2022-09-21 | 2022-09-21 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | مسحوب | No
2100004966 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 5942467.35 | 297123.3675 | 1876210 | 1876210 | 1010678591 | لا | 0 |  | مسحوب | التكلفة المفوترة | 32 | 100 | 2011-09-10 | 2013-09-01 | 2023-07-21 | 2023-07-21 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | مسحوب | No
2100058391 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 7180245.27 | 359012.2635 | 1794537.36 | 0 | 5950007285 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 25 | 100 | 2013-09-17 | 2015-06-10 | 2023-08-21 | 2023-08-21 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | مسحوب | Yes
2100079450 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 5609950.24 | 280497.512 | 0 | 0 | 1010188602 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0 | 100 | 2007-07-24 | 2007-07-25 | 2023-03-08 | 2023-03-08 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.5429 | 16.8808 | مسحوب | No
2100104296 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 6299856.77 | 314992.8385 | 0 | 0 | 2251033167 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 9 | 100 | 2008-05-20 | 2010-02-09 | 2023-05-07 | 2023-05-07 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.5429 | 16.8808 | مسحوب | No
2100087776 | وزارة التعليم | تشييد | ذات اولوية عالية | 5149400 | 257470 | 1266996.14 | 1109182 | 4030288443 | لا | 0 |  | مسحوب | التكلفة المفوترة | 55 | 100 | 2015-04-29 | 2016-10-21 | 2023-01-15 | 2023-01-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | No
2100055215 | وزارة الصحة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 783861 | 39193.05 | 394324 | 0 | 4650040868 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-12-08 | 2019-03-08 | 2022-03-31 | 2022-03-31 | 2019-03-08 |  | تأخرصرف المستحقات المالية |  | 37.9487 | 26.5559 | منجز | Yes
2100041926 | وزارة الموارد البشرية والتنمية الإجتماعية | تشييد | ذات اولوية منخفضة | 16369765.1 | 818488.255 | 7527357.98 | 7527357.98 | 1010110229 | لا | 0 | 180909066686 | مسحوب | الكميات التي تم تركيبها | 75 | 100 | 2011-02-23 | 2013-07-26 | 2023-12-31 | 2023-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 39.4926 | 24.4273 | مسحوب | No
2100038566 | جامعة طيبة | تشييد | ذات اولوية عالية | 41420253.65 | 2071012.6825 | 21584287.86 | 20425051.36 | 4650015928 | لا | 0 | 180909107889 | جاري | تكلفة العمل المنجز | 53 | 100 | 2016-01-21 | 2017-07-13 | 2022-11-22 | 2022-11-22 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال | تم إنذار المقاول كتابيا | 39.6005 | 24.4595 | Failed | No
2100001201 | جامعة طيبة | تشييد | ذات اولوية عالية | 334500 | 16725 | 213659.39 | 100409.39 | 4650040868 | لا | 0 | 180809039392 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2017-01-10 | 2018-04-01 | 2018-03-30 | 2018-03-30 | 2018-04-01 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.6005 | 24.4595 | منجز | No
2100022901 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية | 17490281 | 874514.05 | 12810411.71 | 10905300.69 | 4650015928 | لا | 0 | 180909083753 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 90.85 | 90 | 2015-01-11 | 2016-06-25 | 2021-09-26 | 2021-09-26 | 2016-06-25 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 37.6895 | 26.4589 | منجز | No
2100000140 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية | 6601638 | 330081.9 | 5032019.55 | 4524829.52 | 4650009299 | لا | 0 | 181009149417 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 93 | 93.42 | 2015-12-31 | 2018-11-28 | 2021-05-22 | 2021-05-22 | 2018-11-28 |  | لا يوجد تأخير |  | 40.5211 | 24.8831 | منجز | No
2100087242 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية وعاجلة | 29875999 | 1493799.95 | 29875999 | 29875999 | 1116006476 | لا | 0 | 181109360834 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 96.3 | 2018-01-07 | 2020-12-05 | 2020-10-25 | 2020-10-25 | 2020-12-05 |  | لا يوجد تأخير |  | 40.8745 | 23.4877 | منجز | No
2100010205 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 10084444.12 | 504222.206 | 6779307.41 | 5816740.81 | 1010089371 | لا | 0 |  | مسحوب | التكلفة المفوترة | 68 | 100 | 2013-02-20 | 2015-02-10 | 2021-06-27 | 2021-06-27 |  |  | ضعف كفاءة المقاول الفنية |  | 40.8817 | 23.5031 | مسحوب | No
2100086940 | وزارة التعليم | تشييد | ذات اولوية عالية | 3741448.03 | 187072.4015 | 2286570.2 | 2286570.2 | 4650039553 | لا | 0 |  | جاري | التكلفة المفوترة | 81 | 100 | 2012-04-03 | 2013-05-28 | 2013-05-28 | 2013-05-28 |  |  | ضعف كفاءة المقاول الفنية |  | 38.0623 | 24.0861 | Failed | No
2100008153 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 4933362 | 246668.1 | 514050 | 514050 | 4030025647 | لا | 0 |  | مسحوب | التكلفة المفوترة | 10.5 | 100 | 2008-11-25 | 2010-05-10 | 2023-11-15 | 2023-11-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | No
2100086531 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1386515 | 69325.75 | 0 | 0 | 4650003547 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 1 | 100 | 2006-05-27 | 2007-04-12 | 2020-01-01 | 2020-01-01 |  |  | ضعف كفاءة المقاول الفنية |  | 38.0623 | 24.0861 | مسحوب | No
2100000350 | وزارة الموارد البشرية والتنمية الإجتماعية | تشييد | ذات اولوية منخفضة | 21779832.3 | 1088991.615 | 18283704.43 | 18283704.43 | 4030140863 | لا | 0 | 180909080362 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-12-11 | 2016-07-23 | 2019-12-24 | 2019-12-24 | 2016-07-23 |  | ضعف كفاءة المقاول الفنية |  | 39.4937 | 24.4273 | منجز | No
2100096714 | وكالة / الإسكان | تشييد | ذات اولوية متوسطة | 127789577.28 | 6389478.864 | 124947220.9 | 104025890.17 | 1010082898 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2014-03-06 | 2016-02-24 | 2020-07-16 | 2020-07-16 | 2016-02-24 |  | ضعف كفاءة المقاول الفنية | أخرى | 37.9236 | 26.6096 | منجز | No
2100062226 | وزارة التجارة | دراسة الجدوى | ذات اولوية عالية وعاجلة | 2678000 | 133900 | 1089589.06 | 1089589.06 | 1010325199 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 75 | 80 | 2018-12-26 | 2020-12-25 | 2022-05-02 | 2022-05-02 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  |  |  | خدمات عامة | No
2100000232 | وزارة التعليم | تشييد | ذات اولوية عالية | 8094308.78 | 404715.439 | 2783372 | 2783372 | 4030288443 | لا | 0 |  | مسحوب | التكلفة المفوترة | 62 | 100 | 2015-01-21 | 2017-01-11 | 2023-06-15 | 2023-06-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | No
2100007523 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 10521208 | 526060.4 | 10303069 | 10303069 | 1010060469 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2016-02-14 | 2018-02-04 | 2019-05-28 | 2019-05-28 | 2018-02-04 |  |  |  | 39.6005 | 24.4595 | منجز | No
2100025513 | وزارة التعليم | تشييد | ذات اولوية عالية | 5735642 | 286782.1 | 0 | 0 | 4030065868 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0 | 100 | 2014-04-10 | 2015-12-02 | 2024-06-15 | 2024-06-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | No
2100063604 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1927477 | 96373.85 | 1674142 | 0 | 4030123131 | لا | 0 |  | مسحوب | التكلفة المفوترة | 85 | 100 | 2008-02-09 | 2009-05-13 | 2022-08-16 | 2022-08-16 |  |  | ضعف كفاءة المقاول الفنية |  | 38.0623 | 24.0861 | مسحوب | Yes
2100006171 | وزارة التعليم | تشييد | ذات اولوية عالية | 8043237 | 402161.85 | 2027015 | 1190015 | 4030288443 | لا | 0 |  | مسحوب | التكلفة المفوترة | 40 | 100 | 2015-06-16 | 2017-06-06 | 2023-11-15 | 2023-11-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | No
2100086155 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 6526847.64 | 326342.382 | 1474978 | 0 | 4650020435 | لا | 0 |  | مسحوب | التكلفة المفوترة | 40 | 100 | 2013-12-29 | 2015-12-20 | 2023-06-15 | 2023-06-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | Yes
2100007254 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2759710 | 137985.5 | 0 | 0 | 4030123131 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 1 | 100 | 2009-05-08 | 2010-04-27 | 2020-01-01 | 2020-01-01 |  |  | ضعف كفاءة المقاول الفنية |  | 38.0623 | 24.0861 | مسحوب | No
2100009030 | وزارة التعليم | تشييد | ذات اولوية عالية | 10732384 | 536619.2 | 2236650.49 | 2236650 | 4030288443 | لا | 0 |  | مسحوب | التكلفة المفوترة | 53 | 100 | 2015-01-21 | 2017-01-11 | 2023-01-15 | 2023-01-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | No
2100104300 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 4890235 | 244511.75 | 3262250.98 | 0 | 4650020435 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2005-08-16 | 2015-08-24 | 2015-10-07 | 2015-10-07 | 2015-08-24 |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | منجز | Yes
2100079166 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 13700224.26 | 685011.213 | 11114745 | 0 | 4650020435 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 85 | 100 | 2008-02-04 | 2010-01-26 | 2023-01-15 | 2023-01-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | Yes
2100104031 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1480605 | 74030.25 | 0 | 0 | 4650003547 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 1 | 100 | 2006-03-05 | 2007-04-12 | 2020-01-01 | 2020-01-01 |  |  | ضعف كفاءة المقاول الفنية |  | 38.0623 | 24.0861 | مسحوب | No
2100095546 | وزارة الصحة / المدينة المنورة | تشييد | ذات اولوية منخفضة | 3839050 | 191952.5 | 2253700 | 2253700 | 4650061289 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2016-05-21 | 2017-02-10 | 2022-02-28 | 2022-02-28 | 2017-02-10 |  | تأخرصرف المستحقات المالية |  | 39.5608 | 24.4952 | منجز | No
2100057105 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 18577583 | 928879.15 | 3235752 | 0 | 4650020435 | لا | 0 |  | مسحوب | التكلفة المفوترة | 22 | 100 | 2013-03-26 | 2015-02-15 | 2023-06-15 | 2023-06-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | Yes
2100196140 | وزارة الرياضة | تشييد | ذات اولوية متوسطة | 1415424.6 | 70771.23 | 476316.2 | 476316.2 | 1010056286 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2021-09-01 | 2022-08-28 | 2022-06-28 | 2022-06-28 | 2022-08-28 |  |  |  | 39.9725 | 21.4819 | منجز | No
2100108091 | وزارة التعليم | تشييد | ذات اولوية عالية | 4797728.77 | 239886.4385 | 1080099 | 0 | 4030288443 | لا | 0 |  | مسحوب | التكلفة المفوترة | 52 | 100 | 2015-05-31 | 2016-11-22 | 2023-06-15 | 2023-06-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | Yes
2100011023 | وزارة التعليم | تشييد | ذات اولوية عالية | 7217910 | 360895.5 | 2779871 | 2360692 | 4030288443 | لا | 0 |  | مسحوب | التكلفة المفوترة | 96 | 100 | 2015-05-10 | 2017-04-30 | 2022-08-15 | 2022-08-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | No
2100005946 | وزارة التعليم | تشييد | ذات اولوية عالية | 1927477 | 96373.85 | 1811874.5 | 0 | 4030123131 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 70 | 100 | 2008-02-12 | 2009-01-30 | 2013-05-12 | 2013-05-12 |  |  | ضعف كفاءة المقاول الفنية |  | 38.0623 | 24.0861 | مسحوب | Yes
2100087964 | وزارة التعليم | تشييد | ذات اولوية عالية | 6064682 | 303234.1 | 2373170 | 0 | 4030065868 | لا | 0 |  | مسحوب | التكلفة المفوترة | 37 | 100 | 2010-10-01 | 2012-05-24 | 2023-06-15 | 2023-06-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | Yes
2100079100 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 15009056.05 | 750452.8025 | 13528056 | 12714102 | 1010060469 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2016-11-29 | 2018-11-20 | 2019-12-19 | 2019-12-19 | 2018-11-20 |  |  |  | 39.6005 | 24.4595 | منجز | No
2100100962 | وزارة الصحة / المدينة المنورة | تشييد | ذات اولوية منخفضة | 29277803 | 1463890.15 | 11907000 | 11907000 | 4650043690 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 46 | 100 | 2015-04-14 | 2017-03-22 | 2022-03-31 | 2022-03-31 |  |  | تأخرصرف المستحقات المالية |  | 39.36 | 24.28 | Failed | No
2100073754 | وزارة الصحة / المدينة المنورة | تشييد | ذات اولوية عالية | 1627725 | 81386.25 | 1627725 | 760193 | 4650040868 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-02-02 | 2019-07-29 | 2022-02-28 | 2022-02-28 | 2019-07-29 |  | تأخرصرف المستحقات المالية |  | 39.5341 | 24.4141 | منجز | No
2100055521 | وزارة الصحة / المدينة المنورة | تشييد | ذات اولوية منخفضة | 7966968 | 398348.4 | 7966968 | 7358558 | 4650007032 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-06-30 | 2019-06-19 | 2022-02-28 | 2022-02-28 | 2019-06-19 |  | تأخرصرف المستحقات المالية |  | 39.5601 | 24.4915 | منجز | No
2100079984 | وزارة المالية | تشييد | ذات اولوية متوسطة | 33835259.89 | 1691762.9945 | 14866216.69 | 14866216.69 | 1010197201 | لا | 0 |  | مسحوب | التكلفة المفوترة | 80 | 80 | 2015-11-09 | 2023-11-30 | 2023-11-30 | 2023-11-30 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.6005 | 24.4595 | مسحوب | No
2100056685 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 11821141.53 | 591057.0765 | 6237791.92 | 0 | 1116004360 | لا | 0 |  | مسحوب | التكلفة المفوترة | 56 | 100 | 2012-12-25 | 2014-12-16 | 2023-06-15 | 2023-06-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | Yes
2100008411 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2157996 | 107899.8 | 1554855 | 1554855 | 4650047835 | لا | 0 |  | مسحوب | التكلفة المفوترة | 91 | 100 | 2015-02-05 | 2016-02-01 | 2023-01-15 | 2023-01-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | No
2100104064 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 14697938 | 734896.9 | 5006976.8 | 0 | 1010090291 | لا | 0 |  | مسحوب | التكلفة المفوترة | 72 | 100 | 2008-01-28 | 2010-01-18 | 2023-01-15 | 2023-01-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | Yes
2100030800 | هيئة المدن الصناعية ومناطق التقنية | تشييد | ذات اولوية عالية | 33682028 | 1684101.4 | 28503719 | 28503719 | 1010276314 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 82 | 100 | 2016-12-20 | 2017-07-19 | 2022-12-20 | 2022-12-20 | 2017-07-19 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 24.2929 | 39.537 | منجز | No
2100058413 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 7135850.4 | 356792.52 | 1538188 | 0 | 1010012745 | لا | 0 |  | مسحوب | التكلفة المفوترة | 20 | 100 | 2009-09-12 | 2011-05-06 | 2024-06-15 | 2024-06-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | Yes
2100017791 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 6080931 | 304046.55 | 1635303 | 0 | 1116004360 | لا | 0 |  | مسحوب | التكلفة المفوترة | 39 | 100 | 2013-06-09 | 2015-03-02 | 2023-06-15 | 2023-06-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | Yes
2100040865 | أمانة / العاصمة المقدسة | دراسة الجدوى | ذات اولوية متوسطة | 3000000 | 150000 | 2141353.66 | 2141353.66 | 4030271639 | لا | 0 | 181009162153 | جاري | تكلفة العمل المنجز | 80.56 | 80.56 | 2018-06-28 | 2019-06-28 | 2022-06-27 | 2022-06-27 |  |  | اخرى |  |  |  | خدمات عامة | No
2100095653 | وزارة الصحة / المدينة المنورة | تشييد | لم تعد تحتاجها الجهة | 4162070 | 208103.5 | 0 | 0 | 4650040868 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 1 | 1 | 2019-01-06 | 2020-06-20 | 2021-11-16 | 2021-11-16 |  |  | اخرى |  | 39.5202 | 24.4083 | مسحوب | No
2100061773 | وزارة الداخلية / المديرية العامة للدفاع المدني | ترميم | ذات اولوية عالية | 5397180 | 269859 | 3771796.03 | 3771796.03 | 4031044308 | لا | 0 | 180701014815 | جاري | الكميات التي تم تركيبها | 85 | 100 | 2018-10-11 | 2020-09-18 | 2022-07-01 | 2022-07-01 |  |  | تأخرصرف المستحقات المالية |  | 39.611 | 24.4871 | Failed | No
2100044472 | وزارة الشـؤون الاسلامية والدعوة والارشاد | تشييد | ذات اولوية عالية | 821469.75 | 41073.4875 | 0 | 0 | 1118003899 | لا | 0 | 190501062219 | ايقاف كلي | الكميات التي تم تركيبها | 40 | 100 | 2018-02-11 | 2019-01-31 | 2019-01-31 | 2019-01-31 |  |  | ضعف كفاءة المقاول الفنية |  | 42.9126 | 23.8946 | Failed | No
2100001676 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 28350150 | 1417507.5 | 19204645 | 19204645 | 7001598437 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2011-10-23 | 2013-10-03 | 2020-02-03 | 2020-02-03 | 2013-10-03 |  | ضعف كفاءة المقاول الفنية |  | 39.836 | 21.4408 | منجز | No
2100059894 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 29348125.79 | 1467406.2895 | 24682775.39 | 24682775.39 | 1010155869 | لا | 0 | 181101269794 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-03-04 | 2019-02-01 | 2022-12-31 | 2022-12-31 |  |  | تأخرصرف المستحقات المالية |  | 39.1677 | 21.5008 | متأخر | No
2100060933 | جامعة الطائف | تشييد | ذات اولوية متوسطة | 127774289.7 | 6388714.485 | 114996744.61 | 114996744.61 | 1010046693 | لا | 0 | 181109320318 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-10-15 | 2017-03-29 | 2020-03-31 | 2020-03-31 | 2017-03-29 |  | لا يوجد تأخير |  | 40.5065 | 21.3211 | منجز | No
2100074270 | جامعة الملك عبدالعزيز | تشييد | لم تعد تحتاجها الجهة | 17498814.4 | 874940.72 | 2774625.9 | 2774625.9 | 1010008634 | لا | 0 | 181101271263 | فسخ العقد | تكلفة العمل المنجز | 15.43 | 15.43 | 2018-07-09 | 2019-04-29 | 2021-12-31 | 2021-12-31 |  |  | أوامر سامية |  | 39.1677 | 21.5008 | مسحوب | No
2100087485 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية متوسطة | 9052861.95 | 452643.0975 | 9052861.89 | 9052861.89 | 5907008656 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2011-11-28 | 2014-05-02 | 2015-02-22 | 2015-02-22 | 2014-05-02 |  |  |  | 41.6531 | 19.8478 | منجز | No
2100043105 | جامعة الملك عبدالعزيز | تشييد | لم تعد تحتاجها الجهة | 88334147.29 | 4416707.3645 | 52953460.98 | 43830243.44 | 1010251358 | لا | 0 | 180709020302 | مسحوب | تكلفة العمل المنجز | 70 | 100 | 2012-08-28 | 2015-01-31 | 2023-12-31 | 2023-12-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.1677 | 21.5008 | مسحوب | No
2100059080 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 7835848.27 | 391792.4135 | 6868729.36 | 6868729.36 | 4030152097 | لا | 0 | 180709029215 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2017-07-30 | 2018-01-27 | 2022-12-31 | 2022-12-31 |  |  | تأخرصرف المستحقات المالية |  | 39.1677 | 21.5008 | متأخر | No
2100042350 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 7110578.63 | 355528.9315 | 3005650.06 | 3005650.06 | 1010046644 | لا | 0 |  | مسحوب | التكلفة المفوترة | 70 | 100 | 2013-07-13 | 2015-10-01 | 2022-05-11 | 2022-05-11 |  |  | ضعف كفاءة المقاول الفنية |  | 40.4511 | 21.2747 | مسحوب | No
2100096062 | جامعة الملك عبدالعزيز | تشييد | لم تعد تحتاجها الجهة | 11912266.41 | 595613.3205 | 5368019.25 | 5368019.25 | 4030016236 | لا | 0 | 180709016076 | فسخ العقد | تكلفة العمل المنجز | 43.68 | 43.68 | 2017-11-13 | 2018-09-09 | 2021-06-30 | 2021-06-30 |  |  | أوامر سامية |  | 39.1677 | 21.5008 | مسحوب | No
2100108275 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية عالية وعاجلة | 34216610 | 1710830.5 | 34216610 | 34216610 | 1116002556 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2011-11-29 | 2014-10-27 | 2015-02-21 | 2015-02-21 | 2014-10-27 |  |  |  | 41.5989 | 27.5017 | منجز | No
2100018782 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 5320969 | 266048.45 | 2188135 | 2188135 | 5860024921 | لا | 0 | 210701047482 | ايقاف جزئي | تكلفة العمل المنجز | 40 | 71 | 2015-08-06 | 2017-07-15 | 2022-12-30 | 2022-12-30 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 41.3446 | 20.0682 | Failed | No
2100190186 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية عالية وعاجلة | 13814777.85 | 690738.8925 | 9986200.49 | 9986200.49 | 1010185929 | لا | 0 | 180709030503 | مسحوب | الكميات التي تم تركيبها | 83 | 100 | 2012-02-26 | 2014-12-26 | 2014-12-26 | 2014-12-26 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 44.2367 | 17.5628 | مسحوب | No
2100190164 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية عالية وعاجلة | 6676987.6 | 333849.38 | 2707834.4 | 2707834.4 | 1010272491 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 51 | 100 | 2013-11-20 | 2017-05-06 | 2017-05-06 | 2017-05-06 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 36.5612 | 28.3865 | مسحوب | No
2100105803 | الهيئة الملكية لمدينة مكة المكرمة و المشاعر المقدسة | تشييد | ذات اولوية عالية وعاجلة | 20916000 | 1045800 | 10102811 | 9037110 | 4031040412 | لا | 0 | 190509071908 | جاري | الكميات التي تم تركيبها | 80 | 100 | 2018-10-24 | 2020-04-06 | 2021-10-01 | 2021-10-01 |  |  | تأخرصرف المستحقات المالية |  | 21.3477 | 39.9601 | Failed | No
2100028523 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 188310228.89 | 9415511.4445 | 133085332.18 | 133085332.18 | 4030008659 | لا | 0 | 190409110385 | جاري | تكلفة العمل المنجز | 97 | 100 | 2012-12-29 | 2014-11-26 | 2022-12-31 | 2022-12-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.1677 | 21.5008 | Failed | No
2100000416 | وزارة الموارد البشرية والتنمية الإجتماعية | تشييد | ذات اولوية منخفضة | 7687112 | 384355.6 | 3007872.78 | 3007872.78 | 4031038849 | لا | 0 | 180501010968 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 100 | 2018-10-03 | 2020-09-11 | 2022-08-23 | 2022-08-23 | 2020-09-11 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.0132 | 21.9309 | منجز | No
2100020370 | أمانة / العاصمة المقدسة | دراسة بيئية | ذات اولوية متوسطة | 2197020 | 109851 | 1945223 | 1945223 | 4031070328 | لا | 0 | 181009187809 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-04-22 | 2021-03-19 | 2021-03-19 | 2021-03-19 |  |  | اخرى |  |  |  | Failed | No
2100001746 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 12082928.66 | 604146.433 | 9884956.21 | 9884956.21 | 1010196220 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-01-23 | 2016-01-13 | 2019-08-01 | 2019-08-01 | 2016-01-13 |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | منجز | No
2100190120 | وزارة البيئة والمياة والزراعة | ترميم | ذات اولوية عالية | 334950 | 16747.5 | 249774 | 249774 | 5801011161 | لا | 0 | 190301078577 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-05-13 | 2019-10-06 | 2021-08-20 | 2021-08-20 | 2019-10-06 |  |  |  | 41.4693 | 20.0179 | منجز | No
2100190256 | وزارة البيئة والمياة والزراعة | توريد وتركيب | ذات اولوية عالية وعاجلة | 137298 | 6864.9 | 0 | 0 | 1010154889 | لا | 0 | 190801113542 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-10-21 | 2020-03-15 | 2020-03-15 | 2020-03-15 | 2020-03-15 |  |  |  | 41.7161 | 27.5027 | منجز | No
2100003824 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 25391542 | 1269577.1 | 18599987 | 18599987 | 1010050730 | لا | 0 |  | مسحوب | التكلفة المفوترة | 75 | 100 | 2011-04-09 | 2013-03-17 | 2018-07-22 | 2018-07-22 |  |  | ضعف كفاءة المقاول الفنية |  | 39.836 | 21.4408 | مسحوب | No
2100088561 | وزارة التعليم | تشييد | ذات اولوية عالية | 18599918.97 | 929995.9485 | 13998709 | 12286142 | 1010060469 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-08-30 | 2017-08-19 | 2019-12-25 | 2019-12-25 | 2017-08-19 |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | منجز | No
2100087426 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 10667716 | 533385.8 | 6814220.21 | 6814220.21 | 1010030949 | لا | 0 | 190209015516 | مسحوب | التكلفة المفوترة | 71 | 90 | 2015-02-21 | 2017-02-10 | 2023-02-02 | 2023-02-02 |  |  | ضعف كفاءة المقاول الفنية |  | 40.2691 | 20.1489 | مسحوب | No
2100058074 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 10753665 | 537683.25 | 0 | 0 | 4030033505 | لا | 0 |  | مسحوب | التكلفة المفوترة | 0 | 100 | 2014-03-19 | 2016-03-08 | 2022-05-31 | 2022-05-31 |  |  | ضعف كفاءة المقاول الفنية |  | 40.2691 | 20.1489 | مسحوب | No
2100096740 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 4375494.24 | 218774.712 | 1902599 | 1902599 | 2050052248 | لا | 0 | 190409017583 | مسحوب | التكلفة المفوترة | 40 | 100 | 2014-10-21 | 2017-04-08 | 2023-02-08 | 2023-02-08 |  |  | ضعف كفاءة المقاول الفنية |  | 40.4511 | 21.2747 | مسحوب | No
2100000744 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البرية | تشييد | ذات اولوية متوسطة | 15750000 | 787500 | 15750000 | 15750000 | 3550023851 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-10-13 | 2021-04-30 | 2020-08-10 | 2020-08-10 | 2021-04-30 |  | موافقات |  | 36.6072 | 28.3378 | منجز | No
2100006436 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البرية | تشييد | ذات اولوية متوسطة | 5277355 | 263867.75 | 5277355 | 5277355 | 4650050716 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 61.41 | 100 | 2015-05-12 | 2016-10-24 | 2016-10-24 | 2016-10-24 |  |  | لا يوجد تأخير | أخرى | 39.6405 | 24.538 | مسحوب | No
2100010312 | أمانة / جدة | ترميم | ذات اولوية متوسطة | 89225491 | 4461274.55 | 88491898.75 | 77912943.55 | 1010403954 | لا | 0 | 190201011048 | جاري | مدفوعات ساعات العمل | 97 | 100 | 2019-04-01 | 2022-03-31 | 2022-10-30 | 2022-10-30 |  |  | اخرى |  | 39.1847 | 21.4902 | منتظم | No
2100012806 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 2816990.36 | 140849.518 | 2816990.36 | 2816990.36 | 4032026620 | لا | 0 | 180809056576 | مسحوب | تكلفة العمل المنجز | 52 | 100 | 2019-03-18 | 2020-09-06 | 2021-09-02 | 2021-09-02 |  |  | اخرى |  | 40.4175 | 21.2566 | مسحوب | No
2100006871 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2079801.88 | 103990.094 | 291206.6 | 256873.38 | 5810007079 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 16 | 100 | 2015-05-09 | 2016-03-25 | 2023-02-02 | 2023-02-02 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 41.4779 | 20.0185 | مسحوب | No
2100017533 | وزارة التعليم | تشييد | ذات اولوية عالية | 1392200 | 69610 | 1122726.6 | 1122726.6 | 4650005144 | لا | 0 |  | مسحوب | التكلفة المفوترة | 80 | 100 | 2007-11-02 | 2008-10-28 | 2022-04-15 | 2022-04-15 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | مسحوب | No
2100011561 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 17603955 | 880197.75 | 10198004 | 10198004 | 1010187466 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 75 | 100 | 2013-12-18 | 2017-06-30 | 2018-09-13 | 2018-09-13 | 2017-06-30 |  | ضعف كفاءة المقاول الفنية |  | 48.9668 | 28.4872 | منجز | No
2100012773 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 68348103 | 3417405.15 | 53454936.15 | 28138107.39 | 5950002027 | لا | 0 | 180709017298 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 91.26 | 100 | 2015-07-22 | 2021-06-30 | 2022-11-09 | 2022-11-09 | 2021-06-30 |  | ضعف كفاءة المقاول الفنية |  | 44.2405 | 17.5381 | منجز | No
2100019272 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 9691000 | 484550 | 4845500.71 | 0 | 5950018186 | لا | 0 | 200309018617 | جاري | تكلفة العمل المنجز | 78 | 83 | 2019-11-02 | 2023-11-26 | 2023-11-26 | 2023-11-26 |  |  | أوامر تغيير |  | 44.2293 | 17.5725 | منتظم | Yes
2100019036 | أمانة / الجوف | تشييد | ذات اولوية عالية | 1461400 | 73070 | 0 | 0 | 3452007751 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 0 | 100 | 2015-12-12 | 2016-03-05 | 2016-03-06 | 2016-03-06 |  |  | تأخرصرف المستحقات المالية |  | 37.1473 | 31.4806 | مسحوب | No
2100017592 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 27910000 | 1395500 | 27910000 | 27910000 | 5810001890 | لا | 0 | 180801056581 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-01-20 | 2019-10-19 | 2020-02-16 | 2020-02-16 | 2019-10-19 |  |  |  | 40.4172 | 21.2586 | منجز | No
2100018852 | وزارة الدفاع / الإدارة الهندسية والاشغال بقوات الدفاع الجوي | تشييد | ذات اولوية متوسطة | 12945011.76 | 647250.588 | 12945011.76 | 11608874.12 | 5800010841 | لا | 0 | 190801015252 | جاري | الكميات التي تم تركيبها | 94 | 100 | 2019-09-26 | 2021-07-30 | 2022-06-06 | 2022-06-06 |  |  | أوامر سامية |  | 39.153 | 21.4414 | Failed | No
2100025211 | وزارة الموارد البشرية والتنمية الإجتماعية | إشراف | ذات اولوية منخفضة | 439740 | 21987 | 356167 | 356167 | 1010431915 | لا | 0 | 190209044347 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-07-03 | 2020-07-02 | 2021-12-15 | 2021-12-15 | 2020-07-02 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.48 | 20.0076 | منجز | No
2100024570 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 489500 | 24475 | 330225.03 | 330225.03 | 4034000979 | لا | 0 | 181001152597 | فسخ العقد | تكلفة العمل المنجز | 64 | 100 | 2018-02-11 | 2019-02-06 | 2022-01-01 | 2022-01-01 |  |  | اخرى |  | 41.6265 | 21.1994 | مسحوب | No
2100020856 | وزارة الشـؤون الاسلامية والدعوة والارشاد | تشييد | ذات اولوية عالية | 2980700 | 149035 | 0 | 0 | 4033000967 | لا | 0 | 200909097094 | جاري | الكميات التي تم تركيبها | 100 | 100 | 2018-04-03 | 2019-09-16 | 2021-09-26 | 2021-09-26 |  |  | تأخرصرف المستحقات المالية |  | 41.7577 | 22.4301 | Failed | No
2100022470 | أمانة / الجوف | تحديث وتوريد | ذات اولوية متوسطة | 10171250 | 508562.5 | 9899264 | 9899264 | 1010076578 | لا | 0 | 180801052742 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-09-10 | 2020-03-03 | 2023-02-23 | 2023-02-23 |  |  | اخرى |  | 40.1032 | 29.8663 | متأخر | No
2100071201 | شركة المياه الوطنية / منطقة القصيم | تصميم وإشراف | ذات اولوية عالية | 21730221.06 | 1086511.053 | 20644470.75 | 20644470.75 | 1010348048 | لا | 0 | 180709020402 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2011-06-18 | 2015-11-18 | 2021-08-17 | 2021-08-17 | 2015-11-18 |  | لا يوجد تأخير |  | 44.0117 | 26.3224 | منجز | No
2100027926 | أمانة / تبوك | تشييد | ذات اولوية عالية وعاجلة | 19915890.75 | 995794.5375 | 6771402 | 6771402 | 4650021867 | لا | 0 | 190701208934 | جاري | الكميات التي تم تركيبها | 90 | 80 | 2019-10-16 | 2022-10-15 | 2023-04-12 | 2023-04-12 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5656 | 28.391 | منتظم | No
2100028486 | أمانة / جازان | تشييد | ذات اولوية عالية | 1972655 | 98632.75 | 1709244 | 1709244 | 5950011723 | لا | 0 | 191201021114 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 92 | 100 | 2019-04-29 | 2020-04-23 | 2021-08-12 | 2021-08-12 | 2020-04-23 |  | ضعف كفاءة المقاول الفنية |  | 42.9403 | 17.2376 | منجز | No
2100027764 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 18070500 | 903525 | 989060.65 | 989060.65 | 5950014853 | لا | 0 | 210601172735 | جاري | الكميات التي تم تركيبها | 49.02 | 55 | 2019-08-31 | 2025-11-25 | 2025-11-25 | 2025-11-25 |  |  | أوامر تغيير |  | 44.2389 | 17.5524 | متأخر | No
2100103644 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 14594546 | 729727.3 | 2918909 | 2918909 | 4030065868 | لا | 0 |  | مسحوب | التكلفة المفوترة | 20 | 100 | 2010-05-11 | 2012-04-19 | 2022-05-19 | 2022-05-19 |  |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | مسحوب | No
2100028055 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 7597799.3 | 379889.965 | 5075280 | 3566047 | 5805000659 | لا | 0 |  | جاري | تكلفة العمل المنجز | 69 | 100 | 2014-08-13 | 2023-09-25 | 2022-06-01 | 2022-06-01 |  |  | ضعف كفاءة المقاول الفنية |  | 41.4514 | 20.0766 | Failed | No
2100024496 | أمانة / الباحة | تشييد | ذات اولوية عالية وعاجلة | 1351654 | 67582.7 | 1351654 | 0.0013517 | 5806008614 | لا | 0 | 210601084360 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-11-06 | 2020-10-27 | 2022-05-01 | 2022-05-01 | 2020-10-27 |  |  |  | 41.4693 | 20.0083 | منجز | No
2100033740 | أمانة / الباحة | تشييد | ذات اولوية منخفضة | 1990560 | 99528 | 1990560 | 1491024 | 5801009694 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2010-02-18 | 2011-02-18 | 2011-02-19 | 2011-02-19 | 2011-02-18 |  | ضعف كفاءة المقاول الفنية |  | 41.631 | 20.0951 | منجز | No
2100033342 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 2392190.85 | 119609.5425 | 1112505.1 | 1112505.1 | 5950016273 | لا | 0 | 210501030518 | جاري | تكلفة العمل المنجز | 86 | 100 | 2019-11-30 | 2021-06-01 | 2023-03-30 | 2023-03-30 |  |  | اخرى |  | 44.2377 | 17.6026 | Failed | No
2100033272 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 783825 | 39191.25 | 783825 | 783825 | 4046001026 | لا | 0 | 191201016944 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-11-27 | 2020-11-21 | 2020-11-21 | 2020-11-21 | 2020-11-21 |  |  |  | 40.9869 | 21.0587 | منجز | No
2100033224 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1000000 | 50000 | 899120.33 | 899120.33 | 4046001026 | لا | 0 | 201101202155 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-10-30 | 2020-08-25 | 2021-01-19 | 2021-01-19 | 2020-08-25 |  |  |  | 40.4303 | 22.4874 | منجز | No
2100033854 | أمانة / الباحة | تشييد | ذات اولوية عالية | 1886039 | 94301.95 | 156928.58 | 156928.58 | 5800011027 | لا | 0 | 200601005709 | مسحوب | تكلفة العمل المنجز | 16 | 100 | 2019-10-30 | 2022-10-21 | 2022-12-30 | 2022-12-30 |  |  | ضعف كفاءة المقاول الفنية |  | 41.4562 | 20.0227 | مسحوب | No
2100023461 | جامعة الملك فيصل | تشييد | ذات اولوية متوسطة | 26389893.75 | 1319494.6875 | 17577672.03 | 17577672.03 | 1010006362 | لا | 0 | 180809056667 | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2011-08-27 | 2013-08-03 | 2014-05-14 | 2014-05-14 |  | 2013-08-03 | ضعف كفاءة المقاول الفنية |  | 49.5604 | 25.3897 | منجز | No
2100092584 | أمانة / جازان | تشييد | ذات اولوية عالية | 815865 | 40793.25 | 151500 | 151500 | 5907014756 | لا | 0 | 181009117100 | مسحوب | تكلفة العمل المنجز | 20 | 100 | 2014-09-08 | 2015-06-04 | 2015-06-05 | 2015-06-05 |  |  | اخرى |  | 42.5784 | 16.8834 | مسحوب | No
2100035420 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 1300000 | 65000 | 1300000 | 1300000 | 5907007322 | لا | 0 | 180801063072 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-09-15 | 2019-09-10 | 2019-09-10 | 2019-09-10 | 2019-09-10 |  | اخرى |  | 42.9315 | 16.5914 | منجز | No
2100036083 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 1538400 | 76920 | 495000 | 0 | 3350017944 | لا | 0 | 190201038969 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 70 | 100 | 2018-12-16 | 2019-12-10 | 2021-07-19 | 2021-07-19 | 2019-12-10 |  |  |  | 42.1272 | 26.5036 | منجز | Yes
2100034996 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 1699700 | 84985 | 1699700 | 1699700 | 4030198598 | لا | 0 | 200209128025 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-12-26 | 2020-12-25 | 2020-12-03 | 2020-12-03 | 2020-12-25 |  | تأخرصرف المستحقات المالية |  | 41.0787 | 19.1281 | منجز | No
2100021335 | جامعة الملك فيصل | تشييد | ذات اولوية عالية | 1500000 | 75000 | 1500000 | 1500000 | 1010423886 | لا | 0 | 181109354524 | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2014-12-15 | 2015-06-10 | 2015-01-19 | 2015-01-19 |  | 2015-06-10 | تأخرصرف المستحقات المالية |  | 49.5604 | 25.3897 | منجز | No
2100044634 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 32457796.12 | 1622889.806 | 30546379.07 | 30546379.07 | 4030138988 | لا | 0 | 180809052023 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-08-03 | 2016-07-23 | 2020-12-31 | 2020-12-31 | 2016-07-23 |  |  |  | 40.4204 | 21.2744 | منجز | No
2100044122 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 626200 | 31310 | 626200 | 626200 | 4031046917 | لا | 0 | 180809065150 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2017-11-07 | 2018-05-06 | 2018-05-06 | 2018-05-06 | 2018-05-06 |  | ضعف كفاءة المقاول الفنية |  | 42.0287 | 21.9246 | منجز | No
2100041031 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البرية | تشييد | ذات اولوية متوسطة | 4392998.82 | 219649.941 | 4392998.82 | 3286752.53 | 1011012750 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-03-23 | 2020-03-11 | 2021-01-10 | 2021-01-10 | 2020-03-11 |  | تأخرصرف المستحقات المالية |  | 36.5513 | 28.3302 | منجز | No
2100037376 | أمانة / الجوف | تشييد | ذات اولوية عالية | 2706500 | 135325 | 2706500 | 2706500 | 1131013633 | لا | 0 | 200601035515 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-07-20 | 2015-07-20 | 2019-09-10 | 2019-09-10 | 2015-07-20 |  | تأخرصرف المستحقات المالية |  | 37.9812 | 30.7109 | منجز | No
2100047143 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 1025942 | 51297.1 | 0 | 0 | 5950015855 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 7 | 100 | 2015-08-16 | 2016-08-03 | 2016-08-03 | 2016-08-03 |  |  | ضعف كفاءة المقاول الفنية |  | 44.2292 | 17.5493 | مسحوب | No
2100048311 | أمانة / جازان | تشييد | لم تعد تحتاجها الجهة | 406100 | 20305 | 223000 | 223000 | 4030145153 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 55 | 100 | 2011-12-04 | 2012-06-01 | 2012-06-02 | 2012-06-02 |  |  | اخرى |  | 42.967 | 16.5296 | مسحوب | No
2100050864 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 2716400 | 135820 | 2716400 | 2716400 | 5800007789 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 83 | 2019-02-04 | 2021-02-03 | 2020-10-21 | 2020-10-21 | 2021-02-03 |  | اخرى |  | 41.0863 | 19.1272 | منجز | No
2100045544 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1486800 | 74340 | 774989.36 | 774989.36 | 4044000973 | لا | 0 | 200401088162 | مسحوب | تكلفة العمل المنجز | 52 | 100 | 2019-01-21 | 2020-11-15 | 2022-01-01 | 2022-01-01 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 40.8207 | 20.7238 | مسحوب | No
2100048112 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 499940 | 24997 | 499940 | 499940 | 4032027280 | لا | 0 | 190509024772 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-07-29 | 2019-07-24 | 2019-07-24 | 2019-07-24 | 2019-07-24 |  |  |  | 42.0236 | 21.9211 | منجز | No
2100077700 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 3567275 | 178363.75 | 2049700 | 2049700 | 4031054258 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 73 | 73 | 2014-06-16 | 2015-11-29 | 2021-06-29 | 2021-06-29 |  |  | اخرى |  | 39.3845 | 21.8993 | مسحوب | No
2100050153 | أمانة / حائل | تشييد | ذات اولوية عالية | 75128 | 3756.4 | 67500.5 | 67500.5 | 3350025993 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-09-29 | 2019-12-29 | 2020-02-03 | 2020-02-03 | 2019-12-29 |  |  |  | 43.0122 | 27.4588 | منجز | No
2100054681 | أمانة / العاصمة المقدسة | تشييد | لم تعد تحتاجها الجهة | 16884000 | 844200 | 15720705 | 15720705 | 4031038849 | لا | 0 | 180909066436 | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2018-07-15 | 2018-10-12 | 2019-10-04 | 2019-10-04 | 2018-10-12 | 2021-08-25 |  |  | 39.8062 | 21.4091 | منجز | No
2100053524 | أمانة / جازان | تشييد | ذات اولوية عالية وعاجلة | 1391450 | 69572.5 | 1391450 | 1391450 | 5907007322 | لا | 0 | 190609013521 | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2015-08-23 | 2016-08-17 | 2020-02-20 | 2020-02-20 | 2016-08-17 |  | ضعف كفاءة المقاول الفنية |  | 42.5743 | 16.8973 | منجز | No
2100051612 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 6999980 | 349999 | 3534990 | 1408000 | 3553000678 | لا | 0 | 190301070101 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 77 | 2019-06-11 | 2021-06-11 | 2021-09-01 | 2021-09-01 | 2021-06-11 |  |  |  | 34.9451 | 29.2864 | منجز | No
2100052953 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 2297080.8 | 114854.04 | 1731838 | 1731838 | 5800010841 | لا | 0 | 190801009888 | منجز – استلام ابتدائي | التكلفة المفوترة | 75.87 | 75.87 | 2019-09-07 | 2020-08-27 | 2020-11-25 | 2020-11-25 | 2020-08-27 |  |  |  | 39.8659 | 21.3772 | منجز | No
2100051096 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 1712870 | 85643.5 | 0 | 0 | 3350017944 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-04-06 | 2019-12-10 | 2021-04-12 | 2021-04-12 | 2019-12-10 |  |  |  | 42.1212 | 26.4879 | منجز | No
2100050330 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 6315925 | 315796.25 | 2899190.35 | 1659022.06 | 5800007456 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 46 | 100 | 2015-01-14 | 2017-01-14 | 2021-06-13 | 2021-06-13 |  |  | ضعف كفاءة المقاول الفنية |  | 41.4716 | 20.0092 | مسحوب | No
2100053432 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 3662202 | 183110.1 | 3295688 | 3295688 | 4030006066 | لا | 0 |  | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 98.48 | 98.48 | 2018-11-13 | 2019-11-09 | 2023-02-01 | 2023-02-01 |  |  | سوء التخطيط الاولي للمشروع |  | 41.5353 | 19.6065 | Failed | No
2100065634 | أمانة / عسير | تشييد | ذات اولوية عالية | 2746300 | 137315 | 622500 | 622500 | 5859004729 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 27 | 100 | 2014-10-28 | 2015-10-24 | 2020-07-07 | 2020-07-07 |  |  | تأخرصرف المستحقات المالية |  |  |  | مسحوب | No
2100056486 | وزارة الصحة / الباحة | تشييد | ذات اولوية متوسطة | 35698327.57 | 1784916.3785 | 28940459.17 | 28098833.16 | 1010132551 | لا | 0 | 181109362485 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-03-19 | 2021-08-13 | 2022-12-06 | 2022-12-06 | 2021-08-13 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.2487 | 20.1948 | منجز | No
2100055904 | وزارة الصحة / الباحة | تشييد | ذات اولوية متوسطة | 14888081 | 744404.05 | 6173986.7 | 5480557.43 | 4030008659 | نعم | 4701422 | 181009183312 | مسحوب | الكميات التي تم تركيبها | 75 | 100 | 2018-05-12 | 2020-12-22 | 2020-12-23 | 2020-12-23 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال | مخطط لإعادة طرحه | 41.4405 | 20.0611 | مسحوب | No
2100063534 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 12377279.25 | 618863.9625 | 9051504 | 299424.62 | 5950014853 | لا | 0 | 220601025060 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 87 | 92 | 2019-05-11 | 2020-04-28 | 2022-09-11 | 2022-09-11 | 2020-04-28 |  |  |  | 44.2249 | 17.5556 | منجز | No
2100062440 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 212987 | 10649.35 | 194866 | 194866 | 5951126918 | لا | 0 | 210501030518 | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2019-07-17 | 2020-05-07 | 2021-09-15 | 2021-09-15 | 2020-05-07 |  |  |  | 44.219 | 17.5433 | منجز | No
2100046524 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 17997125 | 899856.25 | 17007287.7 | 17007287.7 | 4605002907 | لا | 0 | 190709018770 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-10-10 | 2019-10-05 | 2021-05-10 | 2021-05-10 | 2019-10-05 |  | ضعف كفاءة المقاول الفنية |  | 42.854 | 21.262 | منجز | No
2100059441 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 4162542 | 208127.1 | 0 | 0 | 2251033167 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 8 | 100 | 2008-04-08 | 2009-10-01 | 2023-05-03 | 2023-05-03 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.5429 | 16.8808 | مسحوب | No
2100060712 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 1999500 | 99975 | 1713440 | 1713440 | 5805003133 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 89.73 | 89.73 | 2015-02-25 | 2016-05-14 | 2021-07-27 | 2021-07-27 | 2016-05-14 |  | تأخرصرف المستحقات المالية |  | 41.3882 | 20.3871 | منجز | No
2100058671 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2362607 | 118130.35 | 973199.39 | 973199.39 | 5859000660 | لا | 0 |  | مسحوب | التكلفة المفوترة | 54 | 100 | 2014-04-15 | 2015-07-08 | 2022-03-09 | 2022-03-09 |  |  | ضعف كفاءة المقاول الفنية |  | 42.1351 | 19.1255 | مسحوب | No
2100064385 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 3097494 | 154874.7 | 0 | 0 | 5950011905 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 0 | 100 | 2015-10-28 | 2016-10-22 | 2016-10-22 | 2016-10-22 |  |  | تأخرصرف المستحقات المالية |  | 42.9522 | 16.7114 | مسحوب | No
2100068854 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 17637600 | 881880 | 11852893 | 11852893 | 1010006004 | لا | 0 | 181209510856 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 80 | 100 | 2015-10-03 | 2017-10-03 | 2021-08-05 | 2021-08-05 | 2017-10-03 |  | ضعف كفاءة المقاول الفنية |  | 42.5728 | 16.8823 | منجز | No
2100011664 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 19998909 | 999945.45 | 12029848 | 9623362 | 5950000060 | لا | 0 |  | جاري | تكلفة العمل المنجز | 78.08 | 83 | 2019-01-02 | 2022-11-13 | 2023-03-30 | 2023-03-30 |  |  | التنسيق مع أصحاب المصلحه (خدمات |  | 44.2154 | 17.5564 | منتظم | No
2100066916 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 1898969.6 | 94948.48 | 187616 | 187616 | 4031057370 | لا | 0 | 180909106408 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 54.39 | 54.39 | 2014-12-11 | 2017-11-08 | 2018-08-24 | 2018-08-24 |  |  |  |  | 39.8939 | 21.3482 | Failed | No
2100023984 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1012219 | 50610.95 | 271090 | 271090 | 4036000759 | لا | 0 | 181009124740 | مسحوب | تكلفة العمل المنجز | 25 | 100 | 2015-03-18 | 2016-03-12 | 2016-03-12 | 2016-03-12 |  |  | ضعف كفاءة المقاول الفنية |  | 42.8474 | 21.2558 | مسحوب | No
2100076381 | أمانة / جازان | تشييد | ذات اولوية عالية وعاجلة | 1298000 | 64900 | 622546.55 | 622546.55 | 7007298198 | لا | 0 | 181009150196 | مسحوب | الكميات التي تم تركيبها | 50 | 100 | 2018-09-10 | 2019-03-10 | 2019-11-05 | 2019-11-05 |  |  | ضعف كفاءة المقاول الفنية |  | 42.6983 | 16.9772 | مسحوب | No
2100069403 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 3727500 | 186375 | 3618134 | 3618134 | 5850017300 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 97 | 97 | 2019-10-19 | 2020-10-13 | 2020-10-08 | 2020-10-08 | 2020-10-13 |  |  |  | 42.5979 | 16.9058 | منجز | No
2100069300 | وزارة الدفاع / الإدارة الهندسية والاشغال بالخدمات الصحية | تشييد | ذات اولوية متوسطة | 98127455.67 | 4906372.7835 | 88200851.73 | 88200851.73 | 1010010873 | لا | 0 | 180909090598 | جاري | الكميات التي تم تركيبها | 96 | 100 | 2013-02-02 | 2015-12-31 | 2022-11-20 | 2022-11-20 |  |  | اخرى |  | 39.3526 | 21.5083 | منتظم | No
2100069554 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 66078919 | 3303945.95 | 59400070 | 59400070 | 1010066115 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2012-11-12 | 2015-05-02 | 2015-05-02 | 2015-05-02 | 2015-05-02 | 2021-10-10 |  |  | 42.177 | 18.917 | منجز | No
2100068316 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 3544350 | 177217.5 | 963026.5 | 711025.92 | 5851000110 | لا | 0 | 191001284315 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-08-04 | 2020-07-29 | 2022-01-01 | 2022-01-01 | 2020-07-29 |  |  |  | 42.8475 | 21.2539 | منجز | No
2100067406 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 3275000 | 163750 | 2440041.25 | 2440041.25 | 4031045634 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 74.51 | 74.51 | 2012-11-26 | 2013-11-26 | 2018-03-21 | 2018-03-21 |  |  |  |  | 40.0082 | 21.9891 | مسحوب | No
2100069031 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 3105110 | 155255.5 | 1486600 | 1486600 | 5808100024 | لا | 0 |  | جاري | تكلفة العمل المنجز | 88 | 100 | 2019-03-18 | 2021-09-11 | 2022-12-30 | 2022-12-30 |  |  |  |  | 41.2457 | 19.9451 | Failed | No
2100071105 | أمانة / حائل | دراسة الجدوى | ذات اولوية متوسطة | 3900000 | 195000 | 2387688 | 845783 | 1010326184 | لا | 0 | 181101360439 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-08-29 | 2021-02-14 | 2021-04-06 | 2021-04-06 | 2021-02-14 |  | ضعف كفاءة المقاول الفنية |  | 41.7221 | 27.5088 | منجز | No
2100075784 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 327000 | 16350 | 327000 | 327000 | 4032027280 | لا | 0 | 181001141058 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-07-09 | 2019-06-12 | 2019-06-12 | 2019-06-12 | 2016-06-12 |  |  |  | 40.8292 | 20.7258 | منجز | No
2100080500 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 4392934.5 | 219646.725 | 3330000 | 1124078.2 | 5950006860 | لا | 0 | 181209477572 | جاري | اخرى | 82.63 | 87 | 2018-04-29 | 2022-09-08 | 2023-03-30 | 2023-03-30 |  |  |  |  | 44.2205 | 17.5397 | متأخر | No
2100053340 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 1630400 | 81520 | 1700274.27 | 1537234.27 | 5806008614 | لا | 0 | 191001188470 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-10-24 | 2020-04-07 | 2020-04-07 | 2020-04-07 | 2020-04-07 |  | ضعف كفاءة المقاول الفنية |  | 40.8639 | 20.4193 | منجز | No
2100071805 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 253187.5 | 12659.375 | 253187.5 | 253187.5 | 4031046917 | لا | 0 | 181001160635 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2017-11-08 | 2018-05-06 | 2019-06-12 | 2019-06-12 | 2018-05-06 |  |  |  | 42.0237 | 21.9199 | منجز | No
2100072343 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 2340175.2 | 117008.76 | 1211913.6 | 1211913.6 | 3350000614 | لا | 0 | 180909106131 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-07-24 | 2021-03-06 | 2021-04-06 | 2021-04-06 | 2021-03-06 |  |  |  | 42.1252 | 26.4957 | منجز | No
2100079026 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 33202901.6 | 1660145.08 | 14369003.12 | 0 | 1010046644 | لا | 0 |  | مسحوب | التكلفة المفوترة | 55 | 100 | 2014-02-04 | 2016-09-20 | 2016-09-20 | 2016-09-20 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5604 | 25.3897 | مسحوب | Yes
2100007825 | صندوق تنمية الموارد البشرية | تشييد | ذات اولوية منخفضة | 29844194.81 | 1492209.7405 | 24331647.15 | 24123837.11 | 1131022493 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 81.53 | 100 | 2015-02-09 | 2017-01-29 | 2021-12-30 | 2021-12-30 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 50.1071 | 26.4051 | مسحوب | No
2100078971 | وزارة الموارد البشرية والتنمية الإجتماعية | إشراف | ذات اولوية منخفضة | 1159200 | 57960 | 1888879.5 | 1888879.5 | 1010320575 | لا | 0 | 181109259201 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 100 | 2018-10-03 | 2020-09-11 | 2023-08-22 | 2023-08-22 | 2020-09-11 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.0286 | 21.9246 | منجز | No
2100081395 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 3932740 | 196637 | 435685 | 435685 | 4032032153 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 45 | 100 | 2015-08-03 | 2016-11-26 | 2020-12-22 | 2020-12-22 |  |  | ضعف كفاءة المقاول الفنية |  | 39.2065 | 21.5218 | مسحوب | No
2100053034 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 13431667 | 671583.35 | 13431614.4 | 13431614.4 | 4030165325 | لا | 0 | 200609077947 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-08-15 | 2016-08-19 | 2018-01-15 | 2018-01-15 | 2016-08-19 |  |  |  | 40.4507 | 21.2876 | منجز | No
2100003312 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 12304839.43 | 615241.9715 | 9286689.4 | 8648092.77 | 4030140863 | لا | 0 | 190209015470 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-09-08 | 2016-08-28 | 2021-11-17 | 2021-11-17 | 2016-08-28 |  | ضعف كفاءة المقاول الفنية |  | 40.2691 | 20.1489 | منجز | No
2100077070 | أمانة / الباحة | تشييد | ذات اولوية عالية | 248730 | 12436.5 | 224735 | 0 | 5802010434 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-11-23 | 2019-08-14 | 2019-09-14 | 2019-09-14 | 2019-08-14 |  | تأخرصرف المستحقات المالية |  | 41.3883 | 20.3871 | منجز | Yes
2100035851 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 6543535 | 327176.75 | 3722991.8 | 3722991.8 | 5950018572 | لا | 0 | 180909110387 | مسحوب | تكلفة العمل المنجز | 55 | 100 | 2014-05-16 | 2015-05-22 | 2019-10-01 | 2019-10-01 |  |  | اخرى |  | 43.2177 | 16.7813 | مسحوب | No
2100092352 | أمانة / جازان | تشييد | ذات اولوية عالية | 3972280.09 | 198614.0045 | 2224476.8504 | 2224476.85 | 1010265080 | لا | 0 | 180809062239 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-05-18 | 2015-05-12 | 2021-08-05 | 2021-08-05 | 2015-05-12 |  | ضعف كفاءة المقاول الفنية |  | 42.676 | 16.8961 | منجز | No
2100083904 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 61990200 | 3099510 | 61615200 | 61615200 | 5900007895 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2011-07-06 | 2018-09-01 | 2018-09-01 | 2018-09-01 | 2018-09-01 | 2020-11-29 |  |  | 42.5478 | 18.2485 | منجز | No
2100085260 | أمانة / جدة | أخرى | ذات اولوية متوسطة | 3990000 | 199500 | 3990000 | 3990000 | 4030287664 | لا | 0 | 181101349119 | منجز – استلام نهائي | تكلفة العمل المنجز | 45 | 60 | 2018-12-25 | 2019-12-25 | 2019-12-25 | 2019-12-25 | 2019-12-25 | 2019-12-26 | اخرى |  |  |  | منجز | No
2100079402 | وزارة التعليم | تشييد | ذات اولوية عالية | 2338690 | 116934.5 | 0 | 0 | 5859000660 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0 | 100 | 2014-02-13 | 2017-05-03 | 2024-05-08 | 2024-05-08 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.1351 | 19.1255 | مسحوب | No
2100090123 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 22969602 | 1148480.1 | 18036777.52 | 12003918.68 | 1010178838 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-04-12 | 2017-07-01 | 2019-09-10 | 2019-09-10 | 2017-07-01 |  |  |  | 39.6005 | 24.4595 | منجز | No
2100047983 | شركة المياه الوطنية / منطقة نجران | دراسات هندسية | ذات اولوية عالية وعاجلة | 8260000 | 413000 | 8260000 | 8260000 | 7009417382 | لا | 0 | 180901112107 | منجز – استلام ابتدائي | التكلفة المفوترة | 99.98 | 100 | 2018-12-23 | 2021-06-23 | 2021-03-25 | 2021-03-25 | 2021-06-23 |  | لا يوجد تأخير |  | 44.2073 | 17.5284 | منجز | No
2100087054 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 600339583.92 | 30016979.196 | 296055358.22 | 296055358.22 | 2055002293 | نعم | 359203478.02 | 180809059196 | مسحوب | منهجية القيمة المكتسبة | 56 | 100 | 2014-11-10 | 2018-11-05 | 2024-06-09 | 2024-06-09 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 49.6626 | 27.0037 | مسحوب | No
2100008422 | وزارة التعليم | تشييد | ذات اولوية عالية | 2359384.25 | 117969.2125 | 1624509 | 1624509 | 4031030655 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 89 | 100 | 2010-05-28 | 2011-05-18 | 2022-12-22 | 2022-12-22 |  |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | مسحوب | No
2100086225 | وزارة التعليم | تشييد | ذات اولوية عالية | 6828165.85 | 341408.2925 | 949088 | 0 | 5950007285 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 10 | 100 | 2014-06-10 | 2015-12-02 | 2024-02-01 | 2024-02-01 |  |  | ضعف كفاءة المقاول الفنية |  | 42.6509 | 17.1567 | مسحوب | Yes
2100044273 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 2804265 | 140213.25 | 2804265 | 2804265 | 2050007224 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-11-05 | 2019-10-26 | 2019-09-26 | 2019-09-26 |  | 2019-10-26 | لا يوجد تأخير |  | 39.2351 | 21.5467 | منجز | No
2100093240 | أمانة / جازان | دراسة الجدوى | ذات اولوية متوسطة | 484000 | 24200 | 0 | 0 | 5855033035 | لا | 0 | 180909110424 | مسحوب | مدفوعات ساعات العمل | 49 | 100 | 2014-06-01 | 2014-10-28 | 2014-10-28 | 2014-10-28 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | مسحوب | No
2100098685 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 3364485.18 | 168224.259 | 538830.42 | 538830.42 | 2511009886 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2019-06-12 | 2019-12-09 | 2021-02-03 | 2021-02-03 | 2019-12-09 |  | ضعف كفاءة المقاول الفنية |  | 45.975 | 28.4334 | منجز | No
2100094323 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 3846440 | 192322 | 3846440 | 3846440 | 4032015171 | لا | 0 | 190309029240 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-01-07 | 2016-12-27 | 2016-12-27 | 2016-12-27 | 2016-12-27 |  |  |  | 41.7471 | 22.4263 | منجز | No
2100094091 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 3799371 | 189968.55 | 0 | 0 | 4030187031 | لا | 0 | 181009117820 | مسحوب | تكلفة العمل المنجز | 0 | 100 | 2019-04-10 | 2020-10-01 | 2022-01-01 | 2022-01-01 |  |  | ضعف كفاءة المقاول الفنية |  | 42.0282 | 21.9216 | مسحوب | No
2100094124 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 846220 | 42311 | 846220 | 846220 | 4032042299 | لا | 0 | 200609072941 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2013-06-30 | 2013-12-27 | 2013-12-27 | 2013-12-27 | 2013-12-27 |  | ضعف كفاءة المقاول الفنية |  | 41.0734 | 20.4609 | منجز | No
2100097775 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 9358732.73 | 467936.6365 | 4119483.78 | 3023530.48 | 1010060469 | لا | 0 | 190409091382 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2018-09-05 | 2020-08-25 | 2021-09-12 | 2021-09-12 | 2020-08-25 |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | منجز | No
2100092761 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 41749250 | 2087462.5 | 37561548 | 37561548 | 4031019848 | لا | 0 | 180909106458 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 93.41 | 93.41 | 2014-04-10 | 2016-10-08 | 2017-05-13 | 2017-05-13 | 2016-10-08 |  |  |  | 39.8741 | 21.3526 | منجز | No
2100104473 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية وعاجلة | 42051460 | 2102573 | 3515460 | 3515460 | 1116000094 | لا | 0 |  | مسحوب | منهجية القيمة المكتسبة | 8.91 | 100 | 2015-08-10 | 2017-07-19 | 2024-12-30 | 2024-12-30 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.7195 | 27.5126 | مسحوب | No
2100103865 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 6999456.18 | 349972.809 | 0 | 0 | 2251033167 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 25 | 100 | 2008-04-08 | 2009-11-30 | 2023-02-01 | 2023-02-01 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.5429 | 16.8808 | مسحوب | No
2100101275 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 1072400 | 53620 | 1040864 | 1040864 | 3357006967 | لا | 0 | 190609025558 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-06-24 | 2019-06-18 | 2019-06-18 | 2019-06-18 | 2019-06-18 |  | ضعف كفاءة المقاول الفنية |  | 40.5483 | 26.4063 | منجز | No
2100078455 | أمانة / جازان | دراسة الجدوى | ذات اولوية متوسطة | 624750 | 31237.5 | 624750 | 624750 | 4030276223 | لا | 0 | 191001087086 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-03-19 | 2019-06-03 | 2019-06-02 | 2019-06-02 | 2019-06-03 |  | اخرى |  | 42.5708 | 16.8877 | منجز | No
2100101194 | هيئة الهلال الأحمر السعودي | تشييد | ذات اولوية عالية | 802520 | 40126 | 338486.56 | 338486.56 | 1010175017 | لا | 0 | 181009154349 | مسحوب | الكميات التي تم تركيبها | 30 | 100 | 2017-09-25 | 2018-07-25 | 2018-08-25 | 2018-08-25 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 40.5584 | 30.6598 | مسحوب | No
2100103703 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1430091 | 71504.55 | 1206382.38 | 1206382.38 | 3350017342 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 86 | 100 | 2005-12-06 | 2007-07-12 | 2019-02-13 | 2019-02-13 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 41.6968 | 27.506 | مسحوب | No
2100106352 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 9396334 | 469816.7 | 1707971.19 | 0 | 1132002570 | لا | 0 |  | مسحوب | التكلفة المفوترة | 21 | 100 | 2013-11-17 | 2015-11-07 | 2020-10-28 | 2020-10-28 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | مسحوب | Yes
2100106481 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | تشييد | ذات اولوية متوسطة | 79638620.62 | 3981931.031 | 25758499.27 | 25758499.27 | 1010147053 | لا | 0 | 180500233265 | ايقاف كلي | تكلفة العمل المنجز | 42 | 100 | 2015-06-04 | 2017-05-12 | 2023-12-31 | 2023-12-31 |  |  | تأخرصرف المستحقات المالية |  | 36.6289 | 28.4408 | Failed | No
2100109314 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 22427937.06 | 1121396.853 | 17093574 | 16994859.91 | 2050018834 | لا | 0 |  | مسحوب | التكلفة المفوترة | 75 | 100 | 2014-02-03 | 2016-07-22 | 2019-03-24 | 2019-03-24 |  |  | ضعف كفاءة المقاول الفنية |  | 50.5176 | 26.4644 | مسحوب | No
2100108323 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البرية | تشييد | ذات اولوية متوسطة | 13792420 | 689621 | 11835851.1 | 11835851.1 | 1010206690 | لا | 0 |  | جاري | تكلفة العمل المنجز | 95 | 100 | 2019-12-06 | 2021-11-22 | 2023-04-01 | 2023-04-01 |  |  | لا يوجد تأخير |  | 42.5996 | 16.9099 | Failed | No
2100042803 | وزارة الحج والعمرة | تشييد | ذات اولوية عالية وعاجلة | 4071028 | 203551.4 | 910935.28 | 910935.28 | 4030170574 | لا | 0 | 190901175460 | جاري | الكميات التي تم تركيبها | 30 | 30 | 2019-11-02 | 2022-06-16 | 2022-01-05 | 2022-01-05 |  |  | اخرى |  | 39.9756 | 21.3486 | Failed | No
2100103946 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 9975380 | 498769 | 7073.098 | 3398.681 | 2050017509 | لا | 0 |  | مسحوب | التكلفة المفوترة | 35 | 100 | 2009-05-07 | 2011-04-16 | 2011-04-16 | 2011-04-16 |  |  | ضعف كفاءة المقاول الفنية |  | 48.173 | 27.5578 | مسحوب | No
2100099164 | جامعة الملك خالد | تشييد | ذات اولوية عالية وعاجلة | 54133008.07 | 2706650.4035 | 42146204.28 | 39396237.64 | 1010140609 | لا | 0 | 181109258899 | جاري | تكلفة العمل المنجز | 96.37 | 100 | 2013-04-14 | 2015-04-14 | 2022-10-17 | 2022-10-17 |  |  | تأخرصرف المستحقات المالية |  | 42.8114 | 18.1027 | منتظم | No
2100101430 | شركة الكهرباء | تشييد | ذات اولوية متوسطة | 20465592 | 1023279.6 | 6670623 | 6670623 | 2050004063 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2015-09-17 | 2017-12-12 | 2022-09-30 | 2022-09-30 | 2017-12-12 |  | تصاريح أعمال التنفيذ |  | 39.8744 | 21.4771 | منجز | No
2100008886 | وزارة التعليم | تشييد | ذات اولوية عالية | 11796849.95 | 589842.4975 | 3569414 | 3006583.45 | 1010181431 | لا | 0 |  | ايقاف كلي | التكلفة المفوترة | 75 | 100 | 2016-08-23 | 2018-08-13 | 2022-12-31 | 2022-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | Failed | No
2100108010 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البرية | تشييد | ذات اولوية متوسطة | 4784183.25 | 239209.1625 | 4784183.25 | 4784183.25 | 3550024970 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-07-14 | 2020-04-03 | 2020-04-03 | 2020-04-03 | 2020-04-03 |  | تأخرصرف المستحقات المالية |  | 36.599 | 28.338 | منجز | No
2100015525 | شركة الكهرباء | تشييد | ذات اولوية متوسطة | 114495518 | 5724775.9 | 91568659 | 91568659 | 2050011871 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 88.3 | 100 | 2015-10-21 | 2020-04-15 | 2023-03-30 | 2023-03-30 |  |  | لا يوجد تأخير |  | 49.5967 | 25.419 | Failed | No
2100001341 | المؤسسة العامة للحبوب | تشييد | ذات اولوية عالية وعاجلة | 349302593.93 | 17465129.6965 | 349302593.93 | 349302593.93 | 1010173601 | لا | 0 | 180809056001 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2017-12-02 | 2020-08-31 | 2021-03-31 | 2021-03-31 | 2020-08-31 |  | لا يوجد تأخير |  | 38.1751 | 23.9026 | منجز | No
2100011233 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 11040796.04 | 552039.802 | 6448648.49 | 5740010.14 | 4030140863 | لا | 0 | 190209015491 | مسحوب | التكلفة المفوترة | 65 | 100 | 2015-05-05 | 2017-04-24 | 2023-08-24 | 2023-08-24 |  |  | ضعف كفاءة المقاول الفنية |  | 40.2691 | 20.1489 | مسحوب | No
2100078330 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية متوسطة | 54117817 | 2705890.85 | 50621173.94 | 50621173.94 | 1010119820 | لا | 0 | 190509087260 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2015-04-06 | 2016-09-17 | 2020-07-01 | 2020-07-01 | 2016-09-17 |  | لا يوجد تأخير |  | 39.2247 | 21.3061 | منجز | No
2100018642 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 12217360.62 | 610868.031 | 9936246.62 | 8663222.45 | 4030140863 | لا | 0 | 190209015475 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-10-15 | 2016-10-04 | 2021-08-05 | 2021-08-05 | 2016-10-04 |  | ضعف كفاءة المقاول الفنية |  | 40.2691 | 20.1489 | منجز | No
2100016936 | وزارة التعليم | تشييد | ذات اولوية عالية | 10049452.65 | 502472.6325 | 4378432.38 | 4378432.38 | 1010187466 | لا | 0 | 190209039857 | مسحوب | التكلفة المفوترة | 52 | 100 | 2013-08-28 | 2015-08-18 | 2022-12-23 | 2022-12-23 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.1677 | 21.5008 | مسحوب | No
2100050621 | أمانة / جازان | تشييد | ذات اولوية عالية | 1913149.75 | 95657.4875 | 1033530 | 0 | 5858046783 | لا | 0 | 190909117509 | مسحوب | الكميات التي تم تركيبها | 70 | 100 | 2015-08-09 | 2019-08-20 | 2020-10-15 | 2020-10-15 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5872 | 16.8372 | مسحوب | Yes
2100050094 | أمانة / جازان | تشييد | ذات اولوية عالية | 6360860 | 318043 | 3171899.93 | 3171899.93 | 5901009711 | لا | 0 | 190309031351 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 90 | 100 | 2014-10-03 | 2015-09-30 | 2021-04-20 | 2021-04-20 | 2015-09-30 |  | ضعف كفاءة المقاول الفنية |  | 42.6984 | 16.9769 | منجز | No
2100064260 | هيئة المدن الصناعية ومناطق التقنية | تشييد | ذات اولوية عالية | 15963114 | 798155.7 | 13068701.18 | 13068701.18 | 4030034104 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-12-05 | 2021-05-28 | 2021-12-05 | 2021-12-05 | 2021-05-28 |  | لا يوجد تأخير |  | 25.9314 | 49.9532 | منجز | No
2100060255 | الرئاسة العامة لهيئة الأمر بالمعروف والنهي عن المنكر | تشييد | ذات اولوية عالية | 16083127.95 | 804156.3975 | 15924024.32 | 15924024.32 | 5857020213 | لا | 0 | 190509110831 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-04-23 | 2014-11-18 | 2022-01-01 | 2022-01-01 | 2014-11-18 |  | تأخرصرف المستحقات المالية |  | 42.5208 | 18.2257 | منجز | No
2100079855 | الهيئة العامة للموانئ | تشييد | ذات اولوية عالية وعاجلة | 98541949.37 | 4927097.4685 | 39396591.5 | 25523171.17 | 4030027340 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 91 | 100 | 2010-04-03 | 2012-10-03 | 2023-05-01 | 2023-05-01 |  |  | التنسيق مع أصحاب المصلحه (خدمات |  | 38.0699 | 24.0815 | متأخر | No
2100023251 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 38595543.8 | 1929777.19 | 0 | 0 | 1010030949 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0 | 100 | 2026-02-04 | 2026-08-05 | 2027-08-18 | 2027-08-18 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 41.0859 | 19.1571 | مسحوب | No
2100025900 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 1829900 | 91495 | 0 | 0 | 3350017944 | لا | 0 | 190201038787 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-12-16 | 2020-12-11 | 2021-07-13 | 2021-07-13 | 2020-12-11 |  |  |  | 42.1252 | 26.4957 | منجز | No
2100071341 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 2410800 | 120540 | 2410800 | 2410800 | 5950016301 | لا | 0 | 210601172735 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 92 | 92 | 2019-11-03 | 2021-07-01 | 2020-10-22 | 2020-10-22 | 2021-07-01 |  | ضعف كفاءة المقاول الفنية |  | 44.2293 | 17.5479 | منجز | No
2100053502 | أمانة / تبوك | تشييد | ذات اولوية عالية | 4849949.5 | 242497.475 | 4025458.085 | 4025458 | 4650032626 | لا | 0 | 181009141652 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-06-29 | 2015-12-29 | 2019-12-23 | 2019-12-23 | 2015-12-29 |  | اخرى |  | 38.5165 | 27.6122 | منجز | No
2100075180 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 2190438 | 109521.9 | 675807.05 | 675807.05 | 3555000646 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 41.28 | 100 | 2009-09-03 | 2010-08-29 | 2021-11-30 | 2021-11-30 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5174 | 28.4002 | مسحوب | No
2100072214 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 10963750.25 | 548187.5125 | 8824437 | 8824437 | 1010055791 | لا | 0 | 181009135110 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 92.89 | 100 | 2015-04-27 | 2017-04-17 | 2021-05-25 | 2021-05-25 | 2017-04-17 |  | ضعف كفاءة المقاول الفنية |  | 36.4571 | 26.2318 | منجز | No
2100036282 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 925170.75 | 46258.5375 | 561600 | 299424.62 | 5950010294 | لا | 0 | 220601025060 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 87 | 92 | 2019-04-20 | 2020-10-02 | 2020-10-02 | 2020-10-02 | 2020-10-02 |  | اخرى |  | 44.2588 | 17.5197 | منجز | No
2100022584 | وزارة التعليم | تشييد | ذات اولوية عالية | 11291715.56 | 564585.778 | 7525822.7 | 0.05 | 4031028157 | لا | 0 |  | مسحوب | التكلفة المفوترة | 76 | 100 | 2014-05-11 | 2016-04-30 | 2021-01-12 | 2021-01-12 |  |  | ضعف كفاءة المقاول الفنية |  | 39.836 | 21.4408 | مسحوب | No
2100178555 | وزارة الثقافة | تصميم وإشراف | ذات اولوية عالية | 44000000 | 2200000 | 0 | 0 | 1010440360 | لا | 0 |  | لم يبدأ | اخرى | 55 | 50 | 2021-03-01 | 2023-03-01 | 2023-03-01 | 2023-03-01 |  |  |  |  | 39.2499 | 21.4246 | منتظم | No
2100091556 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | تشييد | ذات اولوية عالية وعاجلة | 99500495.73 | 4975024.7865 | 89361990.11 | 70547081.11 | 1010147053 | لا | 0 | 181009178687 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 99 | 100 | 2014-05-13 | 2020-09-28 | 2022-03-31 | 2022-03-31 | 2020-09-28 |  | تأخرصرف المستحقات المالية |  | 39.6005 | 24.4595 | منجز | No
2100017150 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | تشييد | ذات اولوية عالية وعاجلة | 99875000 | 4993750 | 87392775.05 | 71542562.02 | 1010318930 | لا | 0 | 190401071106 | جاري | تكلفة العمل المنجز | 100 | 96 | 2019-08-27 | 2022-11-16 | 2023-03-26 | 2023-03-26 |  |  | لا يوجد تأخير |  | 42.7302 | 18.3003 | منتظم | No
2100023881 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | تشييد | ذات اولوية متوسطة | 12747071.2 | 637353.56 | 6089066.4 | 6089066.4 | 1010296235 | لا | 0 | 180555652055 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-02-23 | 2021-02-17 | 2022-12-31 | 2022-12-31 | 2021-02-17 |  | اخرى |  | 50.101 | 26.4494 | منجز | No
2100087765 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | تشييد | ذات اولوية عالية | 73912850 | 3695642.5 | 73912850 | 64942108.78 | 1010009592 | لا | 0 | 180709033857 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-04-11 | 2020-03-31 | 2021-03-04 | 2021-03-04 | 2020-03-31 |  | تأخرصرف المستحقات المالية |  | 36.5638 | 28.4092 | منجز | No
2100087931 | وزارة التعليم | تشييد | ذات اولوية عالية | 9951584.86 | 497579.243 | 7416848 | 6139589 | 1010008713 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-11-19 | 2017-11-08 | 2020-01-23 | 2020-01-23 | 2017-11-08 |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | منجز | No
2100087625 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 3037362.99 | 151868.1495 | 1089037.29 | 382012.1 | 4030244549 | لا | 0 | 191001247701 | منجز – استلام ابتدائي | التكلفة المفوترة | 82 | 100 | 2019-02-17 | 2020-02-12 | 2022-12-07 | 2022-12-07 | 2020-02-12 |  | ضعف كفاءة المقاول الفنية |  | 40.2691 | 20.1489 | منجز | No
2100086085 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 3264781 | 163239.05 | 2396176.97 | 2396176.97 | 4030164183 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 80 | 100 | 2014-11-18 | 2015-11-13 | 2022-03-11 | 2022-03-11 |  |  | ضعف كفاءة المقاول الفنية |  | 40.2691 | 20.1489 | مسحوب | No
2100042206 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 7703795 | 385189.75 | 0 | 0 | 4030033505 | لا | 0 |  | مسحوب | التكلفة المفوترة | 0 | 100 | 2014-03-19 | 2015-06-12 | 2023-05-10 | 2023-05-10 |  |  | ضعف كفاءة المقاول الفنية |  | 40.2691 | 20.1489 | مسحوب | No
2100086785 | وزارة التعليم | تشييد | ذات اولوية عالية | 9584597.84 | 479229.892 | 7212183 | 6307800 | 1010178798 | لا | 0 |  | مسحوب | التكلفة المفوترة | 79 | 100 | 2012-11-30 | 2014-11-20 | 2022-11-10 | 2022-11-10 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.1677 | 21.5008 | مسحوب | No
2100058660 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 8972730 | 448636.5 | 2239488 | 2239488 | 1010181942 | لا | 0 |  | مسحوب | التكلفة المفوترة | 24 | 100 | 2006-04-15 | 2008-02-05 | 2024-02-07 | 2024-02-07 |  |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | مسحوب | No
2100041576 | جامعة جدة | تصميم وتشييد | ذات اولوية متوسطة | 11926629 | 596331.45 | 9507554.51 | 9507554.51 | 1010251358 | لا | 0 | 180709029257 | جاري | تكلفة العمل المنجز | 90.1 | 100 | 2017-06-15 | 2019-05-29 | 2019-05-29 | 2019-05-29 |  |  | أوامر تغيير |  | 21.8911 | 39.2563 | Failed | No
2100097020 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2674010 | 133700.5 | 0 | 0 | 1129001539 | لا | 0 |  | مسحوب | التكلفة المفوترة | 1 | 100 | 2014-06-26 | 2015-06-21 | 2023-05-17 | 2023-05-17 |  |  | ضعف كفاءة المقاول الفنية |  | 40.2691 | 20.1489 | مسحوب | No
2100078676 | أمانة / العاصمة المقدسة | دراسة بيئية | ذات اولوية متوسطة | 19990000 | 999500 | 13422800 | 13422800 | 4650033223 | لا | 0 |  | ايقاف كلي | مدفوعات ساعات العمل | 94 | 94 | 2014-01-02 | 2016-11-30 | 2016-11-30 | 2016-11-30 |  |  | عدم وجود مبالغ في البنود تغطي الأعمال المرصودة |  |  |  | Failed | No
2100002516 | وزارة الدفاع / الإدارة الهندسية والاشغال بالخدمات الصحية | تشييد | ذات اولوية عالية | 51510061.53 | 2575503.0765 | 51510061.53 | 51510061.53 | 1010034808 | لا | 0 |  | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-10-08 | 2017-03-11 | 2021-12-31 | 2021-12-31 |  |  | اخرى |  |  |  | Failed | No
2100104053 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 12400000 | 620000 | 5517136 | 5517136 | 4030023890 | لا | 0 | 190209036289 | مسحوب | التكلفة المفوترة | 71 | 100 | 2012-07-16 | 2017-03-13 | 2023-05-03 | 2023-05-03 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0859 | 19.1571 | مسحوب | No
2100091081 | وزارة التعليم | تشييد | ذات اولوية عالية | 14506894.23 | 725344.7115 | 7140309 | 7140309 | 1010196220 | لا | 0 | 190209015500 | مسحوب | التكلفة المفوترة | 50 | 95 | 2013-12-31 | 2015-12-21 | 2023-05-10 | 2023-05-10 |  |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | مسحوب | No
2100099352 | وزارة التعليم | تشييد | ذات اولوية عالية | 10556350.4 | 527817.52 | 3587224 | 3587224 | 4603000055 | لا | 0 |  | مسحوب | التكلفة المفوترة | 33 | 100 | 2007-06-11 | 2009-05-31 | 2022-11-18 | 2022-11-18 |  |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | مسحوب | No
2100088023 | وزارة التعليم | تشييد | ذات اولوية عالية | 14485055.47 | 724252.7735 | 10485914.73 | 10485914.73 | 1010196220 | لا | 0 | 190409022089 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 94 | 2013-09-14 | 2015-09-04 | 2022-06-18 | 2022-06-18 | 2015-09-04 |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | منجز | No
2100086295 | وزارة التعليم | تشييد | ذات اولوية عالية | 8600000 | 430000 | 1511603 | 1511603 | 2057001038 | لا | 0 |  | مسحوب | التكلفة المفوترة | 60 | 100 | 2013-07-21 | 2015-04-12 | 2022-08-16 | 2022-08-16 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0859 | 19.1571 | مسحوب | No
2100089036 | وزارة التعليم | تشييد | ذات اولوية عالية | 1910547.97 | 95527.3985 | 2084669 | 1863054 | 4603004056 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-03-17 | 2015-05-11 | 2016-06-08 | 2016-06-08 | 2015-05-11 |  | ضعف كفاءة المقاول الفنية |  | 41.0859 | 19.1571 | منجز | No
2100088922 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2516117 | 125805.85 | 2515588.54 | 2515588.54 | 1010008713 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2018-09-13 | 2019-05-08 | 2019-05-08 | 2019-05-08 | 2019-05-08 |  |  |  | 40.4511 | 21.2747 | منجز | No
2100002505 | وزارة التعليم | تشييد | ذات اولوية عالية | 8420094 | 421004.7 | 0.02 | 0.02 | 4031043999 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-01-14 | 2016-01-14 | 2019-08-04 | 2019-08-04 | 2016-01-14 |  | ضعف كفاءة المقاول الفنية |  | 39.836 | 21.4408 | منجز | No
2100096294 | أمانة / العاصمة المقدسة | دراسة الجدوى | ذات اولوية متوسطة | 8304300 | 415215 | 6191394 | 6191394 | 1010308543 | لا | 0 | 200209128506 | جاري الاستلام الإبتدائي | مدفوعات ساعات العمل | 86.6 | 86.6 | 2019-08-18 | 2021-08-17 | 2021-08-17 | 2021-08-17 |  |  | اخرى |  |  |  | Failed | No
2100079844 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 16094697.39 | 804734.8695 | 13020176.47 | 13020176.47 | 1010136405 | لا | 0 | 180709019749 | جاري | تكلفة العمل المنجز | 86.6 | 100 | 2017-05-07 | 2018-04-27 | 2022-12-31 | 2022-12-31 |  |  | تأخرصرف المستحقات المالية |  | 39.1677 | 21.5008 | متأخر | No
2100060491 | جامعة الطائف | تشييد | ذات اولوية متوسطة | 8530701 | 426535.05 | 8530701 | 8530701 | 4030023917 | لا | 0 | 181109273026 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-02-18 | 2018-10-14 | 2019-02-12 | 2019-02-12 | 2018-10-14 |  | لا يوجد تأخير |  | 40.4952 | 21.4338 | منجز | No
2100061703 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 6593960 | 329698 | 6590507.33 | 5354329.69 | 1010008713 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 87 | 2018-11-12 | 2019-10-06 | 2019-08-01 | 2019-08-01 | 2019-10-06 |  |  |  | 40.4511 | 21.2747 | منجز | No
2100006333 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 6156774.96 | 307838.748 | 0 | 0 | 4030033505 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0 | 100 | 2014-03-24 | 2015-09-15 | 2023-05-18 | 2023-05-18 |  |  | ضعف كفاءة المقاول الفنية |  | 40.2691 | 20.1489 | مسحوب | No
2100017894 | وزارة التعليم | تشييد | ذات اولوية عالية | 14847699.21 | 742384.9605 | 11325010.5 | 11325010.5 | 1010196220 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2013-10-22 | 2015-10-12 | 2021-01-24 | 2021-01-24 | 2015-10-12 |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | منجز | No
2100004093 | وزارة التعليم | تشييد | ذات اولوية عالية | 9472751.46 | 473637.573 | 2082341.79 | 2082341.79 | 1010187466 | لا | 0 | 190309000210 | مسحوب | التكلفة المفوترة | 27 | 100 | 2015-01-05 | 2016-12-25 | 2023-02-15 | 2023-02-15 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.1677 | 21.5008 | مسحوب | No
2100016402 | وزارة التعليم | تشييد | ذات اولوية عالية | 8206823.48 | 410341.174 | 4324305 | 3914910 | 1132002624 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2013-10-26 | 2015-10-16 | 2021-06-09 | 2021-06-09 | 2015-10-16 |  | ضعف كفاءة المقاول الفنية |  | 39.836 | 21.4408 | منجز | No
2100006543 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 9766851.02 | 488342.551 | 0 | 0 | 4030033505 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0 | 100 | 2013-10-26 | 2015-10-16 | 2023-05-17 | 2023-05-17 |  |  | ضعف كفاءة المقاول الفنية |  | 40.2691 | 20.1489 | مسحوب | No
2100018362 | أمانة / العاصمة المقدسة | إشراف | ذات اولوية متوسطة | 5443683 | 272184.15 | 5443683 | 5443683 | 4031063586 | لا | 0 | 180909066377 | منجز – استلام نهائي | مدفوعات ساعات العمل | 100 | 100 | 2018-07-15 | 2019-07-15 | 2019-12-19 | 2019-12-19 | 2019-07-15 | 2020-02-12 | اخرى |  |  |  | منجز | No
2100084980 | مدينة الملك عبدالله الطبية بالعاصمة المقدسة | تشييد | ذات اولوية عالية | 923769 | 46188.45 | 0 | 0 | 4032032258 | لا | 0 | 190701117566 | فسخ العقد | الكميات التي تم تركيبها | 0 | 0 | 2021-01-01 | 2021-01-02 | 2021-01-02 | 2021-01-02 |  |  | موافقات | مخطط لإعادة طرحه |  |  | مسحوب | No
2100086354 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 11061588 | 553079.4 | 2402096 | 2402096 | 1010072637 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 60 | 100 | 2015-10-18 | 2018-12-15 | 2023-05-30 | 2023-05-30 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0859 | 19.1571 | مسحوب | No
2100057676 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 16000000 | 800000 | 7995840 | 7995840 | 1010072637 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 64 | 100 | 2014-02-03 | 2016-10-20 | 2023-02-09 | 2023-02-09 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0859 | 19.1571 | مسحوب | No
2100088093 | وزارة التعليم | تشييد | ذات اولوية عالية | 12338114.11 | 616905.7055 | 9733576.82 | 9733576.82 | 1010196220 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 89 | 100 | 2014-01-23 | 2016-01-13 | 2020-11-20 | 2020-11-20 | 2016-01-13 |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | منجز | No
2100036072 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 3919542.45 | 195977.1225 | 1215778.45 | 1215778.45 | 4603006868 | لا | 0 | 190209036289 | مسحوب | التكلفة المفوترة | 32 | 85 | 2017-09-14 | 2019-03-08 | 2023-02-01 | 2023-02-01 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0859 | 19.1571 | مسحوب | No
2100032023 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2549638 | 127481.9 | 0 | 0 | 4030186469 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0 | 100 | 2014-08-17 | 2015-08-12 | 2023-05-10 | 2023-05-10 |  |  | ضعف كفاءة المقاول الفنية |  | 40.2691 | 20.1489 | مسحوب | No
2100074395 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 11499997.79 | 574999.8895 | 0.02 | 0.02 | 1010213931 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0 | 100 | 2015-02-26 | 2019-11-27 | 2027-05-05 | 2027-05-05 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.836 | 21.4408 | مسحوب | No
2100019246 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 10171530 | 508576.5 | 8530792 | 8530792 | 4030140863 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-06-20 | 2017-06-09 | 2020-01-30 | 2020-01-30 | 2017-06-09 |  | ضعف كفاءة المقاول الفنية |  | 39.836 | 21.4408 | منجز | No
2100105781 | الهيئة الملكية لمدينة مكة المكرمة و المشاعر المقدسة | تشييد | ذات اولوية عالية وعاجلة | 69720492 | 3486024.6 | 56717959 | 41661460 | 4021041927 | لا | 0 | 190109007147 | جاري | تكلفة العمل المنجز | 91.8 | 100 | 2019-02-11 | 2019-11-10 | 2021-10-30 | 2021-10-30 |  |  | التنسيق مع أصحاب المصلحه (خدمات |  | 39.836 | 21.4408 | Failed | No
2100108135 | وزارة التعليم | تشييد | ذات اولوية عالية | 8743355 | 437167.75 | 8743355 | 7828045 | 1010168033 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-08-06 | 2016-04-27 | 2017-06-04 | 2017-06-04 | 2016-04-27 |  |  |  | 41.0859 | 19.1571 | منجز | No
2100097300 | وزارة التعليم | تشييد | ذات اولوية عالية | 8828781.84 | 441439.092 | 5949447.95 | 5949447.95 | 4603008020 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 80 | 100 | 2010-03-01 | 2011-11-20 | 2023-08-09 | 2023-08-09 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 41.0859 | 19.1571 | مسحوب | No
2100104510 | وزارة التعليم | تشييد | ذات اولوية عالية | 2477711.96 | 123885.598 | 1491287.5 | 1491287.5 | 2050018834 | لا | 0 |  | مسحوب | التكلفة المفوترة | 66 | 100 | 2015-04-05 | 2016-03-30 | 2023-02-01 | 2023-02-01 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.1677 | 21.5008 | مسحوب | No
2100096950 | وزارة التعليم | تشييد | ذات اولوية عالية | 7550000 | 377500 | 2231532 | 2231532 | 1010072637 | لا | 0 |  | مسحوب | التكلفة المفوترة | 50 | 100 | 2015-07-23 | 2018-07-22 | 2023-02-02 | 2023-02-02 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0859 | 19.1571 | مسحوب | No
2100091136 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 7596047 | 379802.35 | 3719785.24 | 3428163 | 4601000417 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 90 | 74 | 2017-01-05 | 2018-03-01 | 2022-12-31 | 2022-12-31 | 2018-03-01 |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | منجز | No
2100106864 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 28186936.06 | 1409346.803 | 0 | 0 | 1010168033 | لا | 0 | 190209018537 | مسحوب | التكلفة المفوترة | 5 | 100 | 2014-09-15 | 2017-03-03 | 2023-03-08 | 2023-03-08 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0859 | 19.1571 | مسحوب | No
2100024183 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 1490165 | 74508.25 | 1490165 | 1490165 | 1010426377 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2019-10-14 | 2020-03-10 | 2020-03-10 | 2020-03-10 | 2020-03-10 |  |  |  | 39.9608 | 21.3345 | منجز | No
2100092411 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 17957665.28 | 897883.264 | 17957665.28 | 17957665.28 | 1010224518 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-10-13 | 2020-04-13 | 2020-06-11 | 2020-06-11 | 2020-04-13 |  | لا يوجد تأخير |  | 39.2504 | 21.5179 | منجز | No
2100102513 | وزارة التجارة | دراسة الجدوى | ذات اولوية عالية وعاجلة | 3300000 | 165000 | 3300000 | 3300000 | 2051059669 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2015-11-26 | 2017-11-25 | 2021-02-10 | 2021-02-10 |  | 2017-11-25 | اخرى |  |  |  | منجز | No
2100054460 | وزارة الداخلية / مديرية الأمن العام | تشييد | ذات اولوية متوسطة | 539030 | 26951.5 | 147645 | 147645 | 4030071125 | لا | 0 |  | جاري | تكلفة العمل المنجز | 85 | 80 | 2020-03-16 | 2020-11-16 | 2021-08-26 | 2021-08-26 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.9443 | 21.4608 | Failed | No
2100002925 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 14074574.44 | 703728.722 | 8201113.19 | 8201113.19 | 1010196220 | لا | 0 |  | مسحوب | التكلفة المفوترة | 69 | 91 | 2013-11-17 | 2015-11-07 | 2025-02-05 | 2025-02-05 |  |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | مسحوب | No
2100028910 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 1950300 | 97515 | 0 | 0 | 5950029458 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 55 | 100 | 2014-04-21 | 2017-02-02 | 2017-02-02 | 2017-02-02 |  |  | اخرى |  | 44.2279 | 17.5554 | مسحوب | No
2100004572 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 25680844.5 | 1284042.225 | 23255875.03 | 21411791.91 | 1010076494 | لا | 0 | 180901096976 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2017-05-01 | 2018-08-01 | 2022-12-31 | 2022-12-31 |  |  | تأخرصرف المستحقات المالية |  | 39.1677 | 21.5008 | منتظم | No
2100106540 | وزارة المالية | ترميم | ذات اولوية متوسطة | 7248049 | 362402.45 | 2574285 | 2574285 | 2050018622 | لا | 0 |  | مسحوب | التكلفة المفوترة | 43 | 100 | 2018-07-22 | 2023-11-30 | 2023-12-13 | 2023-12-13 |  |  | ضعف كفاءة المقاول الفنية |  | 40.4511 | 21.2747 | مسحوب | No
2100010356 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 3739164 | 186958.2 | 3513998 | 3513998 | 4603005625 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2017-09-10 | 2019-03-04 | 2019-04-16 | 2019-04-16 | 2019-03-04 |  |  |  | 41.0859 | 19.1571 | منجز | No
2100004174 | وزارة التعليم | تشييد | ذات اولوية عالية وعاجلة | 1400000 | 70000 | 0 | 0 | 1010756489 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2011-07-09 | 2012-03-05 | 2021-08-11 | 2021-08-11 | 2012-03-05 |  | ضعف كفاءة المقاول الفنية |  | 41.0859 | 19.1571 | منجز | No
2100004384 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 3077880 | 153894 | 0 | 0 | 4031033783 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 80.9 | 100 | 2017-10-16 | 2018-06-10 | 2020-04-06 | 2020-04-06 | 2018-06-10 |  | لا يوجد تأخير |  | 41.3834 | 20.8479 | منجز | No
2100003544 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 14238172.27 | 711908.6135 | 13865295 | 11782693 | 5855007803 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2013-02-02 | 2015-01-23 | 2016-09-24 | 2016-09-24 | 2015-01-23 |  |  |  | 41.0859 | 19.1571 | منجز | No
2100002100 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 8869261.52 | 443463.076 | 0.03 | 0.03 | 1010023313 | لا | 0 |  | مسحوب | التكلفة المفوترة | 52 | 100 | 2013-07-13 | 2015-07-03 | 2020-12-23 | 2020-12-23 |  |  | ضعف كفاءة المقاول الفنية |  | 39.836 | 21.4408 | مسحوب | No
2100007571 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 12133892.36 | 606694.618 | 9325609.92 | 9325609.92 | 5802000515 | لا | 0 |  | مسحوب | التكلفة المفوترة | 72 | 100 | 2012-05-25 | 2014-05-15 | 2023-08-16 | 2023-08-16 |  |  | ضعف كفاءة المقاول الفنية |  | 40.2691 | 20.1489 | مسحوب | No
2100042840 | وزارة التعليم | تشييد | ذات اولوية عالية | 10542052.22 | 527102.611 | 4479300 | 4479300 | 1132002624 | لا | 0 |  | جاري | التكلفة المفوترة | 77 | 100 | 2016-06-05 | 2018-05-26 | 2022-12-31 | 2022-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | Failed | No
2100005471 | وزارة التعليم | تشييد | ذات اولوية عالية | 28670170.32 | 1433508.516 | 21102971 | 21102971 | 1010196220 | لا | 0 |  | جاري | التكلفة المفوترة | 90.5 | 100 | 2013-10-26 | 2016-01-14 | 2022-12-30 | 2022-12-30 |  |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | متأخر | No
2100074642 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2845061 | 142253.05 | 1023750 | 1023750 | 4700014775 | لا | 0 |  | جاري | التكلفة المفوترة | 80 | 100 | 2015-12-27 | 2016-10-17 | 2022-12-28 | 2022-12-28 |  |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | Failed | No
2100023192 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 8278276 | 413913.8 | 1174609.48 | 1174609.48 | 5802000515 | لا | 0 |  | مسحوب | التكلفة المفوترة | 23 | 100 | 2013-04-06 | 2014-09-28 | 2023-05-03 | 2023-05-03 |  |  | ضعف كفاءة المقاول الفنية |  | 40.2691 | 20.1489 | مسحوب | No
2100000302 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 10984780.52 | 549239.026 | 6896515.43 | 6896515.43 | 1010023313 | لا | 0 | 190209015517 | مسحوب | التكلفة المفوترة | 70 | 88 | 2014-07-02 | 2016-06-21 | 2023-05-10 | 2023-05-10 |  |  | ضعف كفاءة المقاول الفنية |  | 40.2691 | 20.1489 | مسحوب | No
2100048193 | وزارة الدفاع / الإدارة الهندسية والاشغال بقوات الدفاع الجوي | تشييد | ذات اولوية متوسطة | 25009427.01 | 1250471.3505 | 25009427.01 | 11278751.39 | 1010006082 | لا | 0 | 19030119774 | جاري | الكميات التي تم تركيبها | 45 | 100 | 2019-09-02 | 2021-08-22 | 2022-10-18 | 2022-10-18 |  |  | أوامر سامية |  | 50.1064 | 26.4423 | Failed | No
2100067255 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 2089886 | 104494.3 | 2089886 | 2089886 | 3350005373 | لا | 0 | 181201485549 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 80 | 100 | 2014-12-21 | 2015-11-26 | 2021-07-07 | 2021-07-07 | 2015-11-26 |  | اخرى |  | 42.9032 | 28.2402 | منجز | No
2100064352 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 2631720 | 131586 | 999787 | 299424.62 | 5950000060 | لا | 0 | 220601025060 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-11-02 | 2020-04-16 | 2021-07-14 | 2021-07-14 | 2020-04-16 |  | تأخرصرف المستحقات المالية |  | 44.2204 | 17.5403 | منجز | No
2100016516 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2900000 | 145000 | 676913 | 676913 | 1010356455 | لا | 0 |  | مسحوب | التكلفة المفوترة | 50 | 100 | 2012-10-17 | 2013-12-11 | 2023-05-07 | 2023-05-07 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0859 | 19.1571 | مسحوب | No
2100058586 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 3492066.69 | 174603.3345 | 2944585.94 | 2944585.94 | 4030164183 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-04-25 | 2016-09-16 | 2020-10-07 | 2020-10-07 | 2016-09-16 |  | ضعف كفاءة المقاول الفنية |  | 40.4511 | 21.2747 | منجز | No
2100031183 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 6964038 | 348201.9 | 2666634.4 | 2666634.4 | 1010196220 | لا | 0 |  | مسحوب | التكلفة المفوترة | 38 | 100 | 2014-08-25 | 2019-10-07 | 2022-02-01 | 2022-02-01 |  |  | ضعف كفاءة المقاول الفنية |  | 40.4511 | 21.2747 | مسحوب | No
2100022164 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 941000 | 47050 | 845931.8 | 845931.8 | 1010296759 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-10-14 | 2019-10-14 | 2019-10-14 | 2019-10-14 |  | 2019-10-14 | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100074723 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 13062497 | 653124.85 | 12982002.63 | 12982002.63 | 4030196153 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 90.04 | 100 | 2015-07-08 | 2018-06-05 | 2020-07-12 | 2020-07-12 | 2018-06-05 |  | لا يوجد تأخير |  | 42.8096 | 21.2873 | منجز | No
2100027414 | جامعة الملك فيصل | تشييد | ذات اولوية عالية | 75065726.76 | 3753286.338 | 75065726.76 | 75065726.76 | 4030006877 | لا | 0 | 180809055100 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2013-07-19 | 2015-06-28 | 2017-10-15 | 2017-10-15 | 2015-06-28 |  | تأخرصرف المستحقات المالية |  | 49.5604 | 25.3897 | منجز | No
2100035825 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 3948810 | 197440.5 | 1974463 | 1974463 | 5950013632 | لا | 0 | 210501030518 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 88.98 | 100 | 2014-06-09 | 2015-05-29 | 2022-09-11 | 2022-09-11 | 2015-05-29 |  | ضعف كفاءة المقاول الفنية |  | 44.2257 | 17.5579 | منجز | No
2100039244 | وزارة الداخلية / المديرية العامة للدفاع المدني | تشييد | ذات اولوية متوسطة | 12012510.99 | 600625.5495 | 12012510.99 | 12012510.99 | 1010001618 | لا | 0 | 181009126896 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2016-05-08 | 2018-03-19 | 2020-11-08 | 2020-11-08 | 2018-03-19 |  | ضعف كفاءة المقاول الفنية |  | 50.1045 | 26.3826 | منجز | No
2100010566 | وزارة الموارد البشرية والتنمية الإجتماعية | دراسة الجدوى | ذات اولوية منخفضة | 3042999.99 | 152149.9995 | 3216233.52 | 3216233.52 | 1010406370 | لا | 0 | 181109270523 | مسحوب | الكميات التي تم تركيبها | 88 | 100 | 2013-07-06 | 2016-11-27 | 2022-09-07 | 2022-09-07 |  |  | ضعف كفاءة المقاول الفنية |  | 43.9318 | 26.2967 | مسحوب | No
2100086026 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 6290409 | 314520.45 | 3935827.28 | 3935827.28 | 1010046644 | نعم | 3935827.28 |  | مسحوب | التكلفة المفوترة | 63 | 100 | 2013-04-24 | 2015-04-14 | 2015-04-14 | 2015-04-14 |  |  | ضعف كفاءة المقاول الفنية |  | 40.4511 | 21.2747 | مسحوب | No
2100191472 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 19985610 | 999280.5 | 19876574.1 | 19876574.1 | 2050003475 | لا | 0 | 200709052696 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99.45 | 100 | 2020-09-13 | 2021-03-08 | 2021-01-21 | 2021-01-21 | 2021-03-08 |  |  |  | 39.2009 | 21.6174 | منجز | No
2100007615 | أمانة / الجوف | تشييد | ذات اولوية عالية | 1479205 | 73960.25 | 1479205 | 1479205 | 3400111080 | لا | 0 | 180909097474 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-07-29 | 2019-07-23 | 2019-09-04 | 2019-09-04 | 2019-07-23 |  | تأخرصرف المستحقات المالية |  | 39.8675 | 29.8075 | منجز | No
2100083156 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 2523129 | 126156.45 | 2353624.45 | 1626062 | 4030159820 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 90 | 100 | 2019-07-27 | 2021-01-09 | 2022-12-30 | 2022-12-30 | 2021-01-09 |  |  |  | 41.2416 | 19.9469 | منجز | No
2100020532 | وزارة الشـؤون الاسلامية والدعوة والارشاد | تشييد | ذات اولوية عالية | 487525.5 | 24376.275 | 214915.01 | 73839.27 | 5950008566 | لا | 0 | 180909070612 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-11-20 | 2020-02-20 | 2020-02-07 | 2020-02-07 | 2020-02-20 |  | تأخرصرف المستحقات المالية |  | 44.2289 | 17.5648 | منجز | No
2100086100 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 7798594.56 | 389929.728 | 2507430.72 | 1646223 | 4030172446 | لا | 0 |  | مسحوب | التكلفة المفوترة | 47 | 100 | 2015-03-25 | 2017-03-12 | 2019-05-02 | 2019-05-02 |  |  | ضعف كفاءة المقاول الفنية |  | 39.836 | 21.4408 | مسحوب | No
2100020436 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 837825 | 41891.25 | 687650 | 687650 | 4030071125 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-09-24 | 2019-02-24 | 2019-02-24 | 2019-02-24 | 2019-02-24 |  | لا يوجد تأخير |  | 21.3355 | 39.9652 | منجز | No
2100065844 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 1900000 | 95000 | 401195 | 401195 | 5806004553 | لا | 0 | 181001210123 | ايقاف كلي | الكميات التي تم تركيبها | 21 | 100 | 2017-03-27 | 2018-03-17 | 2023-12-31 | 2023-12-31 |  |  | تأخرصرف المستحقات المالية |  | 41.461 | 20.0066 | Failed | No
2100097053 | الهيئة الملكية لمدينة مكة المكرمة و المشاعر المقدسة | تشييد | ذات اولوية عالية وعاجلة | 10740236 | 537011.8 | 9207065.66 | 9207065.66 | 4031036822 |  | 0 | 190109007307 | جاري | تكلفة العمل المنجز | 100 | 100 | 2019-02-11 | 2019-11-10 | 2021-10-30 | 2021-10-30 |  |  | التنسيق مع أصحاب المصلحه (خدمات |  | 39.836 | 21.4408 | Failed | No
2100047541 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 2472252.15 | 123612.6075 | 2472252.15 | 2472252.15 | 5801007594 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2012-03-18 | 2013-03-18 | 2022-12-30 | 2022-12-30 | 2013-03-18 |  | ضعف كفاءة المقاول الفنية |  | 41.661 | 19.9966 | منجز | No
2100002995 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 5237763.26 | 261888.163 | 5237763.26 | 0 | 3350003498 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-01-03 | 2015-06-26 | 2019-03-21 | 2019-03-21 | 2015-06-26 |  |  |  | 41.6968 | 27.506 | منجز | Yes
2100064470 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 2426311.96 | 121315.598 | 1407649.56 | 1407649.56 | 5803009814 | لا | 0 | 201009067697 | مسحوب | تكلفة العمل المنجز | 55.96 | 100 | 2018-12-14 | 2020-05-28 | 2021-10-13 | 2021-10-13 |  |  | ضعف كفاءة المقاول الفنية |  | 41.7906 | 19.8202 | مسحوب | No
2100055672 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 13577752 | 678887.6 | 9684533 | 9684533 | 1010263814 | لا | 0 | 180301000694 | جاري | منهجية القيمة المكتسبة | 76.51 | 100 | 2018-10-28 | 2020-10-26 | 2023-03-14 | 2023-03-14 |  |  | تأخرصرف المستحقات المالية |  | 38.1903 | 24.0147 | متأخر | No
2100066275 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 12534382 | 626719.1 | 9964223 | 9964223 | 4031045263 | لا | 0 |  | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2013-03-16 | 2014-08-30 | 2016-01-06 | 2016-01-06 | 2014-08-30 | 2020-01-02 | ضعف كفاءة المقاول الفنية |  | 39.1826 | 21.5346 | منجز | No
2100085923 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 12016086.98 | 600804.349 | 4437193.39 | 1796525.64 | 1010046644 | لا | 0 |  | مسحوب | التكلفة المفوترة | 55 | 100 | 2013-08-25 | 2016-02-10 | 2022-09-15 | 2022-09-15 |  |  | ضعف كفاءة المقاول الفنية |  | 40.4511 | 21.2747 | مسحوب | No
2100097926 | وزارة التعليم | تشييد | ذات اولوية عالية | 7568206.86 | 378410.343 | 656271 | 656271 | 7013469452 | لا | 0 |  | مسحوب | التكلفة المفوترة | 37 | 100 | 2013-06-04 | 2015-05-26 | 2023-06-02 | 2023-06-02 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0859 | 19.1571 | مسحوب | No
2100088104 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2762037.92 | 138101.896 | 1986228 | 1986228 | 4030140863 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 89 | 100 | 2015-08-26 | 2016-08-20 | 2022-03-16 | 2022-03-16 | 2016-08-20 |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | منجز | No
2100076241 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1542870 | 77143.5 | 1542870 | 1542870 | 4032015171 | لا | 0 | 181001154266 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-05-22 | 2019-05-17 | 2019-05-17 | 2019-05-17 | 2019-05-17 |  | اخرى |  | 41.5897 | 22.7418 | منجز | No
2100097473 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1931008 | 96550.4 | 395587 | 395587 | 4603003958 | لا | 0 | 201101002795 | جاري الاستلام الإبتدائي | التكلفة المفوترة | 95 | 100 | 2019-07-30 | 2020-05-25 | 2022-08-23 | 2022-08-23 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0859 | 19.1571 | Failed | No
2100106271 | وزارة التعليم | تشييد | ذات اولوية عالية | 10594439.13 | 529721.9565 | 3855948 | 3855948 | 1010051817 | لا | 0 |  | مسحوب | التكلفة المفوترة | 37 | 100 | 2014-05-13 | 2016-05-02 | 2021-06-17 | 2021-06-17 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | مسحوب | No
2100044063 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 14626843.49 | 731342.1745 | 13164159.14 | 13164159.14 | 1131009849 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-04-08 | 2022-01-05 | 2022-01-05 | 2022-01-05 | 2022-01-05 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.5714 | 24.5212 | منجز | No
2100081130 | أمانة / عسير | تشييد | ذات اولوية عالية | 3365825 | 168291.25 | 291868 | 291868 | 5855254445 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 32 | 100 | 2016-09-28 | 2017-09-23 | 2022-06-06 | 2022-06-06 |  |  | ضعف كفاءة المقاول الفنية |  | 42.1768 | 18.9287 | مسحوب | No
2100057573 | شركة المياه الوطنية / منطقة الباحة | إشراف | ذات اولوية عالية وعاجلة | 2998800 | 149940 | 2291938.02 | 2291938.02 | 1010321498 | لا | 0 | 181201499519 | جاري | التكلفة المفوترة | 76.5 | 100 | 2018-11-21 | 2021-11-21 | 2022-05-22 | 2022-05-22 |  |  | لا يوجد تأخير |  | 41.6249 | 19.8632 | خدمات عامة | No
2100061530 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية | 37514998 | 1875749.9 | 19305033.71 | 12586149.44 | 1010127329 | لا | 0 | 190401104979 | جاري | منهجية القيمة المكتسبة | 78.17 | 66.27 | 2020-03-18 | 2023-02-13 | 2023-05-10 | 2023-05-10 |  |  | لا يوجد تأخير |  | 41.2405 | 19.951 | منتظم | No
2100105350 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية | 131629248.9 | 6581462.445 | 103696843.74 | 98500330.19 | 1010012911 | لا | 0 | 181209500269 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2012-04-08 | 2015-03-07 | 2020-12-15 | 2020-12-15 |  | 2015-03-07 | لا يوجد تأخير |  | 43.9553 | 26.3508 | منجز | No
2100092271 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2192984 | 109649.2 | 1702656.8 | 991847 | 5857031865 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2017-09-10 | 2019-08-31 | 2020-03-10 | 2020-03-10 | 2019-08-31 |  | ضعف كفاءة المقاول الفنية |  | 42.4987 | 18.2178 | منجز | No
2100002472 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 7809334.16 | 390466.708 | 5680402.9 | 0 | 3350003498 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 85 | 100 | 2013-09-02 | 2014-10-27 | 2021-05-31 | 2021-05-31 | 2014-10-27 |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | منجز | Yes
2100194504 | أمانة / جدة | تصميم وتشييد | ذات اولوية عالية | 1469245 | 73462.25 | 1566143.39 | 1363305.3 | 5906014131 | لا | 0 | 201109000907 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 95 | 86 | 2020-07-12 | 2021-12-09 | 2022-11-27 | 2022-11-27 | 2021-12-09 |  |  |  | 41.3762 | 19.4441 | منجز | No
2100095174 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 4179329 | 208966.45 | 944317 | 944316.84 | 2057001038 | لا | 0 |  | مسحوب | التكلفة المفوترة | 28 | 100 | 2013-08-24 | 2015-02-07 | 2023-02-09 | 2023-02-09 |  |  | ضعف كفاءة المقاول الفنية |  | 42.0529 | 18.5228 | مسحوب | No
2100091033 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 3886000 | 194300 | 3886000 | 3886000 | 4031045075 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 93 | 93 | 2018-12-01 | 2022-03-30 | 2021-09-05 | 2021-09-05 | 2022-03-30 |  | اخرى |  | 39.5197 | 24.436 | منجز | No
2100020952 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية عالية | 5264295 | 263214.75 | 5264295 | 5264295 | 5855020873 | لا | 0 | 181201498633 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-03-03 | 2020-08-16 | 2020-08-10 | 2020-08-10 |  | 2020-08-16 | لا يوجد تأخير |  | 42.6031 | 20.0028 | منجز | No
2100033482 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية | 21790350 | 1089517.5 | 18258060.9 | 18258060.9 | 5800004747 | لا | 0 | 180201000309 | جاري | منهجية القيمة المكتسبة | 97.45 | 100 | 2018-10-18 | 2021-09-16 | 2022-06-01 | 2022-06-01 |  |  | اخرى |  | 41.4342 | 19.7674 | متأخر | No
2100099256 | جامعة الإمام عبدالرحمن بن فيصل | تشييد | ذات اولوية عالية وعاجلة | 113864631.04 | 5693231.552 | 84421439.59 | 84421439.59 | 1010166751 | لا | 0 | 180809043989 | ايقاف كلي | تكلفة العمل المنجز | 74 | 97.4 | 2012-11-20 | 2015-10-18 | 2022-12-29 | 2022-12-29 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 50.1983 | 26.3741 | Failed | No
2100096773 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 15488270.97 | 774413.5485 | 11450621.74 | 10661107.32 | 1010251358 | لا | 0 | 180709030606 | جاري | تكلفة العمل المنجز | 85.1 | 100 | 2017-05-03 | 2018-04-23 | 2022-12-31 | 2022-12-31 |  |  | تأخرصرف المستحقات المالية |  | 39.1677 | 21.5008 | متأخر | No
2100103504 | هيئة المدن الصناعية ومناطق التقنية | تشييد | ذات اولوية عالية | 19685651 | 984282.55 | 16722421 | 16722421 | 1010021352 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 93.36 | 100 | 2016-12-15 | 2018-02-14 | 2023-02-28 | 2023-02-28 |  |  | ضعف كفاءة المقاول الفنية |  | 21.901 | 39.2881 | Failed | No
2100105276 | جامعة الطائف | تشييد | ذات اولوية متوسطة | 44770000 | 2238500 | 30881932.4 | 30881932.4 | 1010132469 | لا | 0 | 180809064858 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2012-12-15 | 2013-12-05 | 2019-06-04 | 2019-06-04 | 2013-12-05 |  | لا يوجد تأخير |  | 40.4972 | 21.337 | منجز | No
2100086096 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2749878 | 137493.9 | 0 | 0 | 4030186469 | لا | 0 |  | مسحوب | التكلفة المفوترة | 0 | 100 | 2014-06-11 | 2015-06-06 | 2024-02-10 | 2024-02-10 |  |  | ضعف كفاءة المقاول الفنية |  | 40.2691 | 20.1489 | مسحوب | No
2100106050 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 79366563 | 3968328.15 | 55021468.75 | 55021468.75 | 2050005846 | لا | 0 | 200709052696 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 96.71 | 97.06 | 2019-06-30 | 2021-06-08 | 2021-10-31 | 2021-10-31 | 2021-06-08 |  | لا يوجد تأخير |  | 39.2536 | 21.3262 | منجز | No
2100039900 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية متوسطة | 5873135.44 | 293656.772 | 5873135.05 | 5873135.05 | 5850002600 | لا | 0 | 180801002534 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-01-17 | 2019-12-27 | 2020-01-08 | 2020-01-08 |  | 2019-12-27 | لا يوجد تأخير |  | 42.6031 | 20.0028 | منجز | No
2100036665 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية متوسطة | 10272905 | 513645.25 | 10272905 | 10272905 | 5855034401 | لا | 0 | 180901088134 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-10-21 | 2020-04-05 | 2020-01-09 | 2020-01-09 |  | 2020-04-05 | لا يوجد تأخير |  | 42.7302 | 18.3003 | منجز | No
2100048602 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1744743 | 87237.15 | 291194.14 | 291194.14 | 4030146783 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 40 | 100 | 2007-11-27 | 2008-10-12 | 2024-02-02 | 2024-02-02 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 40.2691 | 20.1489 | مسحوب | No
2100062370 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 16885833.75 | 844291.6875 | 8328264 | 8328264 | 1010072637 | لا | 0 | 190309000321 | مسحوب | التكلفة المفوترة | 65 | 100 | 2014-02-03 | 2016-10-20 | 2024-02-07 | 2024-02-07 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0859 | 19.1571 | مسحوب | No
2100109196 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2587922.61 | 129396.1305 | 1729278 | 1729278 | 4030140863 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-12-30 | 2015-12-21 | 2019-09-09 | 2019-09-09 | 2015-12-21 |  | اخرى |  | 39.1677 | 21.5008 | منجز | No
2100000081 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 5885920 | 294296 | 1769200 | 1769200 | 5855014881 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 37 | 100 | 2014-12-14 | 2016-06-06 | 2022-05-18 | 2022-05-18 |  |  | ضعف كفاءة المقاول الفنية |  | 42.4987 | 18.2178 | مسحوب | No
2100088712 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2682675.79 | 134133.7895 | 2590751 | 2495328 | 4603008331 | لا | 0 | 190609041046 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2019-01-07 | 2020-03-02 | 2021-08-12 | 2021-08-12 | 2020-03-02 |  | ضعف كفاءة المقاول الفنية |  | 41.0859 | 19.1571 | منجز | No
2100069661 | وزارة التعليم | تشييد | ذات اولوية عالية | 1823028 | 91151.4 | 331324 | 331324 | 4651001095 | لا | 0 |  | مسحوب | التكلفة المفوترة | 29 | 100 | 2014-03-23 | 2014-09-16 | 2014-09-17 | 2014-09-17 |  |  | ضعف كفاءة المقاول الفنية |  | 37.9386 | 26.6035 | مسحوب | No
2100103460 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 5768464 | 288423.2 | 1780639 | 0 | 1128003208 | لا | 0 |  | مسحوب | التكلفة المفوترة | 35 | 100 | 2016-03-06 | 2017-11-26 | 2020-01-29 | 2020-01-29 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | مسحوب | Yes
2100096795 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 6874957 | 343747.85 | 0 | 0 | 4650020435 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0 | 100 | 2012-03-30 | 2013-11-21 | 2020-12-21 | 2020-12-21 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | No
2100017091 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 27325968.23 | 1366298.4115 | 27325968.23 | 27325968.23 | 1010072637 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-03-17 | 2019-12-08 | 2019-12-17 | 2019-12-17 | 2019-12-08 |  |  |  | 37.3233 | 31.3535 | منجز | No
2100086214 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 8263991.69 | 413199.5845 | 3637390.91 | 0 | 2031040463 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 50 | 100 | 2012-09-23 | 2014-09-13 | 2014-11-12 | 2014-11-12 |  |  | ضعف كفاءة المقاول الفنية |  | 45.975 | 28.4334 | مسحوب | Yes
2100192592 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 1904459.55 | 95222.9775 | 1767805.33 | 1767805.33 | 4030156456 | لا | 0 | 190509126568 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-01-27 | 2019-02-15 | 2020-04-03 | 2020-04-03 |  |  |  |  | 38.9603 | 22.7892 | Failed | No
2100074255 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 15396967 | 769848.35 | 1926248.1 | 1926248.1 | 1010213931 | لا | 0 |  | مسحوب | التكلفة المفوترة | 13 | 100 | 2015-03-31 | 2018-03-15 | 2023-09-19 | 2023-09-19 |  |  | ضعف كفاءة المقاول الفنية |  | 40.4511 | 21.2747 | مسحوب | No
2100031780 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 3498000 | 174900 | 528200 | 528200 | 4650044646 | لا | 0 |  | جاري | التكلفة المفوترة | 32 | 100 | 2015-05-11 | 2016-05-29 | 2023-11-15 | 2023-11-15 |  |  | ضعف كفاءة المقاول الفنية |  | 38.1067 | 25.0621 | Failed | No
2100000733 | جامعة الملك خالد | تشييد | ذات اولوية عالية وعاجلة | 34657812 | 1732890.6 | 22756133.1 | 22377447.87 | 1010140609 | لا | 0 | 180709036671 | جاري | تكلفة العمل المنجز | 93.03 | 100 | 2017-05-01 | 2019-04-21 | 2022-07-25 | 2022-07-25 |  |  | تأخرصرف المستحقات المالية |  | 42.8114 | 18.0836 | متأخر | No
2100097613 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 3084401 | 154220.05 | 3084401 | 3084401 | 4032026755 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2017-09-21 | 2018-12-15 | 2018-12-15 | 2018-12-15 | 2018-12-15 |  |  |  | 40.2691 | 20.1489 | منجز | No
2100107962 | وزارة التعليم | تشييد | ذات اولوية عالية | 9355389 | 467769.45 | 9876876 | 7828045 | 1010168033 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-08-06 | 2016-04-27 | 2017-06-06 | 2017-06-06 | 2016-04-27 |  | ضعف كفاءة المقاول الفنية |  | 41.0859 | 19.1571 | منجز | No
2100086343 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1100000 | 55000 | 0 | 0 | 1010242292 | لا | 0 |  | مسحوب | التكلفة المفوترة | 6 | 100 | 2012-09-13 | 2013-05-12 | 2023-02-01 | 2023-02-01 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0859 | 19.1571 | مسحوب | No
2100079494 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 8555700 | 427785 | 4972846.8 | 4972846.8 | 1010212379 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 75.1 | 100 | 2018-05-17 | 2019-05-07 | 2022-01-09 | 2022-01-09 |  |  | اخرى |  | 39.947 | 21.5671 | Failed | No
2100018292 | جامعة الإمام محمد بن سعود الاسلامية | دراسة الجدوى | ذات اولوية عالية وعاجلة | 27259232.4675 | 1362961.6234 | 11021938.0798 | 10512509.8398 | 1010078921 | لا | 0 | 180909094588 | جاري | اخرى | 46 | 100 | 2012-05-09 | 2015-08-30 | 2023-11-10 | 2023-11-10 |  |  | تغيرات في نطاق المشروع |  | 46.7114 | 24.8146 | خدمات عامة | No
2100051321 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 10098750.28 | 504937.514 | 2864257.5 | 0 | 1010090099 | لا | 0 |  | مسحوب | التكلفة المفوترة | 55 | 100 | 2014-01-15 | 2014-05-01 | 2016-01-05 | 2016-01-05 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5604 | 25.3897 | مسحوب | Yes
2100038721 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 17626188 | 881309.4 | 9635805 | 9635805 | 2051020158 | لا | 0 | 181209546830 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 99.8 | 100 | 2012-02-20 | 2014-02-19 | 2023-05-17 | 2023-05-17 |  |  |  |  | 38.3339 | 23.9637 | Failed | No
2100179056 | جامعة حائل | تشييد | ذات اولوية عالية | 110515153.7 | 5525757.685 | 8277662.86 | 3749263.44 | 1010078607 | لا | 0 |  | جاري | تكلفة العمل المنجز | 64.53 | 92 | 2014-12-14 | 2021-11-27 | 2022-07-31 | 2022-07-31 |  |  |  |  | 41.7094 | 27.6622 | Failed | No
2100088281 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية متوسطة | 9835595 | 491779.75 | 9835595 | 9835595 | 5850028078 | لا | 0 | 190301022557 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-05-06 | 2021-04-13 | 2021-03-28 | 2021-03-28 | 2021-04-13 |  | لا يوجد تأخير |  | 42.4989 | 18.2169 | منجز | No
2100001890 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 12102752.4 | 605137.62 | 12457303 | 409941 | 2050030703 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2016-03-10 | 2018-02-28 | 2020-07-05 | 2020-07-05 | 2018-02-28 |  | ضعف كفاءة المقاول الفنية |  | 50.5295 | 26.4337 | منجز | No
2100192194 | وزارة الصحة / القنفذة | تحديث وتوريد | ذات اولوية عالية | 2731700 | 136585 | 2731700 | 0.01 | 1010090071 | لا | 0 | 190401091184 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-05-29 | 2021-07-14 | 2021-07-14 | 2021-07-14 | 2021-07-14 |  |  |  | 41.0807 | 19.1352 | منجز | No
2100095336 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 63897070 | 3194853.5 | 55712533 | 55712533 | 1010017123 | لا | 0 | 180809040805 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-09-10 | 2019-09-10 | 2023-02-18 | 2023-02-18 |  |  | ضعف كفاءة المقاول الفنية |  | 38.3404 | 23.9324 | متأخر | No
2100045032 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 2994525 | 149726.25 | 2981477.39 | 2981477.39 | 4034000682 | لا | 0 | 180809063664 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-04-30 | 2019-10-22 | 2019-10-22 | 2019-10-22 | 2019-10-22 |  |  |  | 41.6332 | 21.2166 | منجز | No
2100189523 | الهيئة العامة للزكاة والدخل | توريد وتركيب | ذات اولوية عالية | 2274261 | 113713.05 | 2274261 | 2274261 | 1010174562 | لا | 0 |  | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2020-10-04 | 2020-12-31 | 2020-12-31 | 2020-12-31 |  | 2020-12-31 |  |  | 42.5814 | 18.2309 | منجز | No
2100102992 | وزارة الثقافة | دراسة الجدوى |  | 4899058.68 | 244952.934 | 4223778.63 | 4223778.63 | 0 |  | 0 |  | جاري | مدفوعات ساعات العمل | 87 | 87 | 2017-07-25 00:59 | 2020-05-31 00:59 | 2020-11-30 | 2020-11-30 | [6 empty] | خدمات عامة | No
2100087555 | وزارة الثقافة | تشييد |  | 15235940.07 | 761797.0035 | 14305807.81 | 14305807.81 | 1010009971 |  | 0 |  | جاري | منهجية القيمة المكتسبة | 98 | 100 | 2017-11-26 00:59 | 2020-05-25 00:59 | 2020-05-25 | 2020-05-25 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  |  |  | Failed | No
2100105346 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 3000000 | 150000 | 1728100 | 1728100 | 1010300601 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-05-30 | 2019-05-20 | 2020-08-13 | 2020-08-13 | 2019-05-20 |  | لا يوجد تأخير |  | 41.876 | 21.6013 | منجز | No
2100037306 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 7855000 | 392750 | 3595950.43 | 3595950.43 | 2031040463 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 48 | 100 | 2012-09-28 | 2014-09-18 | 2014-09-19 | 2014-09-19 |  |  | ضعف كفاءة المقاول الفنية |  | 45.975 | 28.4334 | مسحوب | No
2100054121 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 82910130 | 4145506.5 | 78782208 | 78782208 | 4030159616 | لا | 0 | 180709036633 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99.43 | 100 | 2017-04-02 | 2019-04-02 | 2022-10-30 | 2022-10-30 | 2019-04-02 |  | ضعف كفاءة المقاول الفنية |  | 38.1901 | 24.0326 | منجز | No
2100000206 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 3020000 | 151000 | 3020000 | 3020000 | 1010174451 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2018-09-12 | 2019-06-21 | 2020-02-07 | 2020-02-07 | 2019-06-21 | [5 empty] | منجز | No
2100018502 | هيئة تطوير بوابة الدرعية | تشييد | ذات اولوية متوسطة | 5343329.25 | 267166.4625 | 5343329.25 | 5343329.25 | 1010126956 | لا | 0 | 200501098048 | جاري | تكلفة العمل المنجز | 100 | 100 | 2020-05-01 | 2021-03-29 | 2021-03-29 | 2021-03-29 |  |  |  |  | 46.553 | 24.7256 | Failed | No
2100041650 | وزارة الثقافة | دراسة الجدوى |  | 5192400 | 259620 | 4229843.33 | 4229843.33 | 0 |  | 0 |  | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2017-07-25 00:59 | 2020-01-24 00:59 | 2020-07-31 | 2020-07-31 | 2020-01-24 00:59 | [5 empty] | منجز | No
2100011502 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 6999674.98 | 349983.749 | 0 | 0 | 2251033167 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 20 | 100 | 2008-06-08 | 2010-01-17 | 2023-02-07 | 2023-02-07 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.5429 | 16.8808 | مسحوب | No
2100008282 | جامعة الجوف | تشييد | ذات اولوية عالية | 95422420 | 4771121 | 93833575.2 | 93833575.2 | 1010009556 | لا | 0 | 180909067036 | جاري | تكلفة العمل المنجز | 100 | 100 | 2017-05-28 | 2021-01-28 | 2021-10-01 | 2021-10-01 |  |  | تأخرصرف المستحقات المالية |  | 40.0664 | 29.7927 | Failed | No
2100107413 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البرية | تشييد | ذات اولوية متوسطة | 4361252.7 | 218062.635 | 4361252.7 | 4361252.7 | 3550023146 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-07-13 | 2020-07-02 | 2020-12-01 | 2020-12-01 | 2020-07-02 |  | تأخرصرف المستحقات المالية |  | 36.6669 | 28.3567 | منجز | No
2100191321 | شركة المياه الوطنية / منطقة الحدود الشمالية | توريد وتركيب | ذات اولوية عالية | 898000 | 44900 | 801700.73 | 0 | 1131055582 | لا | 0 | 200201118725 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2020-09-20 | 2021-09-10 | 2021-09-06 | 2021-09-06 | 2021-09-10 |  |  |  | 43.5304 | 29.6295 | منجز | Yes
2100102454 | وزارة الثقافة | تصميم |  | 58536905.48 | 2926845.274 | 38245834.72 | 38245834.72 | 0 |  | 0 |  | ايقاف كلي | اخرى | 75 | 75 | 2017-09-15 00:59 | 2020-01-14 00:59 | 2021-05-13 | 2021-05-13 |  |  | التنسيق مع أصحاب المصلحه (خدمات |  |  |  | Failed | No
2100190956 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 870000 | 43500 | 870000 | 870000 | 4030017054 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2020-02-17 | 2020-08-17 | 2020-08-10 | 2020-08-10 | 2020-08-17 |  |  |  | 40.0027 | 21.3132 | منجز | No
2100061460 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 18527206.5 | 926360.325 | 18527206.5 | 18527206.5 | 1010224518 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 84.74 | 48.37 | 2019-07-18 | 2021-06-25 | 2020-09-28 | 2020-09-28 | 2021-06-25 |  | لا يوجد تأخير |  | 39.1889 | 21.7777 | منجز | No
2100017172 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية منخفضة | 3680000 | 184000 | 2824051.59 | 2824051.59 | 5950007219 | لا | 0 | 180709020682 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 94.25 | 98.1 | 2017-11-22 | 2020-10-21 | 2021-06-13 | 2021-06-13 | 2020-10-21 |  | لا يوجد تأخير |  | 38.5285 | 27.6159 | منجز | No
2100091490 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تصميم | ذات اولوية عالية وعاجلة | 18456212 | 922810.6 | 18430492.5 | 18430492.5 | 1010320575 | لا | 0 | 180909069926 | منجز – استلام ابتدائي | اخرى | 99.86 | 100 | 2014-12-17 | 2017-12-16 | 2017-12-16 | 2017-12-16 | 2017-12-16 |  |  |  | 38.1967 | 24.0167 | منجز | No
2100106024 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية متوسطة | 13649500 | 682475 | 11327560.08 | 9874857.58 | 5855037099 | لا | 0 | 180909089099 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99.99 | 100 | 2017-11-07 | 2020-10-05 | 2020-11-18 | 2020-11-18 | 2020-10-05 |  | لا يوجد تأخير |  | 35.7077 | 27.343 | منجز | No
2100072251 | أمانة / تبوك | تشييد | ذات اولوية عالية | 2010000 | 100500 | 1122406 | 1122406 | 3550023552 | لا | 0 | 190509000533 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-06-08 | 2020-06-03 | 2020-11-30 | 2020-11-30 | 2020-06-03 |  | ضعف كفاءة المقاول الفنية |  | 36.5959 | 28.3655 | منجز | No
2100044365 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 1499925 | 74996.25 | 0.01 | 0.01 | 4653001158 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 3 | 35 | 2019-06-25 | 2020-12-06 | 2020-12-06 | 2020-12-06 |  |  | ضعف كفاءة المقاول الفنية |  | 39.5772 | 24.5311 | مسحوب | No
2100095631 | شركة الكهرباء | تشييد | ذات اولوية متوسطة | 13644850 | 682242.5 | 5410774 | 5410774 | 2050004063 | لا | 0 |  | جاري الاستلام الإبتدائي | اخرى | 100 | 100 | 2015-09-17 | 2019-03-30 | 2022-08-31 | 2022-08-31 |  |  | تصاريح أعمال التنفيذ |  | 39.7881 | 21.371 | منتظم | No
2100020274 | أمانة / تبوك | دراسات هندسية | ذات اولوية متوسطة | 4977000 | 248850 | 4977000 | 2750000 | 1010440712 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-01-23 | 2022-07-11 | 2022-07-11 | 2022-07-11 | 2022-07-11 |  | اخرى |  |  |  | منجز | No
2100050175 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 2667405 | 133370.25 | 1447919 | 1447919 | 3550026725 | لا | 0 | 181009131057 | مسحوب | الكميات التي تم تركيبها | 73 | 73 | 2014-07-20 | 2016-01-11 | 2020-09-28 | 2020-09-28 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5857 | 28.3754 | مسحوب | No
2100070755 | وزارة النقل والخدمات اللوجستية / منطقة المدينة المنورة | تشييد | ذات اولوية متوسطة | 45694055.3 | 2284702.765 | 40846426 | 40846426 | 4650009788 | لا | 0 | 181109349090 | مسحوب | الكميات التي تم تركيبها | 90.4 | 100 | 2011-06-02 | 2013-11-02 | 2014-10-23 | 2014-10-23 |  |  | اخرى |  | 39.6018 | 24.5048 | مسحوب | No
2100105626 | جامعة الإمام محمد بن سعود الاسلامية | تشييد | ذات اولوية متوسطة | 25068755.8 | 1253437.79 | 25067872.45 | 25067872.45 | 3350003498 | لا | 0 | 180809038533 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2011-01-22 | 2013-01-22 | 2018-05-03 | 2018-05-03 | 2013-01-22 |  | لا يوجد تأخير |  | 41.4129 | 27.2907 | منجز | No
2100064816 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 15149720.65 | 757486.0325 | 2138555 | 1654555 | 4650020435 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 11 | 100 | 2015-05-09 | 2017-04-16 | 2021-09-07 | 2021-09-07 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6265 | 24.4907 | مسحوب | No
2100000335 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 10252050.62 | 512602.531 | 2583721.26 | 0 | 1010196220 | لا | 0 |  | مسحوب | التكلفة المفوترة | 30 | 100 | 2012-12-16 | 2014-12-06 | 2022-11-30 | 2022-11-30 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | مسحوب | Yes
2100064702 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 6485860 | 324293 | 4490416.05 | 4490416.05 | 4032026620 | لا | 0 | 180809052030 | فسخ العقد | تكلفة العمل المنجز | 69 | 100 | 2015-04-19 | 2016-10-10 | 2017-10-13 | 2017-10-13 |  |  | ضعف كفاءة المقاول الفنية |  | 40.4148 | 21.2502 | مسحوب | No
2100020731 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 2809985 | 140499.25 | 2809985 | 2809985 | 4030071125 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-11-02 | 2019-12-02 | 2020-01-05 | 2020-01-05 | 2019-12-02 | [5 empty] | منجز | No
2100194132 | أمانة / جدة | تشييد | ذات اولوية عالية وعاجلة | 3569579 | 178478.95 | 1511198.76 | 1161007.54 | 4030215967 | لا | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 72 | 80 | 2019-11-14 | 2021-10-22 | 2022-09-26 | 2022-09-26 |  |  |  |  | 39.3171 | 22.1459 | Failed | No
2100033250 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 3416481 | 170824.05 | 3416481 | 3416481 | 1010008816 | لا | 0 | 181009124681 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2013-02-12 | 2014-02-07 | 2014-02-07 | 2014-02-07 | 2014-02-07 |  |  |  | 42.8502 | 21.258 | منجز | No
2100080640 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 54748670 | 2737433.5 | 49821289.7 | 49821289.7 | 4704000039 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2017-12-24 | 2022-05-09 | 2022-05-09 | 2022-05-09 | 2022-05-09 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.6498 | 24.4389 | منجز | No
2100007092 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 6988554 | 349427.7 | 5707055 | 5707055 | 5911006877 | لا | 0 | 200901006846 | منجز – استلام ابتدائي | اخرى | 87 | 100 | 2009-08-18 | 2010-08-03 | 2019-06-10 | 2019-06-10 | 2010-08-03 |  | اخرى |  | 42.9667 | 17.5215 | منجز | No
2100095292 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 23065564 | 1153278.2 | 20170068 | 20170068 | 2051034655 | لا | 0 | 190509130274 | مسحوب | منهجية القيمة المكتسبة | 84 | 100 | 2014-08-11 | 2016-08-10 | 2023-06-04 | 2023-06-04 |  |  | ضعف كفاءة المقاول الفنية |  | 38.3339 | 23.9436 | مسحوب | No
2100019460 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 1047619.02 | 52380.951 | 1047619.02 | 1047619.02 | 4030237556 | لا | 0 | 191101248610 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-09-29 | 2019-09-30 | 2020-12-17 | 2020-12-17 | 2019-09-30 |  | ضعف كفاءة المقاول الفنية |  | 40.4586 | 20.3029 | منجز | No
2100070464 | هيئة تطوير بوابة الدرعية | تشييد | ذات اولوية متوسطة | 3625211 | 181260.55 | 3443950.52 | 3443950.52 | 1010126956 | لا | 0 | 200501052623 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-08-21 | 2019-01-11 | 2019-11-01 | 2019-11-01 | 2019-01-11 |  |  |  | 46.5808 | 24.7357 | منجز | No
2100049070 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 98020 | 4901 | 67231.29 | 67231.29 | 3555000931 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-11-26 | 2020-09-21 | 2020-09-22 | 2020-09-22 | 2020-09-21 |  |  |  | 36.5928 | 28.401 | منجز | No
2100024813 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 4053370 | 202668.5 | 3661605 | 3661605 | 4601001792 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 99 | 2019-01-23 | 2020-07-08 | 2021-12-14 | 2021-12-14 | 2020-07-08 |  | ضعف كفاءة المقاول الفنية |  | 40.7415 | 19.9161 | منجز | No
2100054714 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 4202573 | 210128.65 | 652850 | 652850 | 1010178740 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 16 | 100 | 2015-06-07 | 2018-12-06 | 2018-07-19 | 2018-07-19 |  |  | ضعف كفاءة المقاول الفنية |  | 36.6242 | 28.4073 | مسحوب | No
2100034613 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 84574493.3 | 4228724.665 | 76114308.4 | 76114308.4 | 5950005891 | لا | 0 | 181009198842 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 98 | 100 | 2015-12-03 | 2021-03-29 | 2021-03-30 | 2021-03-30 | 2021-03-29 |  |  |  | 44.1656 | 17.5685 | منجز | No
2100058380 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 19587803 | 979390.15 | 15619201 | 15619201 | 4031019772 | لا | 0 | 191101113675 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 75.94 | 75.94 | 2019-06-09 | 2020-06-08 | 2020-04-11 | 2020-04-11 | 2020-06-08 |  |  |  | 39.8678 | 21.3628 | منجز | No
2100013985 | أمانة / نجران | تشييد | ذات اولوية عالية | 6452051.55 | 322602.5775 | 5986321 | 5986321 | 5950000442 | لا | 0 | 180401001866 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 96 | 100 | 2018-07-08 | 2019-10-27 | 2021-03-31 | 2021-03-31 | 2019-10-27 |  | تأخرصرف المستحقات المالية |  | 44.2896 | 17.4173 | منجز | No
2100034554 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية عالية | 995946 | 49797.3 | 995946 | 995946 | 4031210147 | لا | 0 | 200201013823 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 45.78 | 45.78 | 2019-04-29 | 2021-04-18 | 2021-04-18 | 2021-04-18 |  |  |  |  | 39.8717 | 21.3668 | Failed | No
2100047563 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 6500000 | 325000 | 6399360.93 | 6399360.93 | 4031046036 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 75.38 | 75.38 | 2014-11-04 | 2016-04-19 | 2017-10-24 | 2017-10-24 | 2016-04-19 |  |  |  | 39.8732 | 21.3638 | منجز | No
2100194261 | أمانة / جدة | مساحة | ذات اولوية متوسطة | 6872250 | 343612.5 | 7036140.81 | 7036140.81 | 1010328456 | لا | 0 | 181101348770 | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2019-01-31 | 2021-12-28 | 2022-04-15 | 2022-04-15 | 2021-12-28 | 2022-05-17 |  |  | 39.1677 | 21.5008 | منجز | No
2100071175 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 13623556.68 | 681177.834 | 12978501.58 | 12977770.07 | 1010101252 | لا | 0 | 181009124711 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-05-18 | 2015-05-13 | 2015-05-13 | 2015-05-13 | 2015-05-13 |  |  |  | 42.8425 | 21.2556 | منجز | No
2100050886 | أمانة / جازان | تشييد | لم تعد تحتاجها الجهة | 3624026.7 | 181201.335 | 3080410 | 3080410 | 5950007619 | لا | 0 | 180809045591 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 85 | 100 | 2015-07-07 | 2017-07-22 | 2019-11-02 | 2019-11-02 | 2017-07-22 |  | اخرى |  | 42.5823 | 16.9136 | منجز | No
2100082515 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 8731635 | 436581.75 | 8380560 | 8380560 | 1010127437 | لا | 0 | 181001215374 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-01-17 | 2020-07-08 | 2020-07-08 | 2020-07-08 | 2020-07-08 |  | ضعف كفاءة المقاول الفنية |  | 42.2576 | 30.3509 | منجز | No
2100081863 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 5018771 | 250938.55 | 0 | 0 | 5853001934 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 29 | 100 | 2010-07-12 | 2019-03-25 | 2019-03-25 | 2019-03-25 |  |  | اخرى |  | 42.6055 | 16.8579 | مسحوب | No
2100030752 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 2049712.08 | 102485.604 | 0 | 0 | 5950006860 | لا | 0 |  | ايقاف جزئي | اخرى | 42.52 | 50 | 2019-07-09 | 2020-12-21 | 2022-09-11 | 2022-09-11 |  |  |  |  | 44.2341 | 17.5405 | Failed | No
2100082600 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 1442918 | 72145.9 | 746588 | 299424.62 | 5950024669 | لا | 0 | 220601025060 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-10-18 | 2021-01-30 | 2022-11-11 | 2022-11-11 | 2021-01-30 |  | أوامر تغيير |  | 44.2379 | 17.552 | منجز | No
2100037855 | صندوق تنمية الموارد البشرية | تشييد | ذات اولوية منخفضة | 34599257.44 | 1729962.872 | 31139331.96 | 31139331.96 | 2050007518 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-01-05 | 2017-01-04 | 2021-11-30 | 2021-11-30 | 2017-01-04 |  | سوء التخطيط الاولي للمشروع |  | 49.615 | 25.9186 | منجز | No
2100083123 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 2598780 | 129939 | 2335580 | 2335580 | 4030237556 | لا | 0 | 190909115789 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-05-09 | 2020-10-21 | 2021-06-14 | 2021-06-14 | 2020-10-21 |  | ضعف كفاءة المقاول الفنية |  | 41.4292 | 19.2841 | منجز | No
2100072295 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 803820 | 40191 | 803820 | 803820 | 4650047820 | لا | 0 | 200201029205 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-02-18 | 2020-02-13 | 2020-02-13 | 2020-02-13 | 2020-02-13 |  |  |  | 41.7608 | 22.4317 | منجز | No
2100195506 | رئاسة أمن الدولة | ترميم | ذات اولوية عالية وعاجلة | 2067876.41 | 103393.8205 | 1817056.15 | 1817056.15 | 1010088643 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2021-09-08 | 2021-11-08 | 2022-12-30 | 2022-12-30 | 2021-11-08 |  |  |  | 39.1016 | 21.8698 | منجز | No
2100072063 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 925500 | 46275 | 0 | 0 | 5904010214 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 0 | 100 | 2015-01-25 | 2016-01-05 | 2019-02-19 | 2019-02-19 |  |  | اخرى |  | 42.5322 | 17.3643 | مسحوب | No
2100011314 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2948737.25 | 147436.8625 | 1441523.4 | 0 | 1010190375 | لا | 0 |  | مسحوب | التكلفة المفوترة | 69 | 100 | 2011-06-01 | 2012-08-24 | 2012-08-24 | 2012-08-24 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5604 | 25.3897 | مسحوب | Yes
2100014512 | أمانة / جازان | تشييد | ذات اولوية عالية | 765462 | 38273.1 | 765462 | 765462 | 5900011363 | لا | 0 | 180601013854 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-08-06 | 2019-08-12 | 2019-08-12 | 2019-08-12 | 2019-08-12 |  | اخرى |  | 42.9361 | 16.6002 | منجز | No
2100027974 | أمانة / جازان | تشييد | ذات اولوية عالية | 10416700 | 520835 | 8187636 | 8187636 | 5935879512 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 90 | 100 | 2012-06-23 | 2013-11-06 | 2021-06-03 | 2021-06-03 | 2013-11-06 |  | ضعف كفاءة المقاول الفنية |  | 42.9581 | 16.7121 | منجز | No
2100052813 | أمانة / جازان | تشييد | ذات اولوية عالية | 83671250 | 4183562.5 | 59994191.84 | 59994191.84 | 5900007895 | لا | 0 | 180809050454 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 85 | 100 | 2012-10-07 | 2019-11-27 | 2021-08-08 | 2021-08-08 | 2019-11-27 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.605 | 16.8843 | منجز | No
2100052485 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 966042 | 48302.1 | 966042 | 966042 | 4031212978 | لا | 0 | 191001287990 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-10-22 | 2019-12-25 | 2019-12-25 | 2019-12-25 | 2019-12-25 |  | ضعف كفاءة المقاول الفنية |  | 41.067 | 20.4631 | منجز | No
2100104904 | وزارة التجارة | تشييد | ذات اولوية عالية وعاجلة | 10672569.8 | 533628.49 | 4484750.93 | 4484750.93 | 3400000500 | لا | 0 | 180301000632 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-07-22 | 2020-07-21 | 2021-03-28 | 2021-03-28 |  | 2020-07-21 | أوامر تغيير |  | 40.2229 | 29.9918 | منجز | No
2100007652 | الهيئة العامة للموانئ | تشييد | ذات اولوية عالية | 7624116.3 | 381205.815 | 4626260.16 | 4626260.16 | 2252032121 | لا | 0 | 181101318581 | جاري | تكلفة العمل المنجز | 75 | 100 | 2019-02-12 | 2020-08-13 | 2022-02-01 | 2022-02-01 |  |  | تصاريح أعمال التنفيذ |  | 49.1952 | 27.5462 | Failed | No
2100014884 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية عالية | 382984173.46 | 19149208.673 | 342770835.25 | 342770835.25 | 4030007516 | لا | 0 |  | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 89.5 | 89.5 | 2012-06-30 | 2014-12-02 | 2019-12-11 | 2019-12-11 |  |  | التنسيق مع أصحاب المصلحه (خدمات |  | 40.4417 | 21.2838 | Failed | No
2100037634 | وزارة التجارة | تشييد | ذات اولوية عالية | 4691671 | 234583.55 | 4691671 | 4691671 | 1010247178 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2020-10-11 | 2020-12-24 | 2021-01-10 | 2021-01-10 |  | 2020-12-24 | اخرى |  | 39.2173 | 21.4795 | منجز | No
2100012515 | أمانة / حائل | تشييد | ذات اولوية عالية | 589246 | 29462.3 | 443869 | 443869 | 3350027442 | لا | 0 | 190701028287 | مسحوب | الكميات التي تم تركيبها | 76 | 100 | 2018-11-19 | 2019-11-14 | 2020-09-19 | 2020-09-19 |  |  | ضعف كفاءة المقاول الفنية |  | 41.3164 | 26.792 | مسحوب | No
2100018432 | أمانة / عسير | تشييد | ذات اولوية عالية | 10810043 | 540502.15 | 872334 | 0 | 5852000047 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 60 | 100 | 2013-09-03 | 2015-09-03 | 2017-09-03 | 2017-09-03 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | مسحوب | Yes
2100100785 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 3804178 | 190208.9 | 3804178 | 3804178 | 2050018628 | لا | 0 | 190609075448 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 55 | 2019-05-28 | 2019-12-09 | 2019-12-09 | 2019-12-09 | 2019-12-09 |  |  |  | 49.6707 | 25.9168 | منجز | No
2100195742 | أمانة / حائل | دراسات هندسية | ذات اولوية متوسطة | 9300375 | 465018.75 | 5089350 | 5089350 | 1010363372 | لا | 0 | 200201037300 | جاري | تكلفة العمل المنجز | 75 | 90 | 2020-04-26 | 2021-10-18 | 2022-08-04 | 2022-08-04 |  |  |  |  | 41.6967 | 27.5055 | خدمات عامة | No
2100008514 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 6513080 | 325654 | 5617597 | 4388541.63 | 5950004617 | لا | 0 | 210501030518 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 99 | 100 | 2015-08-18 | 2020-10-04 | 2020-04-10 | 2020-04-10 | 2020-10-04 |  | ضعف كفاءة المقاول الفنية |  | 44.2415 | 17.5627 | منجز | No
2100195845 | الهيئة العامة للزكاة والدخل | ترميم | ذات اولوية عالية | 1541000 | 77050 | 1541000 | 1541000 | 1010174562 | لا | 0 |  | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2021-05-18 | 2021-08-17 | 2021-07-17 | 2021-07-17 |  | 2021-08-17 |  |  | 41.7048 | 27.4746 | منجز | No
2100044494 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 5882150 | 294107.5 | 1048000 | 0 | 1114000037 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 69 | 100 | 2015-01-16 | 2016-07-09 | 2019-06-09 | 2019-06-09 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6857 | 24.7138 | Failed | Yes
2100017010 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 13087781.46 | 654389.073 | 11356246.62 | 113562.47 | 2251003882 | لا | 0 |  | مسحوب | التكلفة المفوترة | 90 | 100 | 2012-03-18 | 2014-03-08 | 2019-06-01 | 2019-06-01 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5604 | 25.3897 | مسحوب | No
2100194552 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1795000 | 89750 | 802790 | 802790 | 4035000994 | لا | 0 | 200409024458 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-12-25 | 2020-12-24 | 2022-06-30 | 2022-06-30 | 2020-12-24 |  |  |  | 41.0727 | 20.4622 | منجز | No
2100195801 | الهيئة العامة للزكاة والدخل | ترميم | ذات اولوية عالية | 4150933 | 207546.65 | 1200000 | 1200000 | 2055010796 | لا | 0 |  | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2021-06-16 | 2021-09-26 | 2021-09-22 | 2021-09-22 |  | 2021-09-26 |  |  | 50.1104 | 26.4351 | منجز | No
2100009811 | أمانة / تبوك | تشييد | ذات اولوية منخفضة | 699932.77 | 34996.6385 | 57797.68 | 57797.68 | 3550027826 | نعم | 57798 | 181201547127 | مسحوب | تكلفة العمل المنجز | 70 | 100 | 2015-11-01 | 2019-08-01 | 2021-10-31 | 2021-10-31 |  |  | ضعف كفاءة المقاول الفنية |  | 37.6847 | 28.3938 | مسحوب | No
2100097532 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 1299000 | 64950 | 1363950 | 1363950 | 4603004089 | لا | 0 | 200609054159 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-04-04 | 2020-06-19 | 2020-03-22 | 2020-03-22 | 2020-06-19 |  | اخرى |  | 41.3169 | 18.9766 | منجز | No
2100054983 | أمانة / نجران | تشييد | ذات اولوية عالية | 28460420.07 | 1423021.0035 | 25320442.65 | 25320442.65 | 5950001999 | لا | 0 | 180909073650 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 99 | 100 | 2015-08-10 | 2017-01-22 | 2020-12-31 | 2020-12-31 | 2017-01-22 |  |  |  | 44.2499 | 17.5603 | منجز | No
2100034403 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 400000 | 20000 | 420000 | 420000 | 4030211394 | لا | 0 | 210309061154 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-08-19 | 2020-08-07 | 2020-08-07 | 2020-08-07 | 2020-08-07 |  | ضعف كفاءة المقاول الفنية |  | 41.3009 | 18.9771 | منجز | No
2100190385 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية عالية وعاجلة | 1977651.55 | 98882.5775 | 707691.6 | 707691.6 | 4030128442 | لا | 0 | 201101387891 | ايقاف جزئي | الكميات التي تم تركيبها | 42 | 100 | 2021-05-05 | 2022-04-23 | 2022-06-07 | 2022-06-07 |  |  |  |  | 49.6054 | 25.4164 | Failed | No
2100011443 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1733955 | 86697.75 | 665081.35 | 665081.35 | 5855018218 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 45 | 100 | 2015-07-28 | 2016-06-12 | 2023-08-16 | 2023-08-16 |  |  | ضعف كفاءة المقاول الفنية |  | 42.0529 | 18.5228 | مسحوب | No
2100039314 | أمانة / الباحة | تشييد | ذات اولوية عالية | 3365963 | 168298.15 | 3365963 | 3365963 | 5810001890 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-11-22 | 2019-11-11 | 2019-11-12 | 2019-11-12 | 2019-11-11 |  | ضعف كفاءة المقاول الفنية |  | 41.3882 | 20.3871 | منجز | No
2100036444 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 699000 | 34950 | 0 | 0 | 4030065096 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 80 | 100 | 2013-05-31 | 2013-11-24 | 2021-09-30 | 2021-09-30 |  |  | ضعف كفاءة المقاول الفنية |  | 44.2537 | 17.5553 | مسحوب | No
2100190271 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية عالية وعاجلة | 2998170 | 149908.5 | 0 | 0 | 4030140033 | لا | 0 | 200301010285 | ايقاف كلي | الكميات التي تم تركيبها | 0 | 100 | 2020-12-16 | 2021-04-13 | 2021-04-12 | 2021-04-12 |  |  |  |  | 39.6046 | 24.4836 | Failed | No
2100190024 | وزارة البيئة والمياة والزراعة | ترميم | ذات اولوية متوسطة | 747426.8 | 37371.34 | 420583.38 | 420583.38 | 5801011161 | لا | 0 | 190201011586 | جاري | الكميات التي تم تركيبها | 95 | 100 | 2019-03-26 | 2019-11-15 | 2019-11-15 | 2019-11-15 |  |  | ضعف كفاءة المقاول الفنية |  | 41.5856 | 19.8549 | Failed | No
2100055834 | وزارة البيئة والمياة والزراعة | تشييد | لم تعد تحتاجها الجهة | 866216 | 43310.8 | 0 | 0 | 1010233732 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 0 | 100 | 2018-11-15 | 2019-04-11 | 2019-09-16 | 2019-09-16 |  |  | اخرى |  | 46.715 | 24.5827 | مسحوب | No
2100190363 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية عالية وعاجلة | 1092000 | 54600 | 0 | 0 | 2511104587 | لا | 0 | 52000005670 | ايقاف كلي | الكميات التي تم تركيبها | 0 | 100 | 2021-03-14 | 2021-11-05 | 2021-11-05 | 2021-11-05 |  |  |  |  | 43.9594 | 26.3256 | Failed | No
2100001131 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية وعاجلة | 23504548 | 1175227.4 | 13663173.6 | 13143308.4 | 5950005816 | لا | 0 | 190901127043 | جاري | منهجية القيمة المكتسبة | 88.7 | 99 | 2019-10-27 | 2020-10-22 | 2022-09-01 | 2022-09-01 |  |  | لا يوجد تأخير |  | 42.5848 | 17.1127 | Failed | No
2100054585 | وزارة الداخلية / المديرية العامة للدفاع المدني | ترميم | ذات اولوية عالية | 3331015.83 | 166550.7915 | 3331015.83 | 3331015.83 | 1010357102 | لا | 0 | 200201093948 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2020-01-05 | 2021-04-21 | 2023-01-01 | 2023-01-01 | 2021-04-21 |  | تأخرصرف المستحقات المالية |  | 41.4578 | 20.0116 | منجز | No
2100029691 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 199500 | 9975 | 199500 | 199500 | 4030006066 | لا | 0 | 191101295486 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-01-22 | 2019-07-21 | 2019-07-21 | 2019-07-21 | 2019-07-21 |  |  |  | 40.8384 | 20.7345 | منجز | No
2100190260 | وزارة البيئة والمياة والزراعة | توريد وتركيب | ذات اولوية عالية وعاجلة | 433387.5 | 21669.375 | 0 | 0 | 4030147825 | لا | 0 | 200501090642 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2020-12-06 | 2021-05-02 | 2021-05-02 | 2021-05-02 | 2021-05-02 |  |  |  | 42.5689 | 16.8875 | منجز | No
2100104425 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية عالية وعاجلة | 132245657.25 | 6612282.8625 | 0 | 0 | 5850008752 | نعم | 0.01 | 181109316565 | مسحوب | الكميات التي تم تركيبها | 5 | 5 | 2018-01-24 | 2020-12-21 | 2021-12-21 | 2021-12-21 |  |  | ضعف كفاءة المقاول الفنية |  | 40.4762 | 20.5103 | مسحوب | No
2100002284 | وزارة التعليم | تشييد | ذات اولوية عالية | 10546358 | 527317.9 | 1054332.83 | 1054332.83 | 2055002421 | لا | 0 |  | مسحوب | التكلفة المفوترة | 17 | 100 | 2015-02-02 | 2017-01-22 | 2017-12-18 | 2017-12-18 |  |  | ضعف كفاءة المقاول الفنية |  | 45.975 | 28.4334 | مسحوب | No
2100011830 | وزارة الخارجية | تشييد | ذات اولوية عالية | 83937297 | 4196864.85 | 276713 | 0 | 0 | لا | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 5 | 77 | 2019-07-01 | 2021-03-01 | 2022-01-03 | 2022-01-03 |  |  | موافقات |  | 18.4302 | 43.8449 | Failed | Yes
2100002096 | وزارة التعليم | تشييد | ذات اولوية عالية | 7149760.2 | 357488.01 | 214790.4 | 0 | 5950007285 | لا | 0 | 190309000539 | مسحوب | التكلفة المفوترة | 10 | 100 | 2013-09-09 | 2015-03-05 | 2023-05-24 | 2023-05-24 |  |  | ضعف كفاءة المقاول الفنية |  | 42.6509 | 17.1567 | مسحوب | Yes
2100003404 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 4178410 | 208920.5 | 240840 | 240840 | 5900073700 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 13 | 100 | 2012-11-12 | 2014-05-06 | 2023-02-01 | 2023-02-01 |  |  | ضعف كفاءة المقاول الفنية |  | 42.0529 | 18.5228 | مسحوب | No
2100016085 | أمانة / العاصمة المقدسة | أخرى | ذات اولوية متوسطة | 13128500 | 656425 | 10033146.76 | 10033146.76 | 4650047424 | لا | 0 | 180401004168 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 92 | 100 | 2018-07-16 | 2021-06-12 | 2021-09-30 | 2021-09-30 | 2021-06-12 |  | عدم اكتمال أو ضعف أعمال التصميم والدراسات |  | 39.1677 | 21.5008 | منجز | No
2100005784 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البحرية | تشييد | ذات اولوية متوسطة | 3549707 | 177485.35 | 2375085 | 2375085 | 1010214015 | لا | 0 | 210309073579 | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-12-19 | 2021-05-03 | 2021-12-31 | 2021-12-31 |  |  |  |  | 50.0633 | 26.4555 | Failed | No
2100009321 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 12669660.72 | 633483.036 | 9156676.07 | 9156676.07 | 1010196220 | لا | 0 | 190309008456 | جاري | التكلفة المفوترة | 99 | 100 | 2012-03-17 | 2014-03-07 | 2022-06-15 | 2022-06-15 |  |  | ضعف كفاءة المقاول الفنية |  | 40.0549 | 29.8587 | Failed | No
2100005574 | وزارة الموارد البشرية والتنمية الإجتماعية | تشييد | ذات اولوية منخفضة | 17555197.53 | 877759.8765 | 15168494.36 | 15168494.36 | 2511006797 | لا | 0 | 190309003252 | مسحوب | الكميات التي تم تركيبها | 97 | 100 | 2014-05-30 | 2016-05-06 | 2022-01-05 | 2022-01-05 |  |  | ضعف كفاءة المقاول الفنية |  | 45.9977 | 28.3641 | مسحوب | No
2100008363 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 1607162 | 80358.1 | 277031.2 | 277031.2 | 5864031115 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 53 | 100 | 2009-09-01 | 2010-06-22 | 2023-02-08 | 2023-02-08 |  |  | ضعف كفاءة المقاول الفنية |  | 42.0529 | 18.5228 | مسحوب | No
2100005121 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 9762527.83 | 488126.3915 | 4235896 | 4235896 | 5859001126 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 35 | 100 | 2011-11-12 | 2013-11-02 | 2023-02-01 | 2023-02-01 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.1351 | 19.1255 | مسحوب | No
2100010942 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 6353044 | 317652.2 | 1923253.2 | 0 | 1010196220 | لا | 0 |  | ايقاف كلي | التكلفة المفوترة | 35 | 100 | 2012-12-29 | 2014-09-20 | 2023-08-16 | 2023-08-16 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | Failed | Yes
2100010640 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 9676365.16 | 483818.258 | 3959174.69 | 3227572.09 | 1010060469 | لا | 0 | 190409087368 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2018-09-02 | 2020-08-22 | 2021-11-07 | 2021-11-07 | 2020-08-22 |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | منجز | No
2100018351 | أمانة / نجران | دراسة بيئية | ذات اولوية متوسطة | 6300000 | 315000 | 3570000 | 3360000 | 1010324035 | لا | 0 |  | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2019-01-31 | 2021-07-30 | 2021-07-30 | 2021-07-30 | 2021-07-30 |  | اخرى |  | 44.2274 | 17.5935 | منجز | No
2100013871 | أمانة / جازان | تشييد | ذات اولوية عالية | 8549762.5 | 427488.125 | 6133459 | 6133459 | 1138000190 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 89 | 100 | 2015-07-22 | 2016-07-17 | 2020-09-16 | 2020-09-16 | 2016-07-17 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 43.2149 | 16.7812 | منجز | No
2100012983 | أمانة / الرياض | تشييد | ذات اولوية عالية | 4936421.64 | 246821.082 | 0 | 0 | 1115001965 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 1 | 1 | 2019-09-18 | 2021-09-07 | 2021-09-07 | 2021-09-07 |  |  |  |  | 46.6888 | 24.7097 | مسحوب | No
2100013436 | أمانة / الباحة | تشييد | ذات اولوية عالية | 3261001.39 | 163050.0695 | 1879626.95 | 1879626.95 | 4031056228 | لا | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 59 | 80 | 2015-08-10 | 2017-07-19 | 2022-12-30 | 2022-12-30 |  |  |  |  | 41.4374 | 20.0509 | Failed | No
2100032701 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2319656 | 115982.8 | 693161.55 | 693161.55 | 1015000742 | لا | 0 |  | مسحوب | التكلفة المفوترة | 53 | 100 | 2010-12-21 | 2011-12-31 | 2013-09-18 | 2013-09-18 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7271 | 22.2863 | مسحوب | No
2100014044 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 4079715 | 203985.75 | 2826616.3 | 2826616.3 | 5810015209 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 70 | 100 | 2015-04-01 | 2016-03-21 | 2021-12-31 | 2021-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6362 | 20.2709 | مسحوب | No
2100023671 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 1927500 | 96375 | 612500 | 612500 | 5906008124 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 75 | 100 | 2014-12-17 | 2015-12-02 | 2019-07-02 | 2019-07-02 |  |  | اخرى |  | 42.8861 | 17.4347 | مسحوب | No
2100016354 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 15393752.73 | 769687.6365 | 4796818.15 | 4796818.15 | 1010046644 | لا | 0 |  | مسحوب | التكلفة المفوترة | 42 | 100 | 2015-10-07 | 2018-01-23 | 2018-01-23 | 2018-01-23 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5604 | 25.3897 | مسحوب | No
2100039572 | أمانة / الباحة | تشييد | ذات اولوية عالية | 33557645.15 | 1677882.2575 | 33557645.15 | 30202609 | 5810001890 | لا | 0 | 181009202799 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2013-11-04 | 2016-10-02 | 2022-10-01 | 2022-10-01 | 2016-10-02 |  | ضعف كفاءة المقاول الفنية |  | 41.4702 | 20.0196 | منجز | No
2100052426 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 989000 | 49450 | 1003207.34 | 1003207.34 | 5906014131 | لا | 0 | 200909036666 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-01-19 | 2021-01-07 | 2020-09-27 | 2020-09-27 | 2021-01-07 |  | اخرى |  | 39.7353 | 23.0091 | منجز | No
2100015621 | وزارة التعليم | تشييد | ذات اولوية عالية | 15168561.71 | 758428.0855 | 11881613.26 | 11881613.26 | 1010196220 | لا | 0 | 190209015502 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-01-08 | 2022-08-28 | 2022-08-18 | 2022-08-18 | 2022-08-28 |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | منجز | No
2100014560 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 15367660 | 768383 | 15478239.26 | 15478239.26 | 4030141919 | لا | 0 | 180709023215 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 97 | 99 | 2017-12-25 | 2020-11-21 | 2021-03-10 | 2021-03-10 | 2020-11-21 |  | اخرى |  | 39.2102 | 21.5069 | منجز | No
2100017032 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 4278310 | 213915.5 | 981789.19 | 611288.06 | 5859001022 | لا | 0 | 191101312566 | جاري | التكلفة المفوترة | 80 | 78 | 2018-12-19 | 2020-04-12 | 2023-01-08 | 2023-01-08 |  |  | ضعف كفاءة المقاول الفنية |  | 42.1351 | 19.1255 | Failed | No
2100014604 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 4074839.27 | 203741.9635 | 1140955 | 0 | 4030204423 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 28 | 100 | 2014-04-01 | 2015-05-26 | 2023-02-01 | 2023-02-01 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | مسحوب | Yes
2100016811 | أمانة / الجوف | تشييد | ذات اولوية عالية | 2990005 | 149500.25 | 2896796.82 | 2896796.82 | 3452007751 | لا | 0 | 180909103175 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-02-14 | 2015-09-30 | 2020-05-11 | 2020-05-11 | 2015-09-30 |  |  |  | 37.1473 | 31.4806 | منجز | No
2100022934 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 14122592.81 | 706129.6405 | 3360075.53 | 0.01 | 1116003554 | لا | 0 |  | جاري | التكلفة المفوترة | 36 | 100 | 2012-05-15 | 2014-05-05 | 2020-12-01 | 2020-12-01 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5604 | 25.3897 | Failed | No
2100015724 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 17647963 | 882398.15 | 5683906.2 | 11331.116 | 2050030703 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 53 | 100 | 2015-11-08 | 2017-10-28 | 2020-07-08 | 2020-07-08 | 2017-10-28 |  | ضعف كفاءة المقاول الفنية |  | 50.4785 | 26.3443 | منجز | No
2100021980 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 244206951 | 12210347.55 | 207372744 | 207372744 | 1010157290 | لا | 0 | 181101337049 | جاري | منهجية القيمة المكتسبة | 93.45 | 95.81 | 2019-01-02 | 2022-01-01 | 2023-05-18 | 2023-05-18 |  |  |  |  | 38.2131 | 23.9486 | منتظم | No
2100023203 | وزارة الموارد البشرية والتنمية الإجتماعية | إشراف | ذات اولوية منخفضة | 2801333.33 | 140066.6665 | 2745857 | 2745857 | 1010440712 | لا | 0 | 180809044852 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-02-21 | 2018-07-14 | 2021-12-15 | 2021-12-15 | 2018-07-14 |  | ضعف كفاءة المقاول الفنية |  | 41.6685 | 27.5238 | منجز | No
2100024021 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1061840 | 53092 | 1061840 | 1061840 | 4030138666 | لا | 0 | 190309004567 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-02-09 | 2015-02-04 | 2015-02-04 | 2015-02-04 | 2015-02-04 |  | ضعف كفاءة المقاول الفنية |  | 42.8415 | 21.2567 | منجز | No
2100018966 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 7315769.34 | 365788.467 | 1541278.44 | 0 | 5950007285 | لا | 0 |  | مسحوب | التكلفة المفوترة | 20 | 100 | 2013-09-17 | 2015-09-07 | 2023-02-02 | 2023-02-02 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | مسحوب | Yes
2100021044 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 9131887 | 456594.35 | 1405243 | 1405243 | 2057001038 | لا | 0 | 190209016293 | مسحوب | التكلفة المفوترة | 25 | 100 | 2013-08-31 | 2015-08-21 | 2023-02-01 | 2023-02-01 |  |  | ضعف كفاءة المقاول الفنية |  | 42.0529 | 18.5228 | مسحوب | No
2100028442 | وزارة الداخلية / مديرية الأمن العام | تشييد | ذات اولوية متوسطة | 2079044.1 | 103952.205 | 1777860 | 1777860 | 4031047242 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-03-22 | 2020-11-23 | 2020-11-21 | 2020-11-21 | 2020-11-23 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.978 | 21.3503 | منجز | No
2100027565 | وزارة التعليم | تشييد | ذات اولوية عالية | 19004619.54 | 950230.977 | 4125271 | 4125271 | 4030288443 | لا | 0 |  | مسحوب | التكلفة المفوترة | 35 | 100 | 2015-04-19 | 2018-07-03 | 2023-12-15 | 2023-12-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | No
2100024846 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 671759 | 33587.95 | 633076.5 | 0 | 4030211394 | لا | 0 | 210809161361 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-08-19 | 2020-11-03 | 2022-03-03 | 2022-03-03 | 2020-11-03 |  | ضعف كفاءة المقاول الفنية |  | 41.3009 | 18.9771 | منجز | Yes
2100027156 | وزارة المالية | تشييد | ذات اولوية متوسطة | 56591607 | 2829580.35 | 31924125.8 | 31924125.8 | 4030047446 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 75 | 100 | 2014-09-08 | 2016-02-21 | 2021-09-01 | 2021-09-01 |  |  | ضعف كفاءة المقاول الفنية |  | 42.4989 | 18.2169 | مسحوب | No
2100024706 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1365652 | 68282.6 | 1209052 | 1209052 | 4031046917 | لا | 0 | 190509001701 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-08-01 | 2019-06-12 | 2019-06-12 | 2019-06-12 | 2019-06-12 |  |  |  | 42.0236 | 21.9217 | منجز | No
2100023365 | وزارة التعليم | تشييد | ذات اولوية عالية | 9578453.4 | 478922.67 | 1615346.37 | 0 | 1010223860 | لا | 0 |  | مسحوب | التكلفة المفوترة | 25 | 100 | 2013-09-06 | 2015-08-28 | 2023-05-10 | 2023-05-10 |  |  | ضعف كفاءة المقاول الفنية |  | 42.6509 | 17.1567 | مسحوب | Yes
2100026401 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1923808 | 96190.4 | 369562 | 99483 | 5859003293 | لا | 0 | 191101283162 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2018-12-06 | 2020-01-30 | 2021-07-08 | 2021-07-08 | 2020-01-30 |  | ضعف كفاءة المقاول الفنية |  | 42.1351 | 19.1255 | منجز | No
2100027996 | أمانة / جازان | تشييد | ذات اولوية عالية | 8048887.24 | 402444.362 | 0 | 0 | 5904006379 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 60 | 100 | 2014-01-05 | 2016-02-21 | 2019-02-26 | 2019-02-26 |  |  | ضعف كفاءة المقاول الفنية |  | 42.513 | 17.1465 | مسحوب | No
2100030542 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 7992562.2 | 399628.11 | 3412824 | 3412824 | 5950014853 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 44 | 100 | 2019-07-07 | 2020-07-27 | 2021-09-30 | 2021-09-30 | 2020-07-27 |  |  |  | 44.2235 | 17.5695 | منجز | No
2100039163 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 18981270 | 949063.5 | 16950959 | 16950959 | 4031019772 | لا | 0 | 3046384 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 95.62 | 95.62 | 2019-11-11 | 2020-04-04 | 2020-04-04 | 2020-04-04 | 2020-04-04 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.8594 | 21.3781 | منجز | No
2100026036 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 4456800 | 222840 | 4248796.7 | 4248796.7 | 4030159820 | لا | 0 | 190709175615 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 99.46 | 100 | 2019-03-23 | 2022-12-06 | 2022-05-16 | 2022-05-16 | 2022-12-06 |  | ضعف كفاءة المقاول الفنية |  | 41.0831 | 19.1217 | منجز | No
2100028490 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 179227059 | 8961352.95 | 72462162 | 72462162 | 2050011975 | لا | 0 | 200209137875 | مسحوب | منهجية القيمة المكتسبة | 77.39 | 100 | 2013-05-28 | 2015-05-27 | 2022-08-30 | 2022-08-30 |  |  | عدم وجود كوادر كافية في الجهه لادارة المشروع |  | 38.3313 | 23.9561 | مسحوب | No
2100029783 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 113698900 | 5684945 | 2273978 | 2273978 | 4030140655 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 2 | 100 | 2013-11-11 | 2020-10-13 | 2022-12-31 | 2022-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 40.4055 | 21.2686 | مسحوب | No
2100106912 | جامعة نجران | تشييد | ذات اولوية عالية وعاجلة | 59724810 | 2986240.5 | 53667278 | 53667278 | 5855000147 | لا | 0 | 181209511592 | جاري | الكميات التي تم تركيبها | 62 | 100 | 2012-09-29 | 2015-08-27 | 2022-08-24 | 2022-08-24 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 47.1167 | 17.4861 | Failed | No
2100031404 | أمانة / عسير | تشييد | ذات اولوية عالية | 3992820 | 199641 | 0 | 0 | 5858010028 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 5 | 100 | 2015-03-01 | 2016-08-20 | 2022-12-20 | 2022-12-20 |  |  | أوامر سامية |  | 43.3292 | 17.5669 | مسحوب | No
2100092956 | أمانة / جازان | تشييد | ذات اولوية عالية وعاجلة | 4389750 | 219487.5 | 3000750 | 3000750 | 5907010673 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-04-20 | 2020-07-29 | 2021-06-03 | 2021-06-03 | 2020-07-29 |  | ضعف كفاءة المقاول الفنية |  | 42.6022 | 16.9042 | منجز | No
2100033622 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 21042678.3 | 1052133.915 | 6507425.64 | 2896112.5 | 1116004360 | لا | 0 |  | مسحوب | التكلفة المفوترة | 50 | 100 | 2011-04-24 | 2014-03-01 | 2014-03-02 | 2014-03-02 |  |  | ضعف كفاءة المقاول الفنية |  | 50.5907 | 26.2816 | مسحوب | No
2100030730 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 159050 | 7952.5 | 159050 | 159050 | 3350027223 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-11-04 | 2020-05-04 | 2020-05-04 | 2020-05-04 | 2020-05-04 |  |  |  | 42.9913 | 27.4726 | منجز | No
2100032045 | أمانة / نجران | تشييد | ذات اولوية عالية | 30546637 | 1527331.85 | 22821750.34 | 22821750.34 | 5950009827 | لا | 0 | 190101005357 | جاري | الكميات التي تم تركيبها | 86.28 | 91 | 2019-03-17 | 2022-12-29 | 2023-03-30 | 2023-03-30 |  |  | ضعف كفاءة المقاول الفنية |  | 44.236 | 17.5582 | منتظم | No
2100030192 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 7989886.63 | 399494.3315 | 5735082 | 5735082 | 5950013363 | لا | 0 |  | جاري | تكلفة العمل المنجز | 66 | 75 | 2015-08-25 | 2021-07-17 | 2022-11-09 | 2022-11-09 |  |  | اخرى |  | 44.2234 | 17.5543 | متأخر | No
2100031356 | أمانة / الباحة | تشييد | ذات اولوية عالية وعاجلة | 2714420 | 135721 | 0 | 0 | 5802013925 | لا | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 0 | 0 | 2019-05-08 | 2020-09-20 | 2022-12-31 | 2022-12-31 |  |  | تأخرصرف المستحقات المالية |  | 41.2907 | 20.166 | Failed | No
2100090086 | جامعة نجران | تشييد | ذات اولوية عالية وعاجلة | 56905225 | 2845261.25 | 48777465 | 48777465 | 2066001761 | لا | 0 | 181109338658 | جاري | الكميات التي تم تركيبها | 99 | 100 | 2013-06-14 | 2015-11-18 | 2021-11-30 | 2021-11-30 |  |  | تأخرصرف المستحقات المالية |  | 44.2341 | 17.5757 | Failed | No
2100107251 | جامعة الملك فيصل | تشييد | ذات اولوية عالية وعاجلة | 1320000 | 66000 | 1320000 | 1320000 | 2251045738 | لا | 0 | 180809054985 | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2016-11-12 | 2017-09-04 | 2018-09-05 | 2018-09-05 |  | 2017-09-04 | تأخرصرف المستحقات المالية |  | 49.5604 | 25.3897 | منجز | No
2100037133 | أمانة / جازان | تشييد | ذات اولوية عالية | 882579 | 44128.95 | 209073 | 209073 | 5906019673 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 94 | 100 | 2019-06-17 | 2019-12-14 | 2021-07-16 | 2021-07-16 | 2019-12-14 |  | ضعف كفاءة المقاول الفنية |  | 42.513 | 17.1465 | منجز | No
2100032690 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 2574150 | 128707.5 | 2316210 | 2316210 | 4032030986 | لا | 0 | 190509006487 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-01-22 | 2019-08-19 | 2019-08-19 | 2019-08-19 | 2019-08-19 |  |  |  | 40.3941 | 21.256 | منجز | No
2100036783 | أمانة / جازان | تشييد | ذات اولوية عالية | 820137 | 41006.85 | 489361 | 489361 | 5903005814 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 60 | 100 | 2012-12-11 | 2013-12-06 | 2019-02-01 | 2019-02-01 |  |  | اخرى |  | 42.2578 | 17.7377 | مسحوب | No
2100034963 | أمانة / جازان | تشييد | ذات اولوية عالية | 4980092 | 249004.6 | 4875509.44 | 4875509.44 | 5855021000 | لا | 0 | 180909098694 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 98 | 100 | 2013-11-09 | 2015-02-20 | 2019-05-03 | 2019-05-03 | 2015-02-20 |  | اخرى |  | 42.6281 | 17.1641 | منجز | No
2100036691 | أمانة / جازان | تشييد | ذات اولوية عالية | 1298000 | 64900 | 1104000 | 1104000 | 5905015155 | لا | 0 | 191001142184 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 92.45 | 100 | 2019-10-30 | 2020-10-29 | 2021-11-11 | 2021-11-11 | 2020-10-29 |  | ضعف كفاءة المقاول الفنية |  | 43.1053 | 17.2475 | منجز | No
2100035022 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 489090 | 24454.5 | 274990 | 274990 | 3550019236 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 64 | 64 | 2016-05-15 | 2016-11-11 | 2021-02-25 | 2021-02-25 |  |  | ضعف كفاءة المقاول الفنية |  | 36.563 | 28.3759 | مسحوب | No
2100034016 | أمانة / جازان | تشييد | ذات اولوية عالية | 5135714 | 256785.7 | 1392181 | 1392181 | 5950011723 | لا | 0 | 201009189455 | مسحوب | الكميات التي تم تركيبها | 79 | 100 | 2019-06-19 | 2020-06-13 | 2021-11-11 | 2021-11-11 |  |  | ضعف كفاءة المقاول الفنية |  | 42.9398 | 17.2377 | مسحوب | No
2100036890 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 2490200 | 124510 | 2490200 | 2490200 | 3357606131 | لا | 0 | 190301028535 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-11-28 | 2019-11-23 | 2020-04-24 | 2020-04-24 | 2019-11-23 |  | تأخرصرف المستحقات المالية |  | 40.9385 | 28.0075 | منجز | No
2100000781 | جامعة نجران | تشييد | ذات اولوية عالية | 50000000 | 2500000 | 28076353.95 | 28076353.95 | 1001032384 | لا | 0 | 181209513558 | جاري | الكميات التي تم تركيبها | 63 | 100 | 2015-01-14 | 2017-12-11 | 2023-01-02 | 2023-01-02 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 44.2341 | 17.5757 | Failed | No
2100103036 | شركة المياه الوطنية / منطقة مكة المكرمة | إشراف | ذات اولوية عالية | 12696000 | 634800 | 13496000 | 9756636.79 | 1010426678 | لا | 0 | 200709052696 | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2014-04-20 | 2018-10-10 | 2018-10-10 | 2018-10-10 | 2018-10-10 |  | لا يوجد تأخير |  | 39.1792 | 21.5319 | منجز | No
2100036260 | أمانة / جازان | تشييد | ذات اولوية عالية | 1911948.3 | 95597.415 | 1213750.5 | 1213750.5 | 1010245651 | لا | 0 | 180909110328 | مسحوب | الكميات التي تم تركيبها | 54 | 100 | 2015-01-16 | 2016-01-11 | 2019-09-09 | 2019-09-09 |  |  | اخرى |  | 42.0282 | 17.7195 | مسحوب | No
2100035700 | أمانة / جازان | تشييد | ذات اولوية عالية | 3999500 | 199975 | 2559680 | 2559680 | 5950018572 | لا | 0 | 180809062072 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-02-24 | 2019-05-18 | 2019-05-18 | 2019-05-18 | 2019-05-18 |  | اخرى |  | 42.9388 | 16.6926 | منجز | No
2100071400 | جامعة نجران | تشييد | ذات اولوية عالية وعاجلة | 19052259 | 952612.95 | 14619777 | 14619777 | 2066001761 | لا | 0 | 181209509752 | جاري | الكميات التي تم تركيبها | 99 | 100 | 2014-12-23 | 2016-09-03 | 2021-12-01 | 2021-12-01 |  |  | تأخرصرف المستحقات المالية |  | 44.2341 | 17.5757 | Failed | No
2100044424 | أمانة / جازان | تشييد | ذات اولوية عالية | 5661038 | 283051.9 | 0 | 0 | 5950012625 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 0 | 100 | 2015-11-25 | 2016-11-19 | 2016-11-20 | 2016-11-20 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | مسحوب | No
2100039141 | وزارة الداخلية / مديرية الأمن العام | تشييد | ذات اولوية متوسطة | 1854573 | 92728.65 | 1854573 | 1854573 | 4031190271 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-10-13 | 2020-10-13 | 2021-09-13 | 2021-09-13 | 2020-10-13 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.3569 | 22.0177 | منجز | No
2100040342 | مدينة الملك عبدالله الطبية بالعاصمة المقدسة | تشييد | ذات اولوية عالية | 16149.62 | 807.481 | 14392.88 | 0 | 4031040631 | لا | 0 | 190901139237 | ايقاف كلي | الكميات التي تم تركيبها | 33 | 66 | 2019-07-21 | 2023-07-20 | 2023-07-20 | 2023-07-20 |  |  | اخرى |  | 39.8811 | 21.382 | Failed | Yes
2100039351 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 1315083 | 65754.15 | 0 | 0 | 5950002027 | لا | 0 | 200309039841 | ايقاف كلي | تكلفة العمل المنجز | 5.5 | 100 | 2019-07-10 | 2020-06-30 | 2020-06-30 | 2020-06-30 |  |  | ضعف كفاءة المقاول الفنية |  | 44.2297 | 17.5482 | Failed | No
2100034296 | أمانة / حفر الباطن | تشييد | ذات اولوية متوسطة | 3981210 | 199060.5 | 3981209.86 | 3981209.86 | 1010350726 | لا | 0 | 0 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-11-06 | 2020-04-30 | 2020-04-16 | 2020-04-16 | 2020-04-30 |  |  |  | 45.985 | 28.3528 | منجز | No
2100031393 | أمانة / العاصمة المقدسة | أخرى | ذات اولوية متوسطة | 2780116.25 | 139005.8125 | 1172914 | 1172914 | 4622100020 | لا | 0 |  | جاري | تكلفة العمل المنجز | 15.49 | 15.49 | 2019-07-08 | 2021-07-07 | 2021-07-07 | 2021-07-07 |  |  |  |  | 39.3829 | 21.9002 | خدمات عامة | No
2100106820 | جامعة نجران | تشييد | ذات اولوية عالية | 20953276 | 1047663.8 | 17862134.4 | 17862134.4 | 5855013111 | لا | 0 | 181209543209 | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-07-28 | 2016-02-26 | 2021-12-31 | 2021-12-31 |  |  | تغيرات في نطاق المشروع |  | 44.2341 | 17.5757 | Failed | No
2100040622 | وزارة الصحة / حائل | تشييد | ذات اولوية عالية | 2499325 | 124966.25 | 2499325 | 2499325 | 3350020848 | لا | 0 | 181009135594 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-07-17 | 2020-11-19 | 2020-11-27 | 2020-11-27 | 2020-11-19 |  | ضعف كفاءة المقاول الفنية |  | 41.6906 | 27.4936 | منجز | No
2100041355 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 19400000 | 970000 | 17134070.86 | 17134070.86 | 1010136405 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-02-27 | 2019-05-23 | 2020-02-18 | 2020-02-18 | 2019-05-23 |  | اخرى |  | 36.5261 | 28.3915 | منجز | No
2100049626 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 3799921.15 | 189996.0575 | 3040225.8 | 3040225.8 | 4700000126 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-06-06 | 2016-12-24 | 2016-06-06 | 2016-06-06 | 2016-12-24 |  |  |  | 37.2629 | 25.0351 | منجز | No
2100039981 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 127640355.61 | 6382017.7805 | 120283943 | 108701743 | 4700004138 | لا | 0 | 180809056153 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2015-05-07 | 2017-05-06 | 2023-01-12 | 2023-01-12 | 2017-05-06 |  | أوامر تغيير |  | 38.2073 | 24.0402 | منجز | No
2100093074 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 24108704.07 | 1205435.2035 | 968660 | 968660 | 4031047880 | لا | 0 | 4046252 | جاري | تكلفة العمل المنجز | 56.55 | 56.55 | 2014-07-13 | 2016-07-12 | 2016-08-28 | 2016-08-28 |  |  | التنسيق مع أصحاب المصلحه (خدمات | أخرى | 39.8585 | 21.384 | Failed | No
2100009461 | وزارة التعليم | تشييد | ذات اولوية عالية | 11618746 | 580937.3 | 0.01 | 0.01 | 1010178798 | لا | 0 |  | مسحوب | التكلفة المفوترة | 65 | 100 | 2013-05-10 | 2015-04-30 | 2023-05-10 | 2023-05-10 |  |  | ضعف كفاءة المقاول الفنية |  | 44.2341 | 17.5757 | مسحوب | No
2100039550 | أمانة / الباحة | تشييد | ذات اولوية منخفضة | 1973995.74 | 98699.787 | 1198708.04 | 1198708.04 | 1010146802 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 64 | 64 | 2015-06-17 | 2016-07-30 | 2020-06-09 | 2020-06-09 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | مسحوب | No
2100045382 | أمانة / جازان | تشييد | ذات اولوية عالية | 1000000 | 50000 | 0.01 | 0.01 | 5855042619 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 0 | 100 | 2015-03-31 | 2015-09-27 | 2020-02-24 | 2020-02-24 |  |  | اخرى |  | 42.8407 | 16.9703 | مسحوب | No
2100009144 | جامعة نجران | تشييد | ذات اولوية عالية وعاجلة | 18695370 | 934768.5 | 16709250 | 16709250 | 2051003225 | لا | 0 | 180709021930 | جاري | الكميات التي تم تركيبها | 97 | 99 | 2014-06-15 | 2016-03-26 | 2022-09-13 | 2022-09-13 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 47.1167 | 17.4861 | Failed | No
2100047445 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 3000000 | 150000 | 3000000 | 3000000 | 1011012161 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-03-10 | 2020-02-27 | 2020-02-27 | 2020-02-27 | 2020-02-27 |  |  |  | 48.864 | 25.9766 | منجز | No
2100044951 | أمانة / الجوف | تشييد | ذات اولوية عالية | 5830000 | 291500 | 5830000 | 5830000 | 3400011095 | لا | 0 | 191101308382 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-11-06 | 2020-05-01 | 2020-05-07 | 2020-05-07 | 2020-05-01 |  |  |  | 40.1043 | 29.878 | منجز | No
2100049335 | أمانة / جازان | تشييد | ذات اولوية عالية وعاجلة | 849200 | 42460 | 71970 | 71970 | 1010293871 | لا | 0 | 181109318294 | مسحوب | الكميات التي تم تركيبها | 10 | 100 | 2013-11-07 | 2014-10-23 | 2019-02-25 | 2019-02-25 |  |  | اخرى |  | 42.6931 | 16.9776 | مسحوب | No
2100050853 | أمانة / جازان | تشييد | ذات اولوية عالية | 547740 | 27387 | 531852 | 531852 | 5900105614 | لا | 0 | 181109329528 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 97 | 100 | 2018-08-26 | 2019-08-21 | 2019-08-22 | 2019-08-22 | 2019-08-21 |  | اخرى |  | 42.5769 | 16.8825 | منجز | No
2100048646 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 2322322.5 | 116116.125 | 2322323 | 2074895 | 3550026097 | لا | 0 | 180909111197 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-10-01 | 2019-05-20 | 2020-10-01 | 2020-10-01 | 2019-05-20 |  | اخرى |  | 35.0202 | 28.4788 | منجز | No
2100049965 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 3114803 | 155740.15 | 1197750 | 1197750 | 3556000250 | لا | 0 | 181209446522 | جاري | تكلفة العمل المنجز | 83 | 100 | 2015-11-07 | 2016-11-01 | 2023-05-01 | 2023-05-01 |  |  | ضعف كفاءة المقاول الفنية |  | 35.0202 | 28.4788 | متأخر | No
2100048333 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 3994200 | 199710 | 3994200 | 3994200 | 4605000749 | لا | 0 | 200101004376 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 95 | 2019-12-19 | 2021-03-19 | 2021-03-09 | 2021-03-09 | 2021-03-19 |  | اخرى |  | 39.7923 | 22.27 | منجز | No
2100057455 | وكالة / الإسكان | تشييد | ذات اولوية متوسطة | 320994335.28 | 16049716.764 | 251417670.07 | 251417670.07 | 1010039430 | لا | 0 |  | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2013-06-17 | 2015-06-07 | 2022-06-30 | 2022-06-30 |  |  | موافقات | أخرى | 44.2341 | 17.5757 | Failed | No
2100048716 | أمانة / الجوف | تشييد | ذات اولوية عالية | 2076950 | 103847.5 | 2066978.58 | 2066978.58 | 3400006337 | لا | 0 | 180901092300 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-09-10 | 2019-08-30 | 2019-08-13 | 2019-08-13 | 2019-08-30 |  |  |  | 40.3826 | 30.1186 | منجز | No
2100051450 | أمانة / جازان | تشييد | ذات اولوية عالية | 998914.55 | 49945.7275 | 659040 | 659040 | 5900011423 | لا | 0 | 181209454763 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 84 | 100 | 2012-12-28 | 2014-01-15 | 2019-09-01 | 2019-09-01 | 2014-01-15 |  | اخرى |  | 42.6979 | 16.9769 | منجز | No
2100050842 | أمانة / جازان | تشييد | ذات اولوية عالية | 4347300 | 217365 | 4347300 | 4347300 | 5901009711 | لا | 0 | 180809061139 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-06-24 | 2016-06-19 | 2019-12-23 | 2019-12-23 | 2016-06-19 |  | اخرى |  | 42.6432 | 16.8855 | منجز | No
2100049350 | أمانة / جازان | تشييد | ذات اولوية عالية | 2889907.2 | 144495.36 | 2889907.2 | 0 | 5901008401 | لا | 0 | 180909110308 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 90 | 100 | 2009-09-11 | 2010-08-30 | 2019-09-09 | 2019-09-09 | 2010-08-30 |  | اخرى |  | 42.0276 | 17.7196 | منجز | Yes
2100050945 | أمانة / جازان | تشييد | ذات اولوية عالية وعاجلة | 2881180 | 144059 | 1946551 | 1946551 | 1017001724 | لا | 0 | 191001113638 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-05-20 | 2019-11-16 | 2021-04-29 | 2021-04-29 | 2019-11-16 |  | ضعف كفاءة المقاول الفنية |  | 42.584 | 16.8819 | منجز | No
2100019213 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 354445.13 | 17722.2565 | 354445.13 | 354445.13 | 4031200354 | لا | 0 | 191001157186 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-07-22 | 2020-07-10 | 2020-05-13 | 2020-05-13 | 2020-07-10 |  | اخرى |  | 39.7363 | 23.0089 | منجز | No
2100050901 | أمانة / جازان | تشييد | ذات اولوية عالية | 6836000 | 341800 | 223344 | 223344 | 5950011723 | لا | 0 | 200201129895 | مسحوب | الكميات التي تم تركيبها | 7 | 100 | 2019-07-02 | 2019-12-29 | 2022-03-30 | 2022-03-30 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5649 | 16.8559 | مسحوب | No
2100049895 | أمانة / تبوك | تشييد | لم تعد تحتاجها الجهة | 1887650 | 94382.5 | 1179527 | 931117 | 3555000931 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 64 | 100 | 2016-01-02 | 2021-09-14 | 2021-03-30 | 2021-03-30 | 2021-09-14 |  | ضعف كفاءة المقاول الفنية |  | 36.5752 | 28.3795 | منجز | No
2100052312 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 27963784.53 | 1398189.2265 | 22719782 | 22719782 | 3350000631 | لا | 0 | 181001173465 | جاري | الكميات التي تم تركيبها | 87 | 100 | 2019-02-18 | 2021-01-26 | 2023-01-31 | 2023-01-31 |  |  | التنسيق مع أصحاب المصلحه (خدمات |  | 41.7452 | 27.4912 | متأخر | No
2100054924 | أمانة / تبوك | تشييد | ذات اولوية عالية وعاجلة | 18560934 | 928046.7 | 16569344 | 12173825.69 | 4030150094 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-03-23 | 2016-03-22 | 2021-03-17 | 2021-03-17 | 2016-03-22 |  | ضعف كفاءة المقاول الفنية |  | 36.559 | 28.3859 | منجز | No
2100053255 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 1100400 | 55020 | 1100399.99 | 1100399.99 | 4030183780 | لا | 0 | 200501045108 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 75 | 85 | 2019-09-07 | 2020-08-07 | 2020-08-26 | 2020-08-26 | 2020-08-07 |  | اخرى |  | 39.7926 | 22.253 | منجز | No
2100053605 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 95767475 | 4788373.75 | 76806949.96 | 63213617.7 | 4030150048 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 80 | 100 | 2014-05-05 | 2016-04-13 | 2020-07-20 | 2020-07-20 |  |  | ضعف كفاءة المقاول الفنية |  | 39.1906 | 21.5365 | مسحوب | No
2100002903 | أمانة / العاصمة المقدسة | أخرى | ذات اولوية متوسطة | 340483457.4 | 17024172.87 | 16629992 | 16629992 | 4030008335 | لا | 0 |  | مسحوب | اخرى | 90 | 90 | 2010-10-09 | 2013-03-13 | 2020-06-30 | 2020-06-30 |  |  | اخرى |  | 39.852 | 21.3817 | مسحوب | No
2100087780 | جامعة نجران | تشييد | ذات اولوية عالية | 9937570 | 496878.5 | 9178235 | 9178235 | 2066001761 | لا | 0 | 181209510917 | جاري | الكميات التي تم تركيبها | 98 | 100 | 2013-06-16 | 2015-05-23 | 2022-05-29 | 2022-05-29 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 44.2341 | 17.5757 | Failed | No
2100053056 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 6579559 | 328977.95 | 6579559 | 6579559 | 5805000328 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-11-26 | 2019-11-15 | 2021-06-14 | 2021-06-14 | 2019-11-15 |  |  |  | 41.4632 | 20.0217 | منجز | No
2100060233 | جامعة الملك فيصل | تشييد | ذات اولوية منخفضة | 68200 | 3410 | 68200 | 68200 | 1010283860 | لا | 0 | 180809055129 | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2018-07-01 | 2018-03-02 | 2018-03-02 | 2018-03-02 |  | 2018-03-02 | تأخرصرف المستحقات المالية |  | 49.5604 | 25.3897 | منجز | No
2100052614 | أمانة / جازان | تشييد | ذات اولوية عالية وعاجلة | 13416042.24 | 670802.112 | 8289908 | 8289908 | 1138000190 | لا | 0 | 181109358768 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 89 | 100 | 2014-12-17 | 2016-12-06 | 2021-11-11 | 2021-11-11 | 2016-12-06 |  | ضعف كفاءة المقاول الفنية |  | 42.6068 | 16.9129 | منجز | No
2100055716 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 42252114 | 2112605.7 | 33801685 | 33801685 | 4030023505 | لا | 0 | 180809040142 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 98.31 | 100 | 2017-09-21 | 2019-09-21 | 2023-01-31 | 2023-01-31 |  |  | اخرى |  | 38.24 | 24.0285 | متأخر | No
2100106654 | جامعة نجران | تشييد | ذات اولوية عالية وعاجلة | 50000000 | 2500000 | 35716222.6 | 35716222.6 | 5950013600 | لا | 0 | 181209454983 | جاري | الكميات التي تم تركيبها | 76 | 90 | 2014-04-11 | 2017-04-11 | 2022-12-29 | 2022-12-29 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 47.1167 | 17.4861 | Failed | No
2100106606 | جامعة نجران | تشييد | ذات اولوية عالية وعاجلة | 27047380 | 1352369 | 4136442 | 4136442 | 2066001761 | لا | 0 | 221009018991 | جاري | الكميات التي تم تركيبها | 60 | 100 | 2017-11-24 | 2021-06-30 | 2022-10-25 | 2022-10-25 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 44.2341 | 17.5757 | Failed | No
2100066522 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 715680 | 35784 | 0 | 0 | 4031071448 | لا | 0 |  | جاري | تكلفة العمل المنجز | 77 | 81 | 2019-05-01 | 2020-07-24 | 2021-07-05 | 2021-07-05 |  |  | اخرى |  | 39.7041 | 21.6101 | Failed | No
2100059356 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 3993275 | 199663.75 | 0.01 | 0.01 | 5950014399 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 0 | 100 | 2015-09-16 | 2016-08-31 | 2019-02-05 | 2019-02-05 |  |  | اخرى |  | 42.5618 | 16.9556 | مسحوب | No
2100063092 | أمانة / عسير | تشييد | ذات اولوية عالية | 779450 | 38972.5 | 701505 | 701505 | 5852002665 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 90 | 100 | 2015-05-24 | 2016-06-11 | 2020-03-02 | 2020-03-02 |  |  | ضعف كفاءة المقاول الفنية |  | 41.9567 | 19.5602 | مسحوب | No
2100058133 | أمانة / الجوف | تشييد | ذات اولوية عالية | 804200 | 40210 | 804200 | 804200 | 3350013518 | لا | 0 | 190509001400 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-02-16 | 2020-02-16 | 2020-02-16 | 2020-02-16 | 2016-09-28 |  |  |  | 37.9787 | 30.714 | منجز | No
2100058402 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 12987447.16 | 649372.358 | 6971602.284 | 6971602.284 | 1010187466 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 77 | 100 | 2013-11-06 | 2017-11-14 | 2021-01-14 | 2021-01-14 |  |  | ضعف كفاءة المقاول الفنية |  | 48.9571 | 28.4519 | مسحوب | No
2100058155 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 1288370 | 64418.5 | 1107641 | 1107641 | 5950002498 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 85 | 100 | 2005-12-03 | 2006-10-19 | 2022-11-17 | 2022-11-17 |  |  | ضعف كفاءة المقاول الفنية |  | 43.5187 | 17.6646 | مسحوب | No
2100058881 | أمانة / جدة | تشييد | ذات اولوية عالية | 15753744 | 787687.2 | 9617484 | 9617484 | 4031036822 | لا | 0 | 190701085198 | جاري | تكلفة العمل المنجز | 85 | 78 | 2019-09-16 | 2021-08-24 | 2023-02-03 | 2023-02-03 |  |  | اخرى |  | 39.218 | 21.5245 | منتظم | No
2100058590 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 3371981 | 168599.05 | 1571247 | 1571247 | 4603004037 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 76 | 100 | 2014-01-15 | 2015-07-10 | 2022-06-10 | 2022-06-10 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0859 | 19.1571 | مسحوب | No
2100060281 | أمانة / تبوك | تشييد | ذات اولوية عالية | 1781666 | 89083.3 | 1781666 | 383476 | 3550123598 | لا | 0 | 200101038949 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-09-23 | 2020-09-17 | 2021-04-30 | 2021-04-30 | 2020-09-17 |  | ضعف كفاءة المقاول الفنية |  | 36.5668 | 28.3786 | منجز | No
2100059776 | أمانة / الجوف | تشييد | ذات اولوية عالية | 1638000 | 81900 | 1638000 | 1638000 | 4030129645 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-10-08 | 2019-12-08 | 2019-12-08 | 2019-12-08 | 2019-12-08 |  |  |  | 38.226 | 30.4957 | منجز | No
2100100122 | وزارة الداخلية / ديوان وزارة الداخلية | تصميم وتشييد | ذات اولوية منخفضة | 961766254.72 | 48088312.736 | 26988074.66 | 26988074.66 | 1010199246 | لا | 0 | 180809053494 | ايقاف كلي | منهجية القيمة المكتسبة | 1 | 1 | 2016-10-17 | 2019-04-04 | 2025-06-30 | 2025-06-30 |  |  | تأخرصرف المستحقات المالية | أخرى | 50.0143 | 18.8185 | Failed | No
2100060082 | أمانة / جازان | تشييد | لم تعد تحتاجها الجهة | 2521870.87 | 126093.5435 | 627059.88 | 627059.88 | 5901014533 | لا | 0 | 180909114414 | مسحوب | الكميات التي تم تركيبها | 26 | 100 | 2014-06-29 | 2015-06-24 | 2015-06-24 | 2015-06-24 |  |  | اخرى |  | 42.9733 | 16.528 | مسحوب | No
2100062580 | أمانة / عسير | تشييد | ذات اولوية عالية | 4993600 | 249680 | 4367871 | 4367871 | 5857024318 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 93 | 100 | 2015-10-03 | 2016-09-30 | 2021-12-15 | 2021-12-15 |  |  | ضعف كفاءة المقاول الفنية |  | 42.8217 | 18.193 | مسحوب | No
2100064971 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 1497820 | 74891 | 397261 | 397261 | 5950005936 | لا | 0 | 210601172735 | جاري | تكلفة العمل المنجز | 77.72 | 83 | 2013-08-26 | 2014-10-14 | 2023-03-31 | 2023-03-31 |  |  | ضعف كفاءة المقاول الفنية |  | 44.2124 | 18.528 | Failed | No
2100059474 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 966300 | 48315 | 339654 | 48000 | 3350106539 | لا | 0 | 181101359589 | مسحوب | الكميات التي تم تركيبها | 37 | 37 | 2018-09-02 | 2021-05-26 | 2022-06-06 | 2022-06-06 |  |  |  |  | 41.7269 | 27.5017 | مسحوب | No
2100090204 | جامعة الإمام محمد بن سعود الاسلامية | تشييد | ذات اولوية متوسطة | 24247079.04 | 1212353.952 | 21702410.73 | 21702410.73 | 1010353173 | لا | 0 | 181109342413 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2011-07-20 | 2013-05-02 | 2019-06-13 | 2019-06-13 | 2013-05-02 |  | لا يوجد تأخير |  | 49.5604 | 25.3897 | منجز | No
2100066544 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 10605591 | 530279.55 | 8122862.04 | 8122862.04 | 5800004732 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-05-15 | 2016-10-29 | 2022-08-01 | 2022-08-01 | 2016-10-29 |  | تأخرصرف المستحقات المالية |  | 41.6511 | 20.2795 | منجز | No
2100066872 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 565850 | 28292.5 | 509265 | 509265 | 3553000678 | لا | 0 | 190509011412 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-12-30 | 2019-12-24 | 2021-09-01 | 2021-09-01 | 2019-12-24 |  |  |  | 34.9451 | 29.2864 | منجز | No
2100074233 | مدينة الملك عبدالله الطبية بالعاصمة المقدسة | تصميم | ذات اولوية عالية | 72825 | 3641.25 | 72825 | 72825 | 1010358934 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-07-26 | 2018-10-24 | 2018-10-24 | 2018-10-24 | 2018-10-24 |  | موافقات |  |  |  | منجز | No
2100011863 | جامعة نجران | تشييد | ذات اولوية عالية | 79910802 | 3995540.1 | 55596756 | 55596756 | 1010019502 | لا | 0 | 181209533277 | ايقاف كلي | الكميات التي تم تركيبها | 89 | 100 | 2011-07-04 | 2014-05-01 | 2023-08-24 | 2023-08-24 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 44.2341 | 17.5757 | Failed | No
2100014195 | جامعة نجران | تشييد | ذات اولوية عالية وعاجلة | 33971700 | 1698585 | 33971700 | 33971700 | 2066001761 | لا | 0 | 181109338440 | جاري | الكميات التي تم تركيبها | 100 | 100 | 2015-11-24 | 2021-06-30 | 2022-09-27 | 2022-09-27 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 44.2341 | 17.5757 | متأخر | No
2100069801 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 1993500 | 99675 | 1993500 | 1993500 | 3350014288 | لا | 0 | 180909099070 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-09-20 | 2019-09-13 | 2020-09-21 | 2020-09-21 | 2019-09-13 |  |  |  | 41.1964 | 27.3744 | منجز | No
2100072575 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 3599272 | 179963.6 | 3375906.42 | 2261897 | 4030159820 | لا | 0 | 190909129022 | جاري | تكلفة العمل المنجز | 98.67 | 100 | 2019-05-19 | 2022-05-18 | 2022-01-19 | 2022-01-19 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0787 | 19.1281 | Failed | No
2100069016 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 960000 | 48000 | 364627.8 | 364627.8 | 3363008738 | لا | 0 | 200401127621 | مسحوب | الكميات التي تم تركيبها | 38 | 100 | 2019-06-16 | 2020-06-10 | 2022-07-03 | 2022-07-03 |  |  | ضعف كفاءة المقاول الفنية |  | 42.4135 | 27.8869 | مسحوب | No
2100107111 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 10074968.2 | 503748.41 | 3810564.44 | 3217252.9 | 4030052981 | لا | 0 | 200609152944 | مسحوب | التكلفة المفوترة | 44 | 100 | 2015-11-22 | 2017-11-11 | 2022-08-25 | 2022-08-25 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | مسحوب | No
2100069285 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 6751780 | 337589 | 3890752 | 2336504 | 4030159820 | لا | 0 |  | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 90 | 100 | 2018-11-01 | 2020-12-01 | 2022-07-01 | 2022-07-01 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 41.3696 | 20.0547 | Failed | No
2100067152 | أمانة / العاصمة المقدسة | أخرى | ذات اولوية متوسطة | 3810250 | 190512.5 | 314000 | 314000 | 4031058457 | لا | 0 |  | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 90.3 | 90.3 | 2015-03-01 | 2015-08-30 | 2016-12-11 | 2016-12-11 |  |  | ضعف كفاءة المقاول الفنية |  | 39.8548 | 21.3653 | Failed | No
2100071455 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 8702885.82 | 435144.291 | 3152165.18 | 3152165.18 | 1010089371 | لا | 0 |  | مسحوب | التكلفة المفوترة | 40 | 100 | 2014-10-19 | 2016-07-10 | 2020-11-18 | 2020-11-18 |  |  | ضعف كفاءة المقاول الفنية |  | 40.8817 | 23.5031 | مسحوب | No
2100074480 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 4853379.15 | 242668.9575 | 0 | 0 | 2050018834 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0.01 | 100 | 2014-03-30 | 2016-03-30 | 2016-08-30 | 2016-08-30 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 50.105 | 26.444 | مسحوب | No
2100115533 | المؤسسة العامة للحبوب | ترميم | ذات اولوية عالية وعاجلة | 4788025 | 239401.25 | 4788025 | 4788025 | 1010127334 | لا | 0 | 200601108257 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2020-11-05 | 2021-12-25 | 2021-12-25 | 2021-12-25 | 2021-12-25 |  |  |  | 43.9982 | 26.3593 | منجز | No
2100072634 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 745237.5 | 37261.875 | 745237.5 | 285710 | 5950027418 | لا | 0 | 181209477572 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 85 | 100 | 2019-07-13 | 2020-07-19 | 2020-07-19 | 2020-07-19 | 2020-07-19 |  | اخرى |  | 43.7178 | 17.8826 | منجز | No
2100074841 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 2989600 | 149480 | 2989600 | 2989600 | 5907024458 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-10-10 | 2020-09-18 | 2020-09-28 | 2020-09-28 | 2020-09-18 |  |  |  | 41.4622 | 20.0126 | منجز | No
2100072446 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 439771 | 21988.55 | 396971 | 396971 | 4601001792 | لا | 0 | 181109287828 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 90.27 | 90.27 | 2018-01-02 | 2019-12-22 | 2018-11-11 | 2018-11-11 | 2019-12-22 |  | ضعف كفاءة المقاول الفنية |  | 41.0536 | 19.5318 | منجز | No
2100076786 | أمانة / جازان | تشييد | ذات اولوية عالية | 3588980 | 179449 | 613610.19 | 613610.19 | 5950011723 | لا | 0 | 181101251307 | مسحوب | الكميات التي تم تركيبها | 60 | 100 | 2018-08-27 | 2019-02-23 | 2020-02-24 | 2020-02-24 |  |  | اخرى |  | 42.698 | 16.9769 | مسحوب | No
2100076904 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 7611855 | 380592.75 | 6392879.6 | 6137164.42 | 3555000709 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-11-04 | 2015-07-02 | 2021-09-01 | 2021-09-01 | 2015-07-02 |  | اخرى |  | 34.9451 | 29.2864 | منجز | No
2100074852 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 24433500 | 1221675 | 15421443.12 | 15421443.12 | 4031045075 | لا | 0 | 181201445038 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-07-01 | 2021-06-20 | 2021-10-31 | 2021-10-31 | 2021-06-20 |  |  |  | 40.4245 | 21.2413 | منجز | No
2100076646 | أمانة / العاصمة المقدسة | أخرى | ذات اولوية متوسطة | 12903850 | 645192.5 | 2840105.64 | 2840105.64 | 4031059785 | لا | 0 |  | مسحوب | التكلفة المفوترة | 26 | 26 | 2015-08-10 | 2018-08-10 | 2020-12-24 | 2020-12-24 |  |  | ضعف كفاءة المقاول الفنية |  | 39.8807 | 21.3786 | مسحوب | No
2100057960 | جامعة نجران | تشييد | ذات اولوية عالية | 27136671 | 1356833.55 | 7161543 | 7161543 | 1010019502 | لا | 0 | 181209533097 | ايقاف كلي | الكميات التي تم تركيبها | 58 | 100 | 2015-10-12 | 2016-08-02 | 2022-12-21 | 2022-12-21 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 44.2341 | 17.5757 | Failed | No
2100071094 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 877400 | 43870 | 148500 | 148500 | 5950022897 | لا | 0 | 220601025060 | مسحوب | اخرى | 17 | 70 | 2018-12-02 | 2019-09-24 | 2019-09-24 | 2019-09-24 |  |  | اخرى |  | 44.2476 | 17.5694 | مسحوب | No
2100077954 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | توريد وتركيب | ذات اولوية عالية وعاجلة | 6144215 | 307210.75 | 4664839 | 4664839 | 4030023890 | لا | 0 | 190509055270 | جاري | اخرى | 81.5 | 86.62 | 2017-10-23 | 2020-10-22 | 2023-10-22 | 2023-10-22 |  |  | اخرى |  | 38.1934 | 24.0126 | متأخر | No
2100080710 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 2551185 | 127559.25 | 1440720 | 144072 | 5950014853 | لا | 0 | 210601172735 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-10-04 | 2020-09-22 | 2020-09-22 | 2020-09-22 | 2020-09-22 |  | اخرى |  | 44.2318 | 17.5567 | منجز | No
2100079575 | هيئة المدن الصناعية ومناطق التقنية | تشييد | ذات اولوية عالية | 63840183 | 3192009.15 | 60796691 | 60796691 | 1010004739 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-12-30 | 2021-12-29 | 2022-03-08 | 2022-03-08 | 2021-12-29 |  | لا يوجد تأخير |  | 25.723 | 45.6896 | منجز | No
2100029400 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 10988970.3 | 549448.515 | 9830614.39 | 9830614.39 | 4031056138 | لا | 0 | 190409069590 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-08-06 | 2019-02-06 | 2020-02-02 | 2020-02-02 | 2019-02-06 |  |  |  | 40.4182 | 21.2511 | منجز | No
2100077825 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 2219904 | 110995.2 | 2145195.99 | 2145195.99 | 4032030986 | لا | 0 | 190701004885 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-01-29 | 2020-07-22 | 2020-07-22 | 2020-07-22 | 2020-07-22 |  |  |  | 40.831 | 20.7304 | منجز | No
2100000534 | جامعة نجران | تشييد | ذات اولوية عالية وعاجلة | 76219616.86 | 3810980.843 | 68520099 | 68520099 | 2051003225 | لا | 0 | 181109375202 | جاري | الكميات التي تم تركيبها | 97 | 89 | 2012-01-01 | 2015-08-29 | 2022-01-22 | 2022-01-22 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 47.1167 | 17.4861 | متأخر | No
2100077243 | أمانة / الجوف | تشييد | ذات اولوية عالية وعاجلة | 7831000 | 391550 | 7000125 | 7000125 | 3350013518 | لا | 0 | 191101096730 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-04-02 | 2020-03-20 | 2020-03-20 | 2020-03-20 | 2020-03-20 |  | ضعف كفاءة المقاول الفنية |  | 38.224 | 30.5013 | منجز | No
2100082504 | أمانة / جازان | تشييد | ذات اولوية عالية | 6965800 | 348290 | 2054506.18 | 2054506.18 | 5907007322 | لا | 0 | 181001161802 | جاري | الكميات التي تم تركيبها | 72 | 100 | 2019-01-03 | 2020-06-26 | 2022-03-30 | 2022-03-30 |  |  | ضعف كفاءة المقاول الفنية |  | 42.6158 | 16.924 | Failed | No
2100081001 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 3286605 | 164330.25 | 1906230.9 | 1906230.9 | 4650032626 | لا | 0 | 191101138640 | جاري | الكميات التي تم تركيبها | 34.24 | 100 | 2019-06-30 | 2020-08-03 | 2023-08-01 | 2023-08-01 |  |  | اخرى |  | 37.2552 | 25.0628 | Failed | No
2100002726 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 87105322.9 | 4355266.145 | 48269710 | 48269710 | 1010210667 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 95 | 100 | 2019-10-29 | 2021-01-21 | 2022-12-31 | 2022-12-31 |  |  | أوامر تغيير | أخرى |  |  | Failed | No
2100082950 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 21662288.58 | 1083114.429 | 17724859.4 | 17724859.4 | 4031041927 | لا | 0 | 4046343 | منجز – استلام ابتدائي | التكلفة المفوترة | 94.14 | 94.14 | 2014-05-30 | 2019-06-17 | 2019-06-17 | 2019-06-17 | 2019-06-17 |  |  |  | 39.8588 | 21.3849 | منجز | No
2100086052 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 3448669.7 | 172433.485 | 2110591 | 0 | 1010023890 | لا | 0 |  | ايقاف كلي | التكلفة المفوترة | 61 | 100 | 2010-05-03 | 2011-10-16 | 2021-12-15 | 2021-12-15 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | Failed | Yes
2100088896 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2617892 | 130894.6 | 1449025.77 | 1449025.77 | 3350014263 | لا | 0 |  | مسحوب | التكلفة المفوترة | 66 | 100 | 2010-03-13 | 2011-06-05 | 2020-11-18 | 2020-11-18 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | مسحوب | No
2100086413 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 4600000 | 230000 | 3029055 | 3029055 | 2511482400 | لا | 0 |  | مسحوب | التكلفة المفوترة | 60 | 100 | 2013-01-12 | 2014-03-08 | 2014-03-08 | 2014-03-08 |  |  | ضعف كفاءة المقاول الفنية |  | 45.975 | 28.4334 | مسحوب | No
2100086122 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 11380779.41 | 569038.9705 | 11380209.91 | 11380209.91 | 1010185409 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-12-25 | 2019-09-21 | 2020-01-19 | 2020-01-19 | 2019-09-21 | [5 empty] | منجز | No
2100084755 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 46292741 | 2314637.05 | 37181973 | 37181973 | 2050027608 | لا | 0 | 180909109659 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 99.7 | 100 | 2017-03-20 | 2019-03-20 | 2023-01-13 | 2023-01-13 |  |  | ضعف كفاءة المقاول الفنية |  | 38.2985 | 23.9852 | متأخر | No
2100089331 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 9364716.2 | 468235.81 | 2350089.43 | 0 | 1010196220 | لا | 0 | 190509026803 | مسحوب | التكلفة المفوترة | 25 | 100 | 2012-12-31 | 2014-09-22 | 2022-12-23 | 2022-12-23 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | مسحوب | Yes
2100089375 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 8675066.98 | 433753.349 | 1632755.88 | 0 | 4030052981 | لا | 0 | 190709098255 | جاري | التكلفة المفوترة | 20 | 100 | 2018-08-28 | 2020-08-17 | 2022-08-10 | 2022-08-10 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | Failed | Yes
2100085002 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية متوسطة | 27279079.75 | 1363953.9875 | 27279079.75 | 27279079.75 | 4030140033 | لا | 0 | 190409020915 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2017-01-09 | 2018-12-18 | 2021-01-01 | 2021-01-01 | 2018-12-18 |  |  |  | 50.2214 | 26.2396 | منجز | No
2100085164 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية متوسطة | 269964.55 | 13498.2275 | 264942.62 | 264942.62 | 2050069840 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-11-20 | 2019-01-19 | 2018-04-01 | 2018-04-01 | 2019-01-19 |  | لا يوجد تأخير |  | 49.7201 | 25.4257 | منجز | No
2100092164 | أمانة / جازان | تشييد | ذات اولوية عالية | 5487700 | 274385 | 0 | 0 | 5855047635 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 0 | 100 | 2015-09-17 | 2016-09-11 | 2019-03-01 | 2019-03-01 |  |  | تأخرصرف المستحقات المالية |  | 42.5778 | 16.9425 | مسحوب | No
2100093634 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 2919835 | 145991.75 | 0 | 0 | 5900012811 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 0 | 100 | 2011-12-09 | 2012-12-02 | 2019-02-19 | 2019-02-19 |  |  | اخرى |  | 42.6004 | 16.9337 | مسحوب | No
2100035814 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 1499999 | 74999.95 | 167581.32 | 107925.71 | 5800010527 | لا | 0 | 181109340502 | مسحوب | تكلفة العمل المنجز | 14 | 100 | 2018-10-07 | 2020-09-14 | 2020-09-14 | 2020-09-14 |  |  | ضعف كفاءة المقاول الفنية |  | 40.8622 | 20.4212 | مسحوب | No
2100034215 | أمانة / حفر الباطن | تشييد | ذات اولوية متوسطة | 1296700 | 64835 | 1158060 | 1158060 | 2511006133 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-10-28 | 2019-10-21 | 2019-11-21 | 2019-11-21 | 2019-10-21 |  |  |  | 45.6646 | 28.1121 | منجز | No
2100091976 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 13051272.27 | 652563.6135 | 13051271.44 | 13051271.44 | 4030006066 | لا | 0 | 181009124802 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-04-20 | 2016-10-11 | 2021-01-01 | 2021-01-01 | 2016-10-11 |  | ضعف كفاءة المقاول الفنية |  | 42.8419 | 21.2585 | منجز | No
2100093041 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 679200 | 33960 | 679200 | 679200 | 3556000295 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-12-13 | 2016-12-08 | 2018-12-04 | 2018-12-04 | 2016-12-08 |  | اخرى |  | 35.0202 | 28.4788 | منجز | No
2100092503 | أمانة / جازان | تشييد | ذات اولوية منخفضة | 11360721.9 | 568036.095 | 9119272 | 9119272 | 1010214056 | لا | 0 | 181109373253 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 100 | 2015-01-31 | 2016-01-26 | 2021-04-29 | 2021-04-29 | 2016-01-26 |  | ضعف كفاءة المقاول الفنية |  | 42.5239 | 16.9629 | منجز | No
2100097226 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1598497 | 79924.85 | 740717.63 | 740717.63 | 2511482400 | لا | 0 |  | مسحوب | التكلفة المفوترة | 60 | 100 | 2013-06-01 | 2014-04-27 | 2014-04-29 | 2014-04-29 |  |  | ضعف كفاءة المقاول الفنية |  | 45.975 | 28.4334 | مسحوب | No
2100094581 | صندوق تنمية الموارد البشرية | تشييد | ذات اولوية عالية | 32223249.36 | 1611162.468 | 28283710.68 | 28283710.68 | 5950000083 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-04-22 | 2017-04-11 | 2021-11-30 | 2021-11-30 | 2017-04-11 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 44.2336 | 17.5584 | منجز | No
2100061666 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 12299654.5 | 614982.725 | 0.01 | 0.01 | 1010178798 | لا | 0 | 190209014193 | مسحوب | التكلفة المفوترة | 75 | 100 | 2013-05-10 | 2015-04-30 | 2021-12-16 | 2021-12-16 |  |  | ضعف كفاءة المقاول الفنية |  | 44.2341 | 17.5757 | مسحوب | No
2100094032 | أمانة / الجوف | تشييد | ذات اولوية عالية | 2790920 | 139546 | 2790920 | 2790920 | 3452005717 | لا | 0 | 190309024026 | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2015-09-12 | 2018-12-03 | 2018-12-12 | 2018-12-12 | 2018-12-03 |  | تأخرصرف المستحقات المالية |  | 37.972 | 30.7222 | منجز | No
2100096913 | وزارة التعليم | تشييد | ذات اولوية عالية | 10688323.12 | 534416.156 | 2865442.06 | 2865442.06 | 2031040463 | لا | 0 |  | مسحوب | التكلفة المفوترة | 41 | 100 | 2013-03-19 | 2015-03-09 | 2016-12-03 | 2016-12-03 |  |  | ضعف كفاءة المقاول الفنية |  | 45.975 | 28.4334 | مسحوب | No
2100099142 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 16525212.88 | 826260.644 | 3595557.87 | 3595557.87 | 1010046644 | لا | 0 |  | مسحوب | التكلفة المفوترة | 25 | 100 | 2015-06-02 | 2017-09-18 | 2017-09-18 | 2017-09-18 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5604 | 25.3897 | مسحوب | No
2100098906 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2426528.8 | 121326.44 | 886771.57 | 593112.5 | 5800007456 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2017-10-15 | 2018-10-10 | 2023-05-10 | 2023-05-10 | 2018-10-10 |  | ضعف كفاءة المقاول الفنية |  | 41.4779 | 20.0185 | منجز | No
2100105394 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 4777421 | 238871.05 | 0.01 | 0.01 | 5950010876 | لا | 0 | 190909199883 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2017-07-13 | 2019-05-04 | 2021-07-08 | 2021-07-08 | 2019-05-04 |  | ضعف كفاءة المقاول الفنية |  | 44.2341 | 17.5757 | منجز | No
2100087791 | جامعة نجران | تشييد | ذات اولوية عالية | 20000000 | 1000000 | 4312511 | 4312511 | 2066001761 | لا | 0 | 181209513090 | جاري | الكميات التي تم تركيبها | 74 | 100 | 2015-02-11 | 2018-11-25 | 2022-06-22 | 2022-06-22 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 44.2341 | 17.5757 | Failed | No
2100106245 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية وعاجلة | 24288579 | 1214428.95 | 15836190.43 | 15836190.43 | 4030163543 | لا | 0 | 180709033690 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 88.51 | 95.51 | 2014-07-20 | 2017-06-18 | 2020-03-01 | 2020-03-01 | 2017-06-18 |  | لا يوجد تأخير |  | 38.7942 | 23.7693 | منجز | No
2100104974 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 22910588.65 | 1145529.4325 | 5827707.39 | 5827707.39 | 1011008214 | لا | 0 |  | مسحوب | التكلفة المفوترة | 58 | 100 | 2014-06-04 | 2016-05-25 | 2023-12-15 | 2023-12-15 |  |  | ضعف كفاءة المقاول الفنية |  | 38.0284 | 24.0924 | مسحوب | No
2100102745 | وزارة الموارد البشرية والتنمية الإجتماعية | إشراف | ذات اولوية منخفضة | 880916.6 | 44045.83 | 935000 | 935000 | 1010323842 | لا | 0 | 190501086671 | مسحوب | الكميات التي تم تركيبها | 97 | 100 | 2013-03-21 | 2014-11-02 | 2022-01-20 | 2022-01-20 |  |  | ضعف كفاءة المقاول الفنية |  | 40.1989 | 29.959 | مسحوب | No
2100104661 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 7529493.71 | 376474.6855 | 4091107.96 | 4091107.96 | 1010183010 | لا | 0 |  | مسحوب | التكلفة المفوترة | 71 | 100 | 2015-02-04 | 2017-01-25 | 2023-01-15 | 2023-01-15 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0165 | 30.9619 | مسحوب | No
2100108894 | وزارة التعليم | تشييد | ذات اولوية عالية | 4740925.91 | 237046.2955 | 4266885.66 | 0 | 1010060469 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2018-01-15 | 2019-07-09 | 2020-06-19 | 2020-06-19 | 2019-07-09 |  | ضعف كفاءة المقاول الفنية |  | 42.6509 | 17.1567 | منجز | Yes
2100107122 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 10817184.96 | 540859.248 | 3853204.95 | 0 | 1010196220 | لا | 0 | 190309008079 | مسحوب | التكلفة المفوترة | 34 | 100 | 2012-12-31 | 2014-12-21 | 2022-08-12 | 2022-08-12 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | مسحوب | Yes
2100103972 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 16769687.56 | 838484.378 | 4858795.61 | 4858795.61 | 1010223860 | لا | 0 | 190209008352 | مسحوب | التكلفة المفوترة | 50 | 100 | 2013-01-08 | 2014-12-27 | 2023-05-10 | 2023-05-10 |  |  | ضعف كفاءة المقاول الفنية |  | 42.4987 | 18.2178 | مسحوب | No
2100082762 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 5982510 | 299125.5 | 333283.5 | 333283.5 | 5900012984 | لا | 0 | 180909110382 | مسحوب | تكلفة العمل المنجز | 7 | 100 | 2014-11-15 | 2016-10-24 | 2019-03-25 | 2019-03-25 |  |  | اخرى |  | 42.5947 | 16.9329 | مسحوب | No
2100108146 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 867575 | 43378.75 | 700400 | 0 | 2511012081 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-08-24 | 2015-04-17 | 2019-04-18 | 2019-04-18 | 2015-04-17 |  |  |  | 47.5111 | 27.0163 | منجز | Yes
2100093660 | وزارة الشـؤون الاسلامية والدعوة والارشاد | تشييد | ذات اولوية عالية | 504515 | 25225.75 | 0 | 0 | 3400013453 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 40 | 100 | 2018-06-04 | 2019-08-20 | 2019-08-20 | 2019-08-20 |  |  | ضعف كفاءة المقاول الفنية |  | 37.3638 | 31.3261 | Failed | No
2100044892 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 442850 | 22142.5 | 0 | 0 | 2050044904 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 0.01 | 100 | 2015-10-04 | 2016-04-01 | 2022-01-01 | 2022-01-01 |  |  | تأخرصرف المستحقات المالية |  | 40.8294 | 20.7272 | مسحوب | No
2100109141 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2651274.51 | 132563.7255 | 212892.69 | 212892.69 | 4030052981 | لا | 0 | 190409104694 | مسحوب | التكلفة المفوترة | 20 | 100 | 2018-10-29 | 2019-10-24 | 2022-02-10 | 2022-02-10 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | مسحوب | No
2100037225 | وزارة الشـؤون الاسلامية والدعوة والارشاد | تشييد | ذات اولوية عالية | 698784 | 34939.2 | 213100 | 0 | 3350027234 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 30 | 40 | 2018-07-31 | 2019-07-31 | 2021-02-25 | 2021-02-25 | 2019-07-31 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.7219 | 27.5086 | منجز | Yes
2100010614 | وزارة الشـؤون الاسلامية والدعوة والارشاد | تشييد | ذات اولوية عالية | 488610 | 24430.5 | 116848 | 0 | 3350013522 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-08-01 | 2019-12-01 | 2021-02-25 | 2021-02-25 | 2019-12-01 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.1708 | 27.9563 | منجز | Yes
2100095992 | المؤسسة العامة للتقاعد | تشييد | ذات اولوية عالية | 122867100 | 6143355 | 92346525 | 92346525 | 1010396723 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-06-20 | 2021-07-31 | 2021-11-30 | 2021-11-30 | 2021-07-31 |  | اخرى |  | 39.1264 | 21.7255 | منجز | No
2100007350 | وزارة الشـؤون الاسلامية والدعوة والارشاد | تشييد | ذات اولوية عالية | 531900 | 26595 | 0 | 0 | 1234567890 | لا | 0 | 181109352412 | ايقاف كلي | الكميات التي تم تركيبها | 70 | 100 | 2016-08-04 | 2017-08-03 | 2020-02-28 | 2020-02-28 |  |  | ضعف كفاءة المقاول الفنية |  | 39.5746 | 24.451 | Failed | No
2100107225 | وزارة الدفاع / الإدارة الهندسية والاشغال بالخدمات الصحية | تشييد | ذات اولوية متوسطة | 6653010 | 332650.5 | 5254761.11 | 5254761.11 | 5950012968 | لا | 0 | 181009131182 | جاري | الكميات التي تم تركيبها | 71 | 93 | 2015-03-05 | 2017-02-10 | 2021-12-31 | 2021-12-31 |  |  | عدم وجود مبالغ في البنود تغطي الأعمال المرصودة |  | 44.23 | 17.4579 | متأخر | No
2100107520 | وزارة الشـؤون الاسلامية والدعوة والارشاد | تشييد | ذات اولوية عالية وعاجلة | 448083 | 22404.15 | 103095 | 0 | 3350027234 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 40 | 45 | 2017-08-14 | 2018-08-14 | 2021-02-25 | 2021-02-25 | 2018-08-14 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 40.3289 | 27.6387 | منجز | Yes
2100106341 | جامعة نجران | تشييد | ذات اولوية عالية وعاجلة | 80000000 | 4000000 | 41367829 | 41367829 | 2066001761 | لا | 0 | 181209496012 | جاري | الكميات التي تم تركيبها | 58 | 100 | 2016-11-24 | 2017-10-21 | 2023-01-04 | 2023-01-04 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 44.2341 | 17.5757 | Failed | No
2100106901 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البرية | تشييد | ذات اولوية متوسطة | 4160000.08 | 208000.004 | 4160000.08 | 3399149.56 | 5855064585 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-02-19 | 2021-07-17 | 2022-08-31 | 2022-08-31 | 2021-07-17 |  | اخرى |  | 42.76 | 18.2576 | منجز | No
2100103132 | جامعة حفر الباطن | تشييد | ذات اولوية عالية وعاجلة | 124040341 | 6202017.05 | 113635241 | 113635241 | 2055002293 | لا | 0 | 190309099935 | مسحوب | تكلفة العمل المنجز | 90 | 90 | 2012-06-16 | 2014-12-16 | 2022-07-31 | 2022-07-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 48.479 | 27.4918 | مسحوب | No
2100095760 | وزارة المالية | إشراف | ذات اولوية متوسطة | 3162000 | 158100 | 3162000 | 3162000 | 4030047446 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 75 | 100 | 2014-09-08 | 2016-02-21 | 2021-04-01 | 2021-04-01 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.5062 | 18.2099 | مسحوب | No
2100003205 | جامعة نجران | تشييد | ذات اولوية عالية وعاجلة | 19988169 | 999408.45 | 14615288 | 14615288 | 2066001761 | لا | 0 | 181209509728 | جاري | الكميات التي تم تركيبها | 98 | 100 | 2014-12-23 | 2016-09-03 | 2022-02-09 | 2022-02-09 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 44.2341 | 17.5757 | Failed | No
2100096552 | وزارة المالية | تشييد | ذات اولوية متوسطة | 33835259.89 | 1691762.9945 | 14866216.69 | 14866216.69 | 1010197201 | لا | 0 | 180809047889 | مسحوب | تكلفة العمل المنجز | 80 | 80 | 2015-11-08 | 2017-11-08 | 2023-11-30 | 2023-11-30 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.5727 | 24.5171 | مسحوب | No
2100093693 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 8272158 | 413607.9 | 7036531.34 | 7036531.34 | 5950003335 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 96 | 100 | 2014-12-24 | 2016-06-07 | 2021-04-09 | 2021-04-09 | 2016-06-07 |  |  |  | 44.2325 | 17.5529 | منجز | No
2100078584 | وزارة التجارة | دراسة الجدوى | ذات اولوية عالية | 2491768 | 124588.4 | 2001653.8 | 2001653.8 | 1010348048 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 75 | 80 | 2018-11-07 | 2020-11-06 | 2022-06-06 | 2022-06-06 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  |  |  | خدمات عامة | No
2100034123 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 1871000 | 93550 | 1964550 | 1670025 | 1131024292 | لا | 0 | 210309098213 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2021-10-18 | 2022-10-17 | 2021-06-29 | 2021-06-29 | 2022-10-17 |  | ضعف كفاءة المقاول الفنية |  | 40.7345 | 19.9175 | منجز | No
2100004815 | وزارة الشـؤون الاسلامية والدعوة والارشاد | تشييد | ذات اولوية عالية | 1306233 | 65311.65 | 858451 | 0 | 3357001765 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 99 | 60 | 2018-07-25 | 2019-07-25 | 2019-07-25 | 2019-07-25 |  |  | لا يوجد تأخير |  | 41.7206 | 27.5004 | Failed | Yes
2100005681 | وزارة الرياضة | تشييد | ذات اولوية عالية | 58182416.36 | 2909120.818 | 35226410 | 35226410 | 1010195208 | نعم | 607839.81 | 180909077891 | مسحوب | الكميات التي تم تركيبها | 82 | 100 | 2011-10-15 | 2015-03-17 | 2021-09-01 | 2021-09-01 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | مسحوب | No
2100178430 | وزارة الثقافة | تشييد | ذات اولوية عالية | 5717688.76 | 285884.438 | 2522940.63 | 2522940.63 | 4030166491 | لا | 0 | 201109022412 | ايقاف جزئي | منهجية القيمة المكتسبة | 65 | 100 | 2018-12-27 | 2020-01-23 | 2022-05-01 | 2022-05-01 |  |  |  |  | 42.6478 | 17.1458 | Failed | No
2100078772 | أمانة / حائل | دراسة الجدوى | ذات اولوية متوسطة | 439635 | 21981.75 | 439635 | 439635 | 3350043756 | لا | 0 | 190201016734 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-01-05 | 2020-04-06 | 2021-08-24 | 2021-08-24 | 2020-04-06 |  | اخرى |  | 42.9875 | 27.4738 | منجز | No
2100189571 | الهيئة العامة للزكاة والدخل | تشييد | ذات اولوية عالية وعاجلة | 16937492 | 846874.6 | 16937492 | 16937492 | 5850021111 | لا | 0 |  | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2014-01-02 | 2021-03-31 | 2021-03-31 | 2021-03-31 |  | 2021-03-31 |  |  | 42.5814 | 18.2309 | منجز | No
2100100273 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية عالية | 24261719.42 | 1213085.971 | 20302232.33 | 20302232.33 | 1010181437 | لا | 0 | 190409022477 | جاري | تكلفة العمل المنجز | 95 | 100 | 2015-07-29 | 2017-07-28 | 2017-07-06 | 2017-07-06 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 44.7746 | 20.4591 | Failed | No
2100077195 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 428716655.02 | 21435832.751 | 306035106.28 | 306035106.28 | 1010224378 | لا | 0 | 180809043291 | جاري | منهجية القيمة المكتسبة | 72 | 98 | 2018-04-09 | 2021-10-04 | 2024-03-06 | 2024-03-06 |  |  | لا يوجد تأخير |  | 49.6626 | 27.0037 | Failed | No
2100030962 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 899690 | 44984.5 | 850206 | 299424.62 | 5950008636 | لا | 0 | 220601025060 | منجز – استلام ابتدائي | اخرى | 96 | 100 | 2018-04-29 | 2019-10-11 | 2022-09-11 | 2022-09-11 | 2019-10-11 |  |  |  | 44.2345 | 17.5583 | منجز | No
2100013786 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 2769564 | 138478.2 | 2545093 | 2545093 | 5806008614 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 92 | 100 | 2018-09-27 | 2020-09-05 | 2021-03-31 | 2021-03-31 | 2020-09-05 |  | تأخرصرف المستحقات المالية |  | 41.4694 | 20.0104 | منجز | No
2100004804 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 75560853 | 3778042.65 | 71545213.2 | 71468374.62 | 4031046036 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-12-23 | 2020-12-22 | 2020-12-22 | 2020-12-22 | 2020-12-22 |  | أوامر تغيير | أخرى |  |  | منجز | No
2100023520 | وزارة التجارة | تشييد | ذات اولوية عالية وعاجلة | 11000000 | 550000 | 8389491 | 8389491 | 4030144266 | لا | 0 | 180701024341 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-10-03 | 2021-07-10 | 2021-08-15 | 2021-08-15 |  | 2021-07-10 | اخرى |  | 44.0345 | 26.0973 | منجز | No
2100096924 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 5758209.7 | 287910.485 | 3566711.69 | 3566711.69 | 3450006687 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2006-08-31 | 2008-03-30 | 2022-02-15 | 2022-02-15 | 2008-03-30 |  | ضعف كفاءة المقاول الفنية |  | 41.0165 | 30.9619 | منجز | No
2100103821 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 20933321 | 1046666.05 | 3207618.4 | 2593593.33 | 1132002570 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 15 | 100 | 2013-01-09 | 2014-12-29 | 2021-01-04 | 2021-01-04 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0165 | 30.9619 | مسحوب | No
2100097661 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | تشييد | ذات اولوية عالية | 26187166.82 | 1309358.341 | 23115056.1 | 10360083.36 | 1010009592 | لا | 0 | 180709033857 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-10-17 | 2021-01-17 | 2023-02-28 | 2023-02-28 |  |  | لا يوجد تأخير |  | 42.7302 | 18.3003 | Failed | No
2100077755 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 31984144 | 1599207.2 | 6387276.97 | 6387276.97 | 5950009685 | لا | 0 | 221009014884 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 97 | 100 | 2019-02-03 | 2020-07-18 | 2022-09-11 | 2022-09-11 | 2020-07-18 |  | ضعف كفاءة المقاول الفنية |  | 44.0528 | 17.6079 | منجز | No
2100057853 | هيئة المدن الصناعية ومناطق التقنية | تشييد | ذات اولوية عالية | 102900000 | 5145000 | 61982570 | 61982570 | 1010127329 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 74 | 78 | 2019-05-06 | 2021-05-05 | 2022-03-22 | 2022-03-22 |  |  | لا يوجد تأخير |  | 31.7107 | 38.9753 | منتظم | No
2100043116 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2267486.1 | 113374.305 | 817766.98 | 596146.5 | 3450005705 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-07-25 | 2016-07-19 | 2021-03-25 | 2021-03-25 | 2016-07-19 |  | ضعف كفاءة المقاول الفنية |  | 41.0165 | 30.9619 | منجز | No
2100073231 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2152149 | 107607.45 | 1638519.54 | 1638519.54 | 3450005705 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-10-25 | 2016-10-19 | 2021-05-02 | 2021-05-02 | 2016-10-19 |  | ضعف كفاءة المقاول الفنية |  | 41.0165 | 30.9619 | منجز | No
2100022864 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | تشييد | ذات اولوية عالية وعاجلة | 195751285.76 | 9787564.288 | 136985573.7 | 136985573.7 | 1010068901 | لا | 0 | 181009178823 | مسحوب | تكلفة العمل المنجز | 66.7 | 100 | 2013-06-22 | 2015-02-06 | 2022-12-31 | 2022-12-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.5429 | 16.8808 | مسحوب | No
2100043083 | هيئة المدن الصناعية ومناطق التقنية | تشييد | ذات اولوية عالية | 14828812 | 741440.6 | 9490703 | 9490703 | 4030087384 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-12-11 | 2021-06-03 | 2022-02-28 | 2022-02-28 | 2021-06-03 |  | اخرى |  | 24.164 | 38.0546 | منجز | No
2100009015 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | تشييد | ذات اولوية متوسطة | 43606439 | 2180321.95 | 14264351.1 | 14264351.1 | 1010172403 | لا | 0 | 181109318697 | مسحوب | تكلفة العمل المنجز | 37 | 100 | 2018-01-31 | 2021-04-08 | 2023-12-30 | 2023-12-30 |  |  | ضعف كفاءة المقاول الفنية |  | 50.101 | 26.4494 | مسحوب | No
2100010463 | هيئة المدن الصناعية ومناطق التقنية | تشييد | ذات اولوية عالية | 43829885 | 2191494.25 | 33395985 | 25668172 | 1010090181 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 98 | 98 | 2019-12-11 | 2021-06-10 | 2023-06-11 | 2023-06-11 |  |  | لا يوجد تأخير |  | 31.7107 | 38.9753 | منتظم | No
2100025852 | صندوق تنمية الموارد البشرية | تشييد | ذات اولوية عالية | 28067010.08 | 1403350.504 | 18297459.3 | 18297459.3 | 5855010714 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 81.38 | 100 | 2016-02-01 | 2018-07-20 | 2022-06-30 | 2022-06-30 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.5672 | 16.8776 | مسحوب | No
2100002063 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 3672746.3 | 183637.315 | 3856383.61 | 3511211.38 | 2050004063 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-08-04 | 2020-01-31 | 2020-01-31 | 2020-01-31 | 2020-01-31 | [5 empty] | منجز | No
2100074082 | وزارة التجارة | دراسة الجدوى | ذات اولوية عالية | 3039110.03 | 151955.5015 | 3000139 | 3000139 | 1010348048 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-03-27 | 2020-03-26 | 2020-12-08 | 2020-12-08 |  | 2020-03-26 | أوامر تغيير |  |  |  | منجز | No
2100090823 | وزارة التجارة | تشييد | ذات اولوية متوسطة | 417716 | 20885.8 | 417716 | 417716 | 1010247178 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2020-07-27 | 2020-12-24 | 2021-01-05 | 2021-01-05 |  | 2020-12-24 | اخرى |  | 41.0128 | 30.9794 | منجز | No
2100106304 | شركة المياه الوطنية / منطقة الحدود الشمالية | تشييد | ذات اولوية عالية | 14294000 | 714700 | 12095488.29 | 12095488.29 | 5850022870 | لا | 0 | 190509066619 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-01-29 | 2021-01-07 | 2021-03-15 | 2021-03-15 | 2021-01-07 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 40.9976 | 30.9656 | منجز | No
2100087640 | وزارة التجارة | تشييد | ذات اولوية عالية وعاجلة | 8664056 | 433202.8 | 7311262 | 7311262 | 1010238171 | لا | 0 | 180909074816 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-03-27 | 2020-03-26 | 2020-12-06 | 2020-12-06 |  | 2020-03-26 | أوامر تغيير |  | 41.0128 | 30.9794 | منجز | No
2100059813 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2267486 | 113374.3 | 956738.44 | 523876.5 | 3450005705 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-07-25 | 2016-07-19 | 2019-12-30 | 2019-12-30 | 2016-07-19 |  | ضعف كفاءة المقاول الفنية |  | 41.0165 | 30.9619 | منجز | No
2100104263 | جامعة الحدود الشمالية | تشييد | ذات اولوية متوسطة | 139899696.54 | 6994984.827 | 71558350 | 71558350 | 1010102314 | لا | 0 | 180709018313 | ايقاف كلي | تكلفة العمل المنجز | 61 | 85 | 2010-07-13 | 2012-02-15 | 2024-12-30 | 2024-12-30 |  |  | تغيرات في نطاق المشروع |  | 43.5207 | 29.6323 | Failed | No
2100058262 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2266570 | 113328.5 | 0 | 0 | 1010320472 | لا | 0 |  | مسحوب | التكلفة المفوترة | 0.5 | 100 | 2012-08-03 | 2013-07-23 | 2014-07-28 | 2014-07-28 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0165 | 30.9619 | مسحوب | No
2100001492 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1392180 | 69609 | 0 | 0 | 1010263720 | لا | 0 |  | مسحوب | التكلفة المفوترة | 6 | 100 | 2014-03-02 | 2014-08-28 | 2022-06-30 | 2022-06-30 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0165 | 30.9619 | مسحوب | No
2100079225 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2484000 | 124200 | 692000 | 692000 | 3450007134 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 45 | 100 | 2012-11-27 | 2014-03-28 | 2021-01-04 | 2021-01-04 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0165 | 30.9619 | مسحوب | No
2100027064 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2267486.1 | 113374.305 | 1857202.2 | 1857202.2 | 3450005705 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-11-08 | 2016-11-02 | 2019-11-19 | 2019-11-19 | 2016-11-02 |  | ضعف كفاءة المقاول الفنية |  | 41.0165 | 30.9619 | منجز | No
2100009516 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 15361424 | 768071.2 | 7068290.98 | 7068290.98 | 2511008693 | لا | 0 |  | مسحوب | التكلفة المفوترة | 74 | 100 | 2011-10-04 | 2013-09-23 | 2022-12-30 | 2022-12-30 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0165 | 30.9619 | مسحوب | No
2100095981 | أمانة / الحدود الشمالية | ادارة مشاريع | ذات اولوية عالية وعاجلة | 25986707.14 | 1299335.357 | 25598089.29 | 15434888 | 1010434042 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-09-15 | 2021-09-04 | 2022-03-15 | 2022-03-15 | 2021-09-04 |  | اخرى |  |  |  | منجز | No
2100079704 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2495744 | 124787.2 | 959240 | 959240 | 1010263720 | لا | 0 |  | جاري | التكلفة المفوترة | 65 | 100 | 2012-07-07 | 2013-07-02 | 2022-07-15 | 2022-07-15 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0165 | 30.9619 | Failed | No
2100038625 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2366829 | 118341.45 | 1440384.04 | 1440384.04 | 3450005705 | لا | 0 |  | جاري | التكلفة المفوترة | 20 | 100 | 2016-02-01 | 2017-01-26 | 2022-05-11 | 2022-05-11 |  |  | أوامر تغيير |  | 41.0165 | 30.9619 | Failed | No
2100009752 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 3981173.63 | 199058.6815 | 2619067.33 | 2141249.97 | 3450006578 | لا | 0 |  | جاري | التكلفة المفوترة | 95 | 100 | 2017-09-20 | 2019-03-14 | 2022-06-29 | 2022-06-29 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0165 | 30.9619 | Failed | No
2100009100 | جامعة الحدود الشمالية | تشييد | ذات اولوية عالية | 96394881 | 4819744.05 | 17213222.75 | 9224355.83 | 1010136405 | لا | 0 | 180701015317 | جاري | تكلفة العمل المنجز | 9 | 10 | 2019-01-10 | 2020-12-29 | 2024-03-19 | 2024-03-19 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0346 | 30.951 | منتظم | No
2100009111 | جامعة الحدود الشمالية | تشييد | ذات اولوية عالية | 130873943 | 6543697.15 | 44061412.137 | 42221604.457 | 1010069654 | لا | 0 | 180409003901 | ايقاف كلي | تكلفة العمل المنجز | 36 | 66 | 2015-10-12 | 2019-03-25 | 2025-12-18 | 2025-12-18 |  |  | تأخرصرف المستحقات المالية |  | 43.5207 | 29.6323 | Failed | No
2100104672 | جامعة الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 144727465.18 | 7236373.259 | 91469294.52 | 91469294.52 | 1010230789 | لا | 0 | 180409004174 | جاري | تكلفة العمل المنجز | 75 | 78 | 2015-06-01 | 2018-05-16 | 2024-04-01 | 2024-04-01 |  |  | تأخرصرف المستحقات المالية |  | 41.0346 | 30.951 | منتظم | No
2100058063 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات الجوية | تشييد | ذات اولوية عالية | 9962857 | 498142.85 | 9962857 | 9962857 | 1010066115 | لا | 0 | 180909067395 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2017-05-25 | 2017-11-16 | 2022-06-30 | 2022-06-30 | 2017-11-16 |  | تصاريح أعمال التنفيذ |  | 37.9455 | 26.58 | منجز | No
2100032922 | وزارة الدفاع / الإدارة الهندسية والاشغال بقوات الدفاع الجوي | تشييد | ذات اولوية متوسطة | 23942715.3 | 1197135.765 | 23942715.3 | 19258801.91 | 4030215955 | لا | 0 | 190901180820 | جاري | الكميات التي تم تركيبها | 68 | 90 | 2020-01-20 | 2022-07-08 | 2022-09-21 | 2022-09-21 |  |  | أوامر سامية |  | 50.1129 | 26.4157 | Failed | No
2100105210 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية وعاجلة | 492275430 | 24613771.5 | 207207477.74 | 207207477.74 | 2050001536 | لا | 0 | 180201000371 | جاري | منهجية القيمة المكتسبة | 64.66 | 70.94 | 2018-08-02 | 2023-06-09 | 2023-09-13 | 2023-09-13 |  |  | اخرى |  | 43.9553 | 26.3508 | متأخر | No
2100002866 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1496892.1 | 74844.605 | 1358963 | 1358963 | 1132006100 | لا | 0 |  | مسحوب | التكلفة المفوترة | 90 | 100 | 2013-05-06 | 2014-05-02 | 2021-06-01 | 2021-06-01 |  |  | ضعف كفاءة المقاول الفنية |  | 43.9875 | 26.0873 | مسحوب | No
2100098696 | جامعة القصيم | تشييد | ذات اولوية عالية وعاجلة | 156950038.7 | 7847501.935 | 107843182.17 | 107843182.17 | 1010009593 | لا | 0 | 200209129993 | جاري | تكلفة العمل المنجز | 76 | 76 | 2019-06-24 | 2021-07-13 | 2023-05-04 | 2023-05-04 |  |  |  |  | 43.7655 | 26.3553 | منتظم | No
2100012854 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 3796180 | 189809 | 3084663 | 3084663 | 1010341771 | لا | 0 | 191001289641 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 90 | 2019-09-15 | 2020-09-09 | 2022-05-16 | 2022-05-16 | 2020-09-09 |  |  |  | 42.8383 | 21.2525 | منجز | No
2100060653 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 29189092.9 | 1459454.645 | 29023139.88 | 25246296.8 | 1010026934 | نعم | 11758191.97 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 80.56 | 100 | 2019-05-23 | 2020-11-23 | 2021-02-03 | 2021-02-03 |  | 2020-11-23 | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100106665 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات الجوية | تشييد | ذات اولوية متوسطة | 15136094 | 756804.7 | 1436711 | 1436711 | 1010214056 | لا | 0 | 180809065570 | ايقاف جزئي | الكميات التي تم تركيبها | 36 | 100 | 2018-06-27 | 2019-07-17 | 2022-12-31 | 2022-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 45.989 | 28.3767 | Failed | No
2100069215 | أمانة / القصيم | تشييد | ذات اولوية متوسطة | 5370000 | 268500 | 3987678.21 | 3987678.21 | 1134000308 | لا | 0 | 190401081949 | جاري | تكلفة العمل المنجز | 98 | 98 | 2019-06-17 | 2021-06-04 | 2023-01-31 | 2023-01-31 |  |  | تأخرصرف المستحقات المالية |  |  |  | منتظم | No
2100007335 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 3798950.44 | 189947.522 | 1463102 | 1463102 | 4031053163 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 58 | 100 | 2013-11-14 | 2015-02-14 | 2020-11-22 | 2020-11-22 |  |  | ضعف كفاءة المقاول الفنية |  | 43.9544 | 26.3504 | مسحوب | No
2100103810 | وزارة التعليم | تشييد | ذات اولوية عالية | 11402079 | 570103.95 | 8542290 | 8542290 | 1131012642 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2012-03-30 | 2014-03-20 | 2020-12-31 | 2020-12-31 | 2014-03-20 |  |  |  | 43.9544 | 26.3504 | منجز | No
2100031953 | وزارة الداخلية / مديرية الأمن العام | تشييد | ذات اولوية متوسطة | 1630000 | 81500 | 1251232.28 | 1251232.28 | 1010134168 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-08-26 | 2022-02-25 | 2021-01-06 | 2021-01-06 | 2022-02-25 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 49.4101 | 26.3233 | منجز | No
2100076193 | أمانة / الباحة | تشييد | ذات اولوية عالية | 1732972 | 86648.6 | 317400.66 | 0 | 1010428119 | لا | 0 | 220209110205 | جاري | الكميات التي تم تركيبها | 37 | 63 | 2019-12-11 | 2021-05-26 | 2023-03-14 | 2023-03-14 |  |  | سوء التخطيط الاولي للمشروع | تم تمديد الجدول الزمني | 41.068 | 20.1883 | Failed | Yes
2100077696 | وزارة الداخلية / مديرية الأمن العام | تشييد | ذات اولوية متوسطة | 2499945 | 124997.25 | 2281511.4 | 2281511.4 | 1010243700 | لا | 0 |  | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 95 | 100 | 2020-01-18 | 2021-01-18 | 2021-04-18 | 2021-04-18 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 41.2697 | 22.0794 | Failed | No
2100103961 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 3939170 | 196958.5 | 962636 | 962636 | 1125200251 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 38 | 100 | 2012-12-09 | 2014-06-02 | 2023-08-23 | 2023-08-23 |  |  | ضعف كفاءة المقاول الفنية |  | 43.6565 | 26.1508 | مسحوب | No
2100092525 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تصميم | ذات اولوية عالية وعاجلة | 68659000 | 3432950 | 39516997.5 | 39516997.5 | 4700106646 | لا | 0 | 190309034203 | جاري | اخرى | 66.36 | 98.13 | 2018-02-06 | 2023-02-05 | 2023-02-05 | 2023-02-05 |  |  |  |  | 38.202 | 23.9837 | Failed | No
2100082084 | أمانة / جدة | تشييد | ذات اولوية عالية | 4938532 | 246926.6 | 4938532.18 | 4938532.18 | 1010064626 | لا | 0 | 181209470332 | منجز – استلام نهائي | تكلفة العمل المنجز | 81 | 100 | 2014-12-17 | 2016-05-31 | 2017-05-26 | 2017-05-26 | 2016-05-31 | 2020-01-07 | ضعف كفاءة المقاول الفنية |  | 40.4654 | 20.2945 | منجز | No
2100065133 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 573216 | 28660.8 | 487990 | 487990 | 4030105559 | لا | 0 | 190701074417 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-07-22 | 2020-07-16 | 2022-06-30 | 2022-06-30 | 2020-07-16 |  | التنسيق مع أصحاب المصلحه (خدمات |  | 42.8475 | 21.2536 | منجز | No
2100000685 | وزارة الدفاع / الإدارة الهندسية والاشغال بالخدمات الصحية | تشييد | ذات اولوية عالية | 171941866.47 | 8597093.3235 | 135785884.7 | 135785884.7 | 1010033701 | لا | 0 | 181009138280 | جاري | الكميات التي تم تركيبها | 79.8 | 100 | 2012-11-20 | 2015-10-18 | 2022-11-29 | 2022-11-29 |  |  | تغيرات في نطاق المشروع |  | 40.4201 | 21.2232 | متأخر | No
2100009225 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية وعاجلة | 98357490 | 4917874.5 | 82611385.53 | 81413938.06 | 1010012911 | لا | 0 | 180901097136 | جاري | منهجية القيمة المكتسبة | 100 | 100 | 2018-12-11 | 2021-11-09 | 2022-06-30 | 2022-06-30 |  |  | اخرى |  | 43.9592 | 26.2189 | متأخر | No
2100104602 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية وعاجلة | 29499925 | 1474996.25 | 0 | 0 | 1128009818 | لا | 0 | 180909113450 | جاري | منهجية القيمة المكتسبة | 91.6 | 100 | 2018-02-25 | 2021-01-22 | 2022-04-30 | 2022-04-30 |  |  | اخرى |  | 44.2022 | 26.8085 | متأخر | No
2100039281 | وزارة الداخلية / مديرية الأمن العام | تشييد | ذات اولوية متوسطة | 1970050 | 98502.5 | 1970050 | 1970050 | 4032147988 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-10-02 | 2020-10-02 | 2021-04-19 | 2021-04-19 | 2020-10-02 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 44.2198 | 17.8843 | منجز | No
2100105641 | جامعة جازان | تشييد | ذات اولوية عالية وعاجلة | 6123577.95 | 306178.8975 | 6123577.95 | 6123577.95 | 5860024921 | لا | 0 | 190701011190 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-04-06 | 2019-08-02 | 2019-12-02 | 2019-12-02 | 2019-08-02 |  | لا يوجد تأخير |  | 42.5452 | 16.9621 | منجز | No
2100077766 | وزارة الخارجية | إشراف | لم تعد تحتاجها الجهة | 11216250 | 560812.5 | 1556899.1 | 1556899.1 | 1010348048 | لا | 0 | 180809037841 | مسحوب | مدفوعات ساعات العمل | 4 | 99 | 2017-10-25 | 2019-12-26 | 2019-12-26 | 2019-12-26 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 15.0509 | 12.1189 | مسحوب | No
2100069053 | أمانة / الجوف | تشييد | ذات اولوية عالية وعاجلة | 51098439 | 2554921.95 | 45550423.21 | 45550423.21 | 3400008531 | لا | 0 | 180909079843 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-02-28 | 2017-08-17 | 2022-09-15 | 2022-09-15 | 2017-08-17 |  |  |  | 40.1341 | 29.8796 | منجز | No
2100028884 | أمانة / الباحة | تشييد | ذات اولوية منخفضة | 3413215 | 170660.75 | 1355210 | 1355210 | 5805010799 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 50.6 | 100 | 2013-09-18 | 2014-09-07 | 2014-09-07 | 2014-09-07 |  |  | ضعف كفاءة المقاول الفنية |  | 41.2671 | 20.191 | مسحوب | No
2100052032 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 5098717.7 | 254935.885 | 5098717.7 | 5098717.7 | 5810001890 | لا | 0 | 181201450065 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-11-25 | 2019-11-15 | 2020-12-30 | 2020-12-30 | 2019-11-15 |  |  |  | 41.3856 | 20.153 | منجز | No
2100041440 | شركة المياه الوطنية / منطقة مكة المكرمة | إشراف | ذات اولوية عالية | 8869200 | 443460 | 6299094.85 | 6299094.85 | 1010326770 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2018-05-13 | 2020-05-13 | 2020-05-13 | 2020-05-13 | 2020-05-13 |  | لا يوجد تأخير |  | 39.2813 | 21.4671 | منجز | No
2100097311 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 35500465 | 1775023.25 | 31950418.3 | 31950418.3 | 2057001166 | لا | 0 | 190401039161 | جاري | منهجية القيمة المكتسبة | 92.9 | 100 | 2019-07-23 | 2021-07-23 | 2022-06-27 | 2022-06-27 |  |  | اخرى |  | 45.9608 | 28.4527 | متأخر | No
2100033504 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية وعاجلة | 24621330.5 | 1231066.525 | 16594609.14 | 12360784.18 | 1128019318 | لا | 0 | 180801055835 | جاري | منهجية القيمة المكتسبة | 79.8 | 97 | 2018-10-03 | 2021-08-31 | 2023-07-31 | 2023-07-31 |  |  | اخرى |  | 43.9875 | 26.0873 | متأخر | No
2100105280 | جامعة الطائف | تشييد | ذات اولوية متوسطة | 11600000 | 580000 | 8431736.3 | 8431736.3 | 1010102752 | لا | 0 | 181109259644 | جاري | تكلفة العمل المنجز | 73 | 100 | 2017-12-03 | 2018-07-30 | 2023-01-01 | 2023-01-01 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 40.4952 | 21.4338 | Failed | No
2100049512 | وزارة الشـؤون الاسلامية والدعوة والارشاد | تشييد | ذات اولوية عالية | 492450 | 24622.5 | 467931.79 | 70881.24 | 5950008566 | لا | 0 | 180909070297 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-03-25 | 2019-06-25 | 2019-11-25 | 2019-11-25 | 2019-06-25 |  | تأخرصرف المستحقات المالية |  | 44.2396 | 17.5273 | منجز | No
2100059065 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 3229493.25 | 161474.6625 | 1099698 | 1099698 | 1010102014 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2018-11-01 | 2020-10-18 | 2022-08-15 | 2022-08-15 | 2020-10-18 |  |  |  | 43.9544 | 26.3504 | منجز | No
2100083215 | أمانة / جازان | تشييد | ذات اولوية عالية | 2545598.3 | 127279.915 | 1829028 | 1829028 | 5950007619 | لا | 0 | 190209046943 | مسحوب | الكميات التي تم تركيبها | 72 | 100 | 2014-07-19 | 2015-07-15 | 2021-11-11 | 2021-11-11 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5948 | 16.8826 | مسحوب | No
2100029330 | أمانة / عسير | تشييد | ذات اولوية عالية | 2829595 | 141479.75 | 1317970 | 1317970 | 5850000022 | لا | 0 |  | جاري | تكلفة العمل المنجز | 88 | 100 | 2011-03-07 | 2015-06-05 | 2021-12-30 | 2021-12-30 |  |  | ضعف كفاءة المقاول الفنية |  | 41.9567 | 19.5602 | Failed | No
2100103891 | وزارة التعليم | تشييد | ذات اولوية عالية | 9532531.5 | 476626.575 | 894844.73 | 894844.73 | 1132000522 | لا | 0 |  | مسحوب | التكلفة المفوترة | 15 | 100 | 2015-05-16 | 2017-05-05 | 2023-08-20 | 2023-08-20 |  |  | ضعف كفاءة المقاول الفنية |  | 43.9544 | 26.3504 | مسحوب | No
2100029573 | أمانة / الجوف | تشييد | ذات اولوية عالية | 598500 | 29925 | 525000 | 525000 | 3400011750 | لا | 0 | 181009132425 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-04-25 | 2018-10-18 | 2018-10-19 | 2018-10-19 | 2018-10-18 |  |  |  | 39.3039 | 29.894 | منجز | No
2100051645 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 7681930 | 384096.5 | 7681930 | 6774778 | 1010238093 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-07-22 | 2018-03-15 | 2021-11-15 | 2021-11-15 | 2018-03-15 |  | موافقات |  | 41.4658 | 20.0054 | منجز | No
2100033401 | أمانة / الجوف | تشييد | ذات اولوية عالية | 767700 | 38385 | 767700 | 767700 | 5802010434 | لا | 0 | 180909091063 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-06-26 | 2019-02-17 | 2019-02-17 | 2019-02-17 | 2019-02-17 |  |  |  | 39.3051 | 29.888 | منجز | No
2100068600 | أمانة / الجوف | تشييد | ذات اولوية عالية وعاجلة | 11580500 | 579025 | 11580500 | 11580500 | 3350000106 | لا | 0 | 190609053438 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-11-20 | 2019-11-20 | 2019-11-20 | 2019-11-20 | 2019-11-20 |  |  |  | 37.382 | 31.3316 | منجز | No
2100080625 | أمانة / الجوف | تشييد | ذات اولوية عالية | 6490000 | 324500 | 6490000 | 6490000 | 1134000444 | لا | 0 | 180709021881 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2017-11-13 | 2018-11-09 | 2018-11-10 | 2018-11-10 | 2018-11-09 |  | تأخرصرف المستحقات المالية |  | 39.3051 | 29.888 | منجز | No
2100067535 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1852690 | 92634.5 | 1168113.29 | 1168113.29 | 4037000411 | لا | 0 | 190609083508 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-02-19 | 2020-02-14 | 2023-04-03 | 2023-04-03 |  |  |  |  | 42.1746 | 22.7212 | منتظم | No
2100074443 | جامعة نجران | تشييد | ذات اولوية عالية | 12077538 | 603876.9 | 5815207 | 5815207 | 1010019502 | لا | 0 | 181209533171 | ايقاف كلي | الكميات التي تم تركيبها | 91 | 100 | 2012-05-23 | 2014-06-28 | 2022-11-30 | 2022-11-30 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 44.2341 | 17.5757 | Failed | No
2100044074 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 25568019 | 1278400.95 | 25568019 | 25568019 | 1010069549 | لا | 0 | 180909081030 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-03-20 | 2019-03-31 | 2022-03-07 | 2022-03-07 | 2019-03-31 |  | ضعف كفاءة المقاول الفنية | تم إنذار المقاول كتابيا | 41.7129 | 27.5158 | منجز | No
2100064735 | أمانة / الجوف | تشييد | ذات اولوية عالية | 1199500 | 59975 | 1199500 | 1199500 | 3400014158 | لا | 0 | 180909099279 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-08-28 | 2019-08-22 | 2019-08-22 | 2019-08-22 | 2019-08-22 |  |  |  | 39.866 | 29.8087 | منجز | No
2100079461 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية وعاجلة | 19431714 | 971585.7 | 10874963.83 | 10874963.83 | 4650002884 | لا | 0 | 180809065455 | جاري | منهجية القيمة المكتسبة | 63.87 | 100 | 2015-06-25 | 2019-05-13 | 2022-12-31 | 2022-12-31 |  |  | لا يوجد تأخير |  | 39.6038 | 24.4963 | Failed | No
2100060966 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 25997407.5 | 1299870.375 | 25470157.5 | 25470157.5 | 2050074755 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 98.3 | 100 | 2018-02-11 | 2020-02-11 | 2020-02-06 | 2020-02-06 |  | 2020-02-11 | لا يوجد تأخير |  | 45.9688 | 28.3676 | منجز | No
2100105125 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية عالية | 15977332.66 | 798866.633 | 15957951.9 | 15957951.9 | 5855007803 | لا | 0 | 180401002997 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-05-23 | 2020-05-01 | 2020-04-28 | 2020-04-28 |  | 2020-05-01 | لا يوجد تأخير |  | 42.6031 | 20.0028 | منجز | No
2100103880 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية | 17803851.25 | 890192.5625 | 18377702.23 | 17808849.27 | 7001805295 | لا | 0 | 180709019624 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2014-06-15 | 2016-11-17 | 2021-04-12 | 2021-04-12 |  | 2016-11-17 | ضعف كفاءة المقاول الفنية |  | 44.2014 | 25.8831 | منجز | No
2100007066 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية وعاجلة | 99991873 | 4999593.65 | 25961121.93 | 25926032 | 1131013992 | لا | 0 | 180901085536 | جاري | منهجية القيمة المكتسبة | 85 | 99.84 | 2018-12-13 | 2021-11-11 | 2022-11-30 | 2022-11-30 |  |  | اخرى |  | 43.956 | 26.2302 | متأخر | No
2100031312 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 19914988 | 995749.4 | 17054209.91 | 17054209.91 | 2050060197 | لا | 0 | 180809038133 | جاري | منهجية القيمة المكتسبة | 93 | 100 | 2017-12-07 | 2019-11-16 | 2022-05-26 | 2022-05-26 |  |  | لا يوجد تأخير |  | 49.8742 | 25.3367 | Failed | No
2100007011 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2085210 | 104260.5 | 122470 | 122470 | 1131040786 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 10 | 100 | 2014-02-19 | 2015-02-07 | 2021-09-05 | 2021-09-05 |  |  | ضعف كفاءة المقاول الفنية |  | 43.2649 | 26.4408 | مسحوب | No
2100002984 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية وعاجلة | 12990500 | 649525 | 10419750.17 | 10419750.17 | 2051001250 | لا | 0 | 181001157296 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 91 | 100 | 2018-05-16 | 2019-05-16 | 2021-03-17 | 2021-03-17 | 2019-05-16 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 50.2204 | 26.2914 | منجز | No
2100105372 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 8413556.25 | 420677.8125 | 0 | 0 | 2057001398 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-10-12 | 2020-09-10 | 2021-02-16 | 2021-02-16 | 2020-09-10 |  | لا يوجد تأخير |  | 45.9513 | 28.3981 | منجز | No
2100003371 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية متوسطة | 3999990 | 199999.5 | 3774990 | 3774990 | 1010436567 | لا | 0 | 180901000179 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-02-14 | 2020-01-04 | 2020-06-04 | 2020-06-04 |  | 2020-01-04 | لا يوجد تأخير |  | 41.5298 | 18.2084 | منجز | No
2100062005 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية | 93506829.6 | 4675341.48 | 71104999.98 | 71104999.98 | 1010009590 | لا | 0 | 181201475037 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 86.58 | 100 | 2019-03-06 | 2020-08-19 | 2021-05-03 | 2021-05-03 | 2020-08-19 |  | تغيرات في نطاق المشروع |  | 43.4693 | 26.6353 | منجز | No
2100074126 | شركة المياه الوطنية / منطقة حائل | إشراف | ذات اولوية عالية | 3486500 | 174325 | 8574848.95 | 8534668.95 | 2050101543 | لا | 0 | 180709026132 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2012-11-10 | 2014-11-10 | 2021-10-03 | 2021-10-03 | 2014-11-10 |  | لا يوجد تأخير |  | 40.4591 | 25.9817 | منجز | No
2100010371 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 49381073 | 2469053.65 | 35261594.9 | 24663172.81 | 1010110229 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2011-09-07 | 2013-08-27 | 2022-12-31 | 2022-12-31 | 2013-08-27 |  | ضعف كفاءة المقاول الفنية | أخرى | 43.6378 | 26.4981 | منجز | No
2100101183 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 41383917 | 2069195.85 | 39226585 | 39226585 | 2051002267 | لا | 0 | 180909089422 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-03-21 | 2019-03-21 | 2022-06-27 | 2022-06-27 | 2019-03-21 |  | أوامر تغيير |  | 38.4437 | 23.8431 | منجز | No
2100087371 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية وعاجلة | 101554461.29 | 5077723.0645 | 91571909.86 | 54759436.8 | 1010262887 | لا | 0 | 180709021971 | جاري | منهجية القيمة المكتسبة | 97.8 | 97.12 | 2018-03-29 | 2021-02-24 | 2022-11-30 | 2022-11-30 |  |  | ضعف كفاءة المقاول الفنية |  | 43.9544 | 26.3504 | منتظم | No
2100000641 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية وعاجلة | 9999986.73 | 499999.3365 | 5025275.24 | 4374334.19 | 2051001250 | لا | 0 | 181101265584 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 53.95 | 100 | 2019-02-13 | 2020-08-13 | 2021-05-23 | 2021-05-23 | 2020-08-13 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 50.1548 | 26.1687 | منجز | No
2100105416 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية وعاجلة | 64666829 | 3233341.45 | 37877158.13 | 37877158.13 | 5855007803 | لا | 0 | 180809061632 | جاري | منهجية القيمة المكتسبة | 86 | 99.64 | 2018-02-08 | 2020-07-13 | 2022-10-30 | 2022-10-30 |  |  | ضعف كفاءة المقاول الفنية |  | 43.9544 | 26.3504 | متأخر | No
2100097403 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية متوسطة | 6822795 | 341139.75 | 6822795 | 6822795 | 5850028078 | لا | 0 | 190401019158 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-08-25 | 2021-02-06 | 2021-02-03 | 2021-02-03 |  | 2021-02-06 | لا يوجد تأخير |  | 42.8019 | 18.1626 | منجز | No
2100024010 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 10235908.7 | 511795.435 | 0 | 0 | 1131021347 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 65 | 100 | 2020-03-29 | 2020-12-20 | 2023-01-01 | 2023-01-01 | 2020-12-20 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 43.9544 | 26.3504 | منجز | No
2100109281 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 5259679 | 262983.95 | 1644020 | 1644020 | 5855014881 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 31 | 100 | 2014-12-14 | 2016-06-06 | 2023-02-01 | 2023-02-01 |  |  | ضعف كفاءة المقاول الفنية |  | 42.4987 | 18.2178 | مسحوب | No
2100073850 | وزارة الصحة / بيشة | تشييد | ذات اولوية عالية | 2062825 | 103141.25 | 746036.27 | 746036.27 | 5851007525 | لا | 0 | 200801061615 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 95 | 100 | 2020-03-14 | 2020-12-03 | 2022-08-24 | 2022-08-24 |  |  | اخرى |  | 42.2366 | 20.0243 | Failed | No
2100063431 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية عالية | 19968260 | 998413 | 19968260 | 19968260 | 5850022870 | لا | 0 | 190301008905 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-03-21 | 2020-03-09 | 2020-03-05 | 2020-03-05 |  | 2020-03-09 | لا يوجد تأخير |  | 42.7302 | 18.3003 | منجز | No
2100083731 | معهد الإدارة العامة | تشييد | ذات اولوية عالية وعاجلة | 142265864 | 7113293.2 | 54297219.69 | 53116578.75 | 1010006362 | لا | 0 | 200209113814 | جاري | التكلفة المفوترة | 37 | 82 | 2012-09-10 | 2015-02-11 | 2023-03-11 | 2023-03-11 |  |  |  |  | 39.155 | 21.6024 | Failed | No
2100115706 | المؤسسة العامة للحبوب | ترميم | ذات اولوية عالية وعاجلة | 4675000 | 233750 | 4675000 | 4675000 | 1010085518 | لا | 0 | 200901103858 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 95 | 2021-02-23 | 2022-02-14 | 2022-02-14 | 2022-02-14 | 2022-02-14 |  |  |  | 41.745 | 27.5173 | منجز | No
2100095502 | جامعة القصيم | تشييد | ذات اولوية عالية وعاجلة | 15831044 | 791552.2 | 14269414.25 | 14269414.25 | 1131013286 | لا | 0 | 190201009111 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-05-06 | 2020-10-27 | 2023-02-01 | 2023-02-01 | 2020-10-27 |  | لا يوجد تأخير |  | 43.7751 | 26.3547 | منجز | No
2100023170 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 15417788.44 | 770889.422 | 4118666.89 | 4118666.89 | 1010223860 | لا | 0 |  | مسحوب | التكلفة المفوترة | 45 | 100 | 2012-11-13 | 2014-11-03 | 2023-05-19 | 2023-05-19 |  |  | ضعف كفاءة المقاول الفنية |  | 42.4987 | 18.2178 | مسحوب | No
2100079833 | جامعة الملك خالد | تشييد | ذات اولوية عالية وعاجلة | 105155456.66 | 5257772.833 | 93569090 | 93569090 | 2051037631 | لا | 0 | 180809037966 | جاري | تكلفة العمل المنجز | 100 | 100 | 2017-01-18 | 2017-12-14 | 2021-05-01 | 2021-05-01 |  |  | تأخرصرف المستحقات المالية |  | 42.8114 | 18.1027 | Failed | No
2100026132 | وزارة التجارة | دراسة الجدوى | ذات اولوية عالية وعاجلة | 2464200 | 123210 | 2176880.46 | 2176880.46 | 1010348048 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-10-03 | 2020-10-02 | 2021-08-15 | 2021-08-15 |  | 2020-10-02 | اخرى |  |  |  | منجز | No
2100107133 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 7251145 | 362557.25 | 5539444.9 | 0 | 1132002570 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 83 | 100 | 2012-05-25 | 2014-05-04 | 2018-12-12 | 2018-12-12 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | مسحوب | Yes
2100002693 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2199998.05 | 109999.9025 | 0 | 0 | 2511004496 | لا | 0 |  | مسحوب | التكلفة المفوترة | 0 | 100 | 2010-09-25 | 2011-11-19 | 2020-10-19 | 2020-10-19 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | مسحوب | No
2100018550 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 3140286.8 | 157014.34 | 364550 | 0 | 3350035090 | لا | 0 |  | جاري | التكلفة المفوترة | 75 | 100 | 2017-12-04 | 2019-01-22 | 2023-06-15 | 2023-06-15 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | Failed | Yes
2100109233 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2499065 | 124953.25 | 930993.6 | 675528.75 | 3450003790 | لا | 0 | 190909118282 | جاري | تكلفة العمل المنجز | 45 | 100 | 2015-03-07 | 2016-05-20 | 2022-05-22 | 2022-05-22 |  |  | ضعف كفاءة المقاول الفنية |  | 37.9236 | 26.6096 | Failed | No
2100038883 | وزارة التعليم | تشييد | ذات اولوية عالية | 7870535.28 | 393526.764 | 2388465.65 | 2388465.65 | 3350003498 | لا | 0 |  | جاري | التكلفة المفوترة | 52 | 100 | 2014-09-07 | 2016-05-30 | 2023-12-15 | 2023-12-15 |  |  | ضعف كفاءة المقاول الفنية |  | 38.2579 | 24.4222 | Failed | No
2100003872 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية وعاجلة | 55027549.9 | 2751377.495 | 36685381.37 | 29058910.09 | 1010184370 | لا | 0 | 180709020123 | جاري | منهجية القيمة المكتسبة | 90 | 100 | 2017-12-07 | 2020-05-11 | 2022-06-24 | 2022-06-24 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 44.251 | 26.7976 | متأخر | No
2100192205 | وزارة الصحة / القنفذة | الخدمات الاستشارية | ذات اولوية عالية | 4680000 | 234000 | 4186000 | 3289000 | 1010327812 | لا | 0 | 210909229053 | جاري | اخرى | 77.78 | 77.78 | 2020-09-01 | 2023-08-31 | 2023-08-31 | 2023-08-31 |  |  |  |  | 41.0714 | 19.149 | خدمات عامة | No
2100192710 | جامعة القصيم | تشييد | ذات اولوية عالية وعاجلة | 66838874.39 | 3341943.7195 | 51490154.77 | 51490154.77 | 1131032608 | لا | 0 | 190601031337 | جاري | تكلفة العمل المنجز | 92 | 80 | 2020-10-18 | 2022-10-08 | 2023-07-05 | 2023-07-05 |  |  |  |  | 43.7726 | 26.3526 | منتظم | No
2100084685 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تصميم | ذات اولوية عالية وعاجلة | 46572955 | 2328647.75 | 41483278.51 | 41483278.51 | 1010322156 | لا | 0 | 190509126984 | جاري | تكلفة العمل المنجز | 86 | 99 | 2018-01-30 | 2023-01-29 | 2023-01-29 | 2023-01-29 |  |  |  |  | 49.176 | 27.4976 | متأخر | No
2100026246 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية | 71155968.37 | 3557798.4185 | 51239905.22 | 51239905.22 | 1010196220 | لا | 0 | 180709021860 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2013-04-08 | 2015-03-29 | 2023-01-19 | 2023-01-19 | 2015-03-29 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 43.9459 | 26.3538 | منجز | No
2100052323 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 29901151.85 | 1495057.5925 | 26909130.56 | 20109655.2 | 2050022550 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2013-05-19 | 2015-05-09 | 2022-06-30 | 2022-06-30 | 2015-05-09 |  |  |  | 43.7149 | 25.9848 | منجز | No
2100061305 | شركة المياه الوطنية | تشييد | ذات اولوية عالية وعاجلة | 397849748.4 | 19892487.42 | 147198531 | 147198531 | 5855000147 | لا | 0 | 190801017929 | ايقاف جزئي | منهجية القيمة المكتسبة | 54.62 | 100 | 2019-09-22 | 2021-08-31 | 2023-03-31 | 2023-03-31 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.6031 | 20.0028 | Failed | No
2100060045 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية وعاجلة | 44715314.4 | 2235765.72 | 21203443.34 | 19788750.85 | 1010012911 | لا | 0 | 190201002220 | جاري | منهجية القيمة المكتسبة | 88.3 | 98.25 | 2019-08-21 | 2021-07-30 | 2022-07-28 | 2022-07-28 |  |  | اخرى |  | 43.9326 | 26.2788 | متأخر | No
2100015385 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 22777830 | 1138891.5 | 18112443 | 18112443 | 4030113058 | لا | 0 | 180709035612 | مسحوب | منهجية القيمة المكتسبة | 86.9 | 100 | 2017-09-14 | 2019-09-14 | 2022-07-18 | 2022-07-18 |  |  | أوامر تغيير |  | 38.2263 | 23.9863 | مسحوب | No
2100058925 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 9148995.88 | 457449.794 | 9148976 | 9148976 | 1131013286 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2017-04-11 | 2019-04-11 | 2019-05-05 | 2019-05-05 | 2019-04-11 |  |  |  | 43.9544 | 26.3504 | منجز | No
2100058542 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 9427515 | 471375.75 | 502021.8 | 502021.8 | 1131010605 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 11 | 100 | 2015-10-13 | 2017-10-03 | 2021-04-13 | 2021-04-13 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 43.9544 | 26.3504 | مسحوب | No
2100060384 | المركز الوطني لتنمية الحياة الفطرية | تشييد | ذات اولوية عالية | 3454231 | 172711.55 | 3454231 | 3454231 | 1116007038 | لا | 0 | 180709024876 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-11-04 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 |  | لا يوجد تأخير |  | 43.4789 | 26.821 | منجز | No
2100006742 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 7169831.52 | 358491.576 | 2125909.13 | 2002078.8 | 1116004360 | لا | 0 | 190309007849 | مسحوب | التكلفة المفوترة | 36 | 100 | 2013-05-31 | 2015-02-20 | 2023-08-16 | 2023-08-16 |  |  | ضعف كفاءة المقاول الفنية |  | 41.4779 | 20.0185 | مسحوب | No
2100055661 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 60849181.5 | 3042459.075 | 47950965 | 47950965 | 3555000709 | لا | 0 | 181209546509 | جاري | منهجية القيمة المكتسبة | 90 | 100 | 2018-01-31 | 2020-01-31 | 2023-04-01 | 2023-04-01 |  |  | ضعف كفاءة المقاول الفنية |  | 38.2222 | 24.0092 | متأخر | No
2100056512 | شركة المياه الوطنية / منطقة عسير | إشراف | ذات اولوية عالية | 14011200 | 700560 | 6603415 | 5942553.45 | 1010325732 | لا | 0 | 190901064501 | جاري | التكلفة المفوترة | 44.7 | 44.7 | 2019-12-30 | 2021-12-29 | 2022-02-15 | 2022-02-15 |  |  | لا يوجد تأخير |  | 42.5106 | 18.2116 | خدمات عامة | No
2100032141 | شركة المياه الوطنية | الخدمات الاستشارية | ذات اولوية عالية وعاجلة | 24183000 | 1209150 | 22256621.74 | 21404621.73 | 1010213041 | لا | 0 |  | منجز – استلام نهائي | التكلفة المفوترة | 100 | 100 | 2017-02-19 | 2020-02-18 | 2021-06-20 | 2021-06-20 |  | 2020-02-18 | لا يوجد تأخير |  | 46.6834 | 24.6878 | منجز | No
2100191494 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 55246166.75 | 2762308.3375 | 3385508 | 3385508 | 2050007224 | لا | 0 | 200709052696 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 84.4 | 100 | 2019-12-04 | 2020-12-04 | 2021-06-13 | 2021-06-13 | 2020-12-04 |  |  |  | 39.2233 | 21.6457 | منجز | No
2100051951 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 6439224.38 | 321961.219 | 2067877.86 | 0 | 1010090099 | لا | 0 |  | مسحوب | التكلفة المفوترة | 45 | 100 | 2014-06-29 | 2016-03-19 | 2020-09-01 | 2020-09-01 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5604 | 25.3897 | مسحوب | Yes
2100061821 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 5617098.28 | 280854.914 | 3261869.54 | 3261869.54 | 1010046644 | لا | 0 |  | مسحوب | التكلفة المفوترة | 95 | 100 | 2013-11-10 | 2016-02-27 | 2019-03-01 | 2019-03-01 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5604 | 25.3897 | مسحوب | No
2100076635 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | توريد وتركيب | ذات اولوية عالية وعاجلة | 5401900 | 270095 | 3186367 | 3186367 | 2051059585 | لا | 0 | 190909028740 | منجز – استلام ابتدائي | اخرى | 60.25 | 100 | 2017-07-03 | 2022-07-02 | 2023-03-09 | 2023-03-09 | 2022-07-02 |  |  |  | 38.1801 | 24.0042 | منجز | No
2100093914 | وزارة الصحة / مستشفى الملك خالد للعيون | تشييد | ذات اولوية متوسطة | 777000 | 38850 | 0.01 | 0.01 | 4030137216 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 50 | 100 | 2012-12-08 | 2013-05-06 | 2022-09-30 | 2022-09-30 |  |  | ضعف كفاءة المقاول الفنية | أخرى | 46.6364 | 24.6948 | مسحوب | No
2100086483 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 10196847.32 | 509842.366 | 7378164.84 | 6761152.2 | 1131014506 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2013-06-11 | 2015-06-01 | 2020-09-10 | 2020-09-10 | 2015-06-01 |  | ضعف كفاءة المقاول الفنية |  | 43.9875 | 26.0873 | منجز | No
2100098571 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 1561602 | 78080.1 | 1470405.76 | 1470405.76 | 1132008973 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2017-12-10 | 2018-12-04 | 2019-08-26 | 2019-08-26 | 2018-12-04 |  |  |  | 43.4919 | 25.8758 | منجز | No
2100062366 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 65658863.48 | 3282943.174 | 63798640.04 | 63798640.04 | 1134000444 | لا | 0 | 180809049031 | جاري | منهجية القيمة المكتسبة | 99 | 100 | 2018-02-18 | 2020-10-11 | 2023-04-16 | 2023-04-16 |  |  | اخرى |  | 49.6626 | 27.0037 | متأخر | No
2100071061 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 270941924.62 | 13547096.231 | 167953327.69 | 167953327.69 | 1010008118 | لا | 0 | 180809046262 | جاري | منهجية القيمة المكتسبة | 65 | 100 | 2015-03-25 | 2018-03-21 | 2024-01-09 | 2024-01-09 |  |  | تأخرصرف المستحقات المالية |  | 49.6626 | 27.0037 | Failed | No
2100007276 | جامعة الجوف | تشييد | ذات اولوية عالية | 213166125.15 | 10658306.2575 | 133522937.46 | 126522937.46 | 3450008383 | لا | 0 | 180809052932 | جاري | تكلفة العمل المنجز | 77 | 85 | 2014-08-11 | 2021-03-17 | 2023-10-04 | 2023-10-04 |  |  | تأخرصرف المستحقات المالية |  | 40.0583 | 29.8064 | متأخر | No
2100091000 | أمانة / تبوك | تشييد | لم تعد تحتاجها الجهة | 575650 | 28782.5 | 380000 | 380000 | 3550025468 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 70 | 100 | 2013-12-18 | 2014-12-19 | 2021-01-04 | 2021-01-04 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5809 | 28.4464 | مسحوب | No
2100053045 | أمانة / جازان | تشييد | ذات اولوية عالية وعاجلة | 35908850 | 1795442.5 | 17966476.62 | 17966476.62 | 5904006379 | لا | 0 | 181109358798 | جاري | تكلفة العمل المنجز | 61 | 100 | 2015-05-20 | 2017-05-10 | 2022-03-30 | 2022-03-30 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5654 | 16.9632 | Failed | No
2100065030 | أمانة / تبوك | تشييد | ذات اولوية عالية وعاجلة | 8636775 | 431838.75 | 7391527 | 7391527 | 4650050668 | لا | 0 | 200309001528 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-09-30 | 2020-09-24 | 2021-03-25 | 2021-03-25 | 2020-09-24 |  | ضعف كفاءة المقاول الفنية |  | 36.5417 | 28.3361 | منجز | No
2100107181 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 105992149.78 | 5299607.489 | 101997942.09 | 101997942.09 | 2050007518 | لا | 0 | 190501013484 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-09-25 | 2022-03-23 | 2023-11-09 | 2023-11-09 |  |  | لا يوجد تأخير |  | 49.6626 | 27.0037 | منتظم | No
2100042383 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 3999275 | 199963.75 | 2917235 | 2172695 | 4030071125 | لا | 0 |  | جاري | اخرى | 100 | 100 | 2019-01-27 | 2020-01-26 | 2020-01-26 | 2020-01-26 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | Failed | No
2100009376 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 59439325 | 2971966.25 | 52344494.89 | 52344494.89 | 3003996726 | لا | 0 | 180901080763 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-03-03 | 2021-02-28 | 2022-07-31 | 2022-07-31 | 2021-02-28 |  | ضعف كفاءة المقاول الفنية |  | 27.1331 | 49.5534 | منجز | No
2100047180 | أمانة / جازان | تشييد | لم تعد تحتاجها الجهة | 1641425 | 82071.25 | 0.01 | 0.01 | 5950018950 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 0 | 100 | 2015-11-04 | 2016-10-19 | 2022-03-30 | 2022-03-30 |  |  | ضعف كفاءة المقاول الفنية |  | 42.6241 | 17.142 | مسحوب | No
2100030306 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 686000 | 34300 | 247564.67 | 247564.67 | 3550023679 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 37 | 37 | 2013-12-25 | 2014-09-01 | 2014-03-01 | 2014-03-01 |  |  | ضعف كفاءة المقاول الفنية |  | 37.2236 | 26.0207 | مسحوب | No
2100074981 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 2433100 | 121655 | 2433100 | 2433100 | 5851000110 | لا | 0 | 190709099031 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-03-11 | 2020-03-05 | 2020-03-05 | 2020-03-05 | 2020-03-05 |  | ضعف كفاءة المقاول الفنية |  | 42.8489 | 21.2544 | منجز | No
2100031345 | أمانة / حائل | تشييد | ذات اولوية عالية | 2916000 | 145800 | 2916000 | 2916000 | 3350013518 | لا | 0 | 210309037986 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-07-03 | 2021-02-18 | 2021-02-19 | 2021-02-19 | 2021-02-18 |  |  |  | 43.0161 | 27.456 | منجز | No
2100045813 | أمانة / عسير | تشييد | ذات اولوية عالية | 8398658 | 419932.9 | 1553022 | 1553022 | 5856021642 | لا | 0 | 190901039747 | فسخ العقد | تكلفة العمل المنجز | 74 | 100 | 2019-09-28 | 2023-04-04 | 2023-04-04 | 2023-04-04 |  |  | اخرى |  | 43.131 | 18.0776 | مسحوب | No
2100005165 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 4775542.07 | 238777.1035 | 1436480.34 | 1436480.34 | 4031053163 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-09-25 | 2016-03-10 | 2021-08-19 | 2021-08-19 | 2016-03-10 |  | ضعف كفاءة المقاول الفنية |  | 43.6578 | 26.1466 | منجز | No
2100004885 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2741254.28 | 137062.714 | 1188899 | 1188899 | 1139003455 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2012-12-19 | 2014-03-14 | 2021-06-05 | 2021-06-05 | 2014-03-14 |  | ضعف كفاءة المقاول الفنية |  | 43.6565 | 26.1508 | منجز | No
2100033132 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 3352365 | 167618.25 | 1356230.18 | 1356230.18 | 1010267848 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 13 | 100 | 2015-07-27 | 2017-01-08 | 2017-01-08 | 2017-01-08 |  |  | ضعف كفاءة المقاول الفنية |  | 39.5577 | 24.5284 | مسحوب | No
2100195532 | وزارة الخارجية | إشراف | ذات اولوية متوسطة | 6157781.25 | 307889.0625 | 0 | 0 | 1010322156 | لا | 0 | 190901056382 | لم يبدأ | مدفوعات ساعات العمل | 10 | 50 | 2020-08-27 | 2022-11-27 | 2022-11-27 | 2022-11-27 |  |  |  |  | 9.4637 | 0.41468 | Failed | No
2100194272 | أمانة / جدة | دراسات هندسية | ذات اولوية متوسطة | 3301379 | 165068.95 | 3447757.17 | 2980178.13 | 4030229097 | لا | 0 | 190509001644 | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2019-01-30 | 2021-12-27 | 2022-06-15 | 2022-06-15 | 2021-12-27 | 2022-06-16 |  |  | 39.1677 | 21.5008 | منجز | No
2100101113 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 9044678 | 452233.9 | 8587470 | 8587470 | 4030023505 | لا | 0 | 181209546650 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2014-04-10 | 2016-04-08 | 2018-02-01 | 2018-02-01 | 2016-04-08 |  | موافقات |  | 38.1884 | 24.0057 | منجز | No
2100050013 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 1799755 | 89987.75 | 1709767 | 784247.55 | 3552000023 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-12-24 | 2019-12-07 | 2020-02-08 | 2020-02-08 | 2019-12-07 |  |  |  | 36.5857 | 28.3633 | منجز | No
2100013941 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 1318500 | 65925 | 137610 | 137610 | 4030154324 | لا | 0 | 181209470332 | فسخ العقد | تكلفة العمل المنجز | 10 | 100 | 2010-10-12 | 2012-08-22 | 2021-09-09 | 2021-09-09 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 40.2799 | 20.1408 | مسحوب | No
2100193583 | رئاسة أمن الدولة / المديرية العامة للمباحث | تشييد | ذات اولوية عالية | 4898628 | 244931.4 | 0.01 | 0.01 | 4031047242 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 95 | 100 | 2020-02-18 | 2022-02-14 | 2023-02-28 | 2023-02-28 |  |  |  |  | 39.8304 | 21.4239 | Failed | No
2100052802 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 4898615.4 | 244930.77 | 3514632.77 | 3514632.77 | 4032030986 | لا | 0 | 191101046138 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-09-26 | 2021-03-19 | 2021-06-06 | 2021-06-06 | 2021-03-19 |  |  |  | 40.4189 | 21.2528 | منجز | No
2100194110 | أمانة / جدة | أخرى | ذات اولوية عالية وعاجلة | 3856954 | 192847.7 | 3582229.2 | 2516341.8 | 4603007919 | لا | 0 |  | جاري | تكلفة العمل المنجز | 78 | 77 | 2019-10-22 | 2021-09-29 | 2022-12-02 | 2022-12-02 |  |  |  |  | 39.3404 | 22.1126 | خدمات عامة | No
2100058822 | وزارة التعليم | تشييد | ذات اولوية عالية | 7416947.34 | 370847.367 | 2489280 | 2489280 | 1132000522 | لا | 0 |  | مسحوب | التكلفة المفوترة | 40 | 100 | 2014-09-09 | 2016-08-29 | 2023-09-20 | 2023-09-20 |  |  | ضعف كفاءة المقاول الفنية |  | 43.9544 | 26.3504 | مسحوب | No
2100065354 | أمانة / الجوف | تشييد | ذات اولوية عالية | 3699750 | 184987.5 | 3699750 | 3699750 | 3450009076 | لا | 0 | 191101093153 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-07-22 | 2020-01-16 | 2020-01-16 | 2020-01-16 | 2020-01-16 |  |  |  | 37.3472 | 31.3283 | منجز | No
2100085212 | هيئة المدن الصناعية ومناطق التقنية | تصميم | ذات اولوية عالية | 16171514 | 808575.7 | 16171514 | 16171514 | 1010213041 | لا | 0 |  | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-02-17 | 2023-01-27 | 2023-01-27 | 2023-01-27 |  |  | لا يوجد تأخير |  | 46.6871 | 24.7069 | منتظم | No
2100068062 | أمانة / تبوك | تشييد | ذات اولوية عالية وعاجلة | 569362.5 | 28468.125 | 449347 | 449347 | 3555000931 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-09-15 | 2020-03-11 | 2020-03-12 | 2020-03-12 | 2020-03-11 |  | ضعف كفاءة المقاول الفنية |  | 36.5763 | 28.3619 | منجز | No
2100054784 | أمانة / تبوك | تشييد | ذات اولوية عالية | 38261715 | 1913085.75 | 29016046.5 | 29016046.5 | 4030139128 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 93.65 | 95 | 2014-11-18 | 2016-02-11 | 2021-04-22 | 2021-04-22 | 2016-02-11 |  | ضعف كفاءة المقاول الفنية |  |  |  | منجز | No
2100195543 | وزارة الخارجية | إشراف | ذات اولوية متوسطة | 3004200 | 150210 | 614263.49 | 0 | 0 | لا | 0 |  | ايقاف كلي | مدفوعات ساعات العمل | 5 | 100 | 2019-07-01 | 2021-03-01 | 2021-03-01 | 2021-03-01 |  |  |  |  | 18.4176 | 43.8549 | Failed | Yes
2100062112 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية وعاجلة | 41869800 | 2093490 | 39566093.75 | 39052997.02 | 7011014615 | لا | 0 | 180709019725 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-10-29 | 2020-04-02 | 2021-09-28 | 2021-09-28 | 2020-04-02 |  | لا يوجد تأخير |  | 43.9875 | 26.0873 | منجز | No
2100100111 | الهيئة العامة للطيران المدني | تشييد | ذات اولوية عالية وعاجلة | 2568501718 | 128425085.9 | 793545116 | 748274681 | 1010034600 | لا | 0 | 200409013724 | جاري | منهجية القيمة المكتسبة | 42.52 | 66.57 | 2014-11-23 | 2018-05-06 | 2024-06-30 | 2024-06-30 |  |  | اخرى |  | 42.6192 | 16.8124 | متأخر | No
2100195016 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 477225 | 23861.25 | 477225 | 477225 | 4032026611 | لا | 0 | 201101230129 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-10-14 | 2020-01-21 | 2020-01-21 | 2020-01-21 | 2020-01-21 |  |  |  | 40.4252 | 21.2292 | منجز | No
2100068180 | أمانة / جازان | تشييد | ذات اولوية عالية | 1339424.8 | 66971.24 | 1339424.8 | 1339424.8 | 4030271639 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-12-01 | 2015-11-21 | 2015-11-23 | 2015-11-23 | 2015-11-21 |  | اخرى |  | 43.0481 | 17.0377 | منجز | No
2100096946 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 576980.25 | 28849.0125 | 576980.25 | 576980.25 | 4031062372 | لا | 0 |  | جاري | اخرى | 100 | 100 | 2019-11-17 | 2020-07-16 | 2020-10-05 | 2020-10-05 |  |  | اخرى |  |  |  | Failed | No
2100079380 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2864774.05 | 143238.7025 | 2314708.95 | 2314708.95 | 1131021347 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2018-10-01 | 2019-11-19 | 2020-09-29 | 2020-09-29 | 2019-11-19 |  |  |  | 43.9544 | 26.3504 | منجز | No
2100099293 | الهيئة العامة للطيران المدني | تشييد | ذات اولوية عالية وعاجلة | 392265996.36 | 19613299.818 | 33035429.14 | 23787141.84 | 1010053925 | لا | 0 | 190401063104 | جاري | مدفوعات ساعات العمل | 37.62 | 100 | 2019-12-22 | 2021-12-11 | 2023-08-26 | 2023-08-26 |  |  | اخرى | تم إنذار المقاول كتابيا | 40.0724 | 29.9146 | Failed | No
2100039690 | وزارة الخارجية | إشراف | لم تعد تحتاجها الجهة | 13765399.86 | 688269.993 | 9791335.5 | 9791335.5 | 1010325199 | لا | 0 |  | فسخ العقد | منهجية القيمة المكتسبة | 66 | 100 | 2015-08-02 | 2018-03-22 | 2018-04-28 | 2018-04-28 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 2.1117 | 13.5132 | مسحوب | No
2100026585 | أمانة / جدة | دراسات هندسية | ذات اولوية متوسطة | 1491000 | 74550 | 1491000 | 1491000 | 4650047424 | لا | 0 |  | منجز – استلام نهائي | اخرى | 90 | 90 | 2020-02-04 | 2020-10-27 | 2020-10-27 | 2020-10-27 | 2020-10-27 | 2020-10-28 | اخرى |  | 39.1715 | 21.5049 | منجز | No
2100178393 | وزارة الثقافة | تشييد | ذات اولوية عالية | 34581261.61 | 1729063.0805 | 7421348.34 | 5042011.68 | 3350012131 | لا | 0 | 201009164225 | مسحوب | منهجية القيمة المكتسبة | 25 | 100 | 2017-11-16 | 2020-01-30 | 2020-01-30 | 2020-01-30 |  |  | اخرى |  | 38.5101 | 27.591 | مسحوب | No
2100195510 | وزارة الخارجية | إشراف | ذات اولوية متوسطة | 2452000 | 122600 | 2452000 | 2452000 | 0 | لا | 0 |  | مسحوب | مدفوعات ساعات العمل | 91 | 100 | 2018-11-20 | 2020-03-20 | 2020-03-20 | 2020-03-20 |  |  |  |  | 12.4964 | 41.9028 | مسحوب | No
2100068191 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية عالية | 110000000 | 5500000 | 80116437.08 | 80116437.08 | 1010197593 | لا | 0 |  | جاري | تكلفة العمل المنجز | 72.84 | 72.84 | 2019-07-14 | 2024-05-18 | 2024-05-18 | 2024-05-18 |  |  |  |  | 39.8994 | 21.4292 | منتظم | No
2100004605 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 3399725 | 169986.25 | 1895390 | 1895390 | 4031054258 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 64 | 64 | 2014-06-19 | 2015-12-02 | 2021-06-29 | 2021-06-29 |  |  | اخرى |  | 39.3837 | 21.899 | مسحوب | No
2100080205 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية | 33398650 | 1669932.5 | 30735196.29 | 30735196.29 | 1131009235 | لا | 0 | 180709019608 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2014-05-21 | 2018-04-08 | 2020-11-23 | 2020-11-23 |  | 2018-04-08 | لا يوجد تأخير |  | 43.9553 | 26.3508 | منجز | No
2100080360 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 6079324.55 | 303966.2275 | 4649467.76 | 4388541.63 | 5950009685 | لا | 0 | 210501030518 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 99.94 | 100 | 2019-08-04 | 2020-07-22 | 2021-10-20 | 2021-10-20 | 2020-07-22 |  |  |  | 44.2386 | 17.5515 | منجز | No
2100034904 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 30678873.75 | 1533943.6875 | 21531243.11 | 21531243.11 | 5950010119 | لا | 0 | 221009014884 | جاري | الكميات التي تم تركيبها | 88 | 93 | 2019-04-07 | 2021-04-25 | 2023-03-30 | 2023-03-30 |  |  | اخرى |  | 44.2283 | 17.6129 | منتظم | No
2100008035 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 110831910.66 | 5541595.533 | 91609647.7 | 91609647.7 | 4031008077 | لا | 0 | 4046301 | منجز – استلام نهائي | تكلفة العمل المنجز | 76 | 76 | 2013-03-23 | 2015-09-21 | 2020-10-21 | 2020-10-21 | 2015-09-21 | 2021-10-31 | التنسيق مع أصحاب المصلحه (خدمات |  | 39.8641 | 21.3745 | منجز | No
2100014792 | أمانة / العاصمة المقدسة | أخرى | ذات اولوية عالية | 103360000 | 5168000 | 75498204.81 | 75498204.81 | 1010197593 | لا | 0 | 190201035622 | جاري | تكلفة العمل المنجز | 73.05 | 73.05 | 2019-07-14 | 2024-05-18 | 2024-05-18 | 2024-05-18 |  |  |  |  | 39.8517 | 21.3255 | خدمات عامة | No
2100102056 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 414289292.15 | 20714464.6075 | 399165769.98 | 392287700.077 | 4030082735 | لا | 0 |  | ايقاف جزئي | منهجية القيمة المكتسبة | 96 | 96 | 2014-01-21 | 2016-01-11 | 2023-06-30 | 2023-06-30 |  |  |  | أخرى | 42.4989 | 18.2169 | Failed | No
2100050540 | أمانة / جازان | تشييد | ذات اولوية عالية | 13574500 | 678725 | 13574497.15 | 13574497.15 | 1010193433 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-04-27 | 2019-04-12 | 2019-12-31 | 2019-12-31 | 2019-04-12 |  | اخرى |  | 42.5695 | 16.8889 | منجز | No
2100086435 | وزارة التعليم | تشييد | ذات اولوية عالية | 3720280 | 186014 | 2190358.6 | 2190358.6 | 4031053163 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 72 | 100 | 2014-01-02 | 2015-04-02 | 2023-11-10 | 2023-11-10 |  |  | ضعف كفاءة المقاول الفنية |  | 43.9544 | 26.3504 | مسحوب | No
2100048440 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 698000 | 34900 | 727939.6 | 658131.6 | 4601000966 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-11-18 | 2020-04-07 | 2020-07-13 | 2020-07-13 | 2020-04-07 |  | ضعف كفاءة المقاول الفنية |  | 39.1417 | 21.4931 | منجز | No
2100093402 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2299684 | 114984.2 | 1953211 | 1953211 | 1100254054 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2012-12-09 | 2014-02-25 | 2019-05-26 | 2019-05-26 | 2014-02-25 |  | ضعف كفاءة المقاول الفنية |  | 43.6565 | 26.1508 | منجز | No
2100099315 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1095248.02 | 54762.401 | 901516.06 | 901516.06 | 1010102014 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 90 | 100 | 2018-01-23 | 2018-07-17 | 2022-07-15 | 2022-07-15 | 2018-07-17 |  | ضعف كفاءة المقاول الفنية |  | 43.9544 | 26.3504 | منجز | No
2100033176 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 2271670 | 113583.5 | 732324 | 732324 | 4030182654 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 32 | 100 | 2015-11-02 | 2016-10-21 | 2016-12-04 | 2016-12-04 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.737 | 23.007 | مسحوب | No
2100050956 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 9777000 | 488850 | 1031205 | 1031205 | 4031045634 | لا | 0 | 1046256 | فسخ العقد | التكلفة المفوترة | 11.18 | 11.18 | 2015-11-18 | 2018-05-18 | 2018-05-18 | 2018-05-18 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.8521 | 21.3482 | مسحوب | No
2100085713 | وزارة التجارة | دراسة الجدوى | ذات اولوية عالية وعاجلة | 2452800 | 122640 | 2021564.55 | 2021564.55 | 1010348048 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-11-14 | 2020-11-13 | 2021-07-25 | 2021-07-25 |  | 2020-11-13 | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  |  |  | منجز | No
2100104926 | وزارة التعليم | تشييد | ذات اولوية عالية | 116720.38 | 5836.019 | 70973.07 | 60358.9 | 1131012642 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 95 | 100 | 2015-11-15 | 2017-11-04 | 2021-03-04 | 2021-03-04 | 2017-11-04 |  | ضعف كفاءة المقاول الفنية |  | 43.9544 | 26.3504 | منجز | No
2100029186 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 61901217 | 3095060.85 | 61901217 | 0 | 1010010466 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 87 | 10 | 2019-03-18 | 2022-02-12 | 2023-02-17 | 2023-02-17 |  |  |  |  | 46.0637 | 25.0976 | Failed | Yes
2100082316 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 7765619 | 388280.95 | 4470617 | 4470617 | 4030193194 | لا | 0 | 210909168719 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 54 | 99 | 2014-05-05 | 2015-10-18 | 2016-11-12 | 2016-11-12 | 2015-10-18 |  | اخرى |  |  |  | منجز | No
2100066640 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 3289270 | 164463.5 | 3291851.57 | 3291851.57 | 4601001792 | لا | 0 | 190901178777 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-01-24 | 2020-07-28 | 2021-09-30 | 2021-09-30 | 2020-07-28 |  | ضعف كفاءة المقاول الفنية |  | 40.7329 | 19.9223 | منجز | No
2100056140 | أمانة / جدة | دراسات هندسية | ذات اولوية متوسطة | 2346750 | 117337.5 | 2346750 | 2346750 | 4030282813 | لا | 0 |  | منجز – استلام نهائي | اخرى | 95 | 94 | 2020-01-26 | 2020-10-26 | 2020-10-18 | 2020-10-18 | 2020-10-26 | 2020-10-19 | اخرى |  | 39.1715 | 21.5049 | منجز | No
2100051203 | أمانة / جازان | تشييد | ذات اولوية عالية | 2600000 | 130000 | 1763580 | 1763580 | 5923455521 | لا | 0 | 180809062112 | مسحوب | تكلفة العمل المنجز | 68 | 100 | 2014-01-12 | 2015-01-06 | 2014-12-28 | 2014-12-28 |  |  | ضعف كفاءة المقاول الفنية |  | 42.9575 | 16.7105 | مسحوب | No
2100048425 | أمانة / جازان | تشييد | ذات اولوية عالية | 4989595 | 249479.75 | 2693452.36 | 2693452.36 | 5905007613 | لا | 0 | 181009193657 | فسخ العقد | الكميات التي تم تركيبها | 54 | 100 | 2014-11-07 | 2016-05-10 | 2021-06-16 | 2021-06-16 |  |  | اخرى |  | 42.5931 | 16.9224 | مسحوب | No
2100021954 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية وعاجلة | 381632457.42 | 19081622.871 | 340275008.96 | 340275008.96 | 1010004739 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 99.9 | 100 | 2016-10-20 | 2018-10-30 | 2021-04-30 | 2021-04-30 | 2018-10-30 | [5 empty] | منجز | No
2100099035 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 1725114.27 | 86255.7135 | 1725114.27 | 1725114.27 | 4030237556 | لا | 0 | 181109340192 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-09-27 | 2020-03-11 | 2020-07-06 | 2020-07-06 | 2020-03-11 |  | ضعف كفاءة المقاول الفنية |  | 41.4323 | 19.2807 | منجز | No
2100012795 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 2500000 | 125000 | 2500000 | 2500000 | 4605002907 | لا | 0 | 191101267486 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-10-01 | 2020-09-25 | 2020-09-25 | 2020-09-25 | 2020-09-25 |  |  |  | 41.0055 | 21.0563 | منجز | No
2100018686 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 5776340 | 288817 | 5776340 | 5776340 | 1010212192 | لا | 0 | 190309006052 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-08-26 | 2016-08-20 | 2016-08-20 | 2016-08-20 | 2016-08-20 |  |  |  | 42.8382 | 21.2587 | منجز | No
2100046432 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 9899998 | 494999.9 | 8154085.94 | 8154085.94 | 4032005233 | لا | 0 | 191109008487 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-01-09 | 2020-12-31 | 2020-12-31 | 2020-12-31 | 2020-12-31 |  | اخرى |  | 40.4455 | 21.2564 | منجز | No
2100024824 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 9124698 | 456234.9 | 8070866 | 8070866 | 4031046917 | لا | 0 | 190301025660 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 99 | 100 | 2018-11-30 | 2019-05-29 | 2022-01-01 | 2022-01-01 | 2019-05-29 |  | ضعف كفاءة المقاول الفنية |  | 42.02 | 21.9187 | منجز | No
2100107306 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البرية | تشييد | ذات اولوية متوسطة | 646044 | 32302.2 | 330130.5 | 0 | 3550122344 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-01-05 | 2020-08-11 | 2021-09-19 | 2021-09-19 | 2020-08-11 |  | تأخرصرف المستحقات المالية |  | 36.5323 | 28.3843 | منجز | Yes
2100109583 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية | 2393247.5 | 119662.375 | 2393247.5 | 2393247.5 | 1131023007 | لا | 0 | 181209406097 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 98.72 | 100 | 2017-12-18 | 2018-12-08 | 2020-04-07 | 2020-04-07 |  | 2018-12-08 | لا يوجد تأخير |  | 44.0155 | 26.3916 | منجز | No
2100010345 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات الجوية | تشييد | ذات اولوية متوسطة | 7679847 | 383992.35 | 5593290 | 5593290 | 2251043785 | لا | 0 | 190301064769 | جاري | الكميات التي تم تركيبها | 90 | 100 | 2019-08-25 | 2020-08-13 | 2022-04-30 | 2022-04-30 |  |  | لا يوجد تأخير |  | 36.5505 | 28.3972 | Failed | No
2100104506 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية وعاجلة | 70000000 | 3500000 | 66433898.24 | 66433898.24 | 1010262887 | لا | 0 | 180101000065 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-03-27 | 2020-08-29 | 2021-06-16 | 2021-06-16 | 2020-08-29 |  | لا يوجد تأخير |  | 43.4572 | 25.9077 | منجز | No
2100095384 | وزارة الصحة / القصيم | تشييد | ذات اولوية عالية | 41758080 | 2087904 | 13780166 | 13780166 | 1018000245 | لا | 0 | 181009159488 | مسحوب | تكلفة العمل المنجز | 42 | 100 | 2013-06-03 | 2015-05-01 | 2022-12-30 | 2022-12-30 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 43.9544 | 26.3504 | مسحوب | No
2100094743 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1499000 | 74950 | 41898 | 0 | 1010231660 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 5 | 100 | 2015-04-22 | 2016-07-15 | 2020-10-18 | 2020-10-18 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6679 | 24.7038 | مسحوب | Yes
2100106724 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | تشييد | ذات اولوية متوسطة | 18013113 | 900655.65 | 15842001 | 12126512.4 | 1010142553 | لا | 0 | 180709032253 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2012-05-05 | 2013-10-28 | 2022-04-30 | 2022-04-30 | 2013-10-28 |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | منجز | No
2100059360 | رئاسة أمن الدولة / المديرية العامة للمباحث | تشييد | ذات اولوية متوسطة | 4124020 | 206201 | 0 | 0 | 1131032707 | لا | 0 |  | ايقاف كلي | اخرى | 5 | 100 | 2018-09-03 | 2019-03-03 | 2022-06-01 | 2022-06-01 |  |  | اخرى |  |  |  | Failed | No
2100079752 | المؤسسة العامة للحبوب | تشييد | ذات اولوية عالية وعاجلة | 47900000 | 2395000 | 47900000 | 47900000 | 1010127334 | لا | 0 | 190309094379 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-11-28 | 2021-12-25 | 2021-12-15 | 2021-12-15 | 2021-12-25 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 43.8401 | 26.4586 | منجز | No
2100061084 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية متوسطة | 2918395 | 145919.75 | 2998467 | 2615238.17 | 1010102014 | لا | 0 | 180709019949 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2015-12-20 | 2016-10-10 | 2020-11-15 | 2020-11-15 |  | 2016-10-10 | لا يوجد تأخير |  | 43.9553 | 26.3508 | منجز | No
2100029094 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 14710275 | 735513.75 | 14710275 | 14710275 | 2060024520 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 92.17 | 100 | 2019-01-12 | 2020-12-20 | 2021-06-17 | 2021-06-17 | 2020-12-20 |  |  |  | 49.9982 | 26.773 | منجز | No
2100068375 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 3833708 | 191685.4 | 3833708 | 3833708 | 4030006066 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-09-24 | 2020-03-10 | 2021-06-14 | 2021-06-14 | 2020-03-10 |  |  |  | 41.2484 | 19.943 | منجز | No
2100066080 | أمانة / نجران | تشييد | ذات اولوية عالية | 10226880 | 511344 | 0 | 0 | 5950000083 | لا | 0 | 19040180025 | ايقاف كلي | تكلفة العمل المنجز | 0 | 0 | 2019-08-18 | 2020-12-18 | 2020-12-02 | 2020-12-02 |  |  | اخرى |  | 44.2518 | 17.5895 | Failed | No
2100025163 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 2173800 | 108690 | 1338000 | 1338000 | 4030237556 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 62 | 100 | 2015-03-01 | 2016-08-13 | 2019-10-20 | 2019-10-20 |  |  | ضعف كفاءة المقاول الفنية |  | 41.4768 | 19.9865 | مسحوب | No
2100060804 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية | 58518203.21 | 2925910.1605 | 49071112.904 | 49071112.904 | 3450002829 | لا | 0 | 180709022399 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 80.68 | 100 | 2013-05-06 | 2016-04-04 | 2020-06-04 | 2020-06-04 |  | 2016-04-04 | لا يوجد تأخير |  | 43.9544 | 26.3504 | منجز | No
2100087102 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية | 19999728.3 | 999986.415 | 17983191.05 | 17983191.05 | 2050003475 | لا | 0 | 180901077153 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-10-24 | 2021-03-28 | 2021-06-30 | 2021-06-30 |  | 2021-03-28 | لا يوجد تأخير |  | 43.9553 | 26.3508 | منجز | No
2100067745 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 6058800 | 302940 | 5963761 | 5963761 | 4031046580 | لا | 0 | 180701017173 | منجز – استلام نهائي | التكلفة المفوترة | 99.43 | 99.43 | 2019-09-30 | 2020-08-19 | 2021-07-05 | 2021-07-05 | 2020-08-19 | 2020-03-10 |  |  | 39.8647 | 21.3896 | منجز | No
2100051682 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 3339630 | 166981.5 | 3180600 | 3180600 | 1010137467 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-07-15 | 2020-07-03 | 2021-06-22 | 2021-06-22 | 2020-07-03 |  |  |  | 48.4855 | 27.4704 | منجز | No
2100015002 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 11478980 | 573949 | 8215480 | 8215480 | 3450007800 | لا | 0 | 190301057870 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 97 | 100 | 2018-09-29 | 2019-05-27 | 2023-05-31 | 2023-05-31 |  |  |  |  | 41.0334 | 30.971 | منتظم | No
2100094220 | وزارة الداخلية / المديرية العامة للدفاع المدني | تشييد | ذات اولوية عالية | 2674411 | 133720.55 | 2674411 | 2674411 | 1010174451 | لا | 0 | 200501011632 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2020-03-31 | 2021-05-18 | 2022-07-01 | 2022-07-01 | 2021-05-18 |  | اخرى |  | 39.9405 | 21.3031 | منجز | No
2100037505 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 1416220 | 70811 | 1075352 | 0 | 3350000631 | لا | 0 | 180909093539 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-06-28 | 2019-12-19 | 2022-01-05 | 2022-01-05 | 2019-12-19 |  |  |  | 42.1341 | 26.4987 | منجز | Yes
2100057632 | وزارة التعليم | تشييد | ذات اولوية عالية | 16175311.8 | 808765.59 | 892472.75 | 0 | 5950007285 | لا | 0 |  | مسحوب | التكلفة المفوترة | 9 | 100 | 2014-06-22 | 2016-06-10 | 2024-01-11 | 2024-01-11 |  |  | ضعف كفاءة المقاول الفنية |  | 42.6509 | 17.1567 | مسحوب | Yes
2100000766 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 3092922.6 | 154646.13 | 414200 | 414200 | 1010233819 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 17 | 100 | 2016-12-20 | 2017-12-15 | 2022-05-31 | 2022-05-31 |  |  | ضعف كفاءة المقاول الفنية |  | 40.0549 | 29.8587 | مسحوب | No
2100087942 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 4363912 | 218195.6 | 1582124 | 1582124 | 1010182198 | لا | 0 |  | جاري | التكلفة المفوترة | 75 | 100 | 2014-02-24 | 2015-04-20 | 2023-12-15 | 2023-12-15 |  |  | ضعف كفاءة المقاول الفنية |  | 43.9875 | 26.0873 | Failed | No
2100001525 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 32386653.12 | 1619332.656 | 18285302 | 18285302 | 1132002624 | لا | 0 |  | جاري | التكلفة المفوترة | 59 | 100 | 2013-09-29 | 2015-11-22 | 2022-08-08 | 2022-08-08 |  |  | ضعف كفاءة المقاول الفنية |  | 44.2014 | 25.8831 | Failed | No
2100003662 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 996841.13 | 49842.0565 | 0 | 0 | 1010223860 | لا | 0 |  | مسحوب | التكلفة المفوترة | 100 | 100 | 2005-12-30 | 2006-10-20 | 2006-10-20 | 2006-10-20 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.1634 | 18.1775 | مسحوب | No
2100190374 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية عالية وعاجلة | 1084105 | 54205.25 | 0 | 0 | 1010308213 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 30 | 100 | 2021-04-07 | 2021-08-02 | 2021-08-03 | 2021-08-03 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5889 | 16.9143 | مسحوب | No
2100060771 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية متوسطة | 564000 | 28200 | 564000 | 564000 | 5855033786 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-06-04 | 2018-11-28 | 2018-11-28 | 2018-11-28 | 2018-11-28 |  |  |  | 42.5921 | 18.238 | منجز | No
2100002800 | وزارة التعليم | تشييد | ذات اولوية عالية | 2433950 | 121697.5 | 2309501.97 | 2309501.97 | 5800006150 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2016-01-24 | 2019-01-03 | 2019-01-03 | 2019-01-03 | 2019-01-03 |  | اخرى |  | 41.4779 | 20.0185 | منجز | No
2100006764 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 4321640.4 | 216082.02 | 2056128 | 2056128 | 2050052248 | لا | 0 |  | جاري | التكلفة المفوترة | 58 | 100 | 2015-12-16 | 2017-05-09 | 2018-08-02 | 2018-08-02 |  |  | ضعف كفاءة المقاول الفنية |  | 50.52 | 26.4048 | Failed | No
2100006904 | وزارة الموارد البشرية والتنمية الإجتماعية | إشراف | ذات اولوية منخفضة | 796000 | 39800 | 1014400 | 1014400 | 1010328167 | لا | 0 | 190309003228 | مسحوب | الكميات التي تم تركيبها | 94 | 100 | 2015-02-09 | 2017-01-17 | 2022-07-13 | 2022-07-13 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 50.1041 | 26.3966 | مسحوب | No
2100013565 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 4778340 | 238917 | 0 | 0 | 5850000579 | لا | 0 | 201009142478 | مسحوب | تكلفة العمل المنجز | 3 | 100 | 2014-01-02 | 2015-12-11 | 2020-08-06 | 2020-08-06 |  |  | ضعف كفاءة المقاول الفنية |  | 39.2264 | 21.5208 | مسحوب | No
2100002936 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 6739597.92 | 336979.896 | 2693784.99 | 2099999.37 | 4030052981 | لا | 0 | 200609154170 | مسحوب | التكلفة المفوترة | 48 | 100 | 2015-11-22 | 2017-08-13 | 2022-03-03 | 2022-03-03 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | مسحوب | No
2100079715 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية عالية | 24016300 | 1200815 | 20500212.63 | 20500212.63 | 1010272491 | لا | 0 | 180709022835 | جاري | الكميات التي تم تركيبها | 81 | 100 | 2015-04-25 | 2018-07-18 | 2018-07-19 | 2018-07-19 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0289 | 20.7494 | Failed | No
2100005762 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 9160072.45 | 458003.6225 | 7197701.6 | 7197701.6 | 1010023313 | لا | 0 | 190209015727 | مسحوب | التكلفة المفوترة | 65 | 100 | 2014-07-02 | 2016-06-21 | 2023-08-08 | 2023-08-08 |  |  | ضعف كفاءة المقاول الفنية |  | 40.2691 | 20.1489 | مسحوب | No
2100000291 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البرية | تشييد | ذات اولوية متوسطة | 17255585 | 862779.25 | 15522736 | 15522736 | 1010177961 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2017-11-21 | 2019-05-20 | 2022-12-31 | 2022-12-31 | 2019-05-20 |  | تأخرصرف المستحقات المالية |  | 50.1597 | 26.5161 | منجز | No
2100005972 | وزارة التعليم | تشييد | ذات اولوية عالية | 17678559.08 | 883927.954 | 17678559.08 | 17678559.08 | 1010233305 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-12-13 | 2018-03-03 | 2019-11-21 | 2019-11-21 | 2018-03-03 |  |  |  | 38.0652 | 24.1313 | منجز | No
2100005445 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 7076399.14 | 353819.957 | 6910486.81 | 6910486.81 | 2250001372 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-11-16 | 2018-03-30 | 2019-09-15 | 2019-09-15 | 2018-03-30 |  |  |  | 49.5604 | 25.3897 | منجز | No
2100053001 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 3250030 | 162501.5 | 3250030 | 3250030 | 1116005887 | لا | 0 | 181009153927 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-05-23 | 2019-05-18 | 2019-05-18 | 2019-05-18 | 2019-05-18 |  |  |  | 41.7465 | 22.4323 | منجز | No
2100007346 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 14883796.4 | 744189.82 | 7628168 | 7628168 | 1132002624 | لا | 0 | 190309000181 | جاري | التكلفة المفوترة | 80 | 100 | 2014-05-26 | 2016-08-13 | 2022-02-09 | 2022-02-09 |  |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | Failed | No
2100002052 | أمانة / الباحة | تشييد | ذات اولوية عالية | 7320298 | 366014.9 | 3713232.5 | 3713232.5 | 5810001890 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-01-23 | 2019-01-12 | 2022-09-01 | 2022-09-01 | 2019-01-12 |  | ضعف كفاءة المقاول الفنية |  | 41.3882 | 20.3871 | منجز | No
2100007291 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 9433831 | 471691.55 | 820306.72 | 0 | 4030052981 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 9 | 100 | 2015-03-22 | 2017-03-11 | 2023-05-10 | 2023-05-10 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.5429 | 16.8808 | مسحوب | Yes
2100008492 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 10542698.16 | 527134.908 | 4141495.1329 | 0 | 1116004360 | لا | 0 | 190309007777 | مسحوب | التكلفة المفوترة | 44 | 100 | 2012-11-16 | 2014-11-06 | 2023-05-10 | 2023-05-10 |  |  | ضعف كفاءة المقاول الفنية |  | 41.4779 | 20.0185 | مسحوب | Yes
2100042103 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 10477567.92 | 523878.396 | 152698 | 152698 | 1010081983 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 2 | 100 | 2015-05-13 | 2017-05-02 | 2022-01-02 | 2022-01-02 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5604 | 25.3897 | مسحوب | No
2100010021 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1911704 | 95585.2 | 0 | 0 | 2511008817 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0 | 100 | 2011-02-08 | 2012-02-03 | 2021-01-18 | 2021-01-18 |  |  | ضعف كفاءة المقاول الفنية |  | 48.7241 | 27.8719 | مسحوب | No
2100008901 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 12740958.68 | 637047.934 | 696000 | 0 | 1010046644 | لا | 0 |  | مسحوب | التكلفة المفوترة | 19 | 100 | 2016-05-03 | 2018-04-23 | 2018-04-23 | 2018-04-23 |  |  | ضعف كفاءة المقاول الفنية |  | 50.5083 | 26.4378 | مسحوب | Yes
2100010916 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 7903596.68 | 395179.834 | 3127828.93 | 3127828.93 | 2031040463 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 45 | 100 | 2012-11-11 | 2014-11-01 | 2021-03-17 | 2021-03-17 |  |  | ضعف كفاءة المقاول الفنية |  | 45.975 | 28.4334 | مسحوب | No
2100011841 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 3485196 | 174259.8 | 1906866 | 1906866 | 2050052248 | لا | 0 |  | مسحوب | التكلفة المفوترة | 67 | 94 | 2016-02-29 | 2017-02-23 | 2019-12-17 | 2019-12-17 |  |  | ضعف كفاءة المقاول الفنية |  | 49.2224 | 26.947 | مسحوب | No
2100010172 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 1734839 | 86741.95 | 269520 | 269520 | 5801006916 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 15.5 | 15.5 | 2009-01-20 | 2010-01-20 | 2019-07-01 | 2019-07-01 |  |  | ضعف كفاءة المقاول الفنية |  | 41.661 | 19.9966 | مسحوب | No
2100009741 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 4936259 | 246812.95 | 4936259 | 4936259 | 4653000386 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-06-23 | 2022-09-04 | 2022-05-20 | 2022-05-20 | 2022-09-04 |  |  |  | 39.6196 | 24.4667 | منجز | No
2100011012 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 7199514.11 | 359975.7055 | 0 | 0 | 2251033167 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 25 | 100 | 2008-05-11 | 2009-12-21 | 2023-05-10 | 2023-05-10 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.5429 | 16.8808 | مسحوب | No
2100011082 | وزارة الرياضة | تشييد | ذات اولوية متوسطة | 78918675.25 | 3945933.7625 | 48738419 | 48738419 | 1010015350 | لا | 0 | 180909079252 | جاري | الكميات التي تم تركيبها | 91 | 100 | 2011-10-15 | 2014-03-17 | 2020-08-12 | 2020-08-12 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | Failed | No
2100014000 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1216220 | 60811 | 372346.18 | 372346.18 | 4603008005 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-01-29 | 2020-01-17 | 2020-01-18 | 2020-01-18 | 2020-01-17 |  | تأخرصرف المستحقات المالية |  | 39.8483 | 21.402 | منجز | No
2100013521 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 433000 | 21650 | 419958 | 0 | 4603003036 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-11-11 | 2019-10-31 | 2020-11-10 | 2020-11-10 | 2019-10-31 |  | ضعف كفاءة المقاول الفنية |  | 41.0787 | 19.1281 | منجز | Yes
2100011045 | وزارة التعليم | تشييد | ذات اولوية عالية | 13080164.78 | 654008.239 | 7142607 | 6644764.55 | 4650049177 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-02-19 | 2017-02-09 | 2021-11-10 | 2021-11-10 | 2017-02-09 |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | منجز | No
2100083440 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 2200000 | 110000 | 2200000 | 990585 | 4037000639 | لا | 0 | 190401135345 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-02-10 | 2020-02-05 | 2021-07-01 | 2021-07-01 | 2020-02-05 |  |  |  | 41.7312 | 22.4283 | منجز | No
2100052791 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 828567 | 41428.35 | 828567 | 828567 | 5864034727 | لا | 0 | 190201023316 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-01-07 | 2020-06-21 | 2020-06-20 | 2020-06-20 | 2020-06-21 |  | اخرى |  | 39.1932 | 21.5485 | منجز | No
2100009365 | جامعة حائل | تشييد | ذات اولوية عالية وعاجلة | 102008194 | 5100409.7 | 26168437.51 | 26168437.51 | 1010012687 | لا | 0 | 190309092074 | جاري | تكلفة العمل المنجز | 25.1 | 100 | 2013-04-15 | 2018-06-22 | 2022-11-30 | 2022-11-30 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.7054 | 27.6816 | Failed | No
2100014022 | أمانة / الباحة | تشييد | ذات اولوية عالية | 616241 | 30812.05 | 616241 | 616241 | 5805010039 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-11-25 | 2019-11-15 | 2019-09-15 | 2019-09-15 | 2019-11-15 |  |  |  | 41.4727 | 20.0159 | منجز | No
2100018465 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 498750 | 24937.5 | 498750 | 498750 | 1010064067 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-05-10 | 2016-05-15 | 2016-05-15 | 2016-05-15 | 2016-05-15 |  |  |  | 41.478 | 20.0307 | منجز | No
2100012784 | أمانة / جازان | تشييد | ذات اولوية عالية | 2450080 | 122504 | 1225040 | 1225040 | 5852000047 | لا | 0 | 181209494644 | منجز – استلام نهائي | تكلفة العمل المنجز | 95 | 100 | 2013-01-07 | 2014-01-07 | 2014-07-04 | 2014-07-04 |  | 2014-01-07 | ضعف كفاءة المقاول الفنية |  | 42.1257 | 17.989 | منجز | No
2100016844 | جامعة الملك فيصل | تشييد | ذات اولوية عالية | 2669824 | 133491.2 | 2669824 | 2669824 | 2252026106 | لا | 0 | 181109353722 | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2017-12-10 | 2018-07-04 | 2017-07-04 | 2017-07-04 |  | 2018-07-04 | تأخرصرف المستحقات المالية |  | 49.5604 | 25.3897 | منجز | No
2100018454 | أمانة / حائل | دراسة الجدوى | ذات اولوية متوسطة | 1245000 | 62250 | 1245000 | 1245000 | 1010463231 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-03-07 | 2021-02-23 | 2021-09-16 | 2021-09-16 | 2021-02-23 |  | ضعف كفاءة المقاول الفنية |  | 42.9029 | 28.2415 | منجز | No
2100081815 | أمانة / عسير | تشييد | ذات اولوية عالية | 3036810 | 151840.5 | 382042 | 0 | 5858010028 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 10 | 100 | 2015-10-26 | 2016-10-27 | 2021-01-20 | 2021-01-20 |  |  | تأخرصرف المستحقات المالية |  | 43.5126 | 17.6602 | مسحوب | Yes
2100080662 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1254250 | 62712.5 | 987650 | 987650 | 4035000994 | لا | 0 | 190301028685 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-12-20 | 2019-12-15 | 2019-12-15 | 2019-12-15 | 2019-12-15 |  |  |  | 40.8329 | 20.7219 | منجز | No
2100015772 | هيئة المدن الصناعية ومناطق التقنية | تشييد | ذات اولوية عالية | 131335659 | 6566782.95 | 110801065 | 110801065 | 1010012911 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 87 | 92 | 2019-12-05 | 2021-12-04 | 2023-03-04 | 2023-03-04 |  |  | لا يوجد تأخير |  | 21.577 | 40.7972 | منتظم | No
2100004712 | جامعة الملك فيصل | تشييد | ذات اولوية عالية | 200884464 | 10044223.2 | 200884464 | 200884464 | 2050018864 | لا | 0 | 180809056625 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2013-01-13 | 2016-01-13 | 2019-03-12 | 2019-03-12 | 2016-01-13 |  | تأخرصرف المستحقات المالية |  | 49.5604 | 25.3897 | منجز | No
2100020204 | أمانة / جازان | تشييد | ذات اولوية عالية | 482402 | 24120.1 | 149000 | 149000 | 5911028222 | لا | 0 | 180809062234 | مسحوب | تكلفة العمل المنجز | 31 | 100 | 2015-11-08 | 2016-11-02 | 2019-11-03 | 2019-11-03 |  |  | اخرى |  | 42.9528 | 16.7102 | مسحوب | No
2100020484 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2883068 | 144153.4 | 2254105.98 | 2254105.98 | 1010008713 | لا | 0 |  | مسحوب | التكلفة المفوترة | 80 | 100 | 2010-09-18 | 2011-09-02 | 2021-11-14 | 2021-11-14 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 43.1379 | 18.0853 | مسحوب | No
2100019670 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 1508535 | 75426.75 | 1357681.5 | 1357681.5 | 4030169145 | لا | 0 | 200509039588 | منجز – استلام ابتدائي | اخرى | 65 | 70 | 2020-03-07 | 2021-05-24 | 2021-05-24 | 2021-05-24 | 2021-05-24 |  | اخرى |  | 40.8643 | 20.4189 | منجز | No
2100017710 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 2997100 | 149855 | 2533820 | 2533820 | 3351005488 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-02-18 | 2022-12-08 | 2021-01-15 | 2021-01-15 | 2022-12-08 |  |  |  | 39.5546 | 24.5657 | منجز | No
2100017975 | جامعة نجران | تشييد | ذات اولوية عالية | 89993398 | 4499669.9 | 57727671.6 | 57727671.6 | 2066001761 | لا | 0 | 190709179691 | جاري | الكميات التي تم تركيبها | 79 | 100 | 2013-06-23 | 2016-05-20 | 2022-05-13 | 2022-05-13 |  |  | تأخرصرف المستحقات المالية |  | 44.2341 | 17.5757 | Failed | No
2100027646 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1396700 | 69835 | 550433.19 | 0 | 4603003036 | لا | 0 |  | جاري | تكلفة العمل المنجز | 45 | 70 | 2018-11-22 | 2020-11-22 | 2021-12-12 | 2021-12-12 |  |  | سوء التخطيط الاولي للمشروع |  | 41.0787 | 19.1281 | Failed | Yes
2100021991 | وزارة الخارجية | تشييد | ذات اولوية عالية | 57322668.75 | 2866133.4375 | 57322668.75 | 57322668.75 | 0 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-07-09 | 2020-03-09 | 2021-02-09 | 2021-02-09 | 2020-03-09 |  |  |  | 114.9374 | 4.9223 | منجز | No
2100092735 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 589871.1 | 29493.555 | 589871.1 | 589871.1 | 4032025297 | لا | 0 | 190901209116 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-03-18 | 2020-03-12 | 2020-03-12 | 2020-03-12 | 2020-03-12 |  |  |  | 41.6263 | 21.2068 | منجز | No
2100021523 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 3659542 | 182977.1 | 1319398.3 | 1319398.3 | 4032021347 | لا | 0 | 191001240050 | مسحوب | تكلفة العمل المنجز | 51 | 100 | 2015-01-26 | 2015-12-12 | 2022-12-31 | 2022-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 40.4349 | 22.4868 | مسحوب | No
2100020226 | أمانة / الجوف | تشييد | ذات اولوية عالية | 2650245 | 132512.25 | 2650245 | 2650245 | 3452005817 | لا | 0 | 190401045137 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-03-27 | 2019-09-19 | 2019-09-20 | 2019-09-20 | 2019-09-19 |  |  |  | 37.3578 | 31.3253 | منجز | No
2100025104 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 2867124 | 143356.2 | 1060835 | 1060835 | 5950010447 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 37 | 100 | 2010-11-18 | 2011-09-14 | 2022-03-30 | 2022-03-30 |  |  | ضعف كفاءة المقاول الفنية |  | 42.6284 | 17.1547 | Failed | No
2100021921 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 13890271.84 | 694513.592 | 2489280 | 0 | 4650020435 | لا | 0 |  | مسحوب | التكلفة المفوترة | 19 | 100 | 2013-08-23 | 2015-05-16 | 2023-11-15 | 2023-11-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | Yes
2100024511 | أمانة / تبوك | تشييد | ذات اولوية عالية | 1025100 | 51255 | 0 | 0 | 3550022695 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 1 | 1 | 2015-04-01 | 2015-12-01 | 2020-12-31 | 2020-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 38.5165 | 27.6122 | مسحوب | No
2100090705 | أمانة / عسير | تشييد | ذات اولوية عالية | 2791747 | 139587.35 | 391386 | 391386 | 5856255454 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 25 | 100 | 2014-12-28 | 2016-02-11 | 2019-11-21 | 2019-11-21 |  |  | تأخرصرف المستحقات المالية |  | 42.6768 | 18.5817 | مسحوب | No
2100025491 | أمانة / جدة | تشييد | ذات اولوية عالية | 6824682 | 341234.1 | 3560772.98 | 483849.57 | 2511007979 | لا | 0 | 190201010274 | جاري | تكلفة العمل المنجز | 56 | 100 | 2019-05-28 | 2020-09-11 | 2021-01-05 | 2021-01-05 |  |  | اخرى |  | 39.2338 | 21.5028 | Failed | No
2100008293 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | تشييد | ذات اولوية عالية وعاجلة | 85060450 | 4253022.5 | 68999796.93 | 68999796.93 | 1010047800 | لا | 0 | 180701025957 | جاري | تكلفة العمل المنجز | 99 | 100 | 2018-11-21 | 2020-05-14 | 2023-02-28 | 2023-02-28 |  |  | تأخرصرف المستحقات المالية |  | 43.9544 | 26.3504 | Failed | No
2100080286 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 8787700 | 439385 | 639320 | 639320 | 4650003908 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 7 | 100 | 2013-08-24 | 2014-08-12 | 2014-08-12 | 2014-08-12 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6586 | 24.3784 | مسحوب | No
2100023866 | وزارة الموارد البشرية والتنمية الإجتماعية | تشييد | ذات اولوية منخفضة | 25625130 | 1281256.5 | 18467694.38 | 18467694.38 | 2051027988 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 82 | 100 | 2013-06-29 | 2016-05-27 | 2022-10-20 | 2022-10-20 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 50.1693 | 26.3745 | مسحوب | No
2100097576 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 5032547.49 | 251627.3745 | 4551330.09 | 4551330.09 | 4032030986 | لا | 0 | 191101045992 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-10-06 | 2020-09-30 | 2020-09-30 | 2020-09-30 | 2020-09-30 |  |  |  | 40.4128 | 21.2812 | منجز | No
2100024673 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 678876 | 33943.8 | 566562.58 | 566562.58 | 5810010448 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 84 | 84 | 2018-11-25 | 2019-08-18 | 2019-08-22 | 2019-08-22 | 2019-08-18 |  |  |  | 41.6556 | 20.2818 | منجز | No
2100024625 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البرية | تشييد | ذات اولوية متوسطة | 13074940 | 653747 | 9271699.5 | 9271699.5 | 1010206690 | لا | 0 | 200309065823 | جاري | تكلفة العمل المنجز | 86 | 100 | 2019-09-28 | 2021-03-21 | 2023-04-29 | 2023-04-29 |  |  | لا يوجد تأخير |  | 42.5759 | 16.9162 | Failed | No
2100024872 | أمانة / الباحة | تشييد | ذات اولوية عالية | 643000 | 32150 | 643000 | 643000 | 4601002260 | لا | 0 | 190301092387 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-09-27 | 2019-10-26 | 2022-08-01 | 2022-08-01 | 2019-10-26 |  | تأخرصرف المستحقات المالية |  | 41.057 | 20.2337 | منجز | No
2100029072 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 17334455 | 866722.75 | 9960000 | 9960000 | 4031045075 | لا | 0 | 191201035508 | ايقاف كلي | تكلفة العمل المنجز | 68 | 100 | 2019-10-29 | 2020-07-25 | 2022-01-01 | 2022-01-01 |  |  |  |  | 39.852 | 21.365 | Failed | No
2100028324 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 10100947.8 | 505047.39 | 3696020 | 3696020 | 1132000522 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 60 | 100 | 2013-10-20 | 2015-10-20 | 2020-12-14 | 2020-12-14 |  |  | ضعف كفاءة المقاول الفنية |  | 43.9544 | 26.3504 | مسحوب | No
2100030236 | أمانة / جازان | تشييد | ذات اولوية عالية | 2198880 | 109944 | 0 | 0 | 5855049165 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 0 | 100 | 2015-10-25 | 2016-10-19 | 2016-10-19 | 2016-10-19 |  |  | تأخرصرف المستحقات المالية |  | 42.9556 | 16.711 | مسحوب | No
2100025561 | أمانة / جازان | تشييد | ذات اولوية عالية | 1941655 | 97082.75 | 1010680 | 1010680 | 5855037133 | لا | 0 | 180909110224 | مسحوب | تكلفة العمل المنجز | 52 | 100 | 2015-10-15 | 2016-10-20 | 2020-11-19 | 2020-11-19 |  |  | اخرى |  | 42.5796 | 16.8817 | مسحوب | No
2100028991 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1890500 | 94525 | 41862 | 0 | 1010168999 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-01-14 | 2015-12-30 | 2019-10-02 | 2019-10-02 | 2015-12-30 |  | ضعف كفاءة المقاول الفنية |  | 46.6754 | 24.7119 | منجز | Yes
2100026891 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 374499 | 18724.95 | 374499 | 374499 | 4031046917 | لا | 0 | 200601068673 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-11-25 | 2019-10-03 | 2019-10-03 | 2019-10-03 | 2019-10-03 |  | ضعف كفاءة المقاول الفنية |  | 42.0282 | 21.9222 | منجز | No
2100082364 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 449400 | 22470 | 148601.25 | 148601.25 | 5855027156 | لا | 0 | 191001089445 | مسحوب | تكلفة العمل المنجز | 56 | 100 | 2018-06-26 | 2019-11-22 | 2022-12-31 | 2022-12-31 |  |  | اخرى |  | 42.1761 | 22.7203 | مسحوب | No
2100074874 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 365455 | 18272.75 | 365455 | 365455 | 4601002288 | لا | 0 | 181109350061 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-05-02 | 2018-10-29 | 2019-10-29 | 2019-10-29 | 2018-10-29 |  |  |  | 40.8095 | 20.9436 | منجز | No
2100027134 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 94994220 | 4749711 | 41729 | 0 | 1010202928 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 92 | 100 | 2014-11-10 | 2016-10-30 | 2020-03-25 | 2020-03-25 |  |  | ضعف كفاءة المقاول الفنية |  | 47.3062 | 24.1693 | Failed | Yes
2100033320 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 1409351.01 | 70467.5505 | 0.01 | 0.01 | 4030168595 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 15 | 100 | 2014-12-14 | 2015-12-05 | 2020-06-12 | 2020-06-12 |  |  | ضعف كفاءة المقاول الفنية |  | 37.6889 | 28.3888 | مسحوب | No
2100032152 | أمانة / تبوك | تشييد | ذات اولوية عالية | 2956919 | 147845.95 | 1803720 | 1803720 | 4650038906 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 65 | 100 | 2015-03-28 | 2016-09-18 | 2021-08-01 | 2021-08-01 |  |  | ضعف كفاءة المقاول الفنية |  | 34.9531 | 29.305 | مسحوب | No
2100033051 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 12652310 | 632615.5 | 12652310 | 12652310 | 1010052246 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-11-07 | 2022-04-04 | 2021-09-08 | 2021-09-08 | 2022-04-04 |  | ضعف كفاءة المقاول الفنية |  | 39.5689 | 24.5395 | منجز | No
2100033106 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 3897168 | 194858.4 | 3897168 | 3897168 | 4030006066 | لا | 0 | 191001264766 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-12-17 | 2020-06-09 | 2020-06-09 | 2020-06-09 | 2020-06-09 |  | ضعف كفاءة المقاول الفنية |  | 41.0712 | 20.4631 | منجز | No
2100033003 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 2668300 | 133415 | 0 | 0 | 4035000994 | لا | 0 | 200701164749 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-09-19 | 2020-09-13 | 2022-05-31 | 2022-05-31 | 2020-09-13 |  | ضعف كفاءة المقاول الفنية |  | 41.0695 | 20.4655 | منجز | No
2100032852 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات الجوية | تشييد | ذات اولوية متوسطة | 6897324 | 344866.2 | 3323403 | 3323403 | 1010214056 | لا | 0 | 181109307272 | جاري | الكميات التي تم تركيبها | 63 | 100 | 2017-12-29 | 2019-06-14 | 2022-06-30 | 2022-06-30 |  |  | ضعف كفاءة المقاول الفنية |  | 39.164 | 21.4957 | Failed | No
2100035652 | أمانة / تبوك | تشييد | ذات اولوية عالية وعاجلة | 12789400 | 639470 | 12789400 | 11510460 | 4030140655 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-02-15 | 2020-05-10 | 2021-01-24 | 2021-01-24 | 2020-05-10 |  |  |  | 36.5908 | 28.3775 | منجز | No
2100035523 | أمانة / تبوك | تشييد | لم تعد تحتاجها الجهة | 2113351 | 105667.55 | 1672179 | 1672179 | 3553000311 | لا | 0 | 181009142084 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-10-11 | 2016-09-28 | 2021-09-01 | 2021-09-01 | 2016-09-28 |  | ضعف كفاءة المقاول الفنية |  | 34.9451 | 29.2864 | منجز | No
2100034101 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 1000000 | 50000 | 926544.93 | 926544.93 | 4030138666 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 90.23 | 90.23 | 2014-11-01 | 2016-10-11 | 2021-07-01 | 2021-07-01 | 2016-10-11 |  |  |  | 40.0056 | 21.989 | منجز | No
2100034171 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 8184100 | 409205 | 3834766 | 3834766 | 4030142592 | لا | 0 | 190609009469 | فسخ العقد | الكميات التي تم تركيبها | 63 | 100 | 2015-05-19 | 2017-04-27 | 2017-04-27 | 2017-04-27 |  |  | تأخرصرف المستحقات المالية |  | 38.8406 | 23.0838 | مسحوب | No
2100034731 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية عالية | 5550000 | 277500 | 1360556 | 1360556 | 4031041927 | لا | 0 | 181101322504 | مسحوب | تكلفة العمل المنجز | 33.69 | 33.69 | 2019-06-13 | 2021-05-21 | 2021-08-19 | 2021-08-19 |  |  |  |  | 39.8939 | 21.4096 | مسحوب | No
2100033924 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 1489500 | 74475 | 1489500 | 1489500 | 5810001890 | لا | 0 | 210601194728 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-11-24 | 2020-11-23 | 2022-09-01 | 2022-09-01 | 2020-11-23 |  |  |  | 41.468 | 19.9903 | منجز | No
2100087496 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية وعاجلة | 18007016.2 | 900350.81 | 14255950.928 | 14255950.928 | 1131005189 | لا | 0 | 180709019613 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 94.5 | 100 | 2013-01-09 | 2014-06-25 | 2021-10-07 | 2021-10-07 | 2014-06-25 |  | لا يوجد تأخير |  | 43.6349 | 26.4729 | منجز | No
2100041543 | وكالة / الإسكان | تشييد | ذات اولوية متوسطة | 136645742.88 | 6832287.144 | 56941349.48 | 56941349.48 | 5855000147 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 82 | 100 | 2019-09-02 | 2021-02-23 | 2023-04-30 | 2023-04-30 |  |  | أوامر تغيير | أخرى |  |  | متأخر | No
2100034322 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 3715005 | 185750.25 | 2244280 | 1608316 | 5950006647 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 97 | 100 | 2019-07-06 | 2020-03-03 | 2020-03-02 | 2020-03-02 | 2020-03-03 |  |  |  | 44.2268 | 17.5301 | منجز | No
2100036396 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 1242000 | 62100 | 1242000 | 943854 | 5800010841 | لا | 0 | 190401123941 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-10-09 | 2019-09-30 | 2021-06-07 | 2021-06-07 | 2019-09-30 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 41.4662 | 20.0126 | منجز | No
2100035044 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 1960616 | 98030.8 | 174101.71 | 174101.71 | 5800010527 | لا | 0 | 181109340300 | مسحوب | تكلفة العمل المنجز | 14 | 100 | 2018-10-07 | 2020-09-15 | 2020-09-15 | 2020-09-15 |  |  | ضعف كفاءة المقاول الفنية |  | 40.8642 | 20.4208 | مسحوب | No
2100035291 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 593775 | 29688.75 | 622049.99 | 622049.99 | 4601002260 | لا | 0 | 181209459943 | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2018-09-08 | 2020-08-17 | 2020-08-18 | 2020-08-18 | 2020-08-17 | 2020-08-18 | ضعف كفاءة المقاول الفنية |  | 40.8759 | 20.4157 | منجز | No
2100061515 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية | 39500000 | 1975000 | 39000500 | 39000500 | 1010188588 | لا | 0 | 180809044710 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-03-29 | 2019-03-19 | 2020-12-07 | 2020-12-07 | 2019-03-19 |  | لا يوجد تأخير |  | 43.9875 | 26.0873 | منجز | No
2100038953 | وزارة الداخلية / مديرية الأمن العام | تشييد | ذات اولوية متوسطة | 2587116 | 129355.8 | 2412403.95 | 2412403.95 | 3350012618 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-03-15 | 2021-03-15 | 2021-03-15 | 2021-03-15 | 2021-03-15 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 40.2806 | 26.9758 | منجز | No
2100036805 | أمانة / جازان | تشييد | ذات اولوية عالية | 33710385.738 | 1685519.2869 | 33710385.74 | 33710385.74 | 5900007895 | لا | 0 | 181109371318 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2010-12-17 | 2012-06-09 | 2020-01-20 | 2020-01-20 | 2012-06-09 |  | اخرى |  | 42.929 | 16.6002 | منجز | No
2100036201 | أمانة / تبوك | تشييد | لم تعد تحتاجها الجهة | 2585690.47 | 129284.5235 | 875516.7 | 875516.7 | 4030222353 | لا | 0 | 181009140333 | مسحوب | الكميات التي تم تركيبها | 34 | 45 | 2014-08-17 | 2015-11-10 | 2020-11-11 | 2020-11-11 |  |  | ضعف كفاءة المقاول الفنية |  | 37.6847 | 28.3938 | مسحوب | No
2100037085 | أمانة / تبوك | تشييد | لم تعد تحتاجها الجهة | 5184190 | 259209.5 | 4743346.5 | 4743346.5 | 1010255485 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-11-13 | 2020-05-02 | 2020-05-01 | 2020-05-01 | 2020-05-02 |  |  |  | 36.5614 | 28.376 | منجز | No
2100036853 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 4225452 | 211272.6 | 3803338.09 | 3803338.09 | 4030159820 | لا | 0 |  | جاري | تكلفة العمل المنجز | 95 | 100 | 2019-02-18 | 2021-02-18 | 2022-06-15 | 2022-06-15 |  |  | ضعف كفاءة المقاول الفنية |  | 40.4593 | 20.3036 | Failed | No
2100037295 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1304010 | 65200.5 | 1304010 | 1304010 | 4046001694 | لا | 0 | 190301010437 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-12-04 | 2020-08-17 | 2020-11-15 | 2020-11-15 | 2020-08-17 |  | ضعف كفاءة المقاول الفنية |  | 41.7482 | 22.4278 | منجز | No
2100035943 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 8398304 | 419915.2 | 8398304 | 8398304 | 3350018969 | لا | 0 | 180909106716 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 63 | 2015-08-02 | 2017-11-21 | 2021-02-25 | 2021-02-25 | 2017-11-21 |  | تأخرصرف المستحقات المالية |  | 40.958 | 27.9983 | منجز | No
2100037450 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 2766679.13 | 138333.9565 | 1185764.5 | 1185764.5 | 5805010799 | لا | 0 | 210509092315 | ايقاف كلي | تكلفة العمل المنجز | 50 | 78 | 2015-10-18 | 2016-10-06 | 2022-09-09 | 2022-09-09 |  |  |  |  | 41.4661 | 20.0131 | Failed | No
2100039001 | أمانة / جدة | تشييد | ذات اولوية عالية وعاجلة | 119700000 | 5985000 | 85637745.81 | 83425323.47 | 1010011560 | لا | 0 | 181209488356 | جاري | تكلفة العمل المنجز | 99 | 100 | 2018-09-30 | 2019-06-30 | 2020-06-28 | 2020-06-28 |  |  | أوامر سامية | أخرى | 39.2039 | 21.5573 | Failed | No
2100040003 | شركة الكهرباء | تشييد | ذات اولوية متوسطة | 92768669 | 4638433.45 | 82661521 | 82661521 | 1010090181 | لا | 0 |  | جاري | اخرى | 98 | 100 | 2015-11-12 | 2019-03-30 | 2022-08-30 | 2022-08-30 |  |  | اخرى |  | 39.8398 | 21.3855 | متأخر | No
2100044192 | أمانة / الباحة | تشييد | ذات اولوية عالية وعاجلة | 19226513.48 | 961325.674 | 4777942.05 | 4777942.05 | 1010152168 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 24 | 100 | 2014-02-14 | 2016-01-23 | 2016-06-23 | 2016-06-23 |  |  | ضعف كفاءة المقاول الفنية |  | 41.2864 | 20.1072 | مسحوب | No
2100039255 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية متوسطة | 12945450 | 647272.5 | 11552458.25 | 11552458.25 | 1134000066 | لا | 0 | 180709019614 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 88.76 | 100 | 2014-05-15 | 2015-05-05 | 2020-03-09 | 2020-03-09 |  | 2015-05-05 | لا يوجد تأخير |  | 43.5613 | 26.1181 | منجز | No
2100043492 | أمانة / عسير | تشييد | ذات اولوية عالية | 3379018 | 168950.9 | 0 | 0 | 2051035036 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 65 | 100 | 2019-01-06 | 2020-12-28 | 2020-07-06 | 2020-07-06 |  |  | ضعف كفاءة المقاول الفنية |  | 42.1351 | 19.1263 | مسحوب | No
2100042615 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 4727500 | 236375 | 2693400 | 2693400 | 2511482400 | لا | 0 |  | مسحوب | التكلفة المفوترة | 62 | 100 | 2011-12-17 | 2013-02-09 | 2013-02-09 | 2013-02-09 |  |  | ضعف كفاءة المقاول الفنية |  | 45.975 | 28.4334 | مسحوب | No
2100042431 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 11297258.26 | 564862.913 | 0.01 | 0.01 | 1010046644 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0 | 100 | 2017-04-30 | 2019-04-20 | 2020-01-28 | 2020-01-28 |  |  | ضعف كفاءة المقاول الفنية |  | 50.4168 | 26.4434 | مسحوب | No
2100042291 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 13557224.69 | 677861.2345 | 4090901.5 | 0 | 1116004360 | لا | 0 |  | مسحوب | التكلفة المفوترة | 30 | 100 | 2012-07-15 | 2017-12-16 | 2017-12-16 | 2017-12-16 |  |  | ضعف كفاءة المقاول الفنية |  | 50.5511 | 26.44 | مسحوب | Yes
2100040972 | وزارة الصحة / حائل | تشييد | ذات اولوية عالية وعاجلة | 1982750 | 99137.5 | 1982750 | 1982750 | 3350017944 | لا | 0 | 181009135633 | جاري | تكلفة العمل المنجز | 97 | 100 | 2018-08-01 | 2020-05-14 | 2022-05-01 | 2022-05-01 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6884 | 27.5058 | Failed | No
2100045640 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1000000 | 50000 | 981750 | 981750 | 4605002907 | لا | 0 | 181009122439 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-08-31 | 2019-06-27 | 2020-01-13 | 2020-01-13 | 2019-06-27 |  |  |  | 40.4057 | 22.4781 | منجز | No
2100042195 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 12694869 | 634743.45 | 2682638.85 | 2589706.14 | 1010090099 | لا | 0 | 190309008197 | مسحوب | التكلفة المفوترة | 39 | 100 | 2012-06-09 | 2014-05-31 | 2023-02-09 | 2023-02-09 |  |  | ضعف كفاءة المقاول الفنية |  | 42.1351 | 19.1255 | مسحوب | No
2100045990 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 715919.5 | 35795.975 | 715919.5 | 715919.5 | 3350021792 | لا | 0 | 2 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-08-20 | 2020-07-22 | 2020-07-22 | 2020-07-22 | 2020-07-22 |  |  |  | 40.9492 | 27.9984 | منجز | No
2100047622 | أمانة / تبوك | تشييد | لم تعد تحتاجها الجهة | 6438815 | 321940.75 | 1166051.58 | 1166051.58 | 4030139128 | لا | 0 | 181109233429 | مسحوب | الكميات التي تم تركيبها | 14 | 91 | 2016-02-28 | 2017-08-13 | 2022-03-06 | 2022-03-06 |  |  | ضعف كفاءة المقاول الفنية |  | 37.6847 | 28.3938 | مسحوب | No
2100025620 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 50110983.16 | 2505549.158 | 45805670.12 | 45805670.12 | 5950010109 | لا | 0 | 180809055706 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 93 | 90 | 2015-01-28 | 2022-12-07 | 2022-11-08 | 2022-11-08 | 2022-12-07 |  | ضعف كفاءة المقاول الفنية |  | 40.3897 | 21.2672 | منجز | No
2100044623 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 3656363.55 | 182818.1775 | 2569555.72 | 2569555.72 | 4032030986 | لا | 0 | 191101045354 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-09-26 | 2021-03-19 | 2021-07-25 | 2021-07-25 | 2021-03-19 |  |  |  | 40.4248 | 21.2663 | منجز | No
2100004432 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 2695080 | 134754 | 1909136 | 1909136 | 2511104587 | لا | 0 |  | جاري | اخرى | 100 | 100 | 2019-11-24 | 2020-10-23 | 2020-12-01 | 2020-12-01 |  |  | لا يوجد تأخير |  |  |  | Failed | No
2100014615 | أمانة / جازان | تشييد | لم تعد تحتاجها الجهة | 2280122.68 | 114006.134 | 1656422.68 | 1656422.68 | 5901012291 | لا | 0 | 180809061263 | مسحوب | الكميات التي تم تركيبها | 70 | 100 | 2015-02-18 | 2016-02-14 | 2020-11-10 | 2020-11-10 |  |  | ضعف كفاءة المقاول الفنية |  | 42.7559 | 16.5 | مسحوب | No
2100049906 | أمانة / تبوك | تشييد | لم تعد تحتاجها الجهة | 2198500 | 109925 | 1978812.14 | 1978812.14 | 3553000678 | لا | 0 | 200101019365 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-06-08 | 2020-04-03 | 2021-06-03 | 2021-06-03 | 2020-04-03 |  | ضعف كفاءة المقاول الفنية |  |  |  | منجز | No
2100046410 | أمانة / جازان | تشييد | ذات اولوية عالية | 1949100 | 97455 | 1949100 | 1949100 | 3452006376 | لا | 0 | 180601014631 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-08-27 | 2019-08-12 | 2019-08-12 | 2019-08-12 | 2019-08-12 |  | اخرى |  | 42.9533 | 16.7111 | منجز | No
2100048510 | وزارة التعليم | تشييد | ذات اولوية عالية | 697673.47 | 34883.6735 | 253234.02 | 0 | 5909008799 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 43 | 100 | 2007-11-24 | 2008-11-19 | 2023-02-23 | 2023-02-23 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.6509 | 17.1567 | مسحوب | Yes
2100048462 | أمانة / جازان | تشييد | ذات اولوية عالية | 2729450 | 136472.5 | 0 | 0 | 5950004973 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 0 | 100 | 2015-07-26 | 2016-07-20 | 2019-11-05 | 2019-11-05 |  |  | تأخرصرف المستحقات المالية |  | 42.6996 | 16.977 | مسحوب | No
2100048355 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 2266250 | 113312.5 | 1825600 | 1825600 | 5802010434 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 89 | 100 | 2019-11-24 | 2020-11-13 | 2022-12-30 | 2022-12-30 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ | مخطط لسحبه وإعادة ترسيته | 41.6511 | 20.2795 | مسحوب | No
2100049840 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 1497096 | 74854.8 | 1347250 | 1347250 | 4603102229 | لا | 0 | 190809018532 | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2018-09-20 | 2020-03-04 | 2021-03-29 | 2021-03-29 | 2020-03-04 | 2020-10-05 | ضعف كفاءة المقاول الفنية |  | 41.0521 | 19.5364 | منجز | No
2100051015 | أمانة / جازان | تشييد | لم تعد تحتاجها الجهة | 1781560.88 | 89078.044 | 85573.08 | 85573.08 | 5950014399 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 5 | 100 | 2015-02-18 | 2015-12-15 | 2015-12-15 | 2015-12-15 |  |  | اخرى |  | 42.5701 | 16.9131 | مسحوب | No
2100050875 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 5535600 | 276780 | 5535602 | 5535602 | 4031046580 | لا | 0 |  | منجز – استلام نهائي | التكلفة المفوترة | 98.15 | 98.15 | 2018-10-01 | 2020-08-20 | 2021-06-29 | 2021-06-29 | 2020-08-20 | 2020-03-10 |  |  | 39.8681 | 21.3888 | منجز | No
2100050934 | أمانة / جازان | تشييد | ذات اولوية عالية وعاجلة | 39743675.04 | 1987183.752 | 39743675.04 | 39743675.04 | 1010193433 | لا | 0 | 180909080246 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-08-10 | 2018-08-30 | 2019-08-04 | 2019-08-04 | 2018-08-30 |  | اخرى |  | 42.5878 | 16.8692 | منجز | No
2100051822 | أمانة / جازان | تشييد | ذات اولوية عالية وعاجلة | 8676700 | 433835 | 7612790 | 7461778.66 | 1131020873 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 91 | 100 | 2013-06-07 | 2015-05-29 | 2019-05-30 | 2019-05-30 | 2015-05-29 |  | اخرى |  | 42.5932 | 16.8933 | منجز | No
2100051170 | أمانة / جدة | تشييد | ذات اولوية عالية وعاجلة | 22838866 | 1141943.3 | 11483123.74 | 11483123.74 | 4030187606 | لا | 0 | 190301086061 | مسحوب | تكلفة العمل المنجز | 52 | 86 | 2019-07-18 | 2021-07-17 | 2021-12-14 | 2021-12-14 |  |  | اخرى |  | 39.1874 | 21.546 | مسحوب | No
2100052194 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 870400 | 43520 | 870400 | 870400 | 4032043085 | لا | 0 | 181009114804 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-07-03 | 2019-06-28 | 2019-06-28 | 2019-06-28 | 2019-06-28 |  |  |  | 40.989 | 21.0542 | منجز | No
2100052710 | أمانة / حائل | تصميم وتشييد | ذات اولوية عالية | 1588800 | 79440 | 1588800 | 0 | 3350000614 | لا | 0 | 180909093599 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-12-24 | 2020-05-24 | 2021-07-06 | 2021-07-06 | 2020-05-24 |  |  |  | 42.1347 | 26.4971 | منجز | Yes
2100054806 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 1445955 | 72297.75 | 1445955 | 1445919.05 | 3360003562 | لا | 0 | 181109278082 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 93 | 100 | 2018-06-24 | 2019-06-18 | 2019-06-19 | 2019-06-19 | 2019-06-18 |  | ضعف كفاءة المقاول الفنية |  | 40.5483 | 26.4063 | منجز | No
2100060686 | أمانة / تبوك | تشييد | لم تعد تحتاجها الجهة | 2552450 | 127622.5 | 2552450 | 2294508.6 | 3553000034 | لا | 0 | 190309006186 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-03-15 | 2014-11-10 | 2021-07-01 | 2021-07-01 | 2014-11-10 |  | اخرى |  | 34.9451 | 29.2864 | منجز | No
2100056523 | وزارة الصحة / حائل | تشييد | ذات اولوية عالية | 52642871.2 | 2632143.56 | 24907124 | 24907124 | 3350009207 | لا | 0 | 181009165390 | جاري | تكلفة العمل المنجز | 50 | 100 | 2014-10-06 | 2021-07-30 | 2022-07-29 | 2022-07-29 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6882 | 27.5703 | Failed | No
2100083624 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1813216 | 90660.8 | 1813216 | 1813216 | 4032025297 | لا | 0 | 190401061782 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-03-07 | 2020-03-01 | 2020-03-01 | 2020-03-01 | 2020-03-01 |  |  |  | 40.9887 | 21.0576 | منجز | No
2100055436 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 32684368 | 1634218.4 | 29394913 | 29394913 | 5950004973 | لا | 0 | 180809039627 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 99.3 | 100 | 2017-09-13 | 2019-09-13 | 2023-02-01 | 2023-02-01 |  |  | ضعف كفاءة المقاول الفنية |  | 38.2025 | 23.9825 | Failed | No
2100055613 | جامعة جدة | تصميم وتشييد | ذات اولوية عالية | 18257143 | 912857.15 | 3053235.96 | 0 | 1010010296 | لا | 0 | 190501131933 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-10-24 | 2021-12-21 | 2022-03-17 | 2022-03-17 | 2021-12-21 |  | لا يوجد تأخير |  | 21.5792 | 39.1808 | منجز | Yes
2100054795 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 967470 | 48373.5 | 398120 | 398120 | 4031083542 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 43.41 | 43.41 | 2015-12-05 | 2016-12-04 | 2016-12-04 | 2016-12-04 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.8669 | 21.3538 | مسحوب | No
2100055893 | وزارة الصحة / الباحة | تشييد | ذات اولوية متوسطة | 32166163.71 | 1608308.1855 | 22578886.97 | 20937582.88 | 1010132551 | لا | 0 | 181009166907 | جاري | الكميات التي تم تركيبها | 85 | 95 | 2015-12-06 | 2021-12-19 | 2022-02-04 | 2022-02-04 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.4087 | 19.8127 | متأخر | No
2100058015 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 9959220.88 | 497961.044 | 4509958.92 | 0 | 1010090099 | لا | 0 |  | مسحوب | التكلفة المفوترة | 63 | 100 | 2013-12-08 | 2016-03-19 | 2020-03-01 | 2020-03-01 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5604 | 25.3897 | مسحوب | Yes
2100068972 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 7884927.48 | 394246.374 | 7884927.48 | 7884927.48 | 4650021867 | لا | 0 | 180809055716 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2016-12-18 | 2017-12-13 | 2018-03-03 | 2018-03-03 | 2017-12-13 |  | التنسيق مع أصحاب المصلحه (خدمات |  | 40.4206 | 21.2563 | منجز | No
2100059043 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 1971695 | 98584.75 | 1002692 | 1002692 | 1010678591 | لا | 0 |  | مسحوب | التكلفة المفوترة | 82 | 100 | 2011-04-17 | 2012-04-11 | 2023-02-22 | 2023-02-22 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | مسحوب | No
2100063475 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 1199205 | 59960.25 | 475985 | 475985 | 4653000983 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 60 | 71 | 2018-12-15 | 2020-05-30 | 2020-05-30 | 2020-05-30 |  |  | ضعف كفاءة المقاول الفنية |  | 39.5847 | 24.5597 | مسحوب | No
2100060266 | وزارة التعليم | تشييد | ذات اولوية عالية | 1721797 | 86089.85 | 843108 | 843108 | 4650031387 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2019-02-07 | 2019-11-05 | 2019-11-04 | 2019-11-04 | 2019-11-05 |  | ضعف كفاءة المقاول الفنية |  | 38.1071 | 25.0626 | منجز | No
2100062506 | أمانة / الباحة | تشييد | ذات اولوية عالية | 23000680.51 | 1150034.0255 | 23000680.51 | 20400943.36 | 5950009827 | لا | 0 | 181109311566 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-05-10 | 2017-04-18 | 2022-06-01 | 2022-06-01 | 2017-04-18 |  |  |  | 41.5686 | 19.8801 | منجز | No
2100058516 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 6571098 | 328554.9 | 698503.71 | 0 | 4650020435 | لا | 0 |  | مسحوب | التكلفة المفوترة | 70 | 100 | 2013-03-26 | 2015-03-17 | 2023-06-15 | 2023-06-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | Yes
2100061950 | وزارة الثقافة | تشييد | ذات اولوية متوسطة | 21573199.89 | 1078659.9945 | 20594538.05 | 20594538.05 | 1010208611 |  | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-10-11 | 2020-04-10 | 2020-04-10 | 2020-04-10 | 2020-04-10 |  | لا يوجد تأخير |  |  |  | منجز | No
2100065730 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 3042697.14 | 152134.857 | 299424.62 | 299424.62 | 5950026666 | لا | 0 | 220601025060 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-05-29 | 2020-04-28 | 2020-04-28 | 2020-04-28 | 2020-04-28 |  | اخرى |  | 44.0538 | 17.5914 | منجز | No
2100063140 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 4138050 | 206902.5 | 4138050 | 4138050 | 1010052246 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-03-09 | 2021-06-24 | 2021-06-24 | 2021-06-24 | 2021-06-24 |  |  |  | 39.5583 | 24.5046 | منجز | No
2100062230 | أمانة / حائل | دراسة الجدوى | ذات اولوية متوسطة | 317000 | 15850 | 317000 | 317000 | 3350043756 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-08-29 | 2020-08-09 | 2020-08-09 | 2020-08-09 | 2020-08-09 |  | اخرى |  | 42.9925 | 27.4718 | منجز | No
2100064750 | أمانة / تبوك | تشييد | ذات اولوية منخفضة | 565650 | 28282.5 | 0.01 | 0.01 | 1134001137 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 25 | 15 | 2015-07-26 | 2016-08-02 | 2021-02-01 | 2021-02-01 | 2016-08-02 |  | ضعف كفاءة المقاول الفنية |  | 36.5696 | 28.3736 | منجز | No
2100079446 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2984942 | 149247.1 | 2470527.17 | 2470527.17 | 4030164183 | لا | 0 |  | مسحوب | التكلفة المفوترة | 85 | 100 | 2014-08-30 | 2015-08-25 | 2022-08-24 | 2022-08-24 |  |  | ضعف كفاءة المقاول الفنية |  | 40.2691 | 20.1489 | مسحوب | No
2100064142 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 342878 | 17143.9 | 267933 | 267933 | 3357606103 | لا | 0 | 19090150733 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-12-22 | 2019-12-17 | 2021-03-15 | 2021-03-15 | 2019-12-17 |  |  |  | 42.443 | 27.1781 | منجز | No
2100028335 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 1096403 | 54820.15 | 1148613 | 1148613 | 4603001574 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-04-29 | 2020-07-29 | 2020-07-14 | 2020-07-14 | 2020-07-29 |  | ضعف كفاءة المقاول الفنية |  | 41.303 | 18.9727 | منجز | No
2100047810 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 1027740 | 51387 | 1027740 | 1027740 | 4030188853 | لا | 0 | 200609038149 | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2019-11-21 | 2020-11-21 | 2021-02-07 | 2021-02-07 | 2020-11-21 |  | اخرى |  | 40.7396 | 19.907 | منجز | No
2100065111 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 31928900 | 1596445 | 31928900 | 31928900 | 1010194943 | لا | 0 | 180809038249 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-02-26 | 2019-08-20 | 2020-02-16 | 2020-02-16 | 2019-08-20 |  |  |  | 40.416 | 21.2586 | منجز | No
2100067723 | أمانة / جازان | تشييد | ذات اولوية عالية | 7479400 | 373970 | 7479400 | 7479400 | 5900008127 | لا | 0 | 180801059841 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-10-21 | 2019-10-16 | 2019-10-16 | 2019-10-16 | 2019-10-16 |  | اخرى |  | 42.5923 | 16.8893 | منجز | No
2100067830 | أمانة / تبوك | تشييد | ذات اولوية عالية | 13290500 | 664525 | 5639288 | 5639288 | 3400011214 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 43 | 89 | 2016-08-20 | 2018-02-10 | 2020-05-21 | 2020-05-21 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5368 | 28.3955 | مسحوب | No
2100069042 | أمانة / تبوك | تشييد | ذات اولوية منخفضة | 12002253 | 600112.65 | 7119342 | 5770817 | 7012378068 | لا | 0 | 181009142848 | مسحوب | الكميات التي تم تركيبها | 60 | 100 | 2015-04-18 | 2017-04-07 | 2021-12-01 | 2021-12-01 |  |  | ضعف كفاءة المقاول الفنية |  | 34.9497 | 29.2813 | مسحوب | No
2100068843 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 63680100 | 3184005 | 56368987.87 | 56368987.87 | 3350000631 | لا | 0 | 190201031906 | جاري | الكميات التي تم تركيبها | 88 | 95 | 2019-05-04 | 2021-04-10 | 2023-10-31 | 2023-10-31 |  |  | ضعف كفاءة المقاول الفنية |  | 41.7077 | 27.5399 | متأخر | No
2100068036 | أمانة / حفر الباطن | تشييد | ذات اولوية متوسطة | 18845910 | 942295.5 | 18845883.3 | 18845883.3 | 1010136405 | لا | 0 | 0 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-09-14 | 2016-09-03 | 2018-12-06 | 2018-12-06 | 2016-09-03 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 45.9787 | 28.3865 | منجز | No
2100072435 | أمانة / جازان | تشييد | ذات اولوية عالية وعاجلة | 2409643 | 120482.15 | 1571562 | 0 | 5911018506 | لا | 0 |  | مسحوب | اخرى | 68 | 100 | 2015-05-10 | 2016-05-04 | 2016-05-11 | 2016-05-11 |  |  | اخرى |  | 42.8238 | 16.4168 | مسحوب | Yes
2100071746 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 164205.88 | 8210.294 | 0 | 0 | 1010895583 | لا | 0 | 200201042715 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-06-15 | 2021-03-24 | 2021-03-10 | 2021-03-10 | 2021-03-24 |  | ضعف كفاءة المقاول الفنية |  | 37.2651 | 25.05 | منجز | No
2100067572 | أمانة / جدة | تشييد | ذات اولوية عالية | 106395390 | 5319769.5 | 47016800.25 | 47016800.25 | 4650007032 | لا | 0 | 181209459901 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-02-04 | 2016-01-13 | 2019-08-14 | 2019-08-14 | 2016-01-13 |  | تأخرصرف المستحقات المالية |  | 39.1817 | 21.5492 | منجز | No
2100074384 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1991371 | 99568.55 | 498842.75 | 498842.75 | 1010203566 | لا | 0 |  | مسحوب | التكلفة المفوترة | 36 | 100 | 2009-11-13 | 2011-04-28 | 2023-12-14 | 2023-12-14 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | مسحوب | No
2100074476 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 12406148 | 620307.4 | 0.01 | 0.01 | 1010081983 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0 | 100 | 2015-12-18 | 2017-12-18 | 2019-03-24 | 2019-03-24 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 43.9544 | 26.3504 | مسحوب | No
2100072505 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 5279550 | 263977.5 | 3227463 | 3227463 | 1131020873 | لا | 0 | 181109358971 | مسحوب | تكلفة العمل المنجز | 63 | 100 | 2012-10-12 | 2014-01-11 | 2019-06-05 | 2019-06-05 |  |  | اخرى |  | 42.5851 | 16.9188 | مسحوب | No
2100072133 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 4834378 | 241718.9 | 4834378 | 4834378 | 5800000659 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2013-12-08 | 2016-11-05 | 2022-08-18 | 2022-08-18 | 2016-11-05 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 41.3671 | 20.0551 | منجز | No
2100072192 | أمانة / الباحة | تشييد | ذات اولوية عالية وعاجلة | 13088275 | 654413.75 | 1511097 | 1511097 | 4030159820 | لا | 0 |  | جاري | تكلفة العمل المنجز | 60 | 100 | 2019-05-12 | 2020-12-06 | 2022-11-30 | 2022-11-30 |  |  | ضعف كفاءة المقاول الفنية |  | 41.2836 | 20.1058 | Failed | No
2100073323 | أمانة / تبوك | تشييد | ذات اولوية عالية وعاجلة | 33167752.41 | 1658387.6205 | 29648576.24 | 29648576.24 | 4030201495 | نعم | 121125664 | 200609054060 | جاري | تكلفة العمل المنجز | 97 | 100 | 2013-09-28 | 2022-02-18 | 2023-04-03 | 2023-04-03 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5468 | 28.4411 | منتظم | No
2100073964 | أمانة / جازان | تصميم | ذات اولوية متوسطة | 420173.4 | 21008.67 | 81610 | 81610 | 1131052059 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 19 | 100 | 2011-05-11 | 2012-01-06 | 2012-01-06 | 2012-01-06 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | مسحوب | No
2100094334 | وزارة التعليم | تشييد | ذات اولوية عالية | 2040983 | 102049.15 | 642908.14 | 0 | 4650003991 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 40 | 100 | 2008-08-06 | 2009-07-30 | 2023-11-15 | 2023-11-15 |  |  | ضعف كفاءة المقاول الفنية |  | 38.3424 | 24.7864 | مسحوب | Yes
2100075751 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 4199500 | 209975 | 2427915 | 2427915 | 5950015390 | لا | 0 | 210501030518 | جاري | تكلفة العمل المنجز | 50 | 55 | 2018-09-02 | 2019-08-22 | 2023-03-30 | 2023-03-30 |  |  | تأخرصرف المستحقات المالية |  | 44.2373 | 17.5622 | Failed | No
2100072800 | أمانة / تبوك | تشييد | لم تعد تحتاجها الجهة | 3819556.7 | 190977.835 | 3819555.7 | 3819555.7 | 3553000034 | لا | 0 | 191109023902 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-09-06 | 2015-09-01 | 2021-08-01 | 2021-08-01 | 2015-09-01 |  | اخرى |  | 34.9451 | 29.2864 | منجز | No
2100074546 | وزارة التعليم | تشييد | لم تعد تحتاجها الجهة | 1993495 | 99674.75 | 681055 | 591924 | 1010069591 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 40 | 100 | 2009-10-03 | 2009-12-30 | 2021-11-10 | 2021-11-10 |  |  | ضعف كفاءة المقاول الفنية |  | 43.1379 | 18.0853 | مسحوب | No
2100074410 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 7495242.02 | 374762.101 | 3321584.85 | 3321584.85 | 2031040463 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 51 | 100 | 2013-04-30 | 2015-04-20 | 2021-01-04 | 2021-01-04 |  |  | ضعف كفاءة المقاول الفنية |  | 45.975 | 28.4334 | مسحوب | No
2100080404 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 6780000 | 339000 | 6102000 | 6102000 | 1010052246 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 90 | 100 | 2019-08-19 | 2022-02-14 | 2022-02-14 | 2022-02-14 | 2022-02-14 |  | ضعف كفاءة المقاول الفنية |  | 39.6153 | 24.4826 | منجز | No
2100076425 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 9124698 | 456234.9 | 8070866 | 8070866 | 4031046917 | لا | 0 | 190301025660 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 99 | 100 | 2018-11-30 | 2019-05-29 | 2022-05-31 | 2022-05-31 | 2019-05-29 |  | ضعف كفاءة المقاول الفنية |  | 42.0224 | 21.9128 | منجز | No
2100100811 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 401782.5 | 20089.125 | 314582.5 | 314582.5 | 4034000979 | لا | 0 | 181001153110 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2017-11-28 | 2018-11-23 | 2018-11-22 | 2018-11-22 | 2018-11-23 |  | ضعف كفاءة المقاول الفنية |  | 41.6258 | 21.204 | منجز | No
2100075445 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 244350 | 12217.5 | 0 | 0 | 3350027442 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-03-24 | 2020-03-19 | 2020-03-22 | 2020-03-22 | 2020-03-19 |  |  |  | 42.443 | 27.1781 | منجز | No
2100081970 | أمانة / تبوك | تشييد | ذات اولوية عالية | 1411016.8 | 70550.84 | 1114703.43 | 1114703.43 | 3550032522 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 80 | 80 | 2016-02-19 | 2017-02-19 | 2018-04-25 | 2018-04-25 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5302 | 28.3926 | مسحوب | No
2100081491 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 495000 | 24750 | 495000 | 495000 | 5950013363 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-06-11 | 2020-02-02 | 2022-02-02 | 2022-02-02 | 2020-02-02 |  | اخرى |  | 44.2407 | 17.5617 | منجز | No
2100081336 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 8894867 | 444743.35 | 0 | 0 | 5950009827 | لا | 0 | 210601172735 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-01-06 | 2020-01-01 | 2020-09-14 | 2020-09-14 | 2020-01-01 |  | ضعف كفاءة المقاول الفنية |  | 44.2478 | 17.5564 | منجز | No
2100078024 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 43977400 | 2198870 | 41778530 | 41778530 | 1010135922 | لا | 0 | 180909083492 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99.16 | 100 | 2017-10-18 | 2019-10-18 | 2022-09-29 | 2022-09-29 | 2019-10-18 |  | عدم اكتمال أو ضعف أعمال التصميم والدراسات |  | 38.1933 | 24.0007 | منجز | No
2100083101 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 1593050 | 79652.5 | 1587477.36 | 1505385 | 4603102229 | لا | 0 | 190809018415 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-11-06 | 2019-10-27 | 2020-02-20 | 2020-02-20 | 2019-10-27 |  | ضعف كفاءة المقاول الفنية |  | 41.0494 | 19.5349 | منجز | No
2100096180 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 3424000 | 171200 | 554056 | 554056 | 1010214056 | لا | 0 | 180809060557 | مسحوب | الكميات التي تم تركيبها | 19 | 100 | 2010-11-23 | 2011-11-08 | 2020-02-20 | 2020-02-20 |  |  | اخرى |  | 42.5722 | 16.9121 | مسحوب | No
2100084420 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 2966325 | 148316.25 | 2626089.38 | 1709044 | 5802010434 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 85 | 85 | 2015-01-03 | 2015-11-05 | 2020-08-31 | 2020-08-31 |  |  | تأخرصرف المستحقات المالية |  | 41.3883 | 20.3871 | Failed | No
2100084361 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 7292668.21 | 364633.4105 | 5192606.89 | 3135753.45 | 4030195842 | لا | 0 | 181109303411 | جاري | تكلفة العمل المنجز | 92 | 92 | 2014-03-06 | 2015-02-23 | 2022-07-06 | 2022-07-06 |  |  | ضعف كفاءة المقاول الفنية |  | 41.5686 | 19.8802 | منتظم | No
2100086192 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 10307537.19 | 515376.8595 | 6079889.2 | 6072683.3 | 2050052248 | لا | 0 | 190209015504 | مسحوب | التكلفة المفوترة | 58 | 100 | 2014-11-30 | 2019-03-03 | 2022-02-23 | 2022-02-23 |  |  | ضعف كفاءة المقاول الفنية |  | 41.4779 | 20.0185 | مسحوب | No
2100083381 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 3993850 | 199692.5 | 3993850 | 3993850 | 5907024458 | لا | 0 | 181209531753 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-10-09 | 2020-09-28 | 2022-10-01 | 2022-10-01 | 2020-09-28 |  |  |  | 41.4767 | 20.0213 | منجز | No
2100084560 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 3488100 | 174405 | 3486697.27 | 3486697.27 | 4030044382 | لا | 0 | 181201474546 | منجز – استلام نهائي | تكلفة العمل المنجز | 99.96 | 99.96 | 2019-02-24 | 2021-01-21 | 2021-01-22 | 2021-01-22 | 2021-01-21 | 2022-12-07 |  |  | 39.8524 | 21.3694 | منجز | No
2100085271 | أمانة / الجوف | دراسات هندسية | ذات اولوية متوسطة | 5664000 | 283200 | 5664000 | 5664000 | 3400011727 | لا | 0 | 190201031002 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-05-01 | 2021-04-20 | 2021-07-01 | 2021-07-01 | 2021-04-20 |  | اخرى |  | 37.3552 | 31.3321 | منجز | No
2100086310 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 16823944.65 | 841197.2325 | 3734206.985 | 0 | 2050010484 | لا | 0 |  | مسحوب | التكلفة المفوترة | 22 | 100 | 2013-07-06 | 2015-09-24 | 2023-05-17 | 2023-05-17 |  |  | ضعف كفاءة المقاول الفنية |  | 50.1128 | 26.9851 | مسحوب | Yes
2100085831 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 14304190 | 715209.5 | 3058067.19 | 3058067.19 | 1010036045 | لا | 0 |  | مسحوب | التكلفة المفوترة | 30 | 100 | 2013-12-30 | 2015-12-20 | 2015-12-20 | 2015-12-20 |  |  | ضعف كفاءة المقاول الفنية |  | 45.975 | 28.4334 | مسحوب | No
2100086321 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 10752021 | 537601.05 | 1441523.4 | 0.01 | 1010174503 | لا | 0 |  | مسحوب | التكلفة المفوترة | 20 | 100 | 2010-03-12 | 2012-01-03 | 2012-01-03 | 2012-01-03 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5604 | 25.3897 | مسحوب | No
2100084932 | وزارة الصحة / المدينة المنورة | تشييد | ذات اولوية منخفضة | 4779730 | 238986.5 | 1191763 | 799763 | 1132002394 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 25 | 100 | 2015-10-05 | 2016-09-23 | 2022-04-30 | 2022-04-30 |  |  | تأخرصرف المستحقات المالية |  | 41.6087 | 24.6115 | Failed | No
2100087850 | وزارة الدفاع / الإدارة الهندسية والاشغال بالخدمات الصحية | تشييد | ذات اولوية متوسطة | 53592519.39 | 2679625.9695 | 53592519.39 | 53592519.39 | 1131020873 | لا | 0 | 180909098459 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-12-06 | 2016-05-08 | 2021-12-31 | 2021-12-31 | 2016-05-08 |  | اخرى |  | 42.6158 | 16.8807 | منجز | No
2100089810 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البرية | تشييد | ذات اولوية متوسطة | 6482294.5 | 324114.725 | 5892995 | 5892995 | 2511009902 | لا | 0 | 18110929490200 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-12-12 | 2019-11-27 | 2021-12-31 | 2021-12-31 | 2019-11-27 |  | لا يوجد تأخير |  | 50.0238 | 26.473 | منجز | No
2100092072 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 2499979 | 124998.95 | 2499979 | 2499979 | 4030006066 | لا | 0 | 190301070637 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-03-17 | 2019-11-12 | 2019-11-12 | 2019-11-12 | 2019-11-12 |  | ضعف كفاءة المقاول الفنية |  | 40.8099 | 20.9465 | منجز | No
2100090996 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 497150 | 24857.5 | 497150 | 497150 | 4046001026 | لا | 0 | 181001154052 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-07-03 | 2019-06-28 | 2019-06-28 | 2019-06-28 | 2019-06-28 |  |  |  | 40.9841 | 21.0567 | منجز | No
2100093656 | أمانة / الجوف | تشييد | ذات اولوية عالية | 2692580 | 134629 | 2692580 | 2692580 | 3400011668 | لا | 0 | 180909098778 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-05-24 | 2015-05-24 | 2019-10-05 | 2019-10-05 | 2015-05-24 |  | تأخرصرف المستحقات المالية |  | 37.9812 | 30.7109 | منجز | No
2100094511 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 1397130 | 69856.5 | 1192727.25 | 1192727.25 | 1118001565 | لا | 0 | 181109366591 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 85 | 100 | 2018-09-09 | 2019-09-03 | 2020-03-25 | 2020-03-25 | 2019-09-03 |  | ضعف كفاءة المقاول الفنية |  | 42.4135 | 27.8869 | منجز | No
2100095244 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 192748373 | 9637418.65 | 173454709 | 173454709 | 1010245164 | لا | 0 | 181209546650 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 99.9 | 100 | 2009-06-27 | 2011-06-27 | 2023-01-29 | 2023-01-29 |  |  |  |  | 38.1902 | 24.0188 | Failed | No
2100103876 | وزارة التعليم | تشييد | ذات اولوية عالية | 2014814 | 100740.7 | 1231475.44 | 0 | 4031007808 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 54 | 100 | 2006-06-21 | 2007-05-08 | 2023-06-15 | 2023-06-15 |  |  | ضعف كفاءة المقاول الفنية |  | 38.1726 | 25.1601 | مسحوب | Yes
2100093306 | أمانة / المدينة المنورة | دراسة الجدوى | ذات اولوية متوسطة | 10878000 | 543900 | 10660440 | 10660440 | 1131052059 | لا | 0 |  | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 98 | 100 | 2019-08-26 | 2022-07-23 | 2022-07-23 | 2022-07-23 |  |  | اخرى |  |  |  | متأخر | No
2100094780 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 67607522 | 3380376.1 | 14979417 | 14979417 | 1010152168 | لا | 0 | 180909091055 | مسحوب | منهجية القيمة المكتسبة | 30.35 | 100 | 2017-02-21 | 2019-02-21 | 2022-04-13 | 2022-04-13 |  |  | ضعف كفاءة المقاول الفنية |  | 38.1898 | 24.0335 | مسحوب | No
2100098243 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية عالية | 12580250 | 629012.5 | 12580250 | 12580250 | 5850031989 | لا | 0 | 180104114784 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-01-06 | 2019-12-27 | 2019-12-22 | 2019-12-22 |  | 2019-12-27 | لا يوجد تأخير |  | 41.944 | 18.9325 | منجز | No
2100099046 | وزارة الدفاع / الإدارة الهندسية والاشغال بقوات الدفاع الجوي | تشييد | ذات اولوية متوسطة | 8223661.95 | 411183.0975 | 8223661.95 | 7401295.76 | 1010245185 | لا | 0 | 181101357307 | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 98 | 100 | 2019-04-10 | 2021-03-30 | 2021-12-31 | 2021-12-31 |  |  | أوامر سامية |  | 50.1158 | 26.3593 | Failed | No
2100100623 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 1876400 | 93820 | 0 | 0 | 3550025589 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 50 | 100 | 2015-08-08 | 2016-08-08 | 2021-07-07 | 2021-07-07 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5612 | 28.4026 | مسحوب | No
2100100726 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 3918789 | 195939.45 | 3176477.77 | 2713369.84 | 4031086274 | لا | 0 | 210101007285 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 80 | 100 | 2019-07-08 | 2020-07-02 | 2022-01-01 | 2022-01-01 | 2020-07-02 |  |  |  | 40.4104 | 21.2609 | منجز | No
2100096445 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 9190529 | 459526.45 | 5137068.19 | 3137031.07 | 1010277276 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 78 | 100 | 2014-03-12 | 2018-03-05 | 2023-05-11 | 2023-05-11 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.5429 | 16.8808 | مسحوب | No
2100097392 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 9147092.85 | 457354.6425 | 142158.1 | 0 | 1010006362 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 11 | 100 | 2013-05-25 | 2015-02-15 | 2022-12-28 | 2022-12-28 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.5429 | 16.8808 | مسحوب | Yes
2100100822 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية منخفضة | 7350000 | 367500 | 4826373 | 4826373 | 4031074430 | لا | 0 | 200309112804 | جاري | تكلفة العمل المنجز | 51.72 | 51.72 | 2019-08-21 | 2022-04-28 | 2022-04-28 | 2022-04-28 |  |  | تأخرصرف المستحقات المالية |  | 39.8539 | 21.3709 | متأخر | No
2100105652 | وزارة الثقافة | تشييد |  | 56724885.38 | 2836244.269 | 44025456.16 | 44025456.16 | 1010070634 |  | 0 |  | جاري | منهجية القيمة المكتسبة | 72 | 100 | 2011-05-02 00:59 | 2013-05-01 00:59 | 2020-03-27 | 2020-03-27 |  |  | أوامر سامية |  |  |  | Failed | No
2100102233 | وزارة الموارد البشرية والتنمية الإجتماعية | إشراف | ذات اولوية منخفضة | 714000 | 35700 | 1345399.99 | 1345399.99 | 1010435790 | لا | 0 | 181009183614 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-12-30 | 2016-12-07 | 2020-10-27 | 2020-10-27 | 2016-12-07 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.9127 | 16.5828 | منجز | No
2100103305 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 6999076 | 349953.8 | 5320979.82 | 5320979.82 | 5859001126 | لا | 0 |  | مسحوب | التكلفة المفوترة | 77 | 100 | 2011-10-14 | 2013-04-06 | 2023-02-02 | 2023-02-02 |  |  | ضعف كفاءة المقاول الفنية |  | 42.1351 | 19.1255 | مسحوب | No
2100100800 | أمانة / الجوف | تشييد | ذات اولوية عالية | 921000 | 46050 | 921000 | 921000 | 1010234790 | لا | 0 | 180909091151 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-06-26 | 2019-02-17 | 2019-02-17 | 2019-02-17 | 2019-02-17 |  |  |  | 39.3051 | 29.888 | منجز | No
2100103950 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 10202156.08 | 510107.804 | 3357516.82 | 3357516.82 | 1010187466 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2013-12-18 | 2015-11-26 | 2021-07-07 | 2021-07-07 | 2015-11-26 |  | ضعف كفاءة المقاول الفنية |  | 43.4919 | 25.8758 | منجز | No
2100108581 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 87580909 | 4379045.45 | 53122509.46 | 53122509.46 | 2051034972 | لا | 0 | 180101000046 | جاري | منهجية القيمة المكتسبة | 62 | 100 | 2018-05-01 | 2022-02-28 | 2024-01-23 | 2024-01-23 |  |  | موافقات |  | 49.6626 | 27.0037 | Failed | No
2100104171 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 9620567.5 | 481028.375 | 0 | 0 | 1010006362 | لا | 0 |  | مسحوب | التكلفة المفوترة | 32 | 100 | 2013-05-25 | 2014-10-09 | 2023-02-09 | 2023-02-09 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | مسحوب | No
2100092444 | أمانة / جازان | تشييد | ذات اولوية عالية | 999800 | 49990 | 0 | 0 | 5903005814 | لا | 0 | 180809060597 | مسحوب | الكميات التي تم تركيبها | 29 | 100 | 2012-11-17 | 2019-02-01 | 2019-09-09 | 2019-09-09 |  |  | ضعف كفاءة المقاول الفنية |  | 42.6235 | 16.8919 | مسحوب | No
2100104650 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 15744254.52 | 787212.726 | 1615629.16 | 0.01 | 1010046644 | لا | 0 |  | مسحوب | التكلفة المفوترة | 7 | 100 | 2016-06-12 | 2018-06-01 | 2018-06-02 | 2018-06-02 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5604 | 25.3897 | مسحوب | No
2100109185 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 7277932.04 | 363896.602 | 2944363.02 | 0.01 | 2251003882 | لا | 0 |  | مسحوب | التكلفة المفوترة | 47 | 100 | 2013-07-28 | 2015-07-18 | 2020-06-01 | 2020-06-01 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5604 | 25.3897 | مسحوب | No
2100107030 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2104860.8 | 105243.04 | 1435868 | 1435868 | 2511009886 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2019-02-04 | 2019-08-03 | 2020-10-21 | 2020-10-21 | 2019-08-03 |  | ضعف كفاءة المقاول الفنية |  | 45.975 | 28.4334 | منجز | No
2100107166 | وزارة الدفاع / الإدارة الهندسية والاشغال بالخدمات الصحية | تشييد | ذات اولوية عالية | 155671996 | 7783599.8 | 22826719.82 | 22826719.82 | 2101026187 | لا | 0 | 180909090022 | ايقاف كلي | الكميات التي تم تركيبها | 13 | 95 | 2015-10-06 | 2021-04-28 | 2023-05-12 | 2023-05-12 |  |  | تغيرات في نطاق المشروع |  | 50.1366 | 26.3601 | Failed | No
2100020790 | وزارة الشـؤون الاسلامية والدعوة والارشاد | تشييد | ذات اولوية عالية | 1248172 | 62408.6 | 0 | 0 | 5850051813 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 75 | 100 | 2019-10-13 | 2020-10-12 | 2022-07-31 | 2022-07-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 43.511 | 17.6642 | Failed | No
2100075364 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1796580 | 89829 | 1394227.72 | 998100 | 4044000973 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 55 | 100 | 2015-05-10 | 2016-05-04 | 2022-01-01 | 2022-01-01 |  |  | تأخرصرف المستحقات المالية |  | 40.8307 | 20.7266 | مسحوب | No
2100059275 | المركز الوطني لتنمية الحياة الفطرية | تشييد | ذات اولوية منخفضة | 902827.8 | 45141.39 | 902827.8 | 902827.8 | 1010102014 | لا | 0 | 180809038856 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2017-11-20 | 2019-04-30 | 2019-04-30 | 2019-04-30 | 2019-04-30 |  | لا يوجد تأخير |  | 46.6261 | 25.2198 | منجز | No
2100097123 | جامعة القصيم | تشييد | ذات اولوية عالية | 8678354.3 | 433917.715 | 7215909.75 | 7049255.41 | 1010299979 | لا | 0 | 190501094449 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 95 | 100 | 2019-06-30 | 2020-03-26 | 2022-12-25 | 2022-12-25 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 43.7776 | 26.3108 | Failed | No
2100019445 | جامعة القصيم | تشييد | ذات اولوية عالية | 445924395.35 | 22296219.7675 | 408174436.1 | 408174436.1 | 1010006362 | لا | 0 | 200209131489 | جاري | تكلفة العمل المنجز | 87 | 90 | 2011-10-25 | 2014-02-11 | 2023-06-30 | 2023-06-30 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 43.7478 | 26.3634 | متأخر | No
2100089095 | وزارة الشـؤون الاسلامية والدعوة والارشاد | تشييد | ذات اولوية عالية | 972625 | 48631.25 | 739946 | 0 | 3350021121 | نعم | 1189178 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2017-08-17 | 2018-04-17 | 2021-11-17 | 2021-11-17 | 2018-04-17 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.7453 | 27.5107 | منجز | Yes
2100062576 | شركة الكهرباء | تشييد | ذات اولوية متوسطة | 173761408 | 8688070.4 | 5952000 | 5952000 | 1010231925 | لا | 0 |  | جاري | اخرى | 12.5 | 100 | 2016-09-28 | 2019-02-28 | 2022-12-29 | 2022-12-29 |  |  | اخرى |  | 39.2732 | 21.6337 | Failed | No
2100085363 | وزارة التجارة | دراسة الجدوى | ذات اولوية عالية وعاجلة | 2738000 | 136900 | 1760485 | 1760485 | 1010348048 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 90 | 91 | 2018-10-10 | 2020-10-09 | 2022-07-05 | 2022-07-05 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  |  |  | خدمات عامة | No
2100108544 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | تشييد | ذات اولوية متوسطة | 9194979 | 459748.95 | 6183206.1 | 5728752.3 | 1010409973 | لا | 0 | 180901101530 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-12-19 | 2020-09-17 | 2023-02-28 | 2023-02-28 |  |  | تأخرصرف المستحقات المالية |  | 42.7302 | 18.3003 | منتظم | No
2100002844 | الجمارك السعودية | تشييد | ذات اولوية عالية | 2956355.82 | 147817.791 | 3778155.81 | 3732155.81 | 1010332416 | لا | 0 | 181209466119 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-03-16 | 2017-02-21 | 2021-03-07 | 2021-03-07 | 2017-02-21 |  | اخرى |  | 37.1508 | 31.4533 | منجز | No
2100010334 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | تشييد | ذات اولوية متوسطة | 16621341.45 | 831067.0725 | 14304821.05 | 3525931.5 | 1010404410 | لا | 0 | 190401115816 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-07-15 | 2021-01-04 | 2021-10-10 | 2021-10-10 | 2021-01-04 |  | لا يوجد تأخير |  | 42.7302 | 18.3003 | منجز | No
2100020834 | الجمارك السعودية | تشييد | ذات اولوية عالية | 1521115.2 | 76055.76 | 1302252.11 | 1302252.11 | 1010433554 | لا | 0 | 200701010918 | جاري | تكلفة العمل المنجز | 85 | 100 | 2020-07-05 | 2021-07-04 | 2021-07-04 | 2021-07-04 |  |  | اخرى |  | 44.2058 | 17.5746 | Failed | No
2100015411 | شركة الكهرباء | تشييد | ذات اولوية متوسطة | 18155622 | 907781.1 | 16211176 | 16211176 | 1010157290 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2015-09-17 | 2018-04-05 | 2021-04-30 | 2021-04-30 | 2018-04-05 |  | لا يوجد تأخير |  | 39.1947 | 21.4754 | منجز | No
2100068935 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 349500 | 17475 | 349500 | 349500 | 4030164524 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-10-25 | 2018-12-23 | 2018-11-09 | 2018-11-09 | 2018-12-23 |  |  |  | 41.4549 | 19.978 | منجز | No
2100076473 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 122000 | 6100 | 0 | 0 | 3351012191 | لا | 0 | 181101374320 | مسحوب | الكميات التي تم تركيبها | 0 | 0 | 2018-11-19 | 2019-11-19 | 2021-09-22 | 2021-09-22 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6753 | 26.7907 | مسحوب | No
2100041005 | الرئاسة العامة لهيئة الأمر بالمعروف والنهي عن المنكر | تشييد | ذات اولوية متوسطة | 30508479.65 | 1525423.9825 | 26027460 | 26027460 | 1115001461 | لا | 0 | 200609086019 | جاري | الكميات التي تم تركيبها | 92 | 100 | 2014-11-04 | 2016-06-26 | 2022-08-31 | 2022-08-31 |  |  | تأخرصرف المستحقات المالية |  | 40.4745 | 25.9973 | Failed | No
2100054191 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 24999765 | 1249988.25 | 21625262 | 21625262 | 5855000147 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2005-10-25 | 2008-05-26 | 2008-05-26 | 2008-05-26 | 2008-05-26 | 2021-07-05 |  |  | 42.4887 | 18.1816 | منجز | No
2100103994 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 4152177.75 | 207608.8875 | 3738295.76 | 3738295.76 | 5950004276 | لا | 0 |  | جاري | تكلفة العمل المنجز | 100 | 100 | 2019-10-15 | 2020-09-15 | 2020-09-15 | 2020-09-15 |  |  | اخرى |  |  |  | Failed | No
2100093170 | جامعة بيشة | تشييد | ذات اولوية عالية | 41947815 | 2097390.75 | 32975019 | 32975019 | 5855025732 | لا | 0 | 200601028296 | جاري | اخرى | 100 | 100 | 2020-06-08 | 2023-06-08 | 2023-06-28 | 2023-06-28 |  |  |  |  | 42.613 | 20.0279 | منتظم | No
2100015562 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 90426047 | 4521302.35 | 53196016 | 53196016 | 4030034104 | لا | 0 | 200209147457 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2012-11-06 | 2015-11-06 | 2019-07-30 | 2019-07-30 | 2015-11-06 |  | أوامر تغيير |  | 38.2378 | 23.9784 | منجز | No
2100018594 | الرئاسة العامة للبحوث العلمية والإفتاء | تشييد | ذات اولوية عالية وعاجلة | 3829416 | 191470.8 | 0 | 0 | 1010087411 |  | 0 |  | مسحوب | مدفوعات ساعات العمل | 28 | 100 | 2012-09-02 | 2014-08-11 | 2015-03-01 | 2015-03-01 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | مسحوب | No
2100104521 | وزارة التعليم | تشييد | ذات اولوية عالية | 2872444.2 | 143622.21 | 1182996.42 | 1182996.42 | 1117001926 | لا | 0 |  | مسحوب | التكلفة المفوترة | 45 | 100 | 2015-01-21 | 2016-03-17 | 2022-09-04 | 2022-09-04 |  |  | ضعف كفاءة المقاول الفنية |  | 45.313 | 24.0763 | مسحوب | No
2100018196 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1995673 | 99783.65 | 1171970 | 577270 | 1117002165 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2018-08-04 | 2019-07-30 | 2021-05-20 | 2021-05-20 | 2019-07-30 |  | اخرى |  | 45.2591 | 25.2379 | منجز | No
2100012294 | وزارة التعليم | تشييد | ذات اولوية عالية | 10956137.07 | 547806.8535 | 9250201.59 | 9250201.59 | 1010081451 | لا | 0 |  | جاري | التكلفة المفوترة | 81 | 100 | 2014-06-01 | 2016-05-21 | 2019-06-17 | 2019-06-17 |  |  | ضعف كفاءة المقاول الفنية |  | 46.5607 | 24.6524 | Failed | No
2100009553 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 1407926.4368 | 70396.3218 | 0 | 0 | 5855018218 | لا | 0 |  | مسحوب | التكلفة المفوترة | 14 | 100 | 2015-07-28 | 2015-12-25 | 2023-05-10 | 2023-05-10 |  |  | ضعف كفاءة المقاول الفنية |  | 42.0529 | 18.5228 | مسحوب | No
2100019854 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 9629889.57 | 481494.4785 | 3752675 | 3257671.28 | 1128003208 | لا | 0 |  | جاري | التكلفة المفوترة | 79 | 100 | 2015-12-23 | 2017-09-13 | 2022-03-08 | 2022-03-08 |  |  | ضعف كفاءة المقاول الفنية |  | 45.2591 | 25.2379 | Failed | No
2100057536 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 10476750 | 523837.5 | 10441746.85 | 9389118.35 | 1010275506 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-11-06 | 2019-11-06 | 2019-11-06 | 2019-11-06 |  | 2019-11-06 | لا يوجد تأخير |  | 46.8037 | 24.7595 | منجز | No
2100103515 | هيئة المدن الصناعية ومناطق التقنية | تشييد | ذات اولوية عالية | 41272415 | 2063620.75 | 39281255 | 39281255 | 1010068242 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-12-04 | 2021-12-03 | 2022-03-05 | 2022-03-05 | 2021-12-03 |  | لا يوجد تأخير |  | 23.8702 | 47.262 | منجز | No
2100001433 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 29228751.01 | 1461437.5505 | 0 | 0 | 1011008214 | لا | 0 |  | جاري | تكلفة العمل المنجز | 84 | 87 | 2014-06-04 | 2019-12-24 | 2022-01-02 | 2022-01-02 |  |  | ضعف كفاءة المقاول الفنية |  | 44.7813 | 20.4716 | Failed | No
2100041801 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 5999692 | 299984.6 | 2279343.25 | 2279343.25 | 1010258091 | لا | 0 |  | جاري | التكلفة المفوترة | 55 | 100 | 2013-08-21 | 2017-07-17 | 2022-02-07 | 2022-02-07 |  |  | ضعف كفاءة المقاول الفنية |  | 44.4412 | 24.5406 | Failed | No
2100042324 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2375248 | 118762.4 | 1821573.14 | 1821573.14 | 1118000833 | لا | 0 |  | جاري | التكلفة المفوترة | 75 | 100 | 2011-01-09 | 2012-02-21 | 2022-01-03 | 2022-01-03 |  |  | ضعف كفاءة المقاول الفنية |  | 44.4412 | 24.5406 | Failed | No
2100096563 | أمانة / الرياض | دراسة الجدوى | ذات اولوية متوسطة | 9542600 | 477130 | 8645384 | 0 | 4030276223 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-02-08 | 2018-04-17 | 2018-04-17 | 2018-04-17 | 2018-04-17 |  | اخرى |  |  |  | منجز | Yes
2100057691 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2399208 | 119960.4 | 290883.14 | 290883.14 | 1010216996 | لا | 0 |  | مسحوب | التكلفة المفوترة | 14 | 100 | 2013-09-23 | 2015-01-23 | 2023-04-11 | 2023-04-11 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7271 | 22.2863 | مسحوب | No
2100106385 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 4378300 | 218915 | 4367223 | 3515677.2 | 1010158780 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-03-28 | 2020-11-28 | 2021-01-26 | 2021-01-26 |  | 2020-11-28 | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100087220 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 2953300 | 147665 | 2918569 | 2918569 | 1010158780 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-04-09 | 2020-10-09 | 2020-08-09 | 2020-08-09 |  | 2020-10-09 | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100074756 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 4564852 | 228242.6 | 4564654.55 | 4564654.55 | 1010158780 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-11-27 | 2020-11-27 | 2020-11-24 | 2020-11-24 |  | 2020-11-27 | لا يوجد تأخير |  | 46.7306 | 24.8039 | منجز | No
2100097591 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 30832124 | 1541606.2 | 27887308.16 | 27887308.16 | 1010219753 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 98.49 | 100 | 2018-04-26 | 2021-04-26 | 2021-07-06 | 2021-07-06 | 2021-04-26 |  | لا يوجد تأخير |  | 46.61 | 24.8862 | منجز | No
2100016122 | وزارة الموارد البشرية والتنمية الإجتماعية | تشييد | ذات اولوية منخفضة | 17123680.56 | 856184.028 | 12589222.11 | 12589222.11 | 1010219247 | لا | 0 | 190209044269 | مسحوب | الكميات التي تم تركيبها | 85 | 100 | 2014-12-28 | 2016-12-05 | 2022-07-05 | 2022-07-05 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 45.152 | 25.181 | مسحوب | No
2100087721 | وزارة الموارد البشرية والتنمية الإجتماعية | تشييد | ذات اولوية منخفضة | 17153464 | 857673.2 | 13905042.89 | 13905042.89 | 1010219247 | لا | 0 | 190209044274 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-12-28 | 2016-12-05 | 2021-12-31 | 2021-12-31 | 2016-12-05 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 44.8482 | 26.3099 | منجز | No
2100039793 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 26171817 | 1308590.85 | 17243406 | 17243406 | 4030023505 | لا | 0 | 180809053209 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 99.7 | 100 | 2015-07-28 | 2017-07-27 | 2023-01-03 | 2023-01-03 |  |  |  |  | 38.3339 | 23.8632 | Failed | No
2100039093 | وزارة الداخلية / المديرية العامة للدفاع المدني | تشييد | ذات اولوية عالية وعاجلة | 11941205.25 | 597060.2625 | 9347210.25 | 9347210.25 | 1010148726 | لا | 0 | 190309067111 | جاري | الكميات التي تم تركيبها | 85 | 100 | 2016-05-22 | 2018-11-14 | 2022-04-01 | 2022-04-01 |  |  | ضعف كفاءة المقاول الفنية |  | 40.0446 | 21.3395 | Failed | No
2100088056 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 9428684.49 | 471434.2245 | 9393214.9 | 0 | 1010060469 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2016-12-25 | 2018-09-17 | 2019-10-20 | 2019-10-20 | 2018-09-17 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.6509 | 17.1567 | منجز | Yes
2100054530 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 115525324 | 5776266.2 | 52713556 | 52713556 | 1010008118 | لا | 0 | 200209140938 | مسحوب | منهجية القيمة المكتسبة | 95 | 100 | 2010-03-01 | 2012-02-28 | 2022-06-28 | 2022-06-28 |  |  | ضعف كفاءة المقاول الفنية |  | 38.3083 | 23.9585 | مسحوب | No
2100100951 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 239007622 | 11950381.1 | 127106714.73 | 127106714.73 | 1010224378 | لا | 0 | 200209141207 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2010-02-23 | 2012-02-23 | 2022-05-12 | 2022-05-12 | 2012-02-23 |  |  |  | 38.1572 | 24.0071 | منجز | No
2100090451 | وزارة الموارد البشرية والتنمية الإجتماعية | تشييد | ذات اولوية منخفضة | 15561831.42 | 778091.571 | 5771897.83 | 5771897.83 | 1010145283 | لا | 0 | 190209044356 | فسخ العقد | الكميات التي تم تركيبها | 76 | 100 | 2015-04-19 | 2017-03-28 | 2021-10-03 | 2021-10-03 |  |  | ضعف كفاءة المقاول الفنية |  | 38.0829 | 24.1239 | مسحوب | No
2100061806 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 79977356.55 | 3998867.8275 | 42013380 | 42013380 | 4030056662 | لا | 0 | 181101338461 | جاري | منهجية القيمة المكتسبة | 91.39 | 96.43 | 2019-02-11 | 2022-02-09 | 2023-01-26 | 2023-01-26 |  |  | موافقات |  | 38.1963 | 24.0222 | Failed | No
2100085901 | وزارة الدفاع / الإدارة الهندسية والاشغال بالخدمات الصحية | تشييد | ذات اولوية متوسطة | 16152319.25 | 807615.9625 | 10121228.16 | 10121228.16 | 1010178740 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 71.6 | 100 | 2014-01-03 | 2015-12-11 | 2021-12-31 | 2021-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5808 | 28.4103 | Failed | No
2100084125 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 39999999 | 1999999.95 | 39999999 | 39999999 | 4031050858 | لا | 0 | 200309001357 | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2010-08-24 | 2014-02-23 | 2015-12-09 | 2015-12-09 | 2014-02-23 | 2018-10-07 |  |  | 39.8426 | 21.375 | منجز | No
2100050562 | أمانة / جدة | تشييد | ذات اولوية عالية وعاجلة | 25900085 | 1295004.25 | 3945077 | 1111047 | 1010004413 | لا | 0 | 190301050675 | مسحوب | تكلفة العمل المنجز | 19.8 | 100 | 2019-05-29 | 2021-05-06 | 2021-05-06 | 2021-05-06 |  |  | اخرى |  | 39.1995 | 21.5158 | مسحوب | No
2100048672 | أمانة / الباحة | تشييد | ذات اولوية عالية | 8932124 | 446606.2 | 8038854 | 8038854 | 4030007950 | لا | 0 | 180501006982 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-10-09 | 2020-04-01 | 2022-08-03 | 2022-08-03 | 2020-04-01 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 41.3665 | 20.0546 | منجز | No
2100029890 | أمانة / الباحة | تشييد | ذات اولوية عالية وعاجلة | 9185850 | 459292.5 | 5250832 | 2068740.74 | 4030159820 | لا | 0 | 180401004343 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 65 | 100 | 2018-10-20 | 2021-10-21 | 2022-11-01 | 2022-11-01 | 2021-10-21 |  | ضعف كفاءة المقاول الفنية |  | 41.4702 | 20.0069 | منجز | No
2100013731 | أمانة / الباحة | تشييد | ذات اولوية عالية | 4009641.75 | 200482.0875 | 2013522.39 | 999908.08 | 5800000059 | لا | 0 | 190909075849 | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 95 | 100 | 2019-08-26 | 2021-02-07 | 2023-02-15 | 2023-02-15 |  |  | ضعف كفاءة المقاول الفنية |  | 41.7499 | 19.7944 | Failed | No
2100189766 | وزارة الاعلام | توريد وتركيب | ذات اولوية عالية وعاجلة | 14940714 | 747035.7 | 13717383 | 13717383 | 1010000849 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 90 | 100 | 2017-07-04 | 2018-04-24 | 2021-12-31 | 2021-12-31 |  | 2018-04-24 |  |  | 42.8251 | 16.3915 | منجز | No
2100091486 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية | 190348545 | 9517427.25 | 114320417.5 | 114320417.5 | 1116000094 | لا | 0 | 181209451330 | مسحوب | منهجية القيمة المكتسبة | 61.8 | 100 | 2014-01-08 | 2016-12-06 | 2024-12-31 | 2024-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 41.482 | 20.0136 | مسحوب | No
2100038765 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 3000000 | 150000 | 2670440.75 | 2396885.75 | 1010227442 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 90.38 | 100 | 2019-12-19 | 2020-06-19 | 2020-08-20 | 2020-08-20 |  | 2020-06-19 | لا يوجد تأخير |  | 46.5239 | 24.4722 | منجز | No
2100089062 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2128091 | 106404.55 | 1393613 | 1393613 | 1128007879 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 40 | 100 | 2012-12-07 | 2014-03-02 | 2022-11-30 | 2022-11-30 |  |  | ضعف كفاءة المقاول الفنية |  | 43.6565 | 26.1508 | مسحوب | No
2100050002 | أمانة / تبوك | تشييد | ذات اولوية منخفضة | 96000000 | 4800000 | 73409887 | 67545600 | 7001378830 | لا | 0 | 181209413989 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-11-14 | 2016-11-13 | 2021-09-09 | 2021-09-09 | 2016-11-13 |  | ضعف كفاءة المقاول الفنية |  | 36.5665 | 28.3712 | منجز | No
2100024953 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 8980000 | 449000 | 9429000 | 9429000 | 4030170755 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 98 | 2019-02-13 | 2021-01-21 | 2021-01-21 | 2021-01-21 | 2021-01-21 | 2022-01-22 | ضعف كفاءة المقاول الفنية |  | 39.0232 | 22.786 | منجز | No
2100006823 | أمانة / الجوف | دراسة الجدوى | ذات اولوية متوسطة | 698000 | 34900 | 698000 | 698000 | 3400014764 | لا | 0 | 200309142560 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-11-18 | 2020-07-16 | 2020-07-07 | 2020-07-07 | 2020-07-16 |  | اخرى |  | 38.2216 | 30.5155 | منجز | No
2100070184 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 7159635.27 | 357981.7635 | 0 | 0 | 1010142553 | لا | 0 |  | مسحوب | التكلفة المفوترة | 12 | 100 | 2008-12-25 | 2010-08-05 | 2023-03-02 | 2023-03-02 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.5429 | 16.8808 | مسحوب | No
2100059570 | جامعة الحدود الشمالية | تشييد | ذات اولوية عالية | 127690465 | 6384523.25 | 113091731 | 111502876 | 2050034321 | لا | 0 | 180809063397 | جاري | تكلفة العمل المنجز | 92 | 100 | 2012-02-21 | 2014-10-20 | 2023-12-31 | 2023-12-31 |  |  | موافقات |  | 41.0346 | 30.951 | متأخر | No
2100191365 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية وعاجلة | 79792530.72 | 3989626.536 | 4635351.92 | 0 | 1010014477 | لا | 0 | 190901074381 | جاري | منهجية القيمة المكتسبة | 13.77 | 22.25 | 2021-04-27 | 2024-03-25 | 2024-03-25 | 2024-03-25 |  |  |  |  | 42.9941 | 27.464 | متأخر | Yes
2100060594 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية متوسطة | 7955000 | 397750 | 8323090.35 | 5791125.38 | 1128004284 | لا | 0 | 180709019639 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-10-15 | 2019-09-24 | 2020-11-24 | 2020-11-24 |  | 2019-09-24 | لا يوجد تأخير |  | 43.9875 | 26.0873 | منجز | No
2100100564 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 525000 | 26250 | 525000 | 525000 | 2050106016 | لا | 0 | 181101289184 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-06-05 | 2019-05-30 | 2019-05-30 | 2019-05-30 | 2019-05-30 |  | ضعف كفاءة المقاول الفنية |  | 40.8094 | 20.9463 | منجز | No
2100041414 | أمانة / نجران | دراسات هندسية | ذات اولوية متوسطة | 5295262.5 | 264763.125 | 4496732.39 | 3475094 | 2051044864 | لا | 0 | 230109005179 | جاري | تكلفة العمل المنجز | 80.88 | 100 | 2015-02-16 | 2018-06-24 | 2023-03-30 | 2023-03-30 |  |  | ضعف اداء الاستشاري |  | 44.2336 | 17.5706 | خدمات عامة | No
2100090985 | أمانة / الباحة | تشييد | ذات اولوية عالية | 1329650 | 66482.5 | 0 | 0 | 5802004740 | لا | 0 |  | لم يبدأ | تكلفة العمل المنجز | 0 | 0 | 2020-03-11 | 2020-12-06 | 2022-10-01 | 2022-10-01 |  |  |  |  | 41.271 | 20.1682 | Failed | No
2100107973 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 6704321.4 | 335216.07 | 2022931.58 | 0 | 2050052248 | لا | 0 |  | جاري | التكلفة المفوترة | 60 | 100 | 2015-08-29 | 2017-02-19 | 2022-08-10 | 2022-08-10 |  |  | ضعف كفاءة المقاول الفنية |  | 41.4779 | 20.0185 | Failed | Yes
2100179922 | جامعة حائل | تشييد | ذات اولوية عالية وعاجلة | 110515153.5 | 5525757.675 | 84662363.9 | 84662363.9 | 1010078607 | لا | 0 | 190309092322 | جاري | تكلفة العمل المنجز | 70.82 | 95 | 2014-12-14 | 2022-07-16 | 2023-03-28 | 2023-03-28 |  |  |  |  | 41.7165 | 27.6594 | متأخر | No
2100081852 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 2071200 | 103560 | 2071200 | 2071200 | 5907024458 | لا | 0 | 190901089785 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 90 | 82 | 2019-09-04 | 2020-09-03 | 2022-08-03 | 2022-08-03 | 2020-09-03 |  |  |  | 41.4701 | 20.0165 | منجز | No
2100049291 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البرية | تشييد | ذات اولوية متوسطة | 14999996 | 749999.8 | 14999996 | 14999996 | 1010209661 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-10-06 | 2020-08-25 | 2021-11-30 | 2021-11-30 | 2020-08-25 |  | تأخرصرف المستحقات المالية |  | 36.5492 | 28.3829 | منجز | No
2100031706 | أمانة / الجوف | تشييد | ذات اولوية عالية | 900000 | 45000 | 900000 | 900000 | 3400016537 | لا | 0 | 181109223435 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-08-01 | 2019-03-26 | 2019-03-27 | 2019-03-27 | 2019-03-26 |  |  |  | 39.3236 | 29.8806 | منجز | No
2100009715 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 2135300 | 106765 | 2224819.42 | 2224819.42 | 4605000749 | لا | 0 | 190601024584 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-04-10 | 2020-03-29 | 2020-03-26 | 2020-03-26 | 2020-03-29 |  | سوء التخطيط الاولي للمشروع |  | 39.2088 | 21.4952 | منجز | No
2100069650 | أمانة / نجران | تشييد | ذات اولوية عالية | 35659929 | 1782996.45 | 28909484.68 | 27927887.27 | 5950002027 | لا | 0 | 181109248709 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 93 | 100 | 2015-07-01 | 2016-12-13 | 2022-12-17 | 2022-12-17 | 2016-12-13 |  | ضعف كفاءة المقاول الفنية |  | 44.2658 | 17.5418 | منجز | No
2100005530 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 8531520.5 | 426576.025 | 3605292.76 | 1799589.06 | 1010183010 | لا | 0 | 190209012614 | مسحوب | التكلفة المفوترة | 62 | 100 | 2014-09-09 | 2016-08-29 | 2022-05-04 | 2022-05-04 |  |  | ضعف كفاءة المقاول الفنية |  | 42.0529 | 18.5228 | مسحوب | No
2100017931 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 6327125.25 | 316356.2625 | 3112800.44 | 0 | 1010072637 | لا | 0 |  | مسحوب | التكلفة المفوترة | 65 | 100 | 2015-12-17 | 2017-06-09 | 2023-02-02 | 2023-02-02 |  |  | ضعف كفاءة المقاول الفنية |  | 42.6509 | 17.1567 | مسحوب | Yes
2100012762 | أمانة / الجوف | تشييد | ذات اولوية متوسطة | 1815035 | 90751.75 | 1802221.75 | 1802221.75 | 3403016184 | لا | 0 | 190309013978 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-11-01 | 2019-10-26 | 2021-06-13 | 2021-06-13 | 2019-10-26 |  |  |  | 39.8888 | 29.8108 | منجز | No
2100016730 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 74976890.1 | 3748844.505 | 56832482.6958 | 49195900 | 3555000709 | لا | 0 |  | جاري | تكلفة العمل المنجز | 66 | 82 | 2019-05-28 | 2023-03-13 | 2023-03-13 | 2023-03-13 |  |  | ضعف كفاءة المقاول الفنية |  | 39.5479 | 24.5384 | متأخر | No
2100007000 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 3017884.24 | 150894.212 | 581113.72 | 581113.72 | 1010233819 | لا | 0 | 190909166051 | مسحوب | التكلفة المفوترة | 22 | 100 | 2015-11-15 | 2016-11-09 | 2023-05-31 | 2023-05-31 |  |  | ضعف كفاءة المقاول الفنية |  | 40.0549 | 29.8587 | مسحوب | No
2100032163 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 3206920.6 | 160346.03 | 1097535.6 | 1097535.6 | 1010233819 | لا | 0 | 190909164826 | مسحوب | التكلفة المفوترة | 47 | 100 | 2015-10-06 | 2016-09-30 | 2019-05-28 | 2019-05-28 |  |  | ضعف كفاءة المقاول الفنية |  | 40.0549 | 29.8587 | مسحوب | No
2100067760 | أمانة / الجوف | تشييد | ذات اولوية عالية وعاجلة | 27817661 | 1390883.05 | 17784257.11 | 17784257.11 | 3401011080 | لا | 0 | 180801052681 | ايقاف كلي | الكميات التي تم تركيبها | 77 | 85 | 2018-12-02 | 2020-11-21 | 2023-04-07 | 2023-04-07 |  |  |  |  | 40.1174 | 29.8712 | Failed | No
2100072306 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 2816990.36 | 140849.518 | 2816990.36 | 2816990.36 | 4032026620 | لا | 0 | 180809056576 | مسحوب | تكلفة العمل المنجز | 65 | 100 | 2016-12-27 | 2018-12-17 | 2022-01-01 | 2022-01-01 |  |  | ضعف كفاءة المقاول الفنية |  | 40.4158 | 21.2796 | مسحوب | No
2100008772 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 9778274 | 488913.7 | 9263628 | 9263628 | 4030006066 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-06-30 | 2019-12-23 | 2019-12-23 | 2019-12-23 | 2019-12-23 |  |  |  | 42.8412 | 21.2524 | منجز | No
2100093262 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 10383175 | 519158.75 | 4374431.6275 | 4374431.6275 | 4030071546 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 28.98 | 28.98 | 2009-06-22 | 2015-07-19 | 2015-07-19 | 2015-07-19 |  |  | اخرى |  | 39.8407 | 21.4095 | مسحوب | No
2100076532 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1282500 | 64125 | 903743 | 903743 | 4035001647 | لا | 0 | 200709004530 | فسخ العقد | تكلفة العمل المنجز | 66 | 100 | 2015-08-05 | 2016-07-30 | 2022-01-01 | 2022-01-01 |  |  |  |  | 40.8296 | 20.7224 | مسحوب | No
2100082924 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 32037527 | 1601876.35 | 28435771 | 28435771 | 4031028157 | لا | 0 |  | جاري | تكلفة العمل المنجز | 96.14 | 96.14 | 2014-09-08 | 2017-08-06 | 2017-08-06 | 2017-08-06 |  |  | اخرى | أخرى | 39.872 | 21.3687 | Failed | No
2100028965 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 6475600 | 323780 | 6399302.5 | 6399302.5 | 4030006066 | لا | 0 | 180909094107 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-08-27 | 2019-08-22 | 2019-08-22 | 2019-08-22 | 2019-08-22 |  |  |  | 42.8425 | 21.2536 | منجز | No
2100045732 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 3570970 | 178548.5 | 77000 | 77000 | 1136000438 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 11 | 100 | 2013-12-30 | 2015-12-08 | 2015-12-08 | 2015-12-08 |  |  | ضعف كفاءة المقاول الفنية |  | 37.9297 | 26.5981 | مسحوب | No
2100101765 | شركة المياه الوطنية / منطقة مكة المكرمة | إشراف | ذات اولوية عالية وعاجلة | 2775000 | 138750 | 2659973 | 2659973 | 1010413771 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2018-03-04 | 2020-03-03 | 2020-03-04 | 2020-03-04 | 2020-03-03 |  | لا يوجد تأخير |  | 39.1928 | 21.5282 | منجز | No
2100023855 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية وعاجلة | 16364907 | 818245.35 | 16085907 | 16085907 | 2251003570 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 98.4 | 100 | 2017-11-05 | 2019-10-15 | 2019-10-13 | 2019-10-13 |  | 2019-10-15 | لا يوجد تأخير |  | 49.5539 | 25.3906 | منجز | No
2100024651 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 4999955 | 249997.75 | 0 | 0 | 1010169405 | لا | 0 |  | مسحوب | التكلفة المفوترة | 5 | 100 | 2002-01-20 | 2004-01-09 | 2022-09-30 | 2022-09-30 |  |  | ضعف كفاءة المقاول الفنية |  | 42.4987 | 18.2178 | مسحوب | No
2100088060 | وزارة التعليم | تشييد | ذات اولوية عالية | 6002840.59 | 300142.0295 | 5830993 | 0 | 1132002624 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-05-12 | 2016-01-31 | 2019-02-19 | 2019-02-19 | 2016-01-31 |  | اخرى |  | 39.1677 | 21.5008 | منجز | Yes
2100091674 | شركة المياه الوطنية / منطقة جازان | إشراف | ذات اولوية عالية وعاجلة | 13500000 | 675000 | 11777355.9 | 11777355.9 | 1010348048 | لا | 0 | 180801062192 | جاري | التكلفة المفوترة | 94.9 | 100 | 2018-10-01 | 2021-09-30 | 2022-05-05 | 2022-05-05 |  |  | لا يوجد تأخير |  | 42.8453 | 16.9687 | خدمات عامة | No
2100011384 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية متوسطة | 15014467 | 750723.35 | 13349949.77 | 13349949.77 | 5850025975 | لا | 0 | 180901075305 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-10-04 | 2021-09-01 | 2021-08-29 | 2021-08-29 | 2021-09-01 |  | لا يوجد تأخير |  | 42.7302 | 18.3003 | منجز | No
2100105685 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 72858810.24 | 3642940.512 | 72858810.24 | 72858810.24 | 1010026934 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-02-18 | 2020-01-27 | 2019-12-30 | 2019-12-30 |  | 2020-01-27 | لا يوجد تأخير |  | 39.2309 | 21.5214 | منجز | No
2100042781 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 157624000 | 7881200 | 154085576.8 | 154085576.8 | 1010026934 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 97.79 | 100 | 2015-09-03 | 2017-09-03 | 2020-04-09 | 2020-04-09 | 2017-09-03 |  | لا يوجد تأخير |  | 39.9514 | 21.4737 | منجز | No
2100041285 | شركة المياه الوطنية / منطقة مكة المكرمة | إشراف | ذات اولوية عالية وعاجلة | 1062000 | 53100 | 952509 | 952509 | 4030267376 | لا | 0 |  | جاري | التكلفة المفوترة | 100 | 100 | 2018-01-10 | 2019-07-09 | 2022-06-02 | 2022-06-02 |  |  | لا يوجد تأخير |  | 42.1631 | 22.7205 | خدمات عامة | No
2100080636 | أمانة / عسير | تشييد | ذات اولوية عالية | 13997910 | 699895.5 | 0 | 0 | 5856021642 | لا | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 0 | 100 | 2019-09-29 | 2020-10-04 | 2023-11-08 | 2023-11-08 |  |  |  |  | 43.1219 | 18.0972 | Failed | No
2100092422 | شركة المياه الوطنية / منطقة نجران | تشييد | ذات اولوية عالية | 15604650 | 780232.5 | 15599574.33 | 15599574.33 | 1010130068 | لا | 0 | 190609021405 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 98 | 100 | 2018-04-08 | 2019-09-21 | 2019-11-10 | 2019-11-10 | 2019-09-21 | 2021-01-04 | لا يوجد تأخير |  | 44.2336 | 17.5636 | منجز | No
2100090182 | جامعة الإمام عبدالرحمن بن فيصل | تشييد | ذات اولوية عالية وعاجلة | 344805156.12 | 17240257.806 | 140543306.46 | 140543306.46 | 2055002293 | لا | 0 | 180709035038 | ايقاف كلي | تكلفة العمل المنجز | 50 | 87 | 2014-07-01 | 2017-05-29 | 2022-12-29 | 2022-12-29 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 50.1893 | 26.3919 | Failed | No
2100005294 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2618656 | 130932.8 | 2061584 | 2061584 | 5858030058 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2011-12-28 | 2013-09-18 | 2020-08-07 | 2020-08-07 | 2013-09-18 |  | ضعف كفاءة المقاول الفنية |  | 42.4987 | 18.2178 | منجز | No
2100096250 | شركة المياه الوطنية / منطقة مكة المكرمة | إشراف | ذات اولوية عالية وعاجلة | 4498021.5 | 224901.075 | 4474100.54 | 4474100.54 | 1010322448 | لا | 0 |  | جاري | التكلفة المفوترة | 79 | 94.5 | 2018-04-15 | 2021-03-13 | 2022-05-14 | 2022-05-14 |  |  | لا يوجد تأخير |  | 39.193 | 21.5278 | خدمات عامة | No
2100059500 | جامعة الملك فيصل | تشييد | ذات اولوية عالية | 734750 | 36737.5 | 734750 | 734750 | 1131021122 | لا | 0 | 180809054824 | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2017-11-30 | 2017-12-30 | 2017-12-30 | 2017-12-30 |  | 2017-12-30 | تأخرصرف المستحقات المالية |  | 49.5604 | 25.3897 | منجز | No
2100016984 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية عالية | 17797808.8 | 889890.44 | 17788335.86 | 17788335.86 | 5855007803 | لا | 0 | 180401001725 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-05-23 | 2020-05-01 | 2020-05-01 | 2020-05-01 |  | 2020-05-01 | لا يوجد تأخير |  | 42.6031 | 20.0028 | منجز | No
2100108872 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية متوسطة | 13500475 | 675023.75 | 13500475 | 13500475 | 5855021983 | لا | 0 | 180901090182 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-09-30 | 2020-09-08 | 2020-08-05 | 2020-08-05 |  | 2020-09-08 | لا يوجد تأخير |  | 42.7302 | 18.3003 | منجز | No
2100020871 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية متوسطة | 2598960 | 129948 | 2598950.5 | 2598950.5 | 4040069541 | لا | 0 | 19030111088 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-05-06 | 2020-10-18 | 2020-10-18 | 2020-10-18 | 2020-10-18 |  | لا يوجد تأخير |  | 42.0529 | 18.5228 | منجز | No
2100032583 | جامعة الملك فيصل | تشييد | ذات اولوية عالية | 24327117.33 | 1216355.8665 | 17577672 | 17577672 | 1010006362 | لا | 0 | 180809056667 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 96 | 4 | 2011-08-27 | 2013-08-26 | 2015-01-06 | 2015-01-06 | 2013-08-26 |  | ضعف كفاءة المقاول الفنية |  | 49.5604 | 25.3897 | منجز | No
2100079214 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2561510 | 128075.5 | 86497.02 | 86497.02 | 1010252898 | لا | 0 |  | مسحوب | التكلفة المفوترة | 11 | 100 | 2014-08-18 | 2015-12-11 | 2022-01-12 | 2022-01-12 |  |  | ضعف كفاءة المقاول الفنية |  | 45.2591 | 25.2379 | مسحوب | No
2100108920 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2203825.5 | 110191.275 | 142158.1 | 142158.1 | 3350009773 | لا | 0 |  | مسحوب | التكلفة المفوترة | 10 | 100 | 2016-04-18 | 2017-04-13 | 2021-12-29 | 2021-12-29 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | مسحوب | No
2100040515 | وزارة الصحة / بيشة | تشييد | ذات اولوية عالية | 2237590 | 111879.5 | 2237590 | 2237590 | 4030174468 | لا | 0 | 191101132202 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2020-01-02 | 2020-08-24 | 2020-08-24 | 2020-08-24 | 2020-08-24 |  | تأخرصرف المستحقات المالية |  | 42 | 20 | منجز | No
2100010695 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 12561362.29 | 628068.1145 | 5339033.29 | 4653964.34 | 5855005104 | لا | 0 |  | جاري | التكلفة المفوترة | 90 | 100 | 2012-09-02 | 2014-08-23 | 2022-10-12 | 2022-10-12 |  |  | ضعف كفاءة المقاول الفنية |  | 42.4987 | 18.2178 | متأخر | No
2100016251 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 13304982.55 | 665249.1275 | 10640385.29 | 6451252.03 | 1008248476 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 98 | 97 | 2014-12-27 | 2020-05-20 | 2020-12-14 | 2020-12-14 | 2020-05-20 |  | ضعف كفاءة المقاول الفنية |  | 45.3525 | 25.8912 | منجز | No
2100089924 | جامعة الملك فيصل | تشييد | ذات اولوية عالية | 142326330.23 | 7116316.5115 | 128816134.07 | 128816134.07 | 2050022550 | لا | 0 | 180809057904 | مسحوب | تكلفة العمل المنجز | 96 | 4 | 2011-04-09 | 2014-03-07 | 2016-01-14 | 2016-01-14 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5604 | 25.3897 | مسحوب | No
2100040191 | وزارة التعليم | تشييد | ذات اولوية عالية | 16327606 | 816380.3 | 2882585 | 2882585 | 1010142553 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 33 | 100 | 2014-12-11 | 2017-05-11 | 2017-06-06 | 2017-06-06 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 46.7098 | 24.6275 | مسحوب | No
2100042011 | وزارة التعليم | تشييد | لم تعد تحتاجها الجهة | 2743315.08 | 137165.754 | 1645989 | 1645989 | 1010240529 | لا | 0 |  | مسحوب | التكلفة المفوترة | 60 | 100 | 2012-06-22 | 2013-12-14 | 2013-12-14 | 2013-12-14 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | مسحوب | No
2100023166 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية وعاجلة | 83199674.58 | 4159983.729 | 56133773.96 | 56133773.96 | 5950009827 | لا | 0 | 180709024595 | جاري | تكلفة العمل المنجز | 86 | 100 | 2013-05-08 | 2015-10-25 | 2024-12-31 | 2024-12-31 |  |  | تأخرصرف المستحقات المالية |  | 42.6993 | 18.3796 | متأخر | No
2100079376 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 12594681.61 | 629734.0805 | 6365976.4 | 6365976.4 | 1010223860 | لا | 0 |  | مسحوب | التكلفة المفوترة | 51 | 100 | 2012-11-30 | 2013-12-01 | 2023-02-05 | 2023-02-05 |  |  | ضعف كفاءة المقاول الفنية |  | 42.4987 | 18.2178 | مسحوب | No
2100000626 | جامعة الملك خالد | تشييد | ذات اولوية عالية وعاجلة | 99364114.2 | 4968205.71 | 98085635 | 88419229.76 | 5855000147 | لا | 0 | 181109278848 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2011-03-20 | 2013-09-03 | 2021-12-10 | 2021-12-10 |  |  | تأخرصرف المستحقات المالية |  | 42.8114 | 18.1027 | متأخر | No
2100062171 | جامعة الملك خالد | تشييد | ذات اولوية عالية وعاجلة | 2526157556.86 | 126307877.843 | 2526157356.86 | 2526157356.86 | 1010434398 | لا | 0 | 181209405199 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2008-10-22 | 2019-12-07 | 2021-06-30 | 2021-06-30 | 2019-12-07 |  | تأخرصرف المستحقات المالية |  | 42.8114 | 18.1027 | منجز | No
2100018001 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 6912938.65 | 345646.9325 | 2485379.77 | 2485379.77 | 2057001038 | لا | 0 | 190209018491 | مسحوب | التكلفة المفوترة | 37 | 100 | 2013-08-24 | 2015-08-14 | 2023-03-01 | 2023-03-01 |  |  | ضعف كفاءة المقاول الفنية |  | 42.0529 | 18.5228 | مسحوب | No
2100048576 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 4671610 | 233580.5 | 4671610 | 4671610 | 5950000442 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 1 | 25 | 2019-09-16 | 2021-12-04 | 2021-12-04 | 2021-12-04 |  |  | اخرى |  | 44.2258 | 17.5795 | مسحوب | No
2100093785 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية عالية | 57879741 | 2893987.05 | 57878689 | 57878689 | 5850031989 | لا | 0 | 190301022225 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 99.38 | 2019-06-09 | 2020-11-21 | 2021-02-12 | 2021-02-12 | 2020-11-21 |  | لا يوجد تأخير |  | 42.4989 | 18.2169 | منجز | No
2100192861 | جامعة القصيم | تشييد | ذات اولوية عالية وعاجلة | 13690972.5 | 684548.625 | 12488265.14 | 12488265.14 | 1128001788 | لا | 0 | 180909083905 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-04-30 | 2015-02-24 | 2015-08-23 | 2015-08-23 | 2015-02-24 |  |  |  | 43.5614 | 26.0764 | منجز | No
2100057595 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2129509 | 106475.45 | 0 | 0 | 1010246941 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 1 | 100 | 2011-11-22 | 2013-02-14 | 2013-03-15 | 2013-03-15 |  |  | ضعف كفاءة المقاول الفنية |  | 44.4412 | 24.5406 | مسحوب | No
2100004756 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 3100345.74 | 155017.287 | 789180.8 | 789180.8 | 1010233819 | لا | 0 |  | مسحوب | التكلفة المفوترة | 26 | 100 | 2015-12-03 | 2016-11-27 | 2023-07-31 | 2023-07-31 |  |  | ضعف كفاءة المقاول الفنية |  | 40.0549 | 29.8587 | مسحوب | No
2100059290 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 57176934.15 | 2858846.7075 | 17441766.7 | 17441766.7 | 1010095105 | لا | 0 | 180709023757 | جاري | تكلفة العمل المنجز | 35 | 100 | 2015-02-01 | 2017-01-01 | 2025-12-31 | 2025-12-31 |  |  | تأخرصرف المستحقات المالية |  | 42.1172 | 19.142 | Failed | No
2100063221 | وزارة الحرس الوطني / الشؤون الصحية | ترميم | ذات اولوية عالية | 21459224.34 | 1072961.217 | 3910710.78 | 3910710.78 | 1010018153 | لا | 0 | 181009204157 | جاري | الكميات التي تم تركيبها | 55 | 100 | 2014-08-25 | 2016-02-16 | 2023-04-30 | 2023-04-30 |  |  | اخرى |  | 49.5345 | 25.4601 | Failed | No
2100041241 | وزارة التعليم | تشييد | ذات اولوية عالية | 25681587.4 | 1284079.37 | 23700869 | 23700869 | 1010099661 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2013-11-04 | 2014-05-15 | 2019-09-29 | 2019-09-29 | 2014-05-15 |  |  |  | 46.7098 | 24.6275 | منجز | No
2100009155 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية وعاجلة | 3145280.25 | 157264.0125 | 1566353.82 | 1135356.32 | 4030219467 | نعم | 15548573.02 | 190301054836 | جاري | تكلفة العمل المنجز | 86 | 100 | 2018-12-10 | 2019-10-06 | 2023-12-31 | 2023-12-31 |  |  | تأخرصرف المستحقات المالية |  | 42.2327 | 18.967 | متأخر | No
2100028210 | جامعة حائل | تشييد | ذات اولوية عالية وعاجلة | 451152144 | 22557607.2 | 358680996.47 | 358680996.47 | 1010054406 | لا | 0 | 190309092125 | جاري | تكلفة العمل المنجز | 79.25 | 96 | 2011-09-26 | 2020-11-11 | 2023-04-09 | 2023-04-09 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.6968 | 27.506 | متأخر | No
2100059054 | وزارة التعليم | تشييد | ذات اولوية عالية | 1043996.8 | 52199.84 | 0 | 0 | 1114000090 | لا | 0 |  | مسحوب | التكلفة المفوترة | 1 | 100 | 2011-05-15 | 2012-01-10 | 2022-12-01 | 2022-12-01 |  |  | ضعف كفاءة المقاول الفنية |  | 45.313 | 24.0763 | مسحوب | No
2100089714 | أمانة / الرياض | دراسة الجدوى | ذات اولوية متوسطة | 5920000 | 296000 | 40033 | 0 | 1010442224 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2010-03-16 | 2012-03-05 | 2012-03-05 | 2012-03-05 | 2012-03-05 |  | اخرى |  |  |  | منجز | Yes
2100079203 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 30475052.43 | 1523752.6215 | 27419970 | 24780615 | 1010300402 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2017-09-17 | 2019-12-06 | 2021-06-12 | 2021-06-12 | 2019-12-06 |  |  |  | 46.8058 | 24.7835 | منجز | No
2100088944 | وزارة التعليم | تشييد | ذات اولوية عالية | 15543526.03 | 777176.3015 | 12511741 | 12511741 | 1010300402 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 77 | 2018-06-02 | 2020-08-20 | 2022-11-02 | 2022-11-02 | 2020-08-20 |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | منجز | No
2100079483 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 8948748 | 447437.4 | 6281419 | 6281419 | 1010156720 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 73 | 100 | 2012-08-31 | 2014-05-23 | 2024-05-08 | 2024-05-08 |  |  | ضعف كفاءة المقاول الفنية |  | 45.3525 | 25.8912 | مسحوب | No
2100099853 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 81403453 | 4070172.65 | 45410368 | 45410368 | 1010236089 | لا | 0 | 200209136963 | ايقاف كلي | منهجية القيمة المكتسبة | 99.7 | 100 | 2013-07-06 | 2015-07-05 | 2023-01-04 | 2023-01-04 |  |  |  |  | 38.1667 | 24.0053 | Failed | No
2100084663 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 32610490 | 1630524.5 | 32610490 | 32610490 | 1010136405 | لا | 0 | 180709023776 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-03-27 | 2019-03-27 | 2022-12-19 | 2022-12-19 | 2019-03-27 |  | ضعف كفاءة المقاول الفنية |  | 38.222 | 24.0036 | منجز | No
2100077873 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تصميم | ذات اولوية عالية وعاجلة | 55728310 | 2786415.5 | 42566986.01 | 42566986.01 | 1010359384 | لا | 0 | 180301001079 | جاري | تكلفة العمل المنجز | 72 | 91 | 2018-10-10 | 2023-10-09 | 2023-10-09 | 2023-10-09 |  |  |  | أخرى | 49.5828 | 26.9705 | متأخر | No
2100086181 | وزارة التعليم | تشييد | ذات اولوية عالية | 2497942.6 | 124897.13 | 544388 | 544388 | 1132002945 | لا | 0 |  | مسحوب | التكلفة المفوترة | 53 | 100 | 2009-01-10 | 2010-05-06 | 2023-02-15 | 2023-02-15 |  |  | ضعف كفاءة المقاول الفنية |  | 44.8241 | 26.3046 | مسحوب | No
2100005331 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية | 53964484.64 | 2698224.232 | 46755810.06 | 46755810.06 | 1010066135 | لا | 0 | 180709023644 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2014-12-23 | 2017-11-19 | 2021-08-18 | 2021-08-18 | 2017-11-19 |  | لا يوجد تأخير |  | 39.5739 | 24.4791 | منجز | No
2100079995 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 46850000 | 2342500 | 45904731 | 45904731 | 1010012911 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 94.197 | 100 | 2016-12-13 | 2019-12-13 | 2021-05-11 | 2021-05-11 | 2019-12-13 |  | لا يوجد تأخير |  | 39.9281 | 21.4828 | منجز | No
2100089876 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية | 51003610 | 2550180.5 | 33123585 | 33123585 | 4030057371 | لا | 0 | 180709025828 | مسحوب | منهجية القيمة المكتسبة | 68.73 | 100 | 2014-05-25 | 2016-05-03 | 2023-08-01 | 2023-08-01 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 40.4731 | 26.0049 | مسحوب | No
2100003920 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية | 130598877.44 | 6529943.872 | 104628017.81 | 104628017.81 | 1010014477 | لا | 0 | 180709026154 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 96.5 | 100 | 2015-02-01 | 2017-01-10 | 2022-02-16 | 2022-02-16 | 2017-01-10 |  | لا يوجد تأخير |  | 41.6968 | 27.506 | منجز | No
2100054865 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 25798164.66 | 1289908.233 | 23770120 | 23770120 | 1010136405 | لا | 0 | 180809056618 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-04-11 | 2019-04-11 | 2022-05-05 | 2022-05-05 | 2019-04-11 |  |  |  | 38.276 | 23.9806 | منجز | No
2100085960 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 25415032.23 | 1270751.6115 | 24046281 | 24046281 | 1010172403 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2012-04-20 | 2014-04-10 | 2015-07-06 | 2015-07-06 | 2014-04-10 |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | منجز | No
2100096353 | وزارة التعليم | تشييد | ذات اولوية عالية | 19186451 | 959322.55 | 2524302 | 2524302 | 1010142553 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 16 | 100 | 2015-08-16 | 2017-11-03 | 2017-11-03 | 2017-11-03 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | مسحوب | No
2100095152 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 14974748 | 748737.4 | 13477240 | 13477240 | 1010136405 | لا | 0 | 180909079013 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 98.8 | 98.8 | 2017-03-13 | 2019-03-13 | 2023-05-07 | 2023-05-07 |  |  | أوامر تغيير |  | 38.3558 | 23.823 | منتظم | No
2100006473 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 43089938 | 2154496.9 | 34648365 | 34648365 | 4030113058 | لا | 0 | 180709031357 | مسحوب | منهجية القيمة المكتسبة | 85.9 | 100 | 2018-01-30 | 2019-03-01 | 2022-07-18 | 2022-07-18 |  |  | أوامر تغيير |  | 38.2197 | 23.99 | مسحوب | No
2100008212 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 9303730 | 465186.5 | 8529022.21 | 8529022.21 | 2050052043 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 91.73 | 100 | 2017-09-09 | 2020-08-08 | 2020-07-20 | 2020-07-20 |  | 2020-08-08 | لا يوجد تأخير |  | 45.9683 | 28.3667 | منجز | No
2100097462 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 29299914.7 | 1464995.735 | 21507579.55 | 21507579.55 | 1118000516 | لا | 0 | 190309028069 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 98.4 | 100 | 2010-10-02 | 2013-03-05 | 2020-01-12 | 2020-01-12 |  | 2013-03-05 | لا يوجد تأخير |  | 46.7271 | 22.2863 | منجز | No
2100095620 | شركة المياه الوطنية | تشييد | ذات اولوية عالية | 6151501 | 307575.05 | 6151360.13 | 6151360.13 | 1010127437 | لا | 0 | 181101287428 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 99.01 | 100 | 2017-12-13 | 2018-08-07 | 2019-02-06 | 2019-02-06 |  | 2018-08-07 | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100097823 | شركة المياه الوطنية | تشييد | ذات اولوية عالية | 54997321 | 2749866.05 | 47772110 | 47772110 | 1010022543 | لا | 0 | 180201000120 | جاري | منهجية القيمة المكتسبة | 100 | 100 | 2018-04-17 | 2021-03-14 | 2022-03-28 | 2022-03-28 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 46.7098 | 24.6275 | متأخر | No
2100039421 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 74900000 | 3745000 | 59920000 | 59920000 | 1010017123 | لا | 0 | 190309057966 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 99.87 | 100 | 2018-08-29 | 2020-08-27 | 2023-06-06 | 2023-06-06 |  |  | عدم اكتمال أو ضعف أعمال التصميم والدراسات |  | 38.3504 | 23.9285 | Failed | No
2100098991 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 14470955.67 | 723547.7835 | 14129635.51 | 14129635.51 | 1010070222 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-09-12 | 2019-08-28 | 2019-08-28 | 2019-08-28 | 2019-08-28 |  |  |  | 45.3525 | 25.8912 | منجز | No
2100193362 | الجمارك السعودية | إشراف | ذات اولوية عالية | 3432000 | 171600 | 3050769.26 | 2645935.92 | 1010312946 | لا | 0 | 181209408749 | ايقاف كلي | تكلفة العمل المنجز | 88 | 100 | 2014-05-12 | 2017-03-23 | 2017-03-23 | 2017-03-23 |  |  |  |  | 55.2282 | 22.5481 | Failed | No
2100103714 | وزارة التعليم | تشييد | ذات اولوية عالية | 14684751.1 | 734237.555 | 3262628.7 | 3262628.7 | 1010051817 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 25 | 100 | 2014-12-15 | 2018-01-28 | 2018-01-28 | 2018-01-28 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | مسحوب | No
2100108452 | وزارة التعليم | تشييد | ذات اولوية عالية | 3144319 | 157215.95 | 2368321 | 2368321 | 1010191039 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-05-12 | 2019-05-02 | 2019-05-02 | 2019-05-02 | 2019-05-02 |  |  |  | 46.7098 | 24.6275 | منجز | No
2100193480 | الجمارك السعودية | إشراف | ذات اولوية عالية | 18505159.54 | 925257.977 | 16497469.98 | 16497469.98 | 5951001037 | لا | 0 | 200601011018 | جاري | تكلفة العمل المنجز | 89 | 100 | 2020-06-05 | 2021-07-04 | 2021-12-16 | 2021-12-16 |  |  |  |  | 42.8714 | 16.4111 | خدمات عامة | No
2100021851 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 22110000 | 1105500 | 22110000 | 22110000 | 1010026934 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-02-18 | 2019-02-07 | 2018-12-31 | 2018-12-31 | 2019-02-07 |  | لا يوجد تأخير |  | 39.1986 | 21.5917 | منجز | No
2100074045 | شركة المياه الوطنية / منطقة مكة المكرمة | إشراف | ذات اولوية عالية | 2327012.5 | 116350.625 | 2327012.5 | 2327012.5 | 1010326770 | لا | 0 |  | منجز – استلام نهائي | التكلفة المفوترة | 100 | 100 | 2016-11-20 | 2018-10-30 | 2018-10-29 | 2018-10-29 |  | 2018-10-30 | لا يوجد تأخير |  | 39.202 | 21.7837 | منجز | No
2100023295 | جامعة الملك سعود | تشييد | ذات اولوية عالية | 44299957.11 | 2214997.8555 | 26846918.39 | 26846918.39 | 1010217074 | لا | 0 | 1808010009092 | جاري | تكلفة العمل المنجز | 77 | 100 | 2018-10-01 | 2020-09-27 | 2022-04-26 | 2022-04-26 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 46.7098 | 24.6275 | متأخر | No
2100089740 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 97880211.39 | 4894010.5695 | 92337739.53 | 92337739.53 | 1010066115 | لا | 0 | 180809043264 | جاري | منهجية القيمة المكتسبة | 93 | 100 | 2017-07-19 | 2019-07-17 | 2023-09-17 | 2023-09-17 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 49.6626 | 27.0037 | متأخر | No
2100010430 | جامعة الملك سعود | تشييد | ذات اولوية عالية | 27188488 | 1359424.4 | 20808656.5 | 17409325.67 | 1010076960 | لا | 0 | 190409002130 | ايقاف كلي | تكلفة العمل المنجز | 79 | 86 | 2018-01-24 | 2023-06-09 | 2023-06-09 | 2023-06-09 |  |  | عدم اكتمال أو ضعف أعمال التصميم والدراسات |  | 46.7098 | 24.6275 | Failed | No
2100034926 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 612155 | 30607.75 | 550605 | 550605 | 3550025589 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-10-17 | 2017-02-19 | 2020-04-30 | 2020-04-30 | 2017-02-19 |  | ضعف كفاءة المقاول الفنية |  | 36.517 | 27.415 | منجز | No
2100064621 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 611143946.7 | 30557197.335 | 457322949.626 | 457322949.626 | 2252000135 | لا | 0 | 180809049347 | جاري | منهجية القيمة المكتسبة | 89 | 89 | 2014-05-22 | 2018-05-17 | 2023-12-18 | 2023-12-18 |  |  | لا يوجد تأخير |  | 49.6626 | 27.0037 | منتظم | No
2100004266 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 19605489 | 980274.45 | 19299248.27 | 19234563.95 | 4650050716 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-04-17 | 2020-04-11 | 2020-07-10 | 2020-07-10 | 2020-04-11 |  | أوامر تغيير |  |  |  | منجز | No
2100020263 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 2293140 | 114657 | 1329122 | 1329122 | 1010217919 | لا | 0 |  | مسحوب | اخرى | 62 | 100 | 2018-02-06 | 2018-11-02 | 2018-11-02 | 2018-11-02 |  |  | ضعف كفاءة المقاول الفنية |  | 46.8637 | 24.7688 | مسحوب | No
2100020440 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية وعاجلة | 19053373.5 | 952668.675 | 10159315.5 | 10159315.5 | 1010259143 | لا | 0 |  | جاري | اخرى | 85 | 100 | 2020-03-30 | 2022-01-01 | 2022-02-27 | 2022-02-27 |  |  |  |  | 46.8637 | 24.7688 | Failed | No
2100026821 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2941353 | 147067.65 | 1029473.55 | 1029473.55 | 1010242421 | نعم | 1029473.55 |  | فسخ العقد | تكلفة العمل المنجز | 35 | 100 | 2011-09-20 | 2014-03-13 | 2019-08-14 | 2019-08-14 |  |  | ضعف كفاءة المقاول الفنية |  | 44.7813 | 20.4716 | مسحوب | No
2100063943 | أمانة / عسير | تشييد | ذات اولوية عالية | 4999050 | 249952.5 | 3797989.08 | 3797989.08 | 5855031154 | لا | 0 | 200201026420 | فسخ العقد | تكلفة العمل المنجز | 100 | 100 | 2019-08-22 | 2020-02-17 | 2022-05-16 | 2022-05-16 |  |  | ضعف كفاءة المقاول الفنية |  | 42.517 | 18.2422 | مسحوب | No
2100057610 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 2100000 | 105000 | 1305175.2 | 1305175.2 | 1017000870 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 62 | 100 | 2011-09-18 | 2012-09-12 | 2012-09-12 | 2012-09-12 |  |  | ضعف كفاءة المقاول الفنية |  | 42.843 | 21.2579 | مسحوب | No
2100004502 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1215040 | 60752 | 1215040 | 1215040 | 1010031532 | لا | 0 | 190301010434 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-02-18 | 2020-02-13 | 2020-02-13 | 2020-02-13 | 2020-02-13 |  | ضعف كفاءة المقاول الفنية |  | 41.7425 | 22.4319 | منجز | No
2100002483 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 3420120 | 171006 | 3285120 | 3285120 | 4038000474 | لا | 0 | 210301198284 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-08-25 | 2020-02-20 | 2020-11-26 | 2020-11-26 | 2020-02-20 |  | ضعف كفاءة المقاول الفنية |  | 42.1952 | 22.7289 | منجز | No
2100090543 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 11315941.74 | 565797.087 | 10098920.25 | 10098920.25 | 1010168999 | لا | 0 | 180909099001 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-08-01 | 2020-11-13 | 2020-04-20 | 2020-04-20 | 2020-11-13 |  |  |  | 42.8438 | 21.2517 | منجز | No
2100020160 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 1467160 | 73358 | 1467160 | 1467160 | 4650009788 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2018-12-30 | 2019-07-13 | 2019-11-30 | 2019-11-30 | 2019-07-13 | [5 empty] | منجز | No
2100040272 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 590105 | 29505.25 | 590105 | 590105 | 4030071125 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2018-12-23 | 2019-08-01 | 2019-08-01 | 2019-08-01 | 2019-08-01 |  |  |  | 39.9608 | 21.3345 | منجز | No
2100067771 | أمانة / الجوف | تشييد | ذات اولوية عالية | 233500 | 11675 | 233500 | 210074 | 3452003891 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-02-25 | 2020-08-25 | 2020-08-25 | 2020-08-25 | 2020-08-25 |  |  |  | 37.9802 | 30.7222 | منجز | No
2100027204 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 9998718.49 | 499935.9245 | 1813275.15 | 1705952.06 | 1131033244 | لا | 0 | 210109009957 | مسحوب | منهجية القيمة المكتسبة | 24.02 | 100 | 2015-08-09 | 2017-07-18 | 2023-11-05 | 2023-11-05 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.9095 | 23.8972 | مسحوب | No
2100083112 | أمانة / جازان | تشييد | ذات اولوية عالية وعاجلة | 2989525 | 149476.25 | 1899485 | 0 | 1010154889 | لا | 0 | 200809126358 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-04-29 | 2020-04-23 | 2020-04-24 | 2020-04-24 | 2020-04-23 |  | ضعف كفاءة المقاول الفنية |  | 42.547 | 16.9151 | منجز | Yes
2100022702 | أمانة / جازان | تصميم | ذات اولوية متوسطة | 895500 | 44775 | 895500 | 895500 | 1010333496 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-08-03 | 2016-07-18 | 2019-02-25 | 2019-02-25 | 2016-07-18 |  | اخرى |  | 42.5938 | 16.8775 | منجز | No
2100009870 | وزارة التعليم | تشييد | ذات اولوية عالية | 17111263.76 | 855563.188 | 7319781 | 7319781 | 1010020305 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 95 | 100 | 2007-08-04 | 2009-01-25 | 2022-05-11 | 2022-05-11 | 2009-01-25 |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | منجز | No
2100092805 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 2524750 | 126237.5 | 2297231 | 2297231 | 1010158252 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-09-03 | 2019-09-25 | 2020-09-13 | 2020-09-13 | 2019-09-25 |  | ضعف كفاءة المقاول الفنية |  | 43.3657 | 29.949 | منجز | No
2100194121 | أمانة / جدة | أخرى | ذات اولوية عالية وعاجلة | 1071000 | 53550 | 717525 | 217103.89 | 4030153746 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 85 | 100 | 2020-02-10 | 2021-02-09 | 2021-06-26 | 2021-06-26 | 2021-02-09 |  |  |  | 39.3481 | 22.1117 | منجز | No
2100002295 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 37569400 | 1878470 | 27054798.5 | 27054798.5 | 1010004413 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 75.58 | 100 | 2015-09-06 | 2019-07-10 | 2020-08-23 | 2020-08-23 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6869 | 24.6978 | Failed | No
2100000582 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 16474750 | 823737.5 | 16308654.2 | 14661659 | 1010158780 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99.17 | 100 | 2019-05-15 | 2021-05-16 | 2021-07-28 | 2021-07-28 | 2021-05-16 |  | لا يوجد تأخير |  | 46.8155 | 24.7866 | منجز | No
2100067034 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 21256690 | 1062834.5 | 3442074.37 | 3442074.37 | 5950009685 | لا | 0 | 180801065406 | ايقاف جزئي | تكلفة العمل المنجز | 16 | 25 | 2018-11-25 | 2020-05-10 | 2022-09-11 | 2022-09-11 |  |  | اخرى |  | 44.21 | 17.5266 | Failed | No
2100045931 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 4450000 | 222500 | 2754322 | 0 | 3552000023 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 65 | 60 | 2019-02-09 | 2020-08-08 | 2023-03-08 | 2023-03-08 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 36.5031 | 28.3956 | منتظم | Yes
2100049884 | أمانة / جدة | تشييد | ذات اولوية عالية وعاجلة | 12585558 | 629277.9 | 11395018 | 11395018 | 4650007032 | لا | 0 | 181209452964 | منجز – استلام نهائي | الكميات التي تم تركيبها | 86 | 86 | 2015-06-13 | 2017-05-21 | 2020-11-15 | 2020-11-15 | 2017-05-21 | 2020-11-15 | اخرى |  | 39.1903 | 21.535 | منجز | No
2100194364 | أمانة / جدة | أخرى | ذات اولوية عالية وعاجلة | 46499250 | 2324962.5 | 38946250 | 22580250 | 1010158466 | لا | 0 | 200201096495 | جاري | منهجية القيمة المكتسبة | 91.5 | 90.1 | 2020-07-12 | 2022-06-20 | 2023-10-22 | 2023-10-22 |  |  |  |  | 39.1677 | 21.5008 | خدمات عامة | No
2100078514 | أمانة / جدة | ادارة مشاريع | ذات اولوية عالية وعاجلة | 177934580 | 8896729 | 111753490.27 | 87480608.14 | 2051025367 | لا | 0 | 180401002924 | جاري | مدفوعات ساعات العمل | 75.4 | 75.4 | 2018-10-14 | 2021-10-14 | 2024-05-22 | 2024-05-22 |  |  | اخرى |  |  |  | خدمات عامة | No
2100194353 | أمانة / جدة | أخرى | ذات اولوية متوسطة | 3945530 | 197276.5 | 2465956.5 | 2137162.3 | 1010059725 | لا | 0 | 200004575585 | جاري | تكلفة العمل المنجز | 70.8 | 70.8 | 2021-08-17 | 2023-07-26 | 2023-07-26 | 2023-07-26 |  |  |  |  | 39.1677 | 21.5008 | خدمات عامة | No
2100194482 | أمانة / الطائف | مساحة | ذات اولوية متوسطة | 477250 | 23862.5 | 0 | 0 | 4650047424 | لا | 0 | 210501053358 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2021-05-09 | 2021-11-09 | 2021-11-09 | 2021-11-09 | 2021-11-09 |  |  |  | 40.4511 | 21.2747 | منجز | No
2100194935 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية عالية | 3999996 | 199999.8 | 1557661 | 0 | 0 | لا | 0 |  | جاري | تكلفة العمل المنجز | 80 | 100 | 2019-12-12 | 2021-08-25 | 2021-08-25 | 2021-08-25 |  |  |  |  | 39.3577 | 22.1131 | Failed | Yes
2100015116 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 53365709 | 2668285.45 | 48029138.1 | 18766920.17 | 5950006860 | لا | 0 | 180809044337 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95.46 | 100 | 2014-09-04 | 2017-01-15 | 2022-12-17 | 2022-12-17 | 2017-01-15 |  | التنسيق مع أصحاب المصلحه (خدمات |  | 44.3043 | 17.5334 | منجز | No
2100032200 | أمانة / تبوك | تشييد | ذات اولوية عالية وعاجلة | 83247000 | 4162350 | 83247000 | 74924381.42 | 4030139128 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-03-04 | 2016-03-03 | 2019-02-27 | 2019-02-27 | 2016-03-03 |  | ضعف كفاءة المقاول الفنية |  | 36.5876 | 28.4119 | منجز | No
2100095826 | هيئة المدن الصناعية ومناطق التقنية | تشييد | ذات اولوية عالية | 22624098 | 1131204.9 | 20790841 | 20790841 | 1010044185 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2020-01-12 | 2021-07-11 | 2022-03-08 | 2022-03-08 | 2021-07-11 |  | لا يوجد تأخير |  | 21.901 | 39.2881 | منجز | No
2100050061 | أمانة / تبوك | تشييد | لم تعد تحتاجها الجهة | 1302000 | 65100 | 1302000 | 1302000 | 3553000034 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-11-08 | 2015-11-05 | 2018-01-04 | 2018-01-04 | 2015-11-05 |  | اخرى |  | 36.5744 | 28.4571 | منجز | No
2100023343 | أمانة / جدة | تشييد | ذات اولوية عالية وعاجلة | 120480927 | 6024046.35 | 105834221.94 | 105834221.94 | 4030007856 | لا | 0 | 190609072912 | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2019-06-16 | 2020-06-16 | 2020-11-12 | 2020-11-12 | 2020-06-16 | 2020-11-01 | عدم اكتمال أو ضعف أعمال التصميم والدراسات |  | 39.2154 | 21.5137 | منجز | No
2100047585 | أمانة / الجوف | تشييد | ذات اولوية عالية | 1321000 | 66050 | 1321000 | 1321000 | 3402001608 | لا | 0 | 191101093361 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-07-29 | 2020-01-22 | 2020-01-22 | 2020-01-22 | 2020-01-22 |  |  |  | 37.3445 | 31.3459 | منجز | No
2100178371 | وزارة الثقافة | تشييد | ذات اولوية عالية | 32950119.02 | 1647505.951 | 22819606.79 | 22819606.79 | 1010070634 | لا | 0 | 201109074284 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-04-09 | 2020-03-10 | 2020-03-10 | 2020-03-10 |  |  |  |  | 41.4639 | 20.0355 | Failed | No
2100028254 | هيئة المدن الصناعية ومناطق التقنية | تشييد | ذات اولوية عالية | 294802962 | 14740148.1 | 259799674 | 259799674 | 1010090968 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 98 | 100 | 2018-01-30 | 2020-07-29 | 2022-09-27 | 2022-09-27 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 31.7107 | 38.9753 | متأخر | No
2100061655 | صندوق تنمية الموارد البشرية | تشييد | ذات اولوية منخفضة | 30009375.28 | 1500468.764 | 11282836.08 | 11282836.08 | 1010145283 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 73 | 100 | 2015-04-21 | 2017-03-29 | 2021-09-08 | 2021-09-08 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 38.1902 | 24.0148 | مسحوب | No
2100194994 | أمانة / الطائف | مساحة | ذات اولوية متوسطة | 1890000 | 94500 | 1890000 | 1890000 | 1010367220 | لا | 0 | 191001203292 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-09-01 | 2020-08-26 | 2020-08-26 | 2020-08-26 | 2020-08-26 |  |  |  | 40.2805 | 21.3649 | منجز | No
2100194515 | أمانة / الطائف | تصميم | ذات اولوية متوسطة | 3346500 | 167325 | 1701137.5 | 1701137.5 | 4650047424 | لا | 0 | 210501053370 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2021-08-08 | 2022-09-17 | 2022-08-08 | 2022-08-08 | 2022-09-17 |  |  |  | 40.4511 | 21.2747 | منجز | No
2100194876 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 5759724 | 287986.2 | 5759724 | 5759724 | 4032015171 | لا | 0 | 191201147274 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-07-05 | 2021-06-30 | 2021-06-30 | 2021-06-30 | 2021-06-30 |  |  |  | 40.4511 | 21.2747 | منجز | No
2100020171 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 888905 | 44445.25 | 888905 | 888905 | 5800010841 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-12-13 | 2019-05-13 | 2020-05-13 | 2020-05-13 | 2019-05-13 |  | لا يوجد تأخير |  | 21.3355 | 39.9652 | منجز | No
2100041624 | أمانة / نجران | دراسة بيئية | ذات اولوية متوسطة | 24580465.8 | 1229023.29 | 15908182.97 | 15908182.97 | 3350029142 | لا | 0 |  | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2019-01-17 | 2021-07-16 | 2022-09-11 | 2022-09-11 | 2021-07-16 |  | اخرى |  | 44.1994 | 17.5613 | منجز | No
2100026810 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 23683998.45 | 1184199.9225 | 19605207 | 19605207 | 5950009437 | لا | 0 | 181209477572 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 96.21 | 100 | 2015-08-23 | 2017-01-30 | 2022-05-30 | 2022-05-30 | 2017-01-30 |  |  |  | 44.2368 | 17.5557 | منجز | No
2100085433 | أمانة / نجران | دراسات هندسية | ذات اولوية متوسطة | 5580000 | 279000 | 5433305 | 5433305 | 3350029142 | لا | 0 | 200609010929 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 69.56 | 100 | 2018-03-05 | 2019-02-21 | 2022-12-17 | 2022-12-17 | 2019-02-21 |  | ضعف اداء الاستشاري |  | 44.2311 | 17.5433 | منجز | No
2100082003 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 3999999.75 | 199999.9875 | 227090 | 227090 | 4031056138 | لا | 0 |  | جاري | تكلفة العمل المنجز | 20.25 | 100 | 2015-05-13 | 2016-05-01 | 2022-02-02 | 2022-02-02 |  |  | اخرى | أخرى | 39.8539 | 21.3881 | Failed | No
2100008433 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 213749334.04 | 10687466.702 | 77107453.5 | 77107453.5 | 1010014477 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 76.1 | 100 | 2014-12-31 | 2016-06-23 | 2023-03-31 | 2023-03-31 |  |  | موافقات | أخرى | 38.0623 | 24.0861 | متأخر | No
2100064400 | أمانة / عسير | تشييد | ذات اولوية عالية | 206330 | 10316.5 | 0 | 0 | 5855035453 | لا | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 0 | 100 | 2014-12-09 | 2015-06-07 | 2023-03-05 | 2023-03-05 |  |  | أوامر سامية |  | 42.6921 | 18.559 | Failed | No
2100012364 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 1087359 | 54367.95 | 349999.82 | 349999.82 | 5950006860 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 94.78 | 100 | 2019-03-18 | 2020-03-05 | 2022-11-17 | 2022-11-17 | 2020-03-05 |  |  |  | 44.2307 | 17.5571 | منجز | No
2100027753 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 1770428 | 88521.4 | 1770428 | 1770428 | 4601000386 | لا | 0 | 190901007666 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-11-18 | 2019-11-07 | 2020-01-15 | 2020-01-15 | 2019-11-07 |  | ضعف كفاءة المقاول الفنية |  | 40.7321 | 19.9164 | منجز | No
2100090484 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 12770100 | 638505 | 3957817.21 | 3957817.21 | 4031019772 | لا | 0 | 200209129524 | جاري | تكلفة العمل المنجز | 30.99 | 30.99 | 2019-05-15 | 2021-08-20 | 2023-01-08 | 2023-01-08 |  |  |  | أخرى | 39.8587 | 21.368 | Failed | No
2100049814 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 5430450 | 271522.5 | 5430450 | 5430450 | 4031045724 | لا | 0 | 180909111102 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-09-15 | 2016-07-31 | 2016-07-31 | 2016-07-31 |  |  |  |  | 39.7024 | 21.5989 | Failed | No
2100067712 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 13198674.6 | 659933.73 | 8626808.97 | 8626808.97 | 4031040412 | لا | 0 | 180909082048 | جاري | تكلفة العمل المنجز | 71.11 | 71.11 | 2015-06-03 | 2020-04-13 | 2023-01-08 | 2023-01-08 |  |  |  | أخرى | 39.8479 | 21.35 | Failed | No
2100041532 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية عالية | 7408275 | 370413.75 | 6979935.6 | 6979935.6 | 4030044382 | لا | 0 | 190301009837 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 94.22 | 94.22 | 2019-05-15 | 2021-04-22 | 2021-07-21 | 2021-07-21 | 2021-04-22 | 2022-09-11 |  |  | 39.7004 | 21.611 | منجز | No
2100047095 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 56632444.44 | 2831622.222 | 5825794.45 | 5825794.45 | 4031005362 | لا | 0 | 180909098329 | مسحوب | تكلفة العمل المنجز | 12 | 100 | 2016-01-17 | 2019-01-16 | 2020-10-19 | 2020-10-19 |  |  | اخرى |  | 39.8657 | 21.3714 | مسحوب | No
2100066253 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 51046366.72 | 2552318.336 | 5108417.15 | 5108417.15 | 4031005362 | لا | 0 | 180909098567 | مسحوب | تكلفة العمل المنجز | 10 | 100 | 2016-01-16 | 2019-01-16 | 2020-03-12 | 2020-03-12 |  |  | اخرى |  | 39.8554 | 21.3805 | مسحوب | No
2100061294 | المؤسسة العامة لتحلية المياه المالحة | تشييد | ذات اولوية عالية | 1968970671 | 98448533.55 | 1520194713.32 | 1520194713.32 | 4030271192 | لا | 0 | 200101012470 | جاري | تكلفة العمل المنجز | 95.8 | 100 | 2019-02-24 | 2022-08-23 | 2023-08-19 | 2023-08-19 |  |  | لا يوجد تأخير |  | 50.2057 | 26.1756 | منتظم | No
2100097451 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية وعاجلة | 2491500.16 | 124575.008 | 2224578.2 | 2187628.21 | 2050060814 | نعم | 1e-20 | 180809065123 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 93.75 | 100 | 2019-06-27 | 2021-06-05 | 2021-08-09 | 2021-08-09 | 2021-06-05 |  | لا يوجد تأخير |  | 47.1565 | 23.9954 | منجز | No
2100010194 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 2190410 | 109520.5 | 2163754.65 | 1965827.85 | 1010275506 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-12-27 | 2019-12-27 | 2019-12-27 | 2019-12-27 |  | 2019-12-27 | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100018874 | وزارة الدفاع / الإدارة الهندسية والاشغال بقوات الدفاع الجوي | تشييد | ذات اولوية متوسطة | 1137027.01 | 56851.3505 | 1137027.01 | 764910.38 | 3550007202 | لا | 0 | 190201000395 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-03-10 | 2020-06-26 | 2021-09-21 | 2021-09-21 | 2020-06-26 |  | أوامر سامية |  | 36.5729 | 28.3777 | منجز | No
2100033246 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 6290000 | 314500 | 6290000 | 6290000 | 4030006066 | لا | 0 | 181009124675 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2017-12-26 | 2018-12-21 | 2020-12-21 | 2020-12-21 | 2018-12-21 |  |  |  | 42.843 | 21.2534 | منجز | No
2100076613 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 8400000 | 420000 | 8400000 | 8400000 | 5851000110 | لا | 0 | 190609031166 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-08-12 | 2019-07-07 | 2019-08-07 | 2019-08-07 | 2019-07-07 |  |  |  | 42.8423 | 21.2547 | منجز | No
2100064201 | أمانة / الطائف | تشييد | ذات اولوية عالية | 1834636.68 | 91731.834 | 1834636.68 | 1834636.68 | 4032025683 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2010-03-09 | 2011-03-04 | 2011-03-04 | 2011-03-04 | 2011-03-04 |  |  |  | 42.8388 | 21.2629 | منجز | No
2100017555 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 3767096 | 188354.8 | 3352715.49 | 2260258 | 1131049774 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-03-02 | 2015-08-24 | 2022-01-01 | 2022-01-01 | 2015-08-24 |  | ضعف كفاءة المقاول الفنية |  | 42.6031 | 20.0028 | منجز | No
2100012843 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1304370.84 | 65218.542 | 1304370.84 | 1304370.84 | 4032025683 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 76 | 100 | 2010-03-09 | 2011-03-04 | 2022-06-30 | 2022-06-30 |  |  | ضعف كفاءة المقاول الفنية |  | 42.8484 | 21.2609 | مسحوب | No
2100087076 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 38080955 | 1904047.75 | 25355159.17 | 24552072.47 | 1010014477 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 96.79 | 100 | 2018-10-16 | 2020-10-16 | 2022-07-31 | 2022-07-31 | 2020-10-16 |  | لا يوجد تأخير |  | 46.687 | 24.7737 | منجز | No
2100061471 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 3595924.65 | 179796.2325 | 2583452.32 | 2583452.32 | 1010276827 | نعم | 28819275.2 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 96.62 | 100 | 2020-06-08 | 2020-12-08 | 2021-05-26 | 2021-05-26 |  | 2020-12-08 | لا يوجد تأخير |  | 46.5373 | 24.7528 | منجز | No
2100021593 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 30679475.71 | 1533973.7855 | 19479813.68 | 18266253.48 | 1011008214 | لا | 0 | 190309060212 | جاري | منهجية القيمة المكتسبة | 93.38 | 100 | 2014-11-04 | 2017-04-08 | 2022-06-30 | 2022-06-30 |  |  | اخرى |  | 46.7124 | 22.3072 | متأخر | No
2100044726 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 48074242.38 | 2403712.119 | 48074242.38 | 48074242.38 | 4030006066 | لا | 0 | 190609051011 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-10-12 | 2016-04-04 | 2017-02-28 | 2017-02-28 | 2016-04-04 |  |  |  | 40.4047 | 21.2682 | منجز | No
2100007733 | أمانة / جازان | تشييد | ذات اولوية عالية | 839223 | 41961.15 | 839223 | 839223 | 5906011310 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 24 | 2019-10-19 | 2020-04-16 | 2020-04-16 | 2020-04-16 | 2020-04-16 |  | ضعف كفاءة المقاول الفنية |  | 42.2701 | 17.7334 | منجز | No
2100066533 | أمانة / الطائف | دراسات هندسية | ذات اولوية متوسطة | 1197000 | 59850 | 838012.33 | 838012.33 | 1010415504 | لا | 0 | 200101008509 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-11-19 | 2020-07-19 | 2020-07-19 | 2020-07-19 | 2020-07-19 |  | اخرى |  | 40.4334 | 21.2844 | منجز | No
2100043890 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 8395374.75 | 419768.7375 | 8395374.75 | 8395374.75 | 4030006066 | لا | 0 | 181009124671 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-01-24 | 2019-01-19 | 2019-01-19 | 2019-01-19 | 2019-01-19 |  |  |  | 42.8443 | 21.2545 | منجز | No
2100069156 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1887150 | 94357.5 | 1236023 | 1236023 | 4037000411 | لا | 0 | 191001276253 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-09-15 | 2021-03-08 | 2021-03-08 | 2021-03-08 | 2021-03-08 |  |  |  | 41.7495 | 22.4285 | منجز | No
2100001396 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 5069786.09 | 253489.3045 | 2305209.87 | 2305209.87 | 1010333894 | لا | 0 | 200209146853 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 82.75 | 100 | 2015-09-02 | 2017-02-15 | 2021-03-03 | 2021-03-03 | 2017-02-15 |  | ضعف كفاءة المقاول الفنية |  | 47.3078 | 24.1522 | منجز | No
2100042140 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات الجوية | تشييد | ذات اولوية عالية | 16382557 | 819127.85 | 12351423 | 12351423 | 4030260915 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 93 | 100 | 2018-12-15 | 2020-08-21 | 2022-06-30 | 2022-06-30 |  |  | لا يوجد تأخير |  | 38.9164 | 30.9888 | Failed | No
2100106573 | وزارة الحرس الوطني / الشؤون الصحية | توريد وتركيب | ذات اولوية عالية | 1610173.95 | 80508.6975 | 647784.33 | 647784.33 | 2051039004 | لا | 0 | 180909102756 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2017-05-03 | 2018-07-17 | 2021-08-31 | 2021-08-31 | 2018-07-17 |  | ضعف كفاءة المقاول الفنية |  | 46.8578 | 24.7525 | منجز | No
2100002240 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 29664146.68 | 1483207.334 | 27630069.9 | 27630069.9 | 2250001372 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-11-02 | 2018-01-20 | 2020-06-08 | 2020-06-08 | 2018-01-20 |  |  |  | 49.5604 | 25.3897 | منجز | No
2100088130 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 312315246.3 | 15615762.315 | 246347498.68 | 246347498.68 | 2050003475 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 95.76 | 100 | 2011-07-23 | 2014-07-23 | 2019-08-15 | 2019-08-15 |  | 2014-07-23 | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100087415 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 12583974.3 | 629198.715 | 12583973.7 | 10544995.68 | 1010216415 | لا | 0 | 180809042771 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2014-07-10 | 2015-06-30 | 2018-12-30 | 2018-12-30 | 2015-06-30 |  | لا يوجد تأخير |  | 42.9095 | 23.8972 | منجز | No
2100034716 | أمانة / جازان | تشييد | ذات اولوية عالية وعاجلة | 1635000 | 81750 | 0 | 0 | 4030065096 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 0 | 100 | 2015-02-18 | 2016-02-13 | 2020-04-13 | 2020-04-13 |  |  | ضعف كفاءة المقاول الفنية |  | 42.6868 | 16.9711 | مسحوب | No
2100051100 | أمانة / جازان | تشييد | ذات اولوية عالية وعاجلة | 1949500 | 97475 | 0 | 0 | 5900030880 | لا | 0 | 190309031426 | مسحوب | الكميات التي تم تركيبها | 0 | 100 | 2015-10-04 | 2016-09-28 | 2016-11-29 | 2016-11-29 |  |  | تأخرصرف المستحقات المالية |  | 42.5722 | 16.8928 | مسحوب | No
2100102863 | أمانة / العاصمة المقدسة | إشراف | ذات اولوية متوسطة | 57715350 | 2885767.5 | 54796717.38 | 54796717.38 | 1010323435 | لا | 0 |  | منجز – استلام نهائي | مدفوعات ساعات العمل | 100 | 100 | 2017-01-31 | 2020-08-20 | 2021-08-20 | 2021-08-20 | 2020-08-20 | 2020-08-29 | اخرى |  | 39.8329 | 21.3956 | منجز | No
2100049276 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 59603.5 | 2980.175 | 216414.45 | 216414.45 | 3352010501 | لا | 0 | 181001158041 | مسحوب | الكميات التي تم تركيبها | 83 | 100 | 2018-07-24 | 2019-07-18 | 2021-08-30 | 2021-08-30 |  |  | سوء التخطيط الاولي للمشروع |  | 42.9235 | 28.2508 | مسحوب | No
2100035991 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 10871496.02 | 543574.801 | 5302159.7 | 5302159.7 | 1010264550 | لا | 0 |  | مسحوب | منهجية القيمة المكتسبة | 64.89 | 100 | 2011-12-05 | 2014-05-09 | 2023-02-20 | 2023-02-20 |  |  | ضعف كفاءة المقاول الفنية |  | 46.8944 | 23.5058 | مسحوب | No
2100001606 | وزارة الشـؤون الاسلامية والدعوة والارشاد | تشييد | ذات اولوية عالية | 2000000 | 100000 | 1014311.15 | 0 | 4650051129 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 55 | 100 | 2017-11-10 00:59 | 2019-06-24 00:59 | 2019-06-24 | 2019-06-24 |  |  | تأخرصرف المستحقات المالية |  | 43.9865 | 26.3604 | Failed | Yes
2100049254 | أمانة / جازان | تشييد | ذات اولوية عالية | 2066500 | 103325 | 1566522 | 1566522 | 5903005814 | لا | 0 | 180909110298 | جاري | الكميات التي تم تركيبها | 75 | 100 | 2015-03-06 | 2016-02-29 | 2021-11-11 | 2021-11-11 |  |  | ضعف كفاءة المقاول الفنية |  | 42.0269 | 17.7149 | Failed | No
2100078260 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية منخفضة | 365175 | 18258.75 | 330082.31 | 330082.31 | 1010273396 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-04-25 | 2018-07-21 | 2018-08-05 | 2018-08-05 | 2018-07-21 |  | تأخرصرف المستحقات المالية |  | 43.9483 | 25.9672 | منجز | No
2100088900 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية وعاجلة | 16832500 | 841625 | 16832500 | 16832500 | 1010319823 | لا | 0 | 181101306124 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-08-26 | 2020-02-09 | 2020-02-06 | 2020-02-06 | 2020-02-09 |  | لا يوجد تأخير |  | 47.3078 | 24.1522 | منجز | No
2100042280 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية متوسطة | 42080950 | 2104047.5 | 34157033 | 34157033 | 5855006176 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2007-07-02 | 2010-05-30 | 2019-04-19 | 2019-04-19 | 2010-05-30 |  |  |  | 42.7361 | 17.4514 | منجز | No
2100108861 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية متوسطة | 2017217.67 | 100860.8835 | 1965129.39 | 1965129.39 | 1010233732 | لا | 0 | 190609008022 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-12-06 | 2019-08-28 | 2019-08-28 | 2019-08-28 | 2019-08-28 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 46.715 | 24.5827 | منجز | No
2100190201 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية عالية وعاجلة | 7711281.6 | 385564.08 | 466426.05 | 466426.05 | 1010272491 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 12 | 51 | 2014-01-22 | 2016-12-20 | 2016-12-20 | 2016-12-20 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 40.0896 | 29.8611 | مسحوب | No
2100000442 | وزارة التعليم | تشييد | ذات اولوية عالية | 1910547.97 | 95527.3985 | 2084669 | 1863054 | 4603004056 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-03-17 | 2015-05-11 | 2020-01-16 | 2020-01-16 | 2015-05-11 |  |  |  | 41.0859 | 19.1571 | منجز | No
2100010485 | وزارة التعليم | تشييد | ذات اولوية عالية | 962800 | 48140 | 778004.65 | 778004.65 | 4650036827 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 90 | 100 | 2005-12-27 | 2006-10-24 | 2023-01-15 | 2023-01-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | No
2100023063 | أمانة / جازان | تصميم | ذات اولوية متوسطة | 9894400 | 494720 | 12230000 | 12230000 | 1010325732 | لا | 0 | 180809061198 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2013-08-22 | 2019-10-29 | 2021-10-29 | 2021-10-29 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5374 | 16.9252 | Failed | No
2100004491 | أمانة / عسير | تشييد | ذات اولوية عالية | 1300365 | 65018.25 | 145044 | 145044 | 5854001345 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 15 | 100 | 2015-09-09 | 2016-09-03 | 2020-10-11 | 2020-10-11 |  |  | ضعف كفاءة المقاول الفنية |  | 43.206 | 18.5656 | مسحوب | No
2100003393 | وزارة الصحة / حائل | تشييد | ذات اولوية عالية | 2686653 | 134332.65 | 1398733.54 | 985798.25 | 3350040482 | لا | 0 | 181009161843 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2017-07-12 | 2020-09-28 | 2021-09-01 | 2021-09-01 | 2020-09-28 |  | تأخرصرف المستحقات المالية |  | 41.696 | 27.5103 | منجز | No
2100004314 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 925480 | 46274 | 319170 | 319170 | 2511482400 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 47 | 100 | 2016-10-20 | 2017-02-17 | 2020-06-02 | 2020-06-02 |  |  | ضعف كفاءة المقاول الفنية |  | 45.975 | 28.4334 | مسحوب | No
2100003710 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 22927377 | 1146368.85 | 9582982.76 | 7715688.53 | 5801003664 | لا | 0 | 190909016152 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2016-03-13 | 2018-06-01 | 2021-05-27 | 2021-05-27 | 2018-06-01 |  | ضعف كفاءة المقاول الفنية |  | 41.4779 | 20.0185 | منجز | No
2100002914 | جامعة نجران | تشييد | ذات اولوية عالية | 7878143 | 393907.15 | 1252659.5 | 1252659.5 | 5950006666 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 10 | 100 | 2015-06-08 | 2015-10-13 | 2023-12-28 | 2023-12-28 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 44.2341 | 17.5757 | Failed | No
2100004550 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البحرية | تشييد | ذات اولوية متوسطة | 4588687 | 229434.35 | 2748906 | 2748906 | 1010301264 | لا | 0 | 200401064424 | جاري | الكميات التي تم تركيبها | 85 | 100 | 2019-11-18 | 2021-12-18 | 2021-12-18 | 2021-12-18 |  |  |  |  | 49.5777 | 26.9378 | Failed | No
2100004513 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البحرية | تشييد | ذات اولوية منخفضة | 8044945 | 402247.25 | 5550154 | 5550154 | 2055002705 | لا | 0 | 190501136094 | جاري | الكميات التي تم تركيبها | 71 | 100 | 2019-10-21 | 2021-01-06 | 2021-10-05 | 2021-10-05 |  |  |  |  | 49.6024 | 26.9747 | Failed | No
2100009133 | وزارة الموارد البشرية والتنمية الإجتماعية | تشييد | ذات اولوية منخفضة | 15549900.76 | 777495.038 | 13381587.71 | 13381587.71 | 1010253962 | لا | 0 | 190409100468 | مسحوب | الكميات التي تم تركيبها | 87 | 100 | 2014-04-20 | 2015-04-08 | 2023-05-17 | 2023-05-17 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 49.5583 | 25.387 | مسحوب | No
2100075596 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 29380754 | 1469037.7 | 29380754 | 24827702 | 4650009788 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 85 | 100 | 2018-10-31 | 2022-05-05 | 2022-05-05 | 2022-05-05 | 2022-05-05 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.6079 | 24.4931 | منجز | No
2100028873 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 85281319.62 | 4264065.981 | 85281319.62 | 85281319.62 | 4030006066 | لا | 0 | 190609039477 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-02-26 | 2016-02-16 | 2017-02-09 | 2017-02-09 | 2016-02-16 |  |  |  | 40.421 | 21.2732 | منجز | No
2100008864 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2741259 | 137062.95 | 2419941.08 | 2419941.08 | 3357004766 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-11-01 | 2015-12-26 | 2021-12-15 | 2021-12-15 | 2015-12-26 |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | منجز | No
2100014700 | أمانة / عسير | تشييد | ذات اولوية عالية | 1825875 | 91293.75 | 420000 | 420000 | 5851002943 | لا | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 29 | 100 | 2015-07-26 | 2016-07-22 | 2023-03-05 | 2023-03-05 |  |  | تأخرصرف المستحقات المالية |  | 43.6578 | 18.7088 | Failed | No
2100007711 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 15920236 | 796011.8 | 1395603 | 1395603 | 1010178798 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 9 | 100 | 2015-05-03 | 2017-07-20 | 2018-08-22 | 2018-08-22 |  |  | ضعف كفاءة المقاول الفنية |  | 38.0577 | 24.1032 | مسحوب | No
2100049733 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 31618450 | 1580922.5 | 23180000 | 23180000 | 1010166750 | لا | 0 |  | ايقاف جزئي | التكلفة المفوترة | 75.91 | 75.91 | 2011-07-09 | 2013-07-08 | 2017-08-05 | 2017-08-05 |  |  | اخرى |  | 39.8613 | 21.3715 | Failed | No
2100013333 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 1291140 | 64557 | 0 | 0 | 5950018592 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2016-04-26 | 2020-12-30 | 2020-01-27 | 2020-01-27 | 2020-12-30 |  | تأخرصرف المستحقات المالية |  | 44.2417 | 17.5529 | منجز | No
2100008013 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 217023732.26 | 10851186.613 | 177830378.28 | 177830378.28 | 1010054406 | لا | 0 |  | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-09-10 | 2021-03-03 | 2022-12-31 | 2022-12-31 |  |  | منازعات قائمة | أخرى |  |  | متأخر | No
2100045043 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 28522624 | 1426131.2 | 28522624 | 28522624 | 2050018628 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-08-11 | 2020-07-19 | 2022-03-03 | 2022-03-03 | 2020-07-19 |  |  |  | 50.0064 | 26.5456 | منجز | No
2100012994 | أمانة / الجوف | تشييد | ذات اولوية عالية | 3736975 | 186848.75 | 1068100 | 1000000 | 3400012611 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 27.4 | 100 | 2015-06-15 | 2016-06-14 | 2016-06-15 | 2016-06-15 |  |  | تأخرصرف المستحقات المالية |  | 40.2961 | 30.1674 | مسحوب | No
2100048930 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 15777397 | 788869.85 | 7484998 | 5616994 | 4030149957 | لا | 0 | 190201036789 | جاري | الكميات التي تم تركيبها | 90 | 100 | 2019-05-16 | 2021-05-16 | 2022-02-16 | 2022-02-16 |  |  | اخرى |  | 39.203 | 21.5259 | Failed | No
2100178356 | وزارة الثقافة | ترميم | ذات اولوية عالية | 56724929.64 | 2836246.482 | 38448929.41 | 38448929.41 | 1010070634 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 70 | 100 | 2011-05-02 | 2020-03-27 | 2022-05-01 | 2022-05-01 |  |  |  |  | 50.0584 | 26.3682 | Failed | No
2100015341 | وزارة الصحة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 1962462 | 98123.1 | 1277770 | 0 | 4650040868 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 80 | 100 | 2018-12-22 | 2019-06-17 | 2022-03-31 | 2022-03-31 | 2019-06-17 |  | تأخرصرف المستحقات المالية |  | 39.5608 | 24.4954 | منجز | Yes
2100008190 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 3889309.32 | 194465.466 | 3889309.32 | 3889309.32 | 4031041345 | لا | 0 | 181009123001 | مسحوب | تكلفة العمل المنجز | 70 | 100 | 2015-05-17 | 2017-05-07 | 2018-02-15 | 2018-02-15 |  |  | ضعف كفاءة المقاول الفنية |  | 40.808 | 20.9464 | مسحوب | No
2100082692 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 2233692.24 | 111684.612 | 2051052.5 | 2051052.5 | 4036001622 | لا | 0 | 181009124834 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2016-01-03 | 2016-12-28 | 2016-12-28 | 2016-12-28 | 2016-12-28 |  |  |  | 42.8476 | 21.2505 | منجز | No
2100023505 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 5976022.5 | 298801.125 | 5417339.5 | 5417339.5 | 2050041707 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 91 | 91 | 2019-01-20 | 2019-07-18 | 2019-07-18 | 2019-07-18 | 2019-07-18 |  |  |  | 39.8096 | 21.3329 | منجز | No
2100016763 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 5999564.08 | 299978.204 | 0 | 0 | 2251033167 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 10 | 100 | 2007-11-27 | 2009-08-18 | 2023-06-12 | 2023-06-12 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.5429 | 16.8808 | مسحوب | No
2100019051 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 10052657 | 502632.85 | 1193450.12 | 1193450.12 | 5802000515 | لا | 0 |  | مسحوب | التكلفة المفوترة | 12 | 100 | 2012-06-22 | 2014-04-13 | 2023-02-04 | 2023-02-04 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 40.2691 | 20.1489 | مسحوب | No
2100019574 | وزارة الرياضة | تشييد | ذات اولوية عالية | 49579140.8 | 2478957.04 | 31317599 | 31317599 | 1010195208 | نعم | 468283.13 | 180909082884 | مسحوب | الكميات التي تم تركيبها | 82 | 100 | 2012-06-23 | 2014-12-23 | 2014-12-23 | 2014-12-23 |  |  | ضعف كفاءة المقاول الفنية |  | 39.3206 | 29.8874 | مسحوب | No
2100021265 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 15487402.5 | 774370.125 | 10545320 | 0.01 | 2050008923 | لا | 0 |  | جاري | التكلفة المفوترة | 82 | 100 | 2011-11-14 | 2013-11-03 | 2017-07-24 | 2017-07-24 |  |  | ضعف كفاءة المقاول الفنية |  | 50.4958 | 26.561 | Failed | No
2100020392 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 4144000 | 207200 | 4351200 | 4351200 | 4030237556 | لا | 0 | 190809018631 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-02-20 | 2020-11-12 | 2021-02-11 | 2021-02-11 | 2020-11-12 |  | ضعف كفاءة المقاول الفنية |  | 41.8656 | 19.3028 | منجز | No
2100020414 | أمانة / العاصمة المقدسة | دراسة الجدوى | ذات اولوية متوسطة | 3852000 | 192600 | 3387114 | 3387114 | 4030271639 | لا | 0 | 181109342858 | منجز – استلام نهائي | مدفوعات ساعات العمل | 84.05 | 84.05 | 2018-09-30 | 2020-09-29 | 2021-07-05 | 2021-07-05 | 2020-09-29 | 2020-11-05 | اخرى |  | 39.8652 | 21.3865 | منجز | No
2100021884 | مدينة الملك عبدالله الطبية بالعاصمة المقدسة | تصميم | ذات اولوية عالية | 308000 | 15400 | 308000 | 308000 | 4031063586 | لا | 0 | 181101258618 | جاري | الكميات التي تم تركيبها | 60 | 100 | 2018-07-29 | 2018-10-14 | 2019-01-25 | 2019-01-25 |  |  | تغيرات في نطاق المشروع |  |  |  | Failed | No
2100060196 | أمانة / جازان | تشييد | ذات اولوية عالية | 1370475 | 68523.75 | 219276 | 219276 | 1010357371 | لا | 0 | 180809060010 | مسحوب | تكلفة العمل المنجز | 16 | 100 | 2014-09-08 | 2015-05-06 | 2015-05-16 | 2015-05-16 |  |  | اخرى |  | 42.6078 | 16.8841 | مسحوب | No
2100028081 | أمانة / جازان | تشييد | ذات اولوية عالية | 1760100 | 88005 | 1387900 | 1387900 | 4030105559 | لا | 0 | 180701014872 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 98 | 100 | 2018-09-16 | 2020-03-10 | 2020-03-10 | 2020-03-10 | 2020-03-10 |  | اخرى |  | 42.9383 | 16.6006 | منجز | No
2100028291 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية منخفضة | 85331312 | 4266565.6 | 76200305 | 76200305 | 5855028046 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2011-09-28 | 2014-10-23 | 2014-10-23 | 2014-10-23 | 2014-10-23 | 2020-07-07 |  |  | 42.5143 | 18.1559 | منجز | No
2100022680 | أمانة / جدة | تصميم وإشراف | ذات اولوية عالية | 4825584 | 241279.2 | 5232685 | 5018742 | 4650047424 | لا | 0 | 190409001450 | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2019-02-17 | 2021-02-16 | 2021-02-16 | 2021-02-16 | 2021-02-16 | 2021-02-17 | اخرى |  |  |  | منجز | No
2100022654 | أمانة / الجوف | دراسة الجدوى | ذات اولوية متوسطة | 2930552.9 | 146527.645 | 2588020.8 | 2588020.8 | 2050025094 | لا | 0 | 190201046926 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-04-03 | 2022-03-04 | 2022-06-18 | 2022-06-18 | 2022-03-04 |  | اخرى |  | 40.1056 | 29.8637 | منجز | No
2100021560 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 3499920 | 174996 | 1419877 | 1419877 | 3357007585 | لا | 0 | 190301044797 | مسحوب | الكميات التي تم تركيبها | 40 | 100 | 2019-01-14 | 2020-07-07 | 2021-04-10 | 2021-04-10 |  |  | ضعف كفاءة المقاول الفنية |  | 40.5483 | 26.4063 | مسحوب | No
2100026736 | أمانة / الرياض | تشييد | ذات اولوية عالية | 1199320 | 59966 | 42107 | 0 | 1010354943 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 20 | 100 | 2015-07-21 | 2018-06-09 | 2018-06-10 | 2018-06-10 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | مسحوب | Yes
2100027090 | أمانة / جازان | تشييد | ذات اولوية عالية | 33710385.74 | 1685519.287 | 30339000 | 0 | 5902368725 | لا | 0 | 181109371318 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2010-12-28 | 2012-06-19 | 2019-04-04 | 2019-04-04 | 2012-06-19 |  | اخرى |  | 42.9557 | 16.7111 | منجز | Yes
2100026972 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 2709000 | 135450 | 485980 | 179170 | 4701000411 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 18 | 100 | 2014-12-13 | 2015-12-12 | 2015-12-12 | 2015-12-12 |  |  | ضعف كفاءة المقاول الفنية |  | 37.2441 | 25.0496 | مسحوب | No
2100000114 | وزارة التعليم | تشييد | ذات اولوية عالية | 18675974 | 933798.7 | 2231330 | 2231330 | 1010142553 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 14 | 100 | 2015-08-16 | 2017-11-04 | 2017-11-04 | 2017-11-04 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | مسحوب | No
2100025771 | أمانة / تبوك | تشييد | ذات اولوية عالية | 4133600 | 206680 | 3159600 | 3121885.36 | 3554000169 | لا | 0 | 180909109351 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-02-26 | 2016-08-21 | 2020-07-17 | 2020-07-17 | 2016-08-21 |  | ضعف كفاءة المقاول الفنية |  | 38.5165 | 27.6122 | منجز | No
2100024942 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 2236185 | 111809.25 | 2236185 | 486034.5 | 4030152625 | لا | 0 | 191101248436 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-08-28 | 2021-02-10 | 2021-02-09 | 2021-02-09 | 2021-02-10 |  | اخرى |  | 40.4588 | 20.2878 | منجز | No
2100024776 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 216541.5 | 10827.075 | 216541.5 | 216541.5 | 5951126918 | لا | 0 | 181209477572 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2016-02-09 | 2020-07-06 | 2020-07-06 | 2020-07-06 | 2020-07-06 |  | ضعف كفاءة المقاول الفنية |  | 44.2302 | 17.5905 | منجز | No
2100028184 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 17281039.62 | 864051.981 | 3008899.59 | 3008899.59 | 1010046644 | لا | 0 |  | مسحوب | التكلفة المفوترة | 17 | 100 | 2016-11-27 | 2018-11-17 | 2018-11-17 | 2018-11-17 |  |  | ضعف كفاءة المقاول الفنية |  | 50.5619 | 26.4366 | مسحوب | No
2100027860 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1313500 | 65675 | 1313500 | 1313500 | 1118001405 | لا | 0 | 190709130425 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-01-13 | 2020-01-08 | 2020-01-07 | 2020-01-07 | 2020-01-08 |  | ضعف كفاءة المقاول الفنية |  | 42.0224 | 21.9247 | منجز | No
2100081244 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 35526150 | 1776307.5 | 738027 | 738027 | 4650052854 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 7 | 100 | 2015-02-09 | 2017-07-13 | 2021-09-08 | 2021-09-08 |  |  | ضعف كفاءة المقاول الفنية |  | 38.1912 | 24.0418 | مسحوب | No
2100031614 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 12345108.21 | 617255.4105 | 13517159 | 11394795 | 5855007803 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2013-02-23 | 2015-02-13 | 2019-01-14 | 2019-01-14 | 2015-02-13 |  |  |  | 41.0859 | 19.1571 | منجز | No
2100028895 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 4750580 | 237529 | 4750580 | 4750580 | 3555000998 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-10-17 | 2016-08-23 | 2016-12-23 | 2016-12-23 | 2016-08-23 |  | اخرى |  | 36.4721 | 26.2347 | منجز | No
2100007980 | وكالة / الإسكان | تشييد | ذات اولوية متوسطة | 56876077.19 | 2843803.8595 | 21763202 | 21763202 | 1010210667 | لا | 0 |  | ايقاف كلي | منهجية القيمة المكتسبة | 39 | 39 | 2019-07-14 | 2021-01-04 | 2021-01-04 | 2021-01-04 |  |  | منازعات قائمة | أخرى |  |  | Failed | No
2100029595 | أمانة / الباحة | تشييد | ذات اولوية عالية | 9512538.05 | 475626.9025 | 9512538.05 | 9512538.05 | 1010176347 | لا | 0 | 190309018856 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-08-23 | 2017-08-01 | 2022-11-13 | 2022-11-13 | 2017-08-01 |  | ضعف كفاءة المقاول الفنية |  | 41.5677 | 19.891 | منجز | No
2100030240 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1367625 | 68381.25 | 658875 | 658875 | 1010132153 | لا | 0 | 181001156804 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-05-28 | 2019-05-23 | 2019-05-23 | 2019-05-23 | 2019-05-23 |  |  |  | 41.7568 | 22.431 | منجز | No
2100032233 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 1312125 | 65606.25 | 466850 | 466850 | 3356353627 | لا | 0 | 200209133394 | جاري | الكميات التي تم تركيبها | 85 | 100 | 2019-02-11 | 2020-01-30 | 2023-02-17 | 2023-02-17 |  |  | ضعف كفاءة المقاول الفنية |  | 40.5509 | 26.4128 | متأخر | No
2100035545 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 71489264.34 | 3574463.217 | 61341527.78 | 57198560.4 | 4032030968 | لا | 0 | 190409023877 | جاري | تكلفة العمل المنجز | 92 | 100 | 2015-12-21 | 2017-12-20 | 2022-01-01 | 2022-01-01 |  |  | ضعف كفاءة المقاول الفنية |  | 40.4251 | 21.2479 | Failed | No
2100106794 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البحرية | تشييد | ذات اولوية متوسطة | 10669406 | 533470.3 | 9744308 | 9187374 | 1010142413 | لا | 0 | 180709028397 | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-10-31 | 2013-11-21 | 2021-09-21 | 2021-09-21 |  |  |  |  | 39.2589 | 21.5037 | Failed | No
2100035626 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 6420500 | 321025 | 3510038.4 | 3510038.4 | 5950010447 | لا | 0 | 190309041301 | جاري | الكميات التي تم تركيبها | 56 | 100 | 2012-06-01 | 2013-05-17 | 2021-11-11 | 2021-11-11 |  |  | اخرى |  | 42.6283 | 17.1545 | Failed | No
2100036400 | أمانة / جازان | تشييد | لم تعد تحتاجها الجهة | 1833317.5 | 91665.875 | 115800 | 0 | 5900026601 | لا | 0 | 181209452966 | مسحوب | الكميات التي تم تركيبها | 6 | 100 | 2015-06-20 | 2016-06-14 | 2016-06-14 | 2016-06-14 |  |  | اخرى |  | 42.9626 | 16.5293 | مسحوب | Yes
2100034915 | أمانة / جدة | تشييد | ذات اولوية عالية | 20512968 | 1025648.4 | 20605767.23 | 19518359.56 | 4030149957 | لا | 0 | 180401004288 | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2018-07-08 | 2019-03-30 | 2022-02-28 | 2022-02-28 | 2019-03-30 |  | سوء التخطيط الاولي للمشروع |  | 39.183 | 21.5314 | منجز | No
2100081830 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 3799371 | 189968.55 | 1437000 | 1437000 | 4030187031 | لا | 0 | 181009117820 | مسحوب | تكلفة العمل المنجز | 70 | 95 | 2015-06-03 | 2016-11-24 | 2020-01-01 | 2020-01-01 |  |  | ضعف كفاءة المقاول الفنية |  | 42.03 | 21.9211 | مسحوب | No
2100035766 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 1298070 | 64903.5 | 1357459.71 | 1357459.71 | 4603102229 | لا | 0 | 190809007620 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-12-12 | 2019-12-01 | 2020-02-20 | 2020-02-20 | 2019-12-01 |  | ضعف كفاءة المقاول الفنية |  | 41.0613 | 19.5359 | منجز | No
2100108765 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 9803803.5 | 490190.175 | 1304905 | 1304905 | 4031033277 | لا | 0 |  | مسحوب | التكلفة المفوترة | 20 | 100 | 2015-04-25 | 2017-04-15 | 2024-01-15 | 2024-01-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | No
2100035335 | أمانة / جازان | تشييد | ذات اولوية عالية | 642250 | 32112.5 | 522087.3 | 522087.3 | 5903025849 | لا | 0 | 181201541446 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 81 | 100 | 2018-08-26 | 2019-08-22 | 2019-08-21 | 2019-08-21 | 2019-08-22 |  | اخرى |  | 42.513 | 17.1465 | منجز | No
2100034576 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 2732720 | 136636 | 501896 | 501896 | 2511022954 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 25 | 25 | 2018-08-28 | 2019-08-27 | 2019-08-28 | 2019-08-28 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | مسحوب | No
2100039115 | أمانة / نجران | تشييد | لم تعد تحتاجها الجهة | 2460965 | 123048.25 | 2460965 | 299424.62 | 5950007223 | لا | 0 | 220601025060 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-04-08 | 2019-12-05 | 2019-12-06 | 2019-12-06 | 2019-12-05 | [5 empty] | منجز | No
2100036772 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 4873050 | 243652.5 | 4244900 | 4244900 | 5851000110 | لا | 0 | 191001284972 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 95 | 100 | 2019-08-04 | 2020-07-29 | 2022-06-30 | 2022-06-30 | 2020-07-29 |  | ضعف كفاءة المقاول الفنية |  | 42.8427 | 21.2589 | منجز | No
2100084394 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 19028835 | 951441.75 | 18629767 | 18629767 | 4031038849 | لا | 0 | 190809067272 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 88.95 | 88.95 | 2019-07-11 | 2019-12-10 | 2021-04-12 | 2021-04-12 | 2019-12-10 |  |  |  | 39.8701 | 21.3827 | منجز | No
2100024894 | جامعة الملك فيصل | تشييد | ذات اولوية عالية | 3195000 | 159750 | 479000 | 479000 | 1010359384 | لا | 0 | 181109353426 | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2011-03-12 | 2012-03-13 | 2020-01-10 | 2020-01-10 |  | 2012-03-13 | تأخرصرف المستحقات المالية |  | 49.5604 | 25.3897 | منجز | No
2100003743 | جامعة الملك فيصل | تشييد | ذات اولوية عالية | 106524866 | 5326243.3 | 106524866 | 106524866 | 1010208002 | لا | 0 | 180909099629 | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2011-11-19 | 2014-10-16 | 2017-11-10 | 2017-11-10 |  | 2014-10-16 | تأخرصرف المستحقات المالية |  | 49.5604 | 25.3897 | منجز | No
2100039734 | هيئة الهلال الأحمر السعودي | تشييد | ذات اولوية عالية | 1278322 | 63916.1 | 237270.69 | 237270.69 | 1010175017 | لا | 0 | 181009198888 | مسحوب | الكميات التي تم تركيبها | 30 | 100 | 2018-02-05 | 2019-02-05 | 2019-03-05 | 2019-03-05 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.0322 | 22.8086 | مسحوب | No
2100074362 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 14294528.03 | 714726.4015 | 4202877.74 | 0 | 1116004360 | لا | 0 |  | مسحوب | التكلفة المفوترة | 49 | 100 | 2012-09-14 | 2014-08-24 | 2014-08-24 | 2014-08-24 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5604 | 25.3897 | مسحوب | Yes
2100039130 | أمانة / تبوك | تشييد | ذات اولوية عالية وعاجلة | 35387697 | 1769384.85 | 29552889 | 23500615 | 1010009592 | لا | 0 | 180301000957 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-09-24 | 2020-06-09 | 2020-05-13 | 2020-05-13 | 2020-06-09 |  | ضعف كفاءة المقاول الفنية |  | 36.5541 | 28.3517 | منجز | No
2100003695 | جامعة الملك سعود | تشييد | ذات اولوية متوسطة | 10021546.77 | 501077.3385 | 10021546.77 | 10021546.77 | 1010135802 | لا | 0 | 180909072859 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2017-10-24 | 2018-07-24 | 2020-08-23 | 2020-08-23 | 2018-07-24 |  | تأخرصرف المستحقات المالية |  | 62.7127 | 27.0663 | منجز | No
2100036735 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية عالية | 15285865.5 | 764293.275 | 3993977.2 | 3993977.2 | 4031046580 | لا | 0 | 190501125676 | جاري | تكلفة العمل المنجز | 26.13 | 26.13 | 2019-09-08 | 2021-08-16 | 2021-11-14 | 2021-11-14 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.9038 | 21.3041 | Failed | No
2100013101 | أمانة / الرياض | دراسة الجدوى | ذات اولوية متوسطة | 3049920 | 152496 | 0 | 0 | 1010372072 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-09-12 | 2021-09-11 | 2021-09-11 | 2021-09-11 | 2021-09-11 |  | اخرى |  |  |  | منجز | No
2100038371 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 11195254 | 559762.7 | 11494164 | 9176627.53 | 2050018834 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-05-11 | 2016-04-30 | 2020-01-08 | 2020-01-08 | 2016-04-30 |  | ضعف كفاءة المقاول الفنية |  | 50.5054 | 26.4769 | منجز | No
2100045452 | أمانة / تبوك | تشييد | لم تعد تحتاجها الجهة | 698000 | 34900 | 462000 | 150566.23 | 4650060073 | لا | 0 | 190309081683 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-05-23 | 2015-09-20 | 2021-01-31 | 2021-01-31 | 2015-09-20 |  | ضعف كفاءة المقاول الفنية |  | 36.542 | 28.4333 | منجز | No
2100042534 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 1157751 | 57887.55 | 325973 | 325973 | 5950002498 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 37 | 100 | 2009-01-18 | 2009-12-03 | 2019-08-19 | 2019-08-19 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 43.1379 | 18.0853 | مسحوب | No
2100088211 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 103401573 | 5170078.65 | 81238495.01 | 81238495.01 | 1010039430 | لا | 0 |  | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-08-28 | 2020-06-23 | 2022-05-01 | 2022-05-01 |  |  | أوامر تغيير | أخرى |  |  | متأخر | No
2100042475 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 10756705.63 | 537835.2815 | 3893193.81 | 3893193.81 | 1116004360 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 36 | 100 | 2013-02-01 | 2015-01-24 | 2015-04-22 | 2015-04-22 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 41.4374 | 19.7864 | مسحوب | No
2100041812 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 55191677.85 | 2759583.8925 | 35766533.65 | 0 | 5950009827 | لا | 0 | 190209019099 | جاري | التكلفة المفوترة | 87 | 100 | 2015-03-10 | 2017-08-26 | 2022-06-24 | 2022-06-24 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | Failed | Yes
2100043772 | أمانة / الجوف | تشييد | ذات اولوية متوسطة | 392000 | 19600 | 392000 | 392000 | 3400101526 | لا | 0 | 190609047966 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-01-30 | 2019-12-05 | 2020-01-19 | 2020-01-19 | 2019-12-05 |  |  |  | 39.8948 | 29.8032 | منجز | No
2100010743 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 6180363.12 | 309018.156 | 3123154 | 3123154 | 2943000000 | لا | 0 |  | مسحوب | التكلفة المفوترة | 66 | 100 | 2014-03-25 | 2015-09-16 | 2023-05-28 | 2023-05-28 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7271 | 22.2863 | مسحوب | No
2100046384 | أمانة / عسير | تشييد | ذات اولوية عالية | 4728248 | 236412.4 | 3339500 | 3339500 | 5857024318 | لا | 0 |  | جاري | تكلفة العمل المنجز | 25 | 100 | 2019-06-30 | 2020-06-20 | 2023-03-05 | 2023-03-05 |  |  | ضعف كفاءة المقاول الفنية |  | 42.8281 | 18.1969 | Failed | No
2100041661 | وزارة الموارد البشرية والتنمية الإجتماعية | إشراف | ذات اولوية منخفضة | 872400 | 43620 | 1345400 | 1345400 | 1010435790 | لا | 0 | 181009183524 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-12-23 | 2016-11-30 | 2022-03-08 | 2022-03-08 | 2016-11-30 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 40.2684 | 20.1706 | منجز | No
2100046491 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 28694292.09 | 1434714.6045 | 28309501 | 4388541.63 | 5950014853 | لا | 0 | 210501030518 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-07-18 | 2020-09-17 | 2020-09-18 | 2020-09-18 | 2020-09-17 |  |  |  | 44.2385 | 17.552 | منجز | No
2100045765 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 1899790 | 94989.5 | 530079.4 | 530079.4 | 4601002288 | لا | 0 |  | جاري | تكلفة العمل المنجز | 27 | 100 | 2019-03-31 | 2020-03-20 | 2023-09-14 | 2023-09-14 |  |  | تأخرصرف المستحقات المالية |  | 41.264 | 20.1793 | Failed | No
2100048086 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 2220365.4 | 111018.27 | 2025470.2 | 1917010.2 | 5810009404 | لا | 0 | 181109304382 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 88 | 100 | 2015-10-11 | 2016-09-30 | 2021-03-30 | 2021-03-30 | 2016-09-30 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 41.4637 | 20.0125 | منجز | No
2100017065 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 3053266.94 | 152663.347 | 1590892.95 | 1590892.95 | 1010164501 | لا | 0 |  | مسحوب | التكلفة المفوترة | 52 | 100 | 2015-10-18 | 2016-10-12 | 2021-07-07 | 2021-07-07 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 46.7098 | 24.6114 | مسحوب | No
2100049921 | أمانة / الجوف | تشييد | ذات اولوية عالية | 285045 | 14252.25 | 285045 | 285045 | 3452101159 | لا | 0 | 190709089772 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-12-22 | 2019-06-22 | 2019-07-23 | 2019-07-23 | 2019-06-22 |  |  |  | 37.9798 | 30.7214 | منجز | No
2100047736 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 2769200 | 138460 | 2616898 | 2616898 | 4030151374 | لا | 0 | 200409125699 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-08-01 | 2021-01-13 | 2021-09-01 | 2021-09-01 | 2021-01-13 |  | ضعف كفاءة المقاول الفنية |  | 41.0787 | 19.1281 | منجز | No
2100045920 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 753116 | 37655.8 | 406280 | 406280 | 5950021811 | لا | 0 | 210501030518 | مسحوب | تكلفة العمل المنجز | 53 | 100 | 2014-11-26 | 2015-11-14 | 2015-11-15 | 2015-11-15 |  |  | ضعف كفاءة المقاول الفنية |  | 44.2281 | 17.5471 | مسحوب | No
2100047272 | أمانة / حائل | تشييد | ذات اولوية عالية وعاجلة | 17467961 | 873398.05 | 15579404.18 | 15579404.18 | 4700003298 | لا | 0 | 181101263217 | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 96 | 100 | 2019-02-11 | 2021-07-29 | 2022-12-25 | 2022-12-25 |  |  |  |  | 41.7306 | 27.5089 | متأخر | No
2100047390 | أمانة / الجوف | تشييد | ذات اولوية عالية وعاجلة | 1426614.88 | 71330.744 | 1030350 | 606350 | 3452004651 | لا | 0 | 190509075446 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-04-11 | 2021-03-30 | 2021-03-31 | 2021-03-31 | 2021-03-30 |  |  |  | 37.1473 | 31.4806 | منجز | No
2100049766 | أمانة / جازان | تشييد | ذات اولوية عالية | 969000 | 48450 | 969000 | 969000 | 5907022967 | لا | 0 | 180601013838 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-08-28 | 2019-08-13 | 2019-08-13 | 2019-08-13 | 2019-08-13 |  | اخرى |  | 42.9536 | 16.7117 | منجز | No
2100018233 | أمانة / جازان | تشييد | لم تعد تحتاجها الجهة | 3700000 | 185000 | 0 | 0 | 5903014222 | لا | 0 | 181109363410 | مسحوب | الكميات التي تم تركيبها | 57 | 100 | 2012-04-16 | 2012-10-13 | 2019-03-31 | 2019-03-31 |  |  | اخرى |  | 42.6272 | 17.1544 | مسحوب | No
2100020451 | أمانة / جازان | تشييد | ذات اولوية عالية | 1931890 | 96594.5 | 1340000 | 1340000 | 9503028621 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 69 | 100 | 2015-06-26 | 2016-06-20 | 2019-09-25 | 2019-09-25 |  |  | اخرى |  | 42.2661 | 17.7335 | مسحوب | No
2100049081 | أمانة / جازان | تشييد | ذات اولوية عالية وعاجلة | 10995587 | 549779.35 | 3794104.45 | 3794104.45 | 5950004973 | لا | 0 | 181101249490 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-01-21 | 2022-04-20 | 2022-03-30 | 2022-03-30 | 2022-04-20 |  | ضعف كفاءة المقاول الفنية |  | 42.7547 | 16.5004 | منجز | No
2100050293 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 11292783.47 | 564639.1735 | 11292783 | 11292783 | 4030201495 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-08-31 | 2017-08-20 | 2018-11-14 | 2018-11-14 | 2017-08-20 |  | اخرى |  | 36.5607 | 28.3864 | منجز | No
2100022820 | أمانة / العاصمة المقدسة | ترميم | ذات اولوية متوسطة | 18282757.5 | 914137.875 | 75246 | 75246 | 4030271639 | لا | 0 | 200209138726 | مسحوب | تكلفة العمل المنجز | 0 | 0 | 2019-09-06 | 2021-05-29 | 2021-05-29 | 2021-05-29 |  |  | اخرى |  | 39.8557 | 21.3852 | مسحوب | No
2100049792 | أمانة / جازان | تشييد | لم تعد تحتاجها الجهة | 5470400 | 273520 | 5470400 | 5470400 | 5901011309 | لا | 0 | 180701017372 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-10-02 | 2020-03-10 | 2020-03-10 | 2020-03-10 | 2020-03-10 |  | اخرى |  | 42.7765 | 17.1089 | منجز | No
2100050654 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 2677794 | 133889.7 | 1207852 | 0 | 3350018969 | لا | 0 | 200501038639 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-10-01 | 2020-09-25 | 2021-04-26 | 2021-04-26 | 2020-09-25 |  | ضعف كفاءة المقاول الفنية |  | 42.4135 | 27.8869 | منجز | Yes
2100051354 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 1950300 | 97515 | 831500 | 831500 | 5850030206 | لا | 0 | 181109358685 | مسحوب | تكلفة العمل المنجز | 43 | 100 | 2015-07-07 | 2016-11-17 | 2021-12-19 | 2021-12-19 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5775 | 16.883 | مسحوب | No
2100074513 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 18583935 | 929196.75 | 2485686.82 | 2485686.82 | 1010142553 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 20 | 100 | 2015-07-05 | 2017-09-22 | 2017-09-22 | 2017-09-22 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 46.7098 | 24.6275 | مسحوب | No
2100050665 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 77999966 | 3899998.3 | 77999966 | 77999966 | 4032002354 | لا | 0 | 181009119031 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2011-01-24 | 2013-01-13 | 2013-01-13 | 2013-01-13 | 2013-01-13 |  |  |  | 42.8476 | 21.2555 | منجز | No
2100052920 | أمانة / نجران | تشييد | ذات اولوية عالية | 2577108 | 128855.4 | 1631061.4 | 1631061.4 | 5950001999 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-06-29 | 2020-06-17 | 2020-04-12 | 2020-04-12 | 2020-06-17 | [5 empty] | منجز | No
2100190783 | شركة المياه الوطنية / منطقة القصيم | إشراف | ذات اولوية عالية وعاجلة | 4802400 | 240120 | 1257295 | 780390 | 1010323435 | لا | 0 | 201201078996 | جاري | منهجية القيمة المكتسبة | 62.29 | 62.29 | 2021-04-12 | 2022-10-04 | 2022-10-05 | 2022-10-05 |  |  |  |  | 43.9864 | 26.3461 | خدمات عامة | No
2100023306 | وزارة التعليم | تشييد | ذات اولوية عالية | 11933532.3 | 596676.615 | 5724899 | 5724899 | 1010051817 | لا | 0 |  | مسحوب | التكلفة المفوترة | 48 | 100 | 2014-02-23 | 2017-11-27 | 2019-10-23 | 2019-10-23 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | مسحوب | No
2100052695 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | تشييد | ذات اولوية عالية | 818384937.55 | 40919246.8775 | 736.5464 | 736.5464 | 2050065077 | لا | 0 | 195856667026 | جاري | تكلفة العمل المنجز | 99 | 100 | 2014-08-22 | 2017-07-06 | 2022-12-31 | 2022-12-31 |  |  | تأخرصرف المستحقات المالية |  | 50.101 | 26.4494 | Failed | No
2100068736 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 1048320 | 52416 | 1048320 | 1048320 | 4030132629 | لا | 0 | 201101176029 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 97 | 95 | 2020-01-05 | 2020-12-24 | 2020-10-11 | 2020-10-11 | 2020-12-24 |  | اخرى |  | 39.1773 | 21.5302 | منجز | No
2100054946 | أمانة / نجران | تشييد | ذات اولوية عالية | 14245620.09 | 712281.0045 | 12139829.09 | 12139829.09 | 5950013363 | لا | 0 | 180909073640 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 96 | 100 | 2015-08-03 | 2017-01-16 | 2021-06-26 | 2021-06-26 | 2017-01-16 |  |  |  | 44.1148 | 17.567 | منجز | No
2100053480 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 11662000 | 583100 | 11662000 | 11662000 | 5810001890 | لا | 0 | 181101311223 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-02-13 | 2021-01-21 | 2022-04-27 | 2022-04-27 | 2021-01-21 |  | ضعف كفاءة المقاول الفنية |  | 41.4603 | 20.0123 | منجز | No
2100053734 | أمانة / جدة | تشييد | ذات اولوية عالية | 19498062 | 974903.1 | 18373074 | 18373074 | 1010187733 | لا | 0 | 191001287216 | منجز – استلام نهائي | تكلفة العمل المنجز | 87 | 100 | 2019-09-24 | 2020-12-04 | 2020-06-04 | 2020-06-04 | 2020-12-04 | 2020-04-12 | اخرى |  | 39.1907 | 21.4867 | منجز | No
2100052150 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البرية | تشييد | ذات اولوية متوسطة | 2305201.5 | 115260.075 | 2305201.5 | 2305201.5 | 3550128603 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-01-12 | 2020-12-02 | 2021-09-05 | 2021-09-05 | 2020-12-02 |  | تأخرصرف المستحقات المالية |  | 36.6003 | 28.4093 | منجز | No
2100058203 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2605624 | 130281.2 | 0.01 | 0.01 | 2251017211 | لا | 0 |  | مسحوب | التكلفة المفوترة | 1 | 100 | 2017-09-28 | 2018-09-13 | 2018-09-23 | 2018-09-23 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5604 | 25.3897 | مسحوب | No
2100063000 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 10566636 | 528331.8 | 8414072 | 299424.62 | 5950005891 | لا | 0 | 220601025060 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-06-05 | 2019-05-25 | 2019-05-26 | 2019-05-26 | 2019-05-25 |  |  |  | 47.1235 | 17.4898 | منجز | No
2100059780 | أمانة / جدة | تشييد | ذات اولوية عالية | 114000000 | 5700000 | 3640232.29 | 41561.68 | 2050027937 | لا | 0 | 190701207031 | مسحوب | تكلفة العمل المنجز | 9 | 83 | 2019-11-03 | 2021-11-03 | 2021-11-24 | 2021-11-24 |  |  | اخرى |  | 39.1854 | 21.5163 | مسحوب | No
2100055355 | وزارة الصحة / القريات | ترميم | ذات اولوية متوسطة | 2974597.5 | 148729.875 | 1868485.53 | 0 | 2050068940 | لا | 0 | 200509012997 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-04-22 | 2019-06-21 | 2021-04-07 | 2021-04-07 | 2019-06-21 |  | ضعف كفاءة المقاول الفنية |  | 37.9435 | 30.7389 | منجز | Yes
2100058656 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 10567253.07 | 528362.6535 | 0 | 0 | 1010233305 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0 | 100 | 2015-05-07 | 2017-02-17 | 2024-06-06 | 2024-06-06 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.5429 | 16.8808 | مسحوب | No
2100056766 | أمانة / جدة | إشراف | ذات اولوية متوسطة | 26222400 | 1311120 | 27121772 | 25027622 | 1010902667 | لا | 0 | 181109275427 | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2018-06-24 | 2021-06-23 | 2022-01-27 | 2022-01-27 | 2021-06-23 |  | اخرى |  | 39.1677 | 21.5008 | منجز | No
2100060174 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 21376034 | 1068801.7 | 2030166 | 2030166 | 1010178798 | لا | 0 |  | مسحوب | التكلفة المفوترة | 14 | 100 | 2015-04-13 | 2017-09-28 | 2021-06-08 | 2021-06-08 |  |  | ضعف كفاءة المقاول الفنية |  | 38.0563 | 24.1078 | مسحوب | No
2100059135 | أمانة / جازان | تشييد | ذات اولوية عالية | 6836000 | 341800 | 4811022 | 4811022 | 5950011723 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 92 | 100 | 2018-12-20 | 2019-12-05 | 2021-10-13 | 2021-10-13 | 2019-12-05 |  | ضعف كفاءة المقاول الفنية |  | 42.7751 | 17.109 | منجز | No
2100062020 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 8476630.45 | 423831.5225 | 4151430 | 4151430 | 2031040463 | لا | 0 |  | مسحوب | التكلفة المفوترة | 55 | 100 | 2012-09-28 | 2014-09-18 | 2014-12-17 | 2014-12-17 |  |  | ضعف كفاءة المقاول الفنية |  | 45.975 | 28.4334 | مسحوب | No
2100058520 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 11714776.33 | 585738.8165 | 136571.82 | 136571.82 | 1010046644 | لا | 0 |  | مسحوب | التكلفة المفوترة | 2 | 83 | 2016-07-26 | 2019-09-03 | 2019-09-04 | 2019-09-04 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5604 | 25.3897 | مسحوب | No
2100019412 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 1326675 | 66333.75 | 1185721 | 1185721 | 4031033277 | لا | 0 | 190609069433 | جاري الاستلام الإبتدائي | التكلفة المفوترة | 94.48 | 94.48 | 2018-10-31 | 2020-12-16 | 2020-12-16 | 2020-12-16 |  |  |  |  | 39.8439 | 21.366 | Failed | No
2100063206 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 1120000 | 56000 | 144692 | 144692 | 3350027442 | لا | 0 | 200501046239 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 65 | 100 | 2019-08-19 | 2020-08-12 | 2020-08-13 | 2020-08-13 | 2020-08-12 |  |  |  | 42.443 | 27.1781 | منجز | No
2100064632 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1800000 | 90000 | 1042931 | 1042931 | 1116006470 | لا | 0 | 210801132015 | ايقاف كلي | تكلفة العمل المنجز | 95 | 100 | 2019-09-30 | 2020-09-24 | 2023-06-15 | 2023-06-15 |  |  | ضعف كفاءة المقاول الفنية |  | 42.172 | 22.7187 | Failed | No
2100062495 | أمانة / الجوف | تشييد | ذات اولوية عالية وعاجلة | 4179910 | 208995.5 | 2844350 | 2844350 | 3452006978 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-03-09 | 2014-09-01 | 2014-09-01 | 2014-09-01 | 2014-09-01 |  |  |  | 37.158 | 31.4855 | منجز | No
2100077991 | مدينة الملك سعود الطبية | دراسة الجدوى |  | 6300000 | 315000 | 0 | 0 | 0 |  | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 0 | 100 | 2020-04-29 00:59 | 2022-04-29 00:59 |  |  |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  |  |  | Failed | No
2100065855 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 8989155 | 449457.75 | 8989155 | 8090239 | 5800000059 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2013-10-23 | 2020-03-30 | 2021-03-14 | 2021-03-14 | 2020-03-30 |  | ضعف كفاءة المقاول الفنية |  | 41.4537 | 20.0137 | منجز | No
2100082865 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 18149538 | 907476.9 | 16227543 | 16227543 | 1010134746 | لا | 0 | 181109230821 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99.9 | 100 | 2017-04-02 | 2019-04-02 | 2022-10-29 | 2022-10-29 | 2019-04-02 |  | أوامر تغيير |  | 38.306 | 23.9596 | منجز | No
2100063884 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 910245 | 45512.25 | 910245 | 910245 | 4658000071 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 100 | 100 | 2019-09-15 | 2020-03-10 | 2020-03-10 | 2020-03-10 |  |  | ضعف كفاءة المقاول الفنية |  | 38.1948 | 24.0522 | مسحوب | No
2100064643 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1496490 | 74824.5 | 701611.98 | 701611.98 | 1017000621 | لا | 0 | 190309002446 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2011-12-13 | 2012-12-07 | 2012-12-07 | 2012-12-07 | 2012-12-07 |  | ضعف كفاءة المقاول الفنية |  | 42.8421 | 21.2536 | منجز | No
2100013532 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 15622087.97 | 781104.3985 | 15622087.97 | 15622087.97 | 4031058219 | لا | 0 | 181201471718 | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2019-02-28 | 2021-02-05 | 2021-02-05 | 2021-02-05 | 2021-02-05 | 2020-02-06 | ضعف كفاءة المقاول الفنية |  | 39.0143 | 22.7832 | منجز | No
2100065192 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 2468832 | 123441.6 | 1077785 | 1077785 | 4032020280 | لا | 0 | 210301237624 | مسحوب | تكلفة العمل المنجز | 56 | 100 | 2019-10-20 | 2020-10-14 | 2022-01-01 | 2022-01-01 |  |  |  |  | 40.411 | 21.258 | مسحوب | No
2100063825 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 3600000 | 180000 | 0 | 0 | 4035000994 | لا | 0 | 201109063561 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 92 | 100 | 2019-07-23 | 2021-01-13 | 2023-03-15 | 2023-03-15 |  |  |  |  | 40.8298 | 20.7294 | Failed | No
2100067200 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 27240207.85 | 1362010.3925 | 24256729.96 | 24256729.96 | 5950009261 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 93 | 100 | 2014-12-14 | 2016-11-22 | 2020-12-30 | 2020-12-30 | 2016-11-22 |  | اخرى |  | 44.2351 | 17.5659 | منجز | No
2100071971 | أمانة / جازان | تشييد | ذات اولوية عالية | 230862.05 | 11543.1025 | 100207 | 100207 | 5950012625 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-10-14 | 2016-04-11 | 2019-02-15 | 2019-02-15 | 2016-04-11 |  | اخرى |  | 42.5715 | 16.8998 | منجز | No
2100065951 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 5929875 | 296493.75 | 3913540.02 | 3913540.02 | 4031045075 | لا | 0 | 191101186083 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-10-15 | 2020-10-09 | 2020-10-14 | 2020-10-14 | 2020-10-09 |  |  |  | 40.4322 | 21.2753 | منجز | No
2100068040 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 182000 | 9100 | 163800 | 163800 | 3550023679 | لا | 0 | 190201005587 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-12-31 | 2019-06-25 | 2019-06-25 | 2019-06-25 | 2019-06-25 |  | اخرى |  | 38.5225 | 27.6086 | منجز | No
2100069171 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 2200000 | 110000 | 2189999.98 | 2189999.98 | 4037000639 | لا | 0 | 190401135345 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-01-31 | 2021-01-25 | 2021-01-25 | 2021-01-25 | 2021-01-25 |  |  |  | 41.3621 | 22.6123 | منجز | No
2100067653 | أمانة / جدة | تشييد | ذات اولوية عالية | 11749500 | 587475 | 10315295.55 | 10315295.55 | 4030183054 | لا | 0 |  | منجز – استلام نهائي | تكلفة العمل المنجز | 88 | 100 | 2020-01-15 | 2020-01-31 | 2021-04-06 | 2021-04-06 | 2020-01-31 | 2021-04-06 | اخرى |  | 39.1772 | 21.5039 | منجز | No
2100069344 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 1720250 | 86012.5 | 1720250 | 1720250 | 4605000749 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-04-14 | 2020-04-02 | 2020-04-02 | 2020-04-02 | 2020-04-02 |  | اخرى |  | 39.7363 | 23.0124 | منجز | No
2100069882 | شركة المياه الوطنية / منطقة مكة المكرمة | دراسات هندسية | ذات اولوية عالية | 46967739 | 2348386.95 | 43245682.62 | 43245682.62 | 1010282788 | لا | 0 |  | جاري | تكلفة العمل المنجز | 57 | 65.8 | 2019-06-18 | 2020-12-18 | 2022-06-18 | 2022-06-18 |  |  | لا يوجد تأخير |  |  |  | خدمات عامة | No
2100086240 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 3028442 | 151422.1 | 892951 | 892951 | 1010287891 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 24 | 100 | 2014-03-26 | 2015-12-04 | 2019-07-31 | 2019-07-31 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 44.4412 | 24.5406 | مسحوب | No
2100071820 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 2000000 | 100000 | 479059 | 479059 | 4030138666 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 36.05 | 48.61 | 2014-11-10 | 2016-10-19 | 2016-11-19 | 2016-11-19 |  |  |  |  | 39.9991 | 21.9815 | مسحوب | No
2100074314 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2581000 | 129050 | 1935750 | 1935750 | 2059001094 | لا | 0 |  | جاري | التكلفة المفوترة | 88 | 100 | 2009-03-27 | 2010-03-22 | 2022-12-31 | 2022-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 50.105 | 26.444 | Failed | No
2100068390 | أمانة / تبوك | تشييد | ذات اولوية عالية | 2800220 | 140011 | 2099900 | 2099900 | 3554000169 | لا | 0 | 181009142350 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-01-27 | 2016-01-22 | 2016-01-22 | 2016-01-22 | 2016-01-22 |  | ضعف كفاءة المقاول الفنية |  | 38.5406 | 27.6143 | منجز | No
2100078606 | أمانة / تبوك | تصميم | ذات اولوية متوسطة | 52500 | 2625 | 52500 | 0 | 3550025925 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-05-01 | 2020-01-26 | 2020-01-26 | 2020-01-26 | 2020-01-26 |  | اخرى |  | 37.187 | 27.0479 | منجز | Yes
2100080231 | وزارة المالية | تشييد | ذات اولوية متوسطة | 2807120.1 | 140356.005 | 2807120.1 | 2807120.1 | 1010349609 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2020-06-24 | 2020-12-24 | 2022-03-31 | 2022-03-31 | 2020-12-24 |  | لا يوجد تأخير |  | 47.3088 | 24.1532 | منجز | No
2100071665 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 1881000 | 94050 | 1670191 | 1670191 | 5950012645 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2018-06-25 | 2020-06-02 | 2020-06-02 | 2020-06-02 | 2020-06-02 |  | اخرى |  | 44.2316 | 17.5569 | منجز | No
2100036680 | أمانة / تبوك | تشييد | ذات اولوية عالية | 2948600 | 147430 | 816548 | 816548 | 1010156220 | لا | 0 | 190401068773 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 38 | 100 | 2018-09-01 | 2020-02-23 | 2020-06-15 | 2020-06-15 | 2020-02-23 |  | ضعف كفاءة المقاول الفنية |  | 36.4986 | 27.3934 | منجز | No
2100003231 | شركة المياه الوطنية / منطقة نجران | تشييد | ذات اولوية عالية وعاجلة | 21360500 | 1068025 | 21360500 | 21360500 | 5950014853 | لا | 0 | 180201000116 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-10-28 | 2021-04-01 | 2021-05-23 | 2021-05-23 | 2021-04-01 |  | لا يوجد تأخير |  | 44.2336 | 17.5636 | منجز | No
2100075946 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 12148932 | 607446.6 | 12148932 | 12148932 | 1010219886 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-06-30 | 2023-01-05 | 2023-05-06 | 2023-05-06 | 2023-01-05 |  |  |  | 39.5442 | 24.4531 | منجز | No
2100072376 | أمانة / الباحة | تشييد | ذات اولوية عالية وعاجلة | 3420625 | 171031.25 | 221915.3 | 221915.3 | 5800007456 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-09-20 | 2020-08-29 | 2021-04-11 | 2021-04-11 | 2020-08-29 |  | ضعف كفاءة المقاول الفنية |  | 41.3145 | 20.1767 | منجز | No
2100074922 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1871900 | 93595 | 687733.25 | 687733.25 | 4036000759 | لا | 0 | 190509041563 | مسحوب | تكلفة العمل المنجز | 37 | 100 | 2013-03-19 | 2014-03-14 | 2020-06-12 | 2020-06-12 |  |  | ضعف كفاءة المقاول الفنية |  | 42.8521 | 21.2551 | مسحوب | No
2100071794 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 3766632.5 | 188331.625 | 3736632.5 | 3736632.5 | 1010182506 | لا | 0 | 181109313941 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 85 | 100 | 2015-10-24 | 2017-04-09 | 2020-04-06 | 2020-04-06 | 2017-04-09 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 41.4573 | 20.0074 | منجز | No
2100075176 | أمانة / الجوف | تشييد | ذات اولوية عالية وعاجلة | 2973420 | 148671 | 0 | 0 | 3453002458 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 0 | 0 | 2015-06-30 | 2016-01-02 | 2023-02-01 | 2023-02-01 |  |  | تصاريح أعمال التنفيذ |  | 37.1469 | 31.4888 | مسحوب | No
2100078632 | شركة المياه الوطنية / منطقة القصيم | إشراف | ذات اولوية عالية وعاجلة | 10784400 | 539220 | 10783661.5 | 10783661.5 | 1010421976 | لا | 0 | 180709019616 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2016-12-01 | 2020-12-01 | 2021-08-24 | 2021-08-24 | 2020-12-01 |  | لا يوجد تأخير |  | 43.7441 | 25.9842 | منجز | No
2100072461 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 10143633.8 | 507181.69 | 9129169.8 | 9129169.8 | 1010188619 | لا | 0 | 181009141357 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-05-12 | 2016-11-02 | 2018-07-23 | 2018-07-23 | 2016-11-02 |  | اخرى |  | 35.0202 | 28.4788 | منجز | No
2100078223 | أمانة / جازان | دراسة الجدوى | ذات اولوية عالية | 499380 | 24969 | 499380 | 499380 | 5850041489 | لا | 0 |  | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2013-09-28 | 2014-03-27 | 2018-12-30 | 2018-12-30 | 2014-03-27 |  | اخرى |  | 42.6937 | 17.5134 | منجز | No
2100076720 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 1740800 | 87040 | 1740800 | 1740800 | 3555000942 | لا | 0 | 190309004666 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-12-02 | 2019-10-22 | 2019-11-22 | 2019-11-22 | 2019-10-22 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 35.7243 | 27.3457 | منجز | No
2100076171 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 1647340 | 82367 | 0 | 0 | 5950001999 | لا | 0 |  | جاري | تكلفة العمل المنجز | 2 | 100 | 2020-01-21 | 2020-08-14 | 2021-07-07 | 2021-07-07 |  |  | اخرى |  | 41.7155 | 27.4974 | Failed | No
2100190724 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية وعاجلة | 200960451.61 | 10048022.5805 | 7942676.25 | 0 | 1010012911 | لا | 0 | 201101019567 | جاري | منهجية القيمة المكتسبة | 40.7 | 36.19 | 2021-01-09 | 2023-06-28 | 2023-06-28 | 2023-06-28 |  |  |  |  | 44.2346 | 26.3172 | منتظم | Yes
2100083451 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1097850 | 54892.5 | 1097850 | 165933 | 4032030968 | لا | 0 | 190509025101 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-12-12 | 2019-12-12 | 2019-12-12 | 2019-12-12 | 2019-12-12 |  | ضعف كفاءة المقاول الفنية |  | 41.0716 | 20.4622 | منجز | No
2100090064 | أمانة / الرياض | دراسة الجدوى | ذات اولوية متوسطة | 1747800 | 87390 | 41809 | 0 | 1010347774 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-11-05 | 2017-10-20 | 2017-10-20 | 2017-10-20 | 2017-10-20 |  | اخرى |  |  |  | منجز | Yes
2100079413 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1718390.72 | 85919.536 | 1214291.98 | 1214291.98 | 2511482400 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2013-06-01 | 2014-04-27 | 2020-11-25 | 2020-11-25 | 2014-04-27 |  | ضعف كفاءة المقاول الفنية |  | 45.975 | 28.4334 | منجز | No
2100028383 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 5999999.25 | 299999.9625 | 4983377 | 4983377 | 1010997845 | لا | 0 | 200309042756 | منجز – استلام ابتدائي | التكلفة المفوترة | 83.42 | 83.42 | 2019-07-09 | 2021-06-28 | 2022-03-05 | 2022-03-05 | 2021-06-28 |  |  |  | 39.8831 | 21.3122 | منجز | No
2100082681 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 777350 | 38867.5 | 777350 | 450000 | 7012378068 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-09-24 | 2020-09-19 | 2020-09-20 | 2020-09-20 | 2020-09-19 |  |  |  | 36.5762 | 28.3654 | منجز | No
2100080522 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 49500000 | 2475000 | 2544178.52 | 0 | 5950010109 | لا | 0 | 181209507660 | ايقاف جزئي | تكلفة العمل المنجز | 46 | 58 | 2018-11-06 | 2020-10-26 | 2023-05-08 | 2023-05-08 |  |  | ضعف كفاءة المقاول الفنية |  | 40.4336 | 21.252 | Failed | Yes
2100084464 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1279250 | 63962.5 | 1279250 | 1279250 | 4032028534 | لا | 0 | 181009151713 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-08-07 | 2019-08-02 | 2019-08-02 | 2019-08-02 | 2019-08-02 |  | اخرى |  | 40.83 | 20.7262 | منجز | No
2100095410 | مدينة الملك سعود الطبية | تشييد |  | 8288224.36 | 414411.218 | 0 | 0 | 2050004344 |  | 0 |  | جاري | تكلفة العمل المنجز | 95 | 100 | 2018-02-28 00:59 | 2018-10-28 00:59 |  |  |  |  | اخرى |  | 46.6906 | 24.6282 | Failed | No
2100095465 | مدينة الملك سعود الطبية | تشييد |  | 862348768.68 | 43117438.434 | 0 | 0 | 1010133046 |  | 0 |  | جاري | تكلفة العمل المنجز | 0 | 100 | 2020-03-23 00:59 | 2023-03-23 00:59 |  |  |  |  | تصاريح أعمال التنفيذ |  | 46.6906 | 24.6282 | Failed | No
2100083506 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 19998909 | 999945.45 | 12029848 | 12029848 | 5950000060 | لا | 0 | 190509001102 | جاري | تكلفة العمل المنجز | 78.08 | 83 | 2019-01-31 | 2022-11-13 | 2022-11-13 | 2022-11-13 |  |  | التنسيق مع أصحاب المصلحه (خدمات |  | 44.2448 | 17.5743 | منتظم | No
2100083495 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 1587720 | 79386 | 555315.36 | 0 | 3350000631 | لا | 0 | 180909093498 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-12-19 | 2019-12-19 | 2021-10-18 | 2021-10-18 | 2019-12-19 |  |  |  | 42.1224 | 26.5105 | منجز | Yes
2100084781 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 7651680 | 382584 | 7608462 | 7266206 | 4030023505 | لا | 0 | 181209546664 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2014-04-09 | 2016-04-08 | 2018-02-01 | 2018-02-01 | 2016-04-08 |  |  |  | 38.1829 | 24.0039 | منجز | No
2100084280 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 26861206 | 1343060.3 | 27311059.94 | 25094678.69 | 5950009827 | لا | 0 | 180809037330 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-01-20 | 2015-12-30 | 2022-03-06 | 2022-03-06 | 2015-12-30 |  |  |  | 41.5688 | 19.8802 | منجز | No
2100087452 | وزارة الثقافة | تشييد |  | 3866118 | 193305.9 | 3511511.4 | 3511511.4 | 2051035552 |  | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-12-20 00:59 | 2020-03-19 00:59 | 2020-03-19 | 2020-03-19 | 2020-03-19 00:59 |  | لا يوجد تأخير |  |  |  | منجز | No
2100088664 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات الجوية | تشييد | ذات اولوية عالية | 17458604.1 | 872930.205 | 17458604.1 | 17458604.1 | 1117001848 | لا | 0 | 190901013308 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2020-07-06 | 2021-11-20 | 2022-10-31 | 2022-10-31 | 2021-11-20 |  | لا يوجد تأخير |  | 36.5941 | 28.4003 | منجز | No
2100086446 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 6039987 | 301999.35 | 4843550.11 | 4843550.11 | 2031040463 | لا | 0 |  | مسحوب | التكلفة المفوترة | 80 | 100 | 2012-12-15 | 2014-06-02 | 2014-06-02 | 2014-06-02 |  |  | ضعف كفاءة المقاول الفنية |  | 45.975 | 28.4334 | مسحوب | No
2100090042 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 138083327.7 | 6904166.385 | 112076170.01 | 112076170.01 | 1010287504 | لا | 0 | 180809049367 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2013-02-09 | 2015-02-07 | 2020-07-20 | 2020-07-20 | 2015-02-07 |  | لا يوجد تأخير |  | 49.6626 | 27.0037 | منجز | No
2100084512 | أمانة / جدة | تشييد | ذات اولوية عالية | 79971987 | 3998599.35 | 68416289.69 | 63433830.55 | 4030034104 | لا | 0 | 181001169720 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-01-10 | 2020-12-18 | 2022-07-08 | 2022-07-08 | 2020-12-18 |  | اخرى |  | 39.1839 | 21.5903 | منجز | No
2100090532 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 16922924 | 846146.2 | 16922899.8 | 16922899.8 | 1010069549 | لا | 0 | 181109374934 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-04-22 | 2019-01-01 | 2021-04-01 | 2021-04-01 | 2019-01-01 |  | ضعف كفاءة المقاول الفنية |  | 41.6829 | 27.5382 | منجز | No
2100098545 | هيئة تطوير بوابة الدرعية | تشييد | ذات اولوية متوسطة | 9975000 | 498750 | 9975000 | 9975000 | 1010079992 | لا | 0 |  | جاري | اخرى | 100 | 100 | 2019-06-10 | 2020-07-12 | 2020-09-29 | 2020-09-29 | [6 empty] | Failed | No
2100088815 | وزارة التعليم | تشييد | ذات اولوية عالية | 12660499.73 | 633024.9865 | 11275759.33 | 11275759.33 | 1116002219 | لا | 0 |  | جاري | التكلفة المفوترة | 92 | 100 | 2012-03-17 | 2014-03-07 | 2014-12-19 | 2014-12-19 |  |  | ضعف كفاءة المقاول الفنية |  | 37.9189 | 26.6149 | Failed | No
2100086973 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 12399783.42 | 619989.171 | 4005171.8 | 4005171.8 | 3350003498 | لا | 0 |  | مسحوب | التكلفة المفوترة | 41 | 100 | 2014-09-07 | 2016-08-27 | 2022-11-16 | 2022-11-16 |  |  | ضعف كفاءة المقاول الفنية |  | 38.0161 | 24.1041 | مسحوب | No
2100090101 | وزارة التعليم | تشييد | ذات اولوية عالية | 29148888.73 | 1457444.4365 | 25128332.77 | 21361174.05 | 4650049177 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-08-03 | 2022-03-09 | 2022-03-15 | 2022-03-15 | 2022-03-09 |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | منجز | No
2100088686 | وزارة الدفاع / الإدارة الهندسية والاشغال بالخدمات الصحية | تشييد | ذات اولوية متوسطة | 22669983 | 1133499.15 | 12055068.57 | 12055068.57 | 1010212437 | لا | 0 | 190501105770 | جاري | الكميات التي تم تركيبها | 80 | 80 | 2019-06-10 | 2020-03-28 | 2023-02-25 | 2023-02-25 |  |  | تغيرات في نطاق المشروع |  | 44.0297 | 26.201 | منتظم | No
2100091696 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 1296893 | 64844.65 | 1296893 | 1296893 | 5950018465 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2018-11-18 | 2019-11-18 | 2021-07-06 | 2021-07-06 | 2019-11-18 |  |  |  | 44.2531 | 17.5332 | منجز | No
2100088841 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 3355082.92 | 167754.146 | 1867392.49 | 1830044.64 | 4031042644 | لا | 0 | 190609081361 | جاري | التكلفة المفوترة | 65 | 100 | 2018-05-01 | 2019-03-16 | 2022-09-16 | 2022-09-16 |  |  | ضعف كفاءة المقاول الفنية |  | 41.4779 | 20.0185 | Failed | No
2100088830 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البحرية | تشييد | ذات اولوية متوسطة | 47500000 | 2375000 | 0 | 0 | 2050045205 | لا | 0 |  | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 100 | 100 | 2016-04-29 | 2020-08-20 | 2021-11-30 | 2021-11-30 |  |  |  |  | 39.1797 | 21.3341 | Failed | No
2100093516 | أمانة / جازان | تشييد | ذات اولوية عالية | 1202850 | 60142.5 | 962280 | 962280 | 5905015155 | لا | 0 | 180909074961 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 80 | 100 | 2014-12-07 | 2015-03-06 | 2020-12-31 | 2020-12-31 | 2015-03-06 |  | اخرى |  | 42.5964 | 16.8783 | منجز | No
2100091195 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 1466675 | 73333.75 | 0 | 0 | 4700012851 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 2 | 100 | 2018-05-08 | 2019-10-21 | 2019-10-21 | 2019-10-21 |  |  | ضعف كفاءة المقاول الفنية |  | 38.4222 | 24.3178 | مسحوب | No
2100092492 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البرية | تشييد | ذات اولوية متوسطة | 2291476 | 114573.8 | 838680 | 461200 | 4650027612 | لا | 0 |  | جاري | تكلفة العمل المنجز | 95 | 100 | 2019-10-20 | 2020-04-14 | 2023-02-10 | 2023-02-10 |  |  | لا يوجد تأخير | أخرى | 39.5398 | 24.5072 | Failed | No
2100096084 | مدينة الملك عبدالله الطبية بالعاصمة المقدسة | تشييد | ذات اولوية عالية | 1768492 | 88424.6 | 0 | 0 | 1010245185 | لا | 0 | 181101235461 | جاري | الكميات التي تم تركيبها | 50 | 50 | 2018-07-23 | 2019-05-17 | 2023-03-02 | 2023-03-02 |  |  |  | أخرى |  |  | Failed | No
2100092536 | أمانة / جدة | تشييد | ذات اولوية عالية | 43225000 | 2161250 | 42240269.31 | 42240269.31 | 4030141919 | لا | 0 | 180501007861 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 98 | 100 | 2018-08-27 | 2020-08-04 | 2020-10-16 | 2020-10-16 | 2020-08-04 |  | اخرى |  | 39.1639 | 21.5956 | منجز | No
2100046922 | أمانة / الطائف | تشييد | ذات اولوية عالية | 77999966 | 3899998.3 | 77999966 | 77999966 | 4032002354 | لا | 0 | 181009119031 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2011-01-24 | 2013-01-31 | 2014-09-05 | 2014-09-05 | 2013-01-31 |  |  |  | 42.8482 | 21.2524 | منجز | No
2100099175 | وزارة الدفاع / الإدارة الهندسية والاشغال بقوات الدفاع الجوي | تشييد | ذات اولوية متوسطة | 13797078.75 | 689853.9375 | 13797078.75 | 11727516.94 | 1010177619 | لا | 0 | 190701093503 | جاري | الكميات التي تم تركيبها | 88 | 100 | 2019-10-22 | 2021-09-24 | 2022-06-13 | 2022-06-13 |  |  | أوامر سامية |  | 50.0789 | 26.4213 | متأخر | No
2100096703 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 18000000 | 900000 | 1.01 | 0.01 | 4030183054 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2016-03-27 | 2018-03-17 | 2019-11-27 | 2019-11-27 | 2018-03-17 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.4987 | 18.2178 | منجز | No
2100088432 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 4765824 | 238291.2 | 4765824 | 4765824 | 1010309164 | لا | 0 |  | جاري | اخرى | 100 | 100 | 2019-01-12 | 2020-11-30 | 2020-11-30 | 2020-11-30 |  |  | لا يوجد تأخير |  |  |  | Failed | No
2100098523 | وزارة الخارجية | تشييد | ذات اولوية عالية | 15630647.15 | 781532.3575 | 14223531.7575 | 14223531.7575 | 0 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 91 | 100 | 2018-11-20 | 2020-03-20 | 2020-08-20 | 2020-08-20 |  |  |  |  | 12.5557 | 41.9019 | مسحوب | No
2100101290 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 1997250 | 99862.5 | 1997250 | 1000500 | 3357007585 | لا | 0 | 200101051767 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 98 | 2019-01-14 | 2020-01-08 | 2020-01-08 | 2020-01-08 | 2020-01-08 |  | ضعف كفاءة المقاول الفنية |  | 40.5483 | 26.4063 | منجز | No
2100100321 | وزارة الدفاع / الإدارة الهندسية والاشغال بالخدمات الصحية | تشييد | ذات اولوية متوسطة | 39995000 | 1999750 | 7106921.29 | 5546079 | 1131020873 | لا | 0 | 201209057268 | جاري | الكميات التي تم تركيبها | 16.51 | 43 | 2020-03-11 | 2022-08-13 | 2023-05-10 | 2023-05-10 |  |  | اخرى |  | 42.5683 | 16.9562 | Failed | No
2100101916 | وزارة الصحة / حائل | تشييد | ذات اولوية عالية | 8529883.76 | 426494.188 | 3631484.24 | 3631484.24 | 1010191039 | لا | 0 | 180909108671 | جاري | تكلفة العمل المنجز | 90 | 100 | 2018-11-13 | 2021-04-07 | 2022-02-01 | 2022-02-01 |  |  | تأخرصرف المستحقات المالية |  | 41.6966 | 27.5075 | Failed | No
2100099606 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1306700 | 65335 | 663077.83 | 663077.83 | 1010203405 | لا | 0 | 200209129646 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-02-18 | 2020-02-13 | 2020-05-25 | 2020-05-25 | 2020-02-13 |  | ضعف كفاءة المقاول الفنية |  | 42.1764 | 22.7227 | منجز | No
2100104042 | وزارة التعليم | تشييد | ذات اولوية عالية | 3100000 | 155000 | 813626 | 813626 | 2050054635 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 63 | 100 | 2008-12-30 | 2010-06-23 | 2018-07-11 | 2018-07-11 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.4987 | 18.2178 | مسحوب | No
2100100660 | أمانة / الجوف | تشييد | ذات اولوية متوسطة | 1356937.46 | 67846.873 | 1251525 | 1123053.75 | 3452005817 | لا | 0 | 181001183451 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-09-04 | 2019-07-24 | 2019-08-31 | 2019-08-31 | 2019-07-24 |  |  |  | 39.8434 | 29.8065 | منجز | No
2100106853 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 9943162.57 | 497158.1285 | 6084195.59 | 6084195.59 | 1010095105 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 92 | 100 | 2015-02-15 | 2016-11-06 | 2022-08-08 | 2022-08-08 | 2016-11-06 |  | ضعف كفاءة المقاول الفنية |  | 43.4919 | 25.8758 | منجز | No
2100103762 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 16989448.17 | 849472.4085 | 2257272.05 | 0.01 | 1010046644 | لا | 0 |  | مسحوب | التكلفة المفوترة | 18 | 100 | 2015-12-08 | 2017-11-26 | 2017-11-26 | 2017-11-26 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5604 | 25.3897 | مسحوب | No
2100104226 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 9214767.77 | 460738.3885 | 963230.56 | 963230.56 | 1010072637 | نعم | 963230.56 | 190209013860 | مسحوب | التكلفة المفوترة | 10.45 | 100 | 2016-02-09 | 2017-04-03 | 2017-04-03 | 2017-04-03 |  |  | ضعف كفاءة المقاول الفنية |  | 41.1632 | 19.5433 | مسحوب | No
2100107951 | وكالة / الإسكان | تشييد | ذات اولوية متوسطة | 1188369724.29 | 59418486.2145 | 615230142.75 | 615230142.75 | 2050001536 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2013-10-21 | 2015-10-10 | 2021-02-18 | 2021-02-18 | 2015-10-10 |  | أوامر تغيير | أخرى | 50.101 | 26.4494 | منجز | No
2100042092 | المؤسسة العامة للتقاعد | تشييد | ذات اولوية عالية | 32504200 | 1625210 | 22603373.99 | 22603373.99 | 1010159308 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-04-03 | 2021-09-30 | 2021-11-30 | 2021-11-30 | 2021-09-30 |  | اخرى |  | 39.1264 | 21.7258 | منجز | No
2100085982 | جامعة جازان | تشييد | ذات اولوية متوسطة | 130759327 | 6537966.35 | 74311449.31 | 74311449.31 | 2050022550 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 57 | 100 | 2013-10-06 | 2016-03-24 | 2026-12-23 | 2026-12-23 |  |  | تأخرصرف المستحقات المالية |  | 42.5429 | 16.9638 | مسحوب | No
2100042173 | جامعة القصيم | تشييد | ذات اولوية عالية | 199506832.8 | 9975341.64 | 67686844 | 67686844 | 1010166751 | نعم | 67686844 |  | مسحوب | تكلفة العمل المنجز | 30 | 100 | 2012-12-15 | 2015-11-30 | 2015-11-30 | 2015-11-30 |  |  | ضعف كفاءة المقاول الفنية |  | 43.7657 | 26.355 | مسحوب | No
2100107870 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 9215098.07 | 460754.9035 | 4271730 | 4271730 | 1010183010 | لا | 0 |  | مسحوب | التكلفة المفوترة | 54 | 100 | 2014-04-13 | 2016-04-02 | 2023-02-02 | 2023-02-02 |  |  | ضعف كفاءة المقاول الفنية |  | 42.0529 | 18.5228 | مسحوب | No
2100002634 | وزارة الشـؤون الاسلامية والدعوة والارشاد | تشييد | ذات اولوية عالية | 576345 | 28817.25 | 0 | 0 | 4031086274 | لا | 0 | 191101366705 | جاري | الكميات التي تم تركيبها | 55 | 100 | 2018-04-22 | 2019-10-03 | 2021-12-13 | 2021-12-13 |  |  | تأخرصرف المستحقات المالية |  | 40.4293 | 21.2755 | Failed | No
2100088653 | المؤسسة العامة للتقاعد | تشييد | ذات اولوية عالية | 21538800 | 1076940 | 15020010.36 | 15020010.36 | 1010159308 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-05-30 | 2021-09-30 | 2021-11-30 | 2021-11-30 | 2021-09-30 |  | اخرى |  | 39.1262 | 21.7256 | منجز | No
2100104311 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 9765371 | 488268.55 | 4051787.1 | 4051787.1 | 1128003208 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 53 | 100 | 2015-12-20 | 2018-02-08 | 2024-05-22 | 2024-05-22 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 44.8241 | 26.3046 | مسحوب | No
2100021615 | المؤسسة العامة لتحلية المياه المالحة | تشييد | ذات اولوية عالية | 3186522039 | 159326101.95 | 3091764857.63 | 3091764857.63 | 1010242485 | لا | 0 | 180909106452 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99 | 100 | 2018-01-09 | 2022-03-10 | 2022-03-10 | 2022-03-10 | 2022-03-10 |  | تأخرصرف المستحقات المالية |  | 39.046 | 22.6452 | منجز | No
2100015665 | جامعة أم القرى | تشييد | ذات اولوية منخفضة | 57805084.92 | 2890254.246 | 44749477.48 | 44749477.48 | 4030008659 | لا | 0 | 181109271950 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2011-10-15 | 2013-09-23 | 2022-12-30 | 2022-12-30 | 2013-09-23 |  |  |  | 39.9506 | 21.3159 | منجز | No
2100027506 | جامعة جازان | توريد وتركيب | ذات اولوية عالية وعاجلة | 3094586 | 154729.3 | 2793963.24 | 0 | 1010162957 | لا | 0 | 200201011112 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2020-02-02 | 2020-11-02 | 2022-07-04 | 2022-07-04 | 2020-11-02 |  | اخرى |  | 42.5532 | 16.9778 | منجز | Yes
2100023214 | جامعة جازان | تشييد | ذات اولوية منخفضة | 73207966.23 | 3660398.3115 | 17027423.96 | 17027423.96 | 1010078607 | لا | 0 | 190909088430 | فسخ العقد | الكميات التي تم تركيبها | 23 | 23 | 2015-07-30 | 2017-07-30 | 2024-01-01 | 2024-01-01 |  |  | المشروع ليس ذو أولوية في الوقت الحالي |  | 42.8931 | 17.0098 | مسحوب | No
2100047191 | وزارة المالية | إشراف | ذات اولوية متوسطة | 360000 | 18000 | 360000 | 360000 | 1010469290 | لا | 0 | 181209455243 | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2013-12-17 | 2014-05-12 | 2020-05-07 | 2020-05-07 | 2014-05-12 |  | ضعف كفاءة المقاول الفنية |  | 40.4487 | 21.1998 | منجز | No
2100019176 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 3587406.3 | 179370.315 | 929223.53 | 929223.53 | 5950006860 | لا | 0 | 191201008670 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 90.91 | 100 | 2019-05-28 | 2022-03-06 | 2023-03-30 | 2023-03-30 |  |  |  |  | 44.1759 | 17.5004 | Failed | No
2100034381 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 1063021 | 53151.05 | 1108579.52 | 0 | 4030006066 | لا | 0 | 210309104881 | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 58 | 2019-11-28 | 2021-05-12 | 2021-05-12 | 2021-05-12 | 2021-05-12 | 2021-05-13 | ضعف كفاءة المقاول الفنية |  | 41.3821 | 18.7713 | منجز | Yes
2100099816 | أمانة / جازان | تشييد | ذات اولوية عالية | 38977354.88 | 1948867.744 | 38977354.88 | 38977354.88 | 1010253433 | لا | 0 | 180709017265 | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2015-05-21 | 2020-12-27 | 2020-12-27 | 2020-12-27 |  | 2020-12-27 | اخرى |  | 44.2022 | 17.5238 | منجز | No
2100108345 | وزارة التعليم | تشييد | ذات اولوية عالية | 25117498.3 | 1255874.915 | 15455626.1 | 15455626.1 | 1010051817 | لا | 0 |  | مسحوب | التكلفة المفوترة | 71 | 100 | 2014-03-31 | 2016-03-20 | 2021-11-15 | 2021-11-15 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | مسحوب | No
2100036901 | أمانة / جازان | تشييد | ذات اولوية عالية وعاجلة | 2894670 | 144733.5 | 332852 | 332852 | 1017001724 | لا | 0 | 191001113583 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-05-20 | 2019-11-16 | 2021-06-03 | 2021-06-03 | 2019-11-16 |  | ضعف كفاءة المقاول الفنية |  | 42.6927 | 16.975 | منجز | No
2100084405 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 16852305 | 842615.25 | 12354430.82 | 11388356.17 | 5950002997 | لا | 0 | 181109284848 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 81 | 85 | 2015-11-26 | 2021-06-28 | 2021-10-18 | 2021-10-18 | 2021-06-28 |  | اخرى |  | 44.2565 | 17.5128 | منجز | No
2100104753 | جامعة الأمير سطام بن عبدالعزيز | تشييد | ذات اولوية عالية | 5028780 | 251439 | 5028751.13 | 4570334 | 1011009562 | لا | 0 | 180709018235 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-06-12 | 2019-06-07 | 2021-12-27 | 2021-12-27 | 2019-06-07 |  | تأخرصرف المستحقات المالية |  | 47.3078 | 24.1522 | منجز | No
2100082014 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 5824132.65 | 291206.6325 | 3176122.61 | 3176122.61 | 5950018186 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 93 | 93 | 2019-09-17 | 2021-08-26 | 2021-08-28 | 2021-08-28 | 2021-08-26 |  | ضعف كفاءة المقاول الفنية |  | 44.228 | 17.557 | منجز | No
2100078724 | جامعة الملك فيصل | تصميم وإشراف | ذات اولوية عالية | 21609129 | 1080456.45 | 19793332 | 19793332 | 2051048523 | لا | 0 | 180809055159 | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2016-03-03 | 2019-03-02 | 2019-07-02 | 2019-07-02 |  | 2019-03-02 | تأخرصرف المستحقات المالية |  | 49.5951 | 25.3434 | منجز | No
2100091991 | أمانة / حفر الباطن | تشييد | ذات اولوية عالية | 13797841.8 | 689892.09 | 12759746.15 | 12759746.15 | 1010008188 | لا | 0 | 190409032045 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-01-09 | 2020-10-15 | 2020-06-30 | 2020-06-30 | 2020-10-15 |  |  |  | 45.9768 | 28.3468 | منجز | No
2100076495 | مدينة الملك عبدالعزيز للعلوم والتقنية | تشييد | ذات اولوية عالية | 620670528.75 | 31033526.4375 | 566674163.9 | 542378973 | 1010419199 | لا | 0 | 180909091618 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 98 | 100 | 2015-03-26 | 2017-03-25 | 2019-11-30 | 2019-11-30 | 2017-03-25 |  |  |  | 48.4887 | 28.4257 | منجز | No
2100083031 | أمانة / جدة | تشييد | ذات اولوية عالية | 3399900 | 169995 | 3714495.73 | 3714495.73 | 1010070662 | لا | 0 | 181209458593 | منجز – استلام نهائي | اخرى | 100 | 100 | 2018-07-10 | 2021-06-07 | 2021-11-22 | 2021-11-22 | 2021-06-07 | 2023-04-03 | اخرى |  | 39.2167 | 21.4523 | منجز | No
2100060664 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 2845288 | 142264.4 | 2720009.75 | 2720009.75 | 2051034972 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 97 | 100 | 2017-08-16 | 2020-07-15 | 2020-07-19 | 2020-07-19 | 2020-07-15 |  | لا يوجد تأخير |  | 50.101 | 26.4494 | منجز | No
2100096401 | شركة المياه الوطنية / منطقة القصيم | إشراف | ذات اولوية متوسطة | 1728000 | 86400 | 942538.78 | 942538.78 | 1131054793 | لا | 0 | 180709022565 | منجز – استلام نهائي | التكلفة المفوترة | 100 | 100 | 2017-07-24 | 2019-07-24 | 2019-10-23 | 2019-10-23 |  | 2019-07-24 | لا يوجد تأخير |  | 43.9682 | 26.3403 | منجز | No
2100061983 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية | 14285000 | 714250 | 11003508.57 | 11003508.57 | 5850002600 | لا | 0 | 190201038181 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 84 | 100 | 2019-03-25 | 2020-03-13 | 2020-10-01 | 2020-10-01 | 2020-03-13 |  | لا يوجد تأخير |  | 42.9306 | 16.5897 | منجز | No
2100068283 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 2183500 | 109175 | 1985000 | 1985000 | 3450003821 | لا | 0 | 191001054999 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-10-09 | 2019-06-06 | 2019-12-18 | 2019-12-18 | 2019-06-06 |  |  |  | 41.0077 | 30.987 | منجز | No
2100071153 | جامعة الملك فيصل | تصميم | ذات اولوية عالية | 23380000 | 1169000 | 15197000 | 15197000 | 1010423886 | لا | 0 | 180809056296 | جاري | تكلفة العمل المنجز | 90 | 10 | 2013-11-13 | 2015-08-23 | 2023-01-01 | 2023-01-01 |  |  | تأخرصرف المستحقات المالية |  | 49.5924 | 25.3418 | Failed | No
2100056744 | أمانة / حفر الباطن | دراسات هندسية | ذات اولوية متوسطة | 7186080 | 359304 | 6454191 | 6454191 | 1010325732 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-09-27 | 2020-09-27 | 2021-03-31 | 2021-03-31 | 2020-09-27 |  | اخرى |  | 45.931 | 28.3938 | منجز | No
2100014162 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 3782600 | 189130 | 2067135 | 2067135 | 2060033083 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 55 | 100 | 2015-05-31 | 2016-05-30 | 2016-05-30 | 2016-05-30 |  |  | تأخرصرف المستحقات المالية |  | 50.2063 | 25.6518 | مسحوب | No
2100048650 | أمانة / حفر الباطن | تشييد | ذات اولوية متوسطة | 7894150 | 394707.5 | 7894150 | 7894150 | 1011010795 | لا | 0 | 191101099488 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-01-09 | 2020-06-24 | 2020-10-04 | 2020-10-04 | 2020-06-24 |  |  |  | 45.9759 | 28.3855 | منجز | No
2100099993 | وزارة التجارة | تصميم | ذات اولوية متوسطة | 456000 | 22800 | 114000 | 114000 | 4030225159 |  | 0 |  | ايقاف كلي | منهجية القيمة المكتسبة | 25 | 25 | 2019-01-06 | 2019-05-06 | 2020-12-30 | 2020-12-30 |  |  | لا يوجد تأخير |  |  |  | Failed | No
2100040935 | جامعة الملك فيصل | دراسة الجدوى | ذات اولوية عالية | 8636562 | 431828.1 | 7005936.65 | 7005936.65 | 1010321932 | لا | 0 | 180809040792 | جاري | تكلفة العمل المنجز | 100 | 100 | 2015-08-19 | 2017-09-18 | 2020-06-17 | 2020-06-17 |  |  | تأخرصرف المستحقات المالية |  | 49.5949 | 25.3371 | خدمات عامة | No
2100108253 | وزارة الدفاع / الإدارة الهندسية والاشغال بالخدمات الصحية | تشييد | ذات اولوية متوسطة | 49679851.8 | 2483992.59 | 49679851.8 | 49679851.8 | 1010005046 | لا | 0 | 181009141511 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-10-13 | 2015-09-29 | 2021-09-21 | 2021-09-21 | 2015-09-29 |  | تأخرصرف المستحقات المالية |  | 46.6855 | 24.6845 | منجز | No
2100019913 | أمانة / حفر الباطن | تشييد | ذات اولوية متوسطة | 7406320 | 370316 | 7406093 | 7406093 | 1010019983 | لا | 0 | 0 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-11-06 | 2020-04-30 | 2020-04-30 | 2020-04-30 | 2020-04-30 |  |  |  | 45.9794 | 28.3871 | منجز | No
2100101975 | وكالة / الإسكان | تشييد | ذات اولوية متوسطة | 50342049.53 | 2517102.4765 | 50342688.92 | 50080459 | 1116000094 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2015-01-24 | 2016-07-17 | 2018-12-22 | 2018-12-22 | 2016-07-17 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال | أخرى | 39.8289 | 22.3121 | منجز | No
2100037273 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية متوسطة | 1873357.5 | 93667.875 | 1498777.35 | 1498777.35 | 4040069541 | لا | 0 | 200691019874 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-11-14 | 2020-05-10 | 2020-05-06 | 2020-05-06 |  | 2020-05-10 | لا يوجد تأخير |  | 42.276 | 18.2348 | منجز | No
2100047644 | أمانة / حفر الباطن | تشييد | ذات اولوية متوسطة | 13780262 | 689013.1 | 13779571.84 | 13779571.84 | 1010090968 | لا | 0 | 0 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-08-11 | 2017-02-01 | 2019-10-02 | 2019-10-02 | 2017-02-01 |  | تأخرصرف المستحقات المالية |  | 45.9736 | 28.3668 | منجز | No
2100066780 | أمانة / حفر الباطن | تشييد | ذات اولوية متوسطة | 12174722.5 | 608736.125 | 12171817 | 12171817 | 1010136405 | لا | 0 | 0 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-09-09 | 2017-03-02 | 2021-07-22 | 2021-07-22 | 2017-03-02 |  | تأخرصرف المستحقات المالية |  | 45.9292 | 28.3938 | منجز | No
2100041451 | جامعة الملك فيصل | تصميم | ذات اولوية عالية | 497000 | 24850 | 479000 | 479000 | 2251042063 | لا | 0 | 181109353220 | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2014-04-28 | 2014-06-28 | 2014-06-17 | 2014-06-17 |  | 2014-06-28 | تأخرصرف المستحقات المالية |  | 49.6049 | 25.334 | منجز | No
2100108006 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 23824988.97 | 1191249.4485 | 21837978.87 | 21812011.12 | 1010039430 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-11-27 | 2020-02-20 | 2021-09-02 | 2021-09-02 | 2020-02-20 |  | أوامر تغيير | أخرى |  |  | منجز | No
2100023612 | المؤسسة العامة للحبوب | تشييد | ذات اولوية عالية | 2887500 | 144375 | 2887500 | 2887500 | 2050008923 | لا | 0 | 190801045784 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-07-28 | 2020-09-13 | 2020-09-13 | 2020-09-13 | 2020-09-13 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 50.2036 | 26.51 | منجز | No
2100191925 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 12999325 | 649966.25 | 0 | 0 | 5855026783 | لا | 0 | 190401133686 | ايقاف كلي | تكلفة العمل المنجز | 2.45 | 100 | 2020-10-18 | 2021-12-05 | 2023-08-26 | 2023-08-26 |  |  | تصاريح أعمال التنفيذ |  | 39.0196 | 22.7708 | Failed | No
2100190422 | جامعة الملك فيصل | تشييد | ذات اولوية عالية | 541989932.95 | 27099496.6475 | 541989932.95 | 360317100.45 | 1010152417 | لا | 0 | 180809040344 | جاري | الكميات التي تم تركيبها | 81 | 19 | 2019-12-19 | 2020-12-16 | 2023-12-16 | 2023-12-16 |  |  |  |  | 49.7892 | 25.3765 | Failed | No
2100050761 | أمانة / جازان | تشييد | ذات اولوية عالية | 1969890 | 98494.5 | 218950 | 218950 | 5903025849 | لا | 0 | 181201541410 | جاري | الكميات التي تم تركيبها | 50 | 100 | 2018-10-26 | 2019-10-26 | 2021-11-11 | 2021-11-11 |  |  | ضعف كفاءة المقاول الفنية |  | 42.6024 | 16.8754 | Failed | No
2100035512 | أمانة / حفر الباطن | تشييد | ذات اولوية متوسطة | 6176640 | 308832 | 6176640 | 4517714 | 1010136405 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-11-02 | 2016-10-27 | 2019-12-31 | 2019-12-31 | 2016-10-27 |  | تأخرصرف المستحقات المالية |  | 46.0595 | 28.3952 | منجز | No
2100096412 | شركة المياه الوطنية / المنطقة الشرقية | إشراف | ذات اولوية عالية | 4997484 | 249874.2 | 4937497.31 | 4937497.31 | 2050107656 | لا | 0 | 180809053092 | منجز – استلام ابتدائي | التكلفة المفوترة | 98.79 | 100 | 2018-01-25 | 2019-07-24 | 2019-09-04 | 2019-09-04 | 2019-07-24 |  | لا يوجد تأخير |  | 48.5004 | 27.4914 | منجز | No
2100035125 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 43175515 | 2158775.75 | 34063973.69 | 34063973.69 | 1010099930 | لا | 0 | 190201028265 | جاري | منهجية القيمة المكتسبة | 83 | 85 | 2015-03-25 | 2018-03-23 | 2023-10-06 | 2023-10-06 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 41.0267 | 30.9863 | منتظم | No
2100049615 | أمانة / الأحساء | تشييد | ذات اولوية عالية وعاجلة | 5269550 | 263477.5 | 1335324 | 1335324 | 2251029920 | لا | 0 |  | جاري | تكلفة العمل المنجز | 60 | 75 | 2019-09-01 | 2021-02-22 | 2022-11-03 | 2022-11-03 |  |  | التنسيق مع أصحاب المصلحه (خدمات |  | 50.2162 | 25.6445 | متأخر | No
2100068482 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 5403000.02 | 270150.001 | 661774 | 661774 | 2251027860 | لا | 0 | 190309005002 | مسحوب | تكلفة العمل المنجز | 16 | 95 | 2019-02-26 | 2021-02-15 | 2021-09-18 | 2021-09-18 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5881 | 25.3693 | مسحوب | No
2100012692 | جامعة حائل | تشييد | ذات اولوية عالية وعاجلة | 114689000 | 5734450 | 73749190.19 | 73749190.19 | 1010078607 | لا | 0 |  | جاري | تكلفة العمل المنجز | 66.73 | 92 | 2014-12-14 | 2017-11-28 | 2022-07-31 | 2022-07-31 |  |  | تأخرصرف المستحقات المالية |  | 41.7161 | 27.6606 | Failed | No
2100018992 | أمانة / الحدود الشمالية | تشييد | ذات اولوية متوسطة | 318010 | 15900.5 | 318010 | 318010 | 1010288150 | لا | 0 | 190509011563 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-08-28 | 2019-08-23 | 2020-06-01 | 2020-06-01 | 2019-08-23 |  | ضعف كفاءة المقاول الفنية |  | 41.0197 | 30.9884 | منجز | No
2100067045 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 20864710 | 1043235.5 | 18778635 | 18778635 | 1010099930 | لا | 0 | 181209402248 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2014-10-20 | 2017-03-30 | 2019-12-10 | 2019-12-10 | 2017-03-30 |  |  |  | 41.0529 | 30.97 | منجز | No
2100092433 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 1207170 | 60358.5 | 897257.32 | 897257.32 | 1010101655 | لا | 0 |  | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 90 | 100 | 2019-11-14 | 2020-11-21 | 2023-05-31 | 2023-05-31 |  |  | اخرى |  | 43.1346 | 29.8516 | متأخر | No
2100005353 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البرية | تشييد | ذات اولوية متوسطة | 5661925.5 | 283096.275 | 5661925.5 | 5661925.5 | 2511009902 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-06-18 | 2020-03-17 | 2022-03-31 | 2022-03-31 | 2020-03-17 |  | لا يوجد تأخير |  | 41.0661 | 30.9808 | منجز | No
2100066430 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 214240 | 10712 | 192819 | 192819 | 1010018550 | لا | 192819 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-12-20 | 2019-12-15 | 2019-12-10 | 2019-12-10 | 2019-12-15 |  |  |  | 44.7336 | 28.8931 | منجز | No
2100071982 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 261240 | 13062 | 0 | 0 | 2511100388 | لا | 0 |  | مسحوب | منهجية القيمة المكتسبة | 0 | 0 | 2019-02-10 | 2019-08-09 | 2021-12-01 | 2021-12-01 |  |  | ضعف كفاءة المقاول الفنية |  | 43.7424 | 28.7608 | مسحوب | No
2100057186 | الرئاسة العامة لهيئة الأمر بالمعروف والنهي عن المنكر | تشييد | ذات اولوية عالية | 13606491.03 | 680324.5515 | 6640106.28 | 6640106.28 | 1011011290 | لا | 0 | 181109297390 | جاري | الكميات التي تم تركيبها | 53 | 100 | 2015-03-07 | 2016-10-27 | 2022-11-30 | 2022-11-30 |  |  | تأخرصرف المستحقات المالية | تم إنذار المقاول كتابيا | 45.9801 | 28.3807 | Failed | No
2100101990 | وزارة الصحة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 4945300 | 247265 | 1002428 | 1002428 | 2050017521 | لا | 0 |  | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 95 | 100 | 2020-02-19 | 2020-08-18 | 2021-08-11 | 2021-08-11 |  |  | سوء التخطيط الاولي للمشروع |  | 44.7376 | 28.8922 | Failed | No
2100061946 | هيئة تطوير بوابة الدرعية | تشييد | ذات اولوية متوسطة | 1806000 | 90300 | 1444800 | 1444800 | 1010277656 | لا | 0 | 200501052623 | جاري | اخرى | 100 | 100 | 2020-02-20 | 2020-08-17 | 2021-12-31 | 2021-12-31 |  |  |  |  | 46.5878 | 24.7279 | منتظم | No
2100077851 | هيئة تطوير بوابة الدرعية | تشييد | ذات اولوية عالية | 117161661 | 5858083.05 | 23432332 | 23432332 | 1010046693 | لا | 0 | 200501059167 | جاري | اخرى | 28 | 30 | 2020-02-27 | 2021-08-26 | 2021-12-31 | 2021-12-31 |  |  |  |  | 46.5804 | 24.7266 | Failed | No
2100054423 | وزارة الداخلية / مديرية الأمن العام | تشييد | ذات اولوية متوسطة | 2311360.8 | 115568.04 | 2311360.8 | 2311360.8 | 1010250698 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-01-28 | 2021-01-28 | 2021-01-28 | 2021-01-28 | 2021-01-28 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 44.0697 | 28.5999 | منجز | No
2100030601 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 752500 | 37625 | 41709 | 0 | 1010166137 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-08-02 | 2015-01-29 | 2019-10-10 | 2019-10-10 | 2015-01-29 |  | ضعف كفاءة المقاول الفنية |  | 46.6885 | 24.7075 | منجز | Yes
2100071002 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 368716640.55 | 18435832.0275 | 124068535.21 | 74068535.21 | 1010015350 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 27 | 100 | 2014-02-18 | 2017-02-17 | 2018-03-15 | 2018-03-15 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6814 | 24.7082 | مسحوب | No
2100191660 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 29918000 | 1495900 | 29636465.9 | 26790109.1 | 1010227442 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99.06 | 100 | 2020-09-17 | 2022-03-18 | 2022-05-30 | 2022-05-30 | 2022-03-18 |  |  |  | 46.6146 | 24.8327 | منجز | No
2100101043 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 429485792.95 | 21474289.6475 | 164616103.5 | 114915329 | 1010271502 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 33 | 100 | 2014-06-04 | 2017-06-03 | 2019-08-17 | 2019-08-17 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6869 | 24.7069 | مسحوب | No
2100102535 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | دراسات هندسية | ذات اولوية عالية | 2980000 | 149000 | 1192000 | 1192000 | 2051011487 | لا | 0 | 200201134641 | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2020-04-26 | 2020-11-03 | 2020-12-25 | 2020-12-25 | 2020-11-03 |  | لا يوجد تأخير |  | 46.6939 | 24.7549 | منجز | No
2100070431 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 92929280.17 | 4646464.0085 | 83637639.35 | 83637639.35 | 1010066115 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-12-11 | 2020-01-31 | 2022-01-31 | 2022-01-31 | 2020-01-31 |  |  |  | 46.3067 | 24.5165 | منجز | No
2100069915 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 157689867.92 | 7884493.396 | 49878024 | 49878024 | 2060002548 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 36.98 | 100 | 2013-03-26 | 2015-08-16 | 2019-10-01 | 2019-10-01 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال | أخرى | 46.6953 | 26.3974 | مسحوب | No
2100065984 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 8494955 | 424747.75 | 804100 | 0 | 1010187076 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 18 | 100 | 2013-10-27 | 2016-12-26 | 2016-12-27 | 2016-12-27 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7143 | 24.7751 | مسحوب | Yes
2100012176 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3678495 | 183924.75 | 41792 | 0 | 1017000955 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 68 | 100 | 2015-04-09 | 2016-09-30 | 2019-07-30 | 2019-07-30 | 2016-09-30 |  | ضعف كفاءة المقاول الفنية |  | 46.6878 | 24.7169 | منجز | Yes
2100069366 | وزارة الدفاع / الإدارة الهندسية والاشغال بالخدمات الصحية | تشييد | ذات اولوية عالية | 11000000 | 550000 | 0 | 0 | 1010146750 | لا | 0 | 190301082734 | جاري | الكميات التي تم تركيبها | 50 | 50 | 2019-09-01 | 2022-07-30 | 2023-07-30 | 2023-07-30 |  |  |  |  | 46.6704 | 24.7019 | منتظم | No
2100200126 | وزارة الحرس الوطني / وكالة الشؤون الفنية | توريد وتركيب | ذات اولوية متوسطة | 90677.5 | 4533.875 | 90677.5 | 0 | 1010064600 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2021-10-24 | 2022-01-20 | 2022-01-20 | 2022-01-20 | 2022-01-20 |  |  |  | 46.6787 | 24.7025 | منجز | Yes
2100201924 | وزارة الصحة / عسير | ترميم | ذات اولوية متوسطة | 3480400 | 174020 | 3480400 | 3480400 | 5851007526 | لا | 0 | 200701171783 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-04-22 | 2021-01-13 | 2022-06-02 | 2022-06-02 | 2021-01-13 |  |  |  | 41.671 | 18.0042 | منجز | No
2100024301 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 45000000 | 2250000 | 42256 | 0 | 1010220868 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 82 | 2017-01-14 | 2020-01-14 | 2021-06-17 | 2021-06-17 | 2020-01-14 |  |  |  | 46.5413 | 24.7369 | منجز | Yes
2100054935 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 29371870 | 1468593.5 | 12781511.78 | 0 | 1010056094 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 55 | 100 | 2014-10-08 | 2016-01-01 | 2020-07-19 | 2020-07-19 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6747 | 24.7088 | مسحوب | Yes
2100044914 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 8706339 | 435316.95 | 7313834.76 | 0 | 1010171813 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 91.16 | 100 | 2014-02-19 | 2016-02-09 | 2019-12-04 | 2019-12-04 | 2016-02-09 |  | ضعف كفاءة المقاول الفنية |  | 46.2753 | 24.4663 | منجز | Yes
2100017813 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 5188271 | 259413.55 | 42072 | 0 | 1113001088 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 8 | 100 | 2015-07-26 | 2017-01-15 | 2017-01-16 | 2017-01-16 |  |  | ضعف كفاءة المقاول الفنية |  | 46.685 | 24.7157 | مسحوب | Yes
2100012261 | أمانة / الرياض | تشييد | ذات اولوية عالية | 1958450 | 97922.5 | 0 | 0 | 1010237336 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 44.02 | 100 | 2014-12-03 | 2018-05-08 | 2022-05-08 | 2022-05-08 |  |  | تأخرصرف المستحقات المالية |  | 44.4146 | 23.4775 | Failed | No
2100065822 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3120600 | 156030 | 41729 | 0 | 1010195827 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 100 | 2014-10-11 | 2016-04-03 | 2019-01-14 | 2019-01-14 | 2016-04-03 |  | ضعف كفاءة المقاول الفنية |  | 46.6745 | 24.7065 | منجز | Yes
2100027462 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2745424 | 137271.2 | 1964913.5 | 0 | 1116005202 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-04-12 | 2017-04-01 | 2020-03-17 | 2020-03-17 | 2017-04-01 |  | ضعف كفاءة المقاول الفنية |  | 46.6699 | 24.7157 | منجز | Yes
2100075051 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2466500 | 123325 | 41050 | 0 | 1010163813 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 0 | 100 | 2013-03-03 | 2018-02-05 | 2024-07-21 | 2024-07-21 |  |  | ضعف كفاءة المقاول الفنية |  | 45.5339 | 23.5352 | Failed | Yes
2100066043 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 394300 | 19715 | 0 | 0 | 1113000219 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 20 | 2019-09-29 | 2020-09-29 | 2020-09-30 | 2020-09-30 | 2020-09-29 |  | ضعف كفاءة المقاول الفنية |  | 45.1848 | 25.3464 | منجز | No
2100062613 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1274680 | 63734 | 1274680 | 0 | 1116007885 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-08-16 | 2015-11-08 | 2015-11-08 | 2015-11-08 | 2015-11-08 |  |  |  | 43.8191 | 25.0104 | منجز | Yes
2100190131 | مدينة الملك فهد الطبية | تشييد | ذات اولوية عالية | 4748533.3 | 237426.665 | 2943813 | 2943813 | 1010217074 | لا | 0 |  | جاري | تكلفة العمل المنجز | 98 | 100 | 2020-12-29 | 2021-12-29 | 2022-04-29 | 2022-04-29 |  |  |  |  | 46.7024 | 24.688 | Failed | No
2100095185 | شركة الكهرباء | تشييد | ذات اولوية متوسطة | 69645130 | 3482256.5 | 61635040 | 61635040 | 7001445233 | لا | 0 |  | جاري | تكلفة العمل المنجز | 97 | 100 | 2016-02-07 | 2020-02-13 | 2023-04-30 | 2023-04-30 |  |  | لا يوجد تأخير |  | 44.405 | 24.522 | منتظم | No
2100071396 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1118775 | 55938.75 | 0 | 0 | 1017000718 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2019-01-24 | 2020-03-24 | 2020-03-24 | 2020-03-24 | 2020-03-24 |  |  |  | 46.7683 | 24.7227 | منجز | No
2100012585 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 375200 | 18760 | 0 | 0 | 1010263223 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 53 | 2019-01-20 | 2019-11-16 | 2019-11-16 | 2019-11-16 | 2019-11-16 |  |  |  | 46.6768 | 24.7144 | منجز | No
2100026880 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1860940 | 93047 | 802315.8 | 0 | 1111001142 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 93 | 100 | 2013-04-22 | 2019-02-03 | 2019-02-03 | 2019-02-03 | 2019-02-03 |  |  |  | 46.6837 | 24.7157 | منجز | Yes
2100028766 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2595950 | 129797.5 | 1083700 | 0 | 1017000718 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-11-06 | 2016-04-29 | 2019-11-11 | 2019-11-11 | 2016-04-29 |  | ضعف كفاءة المقاول الفنية |  | 46.6768 | 24.7082 | منجز | Yes
2100057352 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 8216700 | 410835 | 624769.4 | 0 | 1185000614 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 23 | 100 | 2015-02-17 | 2017-02-06 | 2021-11-26 | 2021-11-26 |  |  | ضعف كفاءة المقاول الفنية |  | 44.8499 | 20.4465 | Failed | Yes
2100053115 | هيئة تطوير بوابة الدرعية | تشييد | ذات اولوية متوسطة | 74319204 | 3715960.2 | 66537191.61 | 66537191.61 | 1010079992 | لا | 0 | 200509052301 | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2019-08-18 | 2019-11-21 | 2020-11-21 | 2020-11-21 | 2019-11-21 |  |  |  | 46.5905 | 24.7364 | منجز | No
2100084700 | هيئة تطوير بوابة الدرعية | دراسة الجدوى | ذات اولوية عالية | 85276449 | 4263822.45 | 24985999.55 | 24985999.55 | 1010282788 | لا | 0 | 200601011945 | جاري | التكلفة المفوترة | 32 | 40 | 2020-02-25 | 2024-06-25 | 2024-06-25 | 2024-06-25 |  |  | لا يوجد تأخير |  | 46.553 | 24.7241 | خدمات عامة | No
2100030763 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 569750 | 28487.5 | 41895 | 0 | 1115001965 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 94.99 | 100 | 2015-01-21 | 2016-01-16 | 2019-10-07 | 2019-10-07 | 2016-01-16 |  | ضعف كفاءة المقاول الفنية |  | 46.674 | 24.7057 | منجز | Yes
2100081270 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1519000 | 75950 | 0 | 0 | 1017000955 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-01-29 | 2020-07-22 | 2022-10-30 | 2022-10-30 | 2020-07-22 |  |  |  | 46.7166 | 22.3069 | منجز | No
2100063442 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2463895 | 123194.75 | 2022884.2 | 0 | 1111000356 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2010-07-13 | 2019-07-07 | 2019-07-07 | 2019-07-07 | 2019-07-07 |  |  |  | 46.7273 | 22.2924 | منجز | Yes
2100074782 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1869325 | 93466.25 | 40987 | 0 | 1010165175 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2012-11-05 | 2013-12-30 | 2013-12-30 | 2013-12-30 | 2013-12-30 |  |  |  | 46.6773 | 24.6815 | منجز | Yes
2100100505 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 571200 | 28560 | 489540 | 0 | 1014000394 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-09-26 | 2019-09-21 | 2019-09-21 | 2019-09-21 | 2019-09-21 |  |  |  | 46.5095 | 23.6184 | منجز | Yes
2100075913 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3655465 | 182773.25 | 2665495 | 0 | 1015000676 | لا | 0 |  | جاري | تكلفة العمل المنجز | 85 | 100 | 2015-04-15 | 2019-03-24 | 2022-11-15 | 2022-11-15 |  |  |  |  | 46.6644 | 24.7169 | Failed | Yes
2100035641 | شركة الكهرباء | تشييد | ذات اولوية متوسطة | 20140700 | 1007035 | 10618859 | 10618859 | 4030171541 | لا | 0 |  | جاري | اخرى | 74.25 | 82.2 | 2015-10-15 | 2017-12-14 | 2023-09-30 | 2023-09-30 |  |  | اخرى |  | 47.3265 | 24.1545 | متأخر | No
2100002822 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 46077596.25 | 2303879.8125 | 42274539.78 | 42274539.78 | 1010168729 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 29 | 32 | 2019-01-24 | 2021-06-29 | 2021-06-30 | 2021-06-30 |  |  |  |  | 46.7408 | 24.7414 | Failed | No
2100031091 | أمانة / الرياض | تشييد | ذات اولوية عالية | 192849123.58 | 9642456.179 | 173525059.05 | 173525059.05 | 1010087370 | لا | 0 | 190201028578 | جاري | الكميات التي تم تركيبها | 18 | 24 | 2019-06-16 | 2022-04-18 | 2023-04-18 | 2023-04-18 |  |  | سوء التخطيط الاولي للمشروع |  | 46.6786 | 24.7082 | متأخر | No
2100107656 | دارة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 783505 | 39175.25 | 0 | 0 | 1010294266 | لا | 0 |  | ايقاف كلي | اخرى | 0 | 0 | 2020-12-13 | 2020-09-11 | 2020-09-11 | 2022-09-22 |  |  | تغيرات في نطاق المشروع |  | 46.682 | 24.6598 | Failed | No
2100195764 | الهيئة العامة للزكاة والدخل | تحديث وتوريد | ذات اولوية متوسطة | 499587.6 | 24979.38 | 499587.6 | 499587.6 | 1010174562 | لا | 0 |  | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2021-04-25 | 2021-05-04 | 2021-05-24 | 2021-05-24 |  | 2021-05-04 |  |  | 46.7136 | 24.656 | منجز | No
2100195860 | الهيئة العامة للزكاة والدخل | توريد وتركيب | ذات اولوية عالية | 185420 | 9271 | 185420 | 185420 | 1010174562 | لا | 0 |  | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2021-09-06 | 2021-09-16 | 2021-09-26 | 2021-09-26 |  | 2021-09-16 |  |  | 46.7137 | 24.6559 | منجز | No
2100006775 | وزارة الدفاع / الإدارة الهندسية والاشغال بقوات الدفاع الجوي | تشييد | ذات اولوية متوسطة | 35487514.36 | 1774375.718 | 35487514.36 | 35487514.36 | 1010195593 | لا | 0 | 180709036144 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-12-11 | 2017-07-28 | 2021-09-19 | 2021-09-19 | 2017-07-28 |  | أوامر سامية |  | 46.6928 | 24.7059 | منجز | No
2100032826 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1510374.4 | 75518.72 | 1098374.4 | 0 | 1010242510 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 99 | 100 | 2015-07-04 | 2018-11-10 | 2018-11-11 | 2018-11-11 | 2018-11-10 |  |  |  | 46.6775 | 24.705 | منجز | Yes
2100043691 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 79773911 | 3988695.55 | 0 | 0 | 1010010305 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 60 | 6 | 2019-04-24 | 2022-04-08 | 2024-07-25 | 2024-07-25 |  |  | ضعف كفاءة المقاول الفنية |  | 46.536 | 24.7375 | Failed | No
2100043750 | الهيئة العامة للطيران المدني | تشييد | ذات اولوية عالية | 47774594 | 2388729.7 | 18915534 | 18915534 | 2050022550 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 40 | 100 | 2015-01-03 | 2016-12-22 | 2016-12-22 | 2016-12-22 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 46.6759 | 24.7107 | مسحوب | No
2100063453 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2372750 | 118637.5 | 0 | 0 | 1010286604 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 30 | 100 | 2014-06-29 | 2015-09-22 | 2020-06-29 | 2020-06-29 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6589 | 24.7094 | مسحوب | No
2100030251 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2731100 | 136555 | 41730 | 0 | 1116002990 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 65 | 100 | 2014-10-12 | 2016-01-05 | 2020-01-22 | 2020-01-22 |  |  | تأخرصرف المستحقات المالية |  | 44.7736 | 23.7681 | Failed | Yes
2100017371 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4181160 | 209058 | 2433002.64 | 0 | 1111000356 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 82 | 100 | 2013-04-09 | 2014-07-03 | 2020-03-16 | 2020-03-16 | 2014-07-03 |  | ضعف كفاءة المقاول الفنية |  | 46.6905 | 24.7119 | منجز | Yes
2100026902 | أمانة / الرياض | تشييد | ذات اولوية عالية | 1589500 | 79475 | 0 | 0 | 1118001565 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 68 | 100 | 2014-07-20 | 2015-10-13 | 2020-05-30 | 2020-05-30 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.9081 | 23.8837 | مسحوب | No
2100100590 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 685965 | 34298.25 | 298694 | 298694 | 5951000762 | لا | 0 | 210501030518 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-06-16 | 2020-05-05 | 2021-07-06 | 2021-07-06 | 2020-05-05 |  | اخرى |  | 44.2405 | 17.5545 | منجز | No
2100189556 | الهيئة العامة للزكاة والدخل | ترميم | ذات اولوية متوسطة | 200684 | 10034.2 | 200684 | 200684 | 1010200847 | لا | 0 |  | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2020-12-27 | 2021-01-26 | 2020-12-27 | 2020-12-27 |  | 2021-01-26 |  |  | 46.7137 | 24.6559 | منجز | No
2100202985 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية وعاجلة | 41702778.72 | 2085138.936 | 33757144.61 | 0.01 | 2050007224 | لا | 0 | 191001137011 | جاري | منهجية القيمة المكتسبة | 94.1 | 78.9 | 2020-12-23 | 2022-12-02 | 2022-12-02 | 2022-12-02 |  |  |  |  | 41.6962 | 27.5194 | منتظم | No
2100046056 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 8994695 | 449734.75 | 41991 | 0 | 1010006004 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 7 | 100 | 2015-05-11 | 2017-04-30 | 2017-04-30 | 2017-04-30 |  |  | ضعف كفاءة المقاول الفنية |  | 45.368 | 25.9017 | مسحوب | Yes
2100047154 | أمانة / الرياض | تشييد | ذات اولوية عالية | 346806644.24 | 17340332.212 | 279807113.2 | 279807113.2 | 1010079853 | لا | 0 | 190701000904 | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-10-17 | 2023-05-19 | 2022-11-12 | 2022-11-12 |  |  |  |  | 46.6786 | 24.7094 | منتظم | No
2100057805 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1427200 | 71360 | 837800 | 0 | 1010101252 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 23 | 2019-02-23 | 2020-08-16 | 2021-06-20 | 2021-06-20 | 2020-08-16 |  |  |  | 47.1467 | 23.9759 | منجز | Yes
2100045301 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 6943903 | 347195.15 | 41377 | 0 | 1010242626 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 58 | 100 | 2014-01-05 | 2015-03-31 | 2019-03-20 | 2019-03-20 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6788 | 24.7013 | مسحوب | Yes
2100009774 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 991000 | 49550 | 42073 | 0 | 1010516124 | لا | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 1 | 2 | 2015-09-05 | 2016-08-20 | 2020-08-01 | 2020-08-01 |  |  | اخرى |  | 46.6846 | 24.7017 | Failed | Yes
2100022153 | هيئة تطوير بوابة الدرعية | تشييد | ذات اولوية متوسطة | 3474788 | 173739.4 | 3474788 | 3474788 | 1010126956 | لا | 0 | 200501053119 | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2019-08-21 | 2019-11-14 | 2019-11-14 | 2019-11-14 | 2019-11-14 |  |  |  | 46.574 | 24.7378 | منجز | No
2100031625 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1762601.243 | 88130.0622 | 41807 | 0 | 1010328499 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 99.83 | 100 | 2015-01-04 | 2016-03-29 | 2019-09-26 | 2019-09-26 | 2016-03-29 |  | ضعف كفاءة المقاول الفنية |  | 46.6994 | 24.7063 | منجز | Yes
2100030391 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4550104 | 227505.2 | 2730572.74 | 0 | 1114000037 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 86 | 100 | 2014-10-21 | 2016-04-13 | 2016-04-12 | 2016-04-12 | 2016-04-13 |  |  |  | 46.6988 | 24.7181 | منجز | Yes
2100028851 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2478480 | 123924 | 282953.9 | 0 | 1010249671 | لا | 0 |  | جاري | تكلفة العمل المنجز | 68 | 100 | 2015-01-14 | 2016-04-08 | 2019-09-18 | 2019-09-18 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6768 | 24.7157 | Failed | Yes
2100024360 | أمانة / الرياض | تشييد | ذات اولوية عالية | 2029112 | 101455.6 | 1454172 | 0 | 1010211585 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 90 | 100 | 2015-05-20 | 2016-08-22 | 2016-08-22 | 2016-08-22 | 2016-08-22 |  |  |  | 46.5123 | 23.6109 | منجز | Yes
2100041845 | وزارة الدفاع / الإدارة الهندسية والاشغال بقوات الدفاع الجوي | تشييد | ذات اولوية متوسطة | 14862886.5 | 743144.325 | 14862886.5 | 6896245.75 | 1010300402 | لا | 0 | 181201406182 | فسخ العقد | الكميات التي تم تركيبها | 47 | 100 | 2019-02-28 | 2022-04-12 | 2022-01-31 | 2022-01-31 |  |  | أوامر سامية | أخرى | 46.6814 | 24.7057 | مسحوب | No
2100032723 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 6999462 | 349973.1 | 41364 | 0 | 1118000832 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 38 | 100 | 2014-05-31 | 2015-08-24 | 2021-07-01 | 2021-07-01 |  |  | ضعف كفاءة المقاول الفنية |  | 42.9845 | 23.8714 | مسحوب | Yes
2100030494 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3940970 | 197048.5 | 765500 | 0 | 1010225108 | لا | 0 |  | جاري | تكلفة العمل المنجز | 75.91 | 3 | 2019-05-28 | 2022-05-12 | 2024-03-30 | 2024-03-30 |  |  |  |  | 46.685 | 24.7094 | متأخر | Yes
2100044030 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2507275 | 125363.75 | 2344316 | 0 | 1010164501 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 98 | 100 | 2013-09-15 | 2014-11-09 | 2019-08-24 | 2019-08-24 | 2014-11-09 |  | ضعف كفاءة المقاول الفنية |  | 46.6823 | 24.7032 | منجز | Yes
2100044881 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 27936942 | 1396847.1 | 17691013.04 | 0 | 1113000219 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 96.87 | 100 | 2014-08-02 | 2016-07-22 | 2020-04-05 | 2020-04-05 | 2016-07-22 |  | ضعف كفاءة المقاول الفنية |  | 45.1749 | 25.4011 | منجز | Yes
2100005084 | الهيئة الملكية لمدينة الرياض | تشييد | ذات اولوية عالية | 93514920.57 | 4675746.0285 | 93514920.57 | 93514920.57 | 1010307848 | لا | 0 | 190209006246 | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2016-08-04 | 2018-11-08 | 2020-08-31 | 2020-08-31 | 2018-11-08 |  | لا يوجد تأخير |  | 46.7139 | 24.6288 | منجز | No
2100063210 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3636298 | 181814.9 | 3480185 | 0 | 1014000081 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 96 | 100 | 2015-02-18 | 2018-07-08 | 2018-07-07 | 2018-07-07 | 2018-07-08 |  |  |  | 46.6727 | 24.7269 | منجز | Yes
2100044461 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4397195 | 219859.75 | 3261566.58 | 0 | 1114000037 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 93 | 100 | 2011-07-26 | 2012-11-17 | 2019-09-19 | 2019-09-19 | 2012-11-17 |  | ضعف كفاءة المقاول الفنية |  | 46.6912 | 24.7088 | منجز | Yes
2100046196 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1402380 | 70119 | 0 | 0 | 1010446037 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 3 | 20 | 2019-02-06 | 2021-01-26 | 2021-01-29 | 2021-01-29 |  |  | ضعف كفاءة المقاول الفنية |  | 45.3536 | 26.4945 | مسحوب | No
2100047003 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 31733688.5 | 1586684.425 | 17896862.879 | 0 | 1010177200 | لا | 0 |  | جاري | تكلفة العمل المنجز | 86 | 100 | 2014-08-03 | 2016-07-23 | 2020-06-27 | 2020-06-27 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6603 | 24.7094 | Failed | Yes
2100064175 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 11648700 | 582435 | 8010510.2902 | 0 | 1010010466 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 98 | 100 | 2014-01-04 | 2018-08-08 | 2018-08-08 | 2018-08-08 | 2018-08-08 |  |  |  | 45.2633 | 24.0374 | منجز | Yes
2100083705 | هيئة تطوير بوابة الدرعية | تشييد | ذات اولوية عالية | 5907530 | 295376.5 | 5907530 | 5907530 | 1010008375 | لا | 0 | 200509087881 | جاري | اخرى | 100 | 100 | 2020-01-13 | 2021-12-04 | 2021-07-23 | 2021-07-23 |  |  |  |  | 46.575 | 24.7373 | متأخر | No
2100075062 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1560526 | 78026.3 | 0 | 0 | 1010182773 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 16 | 100 | 2014-10-18 | 2016-01-11 | 2019-05-13 | 2019-05-13 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6802 | 24.7007 | مسحوب | No
2100081701 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2267500 | 113375 | 42150 | 0 | 5950015390 | لا | 0 |  | جاري | تكلفة العمل المنجز | 85 | 100 | 2015-08-24 | 2016-08-18 | 2019-07-17 | 2019-07-17 |  |  | تأخرصرف المستحقات المالية |  | 46.6727 | 24.7206 | Failed | Yes
2100076020 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4413400 | 220670 | 4134941.816 | 0 | 4650022377 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 94 | 100 | 2013-12-10 | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 |  |  |  | 43.2737 | 24.3496 | منجز | Yes
2100071385 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 7404000 | 370200 | 41729 | 0 | 1010187076 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 15 | 100 | 2014-09-20 | 2017-01-10 | 2017-01-11 | 2017-01-11 |  |  | ضعف كفاءة المقاول الفنية |  | 45.3845 | 26.4853 | مسحوب | Yes
2100031010 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3280250 | 164012.5 | 0 | 0 | 4030065096 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 1 | 100 | 2014-03-16 | 2018-09-08 | 2018-01-01 | 2018-01-01 |  |  | ضعف كفاءة المقاول الفنية |  | 47.3269 | 24.1353 | مسحوب | No
2100013845 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 365006.25 | 18250.3125 | 0 | 0 | 1011018983 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 94.76 | 46 | 2019-01-17 | 2020-01-12 | 2020-01-12 | 2020-01-12 | 2020-01-12 |  | ضعف كفاءة المقاول الفنية |  | 46.6727 | 24.7157 | منجز | No
2100075493 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1152782 | 57639.1 | 793102 | 0 | 1015000676 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 95.74 | 100 | 2014-12-18 | 2019-03-25 | 2019-03-24 | 2019-03-24 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6644 | 24.7181 | مسحوب | Yes
2100051026 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 10375679 | 518783.95 | 10375679 | 0 | 1117001926 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 100 | 2014-10-19 | 2016-10-08 | 2020-07-31 | 2020-07-31 | 2016-10-08 |  |  |  | 46.672 | 24.705 | منجز | Yes
2100017861 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1852503.996 | 92625.1998 | 1621386.7747 | 0 | 1114000037 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2013-08-19 | 2014-11-12 | 2016-04-18 | 2016-04-18 | 2014-11-12 |  |  |  | 46.6809 | 24.7244 | منجز | Yes
2100062053 | وزارة الداخلية / مديرية الأمن العام | تشييد | ذات اولوية متوسطة | 2094697.5 | 104734.875 | 2094697.5 | 2094697.5 | 1010070662 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-10-20 | 2020-10-21 | 2021-01-21 | 2021-01-21 | 2020-10-21 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 46.3658 | 25.0765 | منجز | No
2100190503 | وزارة الاعلام | توريد وتركيب | ذات اولوية عالية وعاجلة | 14940714 | 747035.7 | 13717383 | 13717383 | 4030025664 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 90 | 100 | 2017-06-04 | 2018-04-24 | 2018-04-24 | 2018-04-24 |  | 2018-04-24 |  |  | 42.9675 | 16.5279 | منجز | No
2100065870 | أمانة / الرياض | تشييد | ذات اولوية عالية | 98889366 | 4944468.3 | 18434214.01 | 18434214.01 | 1010044185 | لا | 0 | 190509114660 | جاري | الكميات التي تم تركيبها | 27 | 27 | 2019-06-04 | 2021-08-09 | 2021-08-10 | 2021-08-10 |  |  |  |  | 46.6814 | 24.7107 | Failed | No
2100075736 | أمانة / الرياض | تشييد | ذات اولوية عالية | 148731811.5 | 7436590.575 | 131713807.14 | 131713807.14 | 1010171813 | لا | 0 | 181001144244 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-08-02 | 2021-09-07 | 2021-09-08 | 2021-09-08 | 2021-09-07 |  |  |  | 46.68 | 24.7119 | منجز | No
2100047902 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 5914000 | 295700 | 5618299.45 | 0 | 1113000219 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2013-11-07 | 2015-05-01 | 2020-08-21 | 2020-08-21 | 2015-05-01 |  | ضعف كفاءة المقاول الفنية |  | 46.6727 | 24.7044 | منجز | Yes
2100033762 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 766285 | 38314.25 | 727970.745 | 0 | 1010154882 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 100 | 2013-01-13 | 2018-01-17 | 2018-01-17 | 2018-01-17 | 2018-01-17 |  |  |  | 46.6718 | 24.7377 | منجز | Yes
2100032255 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1055050 | 52752.5 | 293537.5 | 0 | 1126000984 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 96.62 | 33 | 2019-02-14 | 2021-05-09 | 2020-05-09 | 2020-05-09 | 2021-05-09 |  |  |  | 46.6795 | 24.7119 | منجز | Yes
2100080743 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1877520 | 93876 | 306000 | 0 | 1126105845 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 67 | 2019-01-19 | 2020-04-13 | 2019-11-18 | 2019-11-18 | 2020-04-13 |  | ضعف كفاءة المقاول الفنية |  | 46.0969 | 25.1161 | منجز | Yes
2100196022 | الهيئة العامة للزكاة والدخل | ترميم | ذات اولوية متوسطة | 200684 | 10034.2 | 200684 | 200684 | 1010200847 | لا | 0 |  | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2020-12-27 | 2021-01-24 | 2021-01-28 | 2021-01-28 |  | 2021-01-24 |  |  | 46.7137 | 24.6559 | منجز | No
2100081771 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 1922100 | 96105 | 2658.95 | 2658.95 | 5950021938 | لا | 0 | 221009014884 | ايقاف كلي | تكلفة العمل المنجز | 32 | 100 | 2019-04-14 | 2019-12-08 | 2022-09-11 | 2022-09-11 |  |  | ضعف كفاءة المقاول الفنية |  | 44.2377 | 17.6055 | Failed | No
2100005655 | أمانة / الرياض | دراسات هندسية | ذات اولوية متوسطة | 2950000 | 147500 | 2950000 | 2632714.37 | 1010463299 | لا | 0 | 180801057287 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-04-27 | 2018-10-27 | 2018-11-27 | 2018-11-27 | 2018-10-27 |  | اخرى |  | 46.6704 | 24.7052 | منجز | No
2100109981 | مدينة الملك فهد الطبية | تشييد | ذات اولوية عالية | 8868296 | 443414.8 | 178275 | 178275 | 1010194970 | لا | 0 |  | جاري | تكلفة العمل المنجز | 20 | 25 | 2020-01-30 | 2022-01-11 | 2024-05-01 | 2024-05-01 |  |  |  |  | 46.702 | 24.686 | منتظم | No
2100078282 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 582055215.1 | 29102760.755 | 570981860.79 | 570981860.79 | 1010057263 | لا | 0 | 180809058542 | جاري | منهجية القيمة المكتسبة | 96 | 100 | 2017-06-14 | 2020-06-10 | 2024-05-30 | 2024-05-30 |  |  | أوامر تغيير |  | 49.5648 | 27.1019 | متأخر | No
2100007184 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 122736368 | 6136818.4 | 98189094.4 | 88696637.63 | 2050005846 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2016-12-11 | 2019-05-17 | 2021-08-23 | 2021-08-23 | 2019-05-17 |  | لا يوجد تأخير |  | 39.7969 | 21.3471 | منجز | No
2100022212 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 44851135 | 2242556.75 | 25026829 | 25026829 | 1010305951 | لا | 0 | 181209546844 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 99.75 | 100 | 2014-08-03 | 2016-08-02 | 2023-01-26 | 2023-01-26 | 2016-08-02 |  | أوامر تغيير |  | 38.183 | 24.0151 | Failed | No
2100070770 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تصميم | ذات اولوية عالية وعاجلة | 41655665 | 2082783.25 | 40717914 | 40717914 | 4700018041 | لا | 0 | 180709030517 | جاري | اخرى | 98.29 | 100 | 2014-03-17 | 2019-03-16 | 2022-12-30 | 2022-12-30 |  |  |  |  | 38.1957 | 24.0189 | منتظم | No
2100018815 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية وعاجلة | 4360345 | 218017.25 | 4360345 | 4360345 | 5808011381 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 81.5 | 100 | 2014-12-06 | 2016-11-14 | 2020-08-20 | 2020-08-20 | 2016-11-14 |  | ضعف كفاءة المقاول الفنية |  | 41.2855 | 20.1136 | منجز | No
2100007206 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2343443.94 | 117172.197 | 1346329 | 1346329 | 3350020093 | لا | 0 |  | مسحوب | التكلفة المفوترة | 55 | 100 | 2010-06-25 | 2011-08-19 | 2020-11-18 | 2020-11-18 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | مسحوب | No
2100005832 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 3098889.4 | 154944.47 | 0 | 0 | 3350013522 | لا | 0 |  | جاري | التكلفة المفوترة | 20 | 100 | 2018-03-27 | 2019-05-21 | 2022-10-31 | 2022-10-31 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | Failed | No
2100021501 | وزارة الداخلية / المديرية العامة للدفاع المدني | تشييد | ذات اولوية عالية | 2022823.76 | 101141.188 | 2022823.76 | 2022823.76 | 1131046150 | لا | 0 | 200201039016 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-11-21 | 2020-11-09 | 2022-11-01 | 2022-11-01 | 2020-11-09 |  | تأخرصرف المستحقات المالية |  | 43.7414 | 25.9714 | منجز | No
2100194106 | أمانة / جدة | توريد وتركيب | ذات اولوية متوسطة | 315000 | 15750 | 315000 | 315000 | 4030156456 | لا | 0 | 200609050418 | منجز – استلام نهائي | تكلفة العمل المنجز | 90 | 95 | 2019-12-18 | 2020-12-06 | 2020-12-06 | 2020-12-06 | 2020-12-06 | 2020-12-07 |  |  | 40.8611 | 20.4184 | منجز | No
2100207981 | الهيئة العامة للطيران المدني | إشراف | ذات اولوية عالية | 20070519.04 | 1003525.952 | 17024904.55 | 16534257.05 | 4030276223 | لا | 0 | 190409031139 | جاري | تكلفة العمل المنجز | 94.85 | 100 | 2017-10-01 | 2021-09-30 | 2021-12-30 | 2021-12-30 |  |  |  |  | 46.7144 | 24.927 | خدمات عامة | No
2100087345 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية وعاجلة | 39113184.82 | 1955659.241 | 35183299.54 | 35183299.54 | 2050052043 | لا | 0 | 180809044325 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2016-04-26 | 2019-03-26 | 2020-12-15 | 2020-12-15 | 2019-03-26 |  | لا يوجد تأخير |  | 49.5957 | 25.3069 | منجز | No
2100019983 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 13835000 | 691750 | 11859135.02 | 11859135.02 | 2050060197 | لا | 0 | 200501006010 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-05-04 | 2022-05-05 | 2022-05-05 | 2022-05-05 | 2022-05-05 |  | لا يوجد تأخير |  | 50.1121 | 26.4267 | منجز | No
2100061283 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية وعاجلة | 3547420 | 177371 | 1784009.08 | 1784009.08 | 2251027822 | لا | 0 | 200101051360 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 91.32 | 100 | 2019-03-27 | 2020-03-27 | 2021-09-19 | 2021-09-19 | 2020-03-27 |  | لا يوجد تأخير |  | 49.5506 | 25.4256 | منجز | No
2100001702 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 16767450 | 838372.5 | 14754191.86 | 12954279.16 | 1010275506 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 88.52 | 100 | 2019-04-18 | 2020-04-18 | 2020-06-10 | 2020-06-10 |  | 2020-04-18 | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100069193 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 8857574.4 | 442878.72 | 8857574.3 | 7506158.12 | 1126000984 | لا | 0 | 1126000984 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-08-05 | 2020-07-25 | 2021-02-24 | 2021-02-24 | 2020-07-25 |  | ضعف كفاءة المقاول الفنية |  | 45.3525 | 25.8912 | منجز | No
2100041834 | الرئاسة العامة لهيئة الأمر بالمعروف والنهي عن المنكر | تشييد | ذات اولوية متوسطة | 9538975 | 476948.75 | 724635.1 | 724635.1 | 1010180774 | نعم | 2895385.22 | 180501008138 | مسحوب | الكميات التي تم تركيبها | 44 | 100 | 2018-08-29 | 2019-11-22 | 2022-12-31 | 2022-12-31 |  |  | تأخرصرف المستحقات المالية | مخطط لسحبه وإعادة ترسيته | 50.2059 | 26.2069 | مسحوب | No
2100106993 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 7680495 | 384024.75 | 1870240 | 1870240 | 5855014881 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 26 | 100 | 2015-03-26 | 2017-03-09 | 2023-02-02 | 2023-02-02 |  |  | ضعف كفاءة المقاول الفنية |  | 42.4987 | 18.2178 | مسحوب | No
2100018443 | أمانة / جدة | دراسات هندسية | ذات اولوية متوسطة | 1620885 | 81044.25 | 1663337 | 1663337 | 4030257071 | لا | 0 | 200201067246 | منجز – استلام نهائي | اخرى | 90 | 90 | 2020-02-05 | 2020-10-28 | 2020-10-28 | 2020-10-28 | 2020-10-28 | 2020-10-29 | اخرى |  | 39.1715 | 21.5049 | منجز | No
2100099116 | أمانة / عسير | دراسات هندسية | ذات اولوية عالية | 3322800 | 166140 | 800577 | 800577 | 5855065029 | لا | 0 |  | جاري | تكلفة العمل المنجز | 64 | 72 | 2019-06-12 | 2022-05-27 | 2023-03-31 | 2023-03-31 |  |  | التنسيق مع أصحاب المصلحه (خدمات |  |  |  | خدمات عامة | No
2100009564 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 511618047.72 | 25580902.386 | 213267929.87 | 213267929.87 | 2051020158 | لا | 0 | 180709034267 | جاري | منهجية القيمة المكتسبة | 52 | 100 | 2014-04-16 | 2018-04-11 | 2024-11-16 | 2024-11-16 |  |  | ضعف كفاءة المقاول الفنية |  | 49.6626 | 27.0037 | Failed | No
2100104930 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 373269560.25 | 18663478.0125 | 94546565.69 | 94546565.69 | 1010053925 | لا | 0 | 181201447981 | جاري | منهجية القيمة المكتسبة | 27 | 65 | 2019-03-05 | 2022-03-01 | 2025-01-09 | 2025-01-09 |  |  | ضعف كفاءة المقاول الفنية |  | 49.6626 | 27.0037 | Failed | No
2100089611 | جامعة الملك فيصل | تشييد | ذات اولوية عالية وعاجلة | 999495 | 49974.75 | 999495 | 999495 | 4030032844 | لا | 0 | 181109372054 | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2017-04-25 | 2018-04-17 | 2018-03-18 | 2018-03-18 |  | 2018-04-17 | تأخرصرف المستحقات المالية |  | 49.5604 | 25.3897 | منجز | No
2100104565 | جامعة الملك فيصل | تشييد | ذات اولوية متوسطة | 799750 | 39987.5 | 799750 | 799750 | 2251006858 | لا | 0 | 180809054453 | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2018-11-28 | 2018-06-02 | 2018-06-02 | 2018-06-02 |  | 2018-06-02 | تأخرصرف المستحقات المالية |  | 49.5604 | 25.3897 | منجز | No
2100079586 | جامعة الملك فيصل | تشييد | ذات اولوية عالية | 233969187.19 | 11698459.3595 | 127322825.68 | 127322825.68 | 1010135922 | لا | 0 | 180909099629 | جاري | تكلفة العمل المنجز | 71 | 71 | 2015-06-27 | 2016-09-17 | 2022-06-17 | 2022-06-17 |  |  | تأخرصرف المستحقات المالية |  | 49.5604 | 25.3897 | Failed | No
2100070114 | وزارة النقل والخدمات اللوجستية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية | 148888252.6 | 7444412.63 | 133999427.31 | 133999427.31 | 1010090968 | لا | 0 | 200409059217 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-11-13 | 2017-04-16 | 2022-07-04 | 2022-07-04 | 2017-04-16 |  |  |  | 39.6481 | 24.579 | منجز | No
2100011115 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية | 81982295.35 | 4099114.7675 | 25119051.52 | 25119051.52 | 2051003203 | لا | 0 | 180709021977 | مسحوب | تكلفة العمل المنجز | 50 | 100 | 2014-03-27 | 2016-09-12 | 2026-12-31 | 2026-12-31 |  |  | تأخرصرف المستحقات المالية |  | 50.1037 | 26.4265 | مسحوب | No
2100097786 | وزارة الثقافة | تشييد |  | 4561812 | 228090.6 | 912362.4 | 912362.4 | 2051035552 |  | 0 |  | جاري | منهجية القيمة المكتسبة | 99 | 100 | 2019-04-22 00:59 | 2019-11-21 00:59 | 2019-11-21 | 2019-11-21 |  |  | موافقات |  |  |  | Failed | No
2100003673 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 8029829 | 401491.45 | 8029829.12 | 0 | 1010191039 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-12-14 | 2018-03-20 | 2019-01-17 | 2019-01-17 | 2018-03-20 |  | اخرى |  | 41.6968 | 27.506 | منجز | Yes
2100105921 | وزارة الثقافة | تشييد |  | 5728700 | 286435 | 4296525 | 4296525 | 2051035552 |  | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-04-24 00:59 | 2020-06-23 00:59 | 2020-06-23 | 2020-06-23 | 2020-06-23 00:59 |  | موافقات |  |  |  | منجز | No
2100097565 | وزارة الثقافة | تشييد |  | 4630500 | 231525 | 3218197.5 | 3218197.5 | 1010156756 |  | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-02-24 00:59 | 2020-04-23 00:59 | 2020-04-23 | 2020-04-23 | 2020-04-23 00:59 |  | موافقات |  |  |  | منجز | No
2100089040 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 3112995.6 | 155649.78 | 396040 | 396040 | 1010233819 | لا | 0 |  | مسحوب | التكلفة المفوترة | 17 | 100 | 2015-12-24 | 2016-12-18 | 2023-06-30 | 2023-06-30 |  |  | ضعف كفاءة المقاول الفنية |  | 40.0549 | 29.8587 | مسحوب | No
2100087161 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية وعاجلة | 52371596.85 | 2618579.8425 | 41445461.56 | 41445461.56 | 1010144696 | لا | 0 | 180809055515 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2011-11-19 | 2013-10-28 | 2021-03-03 | 2021-03-03 | 2013-10-28 |  | لا يوجد تأخير |  | 42.6335 | 17.155 | منجز | No
2100003006 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 24504052.27 | 1225202.6135 | 24469237.77 | 0 | 1010060469 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-04-19 | 2017-10-05 | 2019-09-19 | 2019-09-19 | 2017-10-05 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.6509 | 17.1567 | منجز | Yes
2100002122 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 10398662.01 | 519933.1005 | 0 | 0 | 1010233305 | لا | 0 |  | ايقاف كلي | التكلفة المفوترة | 0 | 100 | 2017-01-29 | 2019-01-19 | 2023-02-02 | 2023-02-02 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | Failed | No
2100010732 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 10971882.72 | 548594.136 | 0 | 0 | 4030052981 | لا | 0 |  | ايقاف كلي | التكلفة المفوترة | 0 | 100 | 2015-11-22 | 2017-11-11 | 2023-02-01 | 2023-02-01 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | Failed | No
2100007814 | وزارة التعليم | تشييد | ذات اولوية عالية | 8361916.2 | 418095.81 | 1097100.68 | 0 | 1010223860 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 16 | 100 | 2013-09-01 | 2015-05-24 | 2023-05-04 | 2023-05-04 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.6509 | 17.1567 | مسحوب | Yes
2100058564 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 6612022 | 330601.1 | 0 | 0 | 1010051817 | لا | 0 |  | ايقاف كلي | التكلفة المفوترة | 0 | 100 | 2015-05-07 | 2017-02-17 | 2023-09-06 | 2023-09-06 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.5429 | 16.8808 | Failed | No
2100022945 | وزارة الرياضة | تشييد | ذات اولوية عالية | 60092740 | 3004637 | 27440134 | 27440134 | 1010015350 | نعم | 371973.64 | 180909080522 | مسحوب | الكميات التي تم تركيبها | 77 | 100 | 2012-09-11 | 2015-02-12 | 2021-07-01 | 2021-07-01 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | مسحوب | No
2100079041 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | لم تعد تحتاجها الجهة | 46222060 | 2311103 | 29982783.12 | 29982783.12 | 4650052854 | لا | 0 | 181009164121 | مسحوب | منهجية القيمة المكتسبة | 70.5 | 100 | 2012-06-18 | 2015-05-17 | 2023-10-21 | 2023-10-21 |  |  | ضعف كفاءة المقاول الفنية |  | 38.1279 | 24.4698 | مسحوب | No
2100086203 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1957227 | 97861.35 | 612298 | 0 | 4030123131 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 40 | 100 | 2008-02-12 | 2009-08-06 | 2023-06-15 | 2023-06-15 |  |  | ضعف كفاءة المقاول الفنية |  | 38.0623 | 24.0861 | مسحوب | Yes
2100004896 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 7516395.8 | 375819.79 | 7125294 | 6611613 | 4031033277 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-03-07 | 2017-02-25 | 2019-03-04 | 2019-03-04 | 2017-02-25 |  |  |  | 39.6005 | 24.4595 | منجز | No
2100079111 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 13405455.73 | 670272.7865 | 3000000 | 0 | 4030065868 | لا | 0 |  | مسحوب | التكلفة المفوترة | 60 | 100 | 2010-10-08 | 2012-09-28 | 2023-01-15 | 2023-01-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | Yes
2100023446 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1484800 | 74240 | 0 | 0 | 4650003547 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 1 | 100 | 2006-03-05 | 2007-04-12 | 2020-01-01 | 2020-01-01 |  |  | ضعف كفاءة المقاول الفنية |  | 38.0623 | 24.0861 | مسحوب | No
2100005261 | وزارة التعليم | تشييد | ذات اولوية عالية | 10435739 | 521786.95 | 8258857.27 | 7554050.66 | 4650013348 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2016-05-16 | 2018-05-07 | 2020-06-24 | 2020-06-24 | 2018-05-07 |  |  |  | 39.6005 | 24.4595 | منجز | No
2100011211 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية وعاجلة | 15490618 | 774530.9 | 10369875 | 10369875 | 4650003255 | لا | 0 | 181009158287 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 87.24 | 90 | 2013-01-13 | 2014-12-23 | 2021-04-14 | 2021-04-14 | 2014-12-23 |  | لا يوجد تأخير |  | 39.9057 | 24.63 | منجز | No
2100080172 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية وعاجلة | 16958350 | 847917.5 | 6737737.9 | 6737737.9 | 1010149483 | لا | 0 | 180809064653 | جاري | منهجية القيمة المكتسبة | 77.1 | 100 | 2017-12-19 | 2020-11-16 | 2023-03-31 | 2023-03-31 |  |  | اخرى |  | 39.587 | 24.5078 | متأخر | No
2100016542 | وزارة التعليم | تشييد | ذات اولوية عالية | 11624287 | 581214.35 | 10730802.07 | 10730802 | 1010060469 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-12-06 | 2017-11-26 | 2019-03-18 | 2019-03-18 | 2017-11-26 |  |  |  | 39.6005 | 24.4595 | منجز | No
2100028372 | وزارة الداخلية / المديرية العامة للدفاع المدني | تشييد | ذات اولوية عالية | 8352847.49 | 417642.3745 | 8352847.49 | 8352847.49 | 1010174451 | لا | 0 | 180901091607 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-01-09 | 2020-11-18 | 2022-07-01 | 2022-07-01 | 2020-11-18 |  | تأخرصرف المستحقات المالية |  | 50.0279 | 26.3811 | منجز | No
2100098195 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 9067915 | 453395.75 | 3284235 | 3284235 | 4031056107 | لا | 0 | 191001081390 | ايقاف جزئي | التكلفة المفوترة | 80 | 100 | 2019-02-17 | 2019-08-16 | 2022-05-04 | 2022-05-04 |  |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | Failed | No
2100059625 | جامعة الملك عبدالعزيز | تشييد | لم تعد تحتاجها الجهة | 29534370.65 | 1476718.5325 | 1693558.67 | 1693558.67 | 1010251358 | لا | 0 | 181101270010 | فسخ العقد | تكلفة العمل المنجز | 0 | 0 | 2018-05-13 | 2019-03-03 | 2021-12-31 | 2021-12-31 |  |  | أوامر سامية |  | 39.1677 | 21.5008 | مسحوب | No
2100021162 | جامعة الملك عبدالعزيز | تشييد | لم تعد تحتاجها الجهة | 23081158.98 | 1154057.949 | 1084282.17 | 1084282.17 | 1010251358 | لا | 0 | 181109315563 | فسخ العقد | تكلفة العمل المنجز | 0 | 0 | 2018-12-03 | 2019-09-24 | 2021-12-31 | 2021-12-31 |  |  | أوامر سامية |  | 39.1677 | 21.5008 | مسحوب | No
2100026106 | وزارة التعليم | تشييد | ذات اولوية عالية | 21761044 | 1088052.2 | 12103178 | 6814918.09 | 1010181431 | لا | 0 | 191009081433 | منجز – استلام ابتدائي | التكلفة المفوترة | 89 | 70 | 2015-08-02 | 2017-10-20 | 2022-08-10 | 2022-08-10 | 2017-10-20 |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | منجز | No
2100043094 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 17073941.51 | 853697.0755 | 11149672.68 | 8297160.7 | 1010078642 | لا | 0 | 190709086821 | جاري | تكلفة العمل المنجز | 90 | 100 | 2018-12-02 | 2019-11-21 | 2022-06-30 | 2022-06-30 |  |  | تأخرصرف المستحقات المالية |  | 39.1677 | 21.5008 | Failed | No
2100056571 | أمانة / جدة | تصميم وإشراف | ذات اولوية عالية | 4920000 | 246000 | 5165024 | 5165024 | 4030263764 | لا | 0 | 190509009115 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 98 | 98 | 2019-02-17 | 2021-02-16 | 2021-02-16 | 2021-02-16 | 2021-02-16 |  | اخرى |  |  |  | منجز | No
2100007033 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 11413519.55 | 570675.9775 | 0.02 | 0.02 | 4030173446 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 16 | 16 | 2013-09-24 | 2015-09-14 | 2020-06-06 | 2020-06-06 |  |  | ضعف كفاءة المقاول الفنية |  | 39.836 | 21.4408 | مسحوب | No
2100070206 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية متوسطة | 865527.82 | 43276.391 | 597882.6 | 597882.6 | 1010175017 | لا | 0 | 190809084401 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2017-11-30 | 2018-03-27 | 2019-05-01 | 2019-05-01 | 2018-03-27 | [5 empty] | منجز | No
2100190050 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية عالية وعاجلة | 1099021.02 | 54951.051 | 64228.5 | 64228.5 | 5857527510 | لا | 0 | 190301083473 | مسحوب | الكميات التي تم تركيبها | 85 | 100 | 2020-01-03 | 2021-10-19 | 2021-10-19 | 2021-10-19 |  |  | ضعف كفاءة المقاول الفنية |  | 42.0593 | 18.5534 | مسحوب | No
2100190013 | وزارة البيئة والمياة والزراعة | تحديث وتوريد | ذات اولوية متوسطة | 336202.6 | 16810.13 | 80860.5 | 80860.5 | 5801011161 | لا | 0 | 190301070502 | جاري | الكميات التي تم تركيبها | 98 | 100 | 2019-05-13 | 2019-11-04 | 2021-08-20 | 2021-08-20 |  |  | ضعف كفاءة المقاول الفنية |  | 41.5768 | 19.8666 | Failed | No
2100089622 | الهيئة الملكية لمدينة مكة المكرمة و المشاعر المقدسة | تشييد | ذات اولوية عالية | 19250400 | 962520 | 17098200 | 6009700 | 4031046580 | لا | 0 | 200101045372 | جاري | الكميات التي تم تركيبها | 100 | 100 | 2019-10-23 | 2020-01-21 | 2020-07-16 | 2020-07-16 |  |  | تأخرصرف المستحقات المالية |  | 39.93 | 21.3782 | Failed | No
2100016376 | جامعة الملك فيصل | تشييد | ذات اولوية متوسطة | 470000 | 23500 | 282000 | 282000 | 2251042063 | لا | 0 | 181109353037 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-06-11 | 2015-08-08 | 2015-08-08 | 2015-08-08 | 2015-08-08 |  | تأخرصرف المستحقات المالية |  | 49.5604 | 25.3897 | منجز | No
2100003835 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 4311489.7 | 215574.485 | 2125640.87 | 2125640.87 | 1010153471 | لا | 0 |  | مسحوب | التكلفة المفوترة | 56 | 100 | 2015-03-22 | 2016-10-12 | 2017-09-27 | 2017-09-27 |  |  | ضعف كفاءة المقاول الفنية |  | 45.975 | 28.4334 | مسحوب | No
2100059754 | جامعة الطائف | تشييد | ذات اولوية متوسطة | 114248416.95 | 5712420.8475 | 102823350.26 | 92162083.66 | 4030154193 | لا | 0 | 180809037667 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2013-07-07 | 2016-06-05 | 2022-03-16 | 2022-03-16 | 2016-06-05 |  | تأخرصرف المستحقات المالية |  | 40.4511 | 21.2747 | منجز | No
2100044450 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 5364233.84 | 268211.692 | 4576476 | 4576476 | 5950012645 | لا | 0 | 181209477572 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 89 | 100 | 2019-06-12 | 2020-06-12 | 2020-06-12 | 2020-06-12 | 2020-06-12 |  | ضعف كفاءة المقاول الفنية |  | 44.25 | 17.5653 | منجز | No
2100196055 | أمانة / الباحة | تصميم وتشييد | ذات اولوية متوسطة | 3014000 | 150700 | 320000 | 320000 | 5801009694 | لا | 0 | 200209133520 | ايقاف جزئي | الكميات التي تم تركيبها | 9 | 40 | 2020-05-16 | 2022-09-02 | 2022-09-29 | 2022-09-29 |  |  |  |  | 41.4623 | 20.0114 | Failed | No
2100046830 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 2725447.5 | 136272.375 | 2725447.5 | 2725447.5 | 3552000661 | لا | 0 | 190209044225 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-08-30 | 2014-08-25 | 2016-02-23 | 2016-02-23 | 2014-08-25 | 2017-05-08 | اخرى |  | 36.4689 | 26.2366 | منجز | No
2100047832 | أمانة / الباحة | تشييد | ذات اولوية عالية | 42759400 | 2137970 | 8139561.65 | 8139561.65 | 4030007950 | لا | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 21 | 90 | 2019-01-10 | 2022-11-01 | 2022-11-02 | 2022-11-02 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 41.4625 | 20.0028 | Failed | No
2100062985 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 1405048 | 70252.4 | 0 | 0 | 3562000009 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 1 | 100 | 2015-12-05 | 2016-11-29 | 2020-02-12 | 2020-02-12 |  |  | ضعف كفاءة المقاول الفنية |  | 35.0202 | 28.4788 | مسحوب | No
2100049976 | أمانة / جازان | تشييد | لم تعد تحتاجها الجهة | 1267025 | 63351.25 | 546740 | 0 | 5900012775 | لا | 0 | 180801063009 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-08-26 | 2019-08-11 | 2019-08-11 | 2019-08-11 | 2019-08-11 |  | اخرى |  | 42.9672 | 16.53 | منجز | Yes
2100057444 | وزارة الرياضة | تشييد | ذات اولوية عالية | 63056520 | 3152826 | 24927193 | 24927193 | 4030139716 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 59 | 100 | 2013-03-19 | 2015-08-31 | 2015-08-31 | 2015-08-31 |  |  | ضعف كفاءة المقاول الفنية |  | 39.8579 | 21.3891 | مسحوب | No
2100057680 | وزارة الدفاع / الإدارة الهندسية والاشغال بالخدمات الصحية | تشييد | ذات اولوية متوسطة | 11815204.42 | 590760.221 | 11815204.42 | 11815204.42 | 1010168646 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 44 | 100 | 2013-09-07 | 2015-02-20 | 2019-12-22 | 2019-12-22 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 40.4329 | 21.2164 | مسحوب | No
2100026202 | وزارة الشـؤون الاسلامية والدعوة والارشاد | تشييد | ذات اولوية عالية | 1345491 | 67274.55 | 464531 | 0 | 3350014233 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2017-08-10 | 2018-08-10 | 2019-04-10 | 2019-04-10 | 2018-08-10 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 40.4597 | 25.9794 | منجز | Yes
2100032981 | أمانة / العاصمة المقدسة | تصميم وإشراف | ذات اولوية متوسطة | 1244500 | 62225 | 1244500 | 1244500 | 4030229175 | لا | 0 | 180909107726 | منجز – استلام نهائي | مدفوعات ساعات العمل | 100 | 100 | 2015-10-19 | 2017-09-27 | 2020-12-14 | 2020-12-14 | 2017-09-27 | 2020-12-14 | اخرى |  |  |  | منجز | No
2100001400 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية | 44328268.34 | 2216413.417 | 31293274.59 | 31293274.59 | 1010085001 | لا | 0 | 180709019958 | فسخ العقد | تكلفة العمل المنجز | 96 | 100 | 2013-04-29 | 2015-04-19 | 2024-12-31 | 2024-12-31 |  |  | لا يوجد تأخير |  | 40.4759 | 21.3577 | مسحوب | No
2100021840 | شركة الكهرباء | تشييد | ذات اولوية متوسطة | 97588009 | 4879400.45 | 91257500 | 91257500 | 1010061697 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 99.64 | 100 | 2015-12-21 | 2019-05-30 | 2023-01-31 | 2023-01-31 |  |  | اخرى |  | 49.9964 | 26.5724 | متأخر | No
2100020042 | وزارة الشـؤون الاسلامية والدعوة والارشاد | تشييد | ذات اولوية عالية | 3937980 | 196899 | 2674668 | 0 | 3350013522 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 100 | 100 | 2018-02-04 | 2019-10-04 | 2021-02-04 | 2021-02-04 |  |  | لا يوجد تأخير |  | 42.1738 | 27.9592 | Failed | Yes
2100178474 | وزارة الثقافة | إشراف | ذات اولوية عالية | 5192400 | 259620 | 5140400 | 4359880 | 1010435790 | لا | 0 | 201009164279 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-07-25 | 2021-07-30 | 2020-07-31 | 2020-07-31 |  | 2021-07-30 |  |  | 49.5865 | 25.4309 | منجز | No
2100064724 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 794300 | 39715 | 437178 | 437178 | 3550023679 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 56 | 100 | 2013-12-25 | 2015-01-02 | 2015-01-03 | 2015-01-03 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5328 | 28.3915 | مسحوب | No
2100079645 | الهيئة العامة للموانئ | توريد وتركيب | ذات اولوية عالية وعاجلة | 8225580 | 411279 | 1497801.83 | 1497801.83 | 1010231383 | لا | 0 | 190301014889 | مسحوب | الكميات التي تم تركيبها | 44 | 100 | 2019-07-07 | 2020-12-28 | 2021-04-07 | 2021-04-07 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.5387 | 16.8915 | مسحوب | No
2100022595 | أمانة / العاصمة المقدسة | ترميم | ذات اولوية متوسطة | 17141385.8 | 857069.29 | 1337632 | 1337632 | 4031041927 | لا | 0 | 200209134311 | جاري | تكلفة العمل المنجز | 10.34 | 10.34 | 2019-06-18 | 2021-06-07 | 2021-09-12 | 2021-09-12 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | Failed | No
2100010555 | هيئة الهلال الأحمر السعودي | دراسة الجدوى |  | 12589.5 | 629.475 | 12589.5 | 12589.5 | 0 |  | 0 |  | ايقاف كلي | التكلفة المفوترة | 80 | 80 | 2019-03-29 21:00 | 2019-04-28 21:00 |  |  |  |  | اخرى |  |  |  | Failed | No
2100104941 | جامعة الطائف | تشييد | ذات اولوية متوسطة | 15451040 | 772552 | 15451040 | 10304234.85 | 4031041927 | لا | 0 | 180709036492 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 97 | 100 | 2017-08-20 | 2018-02-17 | 2019-04-18 | 2019-04-18 | 2018-02-17 |  | لا يوجد تأخير |  | 42.0281 | 21.9071 | منجز | No
2100106374 | وزارة التعليم | تشييد | ذات اولوية عالية | 7454770.48 | 372738.524 | 5787567 | 5787567 | 1132002624 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-01-12 | 2016-01-02 | 2021-03-23 | 2021-03-23 | 2016-01-02 |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | منجز | No
2100056350 | أمانة / جدة | تصميم | ذات اولوية عالية وعاجلة | 204039998 | 10201999.9 | 138646076.11 | 119061824.46 | 2051011487 | لا | 0 | 180709015737 | جاري | منهجية القيمة المكتسبة | 80.5 | 92.3 | 2017-11-29 | 2019-07-11 | 2023-04-28 | 2023-04-28 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  |  |  | متأخر | No
2100060340 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 109907971.26 | 5495398.563 | 93861789.73 | 87936211.18 | 1010136405 | لا | 0 | 180709021104 | جاري | تكلفة العمل المنجز | 91.39 | 96.72 | 2017-05-08 | 2018-11-06 | 2023-12-31 | 2023-12-31 |  |  | تأخرصرف المستحقات المالية |  | 39.1677 | 21.5008 | متأخر | No
2100073695 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 16437437 | 821871.85 | 10626728 | 10626728 | 4030113058 | لا | 0 | 180709035724 | مسحوب | منهجية القيمة المكتسبة | 68.97 | 100 | 2018-01-29 | 2020-01-29 | 2022-08-29 | 2022-08-29 |  |  | أوامر تغيير |  | 38.1857 | 24.0249 | مسحوب | No
2100018056 | وزارة التعليم | تشييد | ذات اولوية عالية | 7194649.66 | 359732.483 | 4401510.97 | 4222928.81 | 1010181431 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 90 | 2015-10-27 | 2017-10-16 | 2022-01-11 | 2022-01-11 | 2017-10-16 |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | منجز | No
2100079063 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 5024154.87 | 251207.7435 | 2118074.71 | 1394117.9 | 4030172446 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 60 | 100 | 2013-07-24 | 2015-01-15 | 2021-01-10 | 2021-01-10 |  |  | ضعف كفاءة المقاول الفنية |  | 39.836 | 21.4408 | مسحوب | No
2100109594 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 4823782 | 241189.1 | 4823782 | 4823782 | 1010259143 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2018-12-13 | 2020-01-21 | 2020-01-21 | 2020-01-21 | 2020-01-21 |  | لا يوجد تأخير |  | 21.3355 | 39.9652 | منجز | No
2100034156 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 4677801.45 | 233890.0725 | 4677801.45 | 4677801.45 | 4032003067 | لا | 0 |  | جاري | اخرى | 100 | 100 | 2019-06-18 | 2020-06-18 | 2020-10-01 | 2020-10-01 |  |  |  |  | 39.9608 | 21.3345 | Failed | No
2100041484 | شركة المياه الوطنية / منطقة مكة المكرمة | إشراف | ذات اولوية عالية وعاجلة | 3944160 | 197208 | 3355999.4 | 3355999.4 | 1010326770 | لا | 0 |  | جاري | التكلفة المفوترة | 100 | 100 | 2019-10-23 | 2021-10-22 | 2022-04-09 | 2022-04-09 |  |  | لا يوجد تأخير |  | 40.4226 | 21.2841 | خدمات عامة | No
2100194165 | أمانة / جدة | تشييد | ذات اولوية عالية | 563850 | 28192.5 | 563849.99 | 507464.99 | 4601002201 | لا | 0 | 201109098390 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-09-03 | 2021-03-05 | 2021-03-05 | 2021-03-05 | 2021-03-05 |  |  |  | 40.4594 | 20.302 | منجز | No
2100007324 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1716665 | 85833.25 | 0 | 0 | 1010163689 | لا | 0 |  | مسحوب | التكلفة المفوترة | 70 | 100 | 2007-10-26 | 2008-09-11 | 2008-09-11 | 2008-09-11 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | مسحوب | No
2100085035 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 72876185.33 | 3643809.2665 | 56856224 | 56856224 | 5950017705 | نعم | 1 |  | جاري | منهجية القيمة المكتسبة | 82.1 | 96 | 2014-01-27 | 2021-10-21 | 2023-03-31 | 2023-03-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال | أخرى | 41.6382 | 21.2199 | متأخر | No
2100036820 | أمانة / الجوف | تشييد | ذات اولوية متوسطة | 1555000 | 77750 | 380000 | 380000 | 1131013633 | لا | 0 | 190309022338 | مسحوب | تكلفة العمل المنجز | 24 | 100 | 2014-11-12 | 2015-11-07 | 2015-02-08 | 2015-02-08 |  |  | تأخرصرف المستحقات المالية |  | 37.6351 | 31.0687 | مسحوب | No
2100025955 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية وعاجلة | 56253331.2 | 2812666.56 | 34502112.75 | 33144999.68 | 1010218930 | لا | 0 | 180801038832 | جاري | منهجية القيمة المكتسبة | 90.1 | 100 | 2018-11-21 | 2021-10-19 | 2022-09-01 | 2022-09-01 |  |  | تصاريح أعمال التنفيذ |  | 41.5686 | 19.8801 | Failed | No
2100102712 | شركة المياه الوطنية / منطقة مكة المكرمة | دراسات هندسية | ذات اولوية عالية | 43387832 | 2169391.6 | 48374732 | 48374732 | 1010322448 | لا | 0 | 200709052696 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-05-24 | 2018-05-23 | 2020-07-11 | 2020-07-11 | 2018-05-23 |  | لا يوجد تأخير |  | 39.2011 | 21.4789 | منجز | No
2100078363 | وزارة الصحة / عسير | ترميم | ذات اولوية منخفضة | 1814681.6 | 90734.08 | 0 | 0 | 5855033786 | لا | 0 | 190701161770 | مسحوب | تكلفة العمل المنجز | 1 | 100 | 2019-05-07 | 2019-10-01 | 2022-06-01 | 2022-06-01 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.5245 | 18.1992 | مسحوب | No
2100006834 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 3111650 | 155582.5 | 1794671.5 | 1794671.5 | 2058000066 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-09-20 | 2015-07-12 | 2015-07-12 | 2015-07-12 | 2015-07-12 |  |  |  | 40.4511 | 21.2747 | منجز | No
2100095373 | وزارة الصحة / بيشة | تشييد | ذات اولوية عالية | 3793063.85 | 189653.1925 | 0 | 0 | 5852002706 | نعم | 1 |  | جاري | تكلفة العمل المنجز | 8 | 27.4 | 2022-05-19 | 2023-11-01 | 2023-11-01 | 2023-11-01 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 21 |  | متأخر | No
2100021792 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 42857628 | 2142881.4 | 34111871 | 34111871 | 4030023505 | لا | 0 | 180809043147 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-07-09 | 2019-07-17 | 2022-05-15 | 2022-05-15 | 2019-07-17 |  | ضعف كفاءة المقاول الفنية |  | 38.3108 | 23.9181 | منجز | No
2100043153 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 144341557.48 | 7217077.874 | 114223538.16 | 114223538.16 | 4030028078 | لا | 0 | 180709034554 | جاري | تكلفة العمل المنجز | 100 | 100 | 2013-07-17 | 2015-06-24 | 2023-12-31 | 2023-12-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.1677 | 21.5008 | منتظم | No
2100088480 | جامعة الملك خالد | تشييد | ذات اولوية عالية وعاجلة | 29486710 | 1474335.5 | 29453145.18 | 29453145.18 | 5855000147 | لا | 0 | 181109278848 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2017-05-31 | 2018-11-22 | 2022-05-23 | 2022-05-23 |  |  | تأخرصرف المستحقات المالية |  | 42.8114 | 18.1027 | متأخر | No
2100088546 | جامعة طيبة | تشييد | ذات اولوية عالية | 96030075.69 | 4801503.7845 | 71794390.14 | 70159380.7 | 1010063483 | لا | 0 | 180809037804 | جاري | تكلفة العمل المنجز | 73.49 | 100 | 2013-08-31 | 2021-12-14 | 2023-08-06 | 2023-08-06 |  |  | تأخرصرف المستحقات المالية | العقد يسير حسب الخطة | 39.6005 | 24.4595 | Failed | No
2100010113 | وزارة الثقافة | دراسة الجدوى |  | 4184250 | 209212.5 | 5645024.63 | 5645024.63 | 0 |  | 0 |  | جاري | مدفوعات ساعات العمل | 60 | 60 | 2019-11-17 00:59 | 2021-02-16 00:59 | 2021-02-16 | 2021-02-16 | [6 empty] | خدمات عامة | No
2100001514 | وزارة الثقافة | تشييد |  | 5717688.76 | 285884.438 | 2522940.63 | 2522940.63 | 4030166491 |  | 0 |  | جاري | منهجية القيمة المكتسبة | 50 | 100 | 2018-12-27 00:59 | 2019-12-26 00:59 | 2020-06-23 | 2020-06-23 |  |  | أوامر تغيير |  |  |  | Failed | No
2100020904 | وزارة الثقافة | دراسة الجدوى |  | 9462000 | 473100 | 1913695 | 1913695 | 0 |  | 0 |  | مسحوب | مدفوعات ساعات العمل | 45 | 60 | 2018-11-11 00:59 | 2021-11-10 00:59 | 2020-03-02 | 2020-03-02 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | مسحوب | No
2100107811 | جامعة الجوف | تشييد | ذات اولوية عالية | 116590752 | 5829537.6 | 105183586.36 | 105183586.36 | 1010166664 | لا | 0 | 181009121569 | جاري | تكلفة العمل المنجز | 100 | 100 | 2014-08-03 | 2021-01-14 | 2022-02-01 | 2022-02-01 |  |  | تأخرصرف المستحقات المالية |  | 40.0594 | 29.7975 | Failed | No
2100035206 | أمانة / الجوف | تشييد | ذات اولوية عالية | 1093520 | 54676 | 1093520 | 1093520 | 3403008631 | لا | 0 | 180901092300 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-09-25 | 2019-09-18 | 2019-09-18 | 2019-09-18 | 2019-09-18 |  |  |  | 40.3742 | 30.1132 | منجز | No
2100099960 | الهيئة العامة للطيران المدني | تشييد | ذات اولوية عالية وعاجلة | 17445377.89 | 872268.8945 | 15678653.03 | 15678653.03 | 4030212161 | لا | 0 | 190201013599 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-03-10 | 2019-09-06 | 2019-09-06 | 2019-09-06 | 2019-09-06 |  | لا يوجد تأخير |  | 42.4173 | 17.9866 | منجز | No
2100000383 | هيئة الهلال الأحمر السعودي | دراسة الجدوى | ذات اولوية عالية | 18669 | 933.45 | 18669 | 18669 | 1010347774 |  | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2017-06-09 | 2018-08-26 | 2019-01-21 | 2019-01-21 | 2018-08-26 |  | اخرى |  |  |  | منجز | No
2100008164 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 5513268 | 275663.4 | 2488731.48 | 2488731.48 | 2031040463 | لا | 0 |  | مسحوب | التكلفة المفوترة | 45 | 100 | 2012-10-05 | 2014-06-27 | 2014-06-27 | 2014-06-27 |  |  | ضعف كفاءة المقاول الفنية |  | 45.975 | 28.4334 | مسحوب | No
2100021895 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 10636000.48 | 531800.024 | 2366075.83 | 2366075.83 | 1010081983 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 25 | 100 | 2015-11-10 | 2017-10-30 | 2021-01-13 | 2021-01-13 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5604 | 25.3897 | مسحوب | No
2100018410 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2719000 | 135950 | 0.01 | 0.01 | 5857031865 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 7 | 2019-12-04 | 2020-09-29 | 2020-12-23 | 2020-12-23 | 2020-09-29 |  | ضعف كفاءة المقاول الفنية |  | 42.1351 | 19.1255 | منجز | No
2100009763 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 4141566 | 207078.3 | 3679143 | 3679143 | 4032023779 | لا | 0 | 190509002101 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-02-11 | 2019-08-10 | 2019-08-10 | 2019-08-10 | 2019-08-10 |  |  |  | 40.408 | 21.2654 | منجز | No
2100029562 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 19820780 | 991039 | 16067414.738 | 0 | 1010056094 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 86 | 100 | 2014-09-19 | 2016-09-08 | 2020-11-21 | 2020-11-21 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6788 | 24.6913 | Failed | Yes
2100030284 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 275948.4 | 13797.42 | 275947.98 | 275947.98 | 4032035669 | لا | 0 | 200401075838 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-08-20 | 2019-11-28 | 2019-11-28 | 2019-11-28 | 2019-11-28 |  |  |  | 40.81 | 20.9439 | منجز | No
2100037310 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 3182786 | 159139.3 | 2663756.4 | 2663756.4 | 4031033277 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-12-02 | 2015-09-28 | 2015-09-28 | 2015-09-28 | 2015-09-28 |  |  |  | 40.4038 | 21.2652 | منجز | No
2100041274 | أمانة / العاصمة المقدسة | إشراف | ذات اولوية متوسطة | 34209000 | 1710450 | 16976910 | 16976910 | 1010427119 | لا | 0 | 190501130126 | جاري | مدفوعات ساعات العمل | 100 | 100 | 2019-09-01 | 2022-08-31 | 2022-08-31 | 2022-08-31 |  |  | اخرى |  | 39.1919 | 21.4851 | خدمات عامة | No
2100048366 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 5947090 | 297354.5 | 4783833 | 4783833 | 4602001545 | لا | 0 | 190609059681 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 96 | 100 | 2015-03-18 | 2017-02-23 | 2020-05-01 | 2020-05-01 | 2017-02-23 |  | تأخرصرف المستحقات المالية |  | 39.3408 | 22.1487 | منجز | No
2100041436 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 1905574 | 95278.7 | 0.01 | 0.01 | 1010129663 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 88 | 100 | 2007-11-03 | 2008-10-29 | 2021-05-12 | 2021-05-12 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 44.2341 | 17.5757 | مسحوب | No
2100107015 | جامعة نجران | تشييد | ذات اولوية عالية وعاجلة | 4899913.8 | 244995.69 | 4408108.32 | 4408108.32 | 1010060399 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 99 | 100 | 2015-01-05 | 2016-06-20 | 2022-02-02 | 2022-02-02 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 44.2341 | 17.5757 | Failed | No
2100058833 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 2670502.4 | 133525.12 | 2670502.4 | 2670502.4 | 4030210663 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-10-04 | 2020-03-19 | 2020-03-18 | 2020-03-18 | 2020-03-19 |  |  |  | 41.2338 | 19.9516 | منجز | No
2100058601 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 2872430 | 143621.5 | 1399990 | 1399990 | 5950006794 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-12-14 | 2019-12-03 | 2020-01-30 | 2020-01-30 | 2019-12-03 |  | تأخرصرف المستحقات المالية |  | 44.162 | 17.5188 | منجز | No
2100062856 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 987762.5 | 49388.125 | 776127.5 | 316397.5 | 5950006647 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-05-07 | 2016-04-23 | 2016-05-14 | 2016-05-14 | 2016-04-23 |  | ضعف كفاءة المقاول الفنية |  | 44.1676 | 17.5037 | منجز | No
2100065096 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 11397813 | 569890.65 | 5404219.96 | 0 | 1010164501 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 65 | 100 | 2014-10-22 | 2016-04-14 | 2020-08-18 | 2020-08-18 | 2016-04-14 |  | ضعف كفاءة المقاول الفنية |  | 44.8334 | 26.2885 | منجز | Yes
2100071595 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 1594200 | 79710 | 1139849.3 | 0 | 5950010293 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2018-11-16 | 2019-11-06 | 2019-02-17 | 2019-02-17 | 2019-11-06 |  |  |  | 44.2332 | 17.5524 | منجز | Yes
2100075165 | أمانة / الطائف | تشييد |  | 1345550 | 67277.5 | 67277.5 | 67277.5 | 0 |  | 0 |  | جاري | تكلفة العمل المنجز | 5 | 67 | 2019-01-27 20:59 | 2020-06-12 20:59 | 2020-06-12 | 2020-06-12 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | Failed | No
2100082806 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 2900000 | 145000 | 2610000 | 905604 | 3553000678 | لا | 0 | 181209402216 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-02-11 | 2020-09-08 | 2021-09-01 | 2021-09-01 | 2020-09-08 |  |  |  | 34.9451 | 29.2864 | منجز | No
2100090440 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 1371200 | 68560 | 1371200 | 1230728.03 | 3357008595 | نعم | 0.01 | 200401127569 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-01-23 | 2020-01-18 | 2021-03-11 | 2021-03-11 | 2020-01-18 |  |  |  | 42.4015 | 27.9096 | منجز | No
2100034311 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 1879895 | 93994.75 | 151559 | 151559 | 4030138666 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 9.15 | 9.15 | 2014-08-05 | 2016-08-04 | 2016-08-04 | 2016-08-04 |  |  |  |  | 40.0099 | 21.99 | مسحوب | No
2100011336 | جامعة نجران | تشييد | ذات اولوية عالية وعاجلة | 90000000 | 4500000 | 51386666 | 51386666 | 2066001761 | لا | 0 | 181109338440 | جاري | الكميات التي تم تركيبها | 64 | 100 | 2014-11-24 | 2017-10-21 | 2022-01-19 | 2022-01-19 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 44.2341 | 17.5757 | Failed | No
2100102524 | وزارة التعليم | تشييد | ذات اولوية عالية | 2947659 | 147382.95 | 2269697 | 2269697 | 5864037186 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2013-02-16 | 2014-02-21 | 2014-08-27 | 2014-08-27 | 2014-02-21 |  |  |  | 42.1351 | 19.1255 | منجز | No
2100100866 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 1931188 | 96559.4 | 1931188 | 1931188 | 5950012112 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-09-02 | 2019-07-23 | 2019-07-23 | 2019-07-23 | 2019-07-23 |  | اخرى |  | 44.2263 | 17.5661 | منجز | No
2100105162 | جامعة الملك فيصل | تشييد | ذات اولوية متوسطة | 40624675 | 2031233.75 | 40624675 | 40624675 | 1010208002 | لا | 0 | 181009198472 | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2015-07-06 | 2016-05-26 | 2017-12-10 | 2017-12-10 |  | 2016-05-26 | تأخرصرف المستحقات المالية |  | 49.5604 | 25.3897 | منجز | No
2100102550 | جامعة جازان | تصميم | ذات اولوية عالية | 15860154 | 793007.7 | 15860154 | 15860154 | 5900028256 | لا | 0 | 180709036304 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-12-15 | 2016-12-15 | 2018-08-09 | 2018-08-09 | 2016-12-15 |  |  |  | 42.5542 | 16.9694 | منجز | No
2100011572 | وزارة الشـؤون الاسلامية والدعوة والارشاد | تشييد | ذات اولوية عالية | 239320 | 11966 | 0 | 0 | 1122003955 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 99 | 100 | 2018-01-25 | 2018-09-22 | 2018-09-22 | 2018-09-22 |  |  | ضعف كفاءة المقاول الفنية |  | 42.999 | 25.4903 | Failed | No
2100020941 | جامعة حائل | تشييد | ذات اولوية عالية وعاجلة | 283248041 | 14162402.05 | 190268334.14 | 190268334.14 | 1010034600 | لا | 0 | 190309092566 | جاري | تكلفة العمل المنجز | 57.69 | 80 | 2013-11-10 | 2022-09-08 | 2023-09-02 | 2023-09-02 |  |  | تأخرصرف المستحقات المالية |  | 41.7156 | 27.6655 | متأخر | No
2100191520 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 3010978 | 150548.9 | 1442515 | 1442515 | 4030129089 | لا | 1 | 200709052696 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2020-07-05 | 2021-03-06 | 2021-09-13 | 2021-09-13 | 2021-03-06 |  |  |  | 39.187 | 21.4635 | منجز | No
2100191063 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية وعاجلة | 59850000 | 2992500 | 35695935.91 | 35695935.91 | 5850002600 | لا | 0 | 200201148393 | جاري | منهجية القيمة المكتسبة | 89.95 | 100 | 2020-05-31 | 2021-03-27 | 2022-12-31 | 2022-12-31 |  |  |  |  | 42.6484 | 17.1602 | Failed | No
2100003916 | وزارة الثقافة | تشييد |  | 96895260.37 | 4844763.0185 | 48627278.3 | 48627278.3 | 1010154344 |  | 0 |  | جاري | منهجية القيمة المكتسبة | 60 | 95 | 2017-12-06 00:59 | 2020-04-05 00:59 | 2020-09-05 | 2020-09-05 |  |  | أوامر تغيير |  |  |  | Failed | No
2100000663 | أمانة / العاصمة المقدسة | إشراف | ذات اولوية متوسطة | 2500000 | 125000 | 2395841 | 2395841 | 4030237556 | لا | 0 | 190909003867 | جاري الاستلام الإبتدائي | اخرى | 95.83 | 95.83 | 2019-05-26 | 2021-05-25 | 2021-05-25 | 2021-05-25 |  |  | اخرى |  | 39.8382 | 21.3987 | Failed | No
2100109152 | شركة المياه الوطنية / منطقة الحدود الشمالية | تشييد | ذات اولوية عالية | 14396400 | 719820 | 14396400 | 14396400 | 3450006303 | نعم | 0.01 | 180601013294 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-11-01 | 2020-10-10 | 2020-08-18 | 2020-08-18 |  | 2020-10-10 | لا يوجد تأخير |  | 44.0348 | 29.2985 | منجز | No
2100003964 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية متوسطة | 11402470 | 570123.5 | 8611448.4 | 8611448.4 | 1131016321 | لا | 0 | 180709019626 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 80.08 | 100 | 2013-12-03 | 2015-05-19 | 2019-11-03 | 2019-11-03 |  | 2015-05-19 | لا يوجد تأخير |  | 43.9875 | 26.0873 | منجز | No
2100086461 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2256540 | 112827 | 0 | 0 | 2511004496 | لا | 0 |  | مسحوب | التكلفة المفوترة | 15 | 100 | 2010-02-13 | 2011-04-10 | 2023-06-15 | 2023-06-15 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0165 | 30.9619 | مسحوب | No
2100059964 | جامعة الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 240923955.29 | 12046197.7645 | 173503784.66 | 167986112.52 | 1010136405 | لا | 0 | 181109235242 | جاري | تكلفة العمل المنجز | 87 | 92 | 2013-12-25 | 2017-06-07 | 2023-12-20 | 2023-12-20 |  |  | تأخرصرف المستحقات المالية |  | 43.5207 | 29.6323 | منتظم | No
2100059076 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية متوسطة | 12000000 | 600000 | 11340000.01 | 11340000.01 | 2057001398 | لا | 0 | 180101000061 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 80 | 100 | 2018-02-18 | 2020-07-23 | 2021-06-21 | 2021-06-21 |  | 2020-07-23 | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 43.9553 | 26.3508 | منجز | No
2100039955 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 89827694 | 4491384.7 | 76490312 | 76490312 | 1010066115 | لا | 0 | 181209500995 | جاري | منهجية القيمة المكتسبة | 96.14 | 99.35 | 2018-01-07 | 2020-01-07 | 2023-01-15 | 2023-01-15 |  |  | ضعف كفاءة المقاول الفنية |  | 38.1659 | 24.0309 | منتظم | No
2100054843 | أمانة / جدة | تشييد | ذات اولوية عالية | 240393735 | 12019686.75 | 256895798.56 | 229055273.37 | 4030140655 | لا | 0 | 180401004879 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2018-12-24 | 2021-05-27 | 2022-04-29 | 2022-04-29 | 2021-05-27 |  | اخرى |  | 39.2074 | 21.532 | منجز | No
2100107855 | وزارة الرياضة | تشييد | ذات اولوية عالية | 57839817.64 | 2891990.882 | 55037846.49 | 55037846.49 | 1010042569 | لا | 0 | 180909079010 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2016-03-06 | 2018-02-10 | 2020-12-13 | 2020-12-13 | 2018-02-10 |  | ضعف كفاءة المقاول الفنية |  |  |  | منجز | No
2100010474 | شركة المياه الوطنية / منطقة جازان | تشييد | ذات اولوية عالية وعاجلة | 10435130 | 521756.5 | 1257906 | 1257906 | 4030159937 | لا | 0 | 180709026196 | مسحوب | منهجية القيمة المكتسبة | 40.74 | 100 | 2014-05-07 | 2015-04-27 | 2022-02-28 | 2022-02-28 |  |  | ضعف كفاءة المقاول الفنية |  | 43.139 | 17.2845 | مسحوب | No
2100028206 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 46102400 | 2305120 | 46102400 | 46102400 | 5950005891 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-07-24 | 2017-01-05 | 2021-01-06 | 2021-01-06 | 2017-01-05 |  | اخرى |  | 44.2251 | 17.5332 | منجز | No
2100011255 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2410538.78 | 120526.939 | 668931 | 668931 | 4030123131 | لا | 0 | 190409041629 | جاري | التكلفة المفوترة | 85 | 100 | 2016-05-01 | 2017-04-26 | 2022-04-26 | 2022-04-26 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.1677 | 21.5008 | Failed | No
2100093450 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 29540858.3 | 1477042.915 | 26602752.63 | 26602752.63 | 2050022550 | لا | 0 | 190309036166 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-07-14 | 2016-01-05 | 2022-06-30 | 2022-06-30 | 2016-01-05 |  | ضعف كفاءة المقاول الفنية |  | 40.4033 | 21.257 | منجز | No
2100105663 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 72732000 | 3636600 | 48429561.75 | 23259459.84 | 1010012911 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 91.61 | 100 | 2014-12-28 | 2016-12-28 | 2020-01-20 | 2020-01-20 | 2016-12-28 |  | لا يوجد تأخير |  | 40.8611 | 21.7326 | منجز | No
2100078315 | وزارة الصحة / الطائف | تشييد | ذات اولوية عالية | 700000 | 35000 | 173800 | 0 | 4032000850 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-02-15 | 2020-05-14 | 2021-03-03 | 2021-03-03 | 2020-05-14 |  | تأخرصرف المستحقات المالية |  | 41.7465 | 22.4304 | منجز | Yes
2100004270 | شركة المياه الوطنية / منطقة نجران | تشييد | ذات اولوية عالية | 19997141 | 999857.05 | 17296820.91 | 17296820.91 | 1010210667 | لا | 0 | 180901097902 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 98.41 | 2018-10-30 | 2020-10-08 | 2022-02-01 | 2022-02-01 | 2020-10-08 |  | اخرى |  | 44.2341 | 17.5757 | منجز | No
2100062624 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 16797376.25 | 839868.8125 | 12766005.95 | 12766005.95 | 4650049563 | لا | 0 |  | جاري | تكلفة العمل المنجز | 76 | 85 | 2019-10-29 | 2023-03-01 | 2023-03-01 | 2023-03-01 |  |  | ضعف كفاءة المقاول الفنية |  | 39.5987 | 24.442 | متأخر | No
2100006683 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 66986900 | 3349345 | 57881576.16 | 57881576.16 | 1010090968 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-02-17 | 2020-06-26 | 2020-08-10 | 2020-08-10 | 2020-06-26 |  | أوامر تغيير |  |  |  | منجز | No
2100014906 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 10682156.7 | 534107.835 | 6843381.22 | 6561587.27 | 1010409973 | لا | 0 | 190209015517 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2016-05-17 | 2018-05-07 | 2020-07-14 | 2020-07-14 | 2018-05-07 |  | ضعف كفاءة المقاول الفنية |  | 42.4987 | 18.2178 | منجز | No
2100105954 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 16413039 | 820651.95 | 15029201.47 | 15029201.47 | 1010074764 | لا | 0 | 190201038726 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-11-30 | 2020-11-30 | 2020-11-24 | 2020-11-24 | 2020-11-30 |  | لا يوجد تأخير |  | 50.1501 | 26.3537 | منجز | No
2100061390 | شركة المياه الوطنية / منطقة حائل | تشييد | ذات اولوية عالية وعاجلة | 36830575.5 | 1841528.775 | 31484137.07 | 31484137.07 | 1132002394 | لا | 0 | 181109365601 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 98.25 | 100 | 2012-11-10 | 2014-10-19 | 2020-10-27 | 2020-10-27 | 2014-10-19 |  | لا يوجد تأخير |  | 40.4847 | 25.9903 | منجز | No
2100019585 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية متوسطة | 1942200 | 97110 | 1741409.82 | 1741409.82 | 1131033767 | لا | 0 | 180701019574 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 84.27 | 100 | 2017-01-08 | 2017-07-04 | 2017-07-04 | 2017-07-04 |  | 2017-07-04 | لا يوجد تأخير |  | 43.9597 | 26.325 | منجز | No
2100011292 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2581000 | 129050 | 682820 | 375920 | 2055122137 | لا | 0 |  | جاري | التكلفة المفوترة | 41 | 100 | 2018-12-13 | 2019-12-08 | 2021-02-01 | 2021-02-01 |  |  | ضعف كفاءة المقاول الفنية |  | 49.0607 | 27.1614 | Failed | No
2100011686 | شركة المياه الوطنية / منطقة عسير | تشييد | ذات اولوية عالية | 9933000 | 496650 | 9927664.14 | 9927664.14 | 1010210389 | لا | 0 | 181201443809 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 99.946 | 100 | 2019-02-28 | 2021-02-05 | 2020-06-08 | 2020-06-08 |  | 2021-02-05 | لا يوجد تأخير |  | 43.526 | 19.539 | منجز | No
2100025944 | شركة المياه الوطنية / منطقة الباحة | تشييد | ذات اولوية عالية | 61538600 | 3076930 | 5348996.18 | 5348996.18 | 1010346404 | لا | 0 | 181001139597 | جاري | منهجية القيمة المكتسبة | 11.3 | 100 | 2019-05-23 | 2022-04-19 | 2024-01-22 | 2024-01-22 |  |  | ضعف كفاءة المقاول الفنية |  | 41.4374 | 19.7864 | Failed | No
2100038931 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية وعاجلة | 41999869.32 | 2099993.466 | 29497533.36 | 29497533.36 | 1010076961 | لا | 0 | 180709036378 | مسحوب | منهجية القيمة المكتسبة | 89.63 | 100 | 2015-04-07 | 2017-09-09 | 2023-12-05 | 2023-12-05 |  |  | ضعف كفاءة المقاول الفنية |  | 49.9893 | 26.6643 | مسحوب | No
2100032966 | وزارة التعليم | تشييد | ذات اولوية عالية | 26433729.71 | 1321686.4855 | 13256348 | 13256348 | 1010099661 | لا | 0 |  | ايقاف جزئي | التكلفة المفوترة | 56 | 100 | 2014-09-14 | 2017-03-02 | 2017-03-17 | 2017-03-17 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | Failed | No
2100191192 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 91500000 | 4575000 | 38464193.65 | 38464193.65 | 1010012911 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 90 | 100 | 2021-03-31 | 2022-01-20 | 2022-04-08 | 2022-04-08 |  |  |  |  | 39.9855 | 21.3529 | Failed | No
2100044601 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 968595.2 | 48429.76 | 748836.01 | 748836.01 | 4036000759 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2013-03-19 | 2014-03-14 | 2014-03-14 | 2014-03-14 | 2014-03-14 |  | ضعف كفاءة المقاول الفنية |  | 42.8518 | 21.2587 | منجز | No
2100005132 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 81287223.15 | 4064361.1575 | 59821586.55 | 59821586.55 | 1010136405 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-03-20 | 2020-10-25 | 2020-10-25 | 2020-10-25 | 2020-10-25 |  | أوامر تغيير |  |  |  | منجز | No
2100063895 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1066000 | 53300 | 1066000 | 1066000 | 4605002907 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-04-29 | 2019-04-24 | 2019-04-24 | 2019-04-24 | 2019-04-24 |  |  |  | 42.8506 | 21.2553 | منجز | No
2100005714 | جامعة أم القرى | تشييد | ذات اولوية متوسطة | 243900963.8 | 12195048.19 | 165352160.52 | 165352160.52 | 4030008659 | لا | 0 | 181109272471 | مسحوب | تكلفة العمل المنجز | 91 | 100 | 2009-02-10 | 2012-02-10 | 2024-12-01 | 2024-12-01 |  |  |  | مخطط لسحبه وإعادة ترسيته | 39.9299 | 21.3435 | مسحوب | No
2100046712 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 7683033 | 384151.65 | 4226934 | 0 | 1116001737 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 98 | 100 | 2011-02-27 | 2013-02-16 | 2019-09-04 | 2019-09-04 | 2013-02-16 |  | ضعف كفاءة المقاول الفنية |  | 46.6768 | 24.7057 | منجز | Yes
2100065866 | أمانة / عسير | تشييد | ذات اولوية عالية | 3998760 | 199938 | 2641373.31 | 1508887 | 5852002774 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-12-15 | 2019-12-18 | 2020-06-09 | 2020-06-09 | 2019-12-18 |  | ضعف كفاءة المقاول الفنية |  |  |  | منجز | No
2100029831 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 18070500 | 903525 | 989060.65 | 989060.65 | 5950014853 | لا | 0 | 210601172735 | جاري | تكلفة العمل المنجز | 49.02 | 55 | 2019-09-01 | 2025-11-25 | 2025-11-25 | 2025-11-25 |  |  |  |  | 44.2406 | 17.5719 | متأخر | No
2100189501 | الهيئة العامة للزكاة والدخل | ترميم | ذات اولوية عالية | 4305000 | 215250 | 4305000 | 4305000 | 1010200847 | لا | 0 |  | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2020-07-16 | 2020-09-13 | 2020-09-13 | 2020-09-13 |  | 2020-09-13 |  |  | 40.2006 | 29.9586 | منجز | No
2100092890 | المؤسسة العامة لتحلية المياه المالحة | توريد | ذات اولوية عالية | 313486821.25 | 15674341.0625 | 257507889.44 | 257507889.44 | 2050037927 | لا | 0 | 180601012772 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-09-02 | 2020-10-10 | 2020-10-10 | 2020-10-10 | 2020-10-10 |  | تأخرصرف المستحقات المالية |  | 38.3749 | 23.8637 | منجز | No
2100019891 | المؤسسة العامة لتحلية المياه المالحة | تشييد | ذات اولوية عالية | 212000000 | 10600000 | 194114632.15 | 194114632.15 | 1010004739 | لا | 0 | 181201451761 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-01-14 | 2021-05-13 | 2021-05-13 | 2021-05-13 | 2021-05-13 |  | تأخرصرف المستحقات المالية |  | 39.5286 | 20.6839 | منجز | No
2100065704 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 1589217 | 79460.85 | 778060 | 299424.62 | 5950030343 | لا | 0 | 220601025060 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 90 | 100 | 2015-02-02 | 2020-10-03 | 2020-10-03 | 2020-10-03 | 2020-10-03 |  | اخرى |  | 44.1803 | 17.5567 | منجز | No
2100071945 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 2908900 | 145445 | 1035305 | 1035305 | 4031076575 | لا | 0 | 2046369 | ايقاف كلي | تكلفة العمل المنجز | 52 | 52 | 2015-09-04 | 2015-12-02 | 2015-12-02 | 2015-12-02 |  |  | اخرى |  | 39.3817 | 21.8935 | Failed | No
2100024780 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 356166 | 17808.3 | 356166 | 356166 | 4601002260 | لا | 0 | 200509095008 | منجز – استلام ابتدائي | اخرى | 90 | 95 | 2020-03-09 | 2021-03-14 | 2021-06-12 | 2021-06-12 | 2021-03-14 |  | اخرى |  |  |  | منجز | No
2100063512 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 661720 | 33086 | 471144.64 | 471144.64 | 4031083542 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 82 | 100 | 2016-08-14 | 2017-08-14 | 2022-01-01 | 2022-01-01 | 2017-08-14 |  | تأخرصرف المستحقات المالية |  | 41.0701 | 20.464 | منجز | No
2100008186 | وزارة الرياضة | تشييد | ذات اولوية عالية | 78918675 | 3945933.75 | 34853314 | 34853314 | 3350012131 | لا | 0 | 181109274742 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2012-09-24 | 2015-02-26 | 2021-02-14 | 2021-02-14 | 2015-02-26 |  | ضعف كفاءة المقاول الفنية |  |  |  | منجز | No
2100012121 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات الجوية | تشييد | ذات اولوية متوسطة | 8774270 | 438713.5 | 6398455 | 6398455 | 4030260915 | لا | 0 | 180401003785 | جاري | الكميات التي تم تركيبها | 88 | 100 | 2018-09-15 | 2020-02-28 | 2022-05-31 | 2022-05-31 |  |  | لا يوجد تأخير |  | 39.2309 | 21.4563 | Failed | No
2100030612 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1411000 | 70550 | 1411000 | 1411000 | 4044000973 | لا | 0 | 181001141298 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-08-30 | 2019-08-25 | 2019-08-25 | 2019-08-25 | 2019-08-25 |  |  |  | 40.833 | 20.7272 | منجز | No
2100035000 | أمانة / جازان | تشييد | لم تعد تحتاجها الجهة | 4594966 | 229748.3 | 4594966 | 4594966 | 1131020873 | لا | 0 | 180809053361 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-04-11 | 2016-03-26 | 2019-02-21 | 2019-02-21 | 2016-03-26 |  | اخرى |  | 42.7737 | 17.1067 | منجز | No
2100046690 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 2918073.48 | 145903.674 | 2860421 | 1988277.57 | 5950006647 | لا | 0 | 210601172735 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-02-16 | 2022-01-14 | 2022-02-28 | 2022-02-28 | 2022-01-14 |  | تأخرصرف المستحقات المالية |  | 44.247 | 17.5667 | منجز | No
2100030085 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية عالية | 6598500 | 329925 | 3594105 | 3594105 | 4031041927 | لا | 0 | 200209129415 | مسحوب | تكلفة العمل المنجز | 55 | 55 | 2019-07-07 | 2021-09-09 | 2021-09-09 | 2021-09-09 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.8956 | 21.3797 | مسحوب | No
2100196044 | أمانة / الباحة | تصميم وتشييد | ذات اولوية متوسطة | 3584400 | 179220 | 199867.5 | 199867.5 | 5801009694 | لا | 0 |  | ايقاف جزئي | الكميات التي تم تركيبها | 11 | 50 | 2020-06-13 | 2022-06-04 | 2022-09-29 | 2022-09-29 |  |  |  |  | 41.4616 | 20.0115 | Failed | No
2100040843 | جامعة الملك سعود | توريد وتركيب | ذات اولوية متوسطة | 1848000 | 92400 | 1848000 | 1848000 | 1010327804 | لا | 0 | 210201081404 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-06-27 | 2020-06-16 | 2020-08-30 | 2020-08-30 | 2020-06-16 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  |  |  | منجز | No
2100046233 | أمانة / الباحة | تشييد | ذات اولوية عالية وعاجلة | 2354385 | 117719.25 | 446361 | 446361 | 5800007456 | لا | 0 | 190409070456 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2018-09-21 | 2021-11-02 | 2021-11-02 | 2021-11-02 | 2021-11-02 |  | ضعف كفاءة المقاول الفنية |  | 41.2878 | 20.0956 | منجز | No
2100049055 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 2950000 | 147500 | 0 | 0 | 5855046815 | لا | 0 | 190309046229 | فسخ العقد | الكميات التي تم تركيبها | 2.9 | 100 | 2015-10-12 | 2016-10-01 | 2016-10-02 | 2016-10-02 |  |  | اخرى |  | 42.6935 | 17.512 | مسحوب | No
2100050514 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 1844850 | 92242.5 | 1106284.5 | 1106284.5 | 5855028046 | لا | 0 | 190201025213 | منجز – استلام ابتدائي | اخرى | 84 | 100 | 2019-01-06 | 2019-07-05 | 2021-12-12 | 2021-12-12 | 2019-07-05 |  | ضعف كفاءة المقاول الفنية |  | 42.5491 | 16.9086 | منجز | No
2100054751 | أمانة / تبوك | تشييد | ذات اولوية عالية وعاجلة | 43650986.82 | 2182549.341 | 43650987 | 43650987 | 3550021826 | لا | 0 | 180909109631 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-10-28 | 2016-04-20 | 2019-04-22 | 2019-04-22 | 2016-04-20 |  | اخرى |  | 36.5943 | 28.4312 | منجز | No
2100050971 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 27480123 | 1374006.15 | 0 | 0 | 5950009827 | لا | 0 | 190401075717 | ايقاف كلي | الكميات التي تم تركيبها | 0 | 0 | 2019-09-07 | 2021-02-20 | 2021-02-20 | 2021-02-20 |  |  | أوامر تغيير |  | 44.2279 | 17.5617 | Failed | No
2100054891 | أمانة / جدة | تشييد | ذات اولوية عالية | 94899338 | 4744966.9 | 88939146 | 88939136 | 4030148791 | لا | 0 | 180701016845 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 99 | 100 | 2018-10-24 | 2020-10-01 | 2021-03-22 | 2021-03-22 | 2020-10-01 |  | اخرى |  | 39.2374 | 21.492 | منجز | No
2100054972 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 254624673.07 | 12731233.6535 | 195526430.91 | 195526430.91 | 1010090968 | لا | 0 |  | ايقاف جزئي | منهجية القيمة المكتسبة | 99 | 100 | 2019-01-29 | 2020-01-29 | 2023-05-31 | 2023-05-31 |  |  | منازعات قائمة | أخرى |  |  | متأخر | No
2100079306 | وزارة التعليم | تشييد | ذات اولوية عالية | 2726370 | 136318.5 | 2238765 | 2238765 | 5858030372 | لا | 0 | 191101366587 | جاري الاستلام الإبتدائي | التكلفة المفوترة | 88 | 100 | 2012-10-01 | 2014-04-26 | 2022-12-29 | 2022-12-29 |  |  | ضعف كفاءة المقاول الفنية |  | 43.1379 | 18.0853 | Failed | No
2100091140 | أمانة / جازان | تشييد | ذات اولوية عالية | 989500 | 49475 | 712060 | 712060 | 5922354851 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 72 | 100 | 2011-12-27 | 2012-12-21 | 2012-12-22 | 2012-12-22 |  |  | اخرى |  | 42.5958 | 16.927 | مسحوب | No
2100091346 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 5792546.64 | 289627.332 | 4002534 | 4002534 | 1010023313 | لا | 0 |  | مسحوب | التكلفة المفوترة | 80 | 100 | 2014-01-16 | 2015-10-08 | 2020-10-25 | 2020-10-25 |  |  | ضعف كفاءة المقاول الفنية |  | 45.975 | 28.4334 | مسحوب | No
2100096364 | جامعة الملك سعود | توريد وتركيب | ذات اولوية عالية | 369736.5 | 18486.825 | 369736.5 | 369736.5 | 1010632197 | لا | 0 | 190601089012 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-06-14 | 2020-08-08 | 2020-08-08 | 2020-08-08 | 2020-08-08 |  | لا يوجد تأخير |  |  |  | منجز | No
2100082795 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 2523200 | 126160 | 0 | 0 | 3350017944 | لا | 0 | 190201038887 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-12-16 | 2019-12-10 | 2021-08-17 | 2021-08-17 | 2019-12-10 |  |  |  | 42.1314 | 26.5147 | منجز | No
2100106842 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 6134394.12 | 306719.706 | 2379370.5 | 0 | 4650020435 | لا | 0 |  | مسحوب | التكلفة المفوترة | 52 | 100 | 2013-01-26 | 2014-10-20 | 2023-06-15 | 2023-06-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | Yes
2100106713 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 14781930.51 | 739096.5255 | 14781930.51 | 14781930.51 | 5855000147 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-08-07 | 2018-08-07 | 2019-01-01 | 2019-01-01 | 2018-08-07 | [5 empty] | منجز | No
2100102266 | أمانة / جدة | دراسات هندسية | ذات اولوية متوسطة | 6600000 | 330000 | 6968220.32 | 6968220.32 | 1010461905 | لا | 0 | 181201478882 | منجز – استلام نهائي | اخرى | 99 | 99 | 2019-02-18 | 2022-01-15 | 2022-01-15 | 2022-01-15 | 2022-01-15 | 2022-04-03 | اخرى |  | 39.1677 | 21.5008 | منجز | No
2100090171 | وزارة الشـؤون الاسلامية والدعوة والارشاد | تشييد | ذات اولوية عالية | 4384457 | 219222.85 | 2409564.5 | 240956.5 | 5905004847 | لا | 0 | 201109233382 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-09-24 | 2015-09-01 | 2021-02-28 | 2021-02-28 | 2015-09-01 |  | تصاريح أعمال التنفيذ |  | 43.0998 | 17.2385 | منجز | No
2100109126 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 14381116.88 | 719055.844 | 7991365.96 | 5730930 | 2050237610 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-12-04 | 2016-11-23 | 2021-05-05 | 2021-05-05 | 2016-11-23 |  | ضعف كفاءة المقاول الفنية |  | 50.4906 | 26.3577 | منجز | No
2100006753 | وزارة الشـؤون الاسلامية والدعوة والارشاد | تشييد | ذات اولوية عالية | 1200000 | 60000 | 485140 | 0 | 3357003880 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2017-10-05 | 2018-10-05 | 2019-07-05 | 2019-07-05 | 2018-10-05 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.2643 | 27.0947 | منجز | Yes
2100016785 | وزارة الشـؤون الاسلامية والدعوة والارشاد | تشييد | ذات اولوية عالية | 599075 | 29953.75 | 0 | 0 | 3350010757 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 25 | 30 | 2018-04-08 | 2019-04-08 | 2021-02-25 | 2021-02-25 | 2019-04-08 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.7139 | 27.5081 | منجز | No
2100069764 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 95950000 | 4797500 | 67357684 | 67357684 | 1010136405 | لا | 0 | 181209413940 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-03-06 | 2017-02-28 | 2021-01-03 | 2021-01-03 | 2017-02-28 |  | ضعف كفاءة المقاول الفنية |  | 36.5443 | 28.366 | منجز | No
2100104156 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 3202668 | 160133.4 | 3407368.97 | 2784406.2 | 1010281366 | نعم | 1761467.4 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 92 | 100 | 2018-07-08 | 2019-11-30 | 2021-06-13 | 2021-06-13 | 2019-11-30 |  | اخرى |  | 47.3078 | 24.1522 | منجز | No
2100022330 | جامعة الملك سعود | توريد وتركيب | ذات اولوية عالية | 2571125 | 128556.25 | 858462.91 | 858462.91 | 1010219247 | لا | 0 | 201009109222 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 99 | 100 | 2020-02-04 | 2021-02-04 | 2023-01-27 | 2023-01-27 |  |  | لا يوجد تأخير |  |  |  | Failed | No
2100016380 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 35688314.5 | 1784415.725 | 28316246.56 | 28316246.56 | 1010224518 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99 | 100 | 2019-04-01 | 2021-04-01 | 2022-03-30 | 2022-03-30 | 2021-04-01 |  | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100110143 | وزارة الداخلية / ديوان وزارة الداخلية | تصميم وتشييد | ذات اولوية عالية وعاجلة | 1050800823.82 | 52540041.191 | 858140072.44 | 840286480.25 | 1010199246 | لا | 0 | 180909071976 | جاري | منهجية القيمة المكتسبة | 97.63 | 100 | 2014-12-01 | 2017-05-18 | 2023-02-23 | 2023-02-23 |  |  | تأخرصرف المستحقات المالية | تم تمديد الجدول الزمني | 42.7482 | 16.6597 | منتظم | No
2100033456 | أمانة / عسير | تشييد | ذات اولوية عالية وعاجلة | 1997936 | 99896.8 | 250706 | 250706 | 5855022244 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 13 | 100 | 2012-07-20 | 2013-07-20 | 2019-10-05 | 2019-10-05 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | مسحوب | No
2100079144 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1200000 | 60000 | 0 | 0 | 5857026966 | لا | 0 |  | مسحوب | التكلفة المفوترة | 95 | 100 | 2008-04-26 | 2009-04-15 | 2022-05-10 | 2022-05-10 |  |  | ضعف كفاءة المقاول الفنية |  | 42.4987 | 18.2178 | مسحوب | No
2100061261 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية متوسطة | 27772060 | 1388603 | 20791667.37 | 20529037.98 | 1010157711 | لا | 0 | 180709022158 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 93.93 | 100 | 2014-06-12 | 2018-04-30 | 2020-05-19 | 2020-05-19 |  | 2018-04-30 | لا يوجد تأخير |  | 43.9553 | 26.3508 | منجز | No
2100101032 | مدينة الملك سعود الطبية | تشييد |  | 270790802 | 13539540.1 | 241756666.42 | 241756666.42 | 1010119820 |  | 0 |  | جاري | تكلفة العمل المنجز | 98 | 100 | 2007-10-28 00:59 | 2010-10-27 00:59 |  |  |  |  | ضعف كفاءة المقاول الفنية |  | 46.6906 | 24.6282 | Failed | No
2100069495 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 799968 | 39998.4 | 404319.2 | 404319.2 | 4035001647 | لا | 0 | 181009123822 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-08-31 | 2016-08-30 | 2016-08-30 | 2016-08-30 | 2016-08-30 |  | ضعف كفاءة المقاول الفنية |  | 41.0472 | 20.5964 | منجز | No
2100030564 | أمانة / الجوف | تشييد | ذات اولوية عالية | 143400 | 7170 | 143400 | 143400 | 3402100412 | لا | 0 | 180909107679 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-08-08 | 2018-12-04 | 2021-06-14 | 2021-06-14 | 2018-12-04 |  |  |  | 39.3051 | 29.888 | منجز | No
2100087150 | شركة المياه الوطنية / منطقة المدينة المنورة | تشييد | ذات اولوية عالية وعاجلة | 7839496 | 391974.8 | 7406186.55 | 7406186.55 | 1010289276 | لا | 0 | 180901076416 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 99 | 2018-09-26 | 2019-09-15 | 2019-09-12 | 2019-09-12 | 2019-09-15 |  | لا يوجد تأخير |  | 39.6457 | 24.2586 | منجز | No
2100001035 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 38111435.25 | 1905571.7625 | 17973019.27 | 17973019.27 | 2050002732 | لا | 0 | 190401039249 | جاري | منهجية القيمة المكتسبة | 52.62 | 99.95 | 2019-07-24 | 2021-07-24 | 2022-12-31 | 2022-12-31 |  |  | لا يوجد تأخير |  | 49.6207 | 26.9975 | Failed | No
2100022105 | وزارة التعليم | تشييد | ذات اولوية عالية | 17291200.08 | 864560.004 | 17519784 | 0 | 1010181431 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-03-31 | 2017-06-18 | 2019-07-17 | 2019-07-17 | 2017-06-18 |  | اخرى |  | 39.1677 | 21.5008 | منجز | Yes
2100052441 | وزارة الرياضة | تشييد | ذات اولوية عالية | 27798010.5 | 1389900.525 | 5636839.33 | 5636839.33 | 1010088518 | لا | 0 | 180909080514 | مسحوب | تكلفة العمل المنجز | 65 | 100 | 2014-05-25 | 2016-10-27 | 2016-10-27 | 2016-10-27 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6753 | 24.7136 | مسحوب | No
2100011196 | شركة المياه الوطنية / المنطقة الشرقية | تشييد | ذات اولوية عالية وعاجلة | 1994000 | 99700 | 0 | 0 | 1010335103 | لا | 0 | 190301028624 | مسحوب | منهجية القيمة المكتسبة | 21.45 | 100 | 2019-01-29 | 2020-01-29 | 2023-02-26 | 2023-02-26 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 49.5499 | 25.5984 | مسحوب | No
2100056560 | شركة المياه الوطنية / منطقة جازان | إشراف | ذات اولوية عالية وعاجلة | 6372000 | 318600 | 10020121.48 | 10020121.48 | 1010315399 | لا | 0 | 180709025970 | جاري | التكلفة المفوترة | 100 | 100 | 2012-08-06 | 2015-08-06 | 2022-06-30 | 2022-06-30 |  |  | لا يوجد تأخير |  | 42.6788 | 16.7881 | خدمات عامة | No
2100020996 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 4108500 | 205425 | 4108340.62 | 3694249.32 | 1010158780 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-10-17 | 2021-10-17 | 2021-06-28 | 2021-06-28 | 2021-10-17 |  | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100017964 | جامعة الملك فيصل | تشييد | ذات اولوية عالية | 192875 | 9643.75 | 192875 | 192875 | 1010258205 | لا | 0 | 180909099482 | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2017-06-18 | 2017-06-29 | 2017-06-29 | 2017-06-29 |  | 2017-06-29 | تأخرصرف المستحقات المالية |  | 49.5604 | 25.3897 | منجز | No
2100078993 | جامعة الملك سعود | توريد وتركيب | ذات اولوية متوسطة | 4217829 | 210891.45 | 1659840 | 1659840 | 1010077408 | لا | 0 | 201001100263 | ايقاف كلي | تكلفة العمل المنجز | 87 | 87 | 2020-06-29 | 2020-12-23 | 2022-04-15 | 2022-04-15 |  |  | لا يوجد تأخير |  |  |  | Failed | No
2100004546 | جامعة الملك خالد | تشييد | ذات اولوية عالية وعاجلة | 153034498 | 7651724.9 | 153034498 | 153034498 | 2051037631 | لا | 0 | 180909086824 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2011-03-27 | 2014-11-03 | 2020-06-19 | 2020-06-19 | 2014-11-03 |  | تأخرصرف المستحقات المالية |  | 42.8114 | 18.1027 | منجز | No
2100005876 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2264000 | 113200 | 0 | 0 | 1010252537 | لا | 0 |  | لم يبدأ | التكلفة المفوترة | 15 | 100 | 2013-10-31 | 2015-01-25 | 2022-12-31 | 2022-12-31 |  |  | اخرى |  | 42.9095 | 23.8972 | Failed | No
2100061865 | شركة المياه الوطنية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 34647850 | 1732392.5 | 19639194.36 | 19639194.36 | 2050011871 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2012-10-03 | 2015-03-08 | 2020-08-20 | 2020-08-20 | 2015-03-08 |  | لا يوجد تأخير |  | 39.1903 | 21.5651 | منجز | No
2100031323 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 18565420.68 | 928271.034 | 14580506.68 | 13998515.53 | 2050018834 | لا | 0 |  | مسحوب | التكلفة المفوترة | 88 | 100 | 2014-01-15 | 2016-04-04 | 2019-04-19 | 2019-04-19 |  |  | ضعف كفاءة المقاول الفنية |  | 48.9668 | 28.4872 | مسحوب | No
2100093796 | جامعة الملك سعود | تشييد | ذات اولوية عالية | 4761220 | 238061 | 4761220 | 4554900 | 1010094443 | لا | 0 | 190509132162 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2017-11-10 | 2018-11-09 | 2020-12-26 | 2020-12-26 | 2018-11-09 |  | تصاريح أعمال التنفيذ |  | 46.7098 | 24.6275 | منجز | No
2100006425 | جامعة الطائف | تشييد | ذات اولوية متوسطة | 16294490 | 814724.5 | 16294490 | 12395706.26 | 4031041927 | لا | 0 | 180709035068 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 98 | 100 | 2017-10-22 | 2018-04-21 | 2019-01-13 | 2019-01-13 | 2018-04-21 |  | لا يوجد تأخير |  | 41.6382 | 21.2199 | منجز | No
2100087861 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 58947852.79 | 2947392.6395 | 33214220.37 | 32622962.72 | 4030185958 | لا | 0 | 180709019712 | مسحوب | تكلفة العمل المنجز | 75 | 100 | 2013-07-07 | 2015-06-27 | 2024-12-31 | 2024-12-31 |  |  | تأخرصرف المستحقات المالية |  | 39.7178 | 24.4844 | مسحوب | No
2100092466 | شركة المياه الوطنية / منطقة تبوك | تشييد | ذات اولوية منخفضة | 9888000 | 494400 | 7787957.4 | 7787957.4 | 1010014082 | لا | 0 | 180909089378 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 94.7 | 93.7 | 2017-11-12 | 2020-10-10 | 2020-12-20 | 2020-12-20 | 2020-10-10 |  | لا يوجد تأخير |  | 38.5313 | 27.6206 | منجز | No
2100194003 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 166855 | 8342.75 | 166855 | 0 | 4603146410 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-09-22 | 2021-06-13 | 2021-06-13 | 2021-06-13 | 2021-06-13 |  |  |  | 41.665 | 19.5325 | منجز | Yes
2100194025 | أمانة / العاصمة المقدسة | أخرى | ذات اولوية عالية وعاجلة | 6103020 | 305151 | 0 | 0 | 4030142592 | لا | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 47 | 67 | 2019-12-13 | 2022-01-31 | 2023-01-31 | 2023-01-31 |  |  |  |  | 39.3684 | 22.1508 | Failed | No
2100049486 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 17393901 | 869695.05 | 4536707 | 4536707 | 1010006004 | لا | 0 | 190401060817 | جاري | اخرى | 80 | 89 | 2019-07-29 | 2021-01-19 | 2022-03-30 | 2022-03-30 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5731 | 16.883 | Failed | No
2100000394 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 1196770 | 59838.5 | 92802 | 92802 | 5000974200 | لا | 0 |  | مسحوب | التكلفة المفوترة | 85 | 100 | 2009-03-02 | 2010-02-19 | 2022-12-28 | 2022-12-28 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0165 | 30.9619 | مسحوب | No
2100090436 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 6999350.58 | 349967.529 | 6970996.52 | 6970996.52 | 4032027295 | لا | 0 | 181001212325 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-06-30 | 2020-06-29 | 2020-06-29 | 2020-06-29 | 2020-06-29 |  | ضعف كفاءة المقاول الفنية |  | 40.4201 | 21.2794 | منجز | No
2100194655 | أمانة / الطائف | تصميم | ذات اولوية متوسطة | 2689500 | 134475 | 1651500 | 1651500 | 1010325732 | لا | 0 | 181001187115 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 97 | 100 | 2018-08-28 | 2021-08-12 | 2021-10-01 | 2021-10-01 | 2021-08-12 |  |  |  | 40.4511 | 21.2747 | منجز | No
2100078212 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 34778339 | 1738916.95 | 14674820.54 | 14674820.54 | 2050022550 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 75.5 | 100 | 2013-09-18 | 2015-09-07 | 2023-03-31 | 2023-03-31 |  |  | ضعف كفاءة المقاول الفنية | أخرى | 44.2476 | 26.3177 | Failed | No
2100063641 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4198450 | 209922.5 | 42008 | 0 | 1010188984 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 62 | 100 | 2015-06-27 | 2016-09-19 | 2021-03-29 | 2021-03-29 |  |  | ضعف كفاءة المقاول الفنية |  | 46.2751 | 24.4616 | مسحوب | Yes
2100008083 | وزارة الدفاع / الإدارة الهندسية والاشغال بالخدمات الصحية | تشييد | ذات اولوية متوسطة | 6376115 | 318805.75 | 6303785.5 | 6303785.5 | 1131020873 | لا | 0 | 181201509347 | جاري | الكميات التي تم تركيبها | 91 | 100 | 2018-12-03 | 2019-07-23 | 2023-02-14 | 2023-02-14 |  |  | عدم وجود مبالغ في البنود تغطي الأعمال المرصودة |  | 44.0207 | 26.4008 | متأخر | No
2100023645 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1274700 | 63735 | 1274700 | 1274700 | 4032015171 | لا | 0 | 200401075545 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-09-12 | 2020-03-30 | 2020-03-30 | 2020-03-30 | 2020-03-30 |  |  |  | 40.8047 | 20.9441 | منجز | No
2100072693 | أمانة / تبوك | تشييد | ذات اولوية عالية وعاجلة | 72589748.53 | 3629487.4265 | 45073629 | 21510460 | 5950005891 | لا | 0 | 200309024852 | جاري | الكميات التي تم تركيبها | 98 | 95.6 | 2019-10-29 | 2023-02-27 | 2023-02-27 | 2023-02-27 |  |  |  |  | 36.5346 | 28.3776 | منتظم | No
2100024312 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 7286800 | 364340 | 5666257.46 | 4403879.7 | 1010160688 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 22 | 20 | 2019-03-23 | 2021-03-12 | 2022-02-09 | 2022-02-09 | 2021-03-12 | [5 empty] | منجز | No
2100023704 | أمانة / الباحة | تشييد | ذات اولوية عالية | 2071800 | 103590 | 1157108 | 909216 | 5802012454 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 55.85 | 100 | 2015-11-21 | 2016-11-09 | 2022-08-01 | 2022-08-01 | 2016-11-09 |  | تأخرصرف المستحقات المالية |  | 41.4721 | 20.0159 | منجز | No
2100039480 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 7938460 | 396923 | 7938460 | 7938460 | 5805009876 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-02-03 | 2021-01-11 | 2021-12-02 | 2021-12-02 | 2021-01-11 |  |  |  | 41.3883 | 20.3871 | منجز | No
2100055112 | شركة المياه الوطنية | تشييد | ذات اولوية عالية | 980500 | 49025 | 1034700 | 646650 | 1011023221 | لا | 0 | 190909021276 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 94 | 100 | 2018-01-15 | 2018-07-15 | 2019-12-10 | 2019-12-10 | 2018-07-15 |  | لا يوجد تأخير |  | 49.5604 | 25.3897 | منجز | No
2100051365 | أمانة / تبوك | تشييد | ذات اولوية عالية | 872203.74 | 43610.187 | 872204 | 872204 | 4650060073 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-12-13 | 2016-11-30 | 2016-12-07 | 2016-12-07 | 2016-11-30 |  | اخرى |  | 36.5596 | 28.4462 | منجز | No
2100067561 | أمانة / جازان | تشييد | ذات اولوية عالية وعاجلة | 2414890 | 120744.5 | 1975050 | 1975050 | 5906012983 | لا | 0 | 181109277458 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-11-17 | 2019-11-12 | 2021-10-10 | 2021-10-10 | 2019-11-12 |  | ضعف كفاءة المقاول الفنية |  | 42.5776 | 16.9165 | منجز | No
2100078536 | جامعة الملك سعود | توريد وتركيب | ذات اولوية عالية | 157500 | 7875 | 157500 | 157500 | 1010277570 | لا | 0 | 201001095295 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-06-28 | 2020-08-26 | 2020-08-26 | 2020-08-26 | 2020-08-26 |  | لا يوجد تأخير |  |  |  | منجز | No
2100082073 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 1520840.41 | 76042.0205 | 541755.4 | 541755.4 | 5808013465 | لا | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 59 | 100 | 2014-09-15 | 2016-07-24 | 2022-12-30 | 2022-12-30 |  |  | أوامر سامية |  | 41.2457 | 19.9451 | Failed | No
2100090790 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 1620000 | 81000 | 842400 | 842400 | 5950031639 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-08-13 | 2021-09-02 | 2021-06-07 | 2021-06-07 | 2021-09-02 |  | اخرى |  | 44.2322 | 17.5579 | منجز | No
2100085304 | أمانة / العاصمة المقدسة | إشراف | ذات اولوية متوسطة | 3506715 | 175335.75 | 3407674 | 3407674 | 1010319312 | لا | 0 | 180909103061 | جاري الاستلام الإبتدائي | مدفوعات ساعات العمل | 88.73 | 88.73 | 2018-03-15 | 2021-03-14 | 2021-11-05 | 2021-11-05 |  |  | اخرى |  | 39.8929 | 21.3502 | Failed | No
2100056862 | شركة المياه الوطنية / منطقة الباحة | إشراف | ذات اولوية عالية وعاجلة | 1332000 | 66600 | 1323200.69 | 1323200.69 | 4031087359 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 99.3 | 100 | 2018-11-21 | 2020-11-21 | 2020-11-20 | 2020-11-20 | 2020-11-21 |  | لا يوجد تأخير |  | 41.3662 | 20.0495 | منجز | No
2100086693 | الجامعة الاسلامية بالمدينة المنورة | تشييد | ذات اولوية عالية | 45037175 | 2251858.75 | 29237079 | 29237079 | 4650001707 | لا | 0 | 190309014742 | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-11-29 | 2016-02-07 | 2022-10-31 | 2022-10-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.5654 | 24.4807 | متأخر | No
2100044354 | وزارة الشـؤون الاسلامية والدعوة والارشاد | تشييد | ذات اولوية عالية | 1343979.06 | 67198.953 | 767035 | 0 | 1010222879 | لا | 0 | 201009150864 | جاري | الكميات التي تم تركيبها | 75 | 100 | 2018-06-27 | 2020-06-10 | 2021-02-28 | 2021-02-28 |  |  | تأخرصرف المستحقات المالية |  | 42.8123 | 25.8588 | Failed | Yes
2100101640 | وكالة / الإسكان | تشييد | ذات اولوية متوسطة | 240663227.78 | 12033161.389 | 190096647.83 | 190096647.83 | 1010006362 | لا | 0 |  | مسحوب | منهجية القيمة المكتسبة | 84 | 100 | 2012-04-30 | 2014-04-20 | 2022-12-31 | 2022-12-31 |  |  | ضعف كفاءة المقاول الفنية | أخرى | 45.3525 | 25.8912 | مسحوب | No
2100103250 | أمانة / الرياض | دراسة الجدوى | ذات اولوية متوسطة | 1498016 | 74900.8 | 41750 | 0 | 4030192494 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-08-21 00:59 | 2016-08-10 00:59 | 2016-08-10 | 2016-08-10 | 2016-08-10 00:59 |  | ضعف كفاءة المقاول الفنية |  |  |  | منجز | Yes
2100020812 | وزارة الشـؤون الاسلامية والدعوة والارشاد | تشييد | ذات اولوية عالية | 964000 | 48200 | 0 | 0 | 5855033786 | لا | 0 | 201009176735 | جاري | الكميات التي تم تركيبها | 99 | 100 | 2018-05-30 | 2019-03-30 | 2021-05-01 | 2021-05-01 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.5366 | 18.2507 | Failed | No
2100072052 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 39210518 | 1960525.9 | 35081651.08 | 34595833.43 | 5950006647 | لا | 0 | 181109248477 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 96 | 100 | 2015-06-18 | 2021-08-17 | 2022-09-11 | 2022-09-11 | 2021-08-17 |  | اخرى |  | 44.2828 | 17.5559 | منجز | No
2100005751 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 675405 | 33770.25 | 675405 | 675405 | 1043292489 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2019-11-07 | 2020-03-11 | 2020-03-11 | 2020-03-11 | 2020-03-11 |  | لا يوجد تأخير |  |  |  | منجز | No
2100084081 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 53739999 | 2686999.95 | 47968817 | 47968817 | 5900008127 | لا | 0 | 180701020745 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-08-21 | 2016-04-02 | 2021-02-06 | 2021-02-06 | 2016-04-02 |  |  |  | 42.4703 | 18.1748 | منجز | No
2100006646 | رئاسة الحرس الملكي | تشييد | ذات اولوية عالية وعاجلة | 84380922.05 | 4219046.1025 | 60100609.52 | 60100609.52 | 1010007315 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 84.5 | 85 | 2018-11-28 | 2023-10-10 | 2023-10-10 | 2023-10-10 |  |  |  |  | 46.6925 | 24.655 | منتظم | No
2100052522 | جامعة جازان | تشييد | ذات اولوية عالية | 3911964 | 195598.2 | 2322846.75 | 2322846.75 | 1010276168 | لا | 0 | 191101300425 | جاري | الكميات التي تم تركيبها | 60 | 100 | 2019-10-10 | 2020-06-30 | 2023-06-30 | 2023-06-30 |  |  | اخرى |  | 42.6215 | 16.9314 | Failed | No
2100074012 | وزارة المالية - الحرمين | إشراف | ذات اولوية عالية وعاجلة | 1915335445 | 45000000 | 1232506438 | 1221356060 | 1010076578 | لا | 0 |  | جاري | مدفوعات ساعات العمل | 74 | 74 | 2013-02-02 | 2016-02-01 | 2026-06-30 | 2026-06-30 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.8257 | 21.4229 | خدمات عامة | No
2100042976 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 4553325 | 227666.25 | 4369081.5 | 4369081.5 | 2050093648 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2019-10-21 | 2020-10-21 | 2021-03-09 | 2021-03-09 | 2020-10-21 |  | اخرى |  |  |  | منجز | No
2100021873 | أمانة / الرياض | دراسة الجدوى | ذات اولوية متوسطة | 13716000 | 685800 | 41980 | 0 | 1010372072 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-11-22 00:59 | 2018-10-19 00:59 | 2018-10-19 | 2018-10-19 | 2018-10-19 00:59 |  | اخرى |  |  |  | منجز | Yes
2100028663 | شركة المياه الوطنية / منطقة القصيم | تصميم | ذات اولوية عالية | 4467662.5 | 223383.125 | 4500000 | 4500000 | 1010348048 | لا | 0 | 180709020475 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 97 | 100 | 2011-06-28 | 2012-04-27 | 2019-12-25 | 2019-12-25 | 2012-04-27 |  | لا يوجد تأخير |  | 43.9864 | 26.3353 | منجز | No
2100007556 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 4740217.3 | 237010.865 | 3594990.04 | 3594990.04 | 1010134079 | لا | 0 |  | مسحوب | التكلفة المفوترة | 76 | 100 | 2014-11-26 | 2016-08-17 | 2021-09-15 | 2021-09-15 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | مسحوب | No
2100018546 | الهيئة العامة للموانئ | إشراف | ذات اولوية عالية وعاجلة | 2830291 | 141514.55 | 2830291 | 2830291 | 1010153458 | لا | 0 |  | جاري | مدفوعات ساعات العمل | 100 | 100 | 2019-03-02 | 2021-09-02 | 2022-10-22 | 2022-10-22 |  |  | لا يوجد تأخير |  | 38.0699 | 24.0815 | خدمات عامة | No
2100106610 | الرئاسة العامة لهيئة الأمر بالمعروف والنهي عن المنكر | تشييد | ذات اولوية متوسطة | 20994684 | 1049734.2 | 20994684 | 20994684 | 1011009562 | لا | 0 | 190509101849 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-03-13 | 2015-11-03 | 2022-05-31 | 2022-05-31 | 2015-11-03 |  | تأخرصرف المستحقات المالية |  | 44.2028 | 17.5257 | منجز | No
2100048101 | أمانة / جازان | تشييد | ذات اولوية عالية | 1098550 | 54927.5 | 0 | 0 | 1116008659 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 0 | 100 | 2015-10-13 | 2016-10-01 | 2019-09-09 | 2019-09-09 |  |  | اخرى |  | 42.0265 | 17.7178 | مسحوب | No
2100015702 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2100972 | 105048.6 | 0 | 0 | 4031073709 | لا | 0 |  | فسخ العقد | اخرى | 50 | 100 | 2009-02-07 | 2009-12-24 | 2009-12-24 | 2009-12-24 |  |  | اخرى |  | 44.7813 | 20.4716 | مسحوب | No
2100052275 | مدينة الملك سعود الطبية | دراسة الجدوى |  | 17624250 | 881212.5 | 0 | 0 | 0 |  | 0 |  | جاري | تكلفة العمل المنجز | 29 | 100 | 2020-03-23 00:59 | 2023-03-23 00:59 |  |  |  |  | موافقات |  |  |  | خدمات عامة | No
2100094290 | وزارة التجارة | دراسة الجدوى | ذات اولوية عالية وعاجلة | 3085680 | 154284 | 2864590.74 | 2864590.74 | 1010348048 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 75 | 90 | 2018-03-26 | 2020-09-25 | 2022-10-11 | 2022-10-11 |  |  | اخرى |  |  |  | خدمات عامة | No
2100057201 | رئاسة أمن الدولة / قوات الأمن الخاصة | تشييد | ذات اولوية عالية وعاجلة | 2398415.25 | 119920.7625 | 2185112.03 | 2185112.03 | 1010286523 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-10-18 | 2021-04-19 | 2021-04-19 | 2021-04-19 | 2021-04-19 |  | اخرى |  | 40.2541 | 20.1619 | منجز | No
2100065483 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 939340 | 46967 | 404300 | 404300 | 5951001646 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 42 | 100 | 2014-03-16 | 2014-12-21 | 2014-12-21 | 2014-12-21 |  |  | ضعف كفاءة المقاول الفنية |  | 37.2199 | 25.9476 | مسحوب | No
2100032211 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 15774666.96 | 788733.348 | 15583980.48 | 15583980.48 | 4031069720 | لا | 0 | 180709030012 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2017-05-07 | 2018-05-02 | 2022-06-30 | 2022-06-30 | 2018-05-02 |  | تأخرصرف المستحقات المالية |  | 39.1677 | 21.5008 | منجز | No
2100023590 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2423149.75 | 121157.4875 | 1668414 | 1668414 | 4031030655 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 89 | 100 | 2010-05-29 | 2011-05-18 | 2023-02-02 | 2023-02-02 |  |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | مسحوب | No
2100093155 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 3099836.25 | 154991.8125 | 2749950 | 2749950 | 1010259143 | لا | 0 |  | جاري | تكلفة العمل المنجز | 100 | 100 | 2019-01-12 | 2020-11-19 | 2020-11-19 | 2020-11-19 |  |  | اخرى |  | 46.0938 | 24.7147 | Failed | No
2100056221 | وزارة التجارة | دراسة الجدوى | ذات اولوية عالية وعاجلة | 2678000 | 133900 | 1457701.33 | 1457701.33 | 1010325199 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 39 | 52 | 2019-02-25 | 2021-02-24 | 2022-11-30 | 2022-11-30 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  |  |  | خدمات عامة | No
2100041764 | شركة المياه الوطنية / المنطقة الشرقية | إشراف | ذات اولوية عالية | 8218224 | 410911.2 | 5923882.51 | 5796937.51 | 2051063103 | لا | 0 | 200501066546 | جاري | التكلفة المفوترة | 73.63 | 100 | 2019-06-17 | 2021-10-16 | 2023-08-06 | 2023-08-06 |  |  | لا يوجد تأخير |  | 49.6292 | 25.3979 | خدمات عامة | No
2100041646 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 25783176.55 | 1289158.8275 | 18131634.15 | 18131634.15 | 1010099661 | لا | 0 |  | مسحوب | التكلفة المفوترة | 75 | 100 | 2014-10-25 | 2017-01-12 | 2021-10-13 | 2021-10-13 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | مسحوب | No
2100073522 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 9382927 | 469146.35 | 4623148.53 | 4623148.53 | 5950010293 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-08-14 | 2015-08-15 | 2020-12-30 | 2020-12-30 | 2015-08-15 |  | اخرى |  | 44.2311 | 17.5626 | منجز | No
2100096821 | جامعة الملك سعود | تشييد | ذات اولوية متوسطة | 3592193 | 179609.65 | 3592192.8 | 3592192.8 | 1010188861 | لا | 0 | 210201081404 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-02-11 | 2019-12-11 | 2020-10-22 | 2020-10-22 | 2019-12-11 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 46.7098 | 24.6275 | منجز | No
2100032281 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2990184.55 | 149509.2275 | 146744.67 | 0 | 1010237336 | لا | 0 |  | مسحوب | التكلفة المفوترة | 7 | 100 | 2013-06-21 | 2015-09-04 | 2023-11-15 | 2023-11-15 |  |  | ضعف كفاءة المقاول الفنية |  | 41.4779 | 20.0185 | مسحوب | Yes
2100018152 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | تشييد | ذات اولوية عالية | 71554615 | 3577730.75 | 2660952.69 | 0 | 1010233574 | لا | 0 | 181001213005 | جاري | تكلفة العمل المنجز | 17.2 | 24.75 | 2019-06-12 | 2024-04-12 | 2024-04-12 | 2024-04-12 |  |  | اخرى |  | 42.7302 | 18.3003 | متأخر | Yes
2100027580 | جامعة نجران | تشييد | ذات اولوية عالية وعاجلة | 80000000 | 4000000 | 57727671 | 57727671 | 2066001761 | لا | 0 | 181209511021 | جاري | الكميات التي تم تركيبها | 80 | 100 | 2014-11-04 | 2017-01-10 | 2022-12-29 | 2022-12-29 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 44.2341 | 17.5757 | Failed | No
2100081760 | أمانة / الجوف | تشييد | ذات اولوية متوسطة | 2552350 | 127617.5 | 0 | 0 | 3550027471 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 0 | 100 | 2015-10-22 | 2016-10-16 | 2016-10-17 | 2016-10-17 |  |  | تأخرصرف المستحقات المالية |  | 37.6236 | 31.0839 | مسحوب | No
2100057746 | شركة المياه الوطنية / منطقة القصيم | تشييد | ذات اولوية عالية وعاجلة | 39666520 | 1983326 | 31953763.52 | 26757738.14 | 2050003338 | لا | 0 | 180701014805 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 95.42 | 100 | 2018-09-11 | 2020-08-20 | 2022-01-30 | 2022-01-30 | 2020-08-20 |  | ضعف كفاءة المقاول الفنية |  | 43.9553 | 26.3508 | منجز | No
2100086715 | وزارة التجارة | تشييد | ذات اولوية عالية | 8549303 | 427465.15 | 1978775 | 1978775 | 1010224125 | لا | 0 | 181101362419 | جاري | منهجية القيمة المكتسبة | 52 | 48.04 | 2019-02-25 | 2021-02-24 | 2022-11-30 | 2022-11-30 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 44.4245 | 24.5291 | منتظم | No
2100081104 | أمانة / تبوك | تشييد | ذات اولوية عالية | 1622225 | 81111.25 | 556400 | 411354 | 3550025722 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 34 | 100 | 2015-05-20 | 2016-05-14 | 2016-05-14 | 2016-05-14 |  |  | ضعف كفاءة المقاول الفنية |  | 36.6004 | 28.3834 | مسحوب | No
2100108286 | الهيئة العامة للموانئ | توريد وتركيب | ذات اولوية عالية وعاجلة | 31048690 | 1552434.5 | 21752271 | 21752271 | 1010159212 | لا | 0 | 191101344579 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-06-26 | 2020-03-02 | 2022-06-01 | 2022-06-01 | 2020-03-02 |  | اخرى |  | 42.1862 | 16.7105 | منجز | No
2100073441 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 2271456.5 | 113572.825 | 1441044 | 1441044 | 4031054258 | لا | 0 |  | جاري | اخرى | 62 | 62 | 2014-06-17 | 2015-11-30 | 2017-02-06 | 2017-02-06 |  |  |  | أخرى | 39.3781 | 21.8982 | Failed | No
2100003813 | شركة المياه الوطنية / منطقة جازان | إشراف | ذات اولوية عالية وعاجلة | 4914000 | 245700 | 3992769.9 | 3992769.9 | 4030275039 | لا | 0 | 190201038177 | جاري | التكلفة المفوترة | 76.72 | 100 | 2019-03-12 | 2020-08-24 | 2022-07-31 | 2022-07-31 |  |  | لا يوجد تأخير |  | 42.9389 | 16.6059 | خدمات عامة | No
2100095255 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 83772675.08 | 4188633.754 | 51729911.64 | 39876127.42 | 1116001737 | لا | 0 | 180809063956 | جاري | منهجية القيمة المكتسبة | 90.7 | 100 | 2014-11-26 | 2017-10-24 | 2023-04-15 | 2023-04-15 |  |  | اخرى |  | 42.9095 | 23.8972 | متأخر | No
2100001971 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 84703482 | 4235174.1 | 70418067.87 | 69541789.71 | 1010014477 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 87.94 | 100 | 2018-01-25 | 2021-01-25 | 2022-04-01 | 2022-04-01 |  |  | لا يوجد تأخير |  | 46.6275 | 24.8333 | Failed | No
2100001632 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 39736384.3 | 1986819.215 | 34400522.71 | 23658862.58 | 1010014477 | لا | 0 |  | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 99.78 | 100 | 2019-04-01 | 2021-04-01 | 2022-05-24 | 2022-05-24 |  |  | لا يوجد تأخير |  | 46.7098 | 24.6275 | Failed | No
2100079564 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2905038 | 145251.9 | 457278.18 | 457278.18 | 1010252898 | لا | 0 |  | مسحوب | التكلفة المفوترة | 26 | 100 | 2014-08-21 | 2015-12-08 | 2016-05-23 | 2016-05-23 |  |  | ضعف كفاءة المقاول الفنية |  | 45.2591 | 25.2379 | مسحوب | No
2100013893 | وزارة التعليم | تشييد | ذات اولوية عالية | 3196092 | 159804.6 | 2250836 | 2250836 | 1010018153 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 85 | 100 | 2014-05-01 | 2015-04-26 | 2021-07-27 | 2021-07-27 | 2015-04-26 |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | منجز | No
2100016446 | وزارة التعليم | تشييد | ذات اولوية عالية | 3144319 | 157215.95 | 2366196 | 2366196 | 1010191039 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-05-22 | 2019-05-04 | 2019-05-04 | 2019-05-04 | 2019-05-04 |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | منجز | No
2100005692 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 4894682.51 | 244734.1255 | 4617334.26 | 4617334.26 | 1115001965 | نعم | 1703630.4 | 190601014583 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99.05 | 100 | 2019-11-21 | 2021-05-06 | 2021-06-24 | 2021-06-24 | 2021-05-06 |  | لا يوجد تأخير |  | 47.1615 | 25.5646 | منجز | No
2100032712 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 45252502 | 2262625.1 | 17292041.45 | 6355709.99 | 1010072033 | لا | 0 | 190309035833 | مسحوب | منهجية القيمة المكتسبة | 19.14 | 32.95 | 2014-08-25 | 2017-07-23 | 2023-08-01 | 2023-08-01 |  |  | تصاريح أعمال التنفيذ |  | 46.1319 | 24.5998 | مسحوب | No
2100095513 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 2976180 | 148809 | 2957790.75 | 2957790.75 | 1010249593 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-09-12 | 2019-11-12 | 2019-05-15 | 2019-05-15 |  | 2019-11-12 | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100024054 | وزارة التجارة | تصميم | ذات اولوية عالية وعاجلة | 394800 | 19740 | 139180 | 139180 | 1010322156 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 90 | 90 | 2019-10-29 | 2020-02-29 | 2020-10-09 | 2020-10-09 |  | 2020-02-29 | لا يوجد تأخير |  |  |  | منجز | No
2100011701 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 3272182 | 163609.1 | 2833520.5 | 2833520.5 | 1010249593 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2020-03-16 | 2021-07-16 | 2022-02-01 | 2022-02-01 | 2021-07-16 |  | لا يوجد تأخير |  | 46.8403 | 24.8465 | منجز | No
2100192953 | وزارة الحرس الوطني / الشؤون الصحية | تشييد | ذات اولوية عالية وعاجلة | 9952272.65 | 497613.6325 | 0.01 | 0.01 | 4030174393 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 1 | 10 | 2020-11-05 | 2021-11-05 | 2022-12-31 | 2022-12-31 |  |  | اخرى |  | 39.3619 | 21.4243 | Failed | No
2100073743 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 15692906 | 784645.3 | 13971566 | 13971566 | 1010263814 | نعم | 18857355 | 180809040140 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 99.7 | 100 | 2017-11-15 | 2018-11-15 | 2023-02-03 | 2023-02-03 |  |  | عدم وجود كوادر كافية في الجهه لادارة المشروع |  | 38.2026 | 24.0038 | Failed | No
2100015503 | وزارة التعليم | تشييد | ذات اولوية عالية | 3196368 | 159818.4 | 2619315 | 2619315 | 1010018153 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-03-17 | 2015-03-12 | 2022-08-03 | 2022-08-03 | 2015-03-12 |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | منجز | No
2100006075 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 115899327.28 | 5794966.364 | 34726112.91 | 23583554.45 | 1010010466 | لا | 0 | 180809055234 | جاري | منهجية القيمة المكتسبة | 49.8 | 53.3 | 2014-06-29 | 2018-05-17 | 2024-08-28 | 2024-08-28 |  |  | تصاريح أعمال التنفيذ |  | 47.3091 | 24.164 | منتظم | No
2100009586 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 40242551.82 | 2012127.591 | 38844724.12 | 35998136 | 1010179797 | لا | 0 | 190609078604 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 97.2 | 100 | 2013-08-14 | 2016-07-12 | 2020-01-20 | 2020-01-20 |  | 2016-07-12 | لا يوجد تأخير |  | 44.7813 | 20.4716 | منجز | No
2100006366 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 5305500 | 265275 | 5305320 | 5305320 | 1010082898 | لا | 0 | 180709019860 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2014-03-19 | 2015-09-02 | 2020-08-23 | 2020-08-23 |  | 2015-09-02 | لا يوجد تأخير |  | 46.2928 | 24.4781 | منجز | No
2100073710 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 15000000 | 750000 | 14360300 | 14360300 | 1010188861 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2016-12-01 | 2017-12-01 | 2019-08-04 | 2019-08-04 | 2017-12-01 |  | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100097510 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 1386000 | 69300 | 1374010 | 1224950 | 1010061463 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-01-17 | 2020-01-17 | 2019-12-30 | 2019-12-30 |  | 2020-01-17 | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100074373 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 10138128.13 | 506906.4065 | 3681801.21 | 3681801.21 | 1010090099 | لا | 0 |  | مسحوب | التكلفة المفوترة | 45 | 100 | 2014-01-19 | 2016-05-11 | 2020-09-01 | 2020-09-01 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5604 | 25.3897 | مسحوب | No
2100024080 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 3875543 | 193777.15 | 1550217 | 716281.65 | 3350017202 | لا | 0 | 190801079090 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-02-08 | 2020-08-01 | 2020-08-02 | 2020-08-02 | 2020-08-01 |  |  |  | 41.7208 | 27.5114 | منجز | No
2100108231 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية وعاجلة | 62067404.93 | 3103370.2465 | 35418116.08 | 35418116.08 | 1010011949 | لا | 0 | 180709015523 | جاري | تكلفة العمل المنجز | 92 | 100 | 2013-05-01 | 2015-07-10 | 2023-12-31 | 2023-12-31 |  |  | تأخرصرف المستحقات المالية |  | 46.736 | 24.6522 | متأخر | No
2100040294 | وزارة الصحة / الرياض | تشييد | ذات اولوية متوسطة | 31966492 | 1598324.6 | 24953604 | 24953604 | 1010191039 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 95 | 2014-04-27 | 2016-04-26 | 2018-10-09 | 2018-10-09 | 2016-04-26 |  | تأخرصرف المستحقات المالية |  | 46.7098 | 24.6275 | منجز | No
2100002236 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 1699248.6 | 84962.43 | 1426342.1 | 1426342.1 | 1010183226 | نعم | 1647079.18 | 200101059056 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 87.69 | 100 | 2020-04-01 | 2021-03-21 | 2021-04-14 | 2021-04-14 |  | 2021-03-21 | لا يوجد تأخير |  | 43.6022 | 26.5646 | منجز | No
2100087135 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 3859800 | 192990 | 3797004 | 3290579.55 | 2051017029 | لا | 0 |  | منجز – استلام نهائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-09-16 | 2020-01-16 | 2019-10-14 | 2019-10-14 |  | 2020-01-16 | لا يوجد تأخير |  | 46.7098 | 24.6275 | منجز | No
2100194375 | أمانة / جدة | أخرى | ذات اولوية عالية وعاجلة | 31999800 | 1599990 | 20382533.75 | 20382533 | 1010156720 | لا | 0 | 200201097023 | جاري | تكلفة العمل المنجز | 92 | 100 | 2020-07-16 | 2022-07-16 | 2023-12-11 | 2023-12-11 |  |  |  |  | 39.1677 | 21.5008 | خدمات عامة | No
2100043120 | المؤسسة العامة للحبوب | تشييد | ذات اولوية عالية | 3194774 | 159738.7 | 3184735.38 | 3184735.38 | 1010895413 | لا | 0 | 190409057197 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-12-04 | 2019-11-23 | 2022-06-01 | 2022-06-01 | 2019-11-23 |  | اخرى |  | 46.8183 | 24.5967 | منجز | No
2100027963 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 15649347 | 782467.35 | 11442778 | 11442778 | 4030091106 | لا | 0 |  | جاري | تكلفة العمل المنجز | 100 | 100 | 2014-05-14 | 2016-05-13 | 2017-02-25 | 2017-02-25 |  |  | اخرى | أخرى | 39.8444 | 21.3294 | Failed | No
2100101555 | شركة المياه الوطنية / منطقة الرياض | تشييد | ذات اولوية عالية | 20645823 | 1032291.15 | 19816216.27 | 19816216.27 | 1010165068 | لا | 0 | 190402081855 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 96.09 | 100 | 2011-05-21 | 2014-04-18 | 2019-10-22 | 2019-10-22 |  | 2014-04-18 | لا يوجد تأخير |  | 45.3525 | 25.8912 | منجز | No
2100052496 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 12569499.19 | 628474.9595 | 12240354.13 | 12240354.13 | 1010221784 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-12-28 | 2019-04-13 | 2019-04-13 | 2019-04-13 | 2019-04-13 |  |  |  | 45.3525 | 25.8912 | منجز | No
2100002111 | وزارة التعليم | تشييد | ذات اولوية عالية | 10202328.61 | 510116.4305 | 8203028.39 | 8203028.39 | 1010081451 | لا | 0 |  | مسحوب | التكلفة المفوترة | 91 | 100 | 2013-10-28 | 2015-10-18 | 2021-11-15 | 2021-11-15 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | مسحوب | No
2100005051 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 52012657.72 | 2600632.886 | 45270616.47 | 45270616.47 | 1010210667 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-03-13 | 2020-10-18 | 2020-10-18 | 2020-10-18 | 2020-10-18 |  | أوامر تغيير | أخرى |  |  | منجز | No
2100058332 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2982774 | 149138.7 | 455307 | 455307 | 1010240529 | لا | 0 |  | مسحوب | التكلفة المفوترة | 43 | 100 | 2013-02-13 | 2014-08-08 | 2015-08-08 | 2015-08-08 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | مسحوب | No
2100066150 | وزارة التعليم | تشييد | ذات اولوية عالية | 25858723.24 | 1292936.162 | 18096312.76 | 18096312.76 | 1010099661 | لا | 0 |  | مسحوب | التكلفة المفوترة | 77 | 100 | 2013-12-01 | 2016-05-19 | 2021-10-18 | 2021-10-18 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | مسحوب | No
2100096670 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 906946 | 45347.3 | 353708.94 | 353708.94 | 1010255245 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 39 | 100 | 2009-12-16 | 2009-12-24 | 2018-07-10 | 2018-07-10 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 44.7813 | 20.4716 | مسحوب | No
2100195005 | أمانة / الطائف | دراسات هندسية | ذات اولوية متوسطة | 5497142.86 | 274857.143 | 5497142.56 | 5497142.56 | 4650047424 | لا | 0 | 190701073413 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-11-10 | 2021-10-30 | 2021-11-10 | 2021-11-10 | 2021-10-30 |  |  |  | 40.4511 | 21.2747 | منجز | No
2100021976 | مدينة الملك سعود الطبية | تشييد |  | 4827664 | 241383.2 | 1054082 | 1054082 | 1010094443 |  | 0 |  | جاري | تكلفة العمل المنجز | 60 | 100 | 2017-12-12 00:59 | 2018-06-07 00:59 |  |  |  |  | اخرى |  | 46.6906 | 24.6282 | Failed | No
2100195882 | الهيئة العامة للزكاة والدخل | ترميم | ذات اولوية عالية وعاجلة | 95087 | 4754.35 | 95087 | 95087 | 1010186502 | لا | 0 |  | منجز – استلام نهائي | تكلفة العمل المنجز | 100 | 100 | 2021-04-11 | 2021-04-22 | 2021-04-22 | 2021-04-22 |  | 2021-04-22 |  |  | 42.5579 | 16.9087 | منجز | No
2100005412 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 5255970.79 | 262798.5395 | 5255970.79 | 5255970.79 | 1128119385 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2018-06-06 | 2019-02-06 | 2022-03-11 | 2022-03-11 | 2019-02-06 |  |  |  | 45.2591 | 25.2379 | منجز | No
2100080673 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 17474000 | 873700 | 3575280 | 0 | 1010056094 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 20 | 100 | 2014-12-15 | 2016-12-04 | 2016-12-05 | 2016-12-05 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | مسحوب | Yes
2100027311 | أمانة / جازان | تشييد | ذات اولوية عالية | 4972999 | 248649.95 | 3727899 | 3727899 | 5911011013 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 75 | 100 | 2014-04-16 | 2015-04-11 | 2019-09-19 | 2019-09-19 |  |  | اخرى |  | 42.5729 | 16.8532 | مسحوب | No
2100025395 | وزارة الدفاع / الإدارة الهندسية والاشغال بالخدمات الصحية | تشييد | ذات اولوية متوسطة | 9444141 | 472207.05 | 5050105.26 | 5050105.26 | 1010212437 | لا | 0 | 200309092603 | جاري | الكميات التي تم تركيبها | 76 | 77 | 2019-11-11 | 2021-05-23 | 2023-02-03 | 2023-02-03 |  |  | تغيرات في نطاق المشروع |  | 43.9529 | 26.1665 | منتظم | No
2100058693 | هيئة المدن الصناعية ومناطق التقنية | تشييد | ذات اولوية متوسطة | 20386962 | 1019348.1 | 17142279 | 17142279 | 1010039430 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 94 | 100 | 2020-01-28 | 2022-01-27 | 2023-02-01 | 2023-02-01 |  |  | اخرى |  | 23.8702 | 47.262 | متأخر | No
2100018174 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 16835175 | 841758.75 | 16744109 | 16744109 | 4031074430 | لا | 0 | 191101122203 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 93.56 | 93.56 | 2019-07-11 | 2019-12-06 | 2020-06-05 | 2020-06-05 | 2019-12-06 |  |  |  | 39.839 | 21.4083 | منجز | No
2100057540 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 4745712 | 237285.6 | 4745712 | 4745712 | 2050093648 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2019-01-28 | 2020-01-28 | 2020-07-21 | 2020-07-21 | 2020-01-28 |  |  |  | 46.8595 | 24.7664 | منجز | No
2100020635 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية وعاجلة | 10229100 | 511455 | 10229100 | 10229100 | 2050093648 | لا | 0 |  | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-03-29 | 2021-09-29 | 2021-11-26 | 2021-11-26 |  |  |  |  | 46.8637 | 24.7688 | Failed | No
2100011476 | وزارة الثقافة | تشييد |  | 5922000 | 296100 | 3553200 | 3553200 | 1010423886 |  | 0 |  | جاري | منهجية القيمة المكتسبة | 99 | 100 | 2018-11-25 00:59 | 2019-05-24 00:59 | 2019-11-30 | 2019-11-30 |  |  | موافقات |  |  |  | Failed | No
2100016645 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 7478625 | 373931.25 | 4675794 | 4675794 | 1155000117 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2019-01-21 | 2021-08-11 | 2022-05-04 | 2022-05-04 | 2021-08-11 |  | اخرى |  | 45.2591 | 25.2379 | منجز | No
2100001411 | وزارة التعليم | تشييد | ذات اولوية عالية | 963381.6 | 48169.08 | 0 | 0 | 1114000090 | لا | 0 |  | جاري | التكلفة المفوترة | 1 | 100 | 2011-06-22 | 2012-01-10 | 2022-12-01 | 2022-12-01 |  |  | ضعف كفاءة المقاول الفنية |  | 45.313 | 24.0763 | Failed | No
2100057665 | وزارة التعليم | تشييد | ذات اولوية عالية | 1495670.8 | 74783.54 | 349755.4 | 349755.4 | 1132003289 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 33 | 100 | 2009-10-25 | 2010-06-04 | 2022-01-11 | 2022-01-11 |  |  | ضعف كفاءة المقاول الفنية |  | 45.313 | 24.0763 | مسحوب | No
2100011185 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 9029037.45 | 451451.8725 | 6868168 | 6868168 | 2511006868 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 99 | 100 | 2012-09-24 | 2014-06-16 | 2016-03-01 | 2016-03-01 | 2014-06-16 |  | ضعف كفاءة المقاول الفنية |  | 45.3525 | 25.8912 | منجز | No
2100010636 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 9923573.72 | 496178.686 | 5890541 | 5890541 | 1011008214 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-03-14 | 2020-07-07 | 2021-05-29 | 2021-05-29 | 2020-07-07 |  | تأخرصرف المستحقات المالية |  | 47.3078 | 24.1522 | منجز | No
2100003555 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 4752911.8 | 237645.59 | 3956230.91 | 3956230.91 | 1010134079 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-09-07 | 2016-05-29 | 2018-08-15 | 2018-08-15 | 2016-05-29 |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | منجز | No
2100011690 | وزارة التعليم | تشييد | ذات اولوية عالية | 11844029.37 | 592201.4685 | 8818492.37 | 8818492.37 | 1010051817 | لا | 0 |  | مسحوب | التكلفة المفوترة | 78 | 100 | 2015-04-08 | 2017-03-28 | 2021-08-22 | 2021-08-22 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | مسحوب | No
2100003592 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 3190306.91 | 159515.3455 | 1498567.28 | 1498567.28 | 1010174589 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-08-02 | 2017-01-23 | 2020-03-23 | 2020-03-23 | 2017-01-23 |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | منجز | No
2200237635 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 6736185.63 | 336809.2815 | 0 | 0 | 4030255980 | نعم | 109517203.4 |  | جاري | الكميات التي تم تركيبها | 0 | 0 | 2022-12-27 | 2023-08-24 | 2023-08-24 | 2023-08-24 |  |  |  |  | 40.9093 | 21.1013 | منتظم | No
2100037763 | وزارة النقل والخدمات اللوجستية / منطقة حائل | تشييد | ذات اولوية متوسطة | 5300000 | 265000 | 4768919.52 | 4768919.52 | 3357001499 | لا | 0 | 190709119864 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-02-12 | 2020-03-19 | 2020-03-19 | 2020-03-19 | 2020-03-19 |  | اخرى |  | 41.7793 | 27.4599 | منجز | No
2100070593 | وزارة النقل والخدمات اللوجستية / منطقة نجران | تشييد | ذات اولوية متوسطة | 31350430.95 | 1567521.5475 | 28185371.5 | 27669221.5 | 5950002770 | لا | 0 | 181109373782 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-06-04 | 2021-01-25 | 2021-11-03 | 2021-11-03 | 2021-01-25 |  | اخرى |  | 44.1677 | 17.5027 | منجز | No
2100070696 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 21469973 | 1073498.65 | 0 | 0 | 1010185409 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 0 | 0 | 2018-02-27 | 2019-08-11 | 2019-08-11 | 2019-08-11 |  |  | اخرى |  | 46.6299 | 25.1739 | مسحوب | No
2100054224 | وزارة النقل والخدمات اللوجستية / منطقة تبوك | تشييد | ذات اولوية متوسطة | 5865839.76 | 293291.988 | 0 | 0 | 1010147422 | نعم | 13006459 |  | ايقاف كلي | الكميات التي تم تركيبها | 6.09 | 100 | 2021-01-12 | 2021-11-07 | 2022-09-06 | 2022-09-06 |  |  | ضعف كفاءة المقاول الفنية |  | 37.5158 | 25.0682 | Failed | No
2100091965 | وزارة النقل والخدمات اللوجستية / منطقة القصيم | تشييد | ذات اولوية متوسطة | 93730229.95 | 4686511.4975 | 79722483 | 79722483 | 1010184457 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 85.4 | 100 | 2010-06-15 | 2013-10-07 | 2022-02-01 | 2022-02-01 |  |  | اخرى |  | 43.9783 | 26.22 | مسحوب | No
2100038393 | وزارة النقل والخدمات اللوجستية / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 60000000 | 3000000 | 35300762 | 35300762 | 2060002548 | لا | 0 | 181109360263 | مسحوب | الكميات التي تم تركيبها | 59 | 81 | 2013-12-08 | 2017-01-18 | 2017-01-18 | 2017-01-18 |  |  | اخرى |  | 48.4576 | 28.4153 | مسحوب | No
2100084276 | وزارة النقل والخدمات اللوجستية / منطقة المدينة المنورة | تشييد | ذات اولوية متوسطة | 14975930.24 | 748796.512 | 213913.84 | 213913.84 | 1010048595 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 1.43 | 1.54 | 2020-04-30 | 2021-04-21 | 2021-04-21 | 2021-04-21 |  |  | اخرى |  | 39.5514 | 24.4919 | مسحوب | No
2100038415 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | لم تعد تحتاجها الجهة | 14820000 | 741000 | 0 | 0 | 4030180242 | لا | 0 | 181109343737 | فسخ العقد | الكميات التي تم تركيبها | 77.45 | 77.45 | 2012-10-24 | 2015-09-20 | 2015-12-18 | 2015-12-18 |  |  | اخرى |  | 39.8322 | 21.4096 | مسحوب | No
2100053513 | وزارة النقل والخدمات اللوجستية / منطقة جازان | تشييد | ذات اولوية متوسطة | 6304000 | 315200 | 0 | 0 | 5855039588 | لا | 0 | 181001212082 | فسخ العقد | الكميات التي تم تركيبها | 7 | 100 | 2019-01-16 | 2020-04-02 | 2021-06-20 | 2021-06-20 |  |  | اخرى |  | 42.8248 | 16.7306 | مسحوب | No
2100094135 | وزارة النقل والخدمات اللوجستية / منطقة الباحة | تشييد | ذات اولوية متوسطة | 3920000 | 196000 | 3470526 | 3048693 | 4031042502 | لا | 0 | 181009162358 | مسحوب | الكميات التي تم تركيبها | 90.4 | 100 | 2013-11-08 | 2018-12-07 | 2018-12-07 | 2018-12-07 |  |  | ضعف كفاءة المقاول الفنية |  | 41.4713 | 20.0217 | مسحوب | No
2200233645 | وزارة النقل والخدمات اللوجستية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 134687972.85 | 6734398.6425 | 53431891.32 | 53431891.32 | 1010039430 | لا | 0 |  | ايقاف جزئي | تكلفة العمل المنجز | 48.5 | 67.48 | 2020-09-09 | 2023-03-12 | 2024-08-31 | 2024-08-31 |  |  |  |  | 50.045 | 26.3058 | متأخر | No
2100053664 | وزارة النقل والخدمات اللوجستية / منطقة القصيم | تشييد | ذات اولوية عالية | 25709575.12 | 1285478.756 | 3059861.4 | 3059861.4 | 1010011059 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 17.97 | 17.97 | 2014-08-18 | 2016-07-26 | 2016-07-26 | 2016-07-26 |  |  | اخرى |  | 43.9562 | 26.2095 | مسحوب | No
2100070825 | وزارة النقل والخدمات اللوجستية / منطقة جازان | تشييد | ذات اولوية منخفضة | 9599997 | 479999.85 | 1671230.75 | 1671230.75 | 1131014252 | لا | 0 | 180301000822 | فسخ العقد | الكميات التي تم تركيبها | 17.41 | 100 | 2018-07-19 | 2019-07-09 | 2021-06-17 | 2021-06-17 |  |  | المشروع ليس ذو أولوية في الوقت الحالي |  | 42.8443 | 16.9692 | مسحوب | No
2100100240 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 75746321 | 3787316.05 | 57279258.26 | 57279258.26 | 1010066115 | لا | 0 | 180901069352 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-12-02 | 2016-10-29 | 2021-08-09 | 2021-08-09 | 2016-10-29 |  |  |  | 42.4696 | 18.224 | منجز | No
2100053281 | وزارة النقل والخدمات اللوجستية / منطقة حائل | تشييد | ذات اولوية متوسطة | 76999999 | 3849999.95 | 48442811 | 48442811 | 2060002548 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 66.64 | 100 | 2012-11-24 | 2017-08-01 | 2017-08-01 | 2017-08-01 |  |  | اخرى |  | 41.8851 | 27.7805 | مسحوب | No
2100195753 | وزارة النقل والخدمات اللوجستية / منطقة الجوف | تشييد | ذات اولوية عالية وعاجلة | 85470791.45 | 4273539.5725 | 61538841.28 | 61538841.28 | 1010048595 | لا | 0 | 181109323577 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2011-08-13 | 2014-01-13 | 2022-07-06 | 2022-07-06 | 2014-01-13 |  |  |  | 38.8197 | 29.8712 | منجز | No
2100073183 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 85337575.92 | 4266878.796 | 68537336.27 | 68537336.27 | 4032026650 | لا | 0 | 180701021789 | جاري | الكميات التي تم تركيبها | 84.57 | 86.28 | 2015-01-14 | 2017-12-10 | 2022-12-22 | 2022-12-22 |  |  |  |  | 39.8459 | 21.4005 | منتظم | No
2100084022 | وزارة النقل والخدمات اللوجستية / منطقة الجوف | تشييد | ذات اولوية متوسطة | 60500000 | 3025000 | 33218831.8 | 33218831.8 | 3450000664 | لا | 0 | 181101275921 | جاري | تكلفة العمل المنجز | 74 | 100 | 2019-02-21 | 2020-08-05 | 2022-11-21 | 2022-11-21 |  |  |  |  | 37.2437 | 31.4171 | Failed | No
2100070453 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 74212740 | 3710637 | 37839286 | 37839286 | 4031046036 | لا | 0 | 181101276011 | جاري | الكميات التي تم تركيبها | 62.55 | 60.4 | 2019-02-14 | 2022-01-11 | 2023-11-19 | 2023-11-19 |  |  |  |  | 39.8812 | 21.3505 | منتظم | No
2100054025 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 78916835.7 | 3945841.785 | 71027342.4 | 71027342.4 | 4030170755 | لا | 0 | 190101001359 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-03-28 | 2020-11-06 | 2022-07-15 | 2022-07-15 | 2020-11-06 |  |  |  | 39.2267 | 21.5115 | منجز | No
2100038500 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 1564479.05 | 78223.9525 | 1313100 | 1313100 | 1017000955 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-01-30 | 2015-01-18 | 2022-06-30 | 2022-06-30 | 2015-01-18 |  | اخرى |  | 46.6775 | 24.6776 | منجز | No
2100083882 | وزارة النقل والخدمات اللوجستية / منطقة القصيم | تشييد | ذات اولوية متوسطة | 103347627.7 | 5167381.385 | 82811502.93 | 82811502.93 | 1129000453 | لا | 0 | 200409109430 | جاري | الكميات التي تم تركيبها | 82.5 | 89.17 | 2013-01-27 | 2016-12-13 | 2023-06-19 | 2023-06-19 |  |  |  |  | 43.8783 | 26.2998 | متأخر | No
2100072984 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية منخفضة | 41991514.95 | 2099575.7475 | 778226 | 778226 | 1010009590 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 2.5 | 2.5 | 2019-08-29 | 2021-01-11 | 2021-01-11 | 2021-01-11 |  |  | المشروع ليس ذو أولوية في الوقت الحالي |  | 46.6887 | 24.5851 | مسحوب | No
2100198380 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية عالية وعاجلة | 79847321.4 | 3992366.07 | 30121621 | 30121621 | 1010009590 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 54.26 | 44.2 | 2020-04-28 | 2021-10-11 | 2023-11-30 | 2023-11-30 |  |  |  |  | 43.8511 | 21.2473 | متأخر | No
2100054062 | وزارة النقل والخدمات اللوجستية / منطقة الباحة | تشييد | ذات اولوية متوسطة | 95568197.15 | 4778409.8575 | 56634739.43 | 56634739.43 | 1010066115 | لا | 0 | 181009148143 | جاري | الكميات التي تم تركيبها | 62 | 100 | 2014-08-28 | 2022-06-02 | 2023-07-18 | 2023-07-18 |  |  |  |  | 41.3912 | 19.8406 | Failed | No
2100038813 | وزارة النقل والخدمات اللوجستية / منطقة القصيم | تشييد | ذات اولوية متوسطة | 76115554.1 | 3805777.705 | 68056437.77 | 68056437.77 | 1132001941 | لا | 0 | 200609159206 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2012-10-23 | 2015-09-20 | 2022-10-26 | 2022-10-26 | 2015-09-20 |  |  |  | 43.5222 | 25.8517 | منجز | No
2100021291 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية منخفضة | 70703677.42 | 3535183.871 | 642174.22 | 642174.22 | 1010152168 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2006-11-20 | 2016-02-05 | 2021-02-04 | 2021-02-04 | 2016-02-05 |  |  |  | 42.2755 | 18.2132 | منجز | No
2100005961 | وزارة التعليم | تشييد | ذات اولوية عالية | 9324206 | 466210.3 | 3175415.46 | 0 | 1116004360 | لا | 0 |  | مسحوب | التكلفة المفوترة | 45 | 100 | 2013-01-02 | 2014-10-05 | 2023-12-15 | 2023-12-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | Yes
2100038183 | وزارة النقل والخدمات اللوجستية / منطقة الحدود الشمالية | تشييد | ذات اولوية عالية | 85295442 | 4264772.1 | 76765886.53 | 76765886.53 | 1010090968 | لا | 0 | 181101224672 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-01-17 | 2022-01-15 | 2022-01-15 | 2022-01-15 | 2022-01-15 |  |  |  | 40.6227 | 31.1235 | منجز | No
2100102896 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | ترميم | ذات اولوية عالية | 103583739 | 5179186.95 | 89800408.64 | 89800408.64 | 1010017123 | لا | 0 | 191001179639 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2020-04-22 | 2022-03-31 | 2022-11-30 | 2022-11-30 | 2022-03-31 |  | لا يوجد تأخير |  | 39.845 | 21.4015 | منجز | No
2100198741 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية عالية وعاجلة | 93341685.15 | 4667084.2575 | 21602876 | 19003996 | 5950010121 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 35.08 | 46.72 | 2020-08-26 | 2022-02-08 | 2023-04-30 | 2023-04-30 |  |  |  |  | 43.4142 | 20.8947 | متأخر | No
2100060922 | وزارة النقل والخدمات اللوجستية / منطقة حائل | تشييد | ذات اولوية متوسطة | 40961863 | 2048093.15 | 32451473.1 | 30345200 | 1010188861 | لا | 0 | 181109353278 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2013-10-23 | 2020-07-15 | 2020-10-11 | 2020-10-11 | 2020-07-15 |  |  |  | 41.7527 | 27.5897 | منجز | No
2100053793 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 194861900.95 | 9743095.0475 | 106277757 | 98632312 | 2051010618 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 68.13 | 64 | 2019-09-01 | 2021-08-09 | 2023-11-30 | 2023-11-30 |  |  |  |  | 45.5439 | 23.5151 | منتظم | No
2100008713 | وزارة النقل والخدمات اللوجستية / منطقة الجوف | تشييد | ذات اولوية عالية | 85470791.45 | 4273539.5725 | 61538841.28 | 61538841.28 | 1010048595 | لا | 0 | 181109323577 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2011-08-13 | 2014-01-13 | 2022-07-06 | 2022-07-06 | 2014-01-13 |  |  |  | 38.8404 | 29.8481 | منجز | No
2100041366 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 73478000 | 3673900 | 0 | 0 | 1010033701 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2007-07-22 | 2018-12-30 | 2018-12-30 | 2018-12-30 | 2018-12-30 |  |  |  | 42.511 | 18.1385 | منجز | No
2100007431 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | ترميم | ذات اولوية عالية | 13200000 | 660000 | 13200000 | 3927131.72 | 5950000060 | لا | 0 | 200101058773 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-04-29 | 2020-12-29 | 2021-04-24 | 2021-04-24 | 2020-12-29 |  | ضعف كفاءة المقاول الفنية |  | 40.4534 | 20.2772 | منجز | No
2100073021 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 148145912.2 | 7407295.61 | 36339403.2 | 36339403.2 | 3550019957 | لا | 0 | 180701030261 | مسحوب | الكميات التي تم تركيبها | 30 | 100 | 2012-09-29 | 2018-07-25 | 2018-07-26 | 2018-07-26 |  |  | اخرى |  | 42.5359 | 18.2478 | مسحوب | No
2100090510 | وزارة النقل والخدمات اللوجستية / منطقة القصيم | تشييد | ذات اولوية متوسطة | 309247374.09 | 15462368.7045 | 255011072.43 | 255011072.43 | 1010069549 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 77.6 | 75.1 | 2019-01-16 | 2022-04-12 | 2025-09-02 | 2025-09-02 |  |  |  |  | 43.5965 | 26.1051 | منتظم | No
2100070674 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 112732787.9 | 5636639.395 | 18681141.63 | 18681141.63 | 5950010109 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 16.39 | 100 | 2015-02-18 | 2018-01-15 | 2023-01-15 | 2023-01-15 |  |  | ضعف كفاءة المقاول الفنية |  | 40.0283 | 21.5007 | مسحوب | No
2100195775 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 75051570.25 | 3752578.5125 | 0 | 0 | 1010066115 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 1.01 | 15 | 2021-02-21 | 2023-02-12 | 2024-02-28 | 2024-02-28 |  |  |  |  | 41.082 | 19.129 | متأخر | No
2100053852 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 98000000 | 4900000 | 35350555 | 31496661 | 5855000147 | لا | 0 | 190701132738 | جاري | الكميات التي تم تركيبها | 48.5 | 63 | 2019-12-04 | 2024-08-20 | 2024-08-20 | 2024-08-20 |  |  |  |  | 42.6144 | 18.1631 | متأخر | No
2100013042 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 2697663.42 | 134883.171 | 2697663.42 | 2697663.42 | 3350039892 | لا | 0 | 19120016027004 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-01-27 | 2020-07-19 | 2022-03-06 | 2022-03-06 | 2020-07-19 |  |  |  | 40.4669 | 25.9933 | منجز | No
2100053351 | وزارة النقل والخدمات اللوجستية / منطقة الباحة | تشييد | ذات اولوية متوسطة | 637777769.9 | 31888888.495 | 57785124.57 | 57785124 | 1010152168 | لا | 0 | 181009170300 | جاري | الكميات التي تم تركيبها | 95.15 | 100 | 2011-09-13 | 2015-07-30 | 2022-10-26 | 2022-10-26 |  |  | ضعف كفاءة المقاول الفنية |  | 41.4713 | 20.0217 | Failed | No
2100070652 | وزارة النقل والخدمات اللوجستية / منطقة المدينة المنورة | تشييد | ذات اولوية متوسطة | 68079467.73 | 3403973.3865 | 61271324 | 61271324 | 4650009788 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-11-16 | 2016-10-14 | 2022-06-26 | 2022-06-26 | 2016-10-14 |  | اخرى |  | 39.4248 | 24.6023 | منجز | No
2100094592 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 226919565 | 11345978.25 | 206552132.82 | 206552132.82 | 5855028046 | لا | 0 | 181109350809 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-03-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 | 2018-07-21 |  |  |  | 42.4642 | 18.486 | منجز | No
2100070335 | وزارة النقل والخدمات اللوجستية / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 188457675.17 | 9422883.7585 | 63424825.5 | 63424825.5 | 2051010618 | لا | 0 | 499000011080500 | جاري | الكميات التي تم تركيبها | 39.93 | 51.85 | 2013-03-20 | 2020-03-02 | 2023-12-11 | 2023-12-11 |  |  |  |  | 49.9498 | 26.5637 | متأخر | No
2100094286 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | لم تعد تحتاجها الجهة | 505173000 | 25258650 | 0 | 0 | 4030007516 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 91.5 | 100 | 2007-09-15 | 2010-08-12 | 2015-02-16 | 2015-02-16 |  |  | ضعف كفاءة المقاول الفنية |  | 39.8535 | 21.4149 | مسحوب | No
2100013915 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 2499268.59 | 124963.4295 | 2374305.16 | 2374305.16 | 3357001499 | لا | 0 | 210209025177 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 93 | 100 | 2019-04-03 | 2021-05-23 | 2020-09-24 | 2020-09-24 | 2021-05-23 |  |  |  | 40.4669 | 25.9933 | منجز | No
2100077486 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | لم تعد تحتاجها الجهة | 7812699.87 | 390634.9935 | 6299189.68 | 6299189.68 | 4031042502 | لا | 0 | 180701021316 | فسخ العقد | الكميات التي تم تركيبها | 79.34 | 79.34 | 2013-10-23 | 2015-09-30 | 2018-07-01 | 2018-07-01 |  |  | اخرى |  | 39.9156 | 21.4206 | مسحوب | No
2100070486 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | لم تعد تحتاجها الجهة | 44650000 | 2232500 | 28499.95 | 28499.95 | 4030021594 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 0.7 | 0.7 | 2013-08-15 | 2015-07-23 | 2015-07-23 | 2015-07-23 |  |  | اخرى |  | 39.8388 | 21.3697 | مسحوب | No
2100070615 | وزارة النقل والخدمات اللوجستية / منطقة القصيم | تشييد | ذات اولوية متوسطة | 42801864.77 | 2140093.2385 | 28009069.54 | 28009069.54 | 1134000719 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 67.42 | 100 | 2015-03-10 | 2018-02-04 | 2021-12-01 | 2021-12-01 |  |  |  |  | 43.9233 | 26.2569 | مسحوب | No
2100037321 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية منخفضة | 68726385.56 | 3436319.278 | 61853747 | 61853747 | 1010149483 | لا | 0 | 181109368543 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-08-13 | 2020-06-19 | 2022-11-25 | 2022-11-25 | 2020-06-19 |  |  |  | 46.6889 | 24.71 | منجز | No
2100198601 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 37615023.71 | 1880751.1855 | 24004350 | 20375354 | 1116005202 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 76.8 | 82.18 | 2020-04-29 | 2022-04-06 | 2023-05-17 | 2023-05-17 |  |  |  |  | 44.1569 | 24.4296 | متأخر | No
2100064540 | أمانة / حائل | تشييد | ذات اولوية عالية | 539133 | 26956.65 | 0 | 0 | 3351010628 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-08-05 | 2020-07-29 | 2021-04-25 | 2021-04-25 | 2020-07-29 |  |  |  | 41.7251 | 27.488 | منجز | No
2100070862 | وزارة النقل والخدمات اللوجستية / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 79430975 | 3971548.75 | 29105018.19 | 29105018.19 | 1010202928 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 37.11 | 100 | 2015-02-22 | 2020-04-16 | 2020-04-16 | 2020-04-16 |  |  | اخرى |  | 50.0681 | 26.4358 | مسحوب | No
2100025454 | وزارة النقل والخدمات اللوجستية / منطقة المدينة المنورة | تشييد | ذات اولوية متوسطة | 46795448 | 2339772.4 | 10105247.2 | 10105247.2 | 1116000094 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 24.06 | 100 | 2013-07-17 | 2017-11-11 | 2017-11-11 | 2017-11-11 |  |  | اخرى |  | 39.5153 | 24.4367 | مسحوب | No
2100038161 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 73999175.25 | 3699958.7625 | 16974987.8 | 16974987.8 | 4031018104 | لا | 0 | 181001219654 | جاري | الكميات التي تم تركيبها | 30.37 | 28.24 | 2019-01-16 | 2020-12-24 | 2024-01-24 | 2024-01-24 |  |  |  |  | 39.7052 | 21.6346 | منتظم | No
2100021173 | وزارة النقل والخدمات اللوجستية / منطقة القصيم | تشييد | ذات اولوية منخفضة | 55115898.8 | 2755794.94 | 41018676.02 | 41018676.02 | 1134000719 | لا | 0 | 181109368776 | جاري | الكميات التي تم تركيبها | 89 | 100 | 2015-03-10 | 2018-12-04 | 2022-03-04 | 2022-03-04 |  |  | المشروع ليس ذو أولوية في الوقت الحالي |  | 43.5315 | 25.8625 | متأخر | No
2100070571 | وزارة النقل والخدمات اللوجستية / منطقة المدينة المنورة | تشييد | ذات اولوية متوسطة | 67787187.93 | 3389359.3965 | 54028034.5 | 54028034.5 | 4650007949 | نعم | 34038583 |  | جاري | الكميات التي تم تركيبها | 88.04 | 90.22 | 2020-04-25 | 2022-04-02 | 2023-05-28 | 2023-05-28 |  |  |  |  | 39.6127 | 24.4866 | منتظم | No
2100037925 | وزارة النقل والخدمات اللوجستية / منطقة تبوك | تشييد | ذات اولوية متوسطة | 60000000 | 3000000 | 4828970.33 | 4828970.33 | 1010055791 | لا | 0 | 181201479785 | ايقاف كلي | الكميات التي تم تركيبها | 7.48 | 100 | 2019-02-28 | 2020-08-12 | 2022-09-04 | 2022-09-04 |  |  |  |  | 36.0536 | 28.8997 | Failed | No
2100026460 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 91340787.3 | 4567039.365 | 26898417 | 26898417 | 4031046036 | لا | 0 | 181209529613 | جاري | الكميات التي تم تركيبها | 42.03 | 39.1 | 2019-02-21 | 2022-01-18 | 2023-12-18 | 2023-12-18 |  |  |  |  | 39.9476 | 21.4212 | منتظم | No
2100094522 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | لم تعد تحتاجها الجهة | 75000000 | 3750000 | 31722074.74 | 31722074.74 | 1116000094 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 42.19 | 100 | 2011-11-28 | 2014-05-01 | 2023-05-07 | 2023-05-07 |  |  | ضعف كفاءة المقاول الفنية |  | 40.3872 | 21.2173 | مسحوب | No
2100070276 | وزارة النقل والخدمات اللوجستية / منطقة جازان | تشييد | ذات اولوية متوسطة | 59194733.64 | 2959736.682 | 8549095 | 8549095 | 4031038036 | لا | 0 | 181109341928 | فسخ العقد | الكميات التي تم تركيبها | 15 | 100 | 2011-12-04 | 2014-05-07 | 2021-05-08 | 2021-05-08 |  |  | اخرى |  | 42.4247 | 17.444 | مسحوب | No
2100037822 | وزارة النقل والخدمات اللوجستية / منطقة المدينة المنورة | تشييد | ذات اولوية متوسطة | 93385862.26 | 4669293.113 | 34038583 | 34038583 | 1010108612 | لا | 0 | 200101067515 | مسحوب | الكميات التي تم تركيبها | 32 | 100 | 2012-08-27 | 2016-07-14 | 2022-04-02 | 2022-04-02 |  |  | اخرى |  | 39.5424 | 24.6034 | مسحوب | No
2100054180 | وزارة النقل والخدمات اللوجستية / منطقة الباحة | تشييد | ذات اولوية عالية | 76973662 | 3848683.1 | 38728461.6 | 346479.71 | 1010152168 | لا | 0 | 181109333755 | فسخ العقد | الكميات التي تم تركيبها | 55 | 100 | 2010-08-26 | 2016-02-24 | 2016-02-24 | 2016-02-24 |  |  | اخرى |  | 41.4475 | 20.0542 | مسحوب | No
2100083860 | وزارة النقل والخدمات اللوجستية / منطقة جازان | تشييد | ذات اولوية متوسطة | 164364337.55 | 8218216.8775 | 117819498.4 | 117819498.4 | 1010152168 | لا | 0 | 181109327408 | مسحوب | الكميات التي تم تركيبها | 90.69 | 100 | 2010-11-25 | 2013-04-28 | 2019-12-03 | 2019-12-03 |  |  | اخرى |  | 42.8297 | 17.617 | مسحوب | No
2100070630 | وزارة النقل والخدمات اللوجستية / منطقة حائل | تشييد | ذات اولوية متوسطة | 48582418.2 | 2429120.91 | 44514658.6 | 39735560 | 1010069549 | لا | 0 | 180909101848 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2012-09-18 | 2017-07-24 | 2021-06-24 | 2021-06-24 | 2017-07-24 |  |  |  | 41.6954 | 27.5349 | منجز | No
2100094662 | وزارة النقل والخدمات اللوجستية / منطقة الحدود الشمالية | تشييد | ذات اولوية متوسطة | 30404500 | 1520225 | 5028196.49 | 4884216.95 | 1010099930 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 17.3 | 17.3 | 2014-03-20 | 2021-03-27 | 2021-05-03 | 2021-05-03 |  |  | اخرى |  | 41.0253 | 30.9615 | مسحوب | No
2100196280 | وزارة النقل والخدمات اللوجستية / منطقة الجوف | تشييد | ذات اولوية عالية | 52168460.29 | 2608423.0145 | 942421.5 | 942421.5 | 2050022550 | لا | 0 | 181109369322 | فسخ العقد | تكلفة العمل المنجز | 1.72 | 100 | 2015-09-13 | 2017-10-10 | 2019-03-24 | 2019-03-24 |  |  |  |  | 38.2519 | 30.3984 | مسحوب | No
2100037601 | وزارة النقل والخدمات اللوجستية / منطقة الباحة | تشييد | ذات اولوية متوسطة | 84172895 | 4208644.75 | 4485450 | 0 | 1010202928 | لا | 0 | 180301000906 | مسحوب | الكميات التي تم تركيبها | 59.5 | 100 | 2018-08-13 | 2021-07-11 | 2021-07-25 | 2021-07-25 |  |  | ضعف كفاءة المقاول الفنية |  | 41.53 | 19.9641 | مسحوب | Yes
2100038091 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 121734153.65 | 6086707.6825 | 101044714.05 | 101044714.05 | 2050022550 | لا | 0 | 181109315707 | مسحوب | الكميات التي تم تركيبها | 85.91 | 100 | 2009-12-22 | 2012-05-25 | 2023-07-31 | 2023-07-31 |  |  | ضعف كفاءة المقاول الفنية |  | 39.7418 | 21.1276 | مسحوب | No
2100056733 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | ترميم | ذات اولوية عالية | 209884456.95 | 10494222.8475 | 39459013.19 | 31246978.59 | 1010017123 | لا | 0 | 200101053512 | جاري | الكميات التي تم تركيبها | 47 | 100 | 2020-05-31 | 2022-05-30 | 2022-04-18 | 2022-04-18 |  |  | لا يوجد تأخير |  | 42.943 | 18.0442 | Failed | No
2100077324 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية منخفضة | 57784500 | 2889225 | 17442442 | 17442442 | 5900000115 | لا | 0 | 181109368364 | فسخ العقد | الكميات التي تم تركيبها | 36.1 | 100 | 2014-07-31 | 2017-01-01 | 2020-11-04 | 2020-11-04 |  |  | اخرى |  | 42.6007 | 18.2427 | مسحوب | No
2200223086 | وزارة النقل والخدمات اللوجستية / منطقة المدينة المنورة | تشييد | ذات اولوية متوسطة | 9041141.13 | 452057.0565 | 1276833.5 | 1276833.5 | 4650007949 | نعم | 40846426 |  | جاري | الكميات التي تم تركيبها | 50.17 | 66.3 | 2022-02-06 | 2023-01-30 | 2023-01-30 | 2023-01-30 |  |  |  |  | 39.2073 | 24.7208 | متأخر | No
2100038054 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 37624230 | 1881211.5 | 24737959 | 19702194 | 4030150094 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 80 | 90 | 2019-01-17 | 2020-07-09 | 2023-02-28 | 2023-02-28 |  |  |  | أخرى | 46.8185 | 24.9241 | متأخر | No
2100070081 | وزارة النقل والخدمات اللوجستية / منطقة الحدود الشمالية | تشييد | ذات اولوية متوسطة | 20791527.2 | 1039576.36 | 1781424 | 1614600 | 1010009352 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 33.93 | 33.93 | 2014-02-16 | 2019-09-07 | 2021-05-03 | 2021-05-03 |  |  | اخرى |  | 41.0809 | 30.9218 | مسحوب | No
2100054003 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية منخفضة | 5101492 | 255074.6 | 774177 | 774177 | 1131014252 | لا | 0 | 180301001014 | فسخ العقد | الكميات التي تم تركيبها | 17.56 | 100 | 2018-06-05 | 2019-12-19 | 2019-12-19 | 2019-12-19 |  |  | اخرى |  | 42.5636 | 18.2226 | مسحوب | No
2100038850 | وزارة النقل والخدمات اللوجستية / منطقة الجوف | تشييد | ذات اولوية متوسطة | 49623500 | 2481175 | 33885596 | 33885596 | 1010080784 | لا | 0 | 191201131509 | مسحوب | تكلفة العمل المنجز | 86 | 100 | 2010-07-14 | 2012-12-14 | 2012-12-14 | 2012-12-14 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.685 | 29.7996 | مسحوب | No
2100053782 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 125970373.07 | 6298518.6535 | 50771646 | 50771646 | 1010008118 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 43.19 | 100 | 2014-11-06 | 2017-10-02 | 2023-09-13 | 2023-09-13 |  |  | ضعف كفاءة المقاول الفنية |  | 39.8711 | 21.4445 | مسحوب | No
2100094102 | وزارة النقل والخدمات اللوجستية / منطقة جازان | تشييد | ذات اولوية عالية | 136284074 | 6814203.7 | 34770244 | 34770244 | 4031038036 | لا | 0 | 181109358325 | فسخ العقد | الكميات التي تم تركيبها | 25.61 | 100 | 2011-12-12 | 2014-05-15 | 2021-05-05 | 2021-05-05 |  |  | اخرى |  | 43.0486 | 17.0379 | مسحوب | No
2100006241 | وزارة النقل والخدمات اللوجستية / منطقة جازان | تشييد | ذات اولوية متوسطة | 71363250.22 | 3568162.511 | 44585934.22 | 44585934.22 | 5900007895 | لا | 0 | 181109361362 | جاري | الكميات التي تم تركيبها | 74.1 | 100 | 2013-10-29 | 2016-09-24 | 2022-10-30 | 2022-10-30 |  |  |  |  | 42.6071 | 16.8742 | Failed | No
2100038776 | وزارة النقل والخدمات اللوجستية / منطقة المدينة المنورة | تشييد | ذات اولوية متوسطة | 50825657.17 | 2541282.8585 | 25711690 | 25711690 | 1010108612 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 50.49 | 100 | 2012-07-17 | 2017-05-22 | 2017-05-22 | 2017-05-22 |  |  | اخرى |  | 38.2068 | 24.025 | مسحوب | No
2100070033 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 125815544.1 | 6290777.205 | 57598209 | 57598209 | 1010017021 | لا | 0 | 181009195447 | مسحوب | الكميات التي تم تركيبها | 46.78 | 100 | 2014-11-13 | 2020-02-10 | 2020-02-10 | 2020-02-10 |  |  | ضعف كفاءة المقاول الفنية |  | 46.4399 | 25.1422 | مسحوب | No
2100054154 | وزارة النقل والخدمات اللوجستية / منطقة تبوك | تشييد | ذات اولوية متوسطة | 167130535.99 | 8356526.7995 | 63083599.93 | 63083599.93 | 3550019957 | لا | 0 | 181109359069 | جاري | الكميات التي تم تركيبها | 59.43 | 66.68 | 2014-07-16 | 2020-08-24 | 2023-06-20 | 2023-06-20 |  |  |  |  | 36.5623 | 28.352 | متأخر | No
2100059931 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية منخفضة | 104499999 | 5224999.95 | 36455143 | 36455143 | 1010039430 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 49.5 | 46.5 | 2019-02-12 | 2021-01-19 | 2023-10-30 | 2023-10-30 |  |  | المشروع ليس ذو أولوية في الوقت الحالي |  | 46.7581 | 24.8021 | منتظم | No
2100053756 | وزارة النقل والخدمات اللوجستية / منطقة الباحة | تشييد | ذات اولوية متوسطة | 65978398 | 3298919.9 | 59380690 | 59380690 | 1010017123 | لا | 0 | 181101221669 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-01-16 | 2022-04-10 | 2022-04-10 | 2022-04-10 | 2022-04-10 |  |  |  | 41.4713 | 20.0217 | منجز | No
2100037936 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 198276126.93 | 9913806.3465 | 118152174 | 118152174 | 1010048595 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 69.5 | 75.7 | 2019-04-24 | 2021-03-31 | 2023-07-31 | 2023-07-31 |  |  |  |  | 45.8957 | 24.0368 | متأخر | No
2100094253 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 79000000 | 3950000 | 37413610 | 37413610 | 5950010121 | لا | 0 | 180501008096 | جاري | الكميات التي تم تركيبها | 55.34 | 56.27 | 2018-07-29 | 2020-07-06 | 2023-08-25 | 2023-08-25 |  |  |  |  | 39.808 | 21.1497 | منتظم | No
2100070324 | وزارة النقل والخدمات اللوجستية / منطقة القصيم | تشييد | ذات اولوية عالية | 80007380.3 | 4000369.015 | 72006642.27 | 72006642.27 | 1116001737 | لا | 0 | 180909103917 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2012-10-24 | 2016-09-08 | 2022-08-30 | 2022-08-30 | 2016-09-08 |  |  |  | 43.4837 | 26.2078 | منجز | No
2100195856 | وزارة النقل والخدمات اللوجستية / منطقة الحدود الشمالية | تشييد | ذات اولوية عالية | 45462787.83 | 2273139.3915 | 33258396 | 33258396 | 1010127437 | لا | 0 | 200201040477 | جاري | الكميات التي تم تركيبها | 84.17 | 82.12 | 2020-04-30 | 2022-04-08 | 2023-09-16 | 2023-09-16 |  |  |  |  | 43.3985 | 29.6905 | منتظم | No
2100077383 | وزارة النقل والخدمات اللوجستية / منطقة جازان | تشييد | ذات اولوية متوسطة | 86593492.23 | 4329674.6115 | 59173520.8 | 59173520.8 | 1010152168 | لا | 0 | 181109298889 | فسخ العقد | الكميات التي تم تركيبها | 94.5 | 100 | 2009-07-04 | 2012-05-31 | 2021-12-29 | 2021-12-29 |  |  | اخرى |  | 43.1311 | 17.3392 | مسحوب | No
2100053163 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية منخفضة | 147464229 | 7373211.45 | 8594808 | 8594808 | 1010213394 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 7 | 7 | 2014-12-31 | 2017-11-26 | 2017-11-26 | 2017-11-26 |  |  | اخرى |  | 47.1918 | 25.5763 | مسحوب | No
2100038150 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 9599933 | 479996.65 | 3627466 | 3627466 | 5855039588 | لا | 0 | 180301001452 | فسخ العقد | الكميات التي تم تركيبها | 39.79 | 100 | 2018-06-07 | 2019-11-19 | 2019-11-19 | 2019-11-19 |  |  | اخرى |  | 42.4713 | 18.3971 | مسحوب | No
2100038253 | وزارة النقل والخدمات اللوجستية / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 11563315 | 578165.75 | 10407310 | 10407310 | 2050045542 | لا | 0 | 181109370728 | جاري | الكميات التي تم تركيبها | 94.98 | 100 | 2014-07-29 | 2016-01-12 | 2022-11-30 | 2022-11-30 |  |  |  |  | 49.6842 | 26.652 | Failed | No
2100070685 | وزارة النقل والخدمات اللوجستية / منطقة الباحة | تشييد | ذات اولوية عالية | 98109769 | 4905488.45 | 90000000 | 90000000 | 1010152168 | لا | 0 | 180909103615 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2010-12-30 | 2013-06-02 | 2022-10-01 | 2022-10-01 | 2013-06-02 |  | اخرى |  | 41.4841 | 20.0141 | منجز | No
2100038651 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية منخفضة | 19843635.22 | 992181.761 | 7089054 | 7089054 | 1010100318 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 41 | 41 | 2009-05-25 | 2012-09-28 | 2012-09-28 | 2012-09-28 |  |  | ضعف كفاءة المقاول الفنية |  | 46.5772 | 24.9095 | مسحوب | No
2100022256 | وزارة النقل والخدمات اللوجستية / منطقة جازان | تشييد | ذات اولوية عالية | 29452675.42 | 1472633.771 | 18486523 | 18486523 | 5900000115 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 75 | 100 | 2011-02-22 | 2013-07-26 | 2021-05-21 | 2021-05-21 |  |  | ضعف كفاءة المقاول الفنية |  | 43.0073 | 17.4872 | مسحوب | No
2100195996 | وزارة النقل والخدمات اللوجستية / منطقة الباحة | تشييد | ذات اولوية متوسطة | 329999994.56 | 16499999.728 | 146253680.21 | 146253680.21 | 5950010121 | لا | 0 |  | جاري | تكلفة العمل المنجز | 46.39 | 47.25 | 2020-04-09 | 2023-03-07 | 2024-04-09 | 2024-04-09 |  |  |  |  | 41.4713 | 20.0217 | منتظم | No
2100070394 | وزارة النقل والخدمات اللوجستية / منطقة جازان | تشييد | ذات اولوية متوسطة | 2691189.94 | 134559.497 | 1438985.44 | 1438985.44 | 1131014252 | لا | 0 | 180301001282 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-07-19 | 2020-06-26 | 2022-06-26 | 2022-06-26 | 2020-06-26 |  | اخرى |  | 42.8164 | 17.3443 | منجز | No
2100053900 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 167824136 | 8391206.8 | 31166386 | 31166386 | 1010080784 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 18.82 | 33 | 2014-05-10 | 2018-03-27 | 2018-03-27 | 2018-03-27 |  |  | اخرى |  | 42.4585 | 18.2773 | مسحوب | No
2100073135 | وزارة النقل والخدمات اللوجستية / منطقة جازان | تشييد | ذات اولوية متوسطة | 54283250.7 | 2714162.535 | 36481051 | 36481051 | 1010166750 | لا | 0 | 181009152086 | مسحوب | الكميات التي تم تركيبها | 74 | 100 | 2011-12-05 | 2014-05-08 | 2019-12-03 | 2019-12-03 |  |  | ضعف كفاءة المقاول الفنية |  | 43.2013 | 17.3182 | مسحوب | No
2100054596 | وزارة النقل والخدمات اللوجستية / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 199329655 | 9966482.75 | 84852569.41 | 84852569.41 | 1010039430 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 71.93 | 71.19 | 2018-12-13 | 2020-10-10 | 2023-09-02 | 2023-09-02 |  |  |  |  | 50.0178 | 26.2151 | منتظم | No
2100015131 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية وعاجلة | 78660474.9 | 3933023.745 | 31727380 | 31727380 | 4030044382 | لا | 0 | 190301083824 | جاري | الكميات التي تم تركيبها | 47.2 | 72.9 | 2019-09-01 | 2021-08-09 | 2023-04-05 | 2023-04-05 |  |  |  |  | 39.7072 | 21.342 | Failed | No
2100054261 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 80985250.5 | 4049262.525 | 14535734.5 | 14535734.5 | 4031018104 | لا | 0 | 181101256424 | جاري | الكميات التي تم تركيبها | 25.32 | 23.08 | 2019-01-22 | 2020-12-30 | 2024-06-17 | 2024-06-17 |  |  |  |  | 39.8247 | 21.4461 | منتظم | No
2100038382 | وزارة النقل والخدمات اللوجستية / منطقة نجران | تشييد | ذات اولوية متوسطة | 79246460 | 3962323 | 71321814 | 71321814 | 5950010121 | لا | 0 | 180801038679 | جاري | الكميات التي تم تركيبها | 99.2 | 100 | 2014-01-27 | 2022-03-07 | 2022-03-08 | 2022-03-08 |  |  |  |  | 44.1745 | 17.5998 | متأخر | No
2100026412 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 62367205 | 3118360.25 | 11811643 | 11811643 | 1010017123 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 19.2 | 19.2 | 2019-05-08 | 2021-04-27 | 2021-04-14 | 2021-04-14 |  |  | اخرى |  | 47.336 | 24.151 | مسحوب | No
2100077442 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 103961978 | 5198098.9 | 66742746 | 64833357 | 1010154882 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 74.8 | 100 | 2014-04-10 | 2016-03-18 | 2023-02-28 | 2023-02-28 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6757 | 24.7209 | Failed | No
2100038404 | وزارة النقل والخدمات اللوجستية / منطقة القصيم | تشييد | ذات اولوية متوسطة | 80270849.03 | 4013542.4515 | 71563952.78 | 71563952.78 | 1129000453 | لا | 0 | 180801061813 | جاري | الكميات التي تم تركيبها | 94 | 96.6 | 2011-06-07 | 2013-11-07 | 2023-01-25 | 2023-01-25 |  |  |  |  | 43.854 | 26.1357 | منتظم | No
2100053491 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 342229159.65 | 17111457.9825 | 308006243 | 308006243 | 4030170755 | لا | 0 | 180701029791 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-11-21 | 2017-10-07 | 2022-08-13 | 2022-08-13 | 2017-10-07 |  |  |  | 39.8338 | 21.4525 | منجز | No
2200223355 | وزارة النقل والخدمات اللوجستية / منطقة جازان | تشييد | ذات اولوية منخفضة | 27930769.05 | 1396538.4525 | 5555200 | 5555200 | 1010080784 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 23.23 | 100 | 2012-07-31 | 2016-06-16 | 2021-05-02 | 2021-05-02 |  |  |  |  | 43.02 | 16.95 | مسحوب | No
2100031651 | وزارة النقل والخدمات اللوجستية / منطقة الجوف | تشييد | ذات اولوية عالية وعاجلة | 110473792 | 5523689.6 | 79539759.84 | 79539759.84 | 1010056094 | لا | 0 | 180801040624 | مسحوب | تكلفة العمل المنجز | 92 | 100 | 2009-07-29 | 2012-06-26 | 2018-12-13 | 2018-12-13 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 40.1764 | 29.8344 | مسحوب | No
2100070416 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية عالية | 80000000 | 4000000 | 23208925.75 | 21673825.75 | 5855000147 | لا | 0 | 180401003839 | جاري | الكميات التي تم تركيبها | 34.98 | 42.96 | 2018-07-30 | 2021-11-10 | 2023-06-19 | 2023-06-19 |  |  |  |  | 42.6534 | 18.209 | متأخر | No
2100195893 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية عالية | 122018283.9 | 6100914.195 | 104131644 | 104131644 | 7001422075 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 85.88 | 100 | 2009-10-06 | 2012-09-03 | 2020-12-14 | 2020-12-14 |  |  |  |  | 42.7695 | 18.165 | مسحوب | No
2100053896 | وزارة النقل والخدمات اللوجستية / منطقة الباحة | تشييد | ذات اولوية متوسطة | 70132928.35 | 3506646.4175 | 30559534 | 30559534 | 5900007895 | لا | 0 | 180701021208 | جاري | الكميات التي تم تركيبها | 55 | 100 | 2014-08-03 | 2017-06-30 | 2023-09-16 | 2023-09-16 |  |  |  |  | 41.4718 | 20.0198 | Failed | No
2100037866 | وزارة النقل والخدمات اللوجستية / منطقة حائل | تشييد | ذات اولوية متوسطة | 31380876 | 1569043.8 | 16351602.95 | 10542599.01 | 3350000631 | لا | 0 | 190501004613 | جاري | تكلفة العمل المنجز | 87.04 | 100 | 2018-09-12 | 2019-12-27 | 2021-06-01 | 2021-06-01 |  |  |  |  | 41.7034 | 27.5564 | Failed | No
2100195941 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية عالية | 39888523 | 1994426.15 | 33189618 | 33189618 | 5860007938 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-08-05 | 2020-12-27 | 2022-01-10 | 2022-01-10 | 2020-12-27 |  |  |  | 42.0534 | 18.5474 | منجز | No
2100098792 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 60388982 | 3019449.1 | 43547660.5 | 43547660.5 | 5950010121 | لا | 0 | 180501008088 | جاري | الكميات التي تم تركيبها | 82.92 | 77.5 | 2018-08-27 | 2020-08-05 | 2022-12-21 | 2022-12-21 |  |  |  |  | 39.8399 | 21.3846 | متأخر | No
2100038080 | وزارة النقل والخدمات اللوجستية / منطقة الحدود الشمالية | تشييد | ذات اولوية متوسطة | 7827766.65 | 391388.3325 | 7075752 | 7075752 | 1010335103 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 97.25 | 100 | 2015-02-24 | 2017-02-01 | 2021-11-24 | 2021-11-24 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.6422 | 30.641 | مسحوب | No
2100083646 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 14131349.4 | 706567.47 | 12718214.5 | 12718214.5 | 4030141919 | لا | 0 | 190509037567 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-02-25 | 2020-02-02 | 2022-08-17 | 2022-08-17 | 2020-02-02 |  | اخرى |  | 39.8438 | 21.433 | منجز | No
2100015610 | وزارة الصحة / الرياض | تشييد | ذات اولوية متوسطة | 103050034 | 5152501.7 | 91368705 | 91368705 | 1010054806 | لا | 0 |  | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 95 | 100 | 2014-05-15 | 2016-04-14 | 2022-04-24 | 2022-04-24 |  |  | اخرى |  | 46.7098 | 24.6275 | متأخر | No
2100101835 | وزارة الصحة / الرياض | تشييد | ذات اولوية عالية وعاجلة | 11618889 | 580944.45 | 7175751 | 7175751 | 1018000245 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 62 | 100 | 2015-03-23 | 2016-09-22 | 2017-05-21 | 2017-05-21 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 46.7098 | 24.6275 | Failed | No
2100090963 | وزارة الصحة / ديوان الوزارة | تشييد | ذات اولوية عالية | 262280792.42 | 13114039.621 | 180440493.6 | 180440493.6 | 1010053925 | لا | 0 | 190309070455 | جاري | تكلفة العمل المنجز | 85.3 | 100 | 2012-06-23 | 2015-05-31 | 2023-03-07 | 2023-03-07 |  |  | تأخرصرف المستحقات المالية |  | 46.641 | 24.6061 | متأخر | No
2100028103 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية عالية | 49947873 | 2497393.65 | 29551384.3 | 29551384.3 | 5950005891 | لا | 0 | 200201034473 | جاري | الكميات التي تم تركيبها | 88.7 | 88.05 | 2020-04-30 | 2023-03-28 | 2023-03-28 | 2023-03-28 |  |  | اخرى |  | 42.5117 | 18.2465 | منتظم | No
2100006915 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 57644533.9 | 2882226.695 | 12793095.74 | 12293030.76 | 1010066115 | لا | 0 | 181109368486 | جاري | الكميات التي تم تركيبها | 37.56 | 48.94 | 2015-07-02 | 2017-12-02 | 2023-07-26 | 2023-07-26 |  |  |  |  | 39.8866 | 21.2906 | متأخر | No
2100039325 | وزارة النقل والخدمات اللوجستية / منطقة الجوف | تشييد | ذات اولوية متوسطة | 74802588.75 | 3740129.4375 | 53857818.72 | 53857818.72 | 1010048595 | لا | 0 | 180909102163 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2013-10-24 | 2016-09-19 | 2021-08-11 | 2021-08-11 | 2016-09-19 |  |  |  | 38.6242 | 30.0614 | منجز | No
2100102115 | وزارة الصحة / الرياض | تشييد | ذات اولوية متوسطة | 26984632 | 1349231.6 | 6169711 | 6169711 | 1018000245 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 25 | 90 | 2014-04-19 | 2019-01-23 | 2019-01-22 | 2019-01-22 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال | مخطط لسحبه وإعادة ترسيته | 45.313 | 24.0763 | Failed | No
2100101625 | وزارة الصحة / الرياض | تشييد | ذات اولوية متوسطة | 20733343 | 1036667.15 | 2474692 | 2474692 | 1118001009 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 18 | 90 | 2015-07-26 | 2017-07-25 | 2020-01-20 | 2020-01-20 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.9095 | 23.8972 | مسحوب | No
2100085190 | وزارة الصحة / الرياض | تشييد | ذات اولوية عالية | 57460042 | 2873002.1 | 21117975 | 21117975 | 1010006362 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 52 | 100 | 2015-09-05 | 2017-09-05 | 2017-09-05 | 2017-09-05 |  |  | تأخرصرف المستحقات المالية | مخطط لسحبه وإعادة ترسيته | 46.7098 | 24.6275 | Failed | No
2100093564 | وزارة الصحة / الرياض | تشييد | ذات اولوية متوسطة | 20347164 | 1017358.2 | 17186334 | 16065613 | 1010208729 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-05-06 | 2016-03-05 | 2019-03-20 | 2019-03-20 | 2016-03-05 |  | تأخرصرف المستحقات المالية |  | 45.2591 | 25.2379 | منجز | No
2100015853 | وزارة الصحة / الرياض | تشييد | ذات اولوية متوسطة | 28478084 | 1423904.2 | 21213369 | 21213369 | 1117001331 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 75 | 80 | 2015-04-08 | 2017-04-07 | 2022-10-05 | 2022-10-05 |  |  | تأخرصرف المستحقات المالية |  | 45.313 | 24.0763 | Failed | No
2100056464 | وزارة الصحة / الرياض | تشييد | ذات اولوية متوسطة | 22310833 | 1115541.65 | 17792411 | 17792411 | 1116005345 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 60 | 66 | 2016-03-06 | 2018-03-05 | 2023-03-02 | 2023-03-02 |  |  | تأخرصرف المستحقات المالية |  | 44.4412 | 24.5406 | Failed | No
2100083893 | وزارة النقل والخدمات اللوجستية / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 99999995 | 4999999.75 | 0 | 0 | 1010202928 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 15 | 21 | 2015-10-04 | 2017-09-11 | 2017-09-11 | 2017-09-11 |  |  | اخرى |  | 50.0771 | 26.3271 | مسحوب | No
2100061176 | وزارة النقل والخدمات اللوجستية / منطقة المدينة المنورة | تشييد | ذات اولوية متوسطة | 11997324.68 | 599866.234 | 4684126.29 | 4684126.29 | 1123001261 | نعم | 25142079.5 | 181109341744 | جاري | الكميات التي تم تركيبها | 47.76 | 66.23 | 2020-04-28 | 2023-08-10 | 2023-08-10 | 2023-08-10 |  |  |  |  | 39.3979 | 24.5799 | متأخر | No
2100021383 | وزارة النقل والخدمات اللوجستية / منطقة جازان | تشييد | ذات اولوية عالية | 89766561.09 | 4488328.0545 | 65362783.2 | 65362783.2 | 1010039430 | لا | 0 | 181109339208 | جاري | الكميات التي تم تركيبها | 95.8 | 100 | 2011-11-13 | 2014-04-29 | 2022-12-20 | 2022-12-20 |  |  | اخرى |  | 42.8297 | 17.617 | متأخر | No
2100021103 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 84542644.8 | 4227132.24 | 67408687.31 | 67408687.31 | 1010004737 | لا | 0 | 180701033883 | مسحوب | الكميات التي تم تركيبها | 79.98 | 100 | 2009-07-18 | 2012-06-14 | 2022-10-31 | 2022-10-31 |  |  | ضعف كفاءة المقاول الفنية |  | 39.805 | 21.376 | مسحوب | No
2100094651 | وزارة النقل والخدمات اللوجستية / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 90000000 | 4500000 | 51015720 | 51015720 | 2060002548 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 58.47 | 100 | 2013-08-12 | 2018-09-10 | 2018-08-10 | 2018-08-10 |  |  | اخرى |  | 48.887 | 25.9565 | مسحوب | No
2100051424 | أمانة / جازان | تشييد | لم تعد تحتاجها الجهة | 654900 | 32745 | 654900 | 654900 | 5950030529 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-08-12 | 2019-07-28 | 2019-07-29 | 2019-07-29 | 2019-07-28 |  | اخرى |  | 42.5802 | 16.8901 | منجز | No
2100078304 | وزارة الصحة / الرياض | تشييد | ذات اولوية متوسطة | 23081654 | 1154082.7 | 20049310 | 20049310 | 1116005345 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 72 | 100 | 2016-04-03 | 2018-04-02 | 2022-06-30 | 2022-06-30 |  |  | تأخرصرف المستحقات المالية |  | 44.4412 | 24.5406 | Failed | No
2100028674 | وزارة الصحة / الرياض | تشييد | ذات اولوية متوسطة | 39912965 | 1995648.25 | 27109263 | 27109263 | 5950011379 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 80 | 100 | 2014-01-29 | 2015-07-28 | 2016-01-12 | 2016-01-12 |  |  | اخرى |  | 45.313 | 24.0763 | Failed | No
2100040655 | وزارة الصحة / الرياض | تشييد | لم تعد تحتاجها الجهة | 12202532 | 610126.6 | 561600 | 5616 | 1116005371 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 8 | 100 | 2015-02-03 | 2016-02-03 | 2016-02-03 | 2016-02-03 |  |  | اخرى | مخطط لفسخ العقد | 45.3618 | 26.4953 | مسحوب | No
2100040493 | وزارة الصحة / الرياض | تشييد | ذات اولوية متوسطة | 1173625 | 58681.25 | 445117 | 445117 | 1010213896 | لا | 0 |  | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 90 | 100 | 2016-01-02 | 2016-04-02 | 2016-04-02 | 2016-04-02 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 46.7098 | 24.6275 | Failed | No
2100008610 | وزارة الصحة / ديوان الوزارة | ترميم | ذات اولوية متوسطة | 31784998 | 1589249.9 | 7956819 | 7956819 | 2050038009 | نعم | 14692334.6 | 180301000697 | مسحوب | الكميات التي تم تركيبها | 65 | 100 | 2018-07-24 | 2021-07-30 | 2021-12-31 | 2021-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7049 | 24.71 | مسحوب | No
2100070895 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 84251338 | 4212566.9 | 360000 | 360000 | 1010039430 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 1 | 35 | 2019-03-28 | 2020-09-08 | 2020-09-08 | 2020-09-08 |  |  | اخرى |  | 46.7392 | 24.6675 | مسحوب | No
2100061482 | وزارة النقل والخدمات اللوجستية / منطقة جازان | تشييد | ذات اولوية متوسطة | 62213830 | 3110691.5 | 49133146.4 | 40606208 | 1010210667 | لا | 0 | 180701021329 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-09-30 | 2017-08-15 | 2020-08-11 | 2020-08-11 | 2017-08-15 |  |  |  | 43.1311 | 17.3392 | منجز | No
2200223160 | وزارة النقل والخدمات اللوجستية / منطقة المدينة المنورة | تشييد | ذات اولوية متوسطة | 32811146.93 | 1640557.3465 | 29223670 | 29223670 | 1010184457 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 75 | 100 | 2011-06-22 | 2013-11-23 | 2011-11-23 | 2011-11-23 |  |  | ضعف كفاءة المقاول الفنية |  | 39.8469 | 23.2994 | مسحوب | No
2100070711 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 169632000 | 8481600 | 152668800 | 151518671 | 1010066115 | لا | 0 | 181109313307 | جاري | الكميات التي تم تركيبها | 94.4 | 100 | 2010-07-04 | 2012-12-05 | 2022-09-30 | 2022-09-30 |  |  |  |  | 47.3003 | 24.1787 | متأخر | No
2100198656 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية عالية وعاجلة | 95959026.45 | 4797951.3225 | 18884489 | 15003996 | 5950010121 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 35.95 | 37 | 2020-07-20 | 2021-01-12 | 2023-08-31 | 2023-08-31 |  |  |  |  | 43.8015 | 21.2369 | منتظم | No
2200225923 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 41875753.64 | 2093787.682 | 1218172 | 1218172 | 5950010121 | نعم | 72891375 |  | جاري | الكميات التي تم تركيبها | 10.05 | 21.56 | 2022-01-22 | 2023-06-07 | 2023-10-03 | 2023-10-03 |  |  |  |  | 40.3974 | 21.6331 | متأخر | No
2100094275 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 2291082.52 | 114554.126 | 1609996 | 1609996 | 1017000955 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-11-06 | 2015-10-15 | 2022-06-30 | 2022-06-30 | 2015-10-15 |  | اخرى |  | 46.5752 | 24.9269 | منجز | No
2100061563 | وزارة النقل والخدمات اللوجستية / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 79849228.63 | 3992461.4315 | 40506571.17 | 40506571.17 | 2050024197 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 62.07 | 54.29 | 2013-10-23 | 2020-08-28 | 2024-01-11 | 2024-01-11 |  |  |  |  | 49.6698 | 25.9667 | منتظم | No
2100053152 | وزارة النقل والخدمات اللوجستية / منطقة جازان | تشييد | ذات اولوية متوسطة | 108246599.98 | 5412329.999 | 77937552 | 77937552 | 5900000115 | لا | 0 | 190709006835 | جاري | الكميات التي تم تركيبها | 98.3 | 100 | 2010-08-18 | 2020-07-28 | 2022-10-31 | 2022-10-31 |  |  |  |  | 42.2658 | 17.7336 | متأخر | No
2100070954 | وزارة الداخلية / مديرية الأمن العام | تشييد | ذات اولوية متوسطة | 3075817.5 | 153790.875 | 2097910.5 | 2097910.5 | 1131023128 | لا | 0 |  | جاري | تكلفة العمل المنجز | 80 | 95 | 2019-11-06 | 2020-11-06 | 2020-11-06 | 2020-11-06 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 41.7543 | 27.4707 | Failed | No
2100094500 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 192527896.46 | 9626394.823 | 136676430 | 136676430 | 1010017021 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 74.18 | 74.18 | 2012-12-08 | 2016-11-17 | 2020-04-17 | 2020-04-17 |  |  | اخرى |  | 46.6672 | 24.6986 | مسحوب | No
2100098766 | وزارة النقل والخدمات اللوجستية / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 171727622 | 8586381.1 | 154548504.96 | 154548504.96 | 2060024520 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 99.81 | 100 | 2014-01-05 | 2017-11-21 | 2022-12-31 | 2022-12-31 |  |  |  |  | 49.6957 | 26.1538 | منتظم | No
2100037682 | وزارة النقل والخدمات اللوجستية / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 209112815 | 10455640.75 | 125990687.79 | 125990687.79 | 1010116309 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 76.52 | 70.99 | 2019-01-22 | 2021-12-19 | 2023-11-14 | 2023-11-14 |  |  |  |  | 50.0227 | 26.2684 | منتظم | No
2100196033 | وزارة النقل والخدمات اللوجستية / منطقة الباحة | تشييد | ذات اولوية متوسطة | 84999993.75 | 4249999.6875 | 27602708.07 | 27602708.07 | 1010017123 | لا | 0 |  | جاري | تكلفة العمل المنجز | 44.95 | 43.55 | 2020-04-23 | 2022-04-01 | 2024-01-20 | 2024-01-20 |  |  |  |  | 41.4713 | 20.0217 | منتظم | No
2100073054 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية منخفضة | 86766682 | 4338334.1 | 41556177.3 | 41556177.3 | 1010004737 | لا | 0 | 181109350614 | مسحوب | الكميات التي تم تركيبها | 48.4 | 100 | 2012-06-18 | 2016-05-04 | 2023-03-10 | 2023-03-10 |  |  | ضعف كفاءة المقاول الفنية |  | 39.91 | 21.4039 | مسحوب | No
2100025830 | وزارة النقل والخدمات اللوجستية / منطقة نجران | تشييد | ذات اولوية عالية | 65779986 | 3288999.3 | 35464828 | 35464828 | 3550019957 | لا | 0 | 181109292523 | فسخ العقد | الكميات التي تم تركيبها | 54 | 54 | 2008-07-19 | 2018-09-12 | 2018-09-12 | 2018-09-12 |  |  | اخرى |  | 44.2332 | 17.5654 | مسحوب | No
2200220043 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 36681047.2 | 1834052.36 | 1745268.97 | 1745268.97 | 4031046580 | نعم | 4499999.6 | 18119364039 | جاري | الكميات التي تم تركيبها | 37.9 | 45.35 | 2022-03-10 | 2023-08-22 | 2023-08-22 | 2023-08-22 |  |  |  |  | 39.6082 | 21.3127 | متأخر | No
2100070814 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 54834196 | 2741709.8 | 18759601 | 18759601 | 5855000147 | لا | 0 | 181109300074 | فسخ العقد | الكميات التي تم تركيبها | 38.54 | 100 | 2011-07-16 | 2015-02-23 | 2020-05-23 | 2020-05-23 |  |  | اخرى |  | 42.736 | 18.3002 | مسحوب | No
2100069812 | وزارة النقل والخدمات اللوجستية / منطقة القصيم | تشييد | ذات اولوية متوسطة | 102660895 | 5133044.75 | 66362433.54 | 66362433.54 | 1129000453 | لا | 0 | 190609058972 | جاري | الكميات التي تم تركيبها | 66.63 | 65.21 | 2014-08-21 | 2017-07-18 | 2024-04-04 | 2024-04-04 |  |  |  |  | 44.0254 | 26.2239 | منتظم | No
2100073076 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 29739449 | 1486972.45 | 15419000 | 15419000 | 1010080784 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 50.64 | 100 | 2012-09-16 | 2014-08-24 | 2014-08-24 | 2014-08-24 |  |  | التنسيق مع أصحاب المصلحه (خدمات |  | 42 | 19.1424 | مسحوب | No
2100077464 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 54780000 | 2739000 | 46100418 | 46100418 | 5855000147 | لا | 0 | 181109294792 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2008-08-18 | 2011-01-20 | 2015-03-29 | 2015-03-29 | 2011-01-20 |  |  |  | 42.5418 | 18.2222 | منجز | No
2100073113 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 124036900 | 6201845 | 107553314 | 107553314 | 4031049008 | لا | 0 | 190509074054 | جاري | الكميات التي تم تركيبها | 87.71 | 92.32 | 2014-11-05 | 2017-10-01 | 2023-04-23 | 2023-04-23 |  |  |  |  | 39.7849 | 21.5245 | منتظم | No
2100070280 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 74305000 | 3715250 | 56543822.5 | 56543822.5 | 4030170755 | لا | 0 | 180701029934 | جاري | الكميات التي تم تركيبها | 85.46 | 96.46 | 2012-10-09 | 2016-08-25 | 2022-12-16 | 2022-12-16 |  |  |  |  | 39.7981 | 21.4305 | متأخر | No
2100025970 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 80000000 | 4000000 | 55566723 | 55566723 | 1010210667 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 85.7 | 86.74 | 2018-06-03 | 2019-11-24 | 2023-04-03 | 2023-04-03 |  |  |  |  | 45.5842 | 23.5456 | منتظم | No
2200231733 | وزارة النقل والخدمات اللوجستية / منطقة جازان | تشييد | ذات اولوية عالية | 9061579.1 | 453078.955 | 0 | 0 | 5950005891 | لا | 0 |  | جاري | تكلفة العمل المنجز | 0 | 0 | 2022-09-10 | 2023-08-29 | 2023-08-29 | 2023-08-29 |  |  |  |  | 42.9393 | 17.2377 | منتظم | No
2100031813 | وزارة النقل والخدمات اللوجستية / منطقة المدينة المنورة | تشييد | ذات اولوية متوسطة | 49999999.5 | 2499999.975 | 15595470 | 15595470 | 4031005362 | لا | 0 | 181109368651 | فسخ العقد | الكميات التي تم تركيبها | 35.5 | 100 | 2014-10-12 | 2016-09-20 | 2017-06-15 | 2017-06-15 |  |  | اخرى |  | 40.0593 | 24.5563 | مسحوب | No
2200231873 | وزارة النقل والخدمات اللوجستية / منطقة المدينة المنورة | تشييد | ذات اولوية متوسطة | 29981620.63 | 1499081.0315 | 0 | 0 | 4650049275 | نعم | 25711690 |  | جاري | الكميات التي تم تركيبها | 66 | 39 | 2022-09-01 | 2026-08-11 | 2026-08-11 | 2026-08-11 |  |  |  |  | 39.8261 | 24.4687 | منتظم | No
2100053535 | وزارة النقل والخدمات اللوجستية / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 77674936.95 | 3883746.8475 | 54374413.84 | 54374413.84 | 2050024197 | لا | 0 | 181109361803 | جاري | الكميات التي تم تركيبها | 84.42 | 97.42 | 2013-10-22 | 2020-04-29 | 2022-12-11 | 2022-12-11 |  |  |  |  | 49.5308 | 26.5832 | متأخر | No
2100094802 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 78092312 | 3904615.6 | 42769873.91 | 42769873.91 | 4030006066 | لا | 0 | 180701022961 | جاري | الكميات التي تم تركيبها | 61.06 | 80.09 | 2018-11-14 | 2021-10-11 | 2023-06-14 | 2023-06-14 |  |  |  |  | 39.9155 | 21.4065 | متأخر | No
2100037914 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 34999996 | 1749999.8 | 29924996.85 | 29924996.85 | 5950005891 | لا | 0 | 180601014448 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-09-12 | 2022-02-02 | 2022-02-02 | 2022-02-02 | 2022-02-02 |  |  |  | 41.415 | 18.59 | منجز | No
2100054375 | وزارة النقل والخدمات اللوجستية / منطقة الباحة | تشييد | ذات اولوية عالية | 112953489 | 5647674.45 | 78486378 | 78486378 | 5900007895 | لا | 0 | 180701033184 | مسحوب | الكميات التي تم تركيبها | 70 | 100 | 2012-10-30 | 2017-12-26 | 2020-08-27 | 2020-08-27 |  |  |  |  | 41.4047 | 20.192 | مسحوب | No
2100053244 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 42859799.6 | 2142989.98 | 10835129.96 | 10835129.96 | 4031046580 | لا | 0 | 181109364039 | مسحوب | الكميات التي تم تركيبها | 27.82 | 100 | 2014-03-05 | 2016-02-12 | 2022-04-02 | 2022-04-02 |  |  | ضعف كفاءة المقاول الفنية |  | 39.8561 | 21.3814 | مسحوب | No
2100053642 | وزارة النقل والخدمات اللوجستية / منطقة المدينة المنورة | تشييد | ذات اولوية متوسطة | 56442815.1 | 2822140.755 | 50800827 | 50798533.59 | 1010184457 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 93 | 100 | 2009-06-24 | 2011-12-25 | 2011-12-25 | 2011-12-25 |  |  | اخرى |  | 39.0346 | 22.7895 | مسحوب | No
2100060336 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 436376250 | 21818812.5 | 236760170 | 236760170 | 1010008118 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 60.47 | 100 | 2009-12-09 | 2012-11-06 | 2018-11-20 | 2018-11-20 |  |  | ضعف كفاءة المقاول الفنية |  | 39.7907 | 21.1931 | مسحوب | No
2100077313 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 140960897.63 | 7048044.8815 | 61609761 | 61609761 | 1116001737 | لا | 0 |  | ايقاف جزئي | الكميات التي تم تركيبها | 46.52 | 63.23 | 2014-09-30 | 2021-07-10 | 2022-11-25 | 2022-11-25 |  |  | اخرى | أخرى | 46.6634 | 24.696 | متأخر | No
2100070700 | وزارة النقل والخدمات اللوجستية / منطقة تبوك | تشييد | ذات اولوية عالية | 79874675 | 3993733.75 | 65451372 | 65451372 | 4030170755 | لا | 0 | 180301000825 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-06-04 | 2020-11-05 | 2022-12-01 | 2022-12-01 | 2020-11-05 |  |  |  | 35.7528 | 27.4301 | منجز | No
2100077604 | وزارة النقل والخدمات اللوجستية / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 94925917.74 | 4746295.887 | 51830592.7 | 51830592.7 | 4031049008 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 43.93 | 100 | 2012-09-19 | 2019-08-22 | 2019-08-22 | 2019-08-22 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 50.091 | 26.3171 | مسحوب | No
2200220905 | وزارة النقل والخدمات اللوجستية | تشييد | ذات اولوية عالية | 17542372.39 | 877118.6195 | 6434973.87 | 6434973.87 | 1131006723 | لا | 0 |  | جاري | تكلفة العمل المنجز | 61.5 | 61.5 | 2022-01-16 | 2022-10-08 | 2023-05-13 | 2023-05-13 |  |  |  |  | 43.0494 | 26.8794 | منتظم | No
2100053093 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 65785015.15 | 3289250.7575 | 40582457.75 | 40582457.75 | 1010004737 | لا | 0 | 181109351399 | مسحوب | الكميات التي تم تركيبها | 62.01 | 100 | 2013-03-16 | 2015-08-18 | 2022-10-14 | 2022-10-14 |  |  | ضعف كفاءة المقاول الفنية |  | 40.4368 | 21.2183 | مسحوب | No
2100070534 | وزارة النقل والخدمات اللوجستية / منطقة الحدود الشمالية | تشييد | ذات اولوية متوسطة | 60993051.43 | 3049652.5715 | 33271871 | 33271871 | 1010095089 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 63.49 | 63.49 | 2013-11-21 | 2017-03-17 | 2021-05-03 | 2021-05-03 |  |  | اخرى |  | 43.7884 | 28.7447 | مسحوب | No
2100010986 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 105773333 | 5288666.65 | 56533003 | 56533003 | 1010066115 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 58.17 | 67.44 | 2013-08-12 | 2019-06-07 | 2022-04-30 | 2022-04-30 |  |  |  | أخرى | 47.2508 | 24.1004 | متأخر | No
2100067863 | وزارة النقل والخدمات اللوجستية / منطقة الجوف | تشييد | ذات اولوية متوسطة | 40000000 | 2000000 | 0 | 0 | 3450000664 | لا | 0 | 181101372189 | فسخ العقد | تكلفة العمل المنجز | 0 | 0 | 2019-02-24 | 2021-01-31 | 2021-05-02 | 2021-05-02 |  |  | اخرى |  | 37.4271 | 31.2575 | مسحوب | No
2100054040 | وزارة النقل والخدمات اللوجستية / منطقة الجوف | تشييد | ذات اولوية متوسطة | 38563000 | 1928150 | 17650600.888 | 17109191.352 | 5850021111 | لا | 0 | 181109351251 | مسحوب | تكلفة العمل المنجز | 57.81 | 100 | 2013-11-21 | 2016-04-24 | 2022-06-13 | 2022-06-13 |  |  |  |  | 40.1908 | 28.9459 | مسحوب | No
2100053546 | وزارة النقل والخدمات اللوجستية / منطقة الجوف | تشييد | ذات اولوية عالية | 100990962 | 5049548.1 | 56897037.6 | 56897037.6 | 1010056094 | لا | 0 | 180801040647 | مسحوب | تكلفة العمل المنجز | 71.25 | 100 | 2012-10-30 | 2016-09-14 | 2018-12-20 | 2018-12-20 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 37.2389 | 31.4085 | مسحوب | No
2100094485 | وزارة النقل والخدمات اللوجستية / منطقة القصيم | تشييد | ذات اولوية متوسطة | 57560374.32 | 2878018.716 | 48760020.29 | 48760020.29 | 1010171813 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-02-06 | 2016-01-15 | 2022-10-16 | 2022-10-16 | 2016-01-15 |  |  |  | 44.3466 | 25.6067 | منجز | No
2100054456 | وزارة النقل والخدمات اللوجستية / منطقة المدينة المنورة | تشييد | ذات اولوية متوسطة | 89396641 | 4469832.05 | 80456982.57 | 80456982.57 | 4031049008 | لا | 0 | 181109312304 | مسحوب | الكميات التي تم تركيبها | 91.46 | 100 | 2010-06-20 | 2012-11-21 | 2017-05-03 | 2017-05-03 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6198 | 24.4626 | مسحوب | No
2100077593 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 98523716.85 | 4926185.8425 | 97681940.61 | 97681940.61 | 1010090968 | لا | 0 | 181209522645 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-10-24 | 2016-09-19 | 2022-03-20 | 2022-03-20 | 2016-09-19 |  |  |  | 39.8605 | 21.3817 | منجز | No
2100038894 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية عالية | 56000000 | 2800000 | 0 | 0 | 2050004344 | لا | 0 | 181101276295 | فسخ العقد | الكميات التي تم تركيبها | 0 | 0 | 2019-02-07 | 2021-01-15 | 2021-01-15 | 2021-01-15 |  |  | اخرى |  | 42.6297 | 18.2662 | مسحوب | No
2100007895 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 9685535 | 484276.75 | 6181617 | 6181617 | 1010180774 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 86.73 | 100 | 2018-06-20 | 2020-05-28 | 2022-02-28 | 2022-02-28 |  |  | اخرى |  | 45.2588 | 26.4359 | مسحوب | No
2100073006 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 193980349.58 | 9699017.479 | 90639864 | 85982743 | 2051010618 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 59.54 | 70.28 | 2019-09-01 | 2021-08-09 | 2023-04-30 | 2023-04-30 |  |  |  |  | 46.6425 | 24.6487 | متأخر | No
2100196490 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية عالية | 79836760 | 3991838 | 13704811 | 12781429 | 5950006123 | لا | 0 | 191001029715 | جاري | الكميات التي تم تركيبها | 30.1 | 35.2 | 2020-07-05 | 2021-12-18 | 2023-05-31 | 2023-05-31 |  |  |  |  | 45.1478 | 22.7004 | متأخر | No
2100094791 | وزارة النقل والخدمات اللوجستية / منطقة جازان | تشييد | ذات اولوية متوسطة | 80314019.57 | 4015700.9785 | 48047671.2 | 48047671.2 | 1010166750 | لا | 0 | 181109340948 | فسخ العقد | الكميات التي تم تركيبها | 61 | 100 | 2012-02-11 | 2014-05-08 | 2021-05-05 | 2021-05-05 |  |  | اخرى |  | 43.1735 | 17.4368 | مسحوب | No
2100061876 | وزارة النقل والخدمات اللوجستية / منطقة جازان | تشييد | ذات اولوية متوسطة | 64768430 | 3238421.5 | 13509000 | 13509000 | 1010152168 | لا | 0 | 181109326959 | فسخ العقد | الكميات التي تم تركيبها | 21 | 70 | 2011-01-24 | 2013-06-28 | 2013-06-28 | 2013-06-28 |  |  | اخرى |  | 43.1529 | 17.7532 | مسحوب | No
2100053970 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 148378399 | 7418919.95 | 88085934 | 88085934 | 1116001737 | لا | 0 |  | ايقاف جزئي | الكميات التي تم تركيبها | 65 | 75.9 | 2012-12-06 | 2020-10-03 | 2023-03-31 | 2023-03-31 |  |  |  | أخرى | 46.2184 | 24.4409 | متأخر | No
2100060701 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 85000000 | 4250000 | 76500803 | 76500803 | 2051010618 | لا | 0 |  | ايقاف جزئي | الكميات التي تم تركيبها | 98.5 | 100 | 2018-07-05 | 2020-06-12 | 2023-05-31 | 2023-05-31 |  |  |  | أخرى | 47.1133 | 24.2965 | Failed | No
2100069904 | وزارة النقل والخدمات اللوجستية / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 38188600 | 1909430 | 25012345 | 25012345 | 1010039430 | لا | 0 | 181109364865 | جاري | الكميات التي تم تركيبها | 66.62 | 89.12 | 2015-09-03 | 2019-05-23 | 2022-01-20 | 2022-01-20 |  |  |  |  | 51.5588 | 24.1091 | متأخر | No
2100070873 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 38071000 | 1903550 | 18937457 | 18937457 | 4030170755 | لا | 0 | 181109348138 | جاري | الكميات التي تم تركيبها | 62.98 | 77.86 | 2010-12-05 | 2013-05-08 | 2023-05-22 | 2023-05-22 |  |  |  |  | 39.971 | 21.3687 | متأخر | No
2100038205 | وزارة النقل والخدمات اللوجستية / منطقة حائل | تشييد | ذات اولوية متوسطة | 40889112.6 | 2044455.63 | 15963470 | 0 | 1010069549 | لا | 0 | 200201034422 | جاري | تكلفة العمل المنجز | 96.1 | 94 | 2020-04-29 | 2021-10-11 | 2022-11-29 | 2022-11-29 |  |  |  |  | 41.8952 | 27.776 | منتظم | Yes
2100038242 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 121250000 | 6062500 | 87371938 | 86237651 | 1010184457 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 74.95 | 100 | 2012-08-30 | 2016-11-11 | 2022-12-31 | 2022-12-31 |  |  | اخرى |  | 47.2791 | 24.1774 | مسحوب | No
2100028033 | وزارة النقل والخدمات اللوجستية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 55210000 | 2760500 | 49689000.2 | 49689000.2 | 2051010618 | لا | 0 | 13400103 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-02-16 | 2020-05-01 | 2020-07-09 | 2020-07-09 | 2020-05-01 |  |  |  | 49.8887 | 26.6072 | منجز | No
2100073393 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 113846502.77 | 5692325.1385 | 3709787 | 3709787 | 1116000094 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 3.77 | 100 | 2013-12-03 | 2016-10-30 | 2016-10-30 | 2016-10-30 |  |  | ضعف كفاءة المقاول الفنية |  | 40.4385 | 21.2716 | مسحوب | No
2100195823 | وزارة النقل والخدمات اللوجستية / منطقة القصيم | تشييد | ذات اولوية متوسطة | 56470955.11 | 2823547.7555 | 24934512.27 | 24934512.27 | 1010040044 | لا | 0 | 191101192314 | جاري | تكلفة العمل المنجز | 59.6 | 51.85 | 2020-10-05 | 2022-09-25 | 2024-01-12 | 2024-01-12 |  |  |  |  | 43.9818 | 26.3592 | منتظم | No
2100062042 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 30000000 | 1500000 | 17465600 | 17465600 | 1010080784 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 54.58 | 100 | 2012-05-09 | 2014-04-17 | 2014-04-17 | 2014-04-17 |  |  | اخرى |  | 42.6032 | 18.1672 | مسحوب | No
2200225912 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 35972364.4 | 1798618.22 | 7658856.25 | 7658856.25 | 4030141919 | نعم | 89999999.85 |  | جاري | الكميات التي تم تركيبها | 33.3 | 68.1 | 2022-02-05 | 2022-11-27 | 2023-02-23 | 2023-02-23 |  |  |  |  | 39.3648 | 21.4421 | Failed | No
2100038743 | وزارة النقل والخدمات اللوجستية / منطقة الحدود الشمالية | تشييد | ذات اولوية منخفضة | 94939998.06 | 4746999.903 | 74402477 | 74402477 | 1010090968 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 83.51 | 81.87 | 2013-09-26 | 2018-06-07 | 2024-07-27 | 2024-07-27 |  |  | المشروع ليس ذو أولوية في الوقت الحالي |  | 41.1815 | 30.8717 | منتظم | No
2100054482 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 21673843.78 | 1083692.189 | 18182971.5 | 18182971.5 | 5950005891 | لا | 0 | 180501005708 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-07-18 | 2020-07-07 | 2020-06-07 | 2020-06-07 | 2020-07-07 |  | اخرى |  | 42.5516 | 18.1909 | منجز | No
2100021556 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 89132356 | 4456617.8 | 38390779.21 | 38390779.21 | 5950005891 | لا | 0 | 180301000782 | جاري | الكميات التي تم تركيبها | 52.17 | 64.09 | 2018-08-28 | 2020-08-18 | 2023-05-21 | 2023-05-21 |  |  |  |  | 39.8641 | 21.4339 | متأخر | No
2100053465 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 84069722 | 4203486.1 | 55890049 | 55890049 | 5851000110 | لا | 0 | 190701013609 | جاري | الكميات التي تم تركيبها | 78.9 | 88.8 | 2019-10-31 | 2021-04-14 | 2023-01-28 | 2023-01-28 |  |  |  |  | 42.75 | 21.5375 | Failed | No
2100100262 | وزارة النقل والخدمات اللوجستية / منطقة القصيم | تشييد | ذات اولوية عالية | 99266066.55 | 4963303.3275 | 65162542.5 | 65162542.5 | 1134000719 | لا | 0 | 180801044990 | جاري | الكميات التي تم تركيبها | 68.85 | 100 | 2013-10-31 | 2016-09-26 | 2022-11-19 | 2022-11-19 |  |  |  |  | 43.9618 | 26.2522 | Failed | No
2100094603 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 122482190.75 | 6124109.5375 | 67371087 | 67371087 | 1010017021 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 55.04 | 100 | 2013-11-18 | 2019-02-28 | 2022-12-31 | 2022-12-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 46.7183 | 24.7371 | مسحوب | No
2100077501 | وزارة النقل والخدمات اللوجستية / منطقة الجوف | تشييد | ذات اولوية متوسطة | 106897919 | 5344895.95 | 76966501.4 | 76966501.4 | 1010090968 | لا | 0 | 181109295642 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2008-07-29 | 2010-12-31 | 2021-11-07 | 2021-11-07 | 2010-12-31 |  |  |  | 37.3034 | 31.3259 | منجز | No
2100032104 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 59455710 | 2972785.5 | 53510327 | 53510327 | 1010082460 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-07-05 | 2020-06-24 | 2022-04-14 | 2022-04-14 | 2020-06-24 |  |  |  | 46.6761 | 24.7312 | منجز | No
2100053712 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 75396332 | 3769816.6 | 51814506.8 | 51814506.8 | 4031049008 | لا | 0 | 180801038668 | جاري | الكميات التي تم تركيبها | 78.63 | 94.43 | 2018-10-29 | 2021-09-26 | 2023-01-29 | 2023-01-29 |  |  |  |  | 39.8542 | 21.3896 | متأخر | No
2100061994 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 69999992.9 | 3499999.645 | 56164708.04 | 56164708.04 | 5855028046 | لا | 0 | 180401005418 | جاري | الكميات التي تم تركيبها | 87 | 100 | 2018-07-24 | 2020-12-23 | 2021-12-06 | 2021-12-06 |  |  |  |  | 42.654 | 18.2695 | Failed | No
2100057002 | وزارة النقل والخدمات اللوجستية / منطقة القصيم | ترميم | ذات اولوية عالية | 92005430.04 | 4600271.502 | 60633943.55 | 60633943.55 | 1010012911 | لا | 0 | 200101027862 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2020-05-09 | 2022-10-25 | 2022-10-25 | 2022-10-25 | 2022-10-25 |  | لا يوجد تأخير |  | 43.1045 | 26.8394 | منجز | No
2100072995 | وزارة النقل والخدمات اللوجستية / منطقة نجران | تشييد | ذات اولوية عالية | 139999998 | 6999999.9 | 0 | 0 | 3550019957 | لا | 0 | 181109352181 | فسخ العقد | الكميات التي تم تركيبها | 0 | 0 | 2012-11-27 | 2022-06-27 | 2018-09-19 | 2018-09-19 |  |  | اخرى |  | 44.2231 | 17.5548 | مسحوب | No
2100038872 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 54999999.6 | 2749999.98 | 49499954.58 | 49499954.58 | 1010017123 | لا | 0 | 181201546746 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-04-03 | 2021-03-10 | 2023-11-20 | 2023-11-20 | 2021-03-10 |  |  |  | 39.8316 | 21.4276 | منجز | No
2100031802 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | لم تعد تحتاجها الجهة | 7600000 | 380000 | 4386027.94 | 4386027.94 | 1010333894 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 56.82 | 56.82 | 2015-08-09 | 2017-07-17 | 2017-07-17 | 2017-07-17 |  |  | اخرى |  | 39.8353 | 21.4369 | مسحوب | No
2100032174 | وزارة النقل والخدمات اللوجستية / منطقة القصيم | تشييد | ذات اولوية متوسطة | 37980522 | 1899026.1 | 212690.92 | 212690.92 | 1010018153 | لا | 0 | 181109364690 | فسخ العقد | الكميات التي تم تركيبها | 50 | 100 | 2014-07-21 | 2016-01-03 | 2016-01-03 | 2016-01-03 |  |  | اخرى |  | 43.5235 | 25.8596 | مسحوب | No
2100073080 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 71790224 | 3589511.2 | 21564827.34 | 21564827.34 | 5860007938 | لا | 0 | 181101372227 | جاري | الكميات التي تم تركيبها | 52.29 | 60 | 2019-02-24 | 2022-01-21 | 2022-01-21 | 2022-01-21 |  |  |  |  | 42.5117 | 18.2465 | Failed | No
2100053060 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية منخفضة | 45365259.2 | 2268262.96 | 12198810 | 12198810 | 1010154882 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 25.77 | 25.77 | 2013-07-12 | 2016-10-04 | 2021-09-30 | 2021-09-30 |  |  | اخرى |  | 46.6953 | 24.709 | مسحوب | No
2100070475 | وزارة النقل والخدمات اللوجستية / منطقة الحدود الشمالية | تشييد | ذات اولوية متوسطة | 26566093.95 | 1328304.6975 | 22856205 | 22856205 | 5950005891 | لا | 0 | 181109361687 | جاري | الكميات التي تم تركيبها | 91.25 | 100 | 2015-11-05 | 2017-10-12 | 2022-12-15 | 2022-12-15 |  |  |  |  | 42.1088 | 29.6535 | Failed | No
2100196070 | وزارة النقل والخدمات اللوجستية / منطقة القصيم | تشييد | ذات اولوية عالية | 144421260.6 | 7221063.03 | 129985976.76 | 129985976.76 | 1116001737 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2012-10-24 | 2016-09-08 | 2021-08-08 | 2021-08-08 | 2016-09-08 |  |  |  | 43.353 | 25.7819 | منجز | No
2100028545 | وزارة النقل والخدمات اللوجستية / منطقة الجوف | تشييد | ذات اولوية متوسطة | 68710490.96 | 3435524.548 | 47933939.96 | 47933939.96 | 3400002435 | لا | 0 | 181109305361 | مسحوب | تكلفة العمل المنجز | 87 | 100 | 2009-06-28 | 2012-05-25 | 2018-10-14 | 2018-10-14 |  |  | اخرى |  | 38.1479 | 30.1578 | مسحوب | No
2100198892 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية منخفضة | 157689867.92 | 7884493.396 | 49878024.36 | 49878024.36 | 2060002548 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 36 | 100 | 2013-03-26 | 2015-08-28 | 2019-02-11 | 2019-02-11 |  |  | ضعف كفاءة المقاول الفنية |  | 44.3811 | 26.4402 | مسحوب | No
2100098501 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 2799868.36 | 139993.418 | 1399128.9 | 1399128.9 | 5855039588 | لا | 0 | 180301001452 | فسخ العقد | الكميات التي تم تركيبها | 49.97 | 100 | 2018-01-09 | 2019-10-24 | 2019-10-24 | 2019-10-24 |  |  | اخرى |  | 42.7116 | 18.1754 | مسحوب | No
2100075891 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 111447651.45 | 5572382.5725 | 42925853 | 42925853 | 1010066115 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 44.3 | 60.97 | 2014-07-21 | 2020-10-26 | 2022-04-30 | 2022-04-30 |  |  | اخرى | أخرى | 47.1485 | 25.0116 | مسحوب | No
2100053572 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 27316259.39 | 1365812.9695 | 21256078 | 21256078 | 1010048595 | لا | 0 | 180301000917 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-06-04 | 2019-11-16 | 2022-12-31 | 2022-12-31 | 2019-11-16 |  | اخرى |  | 46.674 | 24.7125 | منجز | No
2100039082 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 148795299.9 | 7439764.995 | 50738028 | 50738028 | 4031049008 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 34.81 | 100 | 2013-11-26 | 2020-07-19 | 2020-07-19 | 2020-07-19 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7114 | 24.9054 | مسحوب | No
2100053723 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | لم تعد تحتاجها الجهة | 89999999.85 | 4499999.9925 | 68257449 | 68257449 | 4030007516 | لا | 0 | 201039264203 | مسحوب | الكميات التي تم تركيبها | 0 | 0 | 2009-07-27 | 2012-06-24 | 2013-04-14 | 2013-04-14 |  |  | ضعف كفاءة المقاول الفنية |  | 39.3033 | 21.4373 | مسحوب | No
2100196092 | وزارة النقل والخدمات اللوجستية / منطقة نجران | تشييد | ذات اولوية متوسطة | 62600000 | 3130000 | 24787144 | 24787144 | 5950010121 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 40 | 40 | 2012-09-20 | 2019-03-14 | 2019-03-14 | 2019-03-14 |  |  |  |  | 44.3201 | 17.542 | مسحوب | No
2100053675 | وزارة النقل والخدمات اللوجستية / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 175414261.04 | 8770713.052 | 11235420 | 11235420 | 2051047879 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 6 | 100 | 2015-05-27 | 2018-04-24 | 2018-04-24 | 2018-04-24 |  |  | اخرى |  | 45.9911 | 28.3896 | مسحوب | No
2100070372 | وزارة النقل والخدمات اللوجستية / منطقة جازان | تشييد | ذات اولوية متوسطة | 107654650.28 | 5382732.514 | 63831016.11 | 63831016.11 | 5900000115 | لا | 0 | 180901072118 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2010-08-18 | 2012-07-26 | 2022-06-30 | 2022-06-30 | 2012-07-26 |  |  |  | 42.9354 | 16.6018 | منجز | No
2200223322 | وزارة النقل والخدمات اللوجستية / منطقة جازان | تشييد | ذات اولوية عالية | 12990678.88 | 649533.944 | 0 | 0 | 1010412530 | نعم | 150692365.91 |  | جاري | الكميات التي تم تركيبها | 12 | 26.61 | 2022-04-19 | 2023-04-13 | 2023-04-08 | 2023-04-08 |  |  |  |  | 42.8297 | 17.617 | متأخر | No
2100077512 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | لم تعد تحتاجها الجهة | 68571395 | 3428569.75 | 17304878 | 17304878 | 1010263576 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 35 | 35 | 2011-06-21 | 2013-11-21 | 2015-03-09 | 2015-03-09 |  |  | اخرى |  | 39.8585 | 21.5137 | مسحوب | No
2100053933 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 21080265.5 | 1054013.275 | 10513652.07 | 10513652.07 | 1010178838 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 51.17 | 54.24 | 2018-02-07 | 2020-01-15 | 2023-06-13 | 2023-06-13 |  |  | اخرى |  |  |  | مسحوب | No
2100031861 | وزارة النقل والخدمات اللوجستية / منطقة الجوف | تشييد | ذات اولوية متوسطة | 24002487.77 | 1200124.3885 | 12713935.112 | 12713935.112 | 1010056094 | لا | 0 | 181009142983 | مسحوب | تكلفة العمل المنجز | 66.88 | 100 | 2014-08-23 | 2017-01-24 | 2022-12-31 | 2022-12-31 |  |  | اخرى |  | 37.9861 | 31.4257 | مسحوب | No
2100069893 | وزارة النقل والخدمات اللوجستية / منطقة الجوف | تشييد | ذات اولوية متوسطة | 22834559 | 1141727.95 | 7264195.33 | 7264195.33 | 1010195538 | لا | 0 | 181009145677 | فسخ العقد | تكلفة العمل المنجز | 31.81 | 31.81 | 2018-02-25 | 2019-08-11 | 2021-05-20 | 2021-05-20 |  |  | اخرى |  | 40.1133 | 29.9501 | مسحوب | No
2100031894 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | لم تعد تحتاجها الجهة | 4559999.48 | 227999.974 | 667426.3 | 667426.3 | 4031047880 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 14.64 | 14.64 | 2015-11-17 | 2017-10-24 | 2017-10-24 | 2017-10-24 |  |  | اخرى |  | 39.8278 | 21.3567 | مسحوب | No
2100094010 | وزارة النقل والخدمات اللوجستية / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 11658998 | 582949.9 | 6777070 | 6777070 | 2050045542 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 58.68 | 58.68 | 2012-05-29 | 2015-08-22 | 2015-08-22 | 2015-08-22 |  |  | اخرى |  | 50.0832 | 26.3176 | مسحوب | No
2100057470 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية عالية | 82504906 | 4125245.3 | 49078316 | 49078316 | 5860007938 | لا | 0 | 180501007714 | جاري | الكميات التي تم تركيبها | 99.5 | 100 | 2018-07-26 | 2020-12-27 | 2022-11-07 | 2022-11-07 |  |  |  |  | 42.5397 | 18.2268 | منتظم | No
2100038146 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 103240441.6 | 5162022.08 | 85109731.5 | 85109731.5 | 5950010121 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 90.9 | 88.3 | 2020-05-31 | 2022-04-08 | 2022-11-06 | 2022-11-06 |  |  |  |  | 41.0957 | 21.4376 | متأخر | No
2100038301 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 76067880 | 3803394 | 7662141.9 | 7662141.9 | 4032026650 | لا | 0 | 190101001727 | ايقاف كلي | الكميات التي تم تركيبها | 14.56 | 73.67 | 2019-04-04 | 2021-03-11 | 2023-02-16 | 2023-02-16 |  |  | ضعف كفاءة المقاول الفنية |  | 40.5534 | 21.4751 | Failed | No
2100021420 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 52143701.75 | 2607185.0875 | 48743932 | 46918023.15 | 5900000115 | لا | 0 | 181109349090 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2012-08-07 | 2016-06-23 | 2020-05-11 | 2020-05-11 | 2016-06-23 |  |  |  | 42.5117 | 18.2465 | منجز | No
2200223145 | وزارة النقل والخدمات اللوجستية / منطقة المدينة المنورة | تشييد | ذات اولوية متوسطة | 10197922.3 | 509896.115 | 5680508 | 5680508 | 4650050716 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 54.38 | 100 | 2011-06-07 | 2014-03-06 | 2014-03-06 | 2014-03-06 |  |  | ضعف كفاءة المقاول الفنية |  | 41.2472 | 23.6035 | مسحوب | No
2100006101 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 1478177.95 | 73908.8975 | 1274690.93 | 1274690.93 | 3350009773 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2018-05-28 | 2019-03-24 | 2021-05-30 | 2021-05-30 | 2019-03-24 |  |  |  | 43.9544 | 26.3504 | منجز | No
2100088012 | جامعة الأمير سطام بن عبدالعزيز | تشييد | ذات اولوية متوسطة | 81520 | 4076 | 0 | 0 | 1010384971 | لا | 0 | 180809050280 | فسخ العقد | تكلفة العمل المنجز | 1 | 100 | 2018-08-02 | 2018-09-16 | 2018-08-16 | 2018-08-16 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 47.274 | 24.1503 | مسحوب | No
2100077416 | وزارة النقل والخدمات اللوجستية / منطقة حائل | تشييد | ذات اولوية متوسطة | 89154670 | 4457733.5 | 14193773.92 | 0 | 1010214056 | لا | 0 | 181101221365 | فسخ العقد | الكميات التي تم تركيبها | 9.4 | 34 | 2019-01-17 | 2021-12-14 | 2021-12-15 | 2021-12-15 |  |  | اخرى |  | 41.7241 | 27.4827 | مسحوب | Yes
2100073172 | وزارة النقل والخدمات اللوجستية / منطقة حائل | تشييد | ذات اولوية متوسطة | 80034696.4 | 4001734.82 | 72197805 | 72197280 | 1010184457 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 96 | 100 | 2008-08-21 | 2011-10-30 | 2011-10-30 | 2011-10-30 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.5583 | 27.7296 | مسحوب | No
2100037995 | وزارة النقل والخدمات اللوجستية / منطقة حائل | تشييد | ذات اولوية متوسطة | 138473088 | 6923654.4 | 133444645.3 | 112907243 | 1010069549 | لا | 0 | 181109313861 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2010-06-30 | 2019-11-14 | 2019-11-15 | 2019-11-15 | 2019-11-14 |  |  |  | 41.8525 | 27.558 | منجز | No
2100028560 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 69712810 | 3485640.5 | 11780000 | 11780000 | 1010152168 | لا | 0 | 181109326959 | فسخ العقد | الكميات التي تم تركيبها | 21.12 | 100 | 2011-01-24 | 2017-05-15 | 2017-06-16 | 2017-06-16 |  |  | اخرى |  | 43.0566 | 17.6089 | مسحوب | No
2100037833 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 54965585.85 | 2748279.2925 | 14320037.8 | 14320037.8 | 2050004344 | لا | 0 | 181101223524 | فسخ العقد | الكميات التي تم تركيبها | 27.35 | 99.49 | 2019-01-10 | 2020-12-29 | 2020-12-30 | 2020-12-30 |  |  | اخرى |  | 42.518 | 18.227 | مسحوب | No
2100070265 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 15994972.07 | 799748.6035 | 12560070 | 12560070 | 5855007548 | لا | 0 | 181009146139 | مسحوب | الكميات التي تم تركيبها | 84.91 | 100 | 2014-02-10 | 2019-10-08 | 2019-10-08 | 2019-10-08 |  |  |  |  | 42.5737 | 18.1947 | مسحوب | No
2100037962 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية عالية | 22453974.74 | 1122698.737 | 9755292 | 9755292 | 5855000147 | لا | 0 | 191201121934 | فسخ العقد | الكميات التي تم تركيبها | 71.34 | 100 | 2007-06-28 | 2015-03-13 | 2015-03-13 | 2015-03-13 |  |  | اخرى |  | 43.0392 | 18.2856 | مسحوب | No
2100037413 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية منخفضة | 5599998 | 279999.9 | 0 | 0 | 1010196247 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 0 | 0 | 2013-10-24 | 2019-02-17 | 2019-02-17 | 2019-02-17 |  |  | اخرى |  | 42.5378 | 18.2651 | مسحوب | No
2100015083 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 76622938.35 | 3831146.9175 | 43674500 | 43674500 | 4030170755 | لا | 0 | 190501047165 | جاري | الكميات التي تم تركيبها | 74.48 | 80.7 | 2019-12-04 | 2021-11-11 | 2023-03-08 | 2023-03-08 |  |  |  |  | 39.8827 | 21.3425 | متأخر | No
2100054095 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 130000000 | 6500000 | 81337218.4 | 80761350.4 | 5855000147 | لا | 0 | 180701021738 | جاري | الكميات التي تم تركيبها | 84 | 83 | 2013-03-21 | 2017-02-06 | 2022-06-01 | 2022-06-01 |  |  |  |  | 42.7881 | 18.1736 | متأخر | No
2100037984 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 123360637.82 | 6168031.891 | 87925770.25 | 87925770.25 | 1010066115 | لا | 0 | 180801049692 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-03-19 | 2021-07-28 | 2021-07-28 | 2021-07-28 | 2021-07-28 |  | اخرى |  | 42.7067 | 18.1264 | منجز | No
2100038290 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية عالية | 272300999 | 13615049.95 | 179666388 | 179666388 | 1010066115 | لا | 0 | 181009219307 | مسحوب | الكميات التي تم تركيبها | 85.36 | 100 | 2012-08-11 | 2020-10-09 | 2020-10-09 | 2020-10-09 |  |  |  |  | 43.328 | 17.576 | مسحوب | No
2100025760 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 87818504 | 4390925.2 | 35175624.86 | 35175624.86 | 5855028046 | لا | 0 | 180701029051 | جاري | الكميات التي تم تركيبها | 52.17 | 63.1 | 2018-09-27 | 2021-02-28 | 2022-08-14 | 2022-08-14 |  |  |  |  | 42.6334 | 18.2551 | متأخر | No
2200225934 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية عالية | 213885094.88 | 10694254.744 | 7699935 | 7699935 | 1010017123 | نعم | 436376250 |  | ايقاف جزئي | الكميات التي تم تركيبها | 17.8 | 16 | 2022-02-05 | 2024-01-15 | 2024-01-15 | 2024-01-15 |  |  |  |  | 39.8142 | 21.417 | منتظم | No
2100053443 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 38577547.9 | 1928877.395 | 30008524 | 30008524 | 5855007548 | لا | 0 | 181009146518 | مسحوب | الكميات التي تم تركيبها | 82.7 | 100 | 2011-12-17 | 2014-05-15 | 2021-03-12 | 2021-03-12 |  |  | اخرى |  | 42.6512 | 18.1808 | مسحوب | No
2100011524 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 76918487.1 | 3845924.355 | 46644161.4 | 46644161.4 | 4031018104 | لا | 0 | 190201003901 | جاري | الكميات التي تم تركيبها | 74.63 | 70.8 | 2019-04-18 | 2021-03-25 | 2023-07-04 | 2023-07-04 |  |  |  |  | 39.6093 | 21.0267 | منتظم | No
2100054036 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 85725000 | 4286250 | 18479333.92 | 18479333.92 | 1010066115 | لا | 0 | 180901069709 | فسخ العقد | الكميات التي تم تركيبها | 33.34 | 100 | 2013-11-06 | 2016-10-03 | 2020-04-24 | 2020-04-24 |  |  | اخرى |  | 42.619 | 18.1378 | مسحوب | No
2100094452 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 125207368.35 | 6260368.4175 | 112686631.5 | 112686631.5 | 5855001146 | لا | 0 | 180701021023 | جاري | الكميات التي تم تركيبها | 95.46 | 97.25 | 2014-07-15 | 2022-04-24 | 2022-04-24 | 2022-04-24 |  |  |  |  | 42.5117 | 18.2465 | متأخر | No
2100073010 | وزارة النقل والخدمات اللوجستية / منطقة تبوك | تشييد | ذات اولوية متوسطة | 50000000 | 2500000 | 2422254.9 | 2422254.9 | 3550019957 | لا | 0 | 181109370912 | فسخ العقد | الكميات التي تم تركيبها | 5 | 48 | 2014-02-22 | 2021-03-05 | 2021-03-05 | 2021-03-05 |  |  | اخرى |  | 34.9622 | 29.2458 | مسحوب | No
2100070162 | وزارة النقل والخدمات اللوجستية / منطقة تبوك | تشييد | ذات اولوية متوسطة | 40436619.61 | 2021830.9805 | 19451816.27 | 19451816.27 | 3550019957 | لا | 0 | 190609059083 | فسخ العقد | الكميات التي تم تركيبها | 48.12 | 100 | 2014-07-30 | 2016-07-07 | 2017-01-28 | 2017-01-28 |  |  | اخرى |  | 38.5234 | 27.618 | مسحوب | No
2200223016 | وزارة النقل والخدمات اللوجستية / منطقة تبوك | تشييد | ذات اولوية عالية | 42291051.68 | 2114552.584 | 273907 | 273907 | 1010412530 | نعم | 20475459 |  | جاري | الكميات التي تم تركيبها | 2 | 27.4 | 2022-03-17 | 2023-09-16 | 2022-09-16 | 2022-09-16 |  |  |  |  | 36.5981 | 28.4132 | Failed | No
2100077420 | وزارة النقل والخدمات اللوجستية / منطقة تبوك | تشييد | ذات اولوية متوسطة | 57090000 | 2854500 | 51382205.28 | 51382205.28 | 1010099930 | لا | 0 | 181109364253 | جاري | الكميات التي تم تركيبها | 89.11 | 96.37 | 2011-08-11 | 2014-11-11 | 2022-12-25 | 2022-12-25 |  |  |  |  | 37.6223 | 28.5138 | متأخر | No
2100195985 | وزارة النقل والخدمات اللوجستية / منطقة تبوك | تشييد | ذات اولوية متوسطة | 83475000 | 4173750 | 0 | 0 | 3550021826 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 0 | 0 | 2018-11-04 | 2021-10-02 | 2021-10-02 | 2021-10-02 |  |  |  |  | 35.6654 | 27.3719 | Failed | No
2200223075 | وزارة النقل والخدمات اللوجستية / منطقة تبوك | تشييد | ذات اولوية متوسطة | 216706998.51 | 10835349.9255 | 34408513.89 | 34408513.89 | 1116000094 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 16 | 100 | 2013-12-05 | 2017-10-22 | 2017-10-22 | 2017-10-22 |  |  |  |  | 37.0053 | 28.1051 | مسحوب | No
2100083996 | وزارة النقل والخدمات اللوجستية / منطقة تبوك | تشييد | ذات اولوية متوسطة | 66990000 | 3349500 | 17861162.4 | 17861162.4 | 3550019957 | لا | 0 | 181109359069 | مسحوب | الكميات التي تم تركيبها | 26.66 | 100 | 2015-03-11 | 2017-02-16 | 2017-02-16 | 2017-02-16 |  |  | ضعف كفاءة المقاول الفنية |  | 36.1579 | 26.8419 | مسحوب | No
2200231711 | وزارة النقل والخدمات اللوجستية / منطقة جازان | تشييد | ذات اولوية عالية | 170849106.69 | 8542455.3345 | 0 | 0 | 1123001261 | لا | 0 |  | جاري | تكلفة العمل المنجز | 0.27 | 1.62 | 2022-08-01 | 2025-11-23 | 2023-11-23 | 2023-11-23 |  |  |  |  | 42.9538 | 16.7112 | منتظم | No
2100198833 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 13757247 | 687862.35 | 1787350 | 1569350 | 1116005202 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 16.81 | 28.16 | 2020-04-29 | 2021-12-04 | 2023-09-30 | 2023-09-30 |  |  |  | أخرى | 46.2581 | 25.0089 | متأخر | No
2100015190 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 59999999 | 2999999.95 | 3476000 | 3476000 | 1010152168 | لا | 34760000 |  | مسحوب | الكميات التي تم تركيبها | 27.2 | 97 | 2013-01-01 | 2016-12-30 | 2016-12-30 | 2016-12-30 |  |  | اخرى |  | 41.5945 | 18.1266 | مسحوب | No
2100073065 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 29490000 | 1474500 | 25436965.34 | 23612959 | 1010247052 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-08-05 | 2016-09-28 | 2016-09-29 | 2016-09-29 | 2016-09-28 |  | اخرى |  | 41.815 | 19.6544 | منجز | No
2100070991 | وزارة النقل والخدمات اللوجستية / منطقة الباحة | تشييد | ذات اولوية متوسطة | 197489976 | 9874498.8 | 134673381 | 134673381 | 1010008118 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 68.27 | 100 | 2011-09-23 | 2015-02-15 | 2015-02-13 | 2015-02-13 |  |  | اخرى |  | 41.6702 | 19.8064 | مسحوب | No
2100070346 | وزارة النقل والخدمات اللوجستية / منطقة الباحة | تشييد | ذات اولوية عالية | 81507358.41 | 4075367.9205 | 73353721.45 | 73353721.45 | 4032026650 | لا | 0 | 181109343870 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-11-27 | 2020-05-16 | 2020-09-17 | 2020-09-17 | 2020-05-16 |  |  |  | 41.4713 | 20.0217 | منجز | No
2100053616 | وزارة النقل والخدمات اللوجستية / منطقة الباحة | تشييد | ذات اولوية متوسطة | 38587373.3 | 1929368.665 | 36104572.6 | 36104572.6 | 1010154882 | لا | 0 | 181009145977 | جاري | الكميات التي تم تركيبها | 94.32 | 100 | 2011-09-13 | 2015-01-05 | 2022-11-24 | 2022-11-24 |  |  | اخرى |  | 41.4623 | 19.9995 | Failed | No
2100084066 | وزارة النقل والخدمات اللوجستية / منطقة الباحة | تشييد | ذات اولوية متوسطة | 18648038.68 | 932401.934 | 14108723.17 | 14108723.17 | 1010154882 | لا | 0 | 181109372920 | جاري | الكميات التي تم تركيبها | 74.66 | 100 | 2015-03-10 | 2018-02-04 | 2023-01-19 | 2023-01-19 |  |  | اخرى |  | 41.4713 | 20.0217 | Failed | No
2100053620 | وزارة النقل والخدمات اللوجستية / منطقة الباحة | تشييد | ذات اولوية متوسطة | 139252486 | 6962624.3 | 54589319.88 | 54589319.88 | 1010066115 | لا | 0 | 181009152177 | جاري | الكميات التي تم تركيبها | 43.99 | 100 | 2014-05-27 | 2018-04-13 | 2023-03-23 | 2023-03-23 |  |  |  |  | 41.6197 | 20.1945 | Failed | No
2100094371 | وزارة النقل والخدمات اللوجستية / منطقة حائل | تشييد | ذات اولوية متوسطة | 43999999.56 | 2199999.978 | 37402013.88 | 37402013.88 | 3350000631 | لا | 0 | 180701036576 | جاري | الكميات التي تم تركيبها | 99.85 | 100 | 2017-11-13 | 2022-07-27 | 2022-07-27 | 2022-07-27 |  |  |  |  | 41.7154 | 27.5125 | متأخر | No
2100028243 | وزارة النقل والخدمات اللوجستية / منطقة حائل | تشييد | ذات اولوية متوسطة | 84206300 | 4210315 | 74952314 | 69325362 | 1010069549 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2009-08-11 | 2019-03-02 | 2021-04-06 | 2021-04-06 | 2019-03-02 |  |  |  | 41.8297 | 27.6603 | منجز | No
2100090926 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2281000 | 114050 | 0 | 0 | 1115001168 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 82 | 92 | 2018-12-29 | 2020-03-23 | 2020-03-23 | 2020-03-23 |  |  |  |  | 46.6857 | 24.705 | Failed | No
2100028420 | وزارة النقل والخدمات اللوجستية / منطقة حائل | تشييد | ذات اولوية متوسطة | 23376000 | 1168800 | 19692444 | 19692444 | 3350000631 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2012-10-03 | 2019-01-22 | 2019-01-22 | 2019-01-22 | 2019-01-22 |  |  |  | 41.7203 | 27.6587 | منجز | No
2100061386 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 29591292 | 1479564.6 | 22800796 | 22800796 | 1010247052 | لا | 0 | 181109343161 | فسخ العقد | الكميات التي تم تركيبها | 67.64 | 100 | 2012-08-22 | 2016-07-08 | 2017-07-13 | 2017-07-13 |  |  | اخرى |  | 42.5336 | 18.2619 | مسحوب | No
2100084254 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 72789375 | 3639468.75 | 64404407 | 64404407 | 1010154882 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-03-04 | 2018-05-07 | 2022-04-30 | 2022-04-30 | 2018-05-07 |  |  |  | 46.6418 | 24.6851 | منجز | No
2100021372 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 31436292 | 1571814.6 | 30598619 | 30598619 | 1010154882 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2012-11-12 | 2019-01-15 | 2022-10-31 | 2022-10-31 | 2019-01-15 |  | اخرى |  | 46.6788 | 24.6963 | منجز | No
2100038021 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 205501625.85 | 10275081.2925 | 147961088.8 | 144190225.1 | 5855029980 | لا | 0 | 181109327435 | مسحوب | الكميات التي تم تركيبها | 95.82 | 100 | 2011-01-01 | 2015-05-15 | 2015-05-15 | 2015-05-15 |  |  | اخرى |  | 42.508 | 18.2362 | مسحوب | No
2100039071 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 39888523 | 1994426.15 | 33189618 | 33189618 | 5860007938 | لا | 0 | 180501007730 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-07-26 | 2020-12-27 | 2020-12-27 | 2020-12-27 | 2020-12-27 |  |  |  | 42.5117 | 18.2465 | منجز | No
2100054106 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 76728264.9 | 3836413.245 | 69056891.3 | 69056891.3 | 5855028046 | لا | 0 | 181209525400 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-10-23 | 2016-09-18 | 2020-03-19 | 2020-03-19 | 2016-09-18 |  |  |  | 42.5611 | 18.2743 | منجز | No
2100070044 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 12739817 | 636990.85 | 9062411 | 9062411 | 1010270823 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 94 | 100 | 2018-07-05 | 2019-12-17 | 2022-09-01 | 2022-09-01 |  |  |  |  | 46.6441 | 24.7034 | Failed | No
2100084114 | وزارة النقل والخدمات اللوجستية / منطقة الباحة | تشييد | ذات اولوية منخفضة | 5557968.29 | 277898.4145 | 3687132 | 3687132 | 5855029980 | لا | 0 | 181009171425 | فسخ العقد | الكميات التي تم تركيبها | 69.61 | 100 | 2014-02-05 | 2016-01-14 | 2016-01-14 | 2016-01-14 |  |  | اخرى |  | 41.4366 | 19.7014 | مسحوب | No
2100039174 | وزارة النقل والخدمات اللوجستية / منطقة جازان | تشييد | ذات اولوية عالية | 138481799 | 6924089.95 | 17093376.13 | 17093376.13 | 4650030714 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 14.59 | 100 | 2012-07-09 | 2016-06-22 | 2018-03-07 | 2018-03-07 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.9733 | 16.5279 | مسحوب | No
2100098862 | وزارة النقل والخدمات اللوجستية / منطقة المدينة المنورة | تشييد | ذات اولوية متوسطة | 47641396 | 2382069.8 | 42877256.4 | 42877256.4 | 4650007949 | لا | 0 | 180701022940 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-09-22 | 2020-03-15 | 2022-10-10 | 2022-10-10 | 2020-03-15 |  |  |  | 39.5945 | 24.5197 | منجز | No
2100015260 | وزارة النقل والخدمات اللوجستية / منطقة جازان | تشييد | ذات اولوية عالية | 131749235 | 6587461.75 | 68288425.71 | 68288425.71 | 1010054406 | لا | 0 | 181109370355 | جاري | الكميات التي تم تركيبها | 65.67 | 66.3 | 2012-11-06 | 2015-10-03 | 2023-12-30 | 2023-12-30 |  |  |  |  | 42.8872 | 17.6547 | منتظم | No
2100038964 | وزارة النقل والخدمات اللوجستية / منطقة جازان | تشييد | ذات اولوية متوسطة | 43246790 | 2162339.5 | 16132759.2 | 16132759.2 | 5900000115 | لا | 0 | 181109343876 | مسحوب | الكميات التي تم تركيبها | 48.7 | 50.3 | 2012-08-27 | 2016-07-13 | 2022-07-28 | 2022-07-28 |  |  |  |  | 43.1164 | 17.2391 | مسحوب | No
2100001142 | وزارة النقل والخدمات اللوجستية / منطقة جازان | ترميم | ذات اولوية عالية | 18959248 | 947962.4 | 14478573.7 | 14478573.7 | 1010039430 | لا | 0 | 200101057156 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2020-04-02 | 2020-11-23 | 2022-10-16 | 2022-10-16 | 2020-11-23 |  | ضعف كفاءة المقاول الفنية |  | 42.7642 | 16.658 | منجز | No
2100038511 | وزارة النقل والخدمات اللوجستية / منطقة المدينة المنورة | تشييد | ذات اولوية متوسطة | 35813694.7 | 1790684.735 | 19976749.15 | 19976749.15 | 4031049008 | لا | 0 | 181109364496 | مسحوب | الكميات التي تم تركيبها | 60.2 | 100 | 2013-10-21 | 2019-05-04 | 2019-05-04 | 2019-05-04 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6157 | 24.4542 | مسحوب | No
2200231744 | وزارة النقل والخدمات اللوجستية / منطقة جازان | تشييد | ذات اولوية متوسطة | 11649074.69 | 582453.7345 | 0 | 0 | 4030216723 | لا | 0 |  | جاري | تكلفة العمل المنجز | 0 | 0 | 2022-09-27 | 2023-09-15 | 2023-09-15 | 2023-09-15 |  |  |  |  | 43.0969 | 17.2357 | منتظم | No
2100038905 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 71850000 | 3592500 | 33588347 | 33588347 | 4031049008 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 48.47 | 100 | 2012-10-31 | 2020-12-07 | 2021-09-08 | 2021-09-08 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 46.1845 | 24.574 | مسحوب | No
2100070545 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 172546850 | 8627342.5 | 170085714.9 | 170085714.9 | 1010247052 | لا | 0 | 181109311273 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2009-12-07 | 2019-11-27 | 2019-11-27 | 2019-11-27 | 2019-11-27 |  | اخرى |  | 42.5249 | 18.4661 | منجز | No
2100037785 | وزارة النقل والخدمات اللوجستية / منطقة الرياض | تشييد | ذات اولوية متوسطة | 12221060.81 | 611053.0405 | 9924785 | 9924785 | 1010171813 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-01-17 | 2021-12-14 | 2022-07-31 | 2022-07-31 | 2021-12-14 |  | اخرى |  | 46.5745 | 24.9001 | منجز | No
2100070582 | وزارة النقل والخدمات اللوجستية / منطقة نجران | تشييد | ذات اولوية متوسطة | 145841128.72 | 7292056.436 | 56069634.84 | 51532997.84 | 3550019957 | لا | 0 | 180701021238 | مسحوب | الكميات التي تم تركيبها | 40.23 | 100 | 2013-12-04 | 2021-03-24 | 2021-03-24 | 2021-03-24 |  |  | اخرى |  | 44.2797 | 17.5499 | مسحوب | No
2100054644 | وزارة النقل والخدمات اللوجستية / منطقة الحدود الشمالية | تشييد | ذات اولوية عالية | 74704555.8 | 3735227.79 | 66827717.53 | 66827717.53 | 3450000664 | لا | 0 | 181101276323 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-02-21 | 2020-09-11 | 2022-10-31 | 2022-10-31 | 2020-09-11 |  |  |  | 40.4986 | 31.1525 | منجز | No
2100073150 | وزارة النقل والخدمات اللوجستية / منطقة نجران | تشييد | ذات اولوية عالية | 31349996.7 | 1567499.835 | 18902380 | 18902380 | 5950005891 | لا | 0 | 181109369111 | جاري | الكميات التي تم تركيبها | 94.5 | 91.36 | 2015-03-05 | 2023-03-17 | 2023-03-17 | 2023-03-17 |  |  | اخرى |  | 44.2387 | 17.5812 | منتظم | No
2100035221 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 156702075.93 | 7835103.7965 | 61191339.34 | 61191339.34 | 7001491393 | لا | 0 | 181109365106 | مسحوب | الكميات التي تم تركيبها | 39.09 | 100 | 2015-01-21 | 2017-12-18 | 2023-05-15 | 2023-05-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.8926 | 21.3616 | مسحوب | No
2100021276 | وزارة النقل والخدمات اللوجستية / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 210954574.22 | 10547728.711 | 37266235 | 37266235 | 1116004092 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 19 | 100 | 2009-09-29 | 2014-06-08 | 2014-06-08 | 2014-06-08 |  |  | اخرى |  | 49.8948 | 26.395 | مسحوب | No
2200233671 | وزارة النقل والخدمات اللوجستية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 49040344.9 | 2452017.245 | 14302024.45 | 14302024.45 | 1123000085 | لا | 0 |  | جاري | تكلفة العمل المنجز | 38.79 | 33.09 | 2022-02-16 | 2024-01-24 | 2024-01-24 | 2024-01-24 |  |  |  |  | 50.0463 | 26.4428 | منتظم | No
2200234113 | وزارة النقل والخدمات اللوجستية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 213028155.5 | 10651407.775 | 102058804.16 | 102058804.16 | 1123000085 | نعم | 37266235.49 |  | جاري | تكلفة العمل المنجز | 59 | 57.77 | 2020-04-28 | 2022-09-29 | 2024-04-24 | 2024-04-24 |  |  |  | تم تمديد الجدول الزمني | 50.0935 | 26.3892 | منتظم | No
2200234124 | وزارة النقل والخدمات اللوجستية / المنطقة الشرقية | تشييد | ذات اولوية عالية | 394759336.65 | 19737966.8325 | 128499144 | 128499144 | 2050024197 | لا | 0 |  | جاري | تكلفة العمل المنجز | 41.5 | 41.98 | 2020-11-12 | 2022-11-02 | 2024-06-07 | 2024-06-07 |  |  |  | تم تمديد الجدول الزمني | 50.0202 | 26.663 | منتظم | No
2100038614 | وزارة النقل والخدمات اللوجستية / منطقة حائل | تشييد | ذات اولوية عالية وعاجلة | 56419861.48 | 2820993.074 | 46110971.55 | 0 | 1123000085 | لا | 0 | 190501020072 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-09-15 | 2021-02-28 | 2021-09-26 | 2021-09-26 | 2021-02-28 |  |  |  | 41.706 | 27.4207 | منجز | Yes
2100053303 | وزارة النقل والخدمات اللوجستية / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 77545292 | 3877264.6 | 38887852.8 | 38887852.8 | 2050009685 | لا | 0 | 180601014436 | ايقاف جزئي | الكميات التي تم تركيبها | 54 | 56.6 | 2018-09-11 | 2020-11-10 | 2022-06-29 | 2022-06-29 |  |  |  |  | 50.0695 | 26.4051 | متأخر | No
2100072962 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 84989746.5 | 4249487.325 | 73233181.81 | 73233181.81 | 5851000110 | لا | 0 | 181109239190 | جاري | الكميات التي تم تركيبها | 92.5 | 93.2 | 2018-02-25 | 2020-08-07 | 2022-01-11 | 2022-01-11 |  |  |  |  | 42.6466 | 20.0287 | متأخر | No
2100084243 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 69346142.5 | 3467307.125 | 58286819.69 | 58286819.69 | 1116001737 | لا | 0 | 190709116194 | جاري | الكميات التي تم تركيبها | 87.59 | 100 | 2013-10-23 | 2016-09-18 | 2022-08-25 | 2022-08-25 |  |  |  |  | 39.9514 | 21.3053 | متأخر | No
2100077346 | وزارة النقل والخدمات اللوجستية / منطقة الباحة | تشييد | ذات اولوية متوسطة | 73332323 | 3666616.15 | 47120248 | 47120248 | 5900007895 | لا | 0 | 180701021620 | مسحوب | الكميات التي تم تركيبها | 57.8 | 100 | 2013-11-27 | 2017-10-14 | 2020-11-04 | 2020-11-04 |  |  |  |  | 41.4713 | 20.0217 | مسحوب | No
2200223182 | وزارة النقل والخدمات اللوجستية / منطقة المدينة المنورة | تشييد | ذات اولوية متوسطة | 34366834.55 | 1718341.7275 | 25142079.5 | 25142079.5 | 1010184457 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 74.9 | 100 | 2012-06-23 | 2015-09-16 | 2015-09-16 | 2015-09-16 |  |  | ضعف كفاءة المقاول الفنية |  | 39.8457 | 23.2984 | مسحوب | No
2100069731 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 331866639.53 | 16593331.9765 | 298679975.58 | 298679975.58 | 1010017123 | نعم | 378410872 | 180501005716 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-07-05 | 2020-06-12 | 2022-04-29 | 2022-04-29 | 2020-06-12 |  |  |  | 39.5782 | 21.4075 | منجز | No
2100093940 | وزارة النقل والخدمات اللوجستية / منطقة جازان | تشييد | ذات اولوية متوسطة | 30147841.92 | 1507392.096 | 14894411.2 | 14894411.2 | 5858014051 | لا | 0 | 181109327729 | مسحوب | الكميات التي تم تركيبها | 70.23 | 100 | 2011-02-15 | 2014-11-04 | 2017-10-07 | 2017-10-07 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.6269 | 17.579 | مسحوب | No
2100039126 | وزارة النقل والخدمات اللوجستية / منطقة جازان | تشييد | ذات اولوية متوسطة | 14400000 | 720000 | 1294000 | 1294000 | 1010080784 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 9.39 | 100 | 2012-07-31 | 2014-07-08 | 2021-06-16 | 2021-06-16 |  |  | اخرى |  | 43.1335 | 16.8731 | مسحوب | No
2100037660 | وزارة النقل والخدمات اللوجستية / منطقة جازان | تشييد | ذات اولوية متوسطة | 11426100 | 571305 | 522000 | 522000 | 1010080784 | لا | 0 | 181101276243 | فسخ العقد | الكميات التي تم تركيبها | 0 | 0 | 2013-09-01 | 2015-08-09 | 2015-08-09 | 2015-08-09 |  |  | اخرى |  | 43.0996 | 16.7979 | مسحوب | No
2100038640 | وزارة النقل والخدمات اللوجستية / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 26164800 | 1308240 | 12247912 | 12247912 | 2050045542 | نعم | 12247912 |  | مسحوب | الكميات التي تم تركيبها | 48 | 61 | 2012-06-13 | 2016-04-29 | 2016-04-29 | 2016-04-29 |  |  | اخرى |  | 49.7311 | 25.4204 | مسحوب | No
2100028350 | وزارة النقل والخدمات اللوجستية / منطقة الحدود الشمالية | تشييد | ذات اولوية عالية | 187362500 | 9368125 | 168626250.67 | 168626250.67 | 1010090968 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-07-22 | 2020-02-22 | 2022-05-18 | 2022-05-18 | 2020-02-22 |  |  |  | 41.0376 | 30.9513 | منجز | No
2100054353 | وزارة النقل والخدمات اللوجستية / منطقة نجران | تشييد | ذات اولوية متوسطة | 90000000 | 4500000 | 83670621 | 83670621 | 1010080784 | لا | 0 | 181109357876 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2011-08-01 | 2015-04-28 | 2020-10-19 | 2020-10-19 | 2015-04-28 |  | اخرى |  | 44.1996 | 17.5959 | منجز | No
2100196066 | وزارة النقل والخدمات اللوجستية / منطقة الباحة | تشييد | ذات اولوية متوسطة | 218564497.91 | 10928224.8955 | 91209044.75 | 91209044.75 | 1010017123 | لا | 0 |  | جاري | تكلفة العمل المنجز | 59 | 57.11 | 2020-10-28 | 2022-09-27 | 2023-10-17 | 2023-10-17 |  |  |  |  | 41.4713 | 20.0217 | منتظم | No
2100031603 | وزارة النقل والخدمات اللوجستية / منطقة القصيم | تشييد | ذات اولوية متوسطة | 10435023.15 | 521751.1575 | 6239247.3 | 6239247.3 | 1010011059 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-12-03 | 2016-02-13 | 2021-09-16 | 2021-09-16 | 2016-02-13 |  | اخرى |  | 43.9681 | 26.4984 | منجز | No
2100070943 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 71920820.4 | 3596041.02 | 55400780.59 | 54022588 | 1010132469 | لا | 0 | 181109357618 | فسخ العقد | الكميات التي تم تركيبها | 77.03 | 100 | 2012-12-10 | 2020-12-03 | 2020-09-28 | 2020-09-28 |  |  | اخرى |  | 42.4844 | 18.2538 | مسحوب | No
2100084151 | وزارة النقل والخدمات اللوجستية / منطقة جازان | تشييد | ذات اولوية متوسطة | 67120142.95 | 3356007.1475 | 17907604.01 | 17907604.01 | 1010152168 | لا | 0 | 181109347050 | فسخ العقد | الكميات التي تم تركيبها | 33.5 | 100 | 2012-09-08 | 2016-07-25 | 2021-06-02 | 2021-06-02 |  |  | اخرى |  | 42.9393 | 17.2377 | مسحوب | No
2100077490 | وزارة النقل والخدمات اللوجستية / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 96024445 | 4801222.25 | 56244682.98 | 56244682.98 | 2051000654 | لا | 0 | 13400148 | جاري | الكميات التي تم تركيبها | 59.62 | 100 | 2014-02-20 | 2017-12-19 | 2017-07-19 | 2017-07-19 |  |  | اخرى |  | 49.6519 | 26.2236 | Failed | No
2100070420 | وزارة النقل والخدمات اللوجستية / منطقة نجران | تشييد | ذات اولوية عالية | 189158043 | 9457902.15 | 189158043 | 189158043 | 1010210667 | لا | 0 | 180701021602 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2012-11-28 | 2019-05-30 | 2021-02-08 | 2021-02-08 | 2019-05-30 |  |  |  | 46.7322 | 17.5286 | منجز | No
2100195904 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية عالية | 80000000 | 4000000 | 35175624.86 | 35175624.86 | 5855028046 | لا | 0 | 180701029051 | جاري | الكميات التي تم تركيبها | 52.17 | 63.1 | 2018-09-27 | 2021-02-28 | 2023-07-13 | 2023-07-13 |  |  |  |  | 42.5902 | 19.9764 | متأخر | No
2100070490 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 90549805.95 | 4527490.2975 | 62338070.2 | 62338070.2 | 3550019957 | لا | 0 | 180801057822 | مسحوب | الكميات التي تم تركيبها | 70.95 | 100 | 2009-09-16 | 2012-03-25 | 2019-02-20 | 2019-02-20 |  |  | اخرى |  | 42.781 | 18.2895 | مسحوب | No
2100038275 | وزارة النقل والخدمات اللوجستية / منطقة جازان | تشييد | ذات اولوية عالية | 293765703.52 | 14688285.176 | 161825052 | 161825052 | 1010039430 | لا | 0 | 181109339208 | جاري | الكميات التي تم تركيبها | 77.8 | 73.46 | 2013-11-19 | 2017-10-05 | 2023-06-04 | 2023-06-04 |  |  |  |  | 42.4181 | 17.3151 | منتظم | No
2100037881 | وزارة النقل والخدمات اللوجستية / منطقة نجران | تشييد | ذات اولوية متوسطة | 47500000 | 2375000 | 0 | 0 | 5950005891 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 0 | 0 | 2015-03-05 | 2017-02-10 | 2017-02-10 | 2017-02-10 |  |  | اخرى |  | 44.2241 | 17.5605 | مسحوب | No
2100038323 | وزارة النقل والخدمات اللوجستية / منطقة جازان | تشييد | ذات اولوية متوسطة | 3799999.05 | 189999.9525 | 0 | 0 | 5858014051 | لا | 0 | 181109368859 | فسخ العقد | الكميات التي تم تركيبها | 0 | 0 | 2013-12-04 | 2015-02-18 | 2021-05-02 | 2021-05-02 |  |  | اخرى |  | 42.2658 | 17.7336 | مسحوب | No
2100053911 | وزارة النقل والخدمات اللوجستية / منطقة القصيم | تشييد | ذات اولوية متوسطة | 135849752.15 | 6792487.6075 | 73433861.5 | 73433861.5 | 1116001737 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 60.87 | 60.87 | 2013-11-26 | 2015-11-04 | 2023-09-17 | 2023-09-17 |  |  |  |  | 43.2126 | 25.1438 | منتظم | No
2100025340 | وزارة النقل والخدمات اللوجستية / منطقة القصيم | تشييد | ذات اولوية متوسطة | 133874846.6 | 6693742.33 | 120487361.94 | 120487361.94 | 1123000085 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 97.07 | 82.85 | 2015-06-04 | 2018-05-04 | 2024-02-06 | 2024-02-06 |  |  | اخرى |  | 43.9112 | 26.2962 | منتظم | No
2100094382 | وزارة النقل والخدمات اللوجستية / منطقة حائل | تشييد | ذات اولوية عالية وعاجلة | 136404779 | 6820238.95 | 87366362 | 83267876 | 2060002548 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 66 | 76 | 2013-10-23 | 2020-04-10 | 2020-04-10 | 2020-04-10 |  |  | اخرى |  | 41.7316 | 27.4283 | مسحوب | No
2100019795 | وزارة النقل والخدمات اللوجستية / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 77365024.95 | 3868251.2475 | 247902.38 | 247902.38 | 1010137467 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 65.5 | 71.59 | 2019-04-03 | 2023-09-09 | 2023-10-15 | 2023-10-15 |  |  |  |  | 47.6996 | 27.5764 | متأخر | No
2100053653 | وزارة النقل والخدمات اللوجستية / منطقة جازان | تشييد | ذات اولوية متوسطة | 17094154.57 | 854707.7285 | 7192165.26 | 7192165.26 | 1010214056 | لا | 0 | 181101224009 | جاري | الكميات التي تم تركيبها | 60 | 56.8 | 2019-01-17 | 2019-10-09 | 2023-03-14 | 2023-03-14 |  |  | اخرى |  | 42.8443 | 16.9692 | منتظم | No
2100048694 | الهيئة العامة للموانئ | تشييد | ذات اولوية عالية | 12842238 | 642111.9 | 11488568.54 | 11488568.54 | 2052001971 | لا | 0 |  | جاري | تكلفة العمل المنجز | 96 | 100 | 2013-10-29 | 2014-10-29 | 2021-12-31 | 2021-12-31 |  |  | تصاريح أعمال التنفيذ |  | 50.2182 | 26.4967 | Failed | No
2100015061 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 90835977.9 | 4541798.895 | 74183104 | 74183104 | 5855005058 | لا | 0 | 181109350839 | فسخ العقد | الكميات التي تم تركيبها | 94 | 100 | 2011-12-12 | 2015-02-05 | 2015-02-05 | 2015-02-05 |  |  |  |  | 42.6195 | 18.1826 | مسحوب | No
2200220636 | وزارة النقل والخدمات اللوجستية / منطقة الجوف | تشييد | ذات اولوية متوسطة | 14998273.55 | 749913.6775 | 0 | 0 | 1010412530 | نعم | 99870894 | 220101077081 | جاري | تكلفة العمل المنجز | 8 | 29 | 2022-03-08 | 2023-03-07 | 2023-03-07 | 2023-03-07 |  |  |  |  | 40.1767 | 29.8349 | متأخر | No
2100195963 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية عالية | 31999950.7 | 1599997.535 | 8460862.32 | 7571620.25 | 1010009590 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 27.2 | 26.4 | 2020-04-16 | 2021-10-07 | 2024-05-23 | 2024-05-23 |  |  |  |  | 42.779 | 18.162 | منتظم | No
2100053922 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 50840150 | 2542007.5 | 31921469 | 31921469 | 5855028046 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 77.13 | 77.13 | 2013-09-29 | 2019-10-22 | 2019-07-24 | 2019-07-24 | 2019-10-22 |  |  |  | 42.5053 | 18.3384 | منجز | No
2100024684 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1959597 | 97979.85 | 1830719 | 1830719 | 3350001367 | لا | 0 |  | مسحوب | التكلفة المفوترة | 85 | 100 | 2010-05-31 | 2011-07-24 | 2021-12-28 | 2021-12-28 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | مسحوب | No
2100048812 | الهيئة العامة للموانئ | توريد وتركيب | ذات اولوية عالية | 47611688.7 | 2380584.435 | 44053237.66 | 44053237.66 | 2050001536 | لا | 0 | 180909096928 | جاري | تكلفة العمل المنجز | 97.5 | 100 | 2014-06-23 | 2016-06-23 | 2022-06-30 | 2022-06-30 |  |  | ضعف كفاءة المقاول الفنية |  | 50.1949 | 26.4779 | Failed | No
2100154151 | الهيئة العامة للموانئ | توريد وتركيب | ذات اولوية عالية | 5650500 | 282525 | 897829 | 897829 | 1010437469 | لا | 0 | 190201003788 | جاري | تكلفة العمل المنجز | 40 | 100 | 2019-03-10 | 2019-12-10 | 2022-09-30 | 2022-09-30 |  |  | تغيرات في نطاق المشروع |  | 50.199 | 26.4938 | Failed | No
2100067686 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 9413468.44 | 470673.422 | 5683391.64 | 0 | 3350003498 | لا | 0 |  | جاري | التكلفة المفوترة | 65 | 100 | 2013-04-17 | 2015-04-07 | 2021-12-15 | 2021-12-15 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | Failed | Yes
2100096541 | الهيئة العامة للموانئ | إشراف | ذات اولوية عالية | 3120000 | 156000 | 3120000 | 3120000 | 1010322156 | لا | 0 | 181109291983 | جاري | تكلفة العمل المنجز | 100 | 100 | 2014-12-10 | 2016-12-09 | 2022-03-31 | 2022-03-31 |  |  | ضعف كفاءة المقاول الفنية |  | 50.1965 | 26.4832 | خدمات عامة | No
2100153941 | الهيئة العامة للموانئ | ترميم | ذات اولوية عالية | 3350900 | 167545 | 176040 | 176040 | 2050064138 | لا | 0 | 180809044505 | ايقاف كلي | تكلفة العمل المنجز | 20 | 100 | 2018-09-13 | 2019-06-10 | 2022-12-31 | 2022-12-31 |  |  | تغيرات في نطاق المشروع |  | 50.2024 | 26.4744 | Failed | No
2100154081 | الهيئة العامة للموانئ | توريد وتركيب | ذات اولوية عالية | 240311728 | 12015586.4 | 197946613 | 197946613 | 1010070514 | لا | 0 | 181109291983 | جاري | تكلفة العمل المنجز | 88.87 | 100 | 2014-01-20 | 2016-01-20 | 2022-03-31 | 2022-03-31 |  |  |  |  | 50.1837 | 26.4552 | Failed | No
2100017496 | الهيئة العامة للموانئ | تشييد | ذات اولوية عالية | 11348380 | 567419 | 10470762 | 10470762 | 2060024520 | لا | 0 | 180809046506 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-05-29 | 2016-05-28 | 2021-12-31 | 2021-12-31 |  |  | تصاريح أعمال التنفيذ |  | 50.1949 | 26.4786 | Failed | No
2100154136 | الهيئة العامة للموانئ | تصميم | ذات اولوية عالية | 3064695 | 153234.75 | 208312 | 208312 | 2051025367 | لا | 0 | 181201445043 | جاري | تكلفة العمل المنجز | 85 | 100 | 2019-01-24 | 2021-01-13 | 2022-03-31 | 2022-03-31 |  |  |  |  | 50.1877 | 26.4725 | Failed | No
2200235712 | الهيئة العامة للموانئ | تشييد | ذات اولوية عالية وعاجلة | 257597.7 | 12879.885 | 0 | 0 | 1010155869 | لا | 0 |  | جاري | تكلفة العمل المنجز | 90 | 100 | 2022-07-28 | 2022-11-28 | 2022-11-28 | 2022-11-28 |  |  |  |  | 50.1948 | 26.4719 | متأخر | No
2200219903 | الهيئة العامة للموانئ | أخرى | ذات اولوية عالية | 65637619 | 3281880.95 | 0 | 0 | 2050050438 | لا | 0 | 201001108406 | جاري | تكلفة العمل المنجز | 15.1 | 63 | 2021-02-14 | 2023-02-04 | 2024-02-20 | 2024-02-20 |  |  |  |  | 50.1949 | 26.4787 | خدمات عامة | No
2100088524 | جامعة طيبة | تشييد | ذات اولوية عالية | 6070743 | 303537.15 | 2256000 | 2256000 | 5911015317 | لا | 0 | 180909071232 | ايقاف كلي | تكلفة العمل المنجز | 34 | 100 | 2017-07-23 | 2018-01-19 | 2024-11-03 | 2024-11-03 |  |  | سوء التخطيط الاولي للمشروع | مخطط لفسخ العقد | 37.9616 | 24.1791 | Failed | No
2100006801 | جامعة طيبة | تشييد | ذات اولوية عالية | 6300000 | 315000 | 2006000 | 2006000 | 5911015317 | لا | 0 | 180909071228 | ايقاف كلي | تكلفة العمل المنجز | 32 | 100 | 2017-07-25 | 2018-01-21 | 2024-11-03 | 2024-11-03 |  |  | ضعف كفاءة المقاول الفنية | مخطط لفسخ العقد | 37.9733 | 26.4848 | Failed | No
2200231862 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 8414512.18 | 420725.609 | 0 | 0 | 4030148791 | نعم | 42199996.58 |  | جاري | الكميات التي تم تركيبها | 0.55 | 6.6 | 2022-09-14 | 2023-09-09 | 2023-09-09 | 2023-09-09 |  |  |  |  | 40.477 | 21.2269 | متأخر | No
2200231851 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 10994131.57 | 549706.5785 | 0 | 0 | 4031049008 | نعم | 57000000 |  | جاري | الكميات التي تم تركيبها | 0 | 4 | 2022-09-14 | 2023-09-02 | 2023-09-02 | 2023-09-02 |  |  |  |  | 40.5115 | 21.2408 | منتظم | No
2100056254 | وزارة الصحة / جازان | تشييد | ذات اولوية متوسطة | 5920025 | 296001.25 | 504533.52 | 504533.52 | 5950011052 | لا | 0 | 190901120169 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-03-19 | 2021-11-19 | 2021-11-01 | 2021-11-01 | 2021-11-19 |  |  |  | 42.8338 | 16.6061 | منجز | No
2100102480 | وزارة الصحة / جازان | تشييد | ذات اولوية منخفضة | 4999960 | 249998 | 392000 | 392000 | 1010215470 | لا | 0 | 201201032148 | ايقاف كلي | تكلفة العمل المنجز | 1 | 1 | 2017-01-01 | 2019-01-01 | 2023-12-31 | 2023-12-31 |  |  | نزع الملكيات |  | 42.8338 | 17.6165 | Failed | No
2100192500 | صندوق التنمية الزراعية | تشييد | ذات اولوية متوسطة | 7210969.5 | 360548.475 | 2383910.05 | 2383910.05 | 7015096691 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 72 | 93 | 2021-05-25 | 2022-07-24 | 2023-02-20 | 2023-02-20 |  |  |  | تم تمديد الجدول الزمني | 42.645 | 18.2365 | متأخر | No
2100040913 | وزارة الصحة / جازان | تشييد | ذات اولوية عالية | 68757027.36 | 3437851.368 | 23051236.93 | 23051236.93 | 4030139128 | نعم | 14049968.61 |  | مسحوب | تكلفة العمل المنجز | 20.43 | 100 | 2015-04-06 | 2017-04-06 | 2017-12-06 | 2017-12-06 |  |  | تأخرصرف المستحقات المالية |  | 42.6268 | 16.9995 | مسحوب | No
2100073920 | وزارة الصحة / جازان | تشييد | ذات اولوية عالية | 20477883 | 1023894.15 | 2316339.2 | 2316339.2 | 5950004973 | لا | 0 | 201109311605 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2021-02-21 | 2022-02-20 | 2021-11-15 | 2021-11-15 | 2022-02-20 |  |  |  | 42.8338 | 16.6061 | منجز | No
2100082644 | أمانة / الرياض | تشييد | ذات اولوية عالية | 32480172 | 1624008.6 | 20707950 | 17165677 | 1010159271 | لا | 0 | 181101227273 | جاري | الكميات التي تم تركيبها | 64 | 92 | 2019-01-23 | 2021-01-22 | 2022-12-14 | 2022-12-14 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 46.68 | 24.7032 | Failed | No
2100025071 | أمانة / الرياض | تشييد | ذات اولوية عالية | 67225645 | 3361282.25 | 34016699 | 29246509 | 1010159271 | لا | 0 | 181101229427 | جاري | الكميات التي تم تركيبها | 49 | 100 | 2019-01-23 | 2021-01-22 | 2022-12-22 | 2022-12-22 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 46.6773 | 24.7032 | Failed | No
2100067362 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 36776992.92 | 1838849.646 | 27547732 | 22440153 | 1010269830 | لا | 0 | 190301055254 | جاري | الكميات التي تم تركيبها | 82 | 83 | 2019-06-12 | 2021-06-11 | 2023-03-16 | 2023-03-16 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6786 | 24.7057 | منتظم | No
2100035556 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 95077588 | 4753879.4 | 64404787 | 43911828 | 1010010506 | لا | 0 | 190301022659 | جاري | الكميات التي تم تركيبها | 68 | 65 | 2019-06-11 | 2021-06-10 | 2023-08-21 | 2023-08-21 |  |  |  |  | 46.6786 | 24.7057 | منتظم | No
2100049641 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 95003914 | 4750195.7 | 53817168 | 42544539 | 1010010506 | لا | 0 | 190301022542 | جاري | الكميات التي تم تركيبها | 58 | 76 | 2019-06-13 | 2021-06-12 | 2023-04-23 | 2023-04-23 |  |  |  |  | 46.6786 | 24.7082 | متأخر | No
2100049722 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 50000000 | 2500000 | 50218955 | 44859383 | 1010010506 | لا | 0 | 190301027167 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-06-13 | 2021-06-12 | 2022-08-23 | 2022-08-23 | 2021-06-12 |  | ضعف كفاءة المقاول الفنية |  | 46.6841 | 24.7044 | منجز | No
2100035571 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 37395015 | 1869750.75 | 34396443 | 32558305 | 1010269830 | لا | 0 | 190201046738 | جاري | الكميات التي تم تركيبها | 90 | 83 | 2019-06-12 | 2021-06-11 | 2023-02-11 | 2023-02-11 |  |  |  |  | 46.6704 | 24.7057 | منتظم | No
2100025093 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 15973965 | 798698.25 | 14604456 | 14604456 | 1010269830 | لا | 0 | 190301027031 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-06-12 | 2020-06-11 | 2022-02-28 | 2022-02-28 | 2020-06-11 |  |  |  | 46.6731 | 24.7107 | منجز | No
2100050083 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 15998640 | 799932 | 15118204 | 15118204 | 1010269830 | لا | 0 | 190201046928 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-06-12 | 2020-06-11 | 2021-06-12 | 2021-06-12 | 2020-06-11 |  |  |  | 46.6814 | 24.7007 | منجز | No
2200231582 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 79744662.5 | 3987233.125 | 45373198 | 30296731 | 4030034104 | لا | 0 | 180809057601 | جاري | التكلفة المفوترة | 55 | 88 | 2021-04-01 | 2023-04-01 | 2023-04-01 | 2023-04-01 |  |  |  |  | 46.7219 | 24.7927 | Failed | No
2200231604 | أمانة / الرياض | إشراف | ذات اولوية عالية | 34650000 | 1732500 | 18441857.6 | 18441857.6 | 7012035502 | لا | 0 | 200901168575 | جاري | التكلفة المفوترة | 55 | 60 | 2021-01-20 | 2024-01-19 | 2022-01-19 | 2022-01-19 |  |  |  |  | 46.6736 | 24.6258 | خدمات عامة | No
2100102126 | وزارة الصحة / جدة | تشييد | ذات اولوية عالية وعاجلة | 845480 | 42274 | 416964.84 | 416964.84 | 4030342353 | لا | 0 | 190401019116 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-03-26 | 2019-06-25 | 2022-08-31 | 2022-08-31 | 2019-06-25 |  | ضعف كفاءة المقاول الفنية |  | 39.2101 | 21.4459 | منجز | No
2100040504 | وزارة الصحة / جدة | تشييد | ذات اولوية عالية | 12300657 | 615032.85 | 11033577 | 11033577 | 4030163543 | لا | 0 | 181109257531 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-05-03 | 2017-05-08 | 2022-06-30 | 2022-06-30 | 2017-05-08 |  | ضعف كفاءة المقاول الفنية | أخرى | 40.6637 | 20.5344 | منجز | No
2100056431 | وزارة الصحة / الطائف | تشييد | ذات اولوية عالية | 106500000 | 5325000 | 29556026.4 | 29556026 | 1010077408 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 99 | 100 | 2018-02-12 | 2019-02-02 | 2021-12-31 | 2021-12-31 | 2019-02-02 |  | تأخرصرف المستحقات المالية |  | 40.4537 | 21.2451 | منجز | No
2100073872 | وزارة الصحة / جدة | تشييد | ذات اولوية عالية | 2982000 | 149100 | 2982000 | 2982000 | 1010185891 | لا | 0 | 190401018718 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-04-01 | 2019-11-30 | 2022-10-31 | 2022-10-31 | 2019-11-30 |  | أوامر تغيير |  | 39.0342 | 22.7741 | منجز | No
2200236294 | الهيئة العامة للموانئ | توريد وتركيب | ذات اولوية متوسطة | 345000 | 17250 | 310468.95 | 310468.95 | 2055009148 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2022-07-24 | 2022-11-19 | 2022-11-19 | 2022-11-19 | 2022-11-19 |  |  |  | 49.6642 | 27.0178 | منجز | No
2100078385 | وزارة الصحة / جدة | تشييد | ذات اولوية عالية وعاجلة | 5037066 | 251853.3 | 3474622.74 | 3474622.74 | 4030207911 | نعم | 2021060.87 | 181009139146 | مسحوب | الكميات التي تم تركيبها | 100 | 100 | 2017-08-12 | 2019-05-31 | 2021-02-16 | 2021-02-16 |  |  | منازعات قائمة |  | 39.2142 | 21.5801 | مسحوب | No
2100022422 | وزارة الصحة / جدة | تشييد | ذات اولوية عالية وعاجلة | 60043696.41 | 3002184.8205 | 52915656.7 | 52915656.7 | 4030096631 | لا | 0 | 181109257663 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-06-11 | 2016-11-23 | 2016-11-23 | 2016-11-23 | 2016-11-23 |  |  |  | 39.1902 | 21.4828 | منجز | No
2100078326 | وزارة الصحة / جدة | تشييد | ذات اولوية عالية وعاجلة | 36974380 | 1848719 | 20905350 | 20905350 | 1010162957 | لا | 0 | 190801004942 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-02-23 | 2019-09-17 | 2020-09-07 | 2020-09-07 | 2019-09-17 |  | ضعف كفاءة المقاول الفنية |  | 39.1669 | 21.5436 | منجز | No
2100085116 | وزارة الصحة / جدة | تشييد | ذات اولوية عالية وعاجلة | 9687393 | 484369.65 | 3399544 | 3399544 | 5855001993 | لا | 0 | 181009149340 | جاري | الكميات التي تم تركيبها | 100 | 100 | 2014-09-01 | 2019-02-28 | 2019-08-13 | 2019-08-13 |  |  | منازعات قائمة |  | 39.2057 | 21.4459 | Failed | No
2200234964 | الهيئة العامة للموانئ | توريد وتركيب | ذات اولوية منخفضة | 977500 | 48875 | 879750 | 879750 | 2055009148 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2022-06-19 | 2022-11-19 | 2022-11-19 | 2022-11-19 | 2022-11-19 |  |  |  | 49.6642 | 27.0178 | منجز | No
2100096040 | وزارة الصحة / جدة | تشييد | ذات اولوية عالية وعاجلة | 101052500 | 5052625 | 101052500 | 101052500 | 4030045393 | لا | 0 | 190709152510 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-07-26 | 2019-03-10 | 2019-03-11 | 2019-03-11 | 2019-03-10 |  |  |  | 39.1669 | 21.5436 | منجز | No
2100058376 | أمانة / الباحة | تشييد | ذات اولوية عالية | 1817440 | 90872 | 1817440 | 0 | 5806008614 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-11-06 | 2020-10-27 | 2021-06-13 | 2021-06-13 | 2020-10-27 |  |  |  | 41.4362 | 19.756 | منجز | Yes
2300237672 | أمانة / الباحة | تشييد | ذات اولوية عالية | 1895085 | 94754.25 | 1705576.5 | 0 | 4030006066 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2022-08-17 | 2023-01-17 | 2023-01-17 | 2023-01-17 | 2023-01-17 |  |  |  | 41.4362 | 19.756 | منجز | Yes
2100180865 | جامعة حائل | تشييد | ذات اولوية عالية | 283248043 | 14162402.15 | 127399138.55 | 127399138.55 | 4030276223 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 4 | 93 | 2013-11-10 | 2021-08-25 | 2021-08-25 | 2021-08-25 |  |  |  |  | 41.7149 | 27.6666 | Failed | No
2100035910 | أمانة / الباحة | تشييد | ذات اولوية عالية | 4549355 | 227467.75 | 4429355 | 3775964.65 | 5806008614 | لا | 0 | 181101273893 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-04-06 | 2021-04-14 | 2022-08-01 | 2022-08-01 | 2021-04-14 |  | تأخرصرف المستحقات المالية |  | 41.4362 | 19.756 | منجز | No
2100092551 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 4998350 | 249917.5 | 4998350 | 4998350 | 5800007789 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-04-13 | 2021-04-21 | 2021-04-02 | 2021-04-02 | 2021-04-21 |  | تأخرصرف المستحقات المالية |  | 41.4362 | 19.756 | منجز | No
2300237661 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 1034100 | 51705 | 0 | 0 | 5901009711 | لا | 0 |  | جاري | تكلفة العمل المنجز | 35 | 40 | 2022-11-02 | 2023-05-02 | 2023-05-02 | 2023-05-02 |  |  |  |  | 41.4362 | 19.756 | منتظم | No
2100019843 | أمانة / الباحة | تشييد | ذات اولوية عالية | 29991304 | 1499565.2 | 17216158 | 2406575 | 4030006066 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 58 | 79 | 2019-05-25 | 2022-04-21 | 2023-10-11 | 2023-10-11 |  |  | تأخرصرف المستحقات المالية |  | 41.4362 | 19.756 | متأخر | No
2100068622 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 12232936 | 611646.8 | 10459680 | 10459680 | 3350014401 | لا | 0 | 181001170480 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-12-16 | 2020-12-05 | 2020-12-05 | 2020-12-05 | 2020-12-05 |  |  |  | 41.7193 | 27.5082 | منجز | No
2100093122 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 9432104 | 471605.2 | 2137317 | 2137317 | 3350000614 | لا | 0 | 190301003842 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-05-05 | 2021-04-24 | 2022-08-31 | 2022-08-31 | 2021-04-24 |  |  | تم إنذار المقاول كتابيا | 41.7208 | 27.5114 | منجز | No
2100067782 | أمانة / حائل | تشييد | ذات اولوية عالية وعاجلة | 8370545 | 418527.25 | 0 | 0 | 3350014401 | لا | 0 | 181101263181 | جاري | الكميات التي تم تركيبها | 85 | 90 | 2019-05-01 | 2020-10-22 | 2023-05-10 | 2023-05-10 |  |  |  | تم إنذار المقاول كتابيا | 41.7208 | 27.5114 | منتظم | No
2100029470 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 8985413.9 | 449270.695 | 8985413.9 | 5466756 | 3350000614 | لا | 0 | 180901071577 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-10-09 | 2020-04-13 | 2022-10-11 | 2022-10-11 | 2020-04-13 |  |  | تم إشعار المقاول كتابيا بالتأخير | 41.7208 | 27.5114 | منجز | No
2100082832 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 12244443 | 612222.15 | 5862039 | 5862039 | 3350014401 | لا | 0 | 190201000431 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-03-02 | 2021-02-19 | 2021-02-19 | 2021-02-19 | 2021-02-19 |  |  |  | 41.71 | 27.4964 | منجز | No
2100014173 | أمانة / الباحة | تشييد | ذات اولوية عالية وعاجلة | 15270112 | 763505.6 | 15270112 | 11721493 | 4030006066 | لا | 0 | 181101273893 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-01-27 | 2021-01-05 | 2022-12-30 | 2022-12-30 | 2021-01-05 |  | تأخرصرف المستحقات المالية |  | 41.4362 | 19.756 | منجز | No
2100068386 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 8667464 | 433373.2 | 4452255.65 | 4452255.65 | 4031055225 | لا | 0 | 181009219623 | جاري | الكميات التي تم تركيبها | 59 | 100 | 2015-05-24 | 2017-05-02 | 2023-12-30 | 2023-12-30 |  |  | تأخرصرف المستحقات المالية |  | 41.4362 | 19.756 | Failed | No
2200212914 | وزارة الصحة / الجوف | ترميم | ذات اولوية عالية | 2828309 | 141415.45 | 25482.93 | 0 | 3400014575 | لا | 0 | 220701125214 | جاري | الكميات التي تم تركيبها | 10 | 35 | 2022-04-10 | 2023-01-31 | 2023-04-30 | 2023-04-30 |  |  |  | أخرى | 38.2234 | 30.4942 | Failed | Yes
2100050120 | أمانة / القصيم | تشييد | ذات اولوية متوسطة | 1372400 | 68620 | 1072400 | 1072400 | 1131044249 | لا | 0 | 181209442665 | جاري | تكلفة العمل المنجز | 80.5 | 81 | 2018-07-22 | 2023-10-14 | 2023-10-14 | 2023-10-14 |  |  | تأخرصرف المستحقات المالية |  | 43.2796 | 26.028 | منتظم | No
2100040073 | وزارة الصحة / الجوف | تشييد | ذات اولوية عالية | 8398537.6 | 419926.88 | 6007338.94 | 6007338.94 | 3400008660 | لا | 0 | 200909019369 | جاري | الكميات التي تم تركيبها | 98 | 100 | 2014-08-09 | 2016-02-08 | 2023-02-15 | 2023-02-15 |  |  | تأخرصرف المستحقات المالية | تم تمديد الجدول الزمني | 40.2188 | 29.8526 | متأخر | No
2100056000 | وزارة الصحة / جدة | تشييد | ذات اولوية عالية وعاجلة | 5215542.95 | 260777.1475 | 987144.48 | 987144.48 | 1010221958 | نعم | 0.01 | 2020262179740 | مسحوب | الكميات التي تم تركيبها | 42 | 100 | 2015-10-18 | 2016-07-11 | 2023-02-17 | 2023-02-17 |  |  | ضعف كفاءة المقاول الفنية |  | 39.1669 | 21.5436 | مسحوب | No
2100094555 | رئاسة الحرس الملكي | تشييد | ذات اولوية عالية وعاجلة | 111500243.3 | 5575012.165 | 29936533.03 | 29936533.03 | 1010019122 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 36 | 100 | 2019-02-06 | 2022-04-07 | 2023-10-26 | 2023-10-26 |  |  |  |  | 39.1475 | 21.5368 | Failed | No
2100078105 | وزارة الصحة / الجوف | تشييد | ذات اولوية عالية وعاجلة | 10000674.19 | 500033.7095 | 2837245.32 | 730133 | 3400011183 | لا | 0 | 220109036752 | جاري | الكميات التي تم تركيبها | 60 | 67 | 2019-12-17 | 2023-04-08 | 2023-04-08 | 2023-04-08 |  |  | تأخرصرف المستحقات المالية | تم تمديد الجدول الزمني | 39.8579 | 29.806 | متأخر | No
2200211433 | وزارة الصحة / الجوف | تشييد | ذات اولوية عالية | 17342472 | 867123.6 | 0 | 0 | 3400010482 | لا | 0 |  | لم يبدأ | الكميات التي تم تركيبها | 0 | 0 | 2022-03-15 | 2023-09-14 | 2023-09-14 | 2023-09-14 |  |  |  |  | 38.253 | 30.4949 | منتظم | No
2100093505 | وزارة الصحة / جدة | تشييد | ذات اولوية عالية | 20271000 | 1013550 | 20271000 | 20271000 | 1010365836 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-08-04 | 2019-03-20 | 2019-11-01 | 2019-11-01 | 2019-03-20 |  |  |  | 39.1669 | 21.5436 | منجز | No
2100067270 | أمانة / القصيم | دراسات هندسية | ذات اولوية عالية | 2443500 | 122175 | 1781000 | 1781000 | 1010327067 | لا | 0 | 190609040121 | جاري | مدفوعات ساعات العمل | 85 | 89 | 2018-09-26 | 2023-05-08 | 2023-05-08 | 2023-05-08 |  |  | ضعف كفاءة المقاول الفنية |  | 43.9937 | 26.2311 | خدمات عامة | No
2100073371 | رئاسة الحرس الملكي | تشييد | ذات اولوية عالية وعاجلة | 3473758.5 | 173687.925 | 3143065.5 | 3143065.5 | 1010270830 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2020-06-14 | 2021-12-14 | 2022-10-01 | 2022-10-01 | 2021-12-14 |  |  |  | 46.6387 | 24.6503 | منجز | No
2100051262 | أمانة / القصيم | تشييد | ذات اولوية متوسطة | 640007067 | 32000353.35 | 549174454.56 | 542862034.87 | 4030007856 | لا | 0 | 180301000858 | جاري | تكلفة العمل المنجز | 74 | 78 | 2018-10-24 | 2023-02-25 | 2023-02-25 | 2023-02-25 |  |  | ضعف كفاءة المقاول الفنية |  | 43.9818 | 26.3592 | منتظم | No
2100200071 | جامعة تبوك | تشييد | ذات اولوية عالية وعاجلة | 31736099.49 | 1586804.9745 | 23283788.35 | 23283788.35 | 3550024769 | نعم | 28346956.57 |  | جاري | تكلفة العمل المنجز | 76 | 77 | 2021-09-28 | 2023-03-25 | 2022-10-25 | 2022-10-25 |  |  |  |  | 36.4828 | 28.3851 | متأخر | No
2100085352 | أمانة / حائل | دراسة الجدوى | ذات اولوية متوسطة | 7118422 | 355921.1 | 7118422 | 6771734 | 1010363372 | لا | 0 | 190401029644 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-05-08 | 2022-04-03 | 2022-05-07 | 2022-05-07 | 2022-04-03 |  | اخرى |  | 41.7208 | 27.5114 | منجز | No
2100069064 | أمانة / القصيم | تشييد | ذات اولوية متوسطة | 252765691 | 12638284.55 | 221372192.1778 | 221372192.1778 | 1131014852 | لا | 0 | 181009193324 | جاري | تكلفة العمل المنجز | 89 | 89 | 2014-08-06 | 2018-08-04 | 2024-08-18 | 2024-08-18 |  |  |  |  | 43.9818 | 26.3592 | منتظم | No
2100192091 | جامعة تبوك | دعم فني | ذات اولوية عالية | 5313000 | 265650 | 5313000 | 5313000 | 1010496830 | لا | 0 | 200801014996 | جاري | مدفوعات ساعات العمل | 100 | 100 | 2020-10-06 | 2022-12-05 | 2022-12-05 | 2022-12-05 |  |  |  |  | 36.4723 | 28.3874 | خدمات عامة | No
2100051251 | أمانة / القصيم | تشييد | ذات اولوية متوسطة | 126091510.75 | 6304575.5375 | 113594065.21 | 113594065.21 | 1131013992 | لا | 0 | 180801039138 | جاري | تكلفة العمل المنجز | 93 | 94 | 2018-11-15 | 2023-03-21 | 2023-03-21 | 2023-03-21 |  |  | ضعف كفاءة المقاول الفنية |  | 43.9818 | 26.3592 | منتظم | No
2100207325 | وزارة الحرس الوطني / وكالة الشؤون الفنية | تشييد | ذات اولوية عالية | 2611931.75 | 130596.5875 | 0 | 0 | 1010345838 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 0 | 1.6 | 2022-11-17 | 2023-11-06 | 2023-11-06 | 2023-11-06 |  |  |  |  | 46.6753 | 24.7136 | منتظم | No
2100015400 | وزارة الصحة / الجوف | تشييد | ذات اولوية عالية وعاجلة | 7170870 | 358543.5 | 6373072.63 | 6373072.63 | 3400009825 | لا | 0 | 181001134642 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2017-12-16 | 2021-02-28 | 2021-01-16 | 2021-01-16 | 2021-02-28 | 2022-02-02 | تأخرصرف المستحقات المالية | تم تمديد الجدول الزمني | 40.193 | 29.9624 | منجز | No
2100200115 | جامعة تبوك | تشييد | ذات اولوية عالية وعاجلة | 408216194.96 | 20410809.748 | 275693761.5 | 272853102.34 | 4030129407 | لا | 0 |  | جاري | تكلفة العمل المنجز | 83.54 | 94 | 2012-03-31 | 2022-11-06 | 2022-11-06 | 2022-11-06 |  |  |  |  | 36.4724 | 28.3876 | متأخر | No
2100052975 | أمانة / القصيم | تشييد | ذات اولوية متوسطة | 270602220 | 13530111 | 189602220 | 189602220 | 1010011560 | لا | 0 | 180801048042 | جاري | تكلفة العمل المنجز | 71 | 75 | 2018-09-12 | 2023-06-23 | 2023-06-23 | 2023-06-23 |  |  | ضعف كفاءة المقاول الفنية |  | 43.9818 | 26.3592 | منتظم | No
2100052835 | أمانة / القصيم | تشييد | ذات اولوية متوسطة | 116719693.65 | 5835984.6825 | 87702957.73 | 87702957.73 | 1131013992 | لا | 0 | 181001164033 | جاري | تكلفة العمل المنجز | 76 | 80 | 2018-11-04 | 2023-07-11 | 2023-07-11 | 2023-07-11 |  |  | تغيرات في نطاق المشروع |  | 43.9818 | 26.3592 | منتظم | No
2200234275 | جامعة تبوك | تشييد | ذات اولوية عالية وعاجلة | 12309605.75 | 615480.2875 | 6233908.5 | 6233908.5 | 5802010434 | لا | 0 |  | جاري | تكلفة العمل المنجز | 60 | 90 | 2022-01-23 | 2023-01-18 | 2023-01-18 | 2023-01-18 |  |  |  |  | 36.4768 | 28.3941 | Failed | No
2100051726 | أمانة / القصيم | تشييد | ذات اولوية عالية | 6835370 | 341768.5 | 5617685 | 5617685 | 1010097188 | لا | 0 | 180809062098 | جاري | تكلفة العمل المنجز | 85 | 87 | 2016-02-15 | 2023-05-15 | 2023-05-15 | 2023-05-15 |  |  | ضعف كفاءة المقاول الفنية |  | 43.5415 | 26.0533 | منتظم | No
2100051796 | أمانة / القصيم | تشييد | ذات اولوية متوسطة | 24595092 | 1229754.6 | 20046497.49 | 20020097.51 | 1131013966 | لا | 0 | 180801039407 | جاري | تكلفة العمل المنجز | 84 | 86 | 2018-11-01 | 2023-07-18 | 2023-07-18 | 2023-07-18 |  |  | نزع الملكيات |  | 43.9818 | 26.3592 | منتظم | No
2100037446 | أمانة / القصيم | تشييد | ذات اولوية عالية | 37920034.7 | 1896001.735 | 35961012.81 | 35950422.49 | 1010074413 | لا | 0 | 180801039164 | جاري | تكلفة العمل المنجز | 96 | 98 | 2018-11-08 | 2023-01-20 | 2023-01-20 | 2023-01-20 |  |  |  |  | 43.991 | 26.2282 | منتظم | No
2200235476 | أمانة / القصيم | تشييد | ذات اولوية عالية | 1217000 | 60850 | 50000 | 50000 | 1135000671 | لا | 0 |  | جاري | تكلفة العمل المنجز | 6 | 10 | 2022-09-26 | 2023-09-20 | 2023-09-20 | 2023-09-20 |  |  |  |  | 43.5222 | 25.8517 | منتظم | No
2200235491 | أمانة / القصيم | تشييد | ذات اولوية عالية | 5972255 | 298612.75 | 4837526.55 | 4837526.55 | 1134001619 | لا | 0 |  | جاري | تكلفة العمل المنجز | 89 | 91 | 2019-12-22 | 2023-04-18 | 2023-04-18 | 2023-04-18 |  |  |  |  | 43.5415 | 26.0533 | منتظم | No
2100092982 | أمانة / القصيم | تشييد | ذات اولوية عالية وعاجلة | 18412300 | 920615 | 15159418.23 | 15159418.23 | 1128001366 | لا | 0 | 180501009756 | جاري | تكلفة العمل المنجز | 90 | 90 | 2019-01-05 | 2021-11-17 | 2023-06-25 | 2023-06-25 |  |  | ضعف كفاءة المقاول الفنية |  | 43.9765 | 26.2349 | منتظم | No
2100002225 | أمانة / القصيم | تشييد | ذات اولوية عالية وعاجلة | 11947552 | 597377.6 | 7025055 | 7025055 | 7003176711 | لا | 0 | 181101274575 | جاري | تكلفة العمل المنجز | 60 | 60 | 2021-09-20 | 2023-09-10 | 2023-09-10 | 2023-09-10 |  |  | تأخرصرف المستحقات المالية |  | 43.9666 | 26.3534 | منتظم | No
2200235421 | أمانة / القصيم | أخرى | ذات اولوية عالية | 119000 | 5950 | 89920.068 | 89920.068 | 1131057745 | لا | 0 |  | جاري | تكلفة العمل المنجز | 88 | 88 | 2022-02-17 | 2023-02-16 | 2023-02-16 | 2023-02-16 |  |  |  |  | 43.9818 | 26.3592 | خدمات عامة | No
2100039524 | أمانة / القصيم | تشييد | ذات اولوية عالية | 116843901.2 | 5842195.06 | 99179566 | 99179566 | 2055014114 | لا | 0 | 180801039078 | جاري | تكلفة العمل المنجز | 83 | 83 | 2018-11-15 | 2023-08-24 | 2023-08-24 | 2023-08-24 |  |  | التنسيق مع أصحاب المصلحه (خدمات |  |  |  | منتظم | No
2200235443 | أمانة / القصيم | توريد وتركيب | ذات اولوية عالية | 10045330 | 502266.5 | 8940343.7 | 8940343.7 | 1010997845 | لا | 0 |  | جاري | تكلفة العمل المنجز | 90 | 91 | 2018-10-10 | 2023-12-24 | 2023-12-24 | 2023-12-24 |  |  |  |  | 43.9818 | 26.3592 | منتظم | No
2200235454 | أمانة / القصيم | دراسات هندسية | ذات اولوية عالية وعاجلة | 76763610 | 3838180.5 | 57767310 | 57767310 | 1010348048 | لا | 0 |  | جاري | مدفوعات ساعات العمل | 80 | 80 | 2019-08-21 | 2023-10-18 | 2023-10-18 | 2023-10-18 |  |  |  |  | 43.9818 | 26.3592 | خدمات عامة | No
2100035770 | أمانة / جازان | تشييد | ذات اولوية عالية | 419899 | 20994.95 | 66206.2 | 66206.2 | 5900013452 | لا | 0 | 200101057733 | مسحوب | تكلفة العمل المنجز | 59 | 100 | 2019-11-10 | 2020-11-05 | 2021-12-31 | 2021-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5706 | 16.8894 | مسحوب | No
2200235465 | أمانة / القصيم | توريد وتركيب | ذات اولوية عالية | 3898730 | 194936.5 | 3703793.5 | 3703793.5 | 1131014859 | لا | 0 |  | جاري | تكلفة العمل المنجز | 95 | 96 | 2020-08-06 | 2023-03-09 | 2023-03-09 | 2023-03-09 |  |  |  |  | 43.9818 | 26.3592 | منتظم | No
2200235502 | أمانة / القصيم | تشييد | ذات اولوية عالية | 1316799 | 65839.95 | 763743.42 | 763743.42 | 1131019382 | لا | 0 |  | جاري | تكلفة العمل المنجز | 58.5 | 60 | 2022-08-17 | 2023-02-12 | 2023-03-09 | 2023-03-09 |  |  |  |  | 43.8614 | 26.2887 | منتظم | No
2100019644 | أمانة / جازان | تشييد | ذات اولوية عالية | 3415399 | 170769.95 | 216190 | 216190 | 1128019021 | لا | 0 | 181209449572 | مسحوب | الكميات التي تم تركيبها | 9 | 100 | 2016-01-24 | 2017-01-18 | 2021-04-29 | 2021-04-29 |  |  | ضعف كفاءة المقاول الفنية |  | 42.8391 | 16.9683 | مسحوب | No
2100046863 | أمانة / جازان | تشييد | ذات اولوية عالية | 15453750 | 772687.5 | 13894100 | 13894100 | 1010214056 | لا | 0 |  | جاري | اخرى | 90 | 100 | 2013-09-03 | 2015-09-23 | 2021-10-11 | 2021-10-11 |  |  | ضعف كفاءة المقاول الفنية |  | 42.6336 | 16.8556 | Failed | No
2100013790 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 3500000 | 175000 | 350850 | 350850 | 5850036238 | لا | 0 |  | مسحوب | اخرى | 10 | 100 | 2015-03-21 | 2016-03-10 | 2019-09-28 | 2019-09-28 |  |  | تأخرصرف المستحقات المالية |  | 43.05 | 17.0351 | مسحوب | No
2100066485 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 889000 | 44450 | 363000 | 0 | 5802010434 | لا | 0 | 220209110053 | جاري | الكميات التي تم تركيبها | 65 | 65 | 2019-08-22 | 2021-02-03 | 2023-02-08 | 2023-02-08 |  |  | سوء التخطيط الاولي للمشروع |  | 41.057 | 20.2337 | منتظم | Yes
2100025045 | أمانة / الباحة | تشييد | ذات اولوية عالية | 3250014 | 162500.7 | 1891024 | 511992 | 5806008614 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 98 | 100 | 2019-01-02 | 2020-12-10 | 2021-12-01 | 2021-12-01 | 2020-12-10 |  | تأخرصرف المستحقات المالية |  | 41.057 | 20.2337 | منجز | No
2100054950 | رئاسة الحرس الملكي | تشييد | ذات اولوية عالية وعاجلة | 26105972.55 | 1305298.6275 | 3248263.63 | 3248263.63 | 4030113058 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 13 | 100 | 2018-11-22 | 2020-11-01 | 2020-11-10 | 2020-11-10 |  |  | ضعف كفاءة المقاول الفنية |  | 39.1474 | 21.537 | مسحوب | No
2100083296 | أمانة / جازان | تشييد | ذات اولوية عالية | 73934535 | 3696726.75 | 72244721.74 | 72244721.74 | 1010193433 | لا | 0 | 180709033890 | جاري | تكلفة العمل المنجز | 88 | 100 | 2013-04-16 | 2015-04-06 | 2021-12-12 | 2021-12-12 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.5676 | 16.9368 | Failed | No
2100077722 | أمانة / جازان | تشييد | ذات اولوية عالية | 21488993 | 1074449.65 | 19864868 | 19864868 | 1010193433 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 84 | 100 | 2014-09-16 | 2015-09-11 | 2021-11-11 | 2021-11-11 |  |  | ضعف كفاءة المقاول الفنية |  | 43.1078 | 17.2451 | Failed | No
2100059150 | المؤسسة العامة لتحلية المياه المالحة | تشييد | ذات اولوية عالية | 1751436160 | 87571808 | 1513126954.27 | 1513126954.27 | 1010242485 | لا | 0 | 180601012769 | جاري | منهجية القيمة المكتسبة | 93.1 | 93.5 | 2018-09-26 | 2023-07-22 | 2023-07-22 | 2023-07-22 |  |  | تأخرصرف المستحقات المالية |  | 38.3827 | 23.8659 | منتظم | No
2200235480 | أمانة / القصيم | تشييد | ذات اولوية عالية | 6839155.67 | 341957.7835 | 5809772.135 | 5809772.135 | 1134000444 | لا | 0 |  | جاري | تكلفة العمل المنجز | 95 | 95 | 2021-08-04 | 2023-01-25 | 2023-01-25 | 2023-01-25 |  |  |  |  | 43.5415 | 26.0533 | منتظم | No
2100075585 | أمانة / الباحة | تشييد | ذات اولوية عالية وعاجلة | 3724313 | 186215.65 | 3724313 | 3724313 | 4030159820 | لا | 0 |  | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-09-30 | 2019-09-19 | 2019-09-19 | 2019-09-19 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 41.071 | 20.1933 | Failed | No
2100102605 | أمانة / جازان | دراسة الجدوى | ذات اولوية متوسطة | 376000 | 18800 | 376000 | 376000 | 5900020940 | لا | 0 | 180701016145 | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2018-09-12 | 2020-01-05 | 2020-01-05 | 2020-01-05 | 2020-01-05 |  | اخرى |  |  |  | منجز | No
2100091862 | أمانة / الباحة | تشييد | ذات اولوية عالية | 2495360 | 124768 | 2064398.8 | 0 | 4030006066 | لا | 0 | 220109050067 | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 98 | 100 | 2019-12-12 | 2021-05-26 | 2022-08-01 | 2022-08-01 |  |  | تأخرصرف المستحقات المالية |  | 41.0675 | 20.1846 | متأخر | Yes
2100035873 | أمانة / جازان | تشييد | ذات اولوية عالية | 2025400 | 101270 | 1553699.4 | 1553699.4 | 5905010261 | لا | 0 | 181109352386 | مسحوب | الكميات التي تم تركيبها | 76 | 100 | 2014-07-16 | 2015-04-12 | 2020-02-01 | 2020-02-01 |  |  | اخرى |  | 42.8642 | 16.9641 | مسحوب | No
2100049151 | أمانة / جازان | تشييد | ذات اولوية عالية | 991000 | 49550 | 768562 | 768562 | 1010193433 | لا | 0 | 180909098312 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 82 | 100 | 2011-07-11 | 2012-07-04 | 2019-07-08 | 2019-07-08 | 2012-07-04 |  | اخرى |  | 42.9553 | 16.7109 | منجز | No
2100078595 | أمانة / حائل | إشراف | ذات اولوية متوسطة | 429996 | 21499.8 | 429996 | 429996 | 3350042762 | لا | 0 | 191101009167 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-07-15 | 2020-09-30 | 2021-09-02 | 2021-09-02 | 2020-09-30 |  | اخرى |  | 41.6732 | 26.7884 | منجز | No
2100095093 | المؤسسة العامة لتحلية المياه المالحة | إشراف | ذات اولوية عالية | 70185982 | 3509299.1 | 49075866.56 | 49075866.56 | 1010407685 | لا | 0 | 180701022444 | جاري | تكلفة العمل المنجز | 69.9 | 71.2 | 2018-10-14 | 2023-10-14 | 2023-10-14 | 2023-10-14 |  |  |  |  | 38.3757 | 23.8637 | خدمات عامة | No
2100052264 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 638665 | 31933.25 | 193145 | 0 | 3350141151 | لا | 0 | 2100052264 | مسحوب | الكميات التي تم تركيبها | 90 | 90 | 2019-07-09 | 2020-07-02 | 2020-06-27 | 2020-06-27 |  |  |  |  | 41.6725 | 26.7887 | مسحوب | Yes
2100068121 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 13000000 | 650000 | 0.01 | 0.01 | 5950010447 | لا | 0 | 181109362681 | جاري | الكميات التي تم تركيبها | 0 | 100 | 2012-06-01 | 2019-03-31 | 2022-05-05 | 2022-05-05 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5866 | 16.888 | Failed | No
2100013366 | أمانة / جازان | تشييد | لم تعد تحتاجها الجهة | 938576 | 46928.8 | 176625 | 0 | 5850030206 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 25 | 100 | 2015-10-03 | 2016-05-29 | 2019-07-27 | 2019-07-27 |  |  | اخرى |  | 42.7766 | 17.1083 | مسحوب | Yes
2100093925 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 1599975 | 79998.75 | 1215275 | 1215275 | 3350009542 | لا | 0 | 2100093925 | مسحوب | الكميات التي تم تركيبها | 80 | 100 | 2019-02-05 | 2020-05-29 | 2021-07-06 | 2021-07-06 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6913 | 26.8113 | مسحوب | No
2100067115 | أمانة / جازان | تشييد | ذات اولوية عالية | 32177921 | 1608896.05 | 19060598 | 19060598 | 5900007896 | لا | 0 | 180809050465 | جاري | تكلفة العمل المنجز | 75 | 100 | 2013-10-19 | 2015-10-09 | 2021-11-11 | 2021-11-11 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.5752 | 16.8834 | Failed | No
2100062403 | المؤسسة العامة لتحلية المياه المالحة | إشراف | ذات اولوية عالية | 85186935 | 4259346.75 | 76018475.51 | 76018475.51 | 1010197409 | لا | 0 | 180401005456 | جاري | تكلفة العمل المنجز | 78.7 | 93.9 | 2018-04-10 | 2023-04-14 | 2023-04-14 | 2023-04-14 |  |  |  |  | 42.0615 | 17.661 | خدمات عامة | No
2100041064 | أمانة / جازان | دراسة الجدوى | ذات اولوية متوسطة | 7900539.69 | 395026.9845 | 7900539.68 | 7900539.68 | 5900018330 | لا | 0 | 180709032147 | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2017-11-30 | 2019-11-20 | 2020-06-25 | 2020-06-25 | 2019-11-20 |  | اخرى |  | 42.5894 | 16.8983 | منجز | No
2100095896 | وزارة الصحة / الجوف | تشييد | ذات اولوية عالية | 2618134 | 130906.7 | 60937.5 | 60937.5 | 3401010075 | نعم | 297393 | 201001068136 | مسحوب | الكميات التي تم تركيبها | 20 | 100 | 2020-02-22 | 2021-02-21 | 2023-03-27 | 2023-03-27 |  |  | تأخرصرف المستحقات المالية | مخطط لسحبه وإعادة ترسيته | 39.3074 | 29.8837 | مسحوب | No
2100064422 | المؤسسة العامة لتحلية المياه المالحة | تشييد | ذات اولوية عالية | 2625498242.37 | 131274912.1185 | 2336937753.08 | 2336937753.08 | 1010004739 | لا | 0 | 180201000079 | جاري | تكلفة العمل المنجز | 96 | 100 | 2018-04-08 | 2022-08-30 | 2023-08-07 | 2023-08-07 |  |  | لا يوجد تأخير |  | 42.0745 | 17.6596 | منتظم | No
2100016236 | المؤسسة العامة لتحلية المياه المالحة | تشييد | ذات اولوية عالية | 526707807.24 | 26335390.362 | 440655734.83 | 440655734.83 | 1010004739 | لا | 0 | 180301000853 | جاري | منهجية القيمة المكتسبة | 96 | 100 | 2018-04-08 | 2022-08-30 | 2023-08-07 | 2023-08-07 |  |  | لا يوجد تأخير |  | 42.0607 | 17.6599 | منتظم | No
2100099971 | أمانة / حائل | إشراف | ذات اولوية متوسطة | 682028 | 34101.4 | 682028 | 682028 | 3350029913 | لا | 0 | 191201032436 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-10-28 | 2021-04-20 | 2021-04-20 | 2021-04-20 | 2021-04-20 |  | اخرى |  | 41.3195 | 26.7882 | منجز | No
2100071956 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 5018771 | 250938.55 | 0 | 0 | 5853001934 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 29 | 100 | 2010-07-11 | 2011-05-08 | 2019-03-25 | 2019-03-25 |  |  | اخرى |  | 42.6279 | 17.1542 | مسحوب | No
2100049873 | أمانة / جازان | تشييد | ذات اولوية عالية | 9519250 | 475962.5 | 6626832 | 6626832 | 1010177200 | لا | 0 | 18209547162 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-11-02 | 2020-10-11 | 2020-12-05 | 2020-12-05 | 2020-10-11 |  | أوامر سامية |  | 42.543 | 16.8729 | منجز | No
2100076403 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 461810 | 23090.5 | 0 | 0 | 5856026069 | لا | 0 |  | مسحوب | اخرى | 0 | 100 | 2018-08-26 | 2020-02-02 | 2020-04-19 | 2020-04-19 |  |  | ضعف كفاءة المقاول الفنية |  | 43.0481 | 17.0374 | مسحوب | No
2100080382 | أمانة / جازان | تشييد | ذات اولوية عالية | 630130 | 31506.5 | 0 | 0 | 1010352474 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 0 | 100 | 2015-04-14 | 2015-07-12 | 2020-02-10 | 2020-02-10 |  |  | ضعف كفاءة المقاول الفنية |  | 42.8397 | 16.9577 | مسحوب | No
2100004944 | المؤسسة العامة لتحلية المياه المالحة | توريد | ذات اولوية عالية | 868335942 | 43416797.1 | 868333184.9 | 868333184.9 | 2051003936 | لا | 0 | 181209482576 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-04-08 | 2020-07-05 | 2020-02-06 | 2020-02-06 | 2020-07-05 |  | تأخرصرف المستحقات المالية |  | 42.0629 | 17.661 | منجز | No
2100048591 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 5250063 | 262503.15 | 0.01 | 0.01 | 5950010447 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 23 | 100 | 2010-12-10 | 2011-11-26 | 2022-03-30 | 2022-03-30 |  |  | اخرى |  | 42.6269 | 17.1544 | Failed | No
2100066964 | أمانة / جازان | تشييد | ذات اولوية عالية وعاجلة | 11256347.2 | 562817.36 | 8967757.15 | 8967757.15 | 5855025377 | لا | 0 | 180701015425 | جاري | الكميات التي تم تركيبها | 73 | 100 | 2018-10-08 | 2020-09-28 | 2021-09-23 | 2021-09-23 |  |  | ضعف كفاءة المقاول الفنية |  | 42.6277 | 17.1409 | Failed | No
2100054736 | أمانة / جازان | تشييد | ذات اولوية عالية | 1987659 | 99382.95 | 1987659 | 1987659 | 1010214056 | لا | 0 | 180701014842 | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2018-08-27 | 2019-08-22 | 2020-02-20 | 2020-02-20 | 2019-08-22 |  | ضعف كفاءة المقاول الفنية |  | 42.5656 | 16.88 | منجز | No
2100056280 | أمانة / جازان | دراسة الجدوى | ذات اولوية متوسطة | 246000 | 12300 | 246000 | 246000 | 5900020940 | لا | 0 | 180701015092 | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2018-09-12 | 2019-09-07 | 2019-09-07 | 2019-09-07 | 2019-09-07 |  | اخرى |  |  |  | منجز | No
2100066990 | أمانة / جازان | تشييد | ذات اولوية عالية | 21971656.326 | 1098582.8163 | 21971656.33 | 21971656.33 | 5900000115 | لا | 0 | 180709024682 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-02-17 | 2016-08-10 | 2018-10-26 | 2018-10-26 | 2016-08-10 |  | اخرى |  | 42.8355 | 16.9669 | منجز | No
2100056475 | أمانة / جازان | دراسة الجدوى | ذات اولوية متوسطة | 499200 | 24960 | 478400 | 478400 | 5900020940 | لا | 0 | 180801038728 | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2018-09-11 | 2020-09-11 | 2020-09-11 | 2020-09-11 | 2020-09-11 |  | ضعف كفاءة المقاول الفنية |  |  |  | منجز | No
2100013860 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 1991475 | 99573.75 | 1469075 | 1469075 | 5851004181 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 74 | 100 | 2014-11-16 | 2015-10-23 | 2019-02-18 | 2019-02-18 |  |  | اخرى |  | 42.5369 | 17.3735 | مسحوب | No
2100072225 | أمانة / جازان | تشييد | ذات اولوية عالية وعاجلة | 7534549.056 | 376727.4528 | 7534549.06 | 6766025 | 1131020873 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2014-11-22 | 2016-05-15 | 2020-08-26 | 2020-08-26 | 2016-05-15 |  | ضعف كفاءة المقاول الفنية |  | 43.0558 | 17.0391 | منجز | No
2100049206 | أمانة / جازان | تشييد | ذات اولوية عالية وعاجلة | 8920504.97 | 446025.2485 | 1685396 | 1685396 | 1131020873 | لا | 0 | 180909114760 | جاري | الكميات التي تم تركيبها | 72 | 100 | 2014-11-22 | 2016-11-11 | 2022-03-30 | 2022-03-30 |  |  | ضعف كفاءة المقاول الفنية |  | 42.9626 | 16.5293 | Failed | No
2100082165 | أمانة / جازان | تشييد | ذات اولوية عالية | 29208353 | 1460417.65 | 15444384.64 | 15444384.64 | 1010214056 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 69 | 100 | 2011-08-25 | 2012-12-09 | 2021-06-01 | 2021-06-01 |  |  | اخرى |  | 42.5706 | 16.8984 | مسحوب | No
2100066706 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 727140 | 36357 | 251065.4 | 47654.37 | 3350032068 | لا | 0 | 200201088839 | مسحوب | الكميات التي تم تركيبها | 24 | 100 | 2019-04-02 | 2020-03-27 | 2022-08-18 | 2022-08-18 |  |  | ضعف كفاءة المقاول الفنية |  | 40.9977 | 28.0254 | مسحوب | No
2100102362 | وزارة الصحة / مكة المكرمة | تشييد | ذات اولوية متوسطة | 2098724 | 104936.2 | 1986937.15 | 1986937.15 | 4031057370 | لا | 0 | 191001086901 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-09-30 | 2019-12-31 | 2021-12-23 | 2021-12-23 | 2019-12-31 |  | ضعف كفاءة المقاول الفنية |  | 39.7891 | 21.4873 | منجز | No
2100050234 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 287000 | 14350 | 0 | 0 | 1010426789 | لا | 0 | 2100050234 | مسحوب | الكميات التي تم تركيبها | 0 | 0 | 2019-08-17 | 2019-08-21 | 2020-08-18 | 2020-08-18 |  |  |  |  | 41.7045 | 26.8096 | مسحوب | No
2100066953 | أمانة / الباحة | تشييد | ذات اولوية عالية | 2077530 | 103876.5 | 1202308 | 0 | 4030159820 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 90 | 100 | 2019-10-27 | 2021-04-10 | 2021-12-22 | 2021-12-22 | 2021-04-10 |  | سوء التخطيط الاولي للمشروع |  | 41.057 | 20.2337 | منجز | Yes
2100040460 | أمانة / الباحة | تصميم | ذات اولوية متوسطة | 943870 | 47193.5 | 943870 | 127400 | 1010326770 | لا | 0 | 190309018856 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 99 | 95 | 2018-06-10 | 2018-07-11 | 2021-08-14 | 2021-08-14 | 2018-07-11 |  | اخرى |  | 41.057 | 20.2337 | منجز | No
2100036540 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 1928916 | 96445.8 | 1219434 | 1155434 | 3350021121 | لا | 0 | 181201397065 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-10-28 | 2022-02-23 | 2021-03-15 | 2021-03-15 | 2022-02-23 |  | ضعف كفاءة المقاول الفنية |  | 40.9369 | 27.9909 | منجز | No
2100048731 | أمانة / الباحة | تشييد | ذات اولوية عالية | 4786849 | 239342.45 | 4786849 | 4786849 | 4030006066 | لا | 0 | 200709032942 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2016-02-14 | 2017-03-15 | 2019-12-29 | 2019-12-29 | 2017-03-15 |  | تأخرصرف المستحقات المالية |  | 41.0754 | 20.1995 | منجز | No
2100045080 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 859320 | 42966 | 859320 | 859320 | 3360005382 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-06-24 | 2019-06-19 | 2020-05-20 | 2020-05-20 | 2019-06-19 |  | سوء التخطيط الاولي للمشروع |  | 40.9595 | 27.9825 | منجز | No
2100068224 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 1995850 | 99792.5 | 1282220 | 1282220 | 1010300118 | لا | 0 | 181109376008 | مسحوب | تكلفة العمل المنجز | 65 | 100 | 2014-04-18 | 2015-04-14 | 2019-07-14 | 2019-07-14 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5684 | 16.8829 | مسحوب | No
2100019655 | أمانة / جازان | تشييد | ذات اولوية عالية وعاجلة | 5693546.14 | 284677.307 | 5516360 | 5516360 | 1131020873 | لا | 0 | 180809060233 | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2014-05-20 | 2016-05-09 | 2019-04-25 | 2019-04-25 | 2016-05-09 |  | اخرى |  | 42.8261 | 16.4167 | منجز | No
2100054762 | أمانة / جازان | تشييد | ذات اولوية عالية | 18065830 | 903291.5 | 6990336 | 6990336 | 5904006379 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 46 | 100 | 2014-11-12 | 2016-11-02 | 2021-03-30 | 2021-03-30 |  |  | ضعف كفاءة المقاول الفنية |  | 42.9521 | 16.7111 | مسحوب | No
2100050610 | أمانة / جازان | تشييد | ذات اولوية عالية | 15934500 | 796725 | 13894100 | 13894100 | 1010214056 | لا | 0 | 180701020988 | جاري | تكلفة العمل المنجز | 50 | 100 | 2018-08-28 | 2020-02-20 | 2021-04-29 | 2021-04-29 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5871 | 16.8928 | Failed | No
2100072181 | أمانة / جازان | تشييد | لم تعد تحتاجها الجهة | 2852280 | 142614 | 2852280 | 2852280 | 1010193433 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 90 | 100 | 2010-12-21 | 2012-06-13 | 2019-08-02 | 2019-08-02 | 2012-06-13 |  | اخرى |  | 42.7776 | 17.1083 | منجز | No
2100050691 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 7999905.45 | 399995.2725 | 7999905.45 | 7999905.45 | 3350018969 | لا | 0 | 190401026565 | جاري | الكميات التي تم تركيبها | 100 | 100 | 2019-03-31 | 2020-10-02 | 2022-06-01 | 2022-06-01 |  |  | ضعف كفاءة المقاول الفنية |  | 40.954 | 28.0037 | Failed | No
2100091921 | أمانة / جازان | تشييد | ذات اولوية عالية | 6985725 | 349286.25 | 0 | 0 | 5900012775 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 65 | 100 | 2015-11-04 | 2017-10-24 | 2021-06-15 | 2021-06-15 |  |  | تأخرصرف المستحقات المالية |  | 42.598 | 16.9373 | مسحوب | No
2100060690 | أمانة / جازان | تشييد | ذات اولوية عالية | 1511979 | 75598.95 | 1070893 | 1070893 | 5900013452 | لا | 0 | 200101057724 | مسحوب | الكميات التي تم تركيبها | 70 | 100 | 2019-11-10 | 2020-10-05 | 2022-03-20 | 2022-03-20 |  |  | ضعف كفاءة المقاول الفنية |  | 42.8294 | 17.617 | مسحوب | No
2100056991 | أمانة / جازان | دراسة الجدوى | ذات اولوية متوسطة | 487500 | 24375 | 487500 | 487500 | 5900020940 | لا | 0 | 180701015090 | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2018-09-12 | 2019-10-07 | 2019-10-07 | 2019-10-07 | 2019-10-07 |  | اخرى |  |  |  | منجز | No
2100050573 | أمانة / جازان | تشييد | ذات اولوية عالية | 1198286 | 59914.3 | 1193786 | 1193786 | 5906019673 | لا | 0 | 180701014929 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-08-28 | 2019-07-24 | 2019-07-25 | 2019-07-25 | 2019-07-24 |  | اخرى |  | 42.5745 | 16.8926 | منجز | No
2100059953 | المؤسسة العامة لتحلية المياه المالحة | تشييد | ذات اولوية عالية | 1698623840 | 84931192 | 1482339844.42 | 1482339844.42 | 1010004739 | لا | 0 | 180401001848 | جاري | منهجية القيمة المكتسبة | 98.8 | 100 | 2018-09-18 | 2022-06-14 | 2022-06-14 | 2022-06-14 |  |  | تأخرصرف المستحقات المالية |  | 47.0237 | 24.9624 | متأخر | No
2100038706 | المؤسسة العامة لتحلية المياه المالحة | إشراف | ذات اولوية عالية | 88503093 | 4425154.65 | 76781926.9 | 76781926.9 | 2051058157 | لا | 0 | 180701022277 | جاري | اخرى | 90.3 | 91 | 2018-10-31 | 2023-10-31 | 2022-10-31 | 2022-10-31 |  |  |  |  | 47.0236 | 24.9623 | خدمات عامة | No
2100050820 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 934545 | 46727.25 | 623400 | 623400 | 5900017349 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 67 | 100 | 2012-10-08 | 2013-09-18 | 2019-07-14 | 2019-07-14 |  |  | اخرى |  | 42.6088 | 16.8992 | مسحوب | No
2100052356 | أمانة / جازان | دراسة الجدوى | ذات اولوية متوسطة | 160000 | 8000 | 160000 | 160000 | 1131049510 | لا | 0 | 180701031624 | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2018-08-28 | 2019-04-25 | 2019-04-25 | 2019-04-25 | 2019-04-25 |  | اخرى |  | 42.6005 | 16.8955 | منجز | No
2100097425 | المؤسسة العامة لتحلية المياه المالحة | تشييد | ذات اولوية عالية | 1675041770 | 83752088.5 | 1470747828.41 | 1470747828.41 | 1010286338 | لا | 0 | 180501009743 | جاري | منهجية القيمة المكتسبة | 99 | 100 | 2018-09-18 | 2022-09-28 | 2022-09-28 | 2022-09-28 |  |  | تأخرصرف المستحقات المالية |  | 47.0238 | 24.9622 | متأخر | No
2100075810 | أمانة / جازان | تشييد | ذات اولوية عالية | 2669800 | 133490 | 0.01 | 0.01 | 5850031232 | لا | 0 | 190909085584 | مسحوب | الكميات التي تم تركيبها | 78 | 100 | 2017-11-14 | 2018-11-09 | 2021-04-29 | 2021-04-29 |  |  | ضعف كفاءة المقاول الفنية |  | 42.8488 | 16.9671 | مسحوب | No
2100020101 | المؤسسة العامة لتحلية المياه المالحة | توريد | ذات اولوية عالية | 75047846 | 3752392.3 | 70951318.95 | 70951318.95 | 2050037927 | لا | 0 | 180909105858 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-01-22 | 2019-07-24 | 2019-07-24 | 2019-07-24 | 2019-07-24 |  |  |  | 40.2401 | 21.3364 | منجز | No
2100082880 | أمانة / جازان | تشييد | ذات اولوية عالية | 3787507.5 | 189375.375 | 3080448.12 | 3080448.12 | 5903015060 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 83 | 100 | 2013-06-07 | 2014-05-23 | 2019-10-04 | 2019-10-04 | 2014-05-23 |  | اخرى |  | 42.6054 | 16.9428 | منجز | No
2100027252 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 2649050 | 132452.5 | 201350 | 201350 | 5850035146 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 13 | 100 | 2014-09-14 | 2015-08-30 | 2019-07-02 | 2019-07-02 |  |  | اخرى |  | 42.8861 | 17.435 | مسحوب | No
2100076834 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 349965 | 17498.25 | 0 | 0 | 1017000899 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 0 | 100 | 2014-10-27 | 2015-10-12 | 2019-02-19 | 2019-02-19 |  |  | اخرى |  | 42.5326 | 17.3714 | مسحوب | No
2100040821 | أمانة / جازان | دراسة الجدوى | ذات اولوية متوسطة | 480480 | 24024 | 480480 | 480480 | 3350029913 | لا | 0 | 190509138345 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-04-07 | 2019-08-05 | 2020-08-05 | 2020-08-05 | 2019-08-05 |  | اخرى |  | 42.5883 | 16.9054 | منجز | No
2100015945 | أمانة / جازان | إشراف | ذات اولوية متوسطة | 2910000 | 145500 | 1980000 | 1980000 | 1010325732 | لا | 0 | 190509026694 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 95 | 100 | 2018-01-30 | 2019-01-15 | 2021-11-15 | 2021-11-15 | 2019-01-15 |  | ضعف كفاءة المقاول الفنية |  | 42.6112 | 16.9051 | منجز | No
2100049501 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 1516079 | 75803.95 | 0.01 | 0.01 | 1010193433 | لا | 0 | 181109364029 | مسحوب | تكلفة العمل المنجز | 0 | 100 | 2015-05-19 | 2015-11-15 | 2019-02-25 | 2019-02-25 |  |  | اخرى |  | 42.5725 | 16.8876 | مسحوب | No
2100040994 | أمانة / جازان | دراسة الجدوى | ذات اولوية متوسطة | 1498000 | 74900 | 1337500 | 1337500 | 5801010135 | لا | 0 | 180701016899 | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2018-09-16 | 2021-01-03 | 2021-01-03 | 2021-01-03 | 2021-01-03 |  | ضعف كفاءة المقاول الفنية |  | 42.6263 | 17.1433 | منجز | No
2100092304 | أمانة / جازان | تشييد | ذات اولوية عالية وعاجلة | 885395.63 | 44269.7815 | 130083 | 0 | 5900016851 | لا | 0 | 190309031178 | مسحوب | الكميات التي تم تركيبها | 14 | 100 | 2015-08-05 | 2016-08-04 | 2019-06-23 | 2019-06-23 |  |  | تأخرصرف المستحقات المالية |  | 42.6688 | 16.8384 | مسحوب | Yes
2100068751 | أمانة / جازان | تشييد | ذات اولوية عالية | 83952000 | 4197600 | 53389325 | 53389325 | 5900008127 | لا | 0 | 190309023275 | جاري | تكلفة العمل المنجز | 83 | 100 | 2013-07-28 | 2015-07-18 | 2021-11-03 | 2021-11-03 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5726 | 16.8895 | Failed | No
2100066382 | أمانة / جازان | تشييد | ذات اولوية عالية | 968916.9 | 48445.845 | 787305 | 787305 | 1010245708 | لا | 0 | 200309045742 | منجز – استلام ابتدائي | اخرى | 81 | 100 | 2019-10-29 | 2020-10-23 | 2021-10-11 | 2021-10-11 | 2020-10-23 |  | ضعف كفاءة المقاول الفنية |  | 42.5384 | 16.8791 | منجز | No
2100014545 | أمانة / جازان | تشييد | لم تعد تحتاجها الجهة | 1835133.35 | 91756.6675 | 1128946 | 1128946 | 5950011432 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 85 | 100 | 2015-02-11 | 2017-01-20 | 2021-12-25 | 2021-12-25 | 2017-01-20 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.9702 | 16.5282 | منجز | No
2100035280 | أمانة / جازان | تشييد | ذات اولوية عالية | 670155 | 33507.75 | 439225 | 439225 | 5903030625 | لا | 0 | 191201009168 | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2018-08-26 | 2020-02-02 | 2020-03-27 | 2020-03-27 | 2020-02-02 |  | اخرى |  | 43.0488 | 17.0376 | منجز | No
2200226995 | الهيئة العامة للموانئ | توريد وتركيب | ذات اولوية عالية وعاجلة | 6040900 | 302045 | 4318986.56 | 4318986.56 | 4030017054 | لا | 0 |  | جاري | تكلفة العمل المنجز | 77 | 84 | 2022-04-17 | 2023-02-11 | 2023-02-11 | 2023-02-11 |  |  |  |  | 39.1753 | 21.4657 | متأخر | No
2100060723 | المؤسسة العامة لتحلية المياه المالحة | تشييد | ذات اولوية عالية | 836713706.27 | 41835685.3135 | 676933383.58 | 676933383.58 | 1010438048 | لا | 0 | 180701028958 | جاري | منهجية القيمة المكتسبة | 90.1 | 93 | 2017-10-12 | 2023-05-31 | 2023-05-31 | 2023-05-31 |  |  | تأخرصرف المستحقات المالية |  | 40.372 | 21.2966 | منتظم | No
2100005600 | الهيئة العامة للموانئ | تصميم | ذات اولوية عالية وعاجلة | 5009400 | 250470 | 3475700 | 3475700 | 1010425870 | لا | 0 | 200509054787 | جاري | اخرى | 95 | 100 | 2018-02-03 | 2019-03-26 | 2021-10-31 | 2021-10-31 |  |  | لا يوجد تأخير |  | 39.165 | 21.4593 | Failed | No
2100001455 | الهيئة العامة للموانئ | تشييد | ذات اولوية عالية وعاجلة | 21208097 | 1060404.85 | 3030132 | 3030132 | 4030272300 | لا | 0 | 190601004364 | جاري | تكلفة العمل المنجز | 30 | 81 | 2020-03-15 | 2022-03-05 | 2022-06-03 | 2022-06-03 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.1693 | 21.4569 | Failed | No
2100066920 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 1424998.5 | 71249.925 | 470903.75 | 470903.75 | 5911011013 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 33 | 100 | 2016-05-10 | 2019-02-25 | 2019-05-15 | 2019-05-15 |  |  | اخرى |  | 42.5823 | 16.8853 | مسحوب | No
2100027425 | المؤسسة العامة لتحلية المياه المالحة | تشييد | ذات اولوية عالية | 1664817500 | 83240875 | 1382538225.96 | 1382538225.96 | 1010210804 | لا | 0 | 180809039983 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-05-15 | 2021-07-29 | 2020-12-13 | 2020-12-13 | 2021-07-29 |  | لا يوجد تأخير |  | 39.5275 | 20.6763 | منجز | No
2100072236 | أمانة / جازان | تشييد | ذات اولوية عالية | 46714500 | 2335725 | 0 | 0 | 5900000115 | لا | 0 | 190401029436 | جاري | اخرى | 45 | 100 | 2019-09-23 | 2021-09-12 | 2021-09-12 | 2021-09-12 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5636 | 16.9094 | Failed | No
2100010850 | الهيئة العامة للموانئ | تشييد | ذات اولوية عالية | 20548635.71 | 1027431.7855 | 20469894.81 | 20469894.81 | 4030149405 | لا | 0 | 200801128895 | جاري | تكلفة العمل المنجز | 100 | 100 | 2019-05-01 | 2021-04-20 | 2022-03-16 | 2022-03-16 |  |  | تأخرصرف المستحقات المالية |  | 39.1718 | 21.4743 | Failed | No
2100041215 | الهيئة العامة للموانئ | تصميم | ذات اولوية عالية | 506000 | 25300 | 273000 | 273000 | 4030237912 | لا | 0 | 190401025129 | جاري | اخرى | 100 | 100 | 2019-02-12 | 2019-07-12 | 2021-10-31 | 2021-10-31 |  |  | لا يوجد تأخير |  | 39.1732 | 21.4674 | Failed | No
2100100995 | المؤسسة العامة لتحلية المياه المالحة | إشراف | ذات اولوية عالية | 41611468 | 2080573.4 | 24724506.38 | 24724506.38 | 2051023736 | لا | 0 | 190901208436 | جاري | منهجية القيمة المكتسبة | 64.1 | 86 | 2020-08-04 | 2023-08-04 | 2023-08-04 | 2023-08-04 |  |  |  |  | 50.1001 | 26.6998 | خدمات عامة | No
2100105700 | وزارة الحرس الوطني / الشؤون الصحية | تشييد | ذات اولوية عالية | 23314959.28 | 1165747.964 | 17056516.6132 | 9802404.73 | 1132002624 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 88 | 100 | 2019-04-08 | 2020-07-01 | 2023-03-30 | 2023-03-30 |  |  | تأخرصرف المستحقات المالية |  | 39.3625 | 21.4223 | Failed | No
2100073253 | وزارة الحرس الوطني / الشؤون الصحية | تشييد | ذات اولوية عالية وعاجلة | 3532149.36 | 176607.468 | 3004175.32 | 3004175.32 | 4030272351 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 87.75 | 100 | 2020-02-23 | 2021-05-31 | 2023-02-28 | 2023-02-28 |  |  |  |  | 39.3625 | 21.4223 | Failed | No
2100057271 | وزارة الحرس الوطني / الشؤون الصحية | تشييد | ذات اولوية عالية | 18970000 | 948500 | 5464775.92 | 5035636.57 | 1010312806 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 25 | 100 | 2015-10-04 | 2018-09-23 | 2022-12-31 | 2022-12-31 |  |  | تأخرصرف المستحقات المالية |  | 39.6368 | 24.5336 | Failed | No
2100037096 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 1020000 | 51000 | 1020000 | 1020000 | 3357007585 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-06-16 | 2019-12-13 | 2019-12-14 | 2019-12-14 | 2019-12-13 |  |  |  | 41.1804 | 27.3782 | منجز | No
2100057993 | وزارة الحرس الوطني / الشؤون الصحية | تشييد | ذات اولوية عالية | 17036104 | 851805.2 | 6581712.3 | 6581712.3 | 4030198872 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 40 | 100 | 2011-09-03 | 2012-08-29 | 2018-12-31 | 2018-12-31 |  |  | ضعف كفاءة المقاول الفنية | تم إعادة ترسيته | 39.3627 | 21.4225 | مسحوب | No
2200220021 | وزارة الحرس الوطني / الشؤون الصحية | توريد وتركيب | ذات اولوية عالية وعاجلة | 790000 | 39500 | 0 | 0 | 1010290098 | لا | 0 | 211209032758 | جاري | الكميات التي تم تركيبها | 0 | 100 | 2022-01-18 | 2022-06-17 | 2022-12-31 | 2022-12-31 |  |  |  |  | 39.3601 | 21.4247 | Failed | No
2100199205 | وزارة الحرس الوطني / الشؤون الصحية | جيوتقنية | ذات اولوية عالية | 99750 | 4987.5 | 99750 | 0 | 4650080268 | لا | 0 | 200301007129 | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2020-10-19 | 2020-11-17 | 2022-08-31 | 2022-08-31 | 2020-11-17 |  |  |  | 39.637 | 24.5336 | منجز | Yes
2100096456 | وزارة الحرس الوطني / الشؤون الصحية | تشييد | ذات اولوية عالية | 161241012.21 | 8062050.6105 | 143534510.27 | 136334510 | 1010057263 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 90.3 | 100 | 2018-02-25 | 2020-02-14 | 2023-06-30 | 2023-06-30 |  |  |  |  | 40.4455 | 21.4193 | Failed | No
2300237694 | أمانة / القصيم | تشييد | ذات اولوية عالية | 2480550 | 124027.5 | 1810000 | 1810000 | 1010211585 | لا | 0 |  | جاري | تكلفة العمل المنجز | 81 | 0.835 | 2022-05-19 | 2023-02-18 | 2023-02-18 | 2023-02-18 |  |  |  |  | 43.9875 | 26.0907 | منتظم | No
2100093343 | أمانة / جازان | تشييد | ذات اولوية عالية | 28694610 | 1434730.5 | 6343262.88 | 6343262.88 | 5904006379 | لا | 0 | 180809048736 | مسحوب | الكميات التي تم تركيبها | 23 | 100 | 2014-10-16 | 2016-10-05 | 2022-03-30 | 2022-03-30 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5395 | 16.9159 | مسحوب | No
2100067266 | أمانة / جازان | تشييد | لم تعد تحتاجها الجهة | 1998500 | 99925 | 1515358.34 | 1515358.34 | 1010214056 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 80 | 100 | 2018-09-10 | 2019-08-26 | 2019-08-27 | 2019-08-27 | 2019-08-26 |  | ضعف كفاءة المقاول الفنية |  | 42.97 | 16.5296 | منجز | No
2100027985 | أمانة / جازان | تشييد | ذات اولوية عالية وعاجلة | 2531455 | 126572.75 | 897075 | 897075 | 5907010673 | لا | 0 | 181209507143 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 99 | 100 | 2015-08-31 | 2019-05-03 | 2021-06-03 | 2021-06-03 | 2019-05-03 |  | تأخرصرف المستحقات المالية |  | 42.5608 | 16.9088 | منجز | No
2100049066 | أمانة / جازان | تشييد | ذات اولوية عالية | 16827800 | 841390 | 9943977 | 8199570.76 | 1010155611 | لا | 0 | 181109358874 | مسحوب | تكلفة العمل المنجز | 60 | 100 | 2009-04-13 | 2012-03-28 | 2019-02-25 | 2019-02-25 |  |  | اخرى |  | 42.5734 | 16.8916 | مسحوب | No
2100079656 | وزارة الحرس الوطني / الشؤون الصحية | تشييد | ذات اولوية عالية | 8942391.99 | 447119.5995 | 7797440.05 | 7098668.16 | 4032010319 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-02-17 | 2019-11-13 | 2022-08-31 | 2022-08-31 | 2019-11-13 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.3625 | 21.4223 | منجز | No
2100193410 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية | 17792274.56 | 889613.728 | 7774261.63 | 2927281.4 | 5801009694 | نعم | 16957055.98 |  | ايقاف كلي | تكلفة العمل المنجز | 46 | 100 | 2020-01-22 | 2020-11-17 | 2025-12-31 | 2025-12-31 |  |  |  |  | 41.5706 | 19.8792 | Failed | No
2100089482 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية وعاجلة | 85248857.2 | 4262442.86 | 76707167.1 | 66134117.7 | 4031052995 | لا | 0 | 180709019409 | جاري | تكلفة العمل المنجز | 90 | 97 | 2014-03-17 | 2016-09-02 | 2023-12-31 | 2023-12-31 |  |  | تأخرصرف المستحقات المالية |  | 46.7394 | 24.4443 | متأخر | No
2100005482 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 91357320.73 | 4567866.0365 | 42674761.2 | 40424599.65 | 4031052995 | لا | 0 | 190509032648 | ايقاف كلي | تكلفة العمل المنجز | 61 | 93 | 2015-01-12 | 2017-06-30 | 2025-12-31 | 2025-12-31 |  |  | تأخرصرف المستحقات المالية |  | 46.4458 | 24.7884 | Failed | No
2300237705 | أمانة / القصيم | تشييد | ذات اولوية عالية | 7225000 | 361250 | 100000 | 100000 | 1135000671 | لا | 0 |  | جاري | تكلفة العمل المنجز | 1 | 3 | 2022-12-19 | 2024-05-31 | 2025-05-31 | 2025-05-31 |  |  |  |  | 43.5222 | 25.8517 | منتظم | No
2300237716 | أمانة / القصيم | تشييد | ذات اولوية متوسطة | 2000000 | 100000 | 150000 | 80000 | 1135000095 | لا | 0 |  | جاري | تكلفة العمل المنجز | 1.5 | 4 | 2022-12-22 | 2023-12-16 | 2023-12-16 | 2023-12-16 |  |  |  |  | 43.5222 | 25.8517 | منتظم | No
2100050536 | أمانة / جازان | تشييد | ذات اولوية عالية | 1186840 | 59342 | 1186840 | 1186840 | 5900012435 | لا | 0 | 181109305723 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-09-25 | 2020-01-23 | 2020-01-23 | 2020-01-23 | 2020-01-23 |  | ضعف كفاءة المقاول الفنية |  | 42.8452 | 16.9666 | منجز | No
2300237720 | أمانة / القصيم | تشييد | ذات اولوية متوسطة | 833089 | 41654.45 | 350000 | 350000 | 1134000308 | لا | 0 |  | جاري | تكلفة العمل المنجز | 50 | 50 | 2022-10-23 | 2023-03-21 | 2023-03-21 | 2023-03-21 |  |  |  |  | 43.6567 | 26.1616 | منتظم | No
2100105696 | وزارة الحرس الوطني / الشؤون الصحية | تشييد | ذات اولوية عالية | 122682046.25 | 6134102.3125 | 105201093.67 | 105201093.67 | 1010157290 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 99 | 100 | 2018-02-22 | 2020-02-12 | 2022-01-30 | 2022-01-30 | 2020-02-12 |  |  |  | 39.3625 | 21.4223 | منجز | No
2100199161 | وزارة الحرس الوطني / الشؤون الصحية | تشييد | ذات اولوية عالية | 3301457.95 | 165072.8975 | 579762.9 | 387101.1 | 1011009116 | لا | 0 | 200401066618 | جاري | الكميات التي تم تركيبها | 58 | 98 | 2020-10-19 | 2022-04-12 | 2023-01-11 | 2023-01-11 |  |  |  |  | 39.6367 | 24.5338 | Failed | No
2100058166 | وزارة الحرس الوطني / الشؤون الصحية | تشييد | ذات اولوية عالية | 9285192 | 464259.6 | 973772.29 | 973772.29 | 4030297482 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 12 | 45 | 2019-12-15 | 2021-03-09 | 2022-06-04 | 2022-06-04 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.4862 | 21.419 | Failed | No
2100100494 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية | 79886966.66 | 3994348.333 | 20328309.31 | 18294110.81 | 1010276314 | لا | 0 | 180709017864 | ايقاف كلي | تكلفة العمل المنجز | 40 | 100 | 2014-10-25 | 2017-04-12 | 2026-12-31 | 2026-12-31 |  |  | تأخرصرف المستحقات المالية |  | 43.0116 | 23.9832 | Failed | No
2100018605 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية وعاجلة | 87232561.02 | 4361628.051 | 59546371.76 | 57445699.23 | 2051003250 | لا | 0 | 180709023548 | جاري | تكلفة العمل المنجز | 86 | 96 | 2014-04-23 | 2016-10-09 | 2023-12-31 | 2023-12-31 |  |  | تأخرصرف المستحقات المالية |  | 47.083 | 17.4764 | متأخر | No
2100049114 | أمانة / جازان | تشييد | ذات اولوية عالية | 5674857 | 283742.85 | 3479611 | 3479611 | 5907007322 | لا | 0 | 180801064261 | جاري | الكميات التي تم تركيبها | 85 | 100 | 2018-10-03 | 2020-03-27 | 2022-03-30 | 2022-03-30 |  |  | ضعف كفاءة المقاول الفنية |  | 42.9273 | 16.6001 | Failed | No
2100071116 | أمانة / جازان | دراسة الجدوى | ذات اولوية متوسطة | 1854000 | 92700 | 1854000 | 1854000 | 1010326184 | لا | 0 | 180909069966 | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2018-05-06 | 2019-04-25 | 2019-04-25 | 2019-04-25 | 2019-04-25 |  | اخرى |  | 42.5672 | 16.8829 | منجز | No
2300237731 | أمانة / القصيم | تشييد | ذات اولوية متوسطة | 3715320 | 185766 | 50000 | 50000 | 1135000671 | لا | 0 |  | جاري | تكلفة العمل المنجز | 2 | 5 | 2022-11-27 | 2023-11-21 | 2023-11-21 | 2023-11-21 |  |  |  |  | 43.7334 | 25.9812 | منتظم | No
2100068235 | أمانة / جازان | تشييد | ذات اولوية عالية | 5055660 | 252783 | 5055660 | 5055660 | 5900012775 | لا | 0 | 180801043980 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-09-15 | 2019-09-11 | 2020-02-20 | 2020-02-20 | 2019-09-11 |  | ضعف كفاءة المقاول الفنية |  | 42.5658 | 16.8878 | منجز | No
2100020005 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية وعاجلة | 49596610.22 | 2479830.511 | 19406438.36 | 17207003.36 | 1116004360 | نعم | 22519483.22 | 180709022483 | جاري | تكلفة العمل المنجز | 67 | 89 | 2015-08-19 | 2016-11-11 | 2025-12-31 | 2025-12-31 |  |  | تأخرصرف المستحقات المالية |  | 49.5742 | 25.4182 | متأخر | No
2100084836 | وزارة الصحة / القصيم | تشييد | ذات اولوية عالية وعاجلة | 54862079 | 2743103.95 | 45535526 | 37768901 | 1010023333 | لا | 0 | 181009188491 | جاري | تكلفة العمل المنجز | 99 | 100 | 2017-12-04 | 2019-08-30 | 2021-12-30 | 2021-12-30 |  |  | تأخرصرف المستحقات المالية |  | 43.9553 | 26.3508 | Failed | No
2100055510 | وزارة الصحة / القصيم | تشييد | ذات اولوية متوسطة | 30047345 | 1502367.25 | 5408522 | 4204281 | 1132000522 | لا | 0 | 181009129176 | جاري | تكلفة العمل المنجز | 32 | 70 | 2017-07-23 | 2019-12-25 | 2022-09-08 | 2022-09-08 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 43.4919 | 25.8758 | Failed | No
2300237742 | وزارة الحرس الوطني / الشؤون الصحية | توريد وتركيب | ذات اولوية عالية وعاجلة | 169291.5 | 8464.575 | 0 | 0 | 5855064184 | لا | 0 | 220901148183 | جاري | الكميات التي تم تركيبها | 0 | 40 | 2022-11-13 | 2023-02-11 | 2023-02-11 | 2023-02-11 |  |  |  |  | 39.3616 | 21.4256 | Failed | No
2100082051 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 1596370 | 79818.5 | 726668 | 0 | 5801009694 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 95.3 | 95.3 | 2019-08-20 | 2020-08-20 | 2022-08-11 | 2022-08-11 | 2020-08-20 |  | ضعف كفاءة المقاول الفنية |  | 41.6553 | 19.9942 | منجز | Yes
2200211455 | وزارة الصحة / القصيم | تشييد | ذات اولوية متوسطة | 4592940 | 229647 | 872658.79 | 320096 | 1131013286 | لا | 0 |  | جاري | تكلفة العمل المنجز | 55 | 78 | 2021-02-02 | 2022-01-22 | 2022-09-30 | 2022-09-30 |  |  |  |  | 43.9702 | 26.3487 | Failed | No
2100102130 | وزارة الصحة / ديوان الوزارة | تشييد | ذات اولوية عالية | 647492621.89 | 32374631.0945 | 252912179.14 | 246201009.02 | 1010133046 | لا | 0 | 190509130818 | جاري | تكلفة العمل المنجز | 66 | 66.29 | 2014-11-17 | 2018-10-03 | 2024-01-01 | 2024-01-01 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.9902 | 21.5308 | منتظم | No
2100075795 | الهيئة العامة للطيران المدني | تشييد | ذات اولوية عالية وعاجلة | 564830302.4 | 28241515.12 | 478606624 | 428719726.31 | 1010034808 | لا | 0 | 190409031996 | جاري | منهجية القيمة المكتسبة | 94.62 | 100 | 2017-01-29 | 2021-06-15 | 2022-12-30 | 2022-12-30 |  |  | اخرى |  | 46.716 | 24.8969 | متأخر | No
2100055204 | وزارة الصحة / القصيم | تشييد | ذات اولوية متوسطة | 1835970 | 91798.5 | 1835970 | 1835970 | 1131021347 | لا | 0 | 181009134694 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 0 | 2018-11-05 | 2021-04-05 | 2022-06-15 | 2022-06-15 | 2021-04-05 |  | اخرى |  | 43.646 | 26.8805 | منجز | No
2100008875 | وزارة الصحة / ديوان الوزارة | تشييد | ذات اولوية عالية | 247951842 | 12397592.1 | 166073635.26 | 166073635.26 | 1010056779 | لا | 0 | 180909111919 | جاري | تكلفة العمل المنجز | 92 | 100 | 2012-06-17 | 2014-05-26 | 2022-11-30 | 2022-11-30 |  |  | تأخرصرف المستحقات المالية |  | 39.6893 | 21.6157 | متأخر | No
2100036050 | أمانة / جازان | تشييد | ذات اولوية عالية وعاجلة | 38293846.82 | 1914692.341 | 11256981.83 | 11256981.83 | 5904006379 | لا | 0 | 181109276705 | مسحوب | الكميات التي تم تركيبها | 31 | 100 | 2015-05-20 | 2016-11-10 | 2022-03-30 | 2022-03-30 |  |  | ضعف كفاءة المقاول الفنية |  | 42.6272 | 17.1549 | مسحوب | No
2100055602 | وزارة الصحة / القصيم | تشييد | ذات اولوية عالية | 2786553 | 139327.65 | 1003159 | 1003159 | 1131038024 | لا | 0 | 181009134671 | جاري | تكلفة العمل المنجز | 99 | 100 | 2018-10-25 | 2022-01-11 | 2022-06-30 | 2022-06-30 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 44.2014 | 25.8831 | Failed | No
2100041462 | أمانة / جازان | دراسة الجدوى | ذات اولوية متوسطة | 59775728 | 2988786.4 | 59775728 | 59775728 | 4030276223 | لا | 0 | 190809112867 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2013-04-14 | 2014-03-30 | 2016-10-02 | 2016-10-02 | 2014-03-30 |  | اخرى |  | 42.5716 | 16.8957 | منجز | No
2100015536 | وزارة الصحة / القصيم | تشييد | ذات اولوية عالية | 40800000 | 2040000 | 7428102.1832 | 7428102.1832 | 1018000245 | لا | 0 | 181009129313 | مسحوب | تكلفة العمل المنجز | 28 | 95 | 2013-06-04 | 2018-04-11 | 2023-04-29 | 2023-04-29 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 43.9544 | 26.3504 | مسحوب | No
2100055801 | وزارة الصحة / ديوان الوزارة | تشييد | ذات اولوية عالية | 851377598 | 42568879.9 | 529369815.11 | 529369815.11 | 1010053925 | لا | 0 | 190309055729 | جاري | تكلفة العمل المنجز | 82.7 | 100 | 2012-09-11 | 2015-08-08 | 2022-12-31 | 2022-12-31 |  |  | تأخرصرف المستحقات المالية |  | 42.6552 | 16.8063 | Failed | No
2100073835 | وزارة الصحة / مكة المكرمة | تشييد | ذات اولوية متوسطة | 27878490 | 1393924.5 | 30490052.84 | 25071546.52 | 4030052981 | لا | 0 | 201209030673 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-05-20 | 2015-07-07 | 2017-05-04 | 2017-05-04 | 2015-07-07 |  | التنسيق مع أصحاب المصلحه (خدمات |  | 39.7029 | 21.405 | منجز | No
2100048473 | أمانة / جازان | تشييد | ذات اولوية عالية | 4709318 | 235465.9 | 4709318 | 4709318 | 5901009711 | لا | 0 | 181009116277 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-01-08 | 2015-12-23 | 2019-02-24 | 2019-02-24 | 2015-12-23 |  | اخرى |  | 42.9222 | 16.6104 | منجز | No
2100040880 | أمانة / جازان | دراسة الجدوى | ذات اولوية متوسطة | 1650000 | 82500 | 502000 | 502000 | 4030276223 | لا | 0 | 181109369133 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-11-25 | 2015-05-24 | 2021-10-21 | 2021-10-21 | 2015-05-24 |  | ضعف كفاءة المقاول الفنية |  | 42.5405 | 17.2707 | منجز | No
2100040110 | وزارة الصحة / القصيم | تشييد | ذات اولوية متوسطة | 1496000 | 74800 | 1360000 | 1360000 | 1131021966 | لا | 0 | 181009133740 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 0 | 2019-04-25 | 2020-09-06 | 2022-03-25 | 2022-03-25 | 2020-09-06 |  | اخرى |  | 43.4866 | 26.7505 | منجز | No
2100092842 | أمانة / جازان | تشييد | ذات اولوية عالية | 2591784.9 | 129589.245 | 1735340 | 1735340 | 5950018304 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 67 | 100 | 2014-12-27 | 2016-03-19 | 2019-08-04 | 2019-08-04 |  |  | اخرى |  | 42.571 | 16.915 | مسحوب | No
2100073791 | وزارة الصحة / القصيم | تشييد | ذات اولوية عالية | 45905185 | 2295259.25 | 41740745 | 41740745 | 1131003889 | لا | 0 | 181009134559 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 0 | 2013-05-05 | 2020-12-05 | 2021-01-01 | 2021-01-01 | 2020-12-05 |  | ضعف كفاءة المقاول الفنية |  | 43.9544 | 26.3504 | منجز | No
2100107461 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية | 47986390.7 | 2399319.535 | 30908600.9 | 29924956.81 | 1010145283 | لا | 0 | 180709016150 | جاري | تكلفة العمل المنجز | 85 | 100 | 2014-09-13 | 2016-08-13 | 2023-12-31 | 2023-12-31 |  |  | تأخرصرف المستحقات المالية |  | 49.5473 | 25.4812 | متأخر | No
2300237753 | وزارة الحرس الوطني / الشؤون الصحية | توريد وتركيب | ذات اولوية عالية وعاجلة | 10237668 | 511883.4 | 0 | 0 | 4031045263 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 5 | 40 | 2022-11-13 | 2023-02-11 | 2023-02-11 | 2023-02-11 |  |  |  |  | 40.4449 | 21.4196 | Failed | No
2100076694 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 561540 | 28077 | 561540 | 0 | 3360003562 | لا | 0 | 190401025795 | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-04-28 | 2020-01-22 | 2023-01-15 | 2023-01-15 |  |  | ضعف كفاءة المقاول الفنية | العقد يسير حسب الخطة | 41.1804 | 27.3782 | Failed | Yes
2100101334 | وزارة الصحة / القصيم | تشييد | ذات اولوية عالية | 2678640 | 133932 | 160718 | 16072 | 1151001112 | لا | 0 | 181009185280 | مسحوب | تكلفة العمل المنجز | 11 | 65 | 2018-12-20 | 2022-03-26 | 2022-08-27 | 2022-08-27 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 43.075 | 25.8576 | مسحوب | No
2100095605 | وزارة الصحة / القصيم | تشييد | ذات اولوية متوسطة | 2783900 | 139195 | 2783900 | 2783900 | 1131044143 | لا | 0 | 200501081802 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 0 | 2020-04-15 | 2021-07-30 | 2021-12-30 | 2021-12-30 | 2021-07-30 |  | اخرى |  | 44.0408 | 26.2734 | منجز | No
2100097705 | أمانة / جازان | تشييد | ذات اولوية عالية وعاجلة | 4193200 | 209660 | 1925929.02 | 1925929.02 | 5905007541 | لا | 0 | 180809060069 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 96 | 100 | 2014-10-27 | 2016-11-05 | 2021-05-08 | 2021-05-08 | 2016-11-05 |  | ضعف كفاءة المقاول الفنية |  | 42.9122 | 17.4775 | منجز | No
2100076985 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 871100 | 43555 | 779209 | 779209 | 2051033934 | لا | 0 | 200401046448 | منجز – استلام ابتدائي | اخرى | 99 | 100 | 2019-11-27 | 2020-11-21 | 2020-11-22 | 2020-11-22 | 2020-11-21 |  | اخرى |  | 42.5843 | 16.8862 | منجز | No
2100006414 | وزارة الصحة / ديوان الوزارة | تشييد | ذات اولوية عالية | 337347398.91 | 16867369.9455 | 220946852.97 | 220946852.97 | 1010032384 | لا | 0 | 181009123089 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 80 | 100 | 2013-06-01 | 2016-04-30 | 2022-02-08 | 2022-02-08 | 2016-04-30 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.2183 | 17.7079 | منجز | No
2100016796 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1677907.5 | 83895.375 | 1669907.49 | 1669907.49 | 1010056526 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2018-10-15 | 2019-04-10 | 2019-04-10 | 2019-04-10 | 2019-04-10 |  |  |  | 44.9488 | 26.0491 | منجز | No
2100078400 | وزارة الصحة / ديوان الوزارة | تشييد | ذات اولوية عالية | 218026391 | 10901319.55 | 102085922.36 | 102085922.36 | 1010032384 | لا | 0 | 181009127382 | جاري | تكلفة العمل المنجز | 68.82 | 70.45 | 2013-11-11 | 2016-10-08 | 2023-11-12 | 2023-11-12 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 43.5314 | 17.6478 | منتظم | No
2100068294 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 9495800 | 474790 | 6102499 | 6102499 | 5908005820 | لا | 0 | 201109423152 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 57 | 2019-10-08 | 2022-12-08 | 2022-01-11 | 2022-01-11 | 2022-12-08 |  | ضعف كفاءة المقاول الفنية |  | 42.5635 | 16.8607 | منجز | No
2100192021 | وزارة الصحة / ديوان الوزارة | تشييد | ذات اولوية عالية | 138456677 | 6922833.85 | 13559541.55 | 13559541.55 | 1010120275 | نعم | 38941740 | 200301063085 | ايقاف جزئي | تكلفة العمل المنجز | 11.36 | 41.74 | 2021-06-29 | 2024-06-28 | 2024-06-28 | 2024-06-28 |  |  |  |  | 45.6572 | 25.5966 | Failed | No
2300237775 | الهيئة العامة للموانئ | تشييد | ذات اولوية عالية | 458470500 | 22923525 | 0 | 0 | 4030140033 | لا | 0 |  | جاري | تكلفة العمل المنجز | 4 | 7 | 2022-10-03 | 2025-09-17 | 2025-09-17 | 2025-09-17 |  |  |  |  | 39.1659 | 21.4648 | منتظم | No
2100043654 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 49648267.19 | 2482413.3595 | 22698015.51 | 22453370.36 | 2050017994 | لا | 0 | 180709016640 | ايقاف كلي | تكلفة العمل المنجز | 52 | 100 | 2014-09-17 | 2016-08-17 | 2025-12-31 | 2025-12-31 |  |  | تأخرصرف المستحقات المالية |  | 50.1635 | 26.1839 | Failed | No
2100047843 | وزارة الصحة / ديوان الوزارة | تشييد | ذات اولوية عالية | 239716442 | 11985822.1 | 94879767.59 | 94879767.59 | 1131046787 | لا | 0 | 181109246897 | جاري | تكلفة العمل المنجز | 63.82 | 77.55 | 2014-08-06 | 2018-06-23 | 2023-08-13 | 2023-08-13 |  |  |  |  | 43.9247 | 26.4419 | متأخر | No
2100050186 | أمانة / جازان | تشييد | ذات اولوية عالية وعاجلة | 1185500 | 59275 | 768121 | 768121 | 5907010673 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-10-18 | 2016-10-13 | 2021-08-05 | 2021-08-05 | 2016-10-13 |  | تأخرصرف المستحقات المالية |  | 43.0802 | 16.6736 | منجز | No
2100050363 | أمانة / جازان | تشييد | لم تعد تحتاجها الجهة | 1912444 | 95622.2 | 178230 | 0 | 5901014533 | لا | 0 | 181209493824 | مسحوب | الكميات التي تم تركيبها | 9 | 100 | 2014-11-02 | 2015-10-28 | 2015-10-28 | 2015-10-28 |  |  | ضعف كفاءة المقاول الفنية |  | 42.9733 | 16.528 | مسحوب | Yes
2100034801 | وزارة الصحة / ديوان الوزارة | تشييد | ذات اولوية عالية | 471558435 | 23577921.75 | 393558435 | 384139370.08 | 1010151889 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 99.91 | 100 | 2012-06-19 | 2015-05-09 | 2020-11-05 | 2020-11-05 | 2015-05-09 |  | تأخرصرف المستحقات المالية |  | 36.5116 | 28.4489 | منجز | No
2100056291 | وزارة الصحة / ديوان الوزارة | تشييد | ذات اولوية عالية | 136910956 | 6845547.8 | 103761228.72 | 103761228.72 | 5855017763 | نعم | 123199584 | 200309067783 | مسحوب | تكلفة العمل المنجز | 98 | 100 | 2008-04-16 | 2010-03-25 | 2020-04-24 | 2020-04-24 |  |  | ضعف كفاءة المقاول الفنية |  | 41.4363 | 19.7443 | مسحوب | No
2100102281 | وزارة الصحة / ديوان الوزارة | تشييد | ذات اولوية عالية | 337847591 | 16892379.55 | 7912261 | 0 | 4030096631 | نعم | 65861328 | 181209490331 | ايقاف كلي | تكلفة العمل المنجز | 4.1 | 6.68 | 2019-02-19 | 2023-02-18 | 2026-06-30 | 2026-06-30 |  |  | موافقات |  | 49.9658 | 26.5267 | Failed | Yes
2100046362 | أمانة / جازان | تشييد | ذات اولوية عالية | 1980000 | 99000 | 1480750 | 1480750 | 5950014693 | لا | 0 | 190309009474 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 97 | 100 | 2015-11-03 | 2016-10-28 | 2021-11-11 | 2021-11-11 | 2016-10-28 |  | ضعف كفاءة المقاول الفنية |  | 42.9397 | 17.2374 | منجز | No
2100002730 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1998089 | 99904.45 | 1998089 | 1763563.3 | 2055004490 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2013-12-25 | 2015-05-26 | 2019-05-12 | 2019-05-12 | 2015-05-26 |  | ضعف كفاءة المقاول الفنية |  | 46.7271 | 22.2863 | منجز | No
2100017743 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 55311325.15 | 2765566.2575 | 36066033.14 | 33004591.73 | 5950014087 | لا | 0 | 180709019142 | ايقاف كلي | تكلفة العمل المنجز | 73 | 97 | 2014-10-22 | 2016-09-21 | 2024-12-31 | 2024-12-31 |  |  | تأخرصرف المستحقات المالية |  | 40.8958 | 31.0229 | Failed | No
2100008923 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية | 75650000.06 | 3782500.003 | 35476754.58 | 35476754.58 | 1010069654 | لا | 0 | 200609055859 | ايقاف كلي | تكلفة العمل المنجز | 60 | 93 | 2015-01-25 | 2017-07-13 | 2025-12-31 | 2025-12-31 |  |  | تأخرصرف المستحقات المالية |  | 43.5557 | 29.6446 | Failed | No
2100028582 | أمانة / جازان | دراسة الجدوى | ذات اولوية متوسطة | 3096000 | 154800 | 1461681.8 | 1461681.8 | 5906012815 | لا | 0 | 180701020001 | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 90 | 2018-09-17 | 2019-09-12 | 2022-03-15 | 2022-03-15 | 2019-09-12 |  | ضعف كفاءة المقاول الفنية |  |  |  | منجز | No
2100017732 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 4975670 | 248783.5 | 508000 | 508000 | 5922585473 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 10.2 | 100 | 2015-03-17 | 2016-03-12 | 2020-02-20 | 2020-02-20 |  |  | ضعف كفاءة المقاول الفنية |  | 42.9516 | 16.7098 | مسحوب | No
2100077000 | أمانة / جازان | تشييد | ذات اولوية عالية | 2672825 | 133641.25 | 2323729.6 | 2323729.6 | 5900000115 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2018-10-15 | 2019-10-04 | 2020-02-20 | 2020-02-20 | 2019-10-04 |  | ضعف كفاءة المقاول الفنية |  | 43.0505 | 17.0374 | منجز | No
2100192010 | وزارة الصحة / ديوان الوزارة | تشييد | ذات اولوية عالية | 103430684.31 | 5171534.2155 | 93087615.78 | 93087615.78 | 4030052981 | نعم | 179196016 | 201201115877 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2021-01-31 | 2021-10-30 | 2021-12-15 | 2021-12-15 | 2021-10-30 |  |  |  | 42.5558 | 16.8956 | منجز | No
2100083086 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 1986129 | 99306.45 | 1364589 | 1364589 | 1010261070 | لا | 0 | 406039901186 | مسحوب | تكلفة العمل المنجز | 69 | 100 | 2011-03-29 | 2012-07-20 | 2019-03-25 | 2019-03-25 |  |  | اخرى |  | 42.593 | 16.8778 | مسحوب | No
2100101710 | وزارة الصحة / ديوان الوزارة | تشييد | ذات اولوية عالية | 217744397 | 10887219.85 | 139932059.46 | 139932059.46 | 1010032384 | لا | 0 | 181109279248 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 98 | 100 | 2013-05-25 | 2016-04-20 | 2020-12-19 | 2020-12-19 | 2016-04-20 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.2626 | 18.2833 | منجز | No
2100025782 | أمانة / جازان | تشييد | ذات اولوية عالية | 8760613 | 438030.65 | 8760613 | 8760613 | 5901005893 | لا | 0 | 180701016850 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-10-24 | 2020-09-29 | 2020-09-29 | 2020-09-29 | 2020-09-29 |  |  |  | 42.9533 | 16.7113 | منجز | No
2100028626 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية | 21695213.62 | 1084760.681 | 10600558.11 | 6176166.81 | 1116006476 | نعم | 18642418.37 |  | جاري | تكلفة العمل المنجز | 88 | 100 | 2020-02-10 | 2020-11-06 | 2023-12-31 | 2023-12-31 |  |  | تأخرصرف المستحقات المالية |  | 39.3558 | 21.4086 | متأخر | No
2100104694 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 119667808.63 | 5983390.4315 | 90501780.21 | 89526332.71 | 1010108054 | لا | 0 | 180709022065 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-01-26 | 2017-04-05 | 2022-06-17 | 2022-06-17 | 2017-04-05 |  | تأخرصرف المستحقات المالية |  | 36.5113 | 26.1825 | منجز | No
2100093354 | وزارة الصحة / ديوان الوزارة | تشييد | ذات اولوية عالية | 280776468 | 14038823.4 | 134917545.6 | 134917545.6 | 2252000135 | لا | 0 | 190509043989 | ايقاف كلي | تكلفة العمل المنجز | 57.78 | 100 | 2008-10-18 | 2011-03-22 | 2025-12-31 | 2025-12-31 |  |  | أوامر تغيير |  | 50.1626 | 26.21 | Failed | No
2100017581 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 590604 | 29530.2 | 590604 | 590604 | 3360005382 | لا | 0 | 200801024880 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-08-21 | 2020-08-15 | 2020-08-15 | 2020-08-15 | 2020-08-15 |  |  |  | 41.7616 | 27.4189 | منجز | No
2100022396 | أمانة / حائل | إشراف | ذات اولوية متوسطة | 819000 | 40950 | 819000 | 819000 | 3350029142 | لا | 0 | 191001248237 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-09-05 | 2021-08-25 | 2021-08-25 | 2021-08-25 | 2021-08-25 |  | اخرى |  | 40.33 | 26.848 | منجز | No
2100064072 | أمانة / جازان | دراسة الجدوى | ذات اولوية متوسطة | 295200 | 14760 | 258300 | 258300 | 5900028256 | لا | 0 | 180701018914 | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2018-08-27 | 2020-08-27 | 2020-11-15 | 2020-11-15 | 2020-08-27 |  | ضعف كفاءة المقاول الفنية |  | 43.0484 | 17.0377 | منجز | No
2100047633 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 13815291 | 690764.55 | 13599794.57 | 13599794.57 | 1010193433 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 90 | 100 | 2013-05-04 | 2014-11-17 | 2020-05-11 | 2020-05-11 | 2014-11-17 |  | اخرى |  |  |  | منجز | No
2300237834 | وزارة الصحة | ترميم | ذات اولوية عالية وعاجلة | 950000 | 47500 | 666840.9 | 341051.6 | 3403011336 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 90 | 100 | 2022-02-16 | 2022-06-15 | 2023-01-31 | 2023-01-31 |  |  |  | تم إنذار المقاول كتابيا | 40.1891 | 29.9393 | Failed | No
2100026040 | أمانة / جازان | توريد | ذات اولوية متوسطة | 4860000 | 243000 | 4557000 | 4557000 | 5855044366 | لا | 0 | 181109358596 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2017-11-15 | 2020-10-30 | 2020-10-30 | 2020-10-30 | 2020-10-30 |  | اخرى |  |  |  | منجز | No
2100082821 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 515858.88 | 25792.944 | 274100 | 274100 | 5950025573 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 51 | 100 | 2015-01-25 | 2016-01-15 | 2019-02-19 | 2019-02-19 |  |  | اخرى |  | 42.558 | 16.9025 | مسحوب | No
2100091103 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 15284301.43 | 764215.0715 | 15284301.47 | 14125532.52 | 1010070222 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-09-12 | 2019-09-21 | 2020-02-20 | 2020-02-20 | 2019-09-21 |  |  |  | 45.3525 | 25.8912 | منجز | No
2100022444 | وزارة الصحة / ديوان الوزارة | تشييد | ذات اولوية عالية | 640673233 | 32033661.65 | 372556433.05 | 372556433.05 | 4030096631 | لا | 0 | 180909106122 | مسحوب | تكلفة العمل المنجز | 75.45 | 0 | 2014-10-20 | 2018-09-06 | 2021-08-22 | 2021-08-22 |  |  | ضعف كفاءة المقاول الفنية |  | 42.7001 | 18.1902 | مسحوب | No
2100102723 | أمانة / جازان | دراسة الجدوى | ذات اولوية متوسطة | 921600 | 46080 | 921600 | 844800 | 5900031907 | لا | 0 | 181101250966 | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2018-11-15 | 2020-11-04 | 2020-11-04 | 2020-11-04 | 2020-11-04 |  | اخرى |  | 42.1361 | 16.6857 | منجز | No
2100103051 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 3542870 | 177143.5 | 0 | 0 | 4030165713 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 0 | 100 | 2009-02-07 | 2009-12-24 | 2021-10-18 | 2021-10-18 |  |  | اخرى |  | 44.7813 | 20.4716 | مسحوب | No
2100104344 | وزارة الحرس الوطني / الشؤون الصحية | تشييد | ذات اولوية عالية | 1997980 | 99899 | 184764 | 0 | 1010306222 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 25 | 100 | 2016-10-10 | 2017-10-01 | 2022-12-31 | 2022-12-31 |  |  | عدم وجود مبالغ في البنود تغطي الأعمال المرصودة |  | 46.8565 | 24.7502 | Failed | Yes
2100090285 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 9967946.12 | 498397.306 | 5681729.29 | 5681729.29 | 5950002943 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 57 | 100 | 2012-04-28 | 2014-04-18 | 2021-10-27 | 2021-10-27 |  |  | ضعف كفاءة المقاول الفنية |  | 44.7813 | 20.4716 | مسحوب | No
2300237871 | أمانة / القصيم | تشييد | ذات اولوية متوسطة | 1000000 | 50000 | 80000 | 80000 | 1131019382 | لا | 0 |  | جاري | تكلفة العمل المنجز | 23 | 23 | 2022-10-13 | 2023-10-07 | 2023-10-07 | 2023-10-07 |  |  |  |  | 43.8745 | 26.8086 | منتظم | No
2100084556 | أمانة / جازان | تشييد | ذات اولوية عالية | 4649975 | 232498.75 | 2077265 | 2077265 | 5900012775 | لا | 0 | 190401133184 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 90 | 100 | 2019-01-28 | 2020-07-21 | 2021-11-11 | 2021-11-11 | 2020-07-21 |  | ضعف كفاءة المقاول الفنية |  | 42.6136 | 16.8804 | منجز | No
2100103924 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1315679.3 | 65783.965 | 853379.1 | 853379.1 | 3350009773 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2018-02-03 | 2018-08-05 | 2022-08-19 | 2022-08-19 | 2018-08-05 |  |  |  | 43.9544 | 26.3504 | منجز | No
2100050595 | أمانة / جازان | تشييد | ذات اولوية عالية | 1463570 | 73178.5 | 0 | 0 | 5900008127 | لا | 0 | 181109361604 | مسحوب | تكلفة العمل المنجز | 0 | 100 | 2013-06-10 | 2013-12-07 | 2019-02-25 | 2019-02-25 |  |  | اخرى |  | 42.5966 | 16.954 | مسحوب | No
2100084431 | أمانة / جازان | تشييد | ذات اولوية عالية | 8987515 | 449375.75 | 6991514 | 6991514 | 4031058260 | لا | 0 | 190909138538 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 91 | 100 | 2015-11-03 | 2019-07-31 | 2021-11-11 | 2021-11-11 | 2019-07-31 |  | تأخرصرف المستحقات المالية |  | 42.5792 | 16.8868 | منجز | No
2100059345 | وزارة الحرس الوطني / الشؤون الصحية | تشييد | ذات اولوية عالية | 5980150.65 | 299007.5325 | 2547818.37 | 2547818.37 | 1010207379 | لا | 0 | 181109354683 | جاري | الكميات التي تم تركيبها | 89 | 100 | 2019-02-14 | 2019-11-10 | 2023-02-28 | 2023-02-28 |  |  | أوامر تغيير |  | 46.8565 | 24.7502 | متأخر | No
2300237904 | أمانة / القصيم | تشييد | ذات اولوية متوسطة | 799250 | 39962.5 | 150000 | 100000 | 1134000105 | لا | 0 |  | جاري | تكلفة العمل المنجز | 25 | 30 | 2022-11-20 | 2023-03-19 | 2023-03-19 | 2023-03-19 |  |  |  |  | 42.9612 | 25.8111 | منتظم | No
2100103176 | وزارة الداخلية / ديوان وزارة الداخلية | تصميم وتشييد | ذات اولوية عالية وعاجلة | 2079815002 | 103990750.1 | 1723329013 | 1723329013 | 1010199246 | لا | 0 | 181009208423 | جاري | التكلفة المفوترة | 79 | 87.23 | 2014-09-24 | 2018-04-08 | 2024-10-19 | 2024-10-19 |  |  | تأخرصرف المستحقات المالية |  | 46.7098 | 24.6275 | متأخر | No
2100099945 | وزارة الداخلية / ديوان وزارة الداخلية | تصميم وتشييد | ذات اولوية عالية وعاجلة | 2384094453 | 119204722.65 | 1656053055 | 1634916105 | 1010152417 | لا | 0 | 181009209237 | جاري | التكلفة المفوترة | 78.5 | 91.5 | 2014-09-17 | 2018-01-24 | 2025-03-26 | 2025-03-26 |  |  | تأخرصرف المستحقات المالية |  | 46.7098 | 24.6275 | متأخر | No
2100020963 | وزارة الداخلية / ديوان وزارة الداخلية | تصميم وتشييد | ذات اولوية عالية وعاجلة | 2492231702 | 124611585.1 | 2048078220 | 2033848461 | 1010004739 | لا | 0 | 180909084609 | جاري | التكلفة المفوترة | 90.8 | 97.5 | 2014-11-10 | 2019-06-30 | 2023-11-03 | 2023-11-03 |  |  | تأخرصرف المستحقات المالية |  | 46.7098 | 24.6275 | متأخر | No
2100108312 | وزارة الداخلية / ديوان وزارة الداخلية | تصميم وتشييد | ذات اولوية عالية وعاجلة | 2375632695 | 118781634.75 | 596223615 | 596223615 | 1010254468 | لا | 0 | 180909085146 | جاري | التكلفة المفوترة | 26.74 | 33.37 | 2014-11-03 | 2017-10-08 | 2024-11-03 | 2024-11-03 |  |  | تأخرصرف المستحقات المالية |  | 46.7098 | 24.6275 | متأخر | No
2100067480 | أمانة / جازان | تشييد | ذات اولوية عالية | 4542800 | 227140 | 1158475 | 1158475 | 5904006379 | لا | 0 | 181109375366 | مسحوب | الكميات التي تم تركيبها | 35 | 100 | 2014-12-11 | 2015-12-11 | 2020-02-28 | 2020-02-28 |  |  | ضعف كفاءة المقاول الفنية |  | 42.8376 | 16.9589 | مسحوب | No
2100081782 | أمانة / جازان | تشييد | ذات اولوية عالية | 2662400 | 133120 | 1475723 | 1475723 | 1010245651 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 55 | 100 | 2013-12-22 | 2014-12-17 | 2014-12-17 | 2014-12-17 |  |  | اخرى |  | 42.026 | 17.7203 | مسحوب | No
2100017603 | أمانة / جازان | تشييد | ذات اولوية عالية وعاجلة | 13992900 | 699645 | 7067000 | 7067000 | 5950011052 | لا | 0 |  | جاري | اخرى | 92 | 100 | 2018-10-18 | 2020-04-08 | 2021-12-25 | 2021-12-25 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 43.048 | 17.0373 | Failed | No
2100078750 | أمانة / جازان | دراسة الجدوى | ذات اولوية متوسطة | 85500 | 4275 | 85500 | 85500 | 1131049510 | لا | 0 | 180701031608 | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2018-08-28 | 2019-05-25 | 2019-05-25 | 2019-05-25 | 2019-05-25 |  | اخرى |  |  |  | منجز | No
2200226461 | وزارة الحرس الوطني / الشؤون الصحية | توريد وتركيب | ذات اولوية عالية | 883200 | 44160 | 694181.95 | 694181.95 | 7016262458 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2022-05-23 | 2022-07-22 | 2022-07-31 | 2022-07-31 | 2022-07-22 |  |  |  | 46.8716 | 24.7622 | منجز | No
2100192006 | وزارة الصحة / ديوان الوزارة | تشييد | ذات اولوية عالية | 355662193.98 | 17783109.699 | 232922596.65 | 232922596.65 | 1010094890 | لا | 0 | 181109270724 | جاري | تكلفة العمل المنجز | 92.01 | 100 | 2013-04-02 | 2016-02-29 | 2023-01-31 | 2023-01-31 |  |  |  |  | 42.7157 | 18.35 | متأخر | No
2100104403 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1906851.64 | 95342.582 | 1329591 | 1329591 | 3350009773 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2018-02-10 | 2019-01-20 | 2022-02-16 | 2022-02-16 | 2019-01-20 |  |  |  | 43.9544 | 26.3504 | منجز | No
2200229331 | الجمارك السعودية | تشييد | ذات اولوية عالية | 77790247.69 | 3889512.3845 | 305453.53 | 305453.53 | 1010212437 | لا | 0 |  | جاري | تكلفة العمل المنجز | 24 | 100 | 2021-12-21 | 2022-08-21 | 2022-10-20 | 2022-10-20 |  |  |  |  | 41.0119 | 30.9931 | Failed | No
2100078890 | الهيئة العامة للموانئ | تصميم | ذات اولوية عالية وعاجلة | 1648400 | 82420 | 1083000 | 1083000 | 4030237912 | لا | 0 | 200801041764 | جاري | تكلفة العمل المنجز | 90 | 100 | 2020-01-05 | 2020-05-03 | 2023-03-01 | 2023-03-01 |  |  | لا يوجد تأخير |  | 38.0642 | 24.073 | Failed | No
2300237930 | وزارة الصحة | تشييد | ذات اولوية عالية | 273521804.05 | 13676090.2025 | 0 | 0 | 1010151889 | نعم | 153219133.84 | 200301010236 | جاري | تكلفة العمل المنجز | 1.49 | 13.02 | 2022-01-19 | 2025-01-18 | 2025-01-18 | 2025-01-18 |  |  |  |  | 41.6271 | 27.4719 | متأخر | No
2200227496 | الهيئة العامة للموانئ | توريد وتركيب | ذات اولوية منخفضة | 199686 | 9984.3 | 180945.6 | 0 | 1010055929 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2022-05-26 | 2022-07-25 | 2022-07-20 | 2022-07-20 | 2022-07-25 |  |  |  | 38.0689 | 24.0855 | منجز | Yes
2100058936 | وزارة الحرس الوطني / الشؤون الصحية | تشييد | ذات اولوية عالية | 7444008.99 | 372200.4495 | 4804138.02 | 4804138.02 | 5950030528 | لا | 0 | 190901142004 | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-11-07 | 2020-10-26 | 2022-12-31 | 2022-12-31 |  |  | اخرى |  | 46.8565 | 24.7502 | Failed | No
2100038356 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2499065 | 124953.25 | 1336059.2 | 1185435.2 | 4650031854 | لا | 0 |  | جاري | التكلفة المفوترة | 63 | 100 | 2015-03-15 | 2016-05-30 | 2023-06-15 | 2023-06-15 |  |  | ضعف كفاءة المقاول الفنية |  | 37.2326 | 27.1538 | Failed | No
2100063910 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 465039 | 23251.95 | 465039 | 465039 | 2050069357 | لا | 0 | 191001168846 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-07-06 | 2020-06-24 | 2020-06-22 | 2020-06-22 | 2020-06-24 |  |  |  | 47.0677 | 27.0141 | منجز | No
2100026611 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 13529421 | 676471.05 | 0 | 0 | 2051007339 | لا | 0 |  | مسحوب | منهجية القيمة المكتسبة | 22 | 100 | 2019-03-09 | 2020-02-26 | 2021-06-16 | 2021-06-16 |  |  | ضعف كفاءة المقاول الفنية |  | 50.0129 | 26.5404 | مسحوب | No
2100044310 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 1093550 | 54677.5 | 1093550 | 1093550 | 2050018628 | لا | 0 | 191101075221 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-05-07 | 2020-03-11 | 2020-03-11 | 2020-03-11 | 2020-03-11 |  |  |  | 49.6707 | 25.9168 | منجز | No
2200229876 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 620379 | 31018.95 | 620379 | 620379 | 2056005766 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2022-06-27 | 2023-11-26 | 2023-11-26 | 2023-11-26 | 2023-11-26 |  |  |  | 48.4887 | 28.4257 | منجز | No
2200228270 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 2359800 | 117990 | 0 | 0 | 1010094436 | لا | 0 |  | جاري | تكلفة العمل المنجز | 31 | 59 | 2022-06-29 | 2023-06-18 | 2023-06-18 | 2023-06-18 |  |  |  |  | 49.4182 | 25.956 | Failed | No
2200229924 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 316658.25 | 15832.9125 | 0 | 0 | 2050132083 | لا | 0 |  | جاري | تكلفة العمل المنجز | 0 | 67 | 2022-08-02 | 2023-03-26 | 2023-03-26 | 2023-03-26 |  |  |  | تم إنذار المقاول كتابيا | 48.4288 | 27.2669 | Failed | No
2100114310 | جامعة أم القرى | ترميم | ذات اولوية عالية وعاجلة | 34857764.34 | 1742888.217 | 29142023.81 | 29142023.81 | 2252004545 | لا | 0 | 200609149573 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 99 | 100 | 2019-05-22 | 2020-05-22 | 2022-11-17 | 2022-11-17 | 2020-05-22 |  |  |  | 39.9532 | 21.3259 | منجز | No
2100077140 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 1484200 | 74210 | 1484200 | 1484200 | 2057001166 | لا | 0 | 201209151434 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-11-09 | 2020-12-14 | 2021-06-27 | 2021-06-27 | 2020-12-14 |  |  |  | 48.4884 | 28.379 | منجز | No
2100062952 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 2516700 | 125835 | 2516700 | 2516700 | 1010094436 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-10-13 | 2019-10-05 | 2019-10-06 | 2019-10-06 | 2019-10-05 |  |  |  | 49.4718 | 25.9952 | منجز | No
2100065214 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 1046660 | 52333 | 1046660 | 1046660 | 2056002346 | لا | 0 | 190809056404 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-03-30 | 2020-03-18 | 2020-03-18 | 2020-03-18 | 2020-03-18 |  |  |  | 48.4307 | 27.2633 | منجز | No
2100068493 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 8197500 | 409875 | 8197500 | 8197500 | 2056001352 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-11-20 | 2020-07-13 | 2021-07-01 | 2021-07-01 | 2020-07-13 |  |  |  | 48.4855 | 27.4704 | منجز | No
2100026854 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 952630 | 47631.5 | 952630 | 952630 | 2056002038 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-02-16 | 2020-02-01 | 2021-06-16 | 2021-06-16 | 2020-02-01 |  |  |  | 48.3789 | 26.9882 | منجز | No
2100080323 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 6105610.35 | 305280.5175 | 6105610.35 | 6105610.35 | 2060024520 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-03-09 | 2020-02-26 | 2021-06-28 | 2021-06-28 | 2020-02-26 |  |  |  | 49.9996 | 26.5546 | منجز | No
2100052636 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 1396374 | 69818.7 | 1396374 | 1396374 | 2056001462 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-12-21 | 2020-12-26 | 2020-12-26 | 2020-12-26 | 2020-12-26 |  |  |  | 48.4997 | 27.4629 | منجز | No
2100030870 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 7158302 | 357915.1 | 7158302 | 7158302 | 2060023127 | لا | 0 | 200309017150 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-08-24 | 2020-08-12 | 2021-01-27 | 2021-01-27 | 2020-08-12 |  |  |  | 50.005 | 26.5291 | منجز | No
2100013720 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 9655800 | 482790 | 9655800 | 9655800 | 2062016958 | لا | 0 | 190201011826 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-08-25 | 2021-05-09 | 2021-09-09 | 2021-09-09 | 2021-05-09 |  |  |  | 49.5448 | 27.031 | منجز | No
2100056070 | جامعة شقراء | تشييد | ذات اولوية عالية | 27373409.29 | 1368670.4645 | 24635042.19 | 24635042.19 | 1010114475 | لا | 0 | 181201409900 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-11-07 | 2019-05-06 | 2021-12-25 | 2021-12-25 | 2019-05-06 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 45.139 | 25.1705 | منجز | No
2100085842 | أمانة / حائل | دراسة الجدوى | ذات اولوية متوسطة | 1052363 | 52618.15 | 675000 | 675000 | 3352359921 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 63 | 100 | 2015-10-05 | 2017-09-24 | 2020-01-14 | 2020-01-14 |  |  | ضعف كفاءة المقاول الفنية |  | 42.9034 | 28.2418 | مسحوب | No
2100073861 | جامعة شقراء | تشييد | ذات اولوية متوسطة | 102711566.38 | 5135578.319 | 85094675.25 | 85094675.25 | 1010011949 | لا | 0 | 180709036296 | جاري | تكلفة العمل المنجز | 95 | 100 | 2013-04-27 | 2015-04-17 | 2022-03-01 | 2022-03-01 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 45.3896 | 24.1062 | Failed | No
2100194386 | جامعة شقراء | تشييد | ذات اولوية عالية وعاجلة | 96617783.28 | 4830889.164 | 21522311.87 | 16352918.98 | 4031038849 | لا | 0 | 190401087764 | ايقاف جزئي | تكلفة العمل المنجز | 21 | 60 | 2020-09-20 | 2022-03-14 | 2023-06-01 | 2023-06-01 |  |  |  |  | 45.1443 | 25.1772 | Failed | No
2100078433 | أمانة / جازان | دراسة الجدوى | ذات اولوية متوسطة | 981984 | 49099.2 | 818320 | 818320 | 5900020940 | لا | 0 | 190301022793 | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 96 | 100 | 2018-12-03 | 2020-11-22 | 2020-10-14 | 2020-10-14 | 2020-11-22 |  | اخرى |  |  |  | منجز | No
2100031544 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 6964350.87 | 348217.5435 | 3444082.44 | 3444082.44 | 1010264550 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 67 | 100 | 2014-03-03 | 2015-08-25 | 2019-07-02 | 2019-07-02 |  |  | اخرى |  | 42.5993 | 16.9291 | مسحوب | No
2100078234 | جامعة شقراء | تشييد | ذات اولوية عالية | 103973538.92 | 5198676.946 | 103973538.92 | 103973538.92 | 4030179603 | لا | 0 | 180909091171 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2012-12-31 | 2015-06-19 | 2019-08-14 | 2019-08-14 |  |  |  |  | 45.1435 | 24.1763 | Failed | No
2100049593 | أمانة / جازان | تشييد | ذات اولوية عالية | 6286000 | 314300 | 0 | 0 | 5907007322 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 82 | 100 | 2019-11-12 | 2020-11-06 | 2022-03-30 | 2022-03-30 | 2020-11-06 |  | ضعف كفاءة المقاول الفنية |  | 42.9362 | 16.6028 | منجز | No
2100068666 | أمانة / جازان | تشييد | ذات اولوية عالية | 45010875 | 2250543.75 | 18864716 | 18864716 | 5900008127 | لا | 0 | 190401064609 | جاري | اخرى | 78 | 71 | 2019-09-15 | 2021-09-04 | 2021-09-05 | 2021-09-05 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5774 | 16.9339 | Failed | No
2100095270 | وزارة الصحة / بيشة | تشييد | ذات اولوية عالية | 2672130 | 133606.5 | 0 | 0 | 1136000755 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 10 | 100 | 2012-11-02 | 2013-10-22 | 2022-11-15 | 2022-11-15 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 21 | 23 | مسحوب | No
2100078142 | مدينة الملك عبدالله الطبية بالعاصمة المقدسة | تشييد | ذات اولوية عالية | 7436689.07 | 371834.4535 | 2778308.29 | 2778308.29 | 1010197808 | لا | 0 | 190701040925 | جاري | الكميات التي تم تركيبها | 95 | 100 | 2020-12-25 | 2022-06-25 | 2023-02-21 | 2023-02-21 |  |  | موافقات |  | 39.8811 | 21.382 | Failed | No
2100101673 | وزارة الصحة / بيشة | تشييد | ذات اولوية عالية | 3199139.46 | 159956.973 | 1205977 | 1205977 | 1010240529 | لا | 0 | 200639167237 | مسحوب | تكلفة العمل المنجز | 63 | 100 | 2012-11-05 | 2013-10-24 | 2022-11-15 | 2022-11-15 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 22 | 20 | مسحوب | No
2100195650 | جامعة أم القرى | تشييد | ذات اولوية عالية | 7675182.9 | 383759.145 | 5561028.12 | 5561028.12 | 4031019772 | لا | 0 | 191101340211 | جاري | تكلفة العمل المنجز | 87 | 100 | 2019-10-21 | 2020-07-11 | 2023-03-27 | 2023-03-27 |  |  |  | تم إشعار المقاول كتابيا بالتأخير | 39.952 | 21.3317 | Failed | No
2100093144 | أمانة / جازان | تشييد | ذات اولوية عالية | 8048887 | 402444.35 | 1152460 | 1152460 | 5904006379 | لا | 0 | 180809061125 | مسحوب | الكميات التي تم تركيبها | 60 | 100 | 2014-02-11 | 2016-02-01 | 2021-08-21 | 2021-08-21 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5942 | 16.9032 | مسحوب | No
2100076296 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية عالية | 99000000 | 4950000 | 103657502 | 90000000 | 2051030949 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2017-10-18 | 2020-03-21 | 2020-03-21 | 2020-03-21 | 2020-03-21 |  |  |  | 50.0647 | 26.3131 | منجز | No
2100016332 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 10434375.52 | 521718.776 | 0 | 0 | 1131021347 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 73 | 6 | 2020-05-13 | 2021-01-23 | 2022-11-25 | 2022-11-25 | 2021-01-23 |  |  |  | 43.9544 | 26.3504 | منجز | No
2100042490 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2099545 | 104977.25 | 70697.54 | 70697.54 | 5857034359 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 15 | 100 | 2014-10-21 | 2016-05-24 | 2024-01-01 | 2024-01-01 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7271 | 22.2863 | مسحوب | No
2100097812 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 7815644.44 | 390782.222 | 2628830 | 2628830 | 2943000000 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 35 | 100 | 2014-03-27 | 2016-03-16 | 2022-10-31 | 2022-10-31 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7271 | 22.2863 | مسحوب | No
2100101684 | وزارة الصحة / بيشة | توريد وتركيب | ذات اولوية عالية وعاجلة | 1170138 | 58506.9 | 1170138 | 833850 | 1010294298 | لا | 0 | 180901111920 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-06-11 | 2018-11-04 | 2020-09-17 | 2020-09-17 | 2018-11-04 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.6132 | 20.0346 | منجز | No
2100082891 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 5000000 | 250000 | 6631275 | 6631275 | 5907010673 | لا | 0 | 190401103327 | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2019-06-09 | 2019-12-06 | 2021-12-15 | 2021-12-15 | 2019-12-06 |  | ضعف كفاءة المقاول الفنية |  | 42.6261 | 17.01 | منجز | No
2100022061 | وزارة الصحة / بيشة | تشييد | ذات اولوية عالية | 2745765 | 137288.25 | 206490 | 206490 | 1136000755 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 10 | 100 | 2012-11-02 | 2013-10-22 | 2022-11-15 | 2022-11-15 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.8462 | 19.2512 | مسحوب | No
2100000976 | وزارة الصحة / بيشة | تشييد | ذات اولوية عالية وعاجلة | 1942380 | 97119 | 573400 | 573400 | 1010294298 | لا | 0 | 180501011246 | مسحوب | تكلفة العمل المنجز | 78 | 100 | 2018-07-03 | 2019-03-25 | 2022-08-17 | 2022-08-17 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42 | 20 | مسحوب | No
2100004340 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 1530659 | 76532.95 | 1015940.83 | 1015940.83 | 1131042309 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 92 | 100 | 2014-11-19 | 2016-01-13 | 2023-02-18 | 2023-02-18 | 2016-01-13 |  | تأخرصرف المستحقات المالية |  | 44.8241 | 26.3046 | منجز | No
2100097801 | وزارة الداخلية / ديوان وزارة الداخلية | تصميم وتشييد | ذات اولوية عالية وعاجلة | 10266284472.71 | 513314223.6355 | 2890136433.3 | 2890136433.3 | 1010254468 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 42.1 | 67.21 | 2013-08-22 | 2016-08-05 | 2024-12-31 | 2024-12-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال | أخرى | 46.5307 | 24.9028 | Failed | No
2100027230 | وزارة الداخلية / ديوان وزارة الداخلية | تصميم وتشييد | ذات اولوية عالية وعاجلة | 11209856101.38 | 560492805.069 | 1722231961.87 | 1655561668.11 | 1010254468 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 19.44 | 27.65 | 2015-08-17 | 2018-07-31 | 2025-08-31 | 2025-08-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال | أخرى | 39.0982 | 21.8605 | متأخر | No
2100048451 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 1192904 | 59645.2 | 814276 | 814276 | 5859006036 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 68 | 68 | 2015-06-14 | 2016-06-14 | 2022-10-01 | 2022-10-01 |  |  | ضعف كفاءة المقاول الفنية |  | 41.661 | 19.9966 | مسحوب | No
2100085072 | وزارة الصحة / الطائف | تشييد | ذات اولوية عالية وعاجلة | 19942120 | 997106 | 6942120 | 6942120 | 2050018622 | لا | 0 | 190409025680 | مسحوب | تكلفة العمل المنجز | 55 | 100 | 2017-09-12 | 2019-02-26 | 2021-12-01 | 2021-12-01 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 40.4167 | 21.2677 | مسحوب | No
2100078411 | وزارة الصحة / الطائف | تشييد | ذات اولوية عالية وعاجلة | 18338105 | 916905.25 | 11471979 | 11471979 | 5851000726 | لا | 0 | 200409064479 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 98 | 100 | 2014-11-02 | 2018-10-21 | 2021-12-01 | 2021-12-01 | 2018-10-21 |  | تأخرصرف المستحقات المالية |  | 40.4537 | 21.2451 | منجز | No
2100073905 | وزارة الصحة / الطائف | تشييد | ذات اولوية عالية | 6368184 | 318409.2 | 0 | 0 | 4030086483 | نعم | 1 | 201109355540 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-06-11 | 2020-05-30 | 2021-12-01 | 2021-12-01 | 2020-05-30 |  | تأخرصرف المستحقات المالية |  |  |  | منجز | No
2100029131 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 5179335 | 258966.75 | 3753029.52 | 0 | 1010056094 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-10-22 | 2016-04-14 | 2020-01-01 | 2020-01-01 | 2016-04-14 |  | ضعف كفاءة المقاول الفنية |  | 46.6672 | 24.6994 | منجز | Yes
2100032443 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 5748980 | 287449 | 1921247.91 | 0 | 1114000037 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 35 | 100 | 2014-07-20 | 2016-07-09 | 2020-11-27 | 2020-11-27 |  |  | ضعف كفاءة المقاول الفنية |  | 46.0483 | 25.0881 | مسحوب | Yes
2100062646 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1453250 | 72662.5 | 525060 | 0 | 1010045354 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 87 | 100 | 2015-06-17 | 2016-09-09 | 2020-02-13 | 2020-02-13 | 2016-09-09 |  | ضعف كفاءة المقاول الفنية |  | 46.4208 | 24.8956 | منجز | Yes
2100058111 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 5977500 | 298875 | 5554498.5 | 0 | 1010203405 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 100 | 2015-01-10 | 2018-06-23 | 2018-06-23 | 2018-06-23 | 2018-06-23 |  |  |  | 42.9598 | 23.92 | منجز | Yes
2100088981 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 933579 | 46678.95 | 0 | 0 | 2057001038 | لا | 0 |  | جاري | التكلفة المفوترة | 50 | 100 | 2012-07-13 | 2013-04-09 | 2023-01-15 | 2023-01-15 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | Failed | No
2100030343 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2671163 | 133558.15 | 2394184.44 | 0 | 1010242793 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-11-16 | 2016-02-09 | 2019-10-01 | 2019-10-01 | 2016-02-09 |  | ضعف كفاءة المقاول الفنية |  | 46.6933 | 24.7219 | منجز | Yes
2100090425 | جامعة أم القرى | تشييد | ذات اولوية متوسطة | 107291649.12 | 5364582.456 | 56117174.5 | 56117174.5 | 4030006877 | لا | 0 | 181109245957 | ايقاف كلي | تكلفة العمل المنجز | 55 | 100 | 2013-06-24 | 2015-11-27 | 2025-12-30 | 2025-12-30 |  |  | ضعف كفاءة المقاول الفنية | أخرى | 39.9262 | 21.3437 | Failed | No
2100064503 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 502860 | 25143 | 0 | 0 | 1010350150 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 94 | 100 | 2019-04-27 | 2020-07-27 | 2023-01-27 | 2023-01-27 |  |  | ضعف كفاءة المقاول الفنية |  | 45.5167 | 23.5406 | Failed | No
2100057374 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1050000 | 52500 | 41807 | 0 | 1116005842 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 10 | 100 | 2015-01-17 | 2016-04-11 | 2018-12-25 | 2018-12-25 |  |  | ضعف كفاءة المقاول الفنية |  | 43.2746 | 24.3491 | مسحوب | Yes
2100045242 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2055000 | 102750 | 42064 | 0 | 1010290949 | لا | 0 |  | جاري | تكلفة العمل المنجز | 74 | 100 | 2015-10-14 | 2017-01-06 | 2020-01-18 | 2020-01-18 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6617 | 24.7181 | Failed | Yes
2100030203 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 949050 | 47452.5 | 854144 | 0 | 1185000614 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 95 | 2014-11-25 | 2015-09-21 | 2015-09-15 | 2015-09-15 | 2015-09-21 |  | ضعف كفاءة المقاول الفنية |  | 46.6933 | 24.7194 | منجز | Yes
2100044096 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2600468.69 | 130023.4345 | 1326830.82 | 0 | 1113000219 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 65 | 2018-06-07 | 2020-01-28 | 2020-01-28 | 2020-01-28 | 2020-01-28 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 46.6795 | 24.7119 | منجز | Yes
2100100531 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 37855006 | 1892750.3 | 37855006 | 0 | 1116001737 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 96 | 100 | 2013-10-20 | 2015-09-25 | 2022-12-20 | 2022-12-20 |  |  | تأخرصرف المستحقات المالية |  | 42.9609 | 23.9125 | Failed | Yes
2100100892 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2694650 | 134732.5 | 41455 | 0 | 1018000156 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 82 | 100 | 2014-02-23 | 2015-05-19 | 2021-07-04 | 2021-07-04 |  |  | ضعف كفاءة المقاول الفنية |  | 45.855 | 25.2995 | مسحوب | Yes
2100007140 | جامعة أم القرى | تشييد | ذات اولوية عالية | 28692084.93 | 1434604.2465 | 20658272.61 | 20658272.61 | 1010152417 | لا | 0 | 181109272248 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2010-04-07 | 2012-03-15 | 2023-02-28 | 2023-02-28 |  |  |  | أخرى | 39.929 | 21.3471 | Failed | No
2100030715 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2245164.7 | 112258.235 | 1018800 | 0 | 1113000219 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 42 | 2018-11-14 | 2020-05-07 | 2020-05-06 | 2020-05-06 | 2020-05-07 |  |  |  | 46.6878 | 24.6895 | منجز | Yes
2100045474 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 17751534.43 | 887576.7215 | 6554155.341 | 0 | 4030065096 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2010-05-03 | 2011-07-27 | 2011-07-27 | 2011-07-27 | 2011-07-27 |  | ضعف كفاءة المقاول الفنية |  | 44.8739 | 20.421 | منجز | Yes
2300238011 | أمانة / القصيم | تشييد | ذات اولوية متوسطة | 1463030 | 73151.5 | 1 | 1 | 1010244841 | لا | 0 |  | جاري | تكلفة العمل المنجز | 1 | 1 | 2022-11-27 | 2023-11-26 | 2023-11-26 | 2023-11-26 |  |  |  |  | 42.932 | 24.7219 | منتظم | No
2100039815 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 37161150 | 1858057.5 | 0 | 0 | 1010203405 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 98 | 100 | 2014-09-17 | 2016-09-06 | 2022-12-02 | 2022-12-02 |  |  | تأخرصرف المستحقات المالية |  | 42.9031 | 23.8993 | Failed | No
2100042184 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البحرية | تشييد | ذات اولوية متوسطة | 44377400 | 2218870 | 31507800 | 31507800 | 1010066115 | لا | 0 | 180901108470 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-03-31 | 2020-09-21 | 2022-03-31 | 2022-03-31 | 2020-09-21 |  |  |  | 39.1728 | 22.3519 | منجز | No
2100055086 | جامعة أم القرى | تشييد | ذات اولوية عالية | 96646666.45 | 4832333.3225 | 63597063.07 | 63597063.07 | 4030006877 | لا | 0 | 181109272642 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2011-04-02 | 2013-09-04 | 2022-12-30 | 2022-12-30 | 2013-09-04 |  |  | أخرى | 39.9297 | 21.347 | منجز | No
2100057923 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 371220 | 18561 | 190220 | 0 | 1113000219 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 51 | 100 | 2014-11-04 | 2015-08-01 | 2019-12-17 | 2019-12-17 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 45.8701 | 25.2787 | Failed | Yes
2100048775 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 300000 | 15000 | 0 | 0 | 1010194071 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 83 | 2019-01-13 | 2020-01-09 | 2020-01-10 | 2020-01-10 | 2020-01-09 |  |  |  | 46.1447 | 24.5975 | منجز | No
2100081384 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1164305 | 58215.25 | 539765 | 0 | 1010010466 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-05-23 | 2019-08-16 | 2019-08-16 | 2019-08-16 | 2019-08-16 |  |  |  | 45.2698 | 24.0658 | منجز | Yes
2100023225 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 13575560 | 678778 | 4172039.1 | 1672039.86 | 1010090099 | لا | 0 |  | مسحوب | التكلفة المفوترة | 40 | 100 | 2012-07-03 | 2014-06-25 | 2022-05-11 | 2022-05-11 |  |  | ضعف كفاءة المقاول الفنية |  | 42.6031 | 20.0028 | مسحوب | No
2100009984 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 461500 | 23075 | 461500 | 0 | 1116002990 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 100 | 2019-01-01 | 2021-06-16 | 2021-06-23 | 2021-06-23 | 2021-06-16 |  | ضعف كفاءة المقاول الفنية |  | 46.7833 | 23.3645 | منجز | Yes
2100100376 | أمانة / الرياض | دراسة الجدوى | ذات اولوية متوسطة | 5892000 | 294600 | 0 | 0 | 1010463299 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-05-27 | 2020-05-16 | 2020-05-16 | 2020-05-16 | 2020-05-16 |  | اخرى |  |  |  | منجز | No
2100001083 | جامعة أم القرى | تشييد | ذات اولوية عالية وعاجلة | 102734822.47 | 5136741.1235 | 57399528.55 | 57399528.55 | 1010066115 | لا | 0 | 181109246273 | جاري | تكلفة العمل المنجز | 66 | 95 | 2012-11-20 | 2014-02-13 | 2023-04-06 | 2023-04-06 |  |  |  | مخطط لسحبه وإعادة ترسيته | 39.9273 | 21.3482 | Failed | No
2100016903 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4915000 | 245750 | 3358708 | 0 | 1010276314 | لا | 0 |  | جاري | تكلفة العمل المنجز | 93 | 100 | 2013-09-10 | 2014-09-05 | 2022-12-04 | 2022-12-04 |  |  | ضعف كفاءة المقاول الفنية |  | 47.3248 | 24.1576 | Failed | Yes
2100034462 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 11935900 | 596795 | 0 | 0 | 1118001565 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 63 | 27 | 2018-10-30 | 2021-04-17 | 2021-04-17 | 2021-04-17 |  |  |  |  | 42.9204 | 23.8963 | Failed | No
2100012972 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 390000 | 19500 | 280500 | 0 | 1011124898 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 44 | 2019-01-22 | 2020-01-17 | 2020-01-17 | 2020-01-17 | 2020-01-17 |  |  |  | 46.6727 | 24.7094 | منجز | Yes
2100071411 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3821940 | 191097 | 41729 | 0 | 1117001757 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 100 | 2014-09-23 | 2016-03-16 | 2016-03-16 | 2016-03-16 | 2016-03-16 |  |  |  | 45.5149 | 23.545 | منجز | Yes
2100062845 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4770000 | 238500 | 0 | 0 | 1116001737 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-08-06 | 2018-11-29 | 2018-11-30 | 2018-11-30 | 2018-11-29 |  | ضعف كفاءة المقاول الفنية |  | 46.683 | 24.7001 | منجز | No
2200235686 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البحرية | دراسات هندسية | ذات اولوية عالية وعاجلة | 32975933.75 | 1648796.6875 | 0 | 0 | 1010459572 | لا | 0 |  | جاري | تكلفة العمل المنجز | 17 | 20 | 2022-10-16 | 2023-07-13 | 2023-07-13 | 2023-07-13 |  |  |  |  | 39.1963 | 21.395 | خدمات عامة | No
2100081690 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1940000 | 97000 | 42141 | 0 | 1113001088 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 0 | 100 | 2015-12-13 | 2016-12-07 | 2016-12-07 | 2016-12-07 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 46.1367 | 24.5978 | مسحوب | Yes
2100108802 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البحرية | تشييد | ذات اولوية عالية | 23941253.07 | 1197062.6535 | 12907455 | 12907455 | 5901011129 | نعم | 18671093.92 | 181101298250 | جاري | الكميات التي تم تركيبها | 60 | 100 | 2018-10-16 | 2020-06-10 | 2023-05-31 | 2023-05-31 |  |  |  | تم إنذار المقاول كتابيا | 42.6261 | 16.9027 | Failed | No
2100028770 | أمانة / الرياض | تشييد | ذات اولوية عالية | 8835670 | 441783.5 | 7271590 | 0 | 1010101252 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 87 | 100 | 2014-02-26 | 2015-10-19 | 2015-10-19 | 2015-10-19 | 2015-10-19 |  |  |  | 46.4087 | 24.8992 | منجز | Yes
2100033445 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 868500 | 43425 | 753075 | 0 | 1131051916 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 86 | 100 | 2015-12-03 | 2017-02-25 | 2017-06-25 | 2017-06-25 | 2017-02-25 |  |  |  | 46.6541 | 24.6988 | منجز | Yes
2100051704 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 5444820 | 272241 | 2352216 | 0 | 1116001737 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 96 | 100 | 2015-09-05 | 2017-02-26 | 2022-06-01 | 2022-06-01 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6665 | 24.7013 | Failed | Yes
2100057304 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 985000 | 49250 | 232263 | 0 | 1017001594 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 23 | 100 | 2015-08-10 | 2017-01-31 | 2019-10-15 | 2019-10-15 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6727 | 24.7032 | مسحوب | Yes
2100027101 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 838875 | 41943.75 | 838874.9996 | 0 | 1170000951 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-09-13 | 2018-11-19 | 2018-11-19 | 2018-11-19 | 2018-11-19 |  |  |  | 46.6795 | 24.7057 | منجز | Yes
2100102642 | أمانة / الرياض | دراسة الجدوى | ذات اولوية متوسطة | 563115 | 28155.75 | 563115 | 0 | 1011008928 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-08-28 | 2019-03-30 | 2019-03-30 | 2019-03-30 | 2019-03-30 |  | اخرى |  |  |  | منجز | Yes
2100010323 | وزارة التعليم | تشييد | ذات اولوية عالية | 28044517 | 1402225.85 | 24599230 | 24599230 | 1131012642 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2012-12-30 | 2015-08-16 | 2020-08-16 | 2020-08-16 | 2015-08-16 |  |  |  | 43.9544 | 26.3504 | منجز | No
2100090392 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2076500 | 103825 | 41406 | 0 | 1010244941 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 89.98 | 100 | 2014-01-29 | 2015-04-24 | 2022-10-31 | 2022-10-31 |  |  | ضعف كفاءة المقاول الفنية |  | 45.3494 | 26.4964 | Failed | Yes
2100039023 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2325801 | 116290.05 | 1530540 | 0 | 1116004150 | لا | 0 |  | جاري | تكلفة العمل المنجز | 67 | 100 | 2012-05-09 | 2013-08-02 | 2021-08-17 | 2021-08-17 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6837 | 24.7181 | Failed | Yes
2100034565 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 786000 | 39300 | 42073 | 0 | 1010516124 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 0 | 100 | 2015-08-24 | 2016-08-08 | 2020-08-01 | 2020-08-01 |  |  | تأخرصرف المستحقات المالية |  | 46.6933 | 24.7057 | Failed | Yes
2100046653 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4834580 | 241729 | 1304766 | 0 | 1010276854 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 10 | 2019-05-08 | 2020-10-29 | 2020-10-28 | 2020-10-28 | 2020-10-29 |  |  |  | 46.6988 | 24.7144 | منجز | Yes
2100000921 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البحرية | تشييد | ذات اولوية متوسطة | 10179705 | 508985.25 | 6252750 | 6252750 | 2511009902 | لا | 0 | 201209150831 | جاري | الكميات التي تم تركيبها | 72 | 100 | 2020-05-14 | 2021-05-02 | 2023-02-28 | 2023-02-28 |  |  |  |  | 49.9793 | 26.4003 | Failed | No
2100057050 | وزارة الصحة / بيشة | تشييد | ذات اولوية عالية | 2991225 | 149561.25 | 1310193.83 | 1310193.83 | 1010222216 | لا | 0 | 201109064043 | جاري | تكلفة العمل المنجز | 75.5 | 100 | 2019-10-09 | 2021-06-15 | 2022-12-15 | 2022-12-15 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42 | 20 | Failed | No
2100029713 | أمانة / الرياض | تشييد | ذات اولوية عالية | 11878150 | 593907.5 | 8747819.25 | 0 | 1116001737 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 94.93 | 100 | 2012-05-06 | 2014-04-26 | 2019-09-08 | 2019-09-08 | 2014-04-26 |  | ضعف كفاءة المقاول الفنية |  | 42.9068 | 23.8789 | منجز | Yes
2100052113 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1633329.62 | 81666.481 | 686010 | 0 | 1010203405 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 84 | 100 | 2018-06-05 | 2020-05-25 | 2022-05-24 | 2022-05-24 |  |  |  |  | 42.9327 | 23.8859 | Failed | Yes
2100091232 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 6610580 | 330529 | 3458920 | 0 | 1113000601 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 53 | 100 | 2014-10-18 | 2016-01-11 | 2020-04-26 | 2020-04-26 |  |  | ضعف كفاءة المقاول الفنية |  | 46.2407 | 24.4488 | مسحوب | Yes
2100031150 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4388360 | 219418 | 1083000 | 0 | 1010010466 | لا | 0 |  | جاري | تكلفة العمل المنجز | 47 | 59 | 2018-10-08 | 2020-01-01 | 2020-01-01 | 2020-01-01 |  |  |  |  | 46.6768 | 24.7157 | Failed | Yes
2100012541 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3409300 | 170465 | 40831 | 0 | 1010216996 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 85 | 100 | 2012-07-13 | 2014-06-02 | 2021-06-17 | 2021-06-17 | 2014-06-02 |  | ضعف كفاءة المقاول الفنية |  | 45.8615 | 25.277 | منجز | Yes
2100104856 | وزارة التعليم | تشييد | ذات اولوية عالية | 4531069 | 226553.45 | 1775216 | 1775216 | 1131021347 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 56 | 100 | 2019-01-27 | 2019-03-28 | 2022-01-10 | 2022-01-10 | 2019-03-28 |  |  |  | 43.9544 | 26.3504 | منجز | No
2100101743 | أمانة / الرياض | دراسة الجدوى | ذات اولوية متوسطة | 1232625 | 61631.25 | 42050 | 0 | 1010024359 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 79 | 100 | 2015-08-20 | 2017-08-09 | 2017-08-09 | 2017-08-09 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | مسحوب | Yes
2100029805 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2760590 | 138029.5 | 39448 | 0 | 1010045354 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 26 | 100 | 2008-05-04 | 2009-07-28 | 2019-03-27 | 2019-03-27 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6754 | 24.7269 | مسحوب | Yes
2100080371 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 28149170 | 1407458.5 | 22313239.2 | 0 | 1010149910 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 92 | 100 | 2011-01-19 | 2013-01-08 | 2013-01-08 | 2013-01-08 | 2013-01-08 |  | ضعف كفاءة المقاول الفنية |  | 46.6809 | 24.7281 | منجز | Yes
2100032572 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 346490 | 17324.5 | 42859 | 0 | 1010240529 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2017-06-15 | 2017-07-30 | 2021-07-01 | 2021-07-01 | 2017-07-30 |  | تأخرصرف المستحقات المالية |  | 44.5948 | 25.1851 | منجز | Yes
2100030144 | أمانة / الرياض | تشييد | ذات اولوية عالية | 1624700 | 81235 | 1303825 | 0 | 1126001146 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 98 | 80 | 2014-08-13 | 2018-09-10 | 2018-09-10 | 2018-09-10 | 2018-09-10 |  |  |  | 45.8771 | 25.6914 | منجز | Yes
2100075375 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1274305 | 63715.25 | 41745 | 0 | 1013000078 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 83 | 100 | 2014-12-10 | 2015-10-06 | 2021-06-20 | 2021-06-20 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7876 | 23.4389 | Failed | Yes
2100062834 | وزارة الصحة / بيشة | تشييد | ذات اولوية عالية وعاجلة | 3909274 | 195463.7 | 681580 | 681580 | 5855033786 | لا | 0 | 180501011246 | ايقاف كلي | تكلفة العمل المنجز | 19 | 100 | 2017-04-26 | 2019-04-04 | 2022-11-17 | 2022-11-17 |  |  | أوامر تغيير |  | 43 | 19 | Failed | No
2100088745 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البحرية | تشييد | ذات اولوية متوسطة | 55528539 | 2776426.95 | 32469756 | 32469756 | 1010120275 | لا | 0 | 180809039027 | جاري | الكميات التي تم تركيبها | 78 | 100 | 2015-03-30 | 2017-10-21 | 2023-03-01 | 2023-03-01 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5544 | 16.8644 | Failed | No
2100057514 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 14358453.98 | 717922.699 | 3998804.04 | 3998804.04 | 4030146035 | لا | 0 |  | مسحوب | التكلفة المفوترة | 52 | 100 | 2012-12-16 | 2014-12-06 | 2023-12-30 | 2023-12-30 |  |  | ضعف كفاءة المقاول الفنية |  | 44.8241 | 26.3046 | مسحوب | No
2100029794 | أمانة / الرياض | تشييد | ذات اولوية عالية | 2739496 | 136974.8 | 42063 | 0 | 1010300507 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-07-11 | 2016-10-03 | 2019-10-14 | 2019-10-14 | 2016-10-03 |  | ضعف كفاءة المقاول الفنية |  |  |  | منجز | Yes
2100071606 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4994300 | 249715 | 3000000 | 0 | 1123000085 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 100 | 100 | 2015-10-14 | 2017-01-06 | 2021-07-04 | 2021-07-04 |  |  | ضعف كفاءة المقاول الفنية |  | 44.8338 | 26.3075 | Failed | Yes
2100036466 | جامعة أم القرى | تشييد | ذات اولوية عالية وعاجلة | 189982992.22 | 9499149.611 | 124134835.85 | 124134835.85 | 4030138280 | لا | 0 | 181109246108 | جاري | تكلفة العمل المنجز | 77 | 90 | 2012-11-20 | 2015-11-18 | 2022-12-31 | 2022-12-31 |  |  |  |  | 39.9275 | 21.3468 | متأخر | No
2100031032 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1757655 | 87882.75 | 865298 | 0 | 1186001229 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 58 | 100 | 2013-09-24 | 2014-12-18 | 2014-12-18 | 2014-12-18 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6809 | 24.7007 | مسحوب | Yes
2100065402 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4000400 | 200020 | 0 | 0 | 1010341087 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 56 | 20 | 2019-07-18 | 2020-10-10 | 2020-10-25 | 2020-10-25 |  |  |  |  | 46.6116 | 24.682 | Failed | No
2100031146 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2488230 | 124411.5 | 374277 | 0 | 1010290449 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 17 | 100 | 2015-07-01 | 2017-06-20 | 2017-06-20 | 2017-06-20 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6782 | 24.6895 | مسحوب | Yes
2100201563 | وزارة الصحة / بيشة | ترميم | ذات اولوية عالية | 799950 | 39997.5 | 54450 | 0 | 1010428119 | لا | 0 | 202101152094 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2021-01-06 | 2021-07-01 | 2021-12-20 | 2021-12-20 | 2021-07-01 |  |  |  | 42.0244 | 19.6968 | منجز | Yes
2100046185 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 10926425 | 546321.25 | 10926425 | 0 | 1010170119 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-02-22 | 2018-09-10 | 2018-09-10 | 2018-09-10 | 2018-09-10 |  |  |  | 47.3001 | 24.1626 | منجز | Yes
2100065273 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1894220 | 94711 | 41995 | 0 | 1010076344 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 24 | 100 | 2015-05-01 | 2016-04-15 | 2016-04-15 | 2016-04-15 |  |  | ضعف كفاءة المقاول الفنية |  | 45.898 | 24.3818 | مسحوب | Yes
2100034591 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 4071785 | 203589.25 | 1270592 | 1270592 | 5904010214 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 40 | 100 | 2013-08-27 | 2014-08-13 | 2019-02-19 | 2019-02-19 |  |  | اخرى |  | 42.5281 | 17.3689 | مسحوب | No
2100090646 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 12187087 | 609354.35 | 9923907.01 | 0 | 1010171813 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 91 | 100 | 2014-09-21 | 2016-09-10 | 2020-03-28 | 2020-03-28 | 2016-09-10 |  | ضعف كفاءة المقاول الفنية |  | 46.6713 | 24.7131 | منجز | Yes
2100107590 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البحرية | تشييد | ذات اولوية متوسطة | 47341891 | 2367094.55 | 13175542 | 13175542 | 1132008741 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 35 | 100 | 2014-10-28 | 2016-06-19 | 2025-11-30 | 2025-11-30 |  |  | ضعف كفاءة المقاول الفنية |  | 48.5905 | 28.1787 | مسحوب | No
2100071654 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 6761400 | 338070 | 1647130 | 0 | 1010168999 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 70 | 100 | 2014-08-27 | 2016-02-18 | 2020-02-28 | 2020-02-28 | 2016-02-18 |  | ضعف كفاءة المقاول الفنية |  | 46.6926 | 24.7038 | منجز | Yes
2100081734 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 9498405.5 | 474920.275 | 9158550.5 | 0 | 1010158786 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2012-06-23 | 2014-06-13 | 2019-09-08 | 2019-09-08 | 2014-06-13 |  | ضعف كفاءة المقاول الفنية |  | 46.6699 | 24.7107 | منجز | Yes
2100099621 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 23599992 | 1179999.6 | 9602215.82 | 0 | 1116005202 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 86.57 | 100 | 2013-07-07 | 2018-09-17 | 2018-09-18 | 2018-09-18 | 2018-09-17 |  |  |  | 44.4378 | 24.5214 | منجز | Yes
2100108290 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البحرية | تشييد | ذات اولوية متوسطة | 25633689 | 1281684.45 | 19762139 | 19762139 | 1010033701 | لا | 0 | 180809046602 | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-01-03 | 2017-10-30 | 2022-07-31 | 2022-07-31 |  |  |  |  | 39.1553 | 21.5727 | Failed | No
2100100575 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3580700 | 179035 | 41370 | 0 | 1010240630 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-10-23 | 2015-01-16 | 2021-06-23 | 2021-06-23 | 2015-01-16 |  | ضعف كفاءة المقاول الفنية |  | 42.9666 | 23.813 | منجز | Yes
2100065332 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 6714200 | 335710 | 941115.2 | 0 | 1185000614 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 39.6 | 100 | 2015-01-13 | 2016-09-04 | 2021-06-16 | 2021-06-16 |  |  | ضعف كفاءة المقاول الفنية |  | 44.8949 | 20.4485 | مسحوب | Yes
2100023074 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 5919590 | 295979.5 | 4876056.2 | 0 | 1010015152 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-10-07 | 2015-09-27 | 2019-08-26 | 2019-08-26 | 2015-09-27 |  | ضعف كفاءة المقاول الفنية |  | 46.6768 | 24.7119 | منجز | Yes
2100018314 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 7866120.4 | 393306.02 | 6539628.4 | 0 | 1010197183 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 93 | 100 | 2015-05-21 | 2016-11-11 | 2019-12-03 | 2019-12-03 | 2016-11-11 |  | ضعف كفاءة المقاول الفنية |  | 46.672 | 24.6988 | منجز | Yes
2100091744 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 6638245.8 | 331912.29 | 3415556.88 | 0 | 1010246223 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-12-03 | 2016-02-26 | 2019-09-18 | 2019-09-18 | 2016-02-26 |  | ضعف كفاءة المقاول الفنية |  | 46.0967 | 25.1227 | منجز | Yes
2200233446 | وزارة الصحة | تصميم وتشييد | ذات اولوية عالية | 1830532.92 | 91526.646 | 0 | 0 | 2051033753 | لا | 0 | 220401024275 | جاري | التكلفة المفوترة | 23 | 23 | 2022-08-03 | 2023-05-02 | 2023-05-02 | 2023-05-02 |  |  |  |  | 50.1006 | 26.4124 | منتظم | No
2100059334 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2232768.59 | 111638.4295 | 1792094.66 | 1792094.66 | 1131021347 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2018-10-01 | 2019-08-22 | 2019-12-19 | 2019-12-19 | 2019-08-22 |  |  |  | 43.9544 | 26.3504 | منجز | No
2100012250 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1382100 | 69105 | 1113077.7 | 0 | 1116007586 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 83 | 100 | 2014-08-10 | 2016-02-01 | 2022-10-10 | 2022-10-10 | 2016-02-01 |  | ضعف كفاءة المقاول الفنية |  | 45.3463 | 26.5018 | منجز | Yes
2100071562 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البحرية | تشييد | ذات اولوية متوسطة | 23576918 | 1178845.9 | 19088373 | 19088373 | 1010188480 | لا | 0 | 180709023246 | جاري | الكميات التي تم تركيبها | 95 | 100 | 2014-10-20 | 2016-06-10 | 2021-11-30 | 2021-11-30 |  |  |  |  | 49.6261 | 26.987 | Failed | No
2100087953 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البحرية | تشييد | ذات اولوية متوسطة | 69286635 | 3464331.75 | 50650550 | 50650550 | 1010033701 | لا | 0 | 180809039480 | جاري | الكميات التي تم تركيبها | 87 | 100 | 2013-01-09 | 2015-12-30 | 2021-11-30 | 2021-11-30 |  |  |  |  | 39.2402 | 21.5514 | Failed | No
2100031253 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2410000 | 120500 | 1609500 | 0 | 1113000219 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-10-30 | 2018-12-09 | 2018-12-09 | 2018-12-09 | 2018-12-09 |  |  |  | 46.6823 | 24.7144 | منجز | Yes
2100091615 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 572560 | 28628 | 0 | 0 | 1010381102 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 1 | 2019-04-18 | 2020-04-01 | 2021-07-01 | 2021-07-01 | 2020-04-01 |  | ضعف كفاءة المقاول الفنية |  | 46.8108 | 23.4112 | منجز | No
2100108673 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البحرية | تشييد | ذات اولوية متوسطة | 23122992 | 1156149.6 | 9975962.85 | 9975962.85 | 1010226597 | لا | 0 | 190801070411 | جاري | الكميات التي تم تركيبها | 63 | 100 | 2019-02-07 | 2020-02-12 | 2021-12-31 | 2021-12-31 |  |  |  | مخطط لسحبه وإعادة ترسيته | 39.1821 | 21.4696 | Failed | No
2100004686 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البحرية | تشييد | ذات اولوية متوسطة | 7862036 | 393101.8 | 5320625.25 | 5320625.25 | 4030144975 | لا | 0 | 180701035898 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2017-11-30 | 2020-01-19 | 2022-04-24 | 2022-04-24 | 2020-01-19 |  |  |  | 39.1587 | 21.5891 | منجز | No
2100063151 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 6789432 | 339471.6 | 3556325 | 0 | 1010195827 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 100 | 2015-01-10 | 2017-12-25 | 2020-11-12 | 2020-11-12 | 2017-12-25 |  | ضعف كفاءة المقاول الفنية |  | 46.6843 | 24.6988 | منجز | Yes
2100022201 | أمانة / الرياض | دراسة الجدوى | ذات اولوية عالية | 9424260 | 471213 | 8189211 | 0 | 1010363372 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-02-23 | 2018-03-15 | 2018-03-15 | 2018-03-15 | 2018-03-15 |  | اخرى |  | 46.7563 | 24.6805 | منجز | Yes
2100100472 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 9855685 | 492784.25 | 3713490 | 0 | 1010006004 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 73 | 100 | 2015-10-14 | 2017-08-04 | 2023-09-13 | 2023-09-13 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 45.2514 | 25.2321 | Failed | Yes
2100101124 | وزارة الصحة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 2969243 | 148462.15 | 1414970 | 610610 | 4653000386 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2020-01-04 | 2020-06-28 | 2022-03-31 | 2022-03-31 | 2020-06-28 |  | تأخرصرف المستحقات المالية |  | 39.533 | 24.4143 | منجز | No
2100045555 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 7771520 | 388576 | 4487312.32 | 0 | 1113000219 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 99 | 100 | 2015-08-18 | 2017-08-07 | 2019-10-27 | 2019-10-27 | 2017-08-07 |  | ضعف كفاءة المقاول الفنية |  | 46.707 | 24.7144 | منجز | Yes
2100078805 | أمانة / الرياض | دراسة الجدوى | ذات اولوية متوسطة | 9694000 | 484700 | 9039600 | 0 | 1010367378 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-02-08 | 2015-07-28 | 2015-07-28 | 2015-07-28 | 2015-07-28 |  | اخرى |  |  |  | منجز | Yes
2100061073 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية وعاجلة | 1537155771 | 76857788.55 | 871499463 | 871499463 | 4030068284 | لا | 0 |  | ايقاف جزئي | منهجية القيمة المكتسبة | 75 | 100 | 2011-03-15 | 2013-04-03 | 2023-11-30 | 2023-11-30 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  |  |  | Failed | No
2100064772 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1256430 | 62821.5 | 0 | 0 | 1010043654 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 99 | 100 | 2019-10-15 | 2020-10-10 | 2020-10-11 | 2020-10-11 | 2020-10-10 |  | اخرى |  | 45.5531 | 25.6183 | منجز | No
2100095675 | وزارة الصحة / المدينة المنورة | تشييد | ذات اولوية منخفضة | 7548450 | 377422.5 | 5936002 | 5274250 | 4650040868 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 75 | 100 | 2018-07-17 | 2019-05-08 | 2022-05-31 | 2022-05-31 |  |  | تأخرصرف المستحقات المالية |  | 39.5615 | 24.4957 | Failed | No
2100105825 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية وعاجلة | 1368527457 | 68426372.85 | 914859769 | 914859769 | 4030068284 | لا | 0 |  | ايقاف جزئي | منهجية القيمة المكتسبة | 96 | 99 | 2011-01-15 | 2013-04-01 | 2023-11-30 | 2023-11-30 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | متأخر | No
2100007070 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2442583 | 122129.15 | 409546 | 409546 | 1010168143 | لا | 0 |  | مسحوب | التكلفة المفوترة | 45 | 100 | 2009-03-16 | 2010-06-02 | 2023-07-26 | 2023-07-26 |  |  | ضعف كفاءة المقاول الفنية |  | 42.9095 | 23.8972 | مسحوب | No
2100080706 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 7135373 | 356768.65 | 6184541.8 | 0 | 1010127437 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 86 | 100 | 2015-08-17 | 2017-02-07 | 2021-11-05 | 2021-11-05 | 2017-02-07 |  | ضعف كفاءة المقاول الفنية |  | 46.6692 | 24.7025 | منجز | Yes
2100032734 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 7412135 | 370606.75 | 40650 | 0 | 1122001367 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 2 | 100 | 2015-10-17 | 2016-10-11 | 2016-10-11 | 2016-10-11 |  |  | ضعف كفاءة المقاول الفنية |  | 45.3558 | 25.9038 | مسحوب | Yes
2100049490 | أمانة / جازان | تشييد | لم تعد تحتاجها الجهة | 11884345 | 594217.25 | 0 | 0 | 5904006379 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 0 | 100 | 2014-06-10 | 2015-06-05 | 2015-06-05 | 2015-06-05 |  |  | اخرى |  | 42.9626 | 16.5293 | مسحوب | No
2100044203 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 7521215 | 376060.75 | 1578884.5 | 0 | 1116003362 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-09-03 | 2015-06-25 | 2020-09-05 | 2020-09-05 | 2015-06-25 |  | ضعف كفاءة المقاول الفنية |  | 46.6692 | 24.6988 | منجز | Yes
2100013683 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1729449 | 86472.45 | 421117 | 0 | 1011015729 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 64 | 2019-01-30 | 2020-04-24 | 2020-04-24 | 2020-04-24 | 2020-04-24 |  | ضعف كفاءة المقاول الفنية |  | 46.1297 | 25.1125 | منجز | Yes
2100039723 | أمانة / جازان | تشييد | ذات اولوية عالية | 6992435 | 349621.75 | 5525913.53 | 5525913.53 | 5911006877 | لا | 0 | 180809060500 | منجز – استلام ابتدائي | اخرى | 82 | 100 | 2009-06-02 | 2010-05-18 | 2019-11-24 | 2019-11-24 | 2010-05-18 |  | اخرى |  | 42.5696 | 16.8868 | منجز | No
2100028954 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 6914680 | 345734 | 6565960.72 | 0 | 1113000219 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 95 | 100 | 2015-05-11 | 2017-04-19 | 2017-04-19 | 2017-04-19 | 2017-04-19 |  |  |  | 46.6864 | 24.7044 | منجز | Yes
2100057400 | أمانة / الرياض | دراسة الجدوى | ذات اولوية متوسطة | 600000 | 30000 | 210000 | 0 | 1010372072 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-12-30 | 2014-05-29 | 2014-05-29 | 2014-05-29 | 2014-05-29 |  | ضعف كفاءة المقاول الفنية |  |  |  | منجز | Yes
2100041786 | جامعة الأمير سطام بن عبدالعزيز | تشييد | ذات اولوية عالية | 116303015 | 5815150.75 | 13962906 | 13962906 | 2050022550 | نعم | 13771070 |  | مسحوب | مدفوعات ساعات العمل | 12 | 30 | 2013-09-23 | 2016-09-07 | 2024-01-01 | 2024-01-01 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 44.7813 | 20.4716 | مسحوب | No
2100081303 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 31972035 | 1598601.75 | 12730421.6 | 0 | 1010203405 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 87.69 | 100 | 2014-09-13 | 2016-09-02 | 2020-04-23 | 2020-04-23 | 2016-09-02 |  | ضعف كفاءة المقاول الفنية |  | 44.4239 | 24.5165 | منجز | Yes
2100029945 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4600975 | 230048.75 | 4370922 | 0 | 1113000219 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 95 | 100 | 2014-09-22 | 2015-11-16 | 2019-11-24 | 2019-11-24 | 2015-11-16 |  | ضعف كفاءة المقاول الفنية |  | 46.6768 | 24.7256 | منجز | Yes
2100066054 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 755400 | 37770 | 42067 | 0 | 1010240630 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 1 | 100 | 2015-07-07 | 2016-06-21 | 2019-03-06 | 2019-03-06 |  |  | ضعف كفاءة المقاول الفنية |  | 45.35 | 26.4969 | مسحوب | Yes
2100006112 | الجمارك السعودية | تصميم | ذات اولوية عالية | 12000000 | 600000 | 8748000 | 8748000 | 1010348048 | لا | 0 | 200701131192 | جاري | تكلفة العمل المنجز | 93 | 100 | 2020-01-12 | 2020-07-12 | 2021-03-09 | 2021-03-09 |  |  | اخرى |  | 51.5664 | 24.1388 | Failed | No
2100008761 | جامعة الأمير سطام بن عبدالعزيز | تشييد | ذات اولوية عالية | 134106503.51 | 6705325.1755 | 113178100.22 | 108055574 | 1010062177 | لا | 0 | 181109372537 | ايقاف كلي | تكلفة العمل المنجز | 87 | 98 | 2013-04-17 | 2016-04-01 | 2023-06-13 | 2023-06-13 |  |  | اخرى |  | 46.8944 | 23.5058 | Failed | No
2100003640 | جامعة الأمير سطام بن عبدالعزيز | تشييد | ذات اولوية عالية | 1588912.5 | 79445.625 | 1410649 | 1410649 | 1010259071 | لا | 0 | 190701201101 | جاري | تكلفة العمل المنجز | 95 | 100 | 2019-08-28 | 2020-02-24 | 2022-06-04 | 2022-06-04 |  |  | اخرى |  | 47.2701 | 24.1468 | Failed | No
2100005515 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البحرية | تشييد | ذات اولوية متوسطة | 8146203 | 407310.15 | 0 | 0 | 1010226597 | لا | 0 | 181201480961 | مسحوب | الكميات التي تم تركيبها | 3 | 100 | 2018-12-13 | 2019-11-23 | 2021-09-21 | 2021-09-21 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5862 | 16.8221 | مسحوب | No
2100198214 | رئاسة أمن الدولة / القيادة العامة لطيران الأمن | تشييد | ذات اولوية عالية وعاجلة | 22462660.05 | 1123133.0025 | 21552616.8 | 21552616.8 | 1010154882 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-01-03 | 2019-03-06 | 2022-08-20 | 2022-08-20 | 2019-03-06 |  |  |  | 39.2137 | 21.5227 | منجز | No
2100108776 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2940491 | 147024.55 | 1420763 | 1420763 | 1015000109 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-12-02 | 2016-01-06 | 2020-11-23 | 2020-11-23 | 2016-01-06 |  | ضعف كفاءة المقاول الفنية |  | 46.7271 | 22.2863 | منجز | No
2100103191 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 31622641.73 | 1581132.0865 | 17523766.541 | 17523766.541 | 1010030949 | لا | 0 |  | مسحوب | التكلفة المفوترة | 73 | 100 | 2013-06-22 | 2015-06-12 | 2023-02-28 | 2023-02-28 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 44.8241 | 26.3046 | مسحوب | No
2100106046 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية وعاجلة | 1338262007 | 66913100.35 | 1059604597 | 1059604597 | 4030068284 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2011-01-03 | 2013-02-18 | 2015-06-18 | 2015-06-18 | 2013-02-18 |  | لا يوجد تأخير |  |  |  | منجز | No
2100033390 | أمانة / جازان | تشييد | ذات اولوية عالية | 948499 | 47424.95 | 0 | 0 | 4030065096 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 0 | 100 | 2015-02-20 | 2016-02-15 | 2020-02-02 | 2020-02-02 |  |  | اخرى |  | 42.266 | 17.7333 | مسحوب | No
2200233575 | وزارة الصحة | توريد وتركيب | ذات اولوية عالية | 332350 | 16617.5 | 0 | 0 | 1010177961 | لا | 0 | 220401074905 | جاري | التكلفة المفوترة | 99 | 99 | 2022-04-14 | 2022-10-16 | 2022-10-16 | 2022-10-16 |  |  |  | أخرى | 50.1007 | 26.4129 | Failed | No
2100096165 | وزارة الداخلية / ديوان وزارة الداخلية | إشراف | ذات اولوية عالية وعاجلة | 390293790.6 | 19514689.53 | 381021679 | 370259974 | 4030068284 | لا | 0 |  | جاري | التكلفة المفوترة | 91 | 91 | 2010-09-10 | 2013-02-10 | 2022-12-31 | 2022-12-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  |  |  | خدمات عامة | No
2100105184 | جامعة الأمير سطام بن عبدالعزيز | تشييد | ذات اولوية عالية | 73350948.45 | 3667547.4225 | 66272720.18 | 52884280 | 1010012687 | لا | 0 | 200209140114 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 98 | 100 | 2011-05-17 | 2014-05-01 | 2023-01-01 | 2023-01-01 | 2014-05-01 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 47.3078 | 24.1522 | منجز | No
2100019095 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البحرية | تشييد | ذات اولوية متوسطة | 31330000 | 1566500 | 25742332 | 25742332 | 5950011723 | لا | 0 | 181109291786 | جاري | الكميات التي تم تركيبها | 88 | 100 | 2015-04-01 | 2017-11-30 | 2022-03-31 | 2022-03-31 |  |  |  | تم إنذار المقاول كتابيا | 39.3266 | 21.4779 | Failed | No
2100097263 | وزارة الحرس الوطني / الشؤون الصحية | تشييد | ذات اولوية عالية | 285990798 | 14299539.9 | 19815964 | 19815964 | 4030068284 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 11 | 100 | 2014-03-25 | 2016-03-13 | 2016-03-13 | 2016-03-13 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 46.8556 | 24.7473 | Failed | No
2100041860 | جامعة الأمير سطام بن عبدالعزيز | تشييد | ذات اولوية عالية | 89084161.05 | 4454208.0525 | 1026828.47 | 1026828.47 | 1010094890 | نعم | 52208429 | 181009136671 | جاري | تكلفة العمل المنجز | 4 | 25 | 2022-02-09 | 2024-01-30 | 2024-01-30 | 2024-01-30 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 47.3078 | 24.1522 | متأخر | No
2100079133 | جامعة الأمير سطام بن عبدالعزيز | تشييد | ذات اولوية عالية وعاجلة | 131689707.31 | 6584485.3655 | 84873053 | 84873053 | 1010245854 | لا | 0 | 180709036286 | مسحوب | تكلفة العمل المنجز | 65 | 100 | 2014-04-03 | 2017-09-14 | 2024-01-01 | 2024-01-01 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 47.3078 | 24.1522 | مسحوب | No
2100027333 | جامعة الأمير سطام بن عبدالعزيز | تشييد | ذات اولوية عالية | 56542301.62 | 2827115.081 | 11205491.56 | 10149633 | 1010011949 | لا | 0 | 200209137526 | جاري | تكلفة العمل المنجز | 22 | 81 | 2014-10-14 | 2016-10-03 | 2023-05-26 | 2023-05-26 |  |  | تأخرصرف المستحقات المالية |  | 47.3078 | 24.1522 | Failed | No
2100078621 | وزارة الداخلية / ديوان وزارة الداخلية | إشراف | ذات اولوية عالية وعاجلة | 890381880 | 44519094 | 696821651.8 | 696821651.8 | 1010081126 | لا | 0 |  | ايقاف كلي | مدفوعات ساعات العمل | 80 | 100 | 2013-05-13 | 2016-12-05 | 2018-06-30 | 2018-06-30 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  |  |  | Failed | No
2100000571 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البحرية | تشييد | ذات اولوية متوسطة | 54574988 | 2728749.4 | 45167183 | 45167183 | 1010033701 | لا | 0 | 180809037772 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 90 | 100 | 2014-11-08 | 2017-12-01 | 2022-02-08 | 2022-02-08 | 2017-12-01 |  |  | تم إنذار المقاول كتابيا | 49.5899 | 26.9699 | منجز | No
2100189895 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية وعاجلة | 12028677974 | 601433898.7 | 0 | 0 | 1010081126 | لا | 0 |  | ايقاف جزئي | الكميات التي تم تركيبها | 2 | 100 | 2015-05-14 | 2017-02-16 | 2017-02-16 | 2017-02-16 |  |  | اخرى |  | 46.7195 | 24.8046 | Failed | No
2100104193 | وزارة الحرس الوطني / الشؤون الصحية | تشييد | ذات اولوية عالية | 3706569.72 | 185328.486 | 3180385.7 | 3180385.7 | 1010306778 | لا | 0 | 190901154414 | ايقاف كلي | الكميات التي تم تركيبها | 86 | 100 | 2019-01-27 | 2020-04-21 | 2023-01-05 | 2023-01-05 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 46.8565 | 24.7502 | Failed | No
2100077206 | جامعة الأمير سطام بن عبدالعزيز | تشييد | ذات اولوية عالية | 5477010 | 273850.5 | 5401834 | 5401834 | 1010332416 | لا | 0 | 200101054259 | جاري الاستلام الإبتدائي | مدفوعات ساعات العمل | 100 | 100 | 2020-01-25 | 2022-01-24 | 2022-02-08 | 2022-02-08 |  |  | لا يوجد تأخير |  | 47.2706 | 24.1474 | Failed | No
2100016203 | وزارة الداخلية / ديوان وزارة الداخلية | إشراف | ذات اولوية عالية وعاجلة | 1016205193.87 | 50810259.6935 | 889675645.38 | 878847912.73 | 1010387565 | لا | 0 |  | جاري | التكلفة المفوترة | 88 | 88 | 2013-08-14 | 2016-07-29 | 2025-11-30 | 2025-11-30 |  |  | عدم وجود مبالغ في البنود تغطي الأعمال المرصودة |  | 46.53 | 24.9023 | خدمات عامة | No
2100103320 | جامعة الأمير سطام بن عبدالعزيز | تشييد | ذات اولوية عالية | 10773166.8 | 538658.34 | 8908981 | 8908981 | 1010032384 | لا | 0 | 180709018369 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 99 | 99 | 2018-07-01 | 2019-06-30 | 2022-02-26 | 2022-02-26 |  |  | اخرى |  | 45.5586 | 20.4465 | متأخر | No
2100019390 | جامعة الأمير سطام بن عبدالعزيز | تشييد | ذات اولوية عالية | 31507115.69 | 1575355.7845 | 25951703 | 23056817 | 2066001761 | لا | 0 | 181109342450 | مسحوب | تكلفة العمل المنجز | 93 | 100 | 2013-09-08 | 2014-09-03 | 2022-07-03 | 2022-07-03 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 47.3078 | 24.1522 | مسحوب | No
2100019935 | رئاسة أمن الدولة / القيادة العامة لطيران الأمن | تشييد | ذات اولوية عالية | 11669656.51 | 583482.8255 | 11669656.51 | 7226154.05 | 1010226539 | لا | 0 |  | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-11-28 | 2021-05-28 | 2022-12-01 | 2022-12-01 |  |  | لا يوجد تأخير |  | 46.7436 | 24.7496 | Failed | No
2100017194 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 12615712.52 | 630785.626 | 4068374.64 | 4068374.64 | 2943000000 | لا | 0 |  | جاري | التكلفة المفوترة | 43 | 100 | 2014-03-26 | 2016-06-13 | 2022-08-29 | 2022-08-29 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7271 | 22.2863 | Failed | No
2100105873 | وزارة الحرس الوطني / الشؤون الصحية | تشييد | ذات اولوية عالية | 19638474 | 981923.7 | 12669981.4 | 11888938.53 | 1010251358 | لا | 0 | 180909075665 | جاري | الكميات التي تم تركيبها | 68 | 100 | 2011-04-12 | 2013-06-01 | 2023-04-30 | 2023-04-30 |  |  | ضعف كفاءة المقاول الفنية |  | 46.5895 | 24.4748 | Failed | No
2100007210 | جامعة الأمير سطام بن عبدالعزيز | تشييد | ذات اولوية عالية | 43957898 | 2197894.9 | 12969773.11 | 11827119.5 | 1010184991 | لا | 0 | 190401071746 | جاري | الكميات التي تم تركيبها | 52 | 60 | 2019-08-29 | 2021-08-18 | 2023-02-09 | 2023-02-09 |  |  | تأخرصرف المستحقات المالية |  | 47.2721 | 24.1444 | متأخر | No
2100083661 | وزارة الصحة / تجمع الشرقية | تشييد | ذات اولوية عالية | 112000000 | 5600000 | 94000000 | 71600000 | 2050007518 | لا | 0 | 181009133090 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 95 | 100 | 2015-01-02 | 2017-01-31 | 2022-07-15 | 2022-07-15 |  |  | تأخرصرف المستحقات المالية |  | 50.0237 | 26.5089 | متأخر | No
2100035755 | وزارة الداخلية / المديرية العامة لحرس الحدود | تشييد | ذات اولوية عالية | 35590781.2 | 1779539.06 | 24165446 | 24165446 | 2251003982 | لا | 0 | 190309071400 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 86 | 100 | 2013-09-12 | 2017-11-23 | 2017-11-23 | 2017-11-23 |  |  | ضعف كفاءة المقاول الفنية |  | 50.1013 | 26.4524 | Failed | No
2100046012 | وزارة الصحة / تجمع الشرقية | تحديث وتوريد | ذات اولوية عالية | 1352253 | 67612.65 | 974963 | 974963 | 2053029899 | لا | 0 | 191001043932 | جاري | تكلفة العمل المنجز | 92 | 100 | 2019-07-05 | 2020-05-07 | 2022-03-15 | 2022-03-15 |  |  | تصاريح أعمال التنفيذ |  | 50.1026 | 26.408 | Failed | No
2100009542 | الجمارك السعودية | تشييد | ذات اولوية عالية | 320992629 | 16049631.45 | 137569797.57 | 137569797.57 | 1010254468 | لا | 0 | 181009138850 | جاري | تكلفة العمل المنجز | 49 | 100 | 2015-02-17 | 2017-08-16 | 2022-12-31 | 2022-12-31 |  |  | أوامر تغيير |  | 37.1632 | 31.4478 | Failed | No
2100089224 | جامعة أم القرى | تشييد | ذات اولوية عالية | 69991000 | 3499550 | 56692400.72 | 56692400.72 | 1010152417 | لا | 0 | 181109245957 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2008-01-07 | 2010-12-04 | 2021-12-30 | 2021-12-30 | 2010-12-04 |  |  |  | 39.9357 | 21.3275 | منجز | No
2100205284 | وزارة الصحة / تجمع الشرقية | تشييد | ذات اولوية عالية | 982550.8 | 49127.54 | 798803.7 | 798803.7 | 2065003779 | لا | 0 | 201201094727 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2021-02-21 | 2021-04-21 | 2021-12-28 | 2021-12-28 | 2021-04-21 |  |  |  | 48.8336 | 25.9596 | منجز | No
2100002041 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البحرية | تشييد | ذات اولوية متوسطة | 5249941 | 262497.05 | 3444235 | 3444235 | 1010142413 | لا | 0 |  | مسحوب | اخرى | 85 | 100 | 2010-06-08 | 2011-07-31 | 2021-09-21 | 2021-09-21 |  |  |  | مخطط لسحبه وإعادة ترسيته | 39.2384 | 21.4903 | مسحوب | No
2100205240 | وزارة الصحة / تجمع الشرقية | تشييد | ذات اولوية عالية | 1749483 | 87474.15 | 0 | 0 | 1010162957 | لا | 0 | 200301115088 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-07-09 | 2020-10-05 | 2020-07-09 | 2020-07-09 | 2020-10-05 |  |  |  | 49.9261 | 26.66 | منجز | No
2100014092 | وزارة الصحة / تجمع الشرقية | توريد | ذات اولوية عالية | 2384730 | 119236.5 | 2300000 | 2300000 | 1010168516 | لا | 0 | 190801013256 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-11-24 | 2020-05-19 | 2020-05-19 | 2020-05-19 | 2020-05-19 |  | سوء التخطيط الاولي للمشروع |  | 49.6597 | 26.9944 | منجز | No
2100048020 | وزارة الصحة / تجمع الشرقية | تشييد | ذات اولوية عالية | 8557205 | 427860.25 | 6870185 | 6870185 | 1010018153 | لا | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 95 | 100 | 2012-05-04 | 2013-02-24 | 2021-12-31 | 2021-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 50.1021 | 26.4086 | Failed | No
2100101986 | وزارة الصحة / تجمع الشرقية | تشييد | ذات اولوية عالية | 25835028 | 1291751.4 | 25835028 | 25835028 | 2050038009 | لا | 0 | 404942800266 | جاري | تكلفة العمل المنجز | 50 | 60 | 2019-04-21 | 2021-04-20 | 2021-08-02 | 2021-08-02 |  |  | ضعف كفاءة المقاول الفنية |  | 48.4655 | 27.4725 | Failed | No
2100004583 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البحرية | تشييد | ذات اولوية متوسطة | 28450645 | 1422532.25 | 24318537 | 24318537 | 2055002705 | لا | 0 | 180801061869 | جاري | الكميات التي تم تركيبها | 89 | 100 | 2019-03-02 | 2022-01-14 | 2022-01-14 | 2022-01-14 |  |  |  |  | 49.5679 | 26.9558 | Failed | No
2100025325 | وزارة الصحة / تجمع الشرقية | تشييد | ذات اولوية عالية وعاجلة | 29291164 | 1464558.2 | 2900000 | 2900000 | 2051040465 | نعم | 2800000 |  | مسحوب | الكميات التي تم تركيبها | 15 | 100 | 2013-09-23 | 2015-09-23 | 2024-07-18 | 2024-07-18 |  |  | ضعف كفاءة المقاول الفنية |  | 50.0875 | 26.4188 | مسحوب | No
2100072096 | وزارة الصحة / تجمع الشرقية | توريد وتركيب | ذات اولوية عالية وعاجلة | 1798482 | 89924.1 | 0 | 0 | 1010228824 | لا | 0 | 200101051793 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-12-17 | 2020-03-14 | 2020-03-14 | 2020-03-14 | 2020-03-14 |  | اخرى |  | 48.4719 | 28.42 | منجز | No
2100102491 | الجمارك السعودية | تشييد | ذات اولوية عالية | 380461904 | 19023095.2 | 322914129.73 | 322914129.73 | 1010430272 | لا | 0 | 181109272530 | جاري | مدفوعات ساعات العمل | 91 | 100 | 2018-06-04 | 2023-06-03 | 2023-06-03 | 2023-06-03 |  |  | اخرى |  | 46.6824 | 24.6965 | متأخر | No
2100076952 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 739510 | 36975.5 | 739510 | 739510 | 7006824705 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-12-29 | 2019-12-24 | 2019-12-24 | 2019-12-24 | 2019-12-24 |  |  |  | 41.5167 | 19.5689 | منجز | No
2100012191 | أمانة / الباحة | تشييد | ذات اولوية عالية وعاجلة | 7700059 | 385002.95 | 7700059 | 6930053.1 | 4030159820 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-03-31 | 2022-06-14 | 2022-12-30 | 2022-12-30 | 2022-06-14 |  | ضعف كفاءة المقاول الفنية |  | 41.5243 | 19.588 | منجز | No
2100072752 | أمانة / جازان | تشييد | ذات اولوية عالية | 5495900 | 274795 | 4214784 | 4214784 | 1010177200 | لا | 0 | 200101065763 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-09-24 | 2021-09-13 | 2021-12-21 | 2021-12-21 | 2021-09-13 |  | ضعف كفاءة المقاول الفنية |  | 42.2681 | 17.7328 | منجز | No
2100052216 | أمانة / جازان | تشييد | ذات اولوية عالية | 121044970.64 | 6052248.532 | 93795117 | 93795117 | 5900008127 | لا | 0 |  | جاري | تكلفة العمل المنجز | 90 | 95 | 2015-09-01 | 2021-11-18 | 2021-12-18 | 2021-12-18 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.561 | 16.8787 | متأخر | No
2100093251 | أمانة / جازان | ترميم | ذات اولوية متوسطة | 3399984 | 169999.2 | 3399984 | 3399984 | 5900018330 | لا | 0 | 180709031552 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-02-18 | 2020-02-20 | 2021-09-15 | 2021-09-15 | 2020-02-20 |  | اخرى |  | 42.5792 | 16.9948 | منجز | No
2100055580 | هيئة الهلال الأحمر السعودي | تشييد | ذات اولوية عالية | 2007459.54 | 100372.977 | 747365.16 | 747365.16 | 1010420294 | لا | 0 | 190201026386 | مسحوب | الكميات التي تم تركيبها | 33 | 100 | 2017-09-20 | 2018-07-20 | 2018-09-15 | 2018-09-15 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 46.7745 | 24.6239 | مسحوب | No
2100195661 | جامعة أم القرى | تشييد | ذات اولوية عالية | 15578115 | 778905.75 | 1129206.67 | 1129206.67 | 1132002783 | لا | 0 | 190901200566 | مسحوب | تكلفة العمل المنجز | 7 | 100 | 2019-08-25 | 2020-08-24 | 2023-12-11 | 2023-12-11 |  |  | ضعف كفاءة المقاول الفنية | مخطط لإعادة طرحه | 39.9472 | 21.3289 | مسحوب | No
2100082622 | أمانة / جازان | تشييد | ذات اولوية عالية | 784730 | 39236.5 | 784730 | 784730 | 5855060253 | لا | 0 | 181001159558 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-09-02 | 2019-08-28 | 2019-08-22 | 2019-08-22 | 2019-08-28 |  | اخرى |  | 42.513 | 17.1465 | منجز | No
2100017220 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البحرية | تشييد | ذات اولوية متوسطة | 8962233.86 | 448111.693 | 8962233 | 8962233 | 1010028451 | لا | 0 | 200709040701 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-06-27 | 2020-02-18 | 2022-01-31 | 2022-01-31 | 2020-02-18 |  |  |  | 42.5858 | 16.9032 | منجز | No
2100090193 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2669551.2 | 133477.56 | 252534 | 252534 | 3350009773 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 35 | 100 | 2018-12-09 | 2019-12-09 | 2020-09-08 | 2020-09-08 |  |  |  |  | 43.9544 | 26.3504 | مسحوب | No
2100066824 | أمانة / جازان | تشييد | ذات اولوية عالية | 4253650 | 212682.5 | 2023215 | 594600 | 5850028435 | لا | 0 | 181001159672 | جاري | الكميات التي تم تركيبها | 67 | 100 | 2018-11-07 | 2020-10-27 | 2021-02-10 | 2021-02-10 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5772 | 16.8695 | Failed | No
2100015444 | جامعة أم القرى | تشييد | ذات اولوية متوسطة | 58779764 | 2938988.2 | 52424617.92 | 52424617.92 | 4030133347 | لا | 0 | 181209499155 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2013-06-15 | 2015-05-23 | 2022-12-30 | 2022-12-30 | 2015-05-23 |  |  |  | 39.7209 | 21.6601 | منجز | No
2100101231 | هيئة الهلال الأحمر السعودي | تشييد | ذات اولوية عالية | 1271672 | 63583.6 | 327133.17 | 327133.17 | 1010175017 | لا | 0 | 181209447052 | مسحوب | الكميات التي تم تركيبها | 30 | 100 | 2017-08-20 | 2018-08-20 | 2020-03-09 | 2020-03-09 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.4368 | 19.7523 | مسحوب | No
2100040902 | أمانة / جازان | دراسة الجدوى | ذات اولوية متوسطة | 3998778 | 199938.9 | 3998778 | 3998778 | 5860008190 | لا | 0 | 191101275883 | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2019-03-12 | 2020-03-06 | 2021-02-03 | 2021-02-03 | 2020-03-06 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.0293 | 17.712 | منجز | No
2100102793 | أمانة / جازان | دراسة الجدوى | ذات اولوية متوسطة | 1056000 | 52800 | 822192.8 | 822192.8 | 5906012815 | لا | 0 | 180701020182 | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2018-09-09 | 2020-08-29 | 2020-11-11 | 2020-11-11 | 2020-08-29 |  | ضعف كفاءة المقاول الفنية |  | 42.8366 | 16.968 | منجز | No
2100077965 | هيئة الهلال الأحمر السعودي | تشييد | ذات اولوية عالية | 4112796.75 | 205639.8375 | 4081188.73 | 1800021.13 | 5858023576 | لا | 0 | 190401000256 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-05-09 | 2020-05-03 | 2020-11-11 | 2020-11-11 | 2020-05-03 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.6734 | 18.3235 | منجز | No
2100008400 | أمانة / جازان | تشييد | ذات اولوية عالية وعاجلة | 10672990.32 | 533649.516 | 6699518.79 | 6699518.79 | 5950008178 | لا | 0 | 180809060069 | مسحوب | الكميات التي تم تركيبها | 75 | 100 | 2011-12-10 | 2012-11-24 | 2021-08-05 | 2021-08-05 |  |  | ضعف كفاءة المقاول الفنية |  | 42.6318 | 17.1502 | مسحوب | No
2100010533 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية وعاجلة | 733695144.4 | 36684757.22 | 491786125.19 | 491786125.19 | 1010004739 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2014-10-15 | 2016-10-04 | 2022-04-30 | 2022-04-30 | 2016-10-04 |  | تأخرصرف المستحقات المالية |  | 24.899 | 46.9327 | منجز | No
2100025200 | أمانة / جازان | تشييد | ذات اولوية عالية | 27908275.7 | 1395413.785 | 26308053.74 | 26308053.74 | 5900008127 | لا | 0 | 180809051713 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-04-04 | 2020-03-04 | 2021-09-25 | 2021-09-25 | 2020-03-04 |  | ضعف كفاءة المقاول الفنية |  | 42.6277 | 17.1542 | منجز | No
2100105136 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية وعاجلة | 218717351.83 | 10935867.5915 | 153145835.22 | 153145835.22 | 1010004739 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 99.93 | 100 | 2013-11-12 | 2015-11-01 | 2022-12-31 | 2022-12-31 |  |  | تأخرصرف المستحقات المالية | أخرى | 24.9874 | 46.9158 | منتظم | No
2100010150 | أمانة / جازان | تشييد | لم تعد تحتاجها الجهة | 5961243.23 | 298062.1615 | 5365103.23 | 5365103.23 | 5950008178 | لا | 0 | 180809061240 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 90 | 100 | 2011-10-16 | 2013-04-08 | 2017-05-11 | 2017-05-11 | 2013-04-08 |  | اخرى |  | 42.7568 | 16.499 | منجز | No
2100074465 | جامعة حفر الباطن | تشييد | ذات اولوية عالية وعاجلة | 135870999 | 6793549.95 | 122245610.7 | 122245610 | 2055002293 | لا | 0 | 181109314649 | مسحوب | تكلفة العمل المنجز | 89.97 | 89.97 | 2012-01-18 | 2014-07-18 | 2022-07-01 | 2022-07-01 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 48.4427 | 28.4717 | مسحوب | No
2100027042 | جامعة حفر الباطن | تشييد | ذات اولوية عالية وعاجلة | 12172800 | 608640 | 8302776 | 8302776 | 2511012086 | لا | 0 | 190309099936 | ايقاف كلي | تكلفة العمل المنجز | 67 | 67 | 2016-03-29 | 2017-09-29 | 2022-07-31 | 2022-07-31 |  |  | ضعف كفاءة المقاول الفنية |  | 45.9376 | 28.2387 | Failed | No
2100023041 | جامعة حفر الباطن | تشييد | ذات اولوية عالية وعاجلة | 152903020 | 7645151 | 136507035 | 136507035 | 2050065077 | لا | 0 | 190309099928 | ايقاف كلي | تكلفة العمل المنجز | 90 | 90 | 2012-04-22 | 2015-04-22 | 2022-07-31 | 2022-07-31 |  |  | منازعات قائمة |  | 45.9267 | 28.231 | Failed | No
2100040563 | جامعة حفر الباطن | تحديث وتوريد | ذات اولوية عالية وعاجلة | 6400000 | 320000 | 4160000 | 4160000 | 2050101543 | لا | 0 | 191001093297 | ايقاف كلي | تكلفة العمل المنجز | 65 | 65 | 2019-12-02 | 2020-12-01 | 2022-07-31 | 2022-07-31 |  |  |  |  | 45.9462 | 28.2416 | Failed | No
2100060270 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية وعاجلة | 221567654.71 | 11078382.7355 | 162746149.26 | 162746149.26 | 1010004739 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2014-07-01 | 2016-06-19 | 2021-04-30 | 2021-04-30 | 2016-06-19 |  | تأخرصرف المستحقات المالية |  | 24.884 | 46.9384 | منجز | No
2100030520 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 8297200 | 414860 | 977992.8 | 0 | 1010015152 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 11 | 100 | 2014-08-20 | 2016-04-11 | 2021-06-20 | 2021-06-20 |  |  | تأخرصرف المستحقات المالية |  | 44.4681 | 24.5246 | مسحوب | Yes
2100062812 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 107936780 | 5396839 | 41523 | 0 | 1010202928 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 38 | 100 | 2013-12-09 | 2015-11-29 | 2022-01-10 | 2022-01-10 |  |  | ضعف كفاءة المقاول الفنية |  | 47.326 | 24.1671 | Failed | Yes
2100066091 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 5689556.09 | 284477.8045 | 0 | 0 | 1116005202 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 100 | 2018-04-21 | 2019-07-15 | 2020-10-18 | 2020-10-18 | 2019-07-15 |  | ضعف كفاءة المقاول الفنية |  | 43.8322 | 25.0191 | منجز | No
2100036035 | أمانة / جازان | تشييد | لم تعد تحتاجها الجهة | 836621 | 41831.05 | 616750 | 616750 | 5950008178 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 72 | 100 | 2012-11-27 | 2013-11-11 | 2019-11-15 | 2019-11-15 |  |  | ضعف كفاءة المقاول الفنية |  | 42.7547 | 16.5014 | مسحوب | No
2100081653 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 7997500 | 399875 | 41338 | 0 | 1010242626 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 50 | 100 | 2013-12-29 | 2015-12-19 | 2020-08-08 | 2020-08-08 |  |  | ضعف كفاءة المقاول الفنية |  | 47.2539 | 24.1705 | مسحوب | Yes
2100079192 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 4984306 | 249215.3 | 650393.5 | 650393.5 | 1010216996 | لا | 0 |  | مسحوب | التكلفة المفوترة | 16 | 100 | 2014-03-19 | 2015-03-18 | 2022-12-30 | 2022-12-30 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7271 | 22.2863 | مسحوب | No
2100023085 | وزارة التعليم | تشييد | ذات اولوية عالية | 11663245 | 583162.25 | 7484675 | 4690126.29 | 1131012642 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 95 | 100 | 2015-11-15 | 2017-11-04 | 2021-04-25 | 2021-04-25 | 2017-11-04 |  | ضعف كفاءة المقاول الفنية |  | 43.9544 | 26.3504 | منجز | No
2100194180 | وزارة الحرس الوطني / وكالة الشؤون الفنية | تشييد | ذات اولوية متوسطة | 3931000 | 196550 | 0 | 0 | 1132103578 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 0 | 58 | 2021-04-11 | 2022-04-01 | 2022-04-01 | 2022-04-01 |  |  | ضعف كفاءة المقاول الفنية |  | 43.9808 | 26.3303 | مسحوب | No
2100095281 | هيئة الهلال الأحمر السعودي | تشييد | ذات اولوية عالية | 3211653.8 | 160582.69 | 3074027.09 | 3074027.09 | 1010239020 | لا | 0 | 181109314256 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 96 | 100 | 2018-03-07 | 2019-03-01 | 2021-03-24 | 2021-03-24 | 2019-03-01 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 46.875 | 24.8094 | منجز | No
2100024474 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 949050 | 47452.5 | 854144 | 0 | 1185000614 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 95 | 2014-11-24 | 2015-09-20 | 2019-09-21 | 2019-09-21 | 2015-09-20 |  | ضعف كفاءة المقاول الفنية |  | 45.5638 | 20.4621 | منجز | Yes
2100035722 | أمانة / جازان | تشييد | ذات اولوية عالية وعاجلة | 522000 | 26100 | 522000 | 522000 | 2050017648 | لا | 0 | 181109306400 | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2018-01-07 | 2020-12-22 | 2021-04-29 | 2021-04-29 | 2020-12-22 |  | ضعف كفاءة المقاول الفنية |  | 42.6281 | 17.1506 | منجز | No
2100101474 | هيئة الهلال الأحمر السعودي | تشييد | ذات اولوية عالية | 1413523 | 70676.15 | 377013 | 377013 | 4651002143 | لا | 0 | 190309087308 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 98 | 100 | 2017-08-20 | 2018-07-13 | 2021-12-01 | 2021-12-01 | 2018-07-13 |  | اخرى |  | 39.3062 | 25.0038 | منجز | No
2100033950 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 1499998 | 74999.9 | 1030499 | 1030499 | 4030065096 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 68 | 68 | 2009-03-26 | 2009-12-21 | 2019-02-19 | 2019-02-19 |  |  | اخرى |  | 42.5378 | 17.3725 | مسحوب | No
2100048790 | أمانة / جازان | تشييد | ذات اولوية عالية | 79467500 | 3973375 | 56422105 | 56422105 | 5900007895 | لا | 0 | 180809054341 | جاري | تكلفة العمل المنجز | 82 | 100 | 2012-10-07 | 2014-09-27 | 2021-11-03 | 2021-11-03 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5753 | 16.8826 | Failed | No
2100041300 | أمانة / جازان | دراسة الجدوى | ذات اولوية متوسطة | 79000 | 3950 | 79000 | 79000 | 5801010135 | لا | 0 | 180701016352 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-09-28 | 2019-02-25 | 2019-02-25 | 2019-02-25 | 2019-02-25 |  | اخرى |  |  |  | منجز | No
2100049394 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 10058479.9 | 502923.995 | 6052883.77 | 6052883.77 | 1116004360 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 70 | 100 | 2012-12-09 | 2014-11-29 | 2020-09-18 | 2020-09-18 |  |  | ضعف كفاءة المقاول الفنية |  | 44.4412 | 24.5406 | مسحوب | No
2100017636 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2113330 | 105666.5 | 883248 | 883248 | 1010350150 | لا | 0 |  | جاري | التكلفة المفوترة | 62 | 100 | 2018-07-17 | 2019-03-14 | 2022-07-21 | 2022-07-21 |  |  | ضعف كفاءة المقاول الفنية |  | 45.313 | 24.0763 | Failed | No
2100041705 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 3094809 | 154740.45 | 707239 | 707239 | 1010287891 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 24 | 100 | 2014-03-26 | 2015-09-26 | 2021-12-11 | 2021-12-11 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 44.4412 | 24.5406 | مسحوب | No
2100024032 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 4901686.7 | 245084.335 | 2244229 | 1725970.72 | 1017000942 | لا | 0 |  | جاري | التكلفة المفوترة | 66 | 100 | 2015-08-19 | 2017-02-09 | 2022-02-03 | 2022-02-03 |  |  | ضعف كفاءة المقاول الفنية |  | 45.313 | 24.0763 | Failed | No
2100079310 | وزارة التعليم | تشييد | ذات اولوية عالية | 8758387 | 437919.35 | 0 | 0 | 1010088136 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 16 | 100 | 2013-02-11 | 2015-01-12 | 2015-02-01 | 2015-02-01 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 45.2591 | 25.2379 | مسحوب | No
2100007394 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2100000 | 105000 | 1453400 | 1453400 | 1010216812 | لا | 0 |  | مسحوب | التكلفة المفوترة | 80 | 100 | 2011-09-04 | 2012-11-27 | 2022-08-09 | 2022-08-09 |  |  | ضعف كفاءة المقاول الفنية |  | 44.4412 | 24.5406 | مسحوب | No
2100008735 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1765280 | 88264 | 0 | 0 | 1010305401 | لا | 0 |  | مسحوب | التكلفة المفوترة | 1 | 100 | 2008-07-17 | 2009-09-04 | 2013-01-15 | 2013-01-15 |  |  | ضعف كفاءة المقاول الفنية |  | 44.4412 | 24.5406 | مسحوب | No
2100016590 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 3130000 | 156500 | 1176909.5 | 1176909.5 | 1010318776 | لا | 0 |  | مسحوب | التكلفة المفوترة | 50 | 100 | 2013-11-10 | 2015-05-04 | 2022-04-13 | 2022-04-13 |  |  | ضعف كفاءة المقاول الفنية |  | 44.4412 | 24.5406 | مسحوب | No
2100018104 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 6592222.8 | 329611.14 | 3534224 | 3534224 | 1116004360 | لا | 0 |  | جاري | التكلفة المفوترة | 60 | 100 | 2013-03-29 | 2014-12-19 | 2022-01-12 | 2022-01-12 |  |  | ضعف كفاءة المقاول الفنية |  | 44.4412 | 24.5406 | Failed | No
2100015470 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 802450 | 40122.5 | 0 | 0 | 1010249051 | لا | 0 |  | جاري | التكلفة المفوترة | 98 | 100 | 2019-01-30 | 2019-05-30 | 2020-05-30 | 2020-05-30 |  |  | اخرى |  | 45.2591 | 25.2379 | Failed | No
2100032270 | وزارة الحرس الوطني / الشؤون الصحية | تشييد | ذات اولوية عالية | 47164214.62 | 2358210.731 | 39004412.87 | 37473331.01 | 1010018153 | لا | 0 | 181009122946 | جاري | الكميات التي تم تركيبها | 93 | 100 | 2016-02-22 | 2017-08-14 | 2023-03-29 | 2023-03-29 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5278 | 25.458 | Failed | No
2100039060 | وزارة الحرس الوطني / الشؤون الصحية | تصميم وإشراف | ذات اولوية عالية | 33083249.39 | 1654162.4695 | 29841608.67 | 28059412 | 1010359384 | لا | 0 | 190401016727 | جاري | مدفوعات ساعات العمل | 90.7 | 90.7 | 2019-10-01 | 2021-09-20 | 2023-04-30 | 2023-04-30 |  |  | تغيرات في نطاق المشروع |  | 46.8814 | 24.7519 | منتظم | No
2100066721 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 8311000 | 415550 | 6718392.5 | 6718392.5 | 5855010714 | لا | 0 | 406029901186 | مسحوب | تكلفة العمل المنجز | 20 | 100 | 2018-09-16 | 2019-09-01 | 2019-05-05 | 2019-05-05 |  |  | اخرى |  | 42.5354 | 17.373 | مسحوب | No
2100049221 | أمانة / جازان | تشييد | ذات اولوية عالية | 5236696.672 | 261834.8336 | 3495536.52 | 3495536.52 | 1010168646 | لا | 0 | 180809059410 | مسحوب | الكميات التي تم تركيبها | 77 | 100 | 2013-04-27 | 2014-04-22 | 2020-02-16 | 2020-02-16 |  |  | اخرى |  | 42.8988 | 16.9622 | مسحوب | No
2100092470 | أمانة / جازان | دراسة الجدوى | ذات اولوية متوسطة | 921600 | 46080 | 806400 | 806400 | 5900031907 | لا | 0 | 181101250966 | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2018-11-15 | 2020-11-04 | 2020-11-04 | 2020-11-04 | 2020-11-04 |  | اخرى |  |  |  | منجز | No
2100081616 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4684525 | 234226.25 | 3222140 | 0 | 1010374883 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 89 | 100 | 2014-10-21 | 2016-04-13 | 2017-06-08 | 2017-06-08 | 2016-04-13 |  | ضعف كفاءة المقاول الفنية |  | 45.3543 | 26.4994 | منجز | Yes
2100075471 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3102000 | 155100 | 1804760.27 | 1804760.27 | 1010148208 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 67 | 100 | 2018-04-07 | 2019-07-01 | 2023-07-11 | 2023-07-11 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | Failed | No
2100083053 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 319050 | 15952.5 | 43076 | 0 | 1115001965 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-03-17 | 2018-06-25 | 2018-06-26 | 2018-06-26 | 2018-06-25 |  |  |  | 44.6302 | 23.9067 | منجز | Yes
2100029853 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4952540.25 | 247627.0125 | 0 | 0 | 1010158466 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 73.96 | 10 | 2019-06-12 | 2021-06-01 | 2021-06-01 | 2021-06-01 |  |  |  |  | 45.455 | 25.0781 | Failed | No
2100090694 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4737840 | 236892 | 1711150 | 0 | 1010168999 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 86 | 100 | 2015-02-11 | 2016-05-06 | 2019-10-19 | 2019-10-19 | 2016-05-06 |  | ضعف كفاءة المقاول الفنية |  | 46.6775 | 24.7025 | منجز | Yes
2100017161 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 12581370 | 629068.5 | 0 | 0 | 1010106132 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 45 | 1 | 2015-08-22 | 2017-09-12 | 2021-06-28 | 2021-06-28 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6745 | 24.6765 | مسحوب | No
2100013226 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 6548601.41 | 327430.0705 | 5835720 | 0 | 4031044308 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 99.94 | 100 | 2015-07-08 | 2017-02-27 | 2018-11-08 | 2018-11-08 | 2017-02-27 |  | ضعف كفاءة المقاول الفنية |  | 46.6713 | 24.7181 | منجز | Yes
2100032863 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1096532.85 | 54826.6425 | 0 | 0 | 1013001518 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 21 | 1 | 2019-08-25 | 2020-11-25 | 2021-06-20 | 2021-06-20 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7624 | 23.3902 | Failed | No
2100018244 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1791829 | 89591.45 | 1062821 | 0 | 1010329512 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 75 | 69 | 2014-08-30 | 2019-05-08 | 2019-05-08 | 2019-05-08 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6857 | 24.7025 | مسحوب | Yes
2100090381 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 9780000 | 489000 | 43311 | 0 | 1010158786 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-11-11 | 2019-10-07 | 2019-10-07 | 2019-10-07 | 2019-10-07 |  |  |  | 47.3246 | 24.1565 | منجز | Yes
2100045054 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3848965 | 192448.25 | 41413 | 0 | 1010242793 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 25 | 100 | 2014-11-04 | 2016-04-27 | 2020-11-09 | 2020-11-09 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6823 | 24.6969 | مسحوب | Yes
2100082401 | أمانة / جازان | تشييد | ذات اولوية منخفضة | 1771087.5 | 88554.375 | 1437899.44 | 1437899.44 | 5850100061 | لا | 0 | 191101282919 | منجز – استلام ابتدائي | اخرى | 81 | 100 | 2020-07-21 | 2020-11-18 | 2021-06-03 | 2021-06-03 | 2020-11-18 |  | ضعف كفاءة المقاول الفنية |  | 42.5735 | 16.9416 | منجز | No
2100008481 | أمانة / جازان | دراسة الجدوى | ذات اولوية متوسطة | 305500 | 15275 | 305500 | 305500 | 1131049510 | لا | 0 | 180701031598 | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2018-08-28 | 2019-09-22 | 2019-12-22 | 2019-12-22 | 2019-09-22 |  | اخرى |  | 42.9395 | 17.2375 | منجز | No
2100013440 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2953910 | 147695.5 | 0 | 0 | 4030197963 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-03-23 | 2014-06-16 | 2014-06-16 | 2014-06-16 | 2014-06-16 |  |  |  | 46.6603 | 24.7032 | منجز | No
2100034064 | أمانة / جازان | تشييد | ذات اولوية عالية | 7258160 | 362908 | 6511610 | 6511610 | 5900008127 | لا | 0 | 201109420716 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-09-13 | 2019-08-29 | 2021-06-03 | 2021-06-03 | 2019-08-29 |  | ضعف كفاءة المقاول الفنية |  | 42.6385 | 17.1464 | منجز | No
2100020366 | أمانة / الرياض | دراسة الجدوى | ذات اولوية عالية | 396000 | 19800 | 42064 | 0 | 1010381419 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-08-12 | 2015-12-10 | 2015-12-10 | 2015-12-10 | 2015-12-10 |  | ضعف كفاءة المقاول الفنية |  |  |  | منجز | Yes
2100033913 | أمانة / جازان | تشييد | ذات اولوية عالية | 2288400 | 114420 | 0 | 0 | 5907014307 | لا | 0 | 200501043718 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-11-12 | 2020-11-06 | 2021-11-11 | 2021-11-11 | 2020-11-06 |  | ضعف كفاءة المقاول الفنية |  | 42.94 | 16.5917 | منجز | No
2100017905 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 7770000 | 388500 | 39567 | 0 | 1011008815 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 90 | 100 | 2008-12-28 | 2019-01-13 | 2019-01-12 | 2019-01-12 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6919 | 24.7131 | مسحوب | Yes
2100031555 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3131668 | 156583.4 | 1759185.92 | 0 | 1118001565 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-07-31 | 2016-10-23 | 2020-08-04 | 2020-08-04 | 2016-10-23 |  | ضعف كفاءة المقاول الفنية |  | 46.6795 | 24.7044 | منجز | Yes
2100047224 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 241650 | 12082.5 | 241650 | 0 | 1113000219 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-01-23 | 2019-06-22 | 2019-07-22 | 2019-07-22 | 2019-06-22 |  |  |  | 45.5283 | 25.2938 | منجز | Yes
2100029341 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1208105 | 60405.25 | 1029756.5 | 0 | 1010168999 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 85 | 85 | 2015-05-27 | 2017-05-16 | 2017-05-17 | 2017-05-17 | 2017-05-16 |  |  |  | 46.6875 | 24.7005 | منجز | Yes
2100013263 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 41943704 | 2097185.2 | 13650080.7 | 0 | 1010101251 | لا | 0 |  | جاري | تكلفة العمل المنجز | 83 | 100 | 2011-01-04 | 2012-12-24 | 2022-12-14 | 2022-12-14 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6837 | 24.6982 | Failed | Yes
2100075655 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 6584350 | 329217.5 | 1819854 | 0 | 1010056094 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 85 | 100 | 2011-09-05 | 2013-04-27 | 2019-09-01 | 2019-09-01 | 2013-04-27 |  | ضعف كفاءة المقاول الفنية |  | 45.2492 | 25.2398 | منجز | Yes
2100080791 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2783365 | 139168.25 | 0 | 0 | 1010446037 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 29 | 20 | 2019-02-06 | 2021-01-26 | 2022-02-17 | 2022-02-17 |  |  | ضعف كفاءة المقاول الفنية |  | 45.3485 | 26.4973 | مسحوب | No
2100075003 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2988565 | 149428.25 | 41576 | 0 | 1010187076 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 18 | 100 | 2014-02-08 | 2016-12-18 | 2016-12-19 | 2016-12-19 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6981 | 24.7025 | مسحوب | Yes
2100062473 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4017330 | 200866.5 | 1637176 | 0 | 1010224518 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 97 | 100 | 2014-11-03 | 2016-04-26 | 2022-02-26 | 2022-02-26 | 2016-04-26 |  | ضعف كفاءة المقاول الفنية |  | 45.5206 | 23.5238 | منجز | Yes
2100029061 | أمانة / الرياض | تشييد | ذات اولوية عالية | 3900000 | 195000 | 4507161.6 | 0 | 1113000219 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 100 | 2014-09-20 | 2016-09-09 | 2020-01-08 | 2020-01-08 | 2016-09-09 |  | ضعف كفاءة المقاول الفنية |  | 45.2541 | 25.2239 | منجز | Yes
2100091512 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1737000 | 86850 | 1737000 | 0 | 1123002152 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-02-07 | 2019-04-10 | 2019-04-10 | 2019-04-10 | 2019-04-10 |  |  |  | 46.685 | 24.7119 | منجز | Yes
2100080275 | الهيئة العامة للطيران المدني | تشييد | ذات اولوية عالية وعاجلة | 29666943096 | 1483347154.8 | 28107044788.28 | 28107044788.28 | 4030068284 | لا | 0 | 181009165834 | جاري | منهجية القيمة المكتسبة | 96.2 | 100 | 2011-01-11 | 2014-01-10 | 2023-02-22 | 2023-02-22 |  |  | اخرى |  | 39.2093 | 21.4607 | Failed | No
2100082751 | أمانة / جازان | تشييد | ذات اولوية عالية | 29648525 | 1482426.25 | 1836863.75 | 1836863.75 | 5904006379 | لا | 0 | 181109368306 | مسحوب | الكميات التي تم تركيبها | 6 | 100 | 2015-04-08 | 2017-03-27 | 2022-03-30 | 2022-03-30 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5956 | 16.8942 | مسحوب | No
2100070070 | الهيئة العامة للطيران المدني | تصميم | ذات اولوية عالية وعاجلة | 17827635 | 891381.75 | 6306764.57 | 2123009.18 | 1010333947 | لا | 0 | 190701074062 | ايقاف كلي | تكلفة العمل المنجز | 22 | 59 | 2019-10-24 | 2020-10-23 | 2021-11-18 | 2021-11-18 |  |  | التنسيق مع أصحاب المصلحه (خدمات |  | 42.4612 | 17.9239 | Failed | No
2100093995 | أمانة / جازان | تشييد | ذات اولوية عالية | 46785375 | 2339268.75 | 21779926.48 | 21779926.48 | 5900000115 | لا | 0 | 180909066401 | جاري | اخرى | 90 | 100 | 2019-09-23 | 2021-09-12 | 2021-09-13 | 2021-09-13 |  |  | ضعف كفاءة المقاول الفنية |  | 42.6073 | 16.9999 | Failed | No
2100026961 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 13480196.2 | 674009.81 | 8966398.697 | 0 | 1116001737 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2011-05-28 | 2013-05-17 | 2019-09-08 | 2019-09-08 | 2013-05-17 |  | ضعف كفاءة المقاول الفنية |  | 46.663 | 24.7057 | منجز | Yes
2100029750 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 851294.5 | 42564.725 | 0 | 0 | 1132006618 | لا | 0 |  | جاري | تكلفة العمل المنجز | 90 | 100 | 2019-10-30 | 2021-04-30 | 2021-04-30 | 2021-04-30 |  |  | اخرى |  | 46.6782 | 24.7107 | Failed | No
2100072612 | أمانة / القصيم | تشييد | ذات اولوية عالية | 48630427 | 2431521.35 | 39202000 | 39202000 | 1131006723 | لا | 0 | 190709020144 | جاري | تكلفة العمل المنجز | 83 | 83 | 2015-02-08 | 2024-02-22 | 2024-02-22 | 2024-02-22 |  |  |  |  | 43.9818 | 26.3592 | منتظم | No
2100061272 | أمانة / جازان | تشييد | ذات اولوية عالية | 3789931.95 | 189496.5975 | 1658400 | 1658400 | 1010245651 | لا | 0 | 180909110317 | مسحوب | الكميات التي تم تركيبها | 49 | 100 | 2014-11-29 | 2015-11-24 | 2019-09-09 | 2019-09-09 |  |  | ضعف كفاءة المقاول الفنية |  | 42.0344 | 17.7043 | مسحوب | No
2100207955 | الهيئة العامة للطيران المدني | إشراف | ذات اولوية عالية | 40224605.74 | 2011230.287 | 26821794.96 | 26821794.96 | 4030216250 | لا | 0 | 200409013789 | جاري | مدفوعات ساعات العمل | 29.52 | 31.61 | 2014-12-19 | 2021-11-21 | 2021-11-21 | 2021-11-21 |  |  |  |  | 42.5839 | 16.8994 | خدمات عامة | No
2100083576 | أمانة / القصيم | تشييد | ذات اولوية عالية | 42740913 | 2137045.65 | 40410086.53 | 40410086.53 | 1131013992 | لا | 0 | 180801039446 | جاري | تكلفة العمل المنجز | 95 | 96 | 2018-11-07 | 2023-02-05 | 2023-02-05 | 2023-02-05 |  |  |  |  | 43.9818 | 26.3592 | منتظم | No
2100093015 | أمانة / جازان | تشييد | ذات اولوية عالية وعاجلة | 1475400 | 73770 | 761600 | 761600 | 5906328881 | لا | 0 |  | مسحوب | اخرى | 65 | 100 | 2019-05-14 | 2020-05-08 | 2021-08-05 | 2021-08-05 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5932 | 16.8839 | مسحوب | No
2100070254 | الهيئة العامة للطيران المدني | تصميم | ذات اولوية عالية | 4383968.5 | 219198.425 | 4383969.26 | 4383969.26 | 1010076578 | لا | 0 | 190401042652 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-05-01 | 2020-10-22 | 2020-10-22 | 2020-10-22 |  |  | التنسيق مع أصحاب المصلحه (خدمات |  | 40.6815 | 29.6761 | Failed | No
2100051144 | الهيئة العامة للطيران المدني | تشييد | ذات اولوية عالية وعاجلة | 517500000 | 25875000 | 481719540.19 | 481719540.19 | 1010011560 | لا | 0 | 190409037637 | جاري | منهجية القيمة المكتسبة | 99 | 100 | 2015-07-29 | 2017-08-26 | 2023-01-17 | 2023-01-17 |  |  | اخرى |  | 46.702 | 24.9453 | منتظم | No
2100007593 | الهيئة العامة للطيران المدني | تشييد | ذات اولوية عالية | 2264000000 | 113200000 | 2149376843.45 | 1871041913.87 | 1010004739 | لا | 0 | 190309099662 | جاري | تكلفة العمل المنجز | 99.98 | 100 | 2017-04-23 | 2022-12-31 | 2023-01-31 | 2023-01-31 |  |  | اخرى |  | 46.7074 | 24.9419 | منتظم | No
2100004830 | الهيئة العامة للطيران المدني | تشييد | ذات اولوية عالية | 367701290.96 | 18385064.548 | 19634029.84 | 19634029.84 | 1131000495 | لا | 0 | 190601033592 | جاري | تكلفة العمل المنجز | 11.9 | 100 | 2020-06-03 | 2022-05-24 | 2023-12-31 | 2023-12-31 |  |  | اخرى |  | 41.4715 | 20.0214 | Failed | No
2100189770 | الهيئة العامة للطيران المدني | تصميم | ذات اولوية عالية | 13847000 | 692350 | 5123585.86 | 5123585.86 | 4030276223 | لا | 0 | 200501052857 | جاري | تكلفة العمل المنجز | 56 | 100 | 2020-10-05 | 2022-06-02 | 2022-12-31 | 2022-12-31 |  |  |  |  | 44.0009 | 26.1782 | Failed | No
2200227813 | أمانة / المنطقة الشرقية | أخرى | ذات اولوية منخفضة | 971750 | 48587.5 | 137616 | 0 | 1010317923 | لا | 0 |  | جاري | التكلفة المفوترة | 14 | 95 | 2022-01-27 | 2023-01-27 | 2023-01-27 | 2023-01-27 |  |  |  |  | 50.0888 | 26.4207 | خدمات عامة | Yes
2100027893 | وزارة الحرس الوطني / الشؤون الفنية بالقطاع الغربي | تشييد | ذات اولوية متوسطة | 2520962.33 | 126048.1165 | 2520962.33 | 2436437.75 | 1010185891 | لا | 0 | 191001038043 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-11-28 | 2021-10-26 | 2021-10-26 | 2021-10-26 | 2021-10-26 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.8316 | 21.4218 | منجز | No
2100104495 | رئاسة أمن الدولة / قوات الأمن الخاصة | تشييد | ذات اولوية عالية وعاجلة | 7275845.85 | 363792.2925 | 7734116.01 | 7734116.01 | 1010188861 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-10-15 | 2020-12-02 | 2022-04-30 | 2022-04-30 | 2020-12-02 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 46.5657 | 24.8795 | منجز | No
2100099470 | رئاسة أمن الدولة / قوات الأمن الخاصة | تشييد | ذات اولوية عالية | 10958634.75 | 547931.7375 | 11820864 | 11820864 | 1010045581 | لا | 0 | 200101001610 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2020-02-13 | 2021-05-30 | 2022-02-13 | 2022-02-13 | 2021-05-30 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 46.564 | 24.8769 | منجز | No
2100085330 | الجمارك السعودية | دراسة الجدوى | ذات اولوية عالية | 7047926.6 | 352396.33 | 7047926.6 | 7047926.6 | 4030234254 | لا | 0 | 181209470655 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-04-02 | 2017-03-01 | 2021-04-02 | 2021-04-02 | 2017-03-01 |  | اخرى |  | 34.9613 | 29.3562 | منجز | No
2100004480 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 450200 | 22510 | 41370 | 0 | 4030065096 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 40 | 100 | 2014-03-22 | 2015-03-07 | 2015-03-07 | 2015-03-07 |  |  | ضعف كفاءة المقاول الفنية |  | 46.658 | 24.6865 | مسحوب | Yes
2100017916 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3662350 | 183117.5 | 0 | 0 | 4030065096 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2012-03-29 | 2013-03-24 | 2021-06-16 | 2021-06-16 | 2013-03-24 |  | ضعف كفاءة المقاول الفنية |  | 46.1032 | 25.1144 | منجز | No
2100106982 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 12515322 | 625766.1 | 6227800 | 0 | 3350003498 | لا | 0 |  | جاري | التكلفة المفوترة | 58 | 100 | 2013-06-17 | 2015-06-07 | 2021-12-29 | 2021-12-29 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | Failed | Yes
2100030365 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4092990 | 204649.5 | 0 | 0 | 1010015152 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 39 | 100 | 2019-06-20 | 2021-02-09 | 2021-02-08 | 2021-02-08 |  |  | اخرى |  | 46.672 | 24.7001 | مسحوب | No
2100090554 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1901180 | 95059 | 1499520 | 0 | 1010194071 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 99 | 100 | 2015-08-20 | 2016-08-04 | 2016-08-04 | 2016-08-04 | 2016-08-04 |  | ضعف كفاءة المقاول الفنية |  | 46.1014 | 25.114 | منجز | Yes
2100103062 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 6241418 | 312070.9 | 3482447 | 3482447 | 3350007326 | لا | 0 |  | مسحوب | التكلفة المفوترة | 60 | 100 | 2013-10-21 | 2015-07-10 | 2019-01-23 | 2019-01-23 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | مسحوب | No
2100105070 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 4170944 | 208547.2 | 597496.25 | 597496.25 | 3350033111 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 18 | 100 | 2015-01-18 | 2016-07-21 | 2020-11-18 | 2020-11-18 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | مسحوب | No
2100044575 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 10000 | 500 | 0 | 0 | 1010158786 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 8 | 2019-10-08 | 2020-09-11 | 2020-09-11 | 2020-09-11 | 2020-09-11 |  |  |  | 46.152 | 24.6111 | منجز | No
2100009682 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 3191512.89 | 159575.6445 | 824341 | 824341 | 1010233819 | لا | 0 | 190909165132 | فسخ العقد | التكلفة المفوترة | 71 | 100 | 2015-06-01 | 2016-05-26 | 2021-06-10 | 2021-06-10 |  |  | ضعف كفاءة المقاول الفنية |  | 40.0549 | 29.8587 | مسحوب | No
2100030531 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1918500 | 95925 | 42077 | 0 | 1113000219 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-11-02 | 2017-01-25 | 2017-01-25 | 2017-01-25 | 2017-01-25 |  | تأخرصرف المستحقات المالية |  | 45.2188 | 25.3664 | منجز | Yes
2200233940 | الهيئة العامة للموانئ | تشييد | ذات اولوية عالية | 102007762.3 | 5100388.115 | 919278.09 | 0 | 4031010826 | لا | 0 |  | جاري | تكلفة العمل المنجز | 5 | 5 | 2022-09-24 | 2024-09-23 | 2024-09-23 | 2024-09-23 |  |  |  | العقد يسير حسب الخطة | 49.625 | 27.0052 | منتظم | Yes
2100032782 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 45770267 | 2288513.35 | 16037828.268 | 0 | 1010203405 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 98 | 100 | 2014-09-15 | 2016-09-04 | 2017-02-15 | 2017-02-15 |  |  | ضعف كفاءة المقاول الفنية |  | 42.9011 | 23.9042 | Failed | Yes
2100041145 | أمانة / الرياض | دراسة الجدوى | ذات اولوية متوسطة | 2108000 | 105400 | 39811 | 0 | 4031257377 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-12-03 | 2014-07-01 | 2014-07-01 | 2014-07-01 | 2014-07-01 |  | ضعف كفاءة المقاول الفنية |  |  |  | منجز | Yes
2100066614 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 5748889 | 287444.45 | 5748889 | 5748889 | 5810009404 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-01-21 | 2016-12-30 | 2016-12-31 | 2016-12-31 | 2016-12-30 |  |  |  | 41.6607 | 20.272 | منجز | No
2100008466 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1512366 | 75618.3 | 0 | 0 | 1132422960 | لا | 0 |  | جاري | التكلفة المفوترة | 47 | 100 | 2007-02-24 | 2008-08-17 | 2024-12-31 | 2024-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | Failed | No
2100108975 | وزارة الحرس الوطني / الشؤون الفنية بالقطاع الغربي | تشييد | ذات اولوية متوسطة | 267001380.36 | 13350069.018 | 233445530.59 | 233445530.59 | 1010023333 | لا | 0 | 180809044013 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-03-29 | 2021-03-21 | 2022-09-30 | 2022-09-30 | 2021-03-21 |  | تأخرصرف المستحقات المالية | تم إنذار المقاول كتابيا | 39.2092 | 21.4708 | منجز | No
2100087905 | وزارة التعليم | تشييد | ذات اولوية عالية | 9942998 | 497149.9 | 5733867.32 | 0 | 3350003498 | لا | 0 |  | جاري | التكلفة المفوترة | 92 | 100 | 2013-04-08 | 2015-03-29 | 2022-01-17 | 2022-01-17 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | متأخر | Yes
2100004141 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2987258 | 149362.9 | 1619663.75 | 1619663.75 | 4650039553 | لا | 0 |  | مسحوب | التكلفة المفوترة | 64 | 100 | 2016-11-27 | 2018-01-21 | 2022-06-15 | 2022-06-15 |  |  | ضعف كفاءة المقاول الفنية |  | 40.8817 | 23.5031 | مسحوب | No
2100040526 | وزارة الصحة/ الاحساء | تشييد | ذات اولوية متوسطة | 512400 | 25620 | 512400 | 512400 | 1010183991 | لا | 0 | 180909110762 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 0 | 2018-11-13 | 2019-02-09 | 2020-07-16 | 2020-07-16 | 2019-02-09 |  | اخرى |  | 49.5675 | 25.3073 | منجز | No
2100015746 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2185033 | 109251.65 | 444302 | 444302 | 3350014233 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 33 | 100 | 2018-02-10 | 2018-10-22 | 2021-12-15 | 2021-12-15 | 2018-10-22 |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | منجز | No
2100066194 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 20233940 | 1011697 | 11733783.28 | 11733783.28 | 5855007548 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 65 | 100 | 2014-04-03 | 2016-03-23 | 2022-10-01 | 2022-10-01 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6511 | 20.2795 | مسحوب | No
2100193244 | وزارة الحرس الوطني / الشؤون الفنية بالقطاع الغربي | توريد وتركيب | ذات اولوية عالية | 591483.33 | 29574.1665 | 591483 | 591483 | 4650041179 | لا | 0 | 200901060142 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2021-01-07 | 2022-01-06 | 2022-01-06 | 2022-01-06 | 2022-01-06 |  |  |  | 39.6583 | 24.5223 | منجز | No
2100103224 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 10995947 | 549797.35 | 3400023 | 0 | 1132002570 | لا | 0 |  | مسحوب | التكلفة المفوترة | 40 | 100 | 2013-12-28 | 2015-12-18 | 2020-08-21 | 2020-08-21 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | مسحوب | Yes
2100075246 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 10208665 | 510433.25 | 4544121.1 | 0 | 1010154882 | لا | 0 |  | جاري | تكلفة العمل المنجز | 80 | 100 | 2015-06-15 | 2017-06-04 | 2020-07-17 | 2020-07-17 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6727 | 24.7007 | Failed | Yes
2100017522 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2414909 | 120745.45 | 2136637 | 2136637 | 3360005060 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 90 | 100 | 2017-09-12 | 2018-09-07 | 2021-12-15 | 2021-12-15 | 2018-09-07 |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | منجز | No
2100016914 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 8346454 | 417322.7 | 5790970.3879 | 0 | 1010168999 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 70 | 100 | 2015-04-16 | 2018-05-21 | 2019-12-30 | 2019-12-30 | 2018-05-21 |  | ضعف كفاءة المقاول الفنية |  | 46.685 | 24.7069 | منجز | Yes
2100090296 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 985000 | 49250 | 232263 | 0 | 1017001594 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 23 | 100 | 2015-08-09 | 2017-01-30 | 2019-10-15 | 2019-10-15 |  |  | ضعف كفاءة المقاول الفنية |  | 45.5581 | 20.4595 | مسحوب | Yes
2100012596 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4335100 | 216755 | 1187817 | 0 | 1116000082 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 27 | 27 | 2012-05-15 | 2013-09-07 | 2013-09-07 | 2013-09-07 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6864 | 24.7094 | Failed | Yes
2100086166 | وزارة التعليم | تشييد | ذات اولوية عالية | 2639769 | 131988.45 | 0 | 0 | 1010312862 | لا | 0 |  | مسحوب | التكلفة المفوترة | 0 | 100 | 2014-11-16 | 2016-02-02 | 2016-02-02 | 2016-02-02 |  |  | ضعف كفاءة المقاول الفنية |  | 37.2711 | 27.0208 | مسحوب | No
2100017511 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 31611510 | 1580575.5 | 3151541 | 0 | 1113000219 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 98 | 100 | 2013-08-04 | 2015-07-25 | 2019-09-11 | 2019-09-11 | 2015-07-25 |  | ضعف كفاءة المقاول الفنية |  | 46.6713 | 24.7069 | منجز | Yes
2100064363 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1447060 | 72353 | 41820 | 0 | 1118001032 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 39 | 100 | 2014-11-26 | 2018-10-07 | 2018-10-07 | 2018-10-07 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7022 | 24.7163 | مسحوب | Yes
2100041171 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 22999446 | 1149972.3 | 0 | 0 | 1131013286 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0.01 | 100 | 2013-01-28 | 2015-01-08 | 2018-05-15 | 2018-05-15 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 41.6968 | 27.506 | مسحوب | No
2100108846 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2112909.08 | 105645.454 | 2013380.43 | 1771768.76 | 1010089371 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-03-05 | 2015-05-29 | 2019-12-10 | 2019-12-10 | 2015-05-29 |  | ضعف كفاءة المقاول الفنية |  | 40.8817 | 23.5031 | منجز | No
2100095815 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4784000 | 239200 | 344056 | 0 | 1010237336 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 35.71 | 100 | 2015-03-19 | 2019-03-25 | 2019-03-25 | 2019-03-25 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6823 | 24.7219 | مسحوب | Yes
2100095314 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2353383.95 | 117669.1975 | 1318659 | 1318659 | 3350008314 | لا | 0 |  | مسحوب | التكلفة المفوترة | 46 | 100 | 2008-10-13 | 2011-09-12 | 2016-02-22 | 2016-02-22 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | مسحوب | No
2100065380 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 17178109 | 858905.45 | 6769475.64 | 0 | 1116000094 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 100 | 2010-10-22 | 2012-08-12 | 2019-09-21 | 2019-09-21 | 2012-08-12 |  | ضعف كفاءة المقاول الفنية |  | 46.0995 | 25.1034 | منجز | Yes
2100002004 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 10239487.35 | 511974.3675 | 3325147.2 | 0 | 3350009307 | لا | 0 |  | جاري | التكلفة المفوترة | 94 | 100 | 2013-03-12 | 2015-03-02 | 2021-12-15 | 2021-12-15 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | متأخر | Yes
2100042335 | الجمارك السعودية | تشييد | ذات اولوية عالية | 4265593.6 | 213279.68 | 3071329.6 | 3071329.6 | 1010203140 | لا | 0 | 200701123424 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-10-11 | 2021-02-11 | 2021-11-08 | 2021-11-08 | 2021-02-11 |  | اخرى |  | 51.5226 | 24.1624 | منجز | No
2200236736 | المركز الوطني لتنمية الحياة الفطرية | تشييد | ذات اولوية متوسطة | 771650 | 38582.5 | 0 | 0 | 1010282908 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 30 | 100 | 2022-06-05 | 2022-07-15 | 2023-03-01 | 2023-03-01 |  |  |  | تم إنذار المقاول كتابيا | 46.6272 | 25.2241 | Failed | No
2200232304 | أمانة / المنطقة الشرقية | تصميم | ذات اولوية متوسطة | 4007675.25 | 200383.7625 | 0 | 0 | 1010464778 | لا | 0 |  | جاري | التكلفة المفوترة | 0 | 15 | 2022-08-07 | 2023-08-07 | 2023-08-07 | 2023-08-07 |  |  |  |  | 50.0888 | 26.4207 | متأخر | No
2100088793 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2291716.93 | 114585.8465 | 1352150.81 | 753637.47 | 3400000500 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2017-03-22 | 2018-03-17 | 2020-03-05 | 2020-03-05 | 2018-03-17 |  |  |  | 40.0549 | 29.8587 | منجز | No
2100029584 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 29836800 | 1491840 | 9160488.25 | 0 | 1010056094 | لا | 0 |  | جاري | تكلفة العمل المنجز | 40 | 100 | 2015-08-04 | 2017-07-24 | 2021-01-11 | 2021-01-11 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6727 | 24.7131 | Failed | Yes
2100075191 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 18538086 | 926904.3 | 9098184.498 | 0 | 1010010466 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 87 | 100 | 2013-03-08 | 2014-12-28 | 2019-11-13 | 2019-11-13 | 2014-12-28 |  | ضعف كفاءة المقاول الفنية |  | 45.2498 | 24.0387 | منجز | Yes
2100193266 | وزارة الحرس الوطني / الشؤون الفنية بالقطاع الغربي | تشييد | ذات اولوية عالية | 6755850.27 | 337792.5135 | 6323059.45 | 4621786.06 | 4030181263 | لا | 0 | 220209090698 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2021-02-21 | 2022-02-09 | 2022-02-28 | 2022-02-28 | 2022-02-09 |  |  |  | 39.3679 | 21.4475 | منجز | No
2100108636 | وزارة الحرس الوطني / الشؤون الفنية بالقطاع الغربي | تشييد | ذات اولوية متوسطة | 133070793.16 | 6653539.658 | 94548618.76 | 94548618.76 | 1010153168 | لا | 0 | 180709028163 | جاري | تكلفة العمل المنجز | 78 | 100 | 2014-12-28 | 2015-12-17 | 2023-03-15 | 2023-03-15 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال | تم إعطاء المقاول مهلة بعد سحبه | 39.6154 | 24.4839 | Failed | No
2100089806 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 909464 | 45473.2 | 736544 | 736544 | 3360005060 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2017-09-17 | 2018-01-05 | 2019-02-15 | 2019-02-15 | 2018-01-05 |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | منجز | No
2100100516 | وزارة الحرس الوطني / الشؤون الفنية بالقطاع الغربي | تشييد | ذات اولوية متوسطة | 5248950 | 262447.5 | 5248950 | 4587975 | 4030023505 | لا | 0 | 180701034240 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-07-08 | 2020-07-06 | 2020-07-06 | 2020-07-06 | 2020-07-06 |  | ضعف كفاءة المقاول الفنية |  | 39.8471 | 21.4213 | منجز | No
2100007022 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1924885 | 96244.25 | 1521800 | 1521800 | 1131017462 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 95 | 100 | 2018-11-12 | 2019-05-11 | 2021-12-15 | 2021-12-15 | 2019-05-11 |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | منجز | No
2200228056 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية عالية | 36126956 | 1806347.8 | 11918123.19 | 5377400 | 2050018628 | لا | 0 | 201101171274 | جاري | التكلفة المفوترة | 34 | 50 | 2022-02-24 | 2023-11-25 | 2023-11-25 | 2023-11-25 |  |  |  |  | 50.0888 | 26.4207 | متأخر | No
2100026320 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 10889895.6 | 544494.78 | 4383748.89 | 0 | 3350003498 | لا | 0 |  | جاري | التكلفة المفوترة | 45 | 100 | 2013-02-05 | 2015-01-26 | 2021-12-15 | 2021-12-15 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | Failed | Yes
2100044811 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2600160 | 130008 | 2080126 | 0 | 1010127437 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 99.48 | 100 | 2015-05-27 | 2016-08-19 | 2019-05-02 | 2019-05-02 | 2016-08-19 |  |  |  | 46.6775 | 24.7125 | منجز | Yes
2100030951 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 564560 | 28228 | 536240 | 0 | 1010024386 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 95 | 100 | 2015-08-20 | 2017-12-21 | 2017-12-21 | 2017-12-21 | 2017-12-21 |  |  |  | 46.6713 | 24.7206 | منجز | Yes
2100064886 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3284420 | 164221 | 799702 | 0 | 1113000601 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 38 | 21 | 2019-03-06 | 2020-08-27 | 2020-08-28 | 2020-08-28 |  |  |  |  | 45.2546 | 25.2452 | Failed | Yes
2100103541 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 15018116.3 | 750905.815 | 10125255.11 | 10125255.11 | 1010196220 | لا | 0 | 190209015495 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2013-05-11 | 2015-05-01 | 2021-11-09 | 2021-11-09 | 2015-05-01 |  | ضعف كفاءة المقاول الفنية |  | 40.0549 | 29.8587 | منجز | No
2100064223 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 588250 | 29412.5 | 301000 | 0 | 1010308396 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 48 | 2018-02-05 | 2020-12-21 | 2020-12-21 | 2020-12-21 | 2020-12-21 |  |  |  | 45.3775 | 25.3548 | منجز | Yes
2100081362 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4994300 | 249715 | 3000000 | 0 | 1123000085 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 100 | 100 | 2015-10-14 | 2017-01-06 | 2019-12-10 | 2019-12-10 | 2017-01-06 |  | ضعف كفاءة المقاول الفنية |  | 44.8315 | 26.2986 | Failed | Yes
2100011815 | أمانة / الرياض | دراسة الجدوى | ذات اولوية متوسطة | 2178000 | 108900 | 1254000 | 0 | 1010372072 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-04-03 | 2020-12-18 | 2020-12-17 | 2020-12-17 | 2020-12-18 |  | اخرى |  |  |  | منجز | Yes
2200228060 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية منخفضة | 7327075 | 366353.75 | 1890358.5 | 1890358.5 | 2050018628 | لا | 0 | 210501051164 | ايقاف كلي | التكلفة المفوترة | 25 | 61 | 2022-02-17 | 2023-08-02 | 2023-08-02 | 2023-08-02 |  |  |  | أخرى | 50.0888 | 26.4207 | Failed | No
2100058785 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البحرية | دراسة الجدوى | ذات اولوية عالية | 8164800 | 408240 | 8466480 | 6840720 | 1010323842 | لا | 0 |  | جاري الاستلام الإبتدائي | مدفوعات ساعات العمل | 100 | 100 | 2019-09-19 | 2022-08-17 | 2022-08-17 | 2022-08-17 |  |  |  |  | 49.6175 | 27.0628 | متأخر | No
2100017953 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4834000 | 241700 | 4524858.4 | 0 | 1113000219 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 93.6 | 100 | 2015-02-24 | 2017-02-08 | 2017-02-08 | 2017-02-08 | 2017-02-08 |  |  |  | 46.6768 | 24.7098 | منجز | Yes
2100029105 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 542000 | 27100 | 542000 | 0 | 1010246223 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2017-11-05 | 2018-10-31 | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 46.685 | 24.7244 | منجز | Yes
2100080850 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4504368 | 225218.4 | 4251166.532 | 0 | 1010064540 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-11-10 | 2018-10-20 | 2018-10-21 | 2018-10-21 | 2018-10-20 |  |  |  | 45.8634 | 25.2645 | منجز | Yes
2100024581 | أمانة / الرياض | تشييد | ذات اولوية عالية | 985000 | 49250 | 232263 | 0 | 1017001594 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 24 | 100 | 2015-08-09 | 2017-01-30 | 2017-01-30 | 2017-01-30 |  |  | ضعف كفاءة المقاول الفنية |  | 45.5894 | 20.4502 | مسحوب | Yes
2100012891 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 7586550 | 379327.5 | 5960086.67 | 0 | 1010056094 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 90 | 100 | 2015-05-13 | 2017-05-02 | 2019-11-23 | 2019-11-23 | 2017-05-02 |  | ضعف كفاءة المقاول الفنية |  | 46.6795 | 24.7069 | منجز | Yes
2100033261 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2274537 | 113726.85 | 1827972.39 | 0 | 4031057760 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 96 | 100 | 2014-08-25 | 2015-11-18 | 2019-11-06 | 2019-11-06 | 2015-11-18 |  | ضعف كفاءة المقاول الفنية |  | 46.6871 | 24.7001 | منجز | Yes
2100101323 | وزارة الصحة / المدينة المنورة | تشييد | ذات اولوية عالية | 2893400 | 144670 | 751255 | 508200 | 4650046499 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 40 | 100 | 2016-07-16 | 2017-03-09 | 2021-11-16 | 2021-11-16 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.5341 | 24.414 | مسحوب | No
2100063416 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 7830000 | 391500 | 2835000 | 0 | 1010168247 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 62 | 2018-04-11 | 2020-03-31 | 2020-03-21 | 2020-03-21 | 2020-03-31 |  |  |  | 46.8773 | 23.493 | منجز | Yes
2100073765 | وزارة الصحة / المدينة المنورة | تشييد | ذات اولوية منخفضة | 27517414 | 1375870.7 | 20545919 | 18688396 | 4030136192 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 85 | 100 | 2013-09-24 | 2015-09-02 | 2022-06-30 | 2022-06-30 |  |  | تأخرصرف المستحقات المالية |  | 39.36 | 24.28 | Failed | No
2100063335 | أمانة / الرياض | دراسة الجدوى | ذات اولوية متوسطة | 1975050 | 98752.5 | 0 | 0 | 1010393520 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 90 | 84 | 2019-09-01 | 2022-02-17 | 2022-10-17 | 2022-10-17 |  |  | اخرى |  |  |  | خدمات عامة | No
2100054876 | وزارة الصحة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 1177701 | 58885.05 | 1177701 | 910355 | 4650027612 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-10-12 | 2020-04-06 | 2021-11-16 | 2021-11-16 | 2020-04-06 |  | تأخرصرف المستحقات المالية |  | 39.5474 | 24.4695 | منجز | No
2100055333 | وزارة الصحة / المدينة المنورة | تشييد | ذات اولوية عالية | 43591315 | 2179565.75 | 20017662.4 | 19635617 | 4030136192 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 65 | 100 | 2015-08-18 | 2017-07-26 | 2022-12-31 | 2022-12-31 |  |  | تأخرصرف المستحقات المالية |  | 38.0289 | 24.0983 | مسحوب | No
2100097904 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 5124777.7 | 256238.885 | 0 | 0 | 1010012745 | لا | 0 |  | مسحوب | التكلفة المفوترة | 40 | 100 | 2010-03-20 | 2011-09-12 | 2016-01-06 | 2016-01-06 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | مسحوب | No
2100024290 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4648025 | 232401.25 | 42103 | 0 | 1113000219 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 0 | 100 | 2015-12-16 | 2017-06-08 | 2021-02-21 | 2021-02-21 |  |  | تأخرصرف المستحقات المالية |  | 45.2921 | 25.2819 | Failed | Yes
2100045065 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2375750 | 118787.5 | 2178780 | 0 | 1010225108 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 91.9 | 100 | 2013-11-17 | 2018-03-31 | 2018-03-31 | 2018-03-31 | 2018-03-31 |  |  |  | 45.8712 | 25.2771 | منجز | Yes
2100032303 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3819945 | 190997.25 | 41386 | 0 | 1010279126 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 89 | 100 | 2014-02-01 | 2015-04-27 | 2019-10-06 | 2019-10-06 | 2015-04-27 |  | ضعف كفاءة المقاول الفنية |  | 46.6926 | 24.7025 | منجز | Yes
2100082121 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 3206070 | 160303.5 | 3206070 | 3206070 | 4030091106 | لا | 0 | 200609098245 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2019-06-10 | 2020-05-29 | 2020-11-07 | 2020-11-07 | 2020-05-29 |  | ضعف كفاءة المقاول الفنية |  | 50.0701 | 26.3622 | منجز | No
2100080651 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2221755 | 111087.75 | 41722 | 0 | 1010290449 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 75 | 100 | 2014-11-24 | 2019-05-09 | 2019-05-09 | 2019-05-09 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6713 | 24.7157 | مسحوب | Yes
2100062683 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1057555 | 52877.75 | 40845 | 0.01 | 2051044373 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 26 | 100 | 2012-07-22 | 2017-04-16 | 2017-04-16 | 2017-04-16 |  |  | ضعف كفاءة المقاول الفنية |  | 44.771 | 23.7713 | مسحوب | No
2100045113 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 6971380 | 348569 | 4706734.98 | 0 | 1010203405 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 98.72 | 100 | 2012-07-13 | 2014-07-03 | 2019-08-28 | 2019-08-28 | 2014-07-03 |  | ضعف كفاءة المقاول الفنية |  | 42.9015 | 23.9093 | منجز | Yes
2100030133 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 787620 | 39381 | 242200 | 0 | 1113000219 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 47 | 2019-01-14 | 2020-01-09 | 2019-12-31 | 2019-12-31 | 2020-01-09 |  |  |  | 46.6754 | 24.7044 | منجز | Yes
2100062381 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1262188 | 63109.4 | 1083700 | 0 | 1017000718 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2019-01-24 | 2020-10-01 | 2020-10-01 | 2020-10-01 | 2020-10-01 |  |  |  | 46.5125 | 23.6149 | منجز | Yes
2100081410 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1258075 | 62903.75 | 452250 | 0 | 1011000444 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 97 | 100 | 2018-05-08 | 2019-04-27 | 2019-04-27 | 2019-04-27 | 2019-04-27 |  | تأخرصرف المستحقات المالية |  | 47.2274 | 24.1657 | منجز | Yes
2100033025 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4493514 | 224675.7 | 1400000 | 0 | 1114000037 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 50 | 100 | 2014-12-21 | 2016-03-15 | 2020-03-30 | 2020-03-30 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6713 | 24.7107 | مسحوب | Yes
2100095535 | وزارة الصحة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 380836 | 19041.8 | 17630 | 0 | 4650040868 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 50 | 100 | 2019-03-26 | 2019-05-24 | 2022-06-30 | 2022-06-30 |  |  | تأخرصرف المستحقات المالية |  | 38.0296 | 24.0983 | Failed | Yes
2100041974 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 1596840 | 79842 | 1155936.44 | 1155936.44 | 1010017756 | لا | 0 |  | جاري | التكلفة المفوترة | 75 | 100 | 2010-06-04 | 2011-08-28 | 2022-05-22 | 2022-05-22 |  |  | ضعف كفاءة المقاول الفنية |  | 41.6968 | 27.506 | Failed | No
2100042766 | وزارة التعليم | تشييد | ذات اولوية عالية | 2054880.61 | 102744.0305 | 943617.5 | 943617.5 | 4652000374 | لا | 0 |  | جاري | التكلفة المفوترة | 46 | 100 | 2013-07-24 | 2014-10-17 | 2023-01-15 | 2023-01-15 |  |  | ضعف كفاءة المقاول الفنية |  | 40.8817 | 23.5031 | Failed | No
2100096644 | وزارة التعليم | تشييد | ذات اولوية عالية | 1969747.19 | 98487.3595 | 848293.75 | 848293.75 | 4652000374 | لا | 0 |  | جاري | التكلفة المفوترة | 44 | 100 | 2013-07-24 | 2014-10-17 | 2023-01-15 | 2023-01-15 |  |  | ضعف كفاءة المقاول الفنية |  | 40.8817 | 23.5031 | Failed | No
2100004723 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البحرية | تشييد | ذات اولوية متوسطة | 20586674 | 1029333.7 | 11613388 | 11613388 | 4030201114 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 71 | 100 | 2013-10-09 | 2015-03-04 | 2021-12-31 | 2021-12-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.2035 | 21.4787 | مسحوب | No
2100063545 | وزارة التعليم | تشييد | ذات اولوية عالية | 2130220 | 106511 | 0 | 0 | 4652000374 | لا | 0 |  | مسحوب | التكلفة المفوترة | 0.5 | 100 | 2014-01-01 | 2015-03-27 | 2019-11-13 | 2019-11-13 |  |  | ضعف كفاءة المقاول الفنية |  | 40.8817 | 23.5031 | مسحوب | No
2100046826 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 28799505 | 1439975.25 | 5100474 | 5100474 | 3350014401 | لا | 0 | 190201021631 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 90 | 100 | 2019-03-03 | 2021-03-21 | 2022-10-31 | 2022-10-31 | 2021-03-21 |  |  |  | 41.6553 | 27.4577 | منجز | No
2100072774 | أمانة / جازان | تشييد | ذات اولوية عالية | 13717388.065 | 685869.4032 | 6624947.07 | 6624947.07 | 1010168646 | لا | 0 | 180809059475 | مسحوب | الكميات التي تم تركيبها | 47 | 100 | 2013-04-27 | 2015-04-17 | 2020-02-17 | 2020-02-17 |  |  | اخرى |  | 42.8498 | 16.9645 | مسحوب | No
2100059161 | أمانة / جازان | تشييد | ذات اولوية عالية | 9047400 | 452370 | 6326900 | 6326900 | 4035000994 | لا | 0 | 181101250720 | جاري | الكميات التي تم تركيبها | 87 | 100 | 2019-01-21 | 2021-01-10 | 2021-11-11 | 2021-11-11 |  |  | ضعف كفاءة المقاول الفنية |  | 43.1077 | 17.2462 | Failed | No
2100046255 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3870420 | 193521 | 2458689.7 | 0 | 1111000356 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 78 | 100 | 2014-08-02 | 2015-10-26 | 2015-10-26 | 2015-10-26 | 2015-10-26 |  | ضعف كفاءة المقاول الفنية |  | 46.6799 | 24.7042 | منجز | Yes
2100045393 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1930170 | 96508.5 | 42106 | 0 | 3350100229 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 95 | 100 | 2015-08-02 | 2016-07-27 | 2019-04-10 | 2019-04-10 | 2016-07-27 |  | ضعف كفاءة المقاول الفنية |  | 46.6878 | 24.7369 | منجز | Yes
2100029326 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 6840898.2 | 342044.91 | 40305 | 0 | 1010203405 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 73.19 | 100 | 2010-10-30 | 2012-06-21 | 2012-06-21 | 2012-06-21 | 2012-06-21 |  | ضعف كفاءة المقاول الفنية |  | 46.6686 | 24.6907 | منجز | Yes
2100032373 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1721812.5 | 86090.625 | 42101 | 0 | 1116005202 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 40 | 100 | 2015-08-21 | 2017-02-11 | 2019-10-27 | 2019-10-27 |  |  | ضعف كفاءة المقاول الفنية |  | 45.2098 | 24.047 | Failed | Yes
2100034705 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 10484280 | 524214 | 6056194.5 | 0 | 1116001737 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 80 | 100 | 2015-08-06 | 2016-10-29 | 2019-12-16 | 2019-12-16 | 2016-10-29 |  | ضعف كفاءة المقاول الفنية |  | 46.6686 | 24.6994 | منجز | Yes
2100043816 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2299900 | 114995 | 1361613.45 | 0 | 1114000037 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 65 | 100 | 2014-10-13 | 2015-12-07 | 2020-02-02 | 2020-02-02 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6898 | 24.7088 | مسحوب | Yes
2100090355 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1516310 | 75815.5 | 1147410 | 0 | 1117002589 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-05-29 | 2016-08-21 | 2021-05-11 | 2021-05-11 | 2016-08-21 |  | ضعف كفاءة المقاول الفنية |  | 46.5072 | 23.6236 | منجز | Yes
2100063722 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1896426 | 94821.3 | 1447087 | 0 | 1131021685 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 75 | 2018-01-03 | 2019-12-24 | 2019-12-24 | 2019-12-24 | 2019-12-24 |  |  |  | 46.6713 | 24.7119 | منجز | Yes
2100071374 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 68364650 | 3418232.5 | 39953426.447 | 0 | 1116001737 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-08-12 | 2015-08-02 | 2020-07-10 | 2020-07-10 | 2015-08-02 |  | ضعف كفاءة المقاول الفنية |  | 46.6624 | 24.7063 | منجز | Yes
2100050993 | أمانة / جازان | تشييد | ذات اولوية عالية | 650088.89 | 32504.4445 | 344124.84 | 344124.84 | 5910030868 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 56 | 100 | 2015-09-12 | 2016-09-05 | 2020-06-23 | 2020-06-23 |  |  | اخرى |  | 42.5724 | 16.8909 | مسحوب | No
2100081292 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 985000 | 49250 | 232263 | 0 | 1017001594 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 24 | 100 | 2015-08-09 | 2017-01-30 | 2021-07-04 | 2021-07-04 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6663 | 24.699 | مسحوب | Yes
2100026946 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 4617330 | 230866.5 | 1923243 | 1923243 | 5950000060 | لا | 0 | 2005059502 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 98.54 | 100 | 2019-05-26 | 2021-03-07 | 2022-05-18 | 2022-05-18 | 2021-03-07 |  | التنسيق مع أصحاب المصلحه (خدمات |  | 44.2186 | 17.5742 | منجز | No
2100060292 | جامعة جازان | تشييد | ذات اولوية متوسطة | 664650 | 33232.5 | 608626.5 | 608626.5 | 5900017383 | لا | 0 | 191001259336 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-09-26 | 2019-12-24 | 2019-12-26 | 2019-12-26 | 2019-12-24 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.5417 | 16.9659 | منجز | No
2100034484 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 1709394.2 | 85469.71 | 276916 | 276916 | 5855031640 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 16 | 100 | 2011-01-26 | 2012-01-20 | 2019-02-18 | 2019-02-18 |  |  | اخرى |  | 42.5784 | 16.9011 | مسحوب | No
2100026283 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2553146.95 | 127657.3475 | 2176418 | 0 | 1010216996 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-11-23 | 2015-05-17 | 2021-06-21 | 2021-06-21 | 2015-05-17 |  |  |  | 45.8121 | 25.2968 | منجز | Yes
2100063851 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1959220 | 97961 | 41745 | 0 | 1010249671 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 0 | 100 | 2014-08-31 | 2015-11-24 | 2016-05-24 | 2016-05-24 |  |  | تأخرصرف المستحقات المالية |  | 44.389 | 23.4804 | Failed | Yes
2100064610 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 12475993 | 623799.65 | 8783190.7434 | 0 | 1010197183 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-07-31 | 2015-07-21 | 2019-09-13 | 2019-09-13 | 2015-07-21 |  | ضعف كفاءة المقاول الفنية |  | 46.6843 | 24.7075 | منجز | Yes
2100081056 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 18056122.5 | 902806.125 | 7035727 | 0 | 1010158786 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-09-11 | 2015-09-01 | 2019-11-07 | 2019-11-07 | 2015-09-01 |  | ضعف كفاءة المقاول الفنية |  | 46.2625 | 24.4796 | منجز | Yes
2100198870 | وزارة الحرس الوطني / وكالة الشؤون الفنية | توريد وتركيب | ذات اولوية متوسطة | 1054665 | 52733.25 | 0 | 0 | 4030141707 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 0 | 0 | 2021-10-24 | 2021-12-22 | 2022-12-15 | 2022-12-15 |  |  |  | أخرى | 46.6759 | 24.71 | مسحوب | No
2100028722 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 28820706.51 | 1441035.3255 | 21674851.847 | 0 | 1010168999 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 96 | 100 | 2015-04-20 | 2017-04-09 | 2019-09-22 | 2019-09-22 | 2017-04-09 |  | ضعف كفاءة المقاول الفنية |  | 46.6898 | 24.6976 | منجز | Yes
2100045824 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3414500 | 170725 | 914106 | 0 | 1122002403 | لا | 0 |  | جاري | تكلفة العمل المنجز | 27 | 75 | 2018-05-23 | 2019-11-14 | 2019-11-13 | 2019-11-13 |  |  |  |  | 46.6782 | 24.7044 | Failed | Yes
2200231626 | وزارة الحرس الوطني / وكالة الشؤون الفنية | توريد وتركيب | ذات اولوية متوسطة | 2944988.6 | 147249.43 | 410639.06 | 0 | 1132010120 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 26 | 53 | 2022-06-08 | 2023-05-28 | 2023-05-28 | 2023-05-28 |  |  |  |  | 46.6771 | 24.7063 | Failed | Yes
2100082596 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1603250 | 80162.5 | 323835.6 | 0 | 1115001965 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 91 | 67 | 2019-01-06 | 2020-12-26 | 2020-12-26 | 2020-12-26 | 2020-12-26 |  |  |  | 46.6782 | 24.7082 | منجز | Yes
2100030936 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 25838830 | 1291941.5 | 8702897.14 | 0 | 1017000207 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2012-02-19 | 2014-08-07 | 2020-04-05 | 2020-04-05 | 2014-08-07 |  | ضعف كفاءة المقاول الفنية |  | 46.6871 | 24.6963 | منجز | Yes
2100078352 | وزارة الصحة/ الاحساء | تشييد | ذات اولوية عالية | 3706299.81 | 185314.9905 | 3930899.84 | 3219375.03 | 2251002570 | لا | 0 | 201109313472 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 0 | 2019-12-22 | 2020-06-16 | 2021-12-17 | 2021-12-17 | 2020-06-16 |  | اخرى |  | 49.572 | 25.3299 | منجز | No
2100077641 | وزارة الداخلية / مديرية الأمن العام | تشييد | ذات اولوية متوسطة | 1854573 | 92728.65 | 1854573 | 1854573 | 4031190271 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-10-13 | 2020-10-13 | 2020-10-13 | 2020-10-13 | 2020-10-13 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.8056 | 21.3771 | منجز | No
2100047681 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 2643261 | 132163.05 | 2548329 | 2401379 | 2060024520 | لا | 0 | 200609143944 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 99 | 100 | 2018-09-14 | 2019-09-03 | 2019-09-03 | 2019-09-03 | 2019-09-03 |  |  |  | 50.1253 | 26.312 | منجز | No
2100015094 | وزارة الداخلية / مديرية الأمن العام | تشييد | ذات اولوية متوسطة | 1749400 | 87470 | 1749400 | 1749400 | 4032147988 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-09-04 | 2020-09-04 | 2020-09-04 | 2020-09-04 | 2020-09-04 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.809 | 19.3281 | منجز | No
2100040924 | وزارة الصحة/ الاحساء | تشييد | ذات اولوية عالية وعاجلة | 2491159 | 124557.95 | 1830090.15 | 1830090.15 | 1010265407 | لا | 0 | 191101039004 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 0 | 2019-12-07 | 2020-03-05 | 2020-03-05 | 2020-03-05 | 2020-03-05 |  | اخرى |  | 49.5948 | 25.3892 | منجز | No
2100040283 | وزارة الصحة/ الاحساء | تشييد | ذات اولوية عالية | 4433745.85 | 221687.2925 | 2281761.59 | 1999508.65 | 2251002570 | لا | 0 | 201109311534 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 50 | 50 | 2019-12-24 | 2020-06-23 | 2021-08-18 | 2021-08-18 | 2020-06-23 |  | اخرى |  | 49.613 | 25.3383 | منجز | No
2100029901 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3299064.9998 | 164953.25 | 2521362.5 | 0 | 1010056094 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 87 | 100 | 2015-03-05 | 2016-08-26 | 2016-08-26 | 2016-08-26 | 2016-08-26 |  | ضعف كفاءة المقاول الفنية |  | 46.6699 | 24.7157 | منجز | Yes
2100091980 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 27564960 | 1378248 | 28926123.05 | 26048201 | 2050001536 | لا | 0 | 190809071855 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-08-25 | 2017-04-06 | 2022-01-28 | 2022-01-28 | 2017-04-06 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 50.0794 | 26.3778 | منجز | No
2100032185 | وزارة الداخلية / مديرية الأمن العام | تشييد | ذات اولوية متوسطة | 996014.25 | 49800.7125 | 996014.25 | 996014.25 | 1131003889 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-09-15 | 2020-09-02 | 2019-06-19 | 2019-06-19 | 2020-09-02 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 40.0843 | 29.8458 | منجز | No
2100031975 | وزارة الداخلية / مديرية الأمن العام | تشييد | ذات اولوية متوسطة | 1636583.3 | 81829.165 | 1565954.85 | 1565954.85 | 1010134168 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-02-29 | 2021-08-29 | 2021-08-29 | 2021-08-29 | 2021-08-29 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 43.2148 | 21.8559 | منجز | No
2100027241 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 57522323 | 2876116.15 | 57498465.87 | 53153957 | 1010067433 | لا | 0 | 180601011624 | منجز – استلام ابتدائي | التكلفة المفوترة | 98 | 100 | 2018-12-01 | 2020-08-13 | 2022-02-11 | 2022-02-11 | 2020-08-13 |  |  |  | 50.0001 | 26.4142 | منجز | No
2100050680 | أمانة / جازان | تشييد | ذات اولوية عالية | 796800 | 39840 | 251880 | 251880 | 5950011294 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 70 | 100 | 2015-01-06 | 2016-01-02 | 2016-01-02 | 2016-01-02 |  |  | اخرى |  | 42.5389 | 17.2671 | مسحوب | No
2100026084 | أمانة / جازان | دراسة الجدوى | ذات اولوية متوسطة | 1668000 | 83400 | 1529000 | 1529000 | 5900028256 | لا | 0 | 180701019824 | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2018-08-27 | 2020-08-27 | 2020-08-27 | 2020-08-27 | 2020-08-27 |  | ضعف كفاءة المقاول الفنية |  |  |  | منجز | No
2100100074 | جامعة جازان | تشييد | ذات اولوية منخفضة | 50474767.5 | 2523738.375 | 11590934.94 | 11590934.94 | 2051001558 | لا | 0 | 190909088694 | جاري | الكميات التي تم تركيبها | 22 | 50 | 2015-07-30 | 2017-05-30 | 2024-01-01 | 2024-01-01 |  |  | المشروع ليس ذو أولوية في الوقت الحالي |  | 43.0169 | 17.0319 | Failed | No
2200213216 | وزارة الحرس الوطني / وكالة الشؤون الفنية | تحديث وتوريد | ذات اولوية متوسطة | 994750 | 49737.5 | 994750 | 715587.5 | 1010147111 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2021-12-07 | 2022-03-06 | 2022-07-25 | 2022-07-25 | 2022-03-06 |  |  |  | 46.6814 | 24.7088 | منجز | No
2100035243 | أمانة / جازان | تشييد | ذات اولوية عالية | 3998778 | 199938.9 | 2319366 | 2319366 | 5860008190 | لا | 0 | 191101275883 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-03-11 | 2020-03-05 | 2021-06-09 | 2021-06-09 | 2020-03-05 |  | ضعف كفاءة المقاول الفنية |  | 42.0257 | 17.7184 | منجز | No
2100045356 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3915500 | 195775 | 2427726 | 0 | 1010234015 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-02-15 | 2015-05-11 | 2019-11-02 | 2019-11-02 | 2015-05-11 |  | ضعف كفاءة المقاول الفنية |  | 46.6761 | 24.7013 | منجز | Yes
2100040552 | وزارة الصحة/ الاحساء | تشييد | ذات اولوية عالية وعاجلة | 81449952 | 4072497.6 | 49539859 | 47227024.2 | 1010162957 | لا | 0 | 201009147034 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 0 | 2015-09-15 | 2018-06-07 | 2020-07-15 | 2020-07-15 | 2018-06-07 |  | اخرى |  | 49.5607 | 25.3583 | منجز | No
2100106805 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية وعاجلة | 73362831.54 | 3668141.577 | 65897558.36 | 65897558.36 | 1010004739 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2014-11-06 | 2016-10-27 | 2019-03-18 | 2019-03-18 | 2016-10-27 |  | تأخرصرف المستحقات المالية |  | 24.6867 | 46.6535 | منجز | No
2100064116 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية وعاجلة | 608409250.01 | 30420462.5005 | 432566242.1 | 432566242.1 | 1010004739 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2014-09-01 | 2016-08-20 | 2020-09-29 | 2020-09-29 | 2016-08-20 |  | تأخرصرف المستحقات المالية |  | 24.8772 | 46.9279 | منجز | No
2100034145 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 16417027 | 820851.35 | 16412159.17 | 14530567.5 | 2050041707 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2019-03-24 | 2020-03-12 | 2021-04-05 | 2021-04-05 | 2020-03-12 |  |  |  | 50.0953 | 26.4059 | منجز | No
2100067012 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 16238985 | 811949.25 | 16155428 | 14614275 | 2060024520 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 95 | 100 | 2019-05-05 | 2020-10-17 | 2020-10-17 | 2020-10-17 | 2020-10-17 |  |  |  | 50.1078 | 26.3791 | منجز | No
2100101614 | وزارة الصحة/ الاحساء | الخدمات الاستشارية | ذات اولوية متوسطة | 4686000 | 234300 | 3922822.58 | 3791791.57 | 7009554440 | لا | 0 | 201109385075 | جاري | تكلفة العمل المنجز | 100 | 10 | 2019-07-27 | 2022-01-26 | 2023-06-19 | 2023-06-19 |  |  | اخرى |  | 49.5607 | 25.3583 | خدمات عامة | No
2100060351 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية وعاجلة | 593542584.78 | 29677129.239 | 483486382.38 | 483486382.38 | 1010004739 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2014-02-17 | 2016-02-07 | 2019-07-21 | 2019-07-21 | 2016-02-07 |  | تأخرصرف المستحقات المالية |  | 24.8736 | 46.9229 | منجز | No
2100059220 | المركز الوطني لتنمية الحياة الفطرية | تشييد | ذات اولوية متوسطة | 420000 | 21000 | 236145 | 236145 | 1010102014 | لا | 0 | 180809039015 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-04-22 | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 |  | لا يوجد تأخير |  | 40.4585 | 27.3145 | منجز | No
2100076226 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 14890260 | 744513 | 14890260 | 14890260 | 2050018628 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 95 | 100 | 2019-12-05 | 2020-11-23 | 2021-03-04 | 2021-03-04 | 2020-11-23 |  | أوامر تغيير |  | 50.0929 | 26.3988 | منجز | No
2100087662 | جامعة أم القرى | تشييد | ذات اولوية عالية وعاجلة | 180077177.45 | 9003858.8725 | 106817843.55 | 106817843.55 | 1010152417 | لا | 0 | 181009150901 | مسحوب | تكلفة العمل المنجز | 68 | 100 | 2006-05-10 | 2009-04-07 | 2024-03-31 | 2024-03-31 |  |  |  | مخطط لسحبه وإعادة ترسيته | 39.9398 | 21.3347 | مسحوب | No
2100098372 | جامعة أم القرى | تشييد | ذات اولوية عالية وعاجلة | 158852822 | 7942641.1 | 55441501.03 | 55441501.03 | 1010152417 | لا | 0 | 181009161679 | مسحوب | تكلفة العمل المنجز | 47 | 100 | 2008-01-05 | 2010-12-02 | 2024-03-31 | 2024-03-31 |  |  |  | مخطط لسحبه وإعادة ترسيته | 39.9398 | 21.3347 | مسحوب | No
2100086892 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية وعاجلة | 195816419.87 | 9790820.9935 | 72693068.65 | 72693068.65 | 4031041927 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 45.36 | 100 | 2016-04-18 | 2018-04-18 | 2023-12-31 | 2023-12-31 |  |  | عدم وجود مبالغ في البنود تغطي الأعمال المرصودة | مخطط لسحبه وإعادة ترسيته | 39.8769 | 21.4016 | Failed | No
2100106223 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية وعاجلة | 222484820.57 | 11124241.0285 | 172843561.33 | 172843561.33 | 1010152417 | لا | 0 |  | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 99.17 | 100 | 2014-06-25 | 2016-06-14 | 2023-06-29 | 2023-06-29 |  |  | تأخرصرف المستحقات المالية | أخرى | 28.4874 | 36.499 | متأخر | No
2100001901 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية وعاجلة | 198488152.07 | 9924407.6035 | 159515780.6 | 159515780.6 | 1010152417 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2014-06-19 | 2016-06-08 | 2020-10-19 | 2020-10-19 | 2016-06-08 |  | تأخرصرف المستحقات المالية |  | 24.866 | 46.5711 | منجز | No
2100089832 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية وعاجلة | 144125832.48 | 7206291.624 | 83737686.36 | 83737686.36 | 1010152417 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2014-10-13 | 2016-10-01 | 2022-07-31 | 2022-07-31 | 2016-10-01 |  | تأخرصرف المستحقات المالية |  | 30.9307 | 41.0606 | منجز | No
2100041790 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية وعاجلة | 160433113.75 | 8021655.6875 | 18156659.85 | 17631005.07 | 1010152417 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 25.32 | 100 | 2017-10-22 | 2019-10-13 | 2023-12-31 | 2023-12-31 |  |  | تأخرصرف المستحقات المالية |  | 21.8845 | 39.116 | Failed | No
2100011266 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية وعاجلة | 162676559.04 | 8133827.952 | 90819807.88 | 89457325.67 | 1010152417 | لا | 0 |  | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 91.76 | 100 | 2013-11-14 | 2015-11-03 | 2023-04-30 | 2023-04-30 |  |  | تأخرصرف المستحقات المالية | أخرى | 26.2812 | 50.221 | متأخر | No
2100099890 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية وعاجلة | 614082201.91 | 30704110.0955 | 351680220.56 | 348307457.03 | 1010152417 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 88.48 | 100 | 2014-10-20 | 2016-10-09 | 2023-12-31 | 2023-12-31 |  |  | تأخرصرف المستحقات المالية | أخرى | 24.877 | 46.5442 | متأخر | No
2100064411 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية وعاجلة | 611833837.54 | 30591691.877 | 416450461.98 | 413592364.35 | 1010152417 | لا | 0 |  | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 94.93 | 100 | 2014-02-16 | 2016-02-06 | 2023-09-30 | 2023-09-30 |  |  | تأخرصرف المستحقات المالية | أخرى | 24.8889 | 46.9354 | متأخر | No
2100066183 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 4862477 | 243123.85 | 4744624.12 | 4706276.44 | 2050041707 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 95 | 100 | 2019-05-27 | 2021-05-04 | 2021-08-27 | 2021-08-27 | 2021-05-04 | 2022-12-01 |  |  | 50.0647 | 26.2589 | منجز | No
2300238066 | رئاسة أمن الدولة / الإدارة العامة للشؤون الفنية | تشييد | ذات اولوية عالية | 38448576.63 | 1922428.8315 | 0 | 0 | 0 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 0 | 0 | 2022-12-18 | 2024-12-18 | 2024-12-18 | 2024-12-18 | [6 empty] | منتظم | No
2100040946 | أمانة / عسير | دراسة بيئية | ذات اولوية عالية | 19494000 | 974700 | 15914879 | 15914879 | 1010312533 | لا | 0 |  | جاري | تكلفة العمل المنجز | 95 | 100 | 2019-03-24 | 2022-02-17 | 2023-03-31 | 2023-03-31 |  |  | التنسيق مع أصحاب المصلحه (خدمات |  | 42.7302 | 18.3003 | خدمات عامة | No
2100075876 | أمانة / عسير | تشييد | ذات اولوية عالية | 4000000 | 200000 | 0 | 0 | 5855022244 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 86 | 100 | 2014-11-29 | 2015-11-25 | 2021-10-15 | 2021-10-15 |  |  | تأخرصرف المستحقات المالية |  | 43.1308 | 18.0789 | مسحوب | No
2100039233 | وزارة الداخلية / مديرية الأمن العام | تشييد | ذات اولوية متوسطة | 7200711 | 360035.55 | 3800638.91 | 3800638.91 | 1010243700 | لا | 0 |  | جاري | تكلفة العمل المنجز | 58 | 80 | 2020-02-02 | 2021-04-02 | 2021-04-02 | 2021-04-02 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 40.2641 | 21.3657 | Failed | No
2100057890 | وزارة الحرس الوطني / الشؤون الصحية | تشييد | ذات اولوية عالية | 74946025.97 | 3747301.2985 | 56062430.02 | 56062430.02 | 1010057263 | لا | 0 | 181109332160 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-12-16 | 2020-11-22 | 2022-01-24 | 2022-01-24 | 2020-11-22 |  |  |  | 46.8599 | 24.7457 | منجز | No
2100076521 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 937350 | 46867.5 | 0 | 0 | 3350017944 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-12-16 | 2019-12-10 | 2021-09-14 | 2021-09-14 | 2019-12-10 |  |  |  | 42.1292 | 26.4801 | منجز | No
2100046874 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1589979 | 79498.95 | 980241.15 | 0 | 1130003142 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 91 | 100 | 2015-01-04 | 2016-03-29 | 2016-03-29 | 2016-03-29 | 2016-03-29 |  | ضعف كفاءة المقاول الفنية |  | 43.2884 | 24.335 | منجز | Yes
2100091545 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 32147750 | 1607387.5 | 1710500 | 0 | 1010101252 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 26 | 10 | 2019-03-31 | 2021-09-16 | 2022-07-08 | 2022-07-08 |  |  |  |  | 47.1471 | 23.9776 | Failed | Yes
2100062823 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 20251562 | 1012578.1 | 10960306.6145 | 0 | 1115001486 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2011-10-08 | 2014-03-26 | 2020-04-20 | 2020-04-20 | 2014-03-26 |  | ضعف كفاءة المقاول الفنية |  | 46.6864 | 24.7007 | منجز | Yes
2100065726 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 45671949 | 2283597.45 | 34264415.48 | 0 | 1116005202 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 91.6 | 100 | 2013-07-20 | 2015-07-10 | 2019-10-22 | 2019-10-22 | 2015-07-10 |  | ضعف كفاءة المقاول الفنية |  | 46.5321 | 24.7486 | منجز | Yes
2100060034 | وزارة التعليم | تشييد | ذات اولوية عالية | 2234696 | 111734.8 | 286144.08 | 0 | 4700009573 | لا | 0 |  | مسحوب | التكلفة المفوترة | 40 | 100 | 2015-04-21 | 2016-03-06 | 2022-11-22 | 2022-11-22 |  |  | ضعف كفاءة المقاول الفنية |  | 38.0623 | 24.0861 | مسحوب | Yes
2100102325 | أمانة / الرياض | دراسة الجدوى | ذات اولوية متوسطة | 12165372 | 608268.6 | 41701 | 0 | 1010325651 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-08-07 | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 |  | اخرى |  |  |  | منجز | Yes
2100042254 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1281901 | 64095.05 | 574694 | 574694 | 3556000177 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 65 | 100 | 2007-10-19 | 2008-08-10 | 2021-08-27 | 2021-08-27 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | مسحوب | No
2100045220 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3089400 | 154470 | 2038696.37 | 0 | 1113000601 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 66 | 100 | 2015-04-19 | 2016-07-12 | 2020-03-15 | 2020-03-15 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6672 | 24.7057 | مسحوب | Yes
2100044144 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 17172438.5 | 858621.925 | 7833422.45 | 0 | 1010010466 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 98 | 100 | 2013-05-11 | 2015-05-01 | 2019-09-11 | 2019-09-11 | 2015-05-01 |  | ضعف كفاءة المقاول الفنية |  | 46.674 | 24.7094 | منجز | Yes
2100075460 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 5186400 | 259320 | 0 | 0 | 1017000207 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 64 | 80 | 2012-02-19 | 2014-08-07 | 2019-12-31 | 2019-12-31 | 2014-08-07 |  | ضعف كفاءة المقاول الفنية |  | 47.1598 | 23.9747 | منجز | No
2100074115 | أمانة / الرياض | دراسة الجدوى | ذات اولوية متوسطة | 995085 | 49754.25 | 0 | 0 | 1010560103 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 36 | 2018-12-20 | 2020-06-20 | 2022-01-09 | 2022-01-09 | 2020-06-20 |  | ضعف كفاءة المقاول الفنية |  |  |  | منجز | No
2100089703 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 47108754 | 2355437.7 | 39813700.6149 | 0 | 1010171813 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 97.36 | 100 | 2014-01-11 | 2016-01-01 | 2019-12-17 | 2019-12-17 | 2016-01-01 |  | ضعف كفاءة المقاول الفنية |  | 44.3812 | 24.4944 | منجز | Yes
2100018620 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1449273 | 72463.65 | 0 | 0 | 1011015729 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 18 | 2019-04-10 | 2020-07-03 | 2020-07-03 | 2020-07-03 | 2020-07-03 |  |  |  | 45.4651 | 25.0665 | منجز | No
2100035921 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 9583146.23 | 479157.3115 | 2575255.4 | 2575255.4 | 1010213931 | لا | 0 |  | مسحوب | التكلفة المفوترة | 70 | 100 | 2014-03-17 | 2016-03-07 | 2023-01-15 | 2023-01-15 |  |  | ضعف كفاءة المقاول الفنية |  | 40.0549 | 29.8587 | مسحوب | No
2100048090 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2779034 | 138951.7 | 2192707 | 2192707 | 3981115687 | لا | 0 |  | مسحوب | التكلفة المفوترة | 80 | 100 | 2005-05-10 | 2007-01-28 | 2022-06-15 | 2022-06-15 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0165 | 30.9619 | مسحوب | No
2100063674 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 56528979 | 2826448.95 | 44258573.5637 | 0 | 1010171813 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2013-08-01 | 2015-07-22 | 2019-01-12 | 2019-01-12 | 2015-07-22 |  | ضعف كفاءة المقاول الفنية |  | 46.6644 | 24.7094 | منجز | Yes
2100071680 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 6733459.15 | 336672.9575 | 2711294.9 | 2711294.9 | 1010213931 | لا | 0 |  | مسحوب | التكلفة المفوترة | 52 | 100 | 2014-03-19 | 2015-12-11 | 2023-06-15 | 2023-06-15 |  |  | ضعف كفاءة المقاول الفنية |  | 40.0549 | 29.8587 | مسحوب | No
2100102841 | أمانة / الرياض | دراسة الجدوى | ذات اولوية عالية | 5047000 | 252350 | 0 | 0 | 1010415802 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2010-03-12 | 2012-03-01 | 2012-03-01 | 2012-03-01 | 2012-03-01 |  | اخرى |  |  |  | منجز | No
2100008912 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 10665044.51 | 533252.2255 | 2786506.24 | 0 | 4650020435 | لا | 0 |  | مسحوب | التكلفة المفوترة | 43 | 100 | 2015-07-26 | 2017-07-16 | 2023-11-15 | 2023-11-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | Yes
2100017415 | وزارة التعليم | تشييد | ذات اولوية عالية | 21499750 | 1074987.5 | 16390124.93 | 16390124.93 | 1010178838 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-03-22 | 2017-06-10 | 2019-07-21 | 2019-07-21 | 2017-06-10 |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | منجز | No
2100089736 | وزارة التعليم | تشييد | ذات اولوية عالية | 9209469 | 460473.45 | 1290883 | 994824 | 4650049177 | لا | 0 |  | مسحوب | التكلفة المفوترة | 36 | 100 | 2017-10-03 | 2019-12-23 | 2023-06-15 | 2023-06-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | No
2100001772 | وزارة التعليم | تشييد | ذات اولوية عالية | 14136334.92 | 706816.746 | 2582499.59 | 2386755.1 | 4030288443 | لا | 0 |  | مسحوب | التكلفة المفوترة | 25 | 100 | 2015-01-22 | 2017-01-11 | 2023-06-15 | 2023-06-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | No
2100086144 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 11546525 | 577326.25 | 3357430 | 3357430 | 1117000834 | لا | 0 |  | مسحوب | التكلفة المفوترة | 29 | 100 | 2006-01-08 | 2008-06-01 | 2013-02-08 | 2013-02-08 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | مسحوب | No
2100032244 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 60967268.24 | 3048363.412 | 19573585.2 | 0 | 1116001737 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2013-08-01 | 2015-07-22 | 2019-12-27 | 2019-12-27 | 2015-07-22 |  | ضعف كفاءة المقاول الفنية |  | 46.674 | 24.7019 | منجز | Yes
2100074686 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2191903 | 109595.15 | 0 | 0 | 3434987105 | لا | 0 |  | جاري | التكلفة المفوترة | 2 | 100 | 2014-03-18 | 2015-02-01 | 2023-06-15 | 2023-06-15 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0165 | 30.9619 | Failed | No
2100013484 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2285872 | 114293.6 | 2285872 | 0 | 1010242793 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-08-19 | 2018-09-12 | 2018-09-12 | 2018-09-12 | 2018-09-12 |  |  |  | 46.6823 | 24.7181 | منجز | Yes
2100003161 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 4331136 | 216556.8 | 0 | 0 | 1132000522 | لا | 0 |  | جاري | التكلفة المفوترة | 1 | 100 | 2013-05-31 | 2014-11-23 | 2024-01-15 | 2024-01-15 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | Failed | No
2100044612 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 7168630 | 358431.5 | 4243034.04 | 0 | 1115001486 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2011-06-24 | 2013-06-13 | 2020-01-15 | 2020-01-15 | 2013-06-13 |  | ضعف كفاءة المقاول الفنية |  | 46.6809 | 24.7144 | منجز | Yes
2100065063 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 5293350 | 264667.5 | 41518 | 0 | 1010272491 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 27 | 100 | 2014-02-09 | 2017-06-07 | 2017-06-08 | 2017-06-08 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6644 | 24.7194 | مسحوب | Yes
2100044133 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 19562223 | 978111.15 | 7198612.59 | 0 | 1116001737 | لا | 0 |  | جاري | تكلفة العمل المنجز | 71 | 100 | 2015-08-08 | 2017-07-28 | 2020-05-06 | 2020-05-06 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6809 | 24.7157 | Failed | Yes
2100095491 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2798615 | 139930.75 | 4593038.01 | 4593038.01 | 1010195827 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 27 | 100 | 2014-10-27 | 2018-07-26 | 2022-11-26 | 2022-11-26 |  |  | تأخرصرف المستحقات المالية |  | 44.602 | 25.1859 | Failed | No
2100086284 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 10910220.21 | 545511.0105 | 1664460 | 1664460 | 4031033277 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 17 | 100 | 2015-05-09 | 2017-04-29 | 2023-12-15 | 2023-12-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | No
2100096272 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 8514639.6 | 425731.98 | 3484648.93 | 0 | 4650020435 | لا | 0 |  | مسحوب | التكلفة المفوترة | 91 | 100 | 2013-01-26 | 2014-10-20 | 2023-01-15 | 2023-01-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | Yes
2100108124 | وزارة التعليم | تشييد | ذات اولوية عالية | 5186118 | 259305.9 | 371550 | 371550 | 1010001374 | لا | 0 |  | مسحوب | التكلفة المفوترة | 8 | 100 | 2008-02-12 | 2009-12-04 | 2024-01-15 | 2024-01-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | No
2100043676 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1120750 | 56037.5 | 41743 | 0 | 1010045354 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 60.7 | 100 | 2014-08-02 | 2015-07-28 | 2021-06-20 | 2021-06-20 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 43.0069 | 24.0139 | Failed | Yes
2100043201 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 5527946 | 276397.3 | 3448097.35 | 0 | 1116001737 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 90 | 100 | 2012-05-06 | 2014-04-26 | 2021-04-14 | 2021-04-14 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6692 | 24.7063 | Failed | Yes
2100010183 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 4448832 | 222441.6 | 0 | 0 | 1010386456 | لا | 0 |  | مسحوب | التكلفة المفوترة | 86 | 100 | 2004-09-18 | 2006-09-09 | 2012-04-25 | 2012-04-25 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | مسحوب | No
2100071772 | أمانة / عسير | تشييد | ذات اولوية عالية | 1673033 | 83651.65 | 1467601.3 | 1467601.3 | 1010191831 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 84 | 100 | 2010-07-22 | 2011-07-17 | 2020-10-01 | 2020-10-01 |  |  | ضعف كفاءة المقاول الفنية |  | 42.179 | 18.9518 | مسحوب | No
2100071481 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 407892 | 20394.6 | 407892 | 381172.2 | 4030222353 | لا | 0 | 181101268670 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-04-24 | 2016-12-24 | 2016-12-25 | 2016-12-25 | 2016-12-24 |  | اخرى |  | 37.6915 | 28.3763 | منجز | No
2100072284 | أمانة / جازان | تشييد | ذات اولوية عالية | 7186225.6 | 359311.28 | 7186225.6 | 7186225.6 | 5900007895 | لا | 0 | 180809055806 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-11-30 | 2015-11-25 | 2019-12-31 | 2019-12-31 | 2015-11-25 |  | اخرى |  | 42.8426 | 16.9691 | منجز | No
2300238184 | أمانة / القصيم | تشييد | ذات اولوية متوسطة | 1705000 | 85250 | 150000 | 150000 | 1129000453 | لا | 0 |  | جاري | تكلفة العمل المنجز | 30 | 30 | 2022-10-15 | 2023-08-10 | 2023-08-10 | 2023-08-10 |  |  |  |  | 43.9875 | 26.0907 | منتظم | No
2300238243 | وزارة الداخلية / المديرية العامة لحرس الحدود | تشييد | ذات اولوية عالية | 552695.75 | 27634.7875 | 0 | 0 | 4031193206 | لا | 0 |  | جاري | تكلفة العمل المنجز | 5 | 33 | 2022-11-10 | 2023-05-10 | 2023-05-10 | 2023-05-10 |  |  |  |  | 39.1925 | 21.4858 | Failed | No
2100024463 | جامعة طيبة | تشييد | ذات اولوية عالية | 170040954 | 8502047.7 | 61228115 | 59667776.87 | 4030068284 | لا | 0 | 181009174305 | جاري | تكلفة العمل المنجز | 38.98 | 90 | 2013-01-13 | 2015-01-03 | 2024-12-01 | 2024-12-01 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال | تم إنذار المقاول كتابيا | 39.6005 | 24.4595 | Failed | No
2100067734 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 23439567.24 | 1171978.362 | 17985979 | 17985979 | 1010056526 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 98 | 100 | 2012-03-30 | 2014-08-14 | 2022-06-15 | 2022-06-15 | 2014-08-14 |  | ضعف كفاءة المقاول الفنية |  | 40.0549 | 29.8587 | منجز | No
2100107612 | جامعة طيبة | تشييد | ذات اولوية عالية وعاجلة | 486565097 | 24328254.85 | 136890624.7 | 136274296.04 | 2050005846 | لا | 0 | 181109377104 | جاري | تكلفة العمل المنجز | 30 | 100 | 2012-04-22 | 2015-05-07 | 2025-12-01 | 2025-12-01 |  |  | منازعات قائمة | تم تمديد الجدول الزمني | 39.6005 | 24.4595 | Failed | No
2100025303 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2607696 | 130384.8 | 927155.52 | 927155.52 | 3552000894 | لا | 0 |  | جاري | التكلفة المفوترة | 40 | 100 | 2014-11-11 | 2016-02-05 | 2023-12-15 | 2023-12-15 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | Failed | No
2200236784 | وزارة الداخلية /الأحوال المدنية | تشييد | ذات اولوية عالية وعاجلة | 946202.25 | 47310.1125 | 0 | 0 | 5950004276 | لا | 0 |  | ايقاف جزئي | تكلفة العمل المنجز | 33 | 100 | 2022-05-11 | 2022-08-08 | 2023-03-01 | 2023-03-01 |  |  |  | تم إنذار المقاول كتابيا | 46.7198 | 22.2962 | Failed | No
2100015153 | وزارة التعليم | تشييد | ذات اولوية عالية | 14699160 | 734958 | 13565313.5 | 13565313.5 | 1116002219 | لا | 0 |  | جاري | التكلفة المفوترة | 100 | 100 | 2011-09-07 | 2013-08-27 | 2013-08-27 | 2013-08-27 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | Failed | No
2100019025 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 11622287 | 581114.35 | 10227323.83 | 6887227.68 | 1010060469 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-12-21 | 2017-12-11 | 2019-03-20 | 2019-03-20 | 2017-12-11 |  |  |  | 39.6005 | 24.4595 | منجز | No
2200236762 | وزارة الداخلية /الأحوال المدنية | تشييد | ذات اولوية عالية وعاجلة | 1090708 | 54535.4 | 435149.3 | 0 | 3450010904 | لا | 0 |  | ايقاف جزئي | تكلفة العمل المنجز | 60 | 100 | 2022-04-06 | 2022-08-04 | 2023-04-01 | 2023-04-01 |  |  |  | تم إنذار المقاول كتابيا | 40.1896 | 29.9646 | Failed | Yes
2100001853 | وزارة التعليم | تشييد | ذات اولوية عالية | 19587208.13 | 979360.4065 | 3255781.88 | 2909675 | 4030288443 | لا | 0 |  | مسحوب | التكلفة المفوترة | 42 | 100 | 2015-06-08 | 2017-08-27 | 2023-12-15 | 2023-12-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | No
2100082110 | وزارة الصحة / تبوك | ترميم | ذات اولوية عالية | 25767416 | 1288370.8 | 9062124 | 9062124 | 1010133046 | لا | 0 | 200309018375 | جاري | الكميات التي تم تركيبها | 100 | 100 | 2020-03-14 | 2021-07-10 | 2022-09-26 | 2022-09-26 |  |  | موافقات |  | 36.5429 | 28.3967 | متأخر | No
2100060480 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 1999845 | 99992.25 | 177290.4 | 177290.4 | 3450008768 | لا | 0 |  | مسحوب | التكلفة المفوترة | 11 | 100 | 2007-07-02 | 2008-05-17 | 2010-08-29 | 2010-08-29 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0165 | 30.9619 | مسحوب | No
2100060616 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 7776135.36 | 388806.768 | 6591087.1 | 6591087.1 | 1010456278 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-05-20 | 2017-05-09 | 2020-07-08 | 2020-07-08 | 2017-05-09 |  | ضعف كفاءة المقاول الفنية |  | 57.3008 | 41.1583 | منجز | No
2100193200 | وزارة الحرس الوطني / وكالة الشؤون الفنية | تشييد | ذات اولوية متوسطة | 1379821.75 | 68991.0875 | 1379821.75 | 1379821.75 | 1010495829 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2021-01-24 | 2022-01-13 | 2022-01-13 | 2022-01-13 | 2022-01-13 |  |  |  | 44.2278 | 17.5617 | منجز | No
2100041915 | وزارة الداخلية / ديوان وزارة الداخلية | تصميم وتشييد | ذات اولوية عالية وعاجلة | 799967614.73 | 39998380.7365 | 9090020.37 | 9090020.37 | 1010254468 | لا | 0 | 180809053588 | ايقاف كلي | منهجية القيمة المكتسبة | 2 | 100 | 2016-10-18 | 2019-05-04 | 2025-06-30 | 2025-06-30 |  |  | تأخرصرف المستحقات المالية | أخرى | 55.3727 | 22.1995 | Failed | No
2100012110 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 3091500 | 154575 | 0 | 0 | 4650037722 | لا | 0 |  | جاري | التكلفة المفوترة | 1 | 100 | 2015-11-02 | 2017-01-25 | 2022-12-30 | 2022-12-30 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | Failed | No
2100077103 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 6182404.5 | 309120.225 | 2642049 | 2642049 | 3350000614 | لا | 0 | 180501010056 | جاري | الكميات التي تم تركيبها | 61 | 100 | 2018-07-31 | 2020-01-21 | 2022-06-30 | 2022-06-30 |  |  | تأخرصرف المستحقات المالية |  | 42.4056 | 27.9057 | Failed | No
2100098965 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 3714799.07 | 185739.9535 | 1655221 | 1655221 | 3350000614 | لا | 0 | 190709111872 | جاري | الكميات التي تم تركيبها | 54 | 100 | 2019-05-05 | 2020-01-30 | 2022-03-31 | 2022-03-31 |  |  | تأخرصرف المستحقات المالية |  | 42.4135 | 27.8869 | Failed | No
2200219682 | وزارة الداخلية / المديرية العامة لحرس الحدود | ترميم | ذات اولوية عالية | 2295126.3 | 114756.315 | 2295126.3 | 2295126.3 | 1010393545 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2022-02-09 | 2022-08-09 | 2022-08-09 | 2022-08-09 | 2022-08-09 |  |  |  | 39.859 | 21.3833 | منجز | No
2300238092 | وزارة الصحة | ترميم | ذات اولوية متوسطة | 2375210 | 118760.5 | 0 | 0 | 1131028904 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 5 | 10 | 2022-12-04 | 2023-04-01 | 2023-04-01 | 2023-04-01 |  |  |  |  | 43.9702 | 26.3487 | منتظم | No
2300238103 | أمانة / القصيم | تشييد | ذات اولوية متوسطة | 1377000 | 68850 | 200000 | 200000 | 1131010033 | لا | 0 |  | جاري | تكلفة العمل المنجز | 31 | 31 | 2022-10-30 | 2023-06-26 | 2023-06-26 | 2023-06-26 |  |  |  |  | 43.4741 | 26.7709 | منتظم | No
2300238081 | أمانة / القصيم | تشييد | ذات اولوية متوسطة | 1000000 | 50000 | 200000 | 200000 | 1010696362 | لا | 0 |  | جاري | تكلفة العمل المنجز | 47 | 47 | 2022-10-19 | 2023-04-16 | 2023-04-16 | 2023-04-16 |  |  |  |  | 42.6798 | 26.0525 | منتظم | No
2300238210 | وزارة الداخلية / المديرية العامة لحرس الحدود | ترميم | ذات اولوية عالية | 383500 | 19175 | 0 | 0 | 4030168691 | لا | 0 |  | جاري | تكلفة العمل المنجز | 0 | 45 | 2022-10-18 | 2023-04-18 | 2023-04-18 | 2023-04-18 |  |  |  |  | 39.019 | 22.7907 | Failed | No
2300238114 | وزارة الصحة | ترميم | ذات اولوية متوسطة | 837035.55 | 41851.7775 | 0 | 0 | 2057006592 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 1 | 5 | 2022-12-01 | 2023-06-01 | 2023-09-03 | 2023-09-03 |  |  |  |  | 43.9421 | 26.3711 | منتظم | No
2100016015 | وزارة الداخلية / ديوان وزارة الداخلية | تصميم وتشييد | ذات اولوية عالية وعاجلة | 719805416.14 | 35990270.807 | 432585376.96 | 432585376.96 | 1010254468 | لا | 0 | 180809053588 | جاري | منهجية القيمة المكتسبة | 63.06 | 100 | 2015-11-23 | 2018-10-05 | 2023-02-23 | 2023-02-23 |  |  | تأخرصرف المستحقات المالية | تم تمديد الجدول الزمني | 50.7469 | 24.8128 | Failed | No
2100078046 | معهد الإدارة العامة | تصميم | ذات اولوية عالية وعاجلة | 1900000 | 95000 | 199950 | 199950 | 1010322156 | لا | 0 | 181009216168 | جاري | التكلفة المفوترة | 10.5 | 100 | 2018-06-10 | 2018-10-27 | 2023-12-01 | 2023-12-01 |  |  |  |  | 50.1169 | 26.4266 | Failed | No
2100199301 | وزارة الداخلية / المديرية العامة لحرس الحدود | توريد | ذات اولوية عالية | 1276500 | 63825 | 1276500 | 1276500 | 5855340104 | لا | 0 | 210901125172 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2021-09-27 | 2022-03-27 | 2022-03-23 | 2022-03-23 | 2022-03-27 |  |  |  | 44.2289 | 17.5656 | منجز | No
2100019530 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 699932.77 | 34996.6385 | 57797.68 | 57797.68 | 3550027826 | نعم | 57798 | 210201047697 | مسحوب | تكلفة العمل المنجز | 8 | 100 | 2015-10-31 | 2016-10-25 | 2021-11-04 | 2021-11-04 |  |  | ضعف كفاءة المقاول الفنية |  | 37.6847 | 28.3938 | مسحوب | No
2300238140 | أمانة / القصيم | تشييد | ذات اولوية متوسطة | 3523941.77 | 176197.0885 | 400000 | 200000 | 1135000671 | لا | 0 |  | جاري | تكلفة العمل المنجز | 8 | 8 | 2022-11-27 | 2024-05-19 | 2024-05-19 | 2024-05-19 |  |  |  |  | 43.5415 | 26.0533 | منتظم | No
2200226015 | وزارة الداخلية / المديرية العامة لحرس الحدود | تشييد | ذات اولوية عالية | 453490 | 22674.5 | 138608.75 | 138608.75 | 1010603840 | لا | 0 | 220601244173 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 87 | 100 | 2022-05-11 | 2022-11-11 | 2022-11-11 | 2022-11-11 |  |  |  |  | 39.3206 | 29.8874 | Failed | No
2100045710 | أمانة / تبوك | تشييد | لم تعد تحتاجها الجهة | 1047375 | 52368.75 | 835231.67 | 835231.67 | 3250040776 | لا | 0 | 65001104853 | مسحوب | تكلفة العمل المنجز | 80 | 100 | 2015-10-28 | 2016-10-16 | 2020-10-17 | 2020-10-17 |  |  | ضعف كفاءة المقاول الفنية |  | 37.6847 | 28.3938 | مسحوب | No
2300238136 | وزارة الحرس الوطني / وكالة الشؤون الفنية | تشييد | ذات اولوية متوسطة | 31041415.94 | 1552070.797 | 0 | 0 | 1010032177 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 4 | 8 | 2022-11-06 | 2024-04-20 | 2024-04-20 | 2024-04-20 |  |  |  |  | 46.9218 | 24.669 | منتظم | No
2200233144 | وزارة الداخلية / المديرية العامة لحرس الحدود | تشييد | ذات اولوية عالية | 2547174.48 | 127358.724 | 120428 | 120428 | 5855057332 | لا | 0 |  | جاري | تكلفة العمل المنجز | 5 | 40 | 2022-08-18 | 2023-08-18 | 2023-08-18 | 2023-08-18 |  |  |  |  | 50.1971 | 26.2172 | Failed | No
2100047283 | أمانة / تبوك | تشييد | لم تعد تحتاجها الجهة | 1732635.65 | 86631.7825 | 360000 | 360000 | 3550027826 | لا | 0 | 181009140027 | مسحوب | الكميات التي تم تركيبها | 21 | 100 | 2015-04-28 | 2016-04-28 | 2020-12-15 | 2020-12-15 |  |  | اخرى |  | 37.6847 | 28.3938 | مسحوب | No
2300238162 | أمانة / القصيم | تشييد | ذات اولوية متوسطة | 2300000 | 115000 | 300000 | 300000 | 1129000453 | لا | 0 |  | جاري | تكلفة العمل المنجز | 30 | 30 | 2022-10-15 | 2023-08-10 | 2023-08-10 | 2023-08-10 |  |  |  |  | 43.9875 | 26.0907 | منتظم | No
2100110176 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية وعاجلة | 1044875056.94 | 52243752.847 | 645067597.65 | 645067597.65 | 1010014578 | لا | 0 | 180909089093 | جاري | مدفوعات ساعات العمل | 82.58 | 91.48 | 2010-06-28 | 2013-06-11 | 2024-12-31 | 2024-12-31 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | متأخر | No
2200233192 | وزارة الداخلية / المديرية العامة لحرس الحدود | ترميم | ذات اولوية عالية | 1661071.5 | 83053.575 | 754095.25 | 754095.25 | 5950006696 | لا | 0 |  | جاري | تكلفة العمل المنجز | 45 | 45 | 2022-08-14 | 2023-07-14 | 2023-07-14 | 2023-07-14 |  |  |  |  | 40.2782 | 20.1405 | منتظم | No
2100069392 | وزارة الداخلية / المديرية العامة لحرس الحدود | تشييد | ذات اولوية عالية | 299785.5 | 14989.275 | 299785.5 | 299785.5 | 1010151378 | لا | 0 | 200501053889 | مسحوب | تكلفة العمل المنجز | 25 | 100 | 2020-01-23 | 2020-04-01 | 2021-07-23 | 2021-07-23 |  |  | ضعف كفاءة المقاول الفنية |  | 50.1013 | 26.4524 | مسحوب | No
2100016074 | وزارة الداخلية / ديوان وزارة الداخلية | إشراف | ذات اولوية عالية وعاجلة | 825459921.78 | 41272996.089 | 753052647.81 | 731064745.14 | 1010348048 | لا | 0 | 201009080996 | جاري | مدفوعات ساعات العمل | 91.23 | 93 | 2010-09-19 | 2013-09-02 | 2024-12-31 | 2024-12-31 |  |  | اخرى |  |  |  | خدمات عامة | No
2100108780 | وزارة الحرس الوطني / وكالة الشؤون الفنية | تشييد | ذات اولوية متوسطة | 4347007.35 | 217350.3675 | 4238059.51 | 4238059.51 | 1010175017 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-12-24 | 2021-03-28 | 2022-02-27 | 2022-02-27 | 2021-03-28 |  |  |  | 43.5192 | 29.6274 | منجز | No
2100063501 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 988000 | 49400 | 0 | 0 | 3550027760 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 35 | 100 | 2015-10-03 | 2016-06-06 | 2016-06-07 | 2016-06-07 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | مسحوب | No
2100051004 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 4850880 | 242544 | 1096144.5 | 1096144.5 | 1010255485 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 27 | 100 | 2014-07-02 | 2015-09-15 | 2015-09-30 | 2015-09-30 |  |  | ضعف كفاءة المقاول الفنية |  | 36.6065 | 28.3923 | مسحوب | No
2300238206 | وزارة الصحة | ترميم | ذات اولوية متوسطة | 599380 | 29969 | 0 | 0 | 1010183991 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 20 | 40 | 2022-12-04 | 2023-03-03 | 2023-03-03 | 2023-03-03 |  |  |  |  | 43.5579 | 26.0494 | متأخر | No
2100080581 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 738720 | 36936 | 0 | 0 | 3562000009 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 15 | 100 | 2015-12-05 | 2016-11-29 | 2019-11-14 | 2019-11-14 |  |  | ضعف كفاءة المقاول الفنية |  | 35.0275 | 28.4746 | مسحوب | No
2100193211 | وزارة الحرس الوطني / وكالة الشؤون الفنية | تشييد | ذات اولوية متوسطة | 1335642.85 | 66782.1425 | 889880.95 | 889880.95 | 1010062992 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 78 | 90 | 2021-03-14 | 2022-06-19 | 2023-03-02 | 2023-03-02 |  |  |  | تم تمديد الجدول الزمني | 46.6747 | 24.7075 | Failed | No
2100082250 | أمانة / جازان | تشييد | ذات اولوية عالية | 1591220 | 79561 | 1591220 | 1591220 | 5907020632 | لا | 0 | 180909110824 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-02-18 | 2016-02-13 | 2019-07-05 | 2019-07-05 | 2016-02-13 |  | اخرى |  | 43.2146 | 16.7811 | منجز | No
2300238195 | وزارة الصحة | ترميم | ذات اولوية متوسطة | 264500 | 13225 | 0 | 0 | 1132105948 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 2 | 14 | 2022-12-09 | 2023-06-05 | 2023-06-05 | 2023-06-05 |  |  |  |  | 43.9922 | 26.1046 | متأخر | No
2100044236 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 1600950 | 80047.5 | 0 | 0 | 4030212516 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 35 | 100 | 2018-12-08 | 2020-06-01 | 2021-06-01 | 2021-06-01 |  |  | ضعف كفاءة المقاول الفنية |  | 36.4689 | 26.2366 | مسحوب | No
2100193163 | وزارة الحرس الوطني / وكالة الشؤون الفنية | تشييد | ذات اولوية متوسطة | 27118538.9 | 1355926.945 | 10251646.34 | 9521571.14 | 1010012674 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 53 | 57 | 2021-01-17 | 2022-07-03 | 2023-06-20 | 2023-06-20 |  |  |  | أخرى | 46.6679 | 24.7063 | منتظم | No
2100014420 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 1341891 | 67094.55 | 670137 | 670137 | 3553000067 | لا | 0 | 181009142203 | مسحوب | تكلفة العمل المنجز | 63 | 100 | 2014-10-11 | 2015-06-09 | 2021-08-30 | 2021-08-30 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5624 | 28.3871 | مسحوب | No
2100034974 | أمانة / جازان | تشييد | ذات اولوية متوسطة | 13814260 | 690713 | 6216417 | 6216417 | 5950010447 | لا | 0 | 181109362416 | جاري | الكميات التي تم تركيبها | 45 | 100 | 2011-01-15 | 2013-01-23 | 2022-03-30 | 2022-03-30 |  |  | اخرى |  | 42.6282 | 17.154 | Failed | No
2100063571 | المركز الوطني لتنمية الحياة الفطرية | تشييد | ذات اولوية عالية | 3095357 | 154767.85 | 452905 | 452905 | 1010287256 | لا | 0 | 190409026153 | مسحوب | الكميات التي تم تركيبها | 15 | 15 | 2014-11-24 | 2016-03-30 | 2016-03-30 | 2016-03-30 |  |  | ضعف كفاءة المقاول الفنية |  | 42.227 | 22.7013 | مسحوب | No
2100012644 | أمانة / عسير | تشييد | ذات اولوية عالية | 1517120 | 75856 | 1463745 | 1463745 | 5856006665 | لا | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 21 | 100 | 2012-08-05 | 2023-04-04 | 2023-04-04 | 2023-04-04 |  |  | أوامر سامية |  | 42.6915 | 18.5932 | Failed | No
2300238232 | وزارة الداخلية / المديرية العامة لحرس الحدود | تشييد | ذات اولوية عالية | 1509046 | 75452.3 | 0 | 0 | 4030168691 | لا | 0 |  | جاري | تكلفة العمل المنجز | 15 | 22 | 2022-11-10 | 2023-08-10 | 2023-08-10 | 2023-08-10 |  |  |  |  | 39.1925 | 21.4858 | متأخر | No
2100077162 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 66008509.32 | 3300425.466 | 28484569 | 26469480.04 | 1010136405 | لا | 0 | 180709022403 | فسخ العقد | تكلفة العمل المنجز | 51 | 100 | 2014-11-11 | 2016-10-19 | 2021-02-28 | 2021-02-28 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5899 | 28.3822 | مسحوب | No
2100043713 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 533300 | 26665 | 34800 | 34800 | 4030212516 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 60 | 100 | 2018-12-08 | 2019-12-03 | 2021-06-01 | 2021-06-01 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5801 | 28.4068 | مسحوب | No
2100012950 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 1341897 | 67094.85 | 308636 | 308636 | 3550027826 | لا | 308636 |  | مسحوب | تكلفة العمل المنجز | 23 | 100 | 2013-06-10 | 2014-06-15 | 2020-07-30 | 2020-07-30 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5778 | 28.3908 | مسحوب | No
2100068633 | أمانة / عسير | تشييد | ذات اولوية عالية | 2259430 | 112971.5 | 535804 | 520751.3 | 5859002900 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 27 | 100 | 2015-10-04 | 2016-09-28 | 2021-09-14 | 2021-09-14 |  |  | تأخرصرف المستحقات المالية |  |  |  | مسحوب | No
2100045253 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 1798500 | 89925 | 0 | 0 | 4030212516 | لا | 0 | 190409131919 | مسحوب | الكميات التي تم تركيبها | 5 | 100 | 2018-12-08 | 2019-12-03 | 2021-12-01 | 2021-12-01 |  |  | ضعف كفاءة المقاول الفنية |  | 36.4689 | 26.2366 | مسحوب | No
2300238254 | وزارة الصحة | ترميم | ذات اولوية متوسطة | 4834784 | 241739.2 | 0 | 0 | 1131002183 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 40 | 80 | 2022-09-06 | 2023-07-15 | 2023-07-15 | 2023-07-15 |  |  |  |  | 43.9803 | 26.327 | Failed | No
2100014232 | أمانة / عسير | تشييد | ذات اولوية عالية | 19994490 | 999724.5 | 15243565 | 15243565 | 5858023576 | لا | 0 | 190401011735 | جاري | الكميات التي تم تركيبها | 90 | 100 | 2019-09-30 | 2021-03-25 | 2022-02-22 | 2022-02-22 |  |  |  |  | 42.0529 | 18.5228 | Failed | No
2100027300 | أمانة / عسير | تشييد | ذات اولوية عالية | 1154950 | 57747.5 | 624764 | 624764 | 1010262622 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 62 | 100 | 2014-09-01 | 2015-08-27 | 2022-02-20 | 2022-02-20 |  |  | اخرى |  | 43.3682 | 17.9233 | مسحوب | No
2100071260 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 1579842 | 78992.1 | 0 | 0 | 3556000250 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 5 | 100 | 2015-11-07 | 2016-10-05 | 2018-10-22 | 2018-10-22 |  |  | ضعف كفاءة المقاول الفنية |  | 35.0202 | 28.4788 | مسحوب | No
2100093811 | أمانة / عسير | دراسات هندسية | ذات اولوية عالية | 8900000 | 445000 | 4845000 | 4845000 | 1010404431 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 75 | 100 | 2014-04-22 | 2016-08-22 | 2020-12-26 | 2020-12-26 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | مسحوب | No
2100043606 | أمانة / تبوك | تشييد | ذات اولوية عالية | 1802888.24 | 90144.412 | 0 | 0 | 3550032522 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 15 | 100 | 2015-10-28 | 2017-04-20 | 2020-12-15 | 2020-12-15 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5929 | 28.4123 | مسحوب | No
2300238280 | وزارة الصحة | ترميم | ذات اولوية متوسطة | 4592940 | 229647 | 0 | 0 | 1131013286 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 49 | 60 | 2022-12-01 | 2024-05-20 | 2023-08-06 | 2023-08-06 |  |  |  |  | 43.9702 | 26.3487 | متأخر | No
2300238313 | وزارة الصحة | ترميم | ذات اولوية متوسطة | 1733246.65 | 86662.3325 | 0 | 0 | 1128008563 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 2 | 10 | 2022-12-01 | 2023-06-04 | 2023-09-03 | 2023-09-03 |  |  |  |  | 43.974 | 26.3489 | متأخر | No
2100017124 | أمانة / تبوك | تشييد | ذات اولوية عالية | 1287720 | 64386 | 253191.95 | 253165.752 | 3350017280 | لا | 0 | 200501038064 | جاري | تكلفة العمل المنجز | 85 | 100 | 2019-12-01 | 2020-11-19 | 2023-08-22 | 2023-08-22 |  |  | تغيرات في نطاق المشروع |  | 36.5635 | 28.4463 | متأخر | No
2100017275 | وزارة الحرس الوطني / وكالة الشؤون الفنية | تشييد | ذات اولوية متوسطة | 1889842.5 | 94492.125 | 1835847.01 | 1700842.51 | 4030190178 | لا | 0 |  | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-07-10 | 2019-07-09 | 2019-07-09 | 2019-07-09 | 2019-07-09 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال | تم إنذار المقاول كتابيا |  |  | Failed | No
2100016306 | جامعة جازان | تشييد | ذات اولوية منخفضة | 11533950.8 | 576697.54 | 11533950.8 | 11533950.8 | 2051001558 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 14 | 14 | 2015-08-20 | 2017-06-20 | 2026-12-23 | 2026-12-23 |  |  | المشروع ليس ذو أولوية في الوقت الحالي |  | 42.3325 | 17.6609 | Failed | No
2100046270 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 6108505 | 305425.25 | 5297083 | 4365015 | 1010156220 | لا | 0 | 181009141167 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-04-18 | 2016-04-12 | 2020-04-25 | 2020-04-25 | 2016-04-12 |  | ضعف كفاءة المقاول الفنية |  | 35.0202 | 28.4788 | منجز | No
2300238335 | وزارة الحرس الوطني / وكالة الشؤون الفنية | توريد وتركيب | ذات اولوية متوسطة | 149996.04 | 7499.802 | 0 | 0 | 5950005113 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 4 | 10 | 2022-11-01 | 2023-02-26 | 2023-02-26 | 2023-02-26 |  |  |  | تم إنذار المقاول كتابيا | 44.2296 | 17.576 | متأخر | No
2100042232 | جامعة جازان | تشييد | ذات اولوية منخفضة | 83053653.1 | 4152682.655 | 1484850 | 1484850 | 2051001558 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 2 | 2 | 2015-07-30 | 2017-05-30 | 2026-12-23 | 2026-12-23 |  |  | المشروع ليس ذو أولوية في الوقت الحالي |  | 43.1226 | 17.3614 | Failed | No
2100050105 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 3030129.285 | 151506.4642 | 1978493 | 1978493 | 3556000250 | لا | 0 | 181009144752 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-03-02 | 2016-08-23 | 2020-03-14 | 2020-03-14 | 2016-08-23 |  | ضعف كفاءة المقاول الفنية |  | 35.0202 | 28.4788 | منجز | No
2100050551 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 1442166.5 | 72108.325 | 1442166.5 | 1442166.5 | 3553000034 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-08-15 | 2016-02-05 | 2017-03-19 | 2017-03-19 | 2016-02-05 |  | اخرى |  | 35.0202 | 28.4788 | منجز | No
2100008584 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 11175904 | 558795.2 | 0 | 0 | 1010142553 | لا | 0 |  | جاري | التكلفة المفوترة | 1 | 100 | 2007-02-16 | 2009-02-05 | 2022-12-15 | 2022-12-15 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | Failed | No
2300238346 | وزارة الحرس الوطني / وكالة الشؤون الفنية | توريد وتركيب | ذات اولوية عالية | 2894875 | 144743.75 | 0 | 0 | 1010094769 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 8 | 100 | 2018-12-06 | 2019-04-09 | 2023-03-16 | 2023-03-16 |  |  |  | أخرى |  |  | Failed | No
2100011970 | وزارة التعليم | تشييد | ذات اولوية عالية | 12021909.52 | 601095.476 | 7806448.7 | 7806448.7 | 1132000522 | لا | 0 |  | جاري | التكلفة المفوترة | 85 | 100 | 2008-07-06 | 2010-02-15 | 2022-10-19 | 2022-10-19 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | Failed | No
2100078923 | جامعة جازان | تشييد | ذات اولوية منخفضة | 18706053.85 | 935302.6925 | 4800627.74 | 4800627.74 | 1010252222 | لا | 0 | 180709036592 | فسخ العقد | الكميات التي تم تركيبها | 22.6 | 100 | 2015-12-27 | 2017-06-27 | 2024-01-01 | 2024-01-01 |  |  | ضعف كفاءة المقاول الفنية |  | 42.9181 | 16.6245 | مسحوب | No
2100048904 | جامعة جازان | تشييد | ذات اولوية منخفضة | 112877308 | 5643865.4 | 67299301.14 | 66003001.14 | 1010066115 | لا | 0 | 181109340199 | جاري | الكميات التي تم تركيبها | 59.62 | 96 | 2012-11-04 | 2016-04-17 | 2024-04-15 | 2024-04-15 |  |  | تأخرصرف المستحقات المالية |  | 42.5501 | 16.9779 | Failed | No
2100196954 | أمانة / المنطقة الشرقية | تصميم وتشييد | ذات اولوية متوسطة | 10551450 | 527572.5 | 10551450 | 9501450 | 2051046158 | لا | 0 | 181209436945 | منجز – استلام ابتدائي | التكلفة المفوترة | 95 | 100 | 2018-10-30 | 2019-10-19 | 2019-10-19 | 2019-10-19 | 2019-10-19 |  |  |  | 50.1971 | 26.2172 | منجز | No
2100009026 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 18658635 | 932931.75 | 2911789.26 | 2911789.26 | 4030085763 | لا | 0 |  | مسحوب | التكلفة المفوترة | 27 | 54 | 2012-05-26 | 2014-05-02 | 2014-12-25 | 2014-12-25 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | مسحوب | No
2100019972 | معهد الإدارة العامة | إشراف | ذات اولوية عالية وعاجلة | 2082024 | 104101.2 | 1874241.62 | 1861145.81 | 1010171914 | لا | 0 | 191101250300 | جاري | التكلفة المفوترة | 90 | 70 | 2019-12-24 | 2020-06-24 | 2023-01-24 | 2023-01-24 |  |  |  |  | 46.6846 | 24.8268 | خدمات عامة | No
2100019611 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 1969493 | 98474.65 | 0 | 0 | 1010263720 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 4 | 100 | 2012-12-01 | 2013-10-16 | 2021-10-26 | 2021-10-26 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0165 | 30.9619 | مسحوب | No
2100011454 | وزارة الداخلية / ديوان وزارة الداخلية | تصميم وتشييد | ذات اولوية عالية وعاجلة | 1038632855.98 | 51931642.799 | 535263084.15 | 535263084.15 | 1010254468 | لا | 0 | 180809053561 | جاري | منهجية القيمة المكتسبة | 56.89 | 67.6 | 2016-02-06 | 2018-11-18 | 2024-11-07 | 2024-11-07 |  |  | تأخرصرف المستحقات المالية | أخرى | 43.5002 | 17.7536 | متأخر | No
2100109896 | وزارة الداخلية / ديوان وزارة الداخلية | تصميم وتشييد | ذات اولوية عالية وعاجلة | 674884519.487 | 33744225.9743 | 326964327.52 | 326964327.52 | 1010254468 | لا | 0 | 180809053561 | جاري | منهجية القيمة المكتسبة | 55.71 | 100 | 2015-05-12 | 2017-10-27 | 2023-12-01 | 2023-12-01 |  |  | تأخرصرف المستحقات المالية | أخرى | 41.7101 | 17.9335 | Failed | No
2300238350 | وزارة الحرس الوطني / وكالة الشؤون الفنية | تشييد | ذات اولوية متوسطة | 229992467.95 | 11499623.3975 | 0 | 0 | 1010047800 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 0 | 0 | 2022-12-08 | 2024-06-07 | 2024-06-07 | 2024-06-07 |  |  |  |  | 43.8107 | 26.3499 | منتظم | No
2100043061 | جامعة جازان | تشييد | ذات اولوية عالية وعاجلة | 118200190.43 | 5910009.5215 | 118200190.43 | 118200190.43 | 1010066115 | لا | 0 | 181009164911 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 99 | 2013-04-18 | 2016-09-29 | 2022-04-24 | 2022-04-24 | 2016-09-29 |  | تأخرصرف المستحقات المالية |  | 42.5459 | 16.9686 | منجز | No
2100192231 | جامعة جازان | توريد وتركيب | ذات اولوية عالية | 8452987.2 | 422649.36 | 3179920 | 3179920 | 5855027386 | لا | 0 | 200601182170 | ايقاف جزئي | الكميات التي تم تركيبها | 39.5 | 96 | 2021-02-11 | 2021-11-10 | 2023-06-01 | 2023-06-01 |  |  |  |  | 42.8933 | 17.0106 | Failed | No
2100059872 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 8897817.955 | 444890.8978 | 6544059 | 6544059 | 1010188619 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-12-21 | 2016-09-18 | 2021-04-20 | 2021-04-20 | 2016-09-18 |  | ضعف كفاءة المقاول الفنية |  | 36.5577 | 28.412 | منجز | No
2300238383 | وزارة الصحة | ترميم | ذات اولوية متوسطة | 4024448.25 | 201222.4125 | 0 | 0 | 5850022870 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 8 | 20 | 2023-01-01 | 2023-09-01 | 2023-09-01 | 2023-09-01 |  |  |  |  | 43.9702 | 26.3487 | متأخر | No
2100086796 | جامعة جازان | توريد وتركيب | ذات اولوية عالية وعاجلة | 10468290 | 523414.5 | 9352540 | 7925230 | 5900112184 | لا | 0 | 200201011572 | جاري | الكميات التي تم تركيبها | 80 | 86 | 2020-03-16 | 2020-10-16 | 2022-12-30 | 2022-12-30 |  |  | التنسيق مع أصحاب المصلحه (خدمات |  | 42.5457 | 16.9687 | متأخر | No
2300238372 | وزارة الصحة | ترميم | ذات اولوية متوسطة | 5903525 | 295176.25 | 0 | 0 | 4030147825 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 1 | 10 | 2022-10-27 | 2023-06-19 | 2023-06-19 | 2023-06-19 |  |  |  |  | 43.9922 | 26.1046 | متأخر | No
2100005375 | جامعة الإمام محمد بن سعود الاسلامية | تشييد | ذات اولوية عالية | 123200000 | 6160000 | 103266464.93 | 101219326 | 1010180118 | لا | 0 |  | جاري | اخرى | 85 | 100 | 2012-04-28 | 2014-06-04 | 2023-02-28 | 2023-02-28 |  |  | ضعف كفاءة المقاول الفنية | أخرى | 46.7098 | 24.6275 | Failed | No
2100009951 | وزارة التعليم | تشييد | ذات اولوية عالية | 25912230.99 | 1295611.5495 | 14004686.71 | 14004686.71 | 1010099661 | لا | 0 |  | مسحوب | التكلفة المفوترة | 57 | 100 | 2014-02-26 | 2016-08-14 | 2021-09-01 | 2021-09-01 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | مسحوب | No
2100108905 | وزارة التعليم | تشييد | ذات اولوية عالية | 9988197.45 | 499409.8725 | 5984982.61 | 5686079.07 | 1010081451 | لا | 0 |  | مسحوب | التكلفة المفوترة | 67 | 100 | 2015-02-01 | 2017-01-21 | 2019-12-24 | 2019-12-24 |  |  | ضعف كفاءة المقاول الفنية |  | 46.5825 | 24.6442 | مسحوب | No
2100041893 | وزارة الداخلية / ديوان وزارة الداخلية | تصميم وتشييد | ذات اولوية عالية وعاجلة | 2393195402.45 | 119659770.1225 | 1074336015.45 | 1074336015.45 | 1010199246 | لا | 0 | 180809053494 | جاري | منهجية القيمة المكتسبة | 53.31 | 51 | 2015-05-19 | 2017-03-11 | 2024-06-30 | 2024-06-30 |  |  | تأخرصرف المستحقات المالية | أخرى | 44.5176 | 17.5224 | Failed | No
2100086564 | جامعة الإمام محمد بن سعود الاسلامية | تشييد | ذات اولوية متوسطة | 1155147611.89 | 57757380.5945 | 849849493.63 | 772541910.79 | 1010046693 | لا | 0 | 180809038517 | جاري | اخرى | 81 | 100 | 2014-09-16 | 2017-08-13 | 2023-03-11 | 2023-03-11 |  |  | تأخرصرف المستحقات المالية |  | 46.7098 | 24.6275 | متأخر | No
2100097016 | جامعة الإمام محمد بن سعود الاسلامية | تشييد | ذات اولوية عالية | 211063782.8 | 10553189.14 | 172407516.36 | 150190658.46 | 1010046693 | لا | 0 | 180809039860 | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2014-10-30 | 2017-09-26 | 2021-09-28 | 2021-09-28 | 2017-09-26 |  | تأخرصرف المستحقات المالية |  | 46.7098 | 24.6275 | منجز | No
2100031920 | وزارة التعليم | تشييد | ذات اولوية عالية | 3199251 | 159962.55 | 2155133 | 2155133 | 1010018153 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-05-14 | 2015-05-09 | 2015-08-07 | 2015-08-07 | 2015-05-09 |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | منجز | No
2100005401 | جامعة جازان | تشييد | ذات اولوية منخفضة | 179122196.8 | 8956109.84 | 72503598 | 68878418.1 | 1010062177 | لا | 0 | 191009026678 | جاري | الكميات التي تم تركيبها | 42 | 92 | 2014-11-18 | 2017-05-18 | 2024-04-15 | 2024-04-15 |  |  | تأخرصرف المستحقات المالية |  | 42.5498 | 16.9617 | Failed | No
2100085610 | جامعة الإمام محمد بن سعود الاسلامية | دراسة الجدوى | ذات اولوية عالية | 9497870.226 | 474893.5113 | 7758335.7387 | 6708586.4087 | 1010078921 | لا | 0 | 180909094657 | جاري | اخرى | 100 | 100 | 2014-10-30 | 2017-09-26 | 2021-09-28 | 2021-09-28 |  |  | تأخرصرف المستحقات المالية |  | 46.7086 | 24.8152 | خدمات عامة | No
2100056932 | وزارة الداخلية / ديوان وزارة الداخلية | إشراف | ذات اولوية عالية وعاجلة | 1250831476 | 62541573.8 | 1146492776 | 1140534450 | 1010330192 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 61 | 88 | 2015-01-01 | 2017-12-16 | 2024-08-07 | 2024-08-07 |  |  | تأخرصرف المستحقات المالية | لم يتم اتخاذ أي إجراء |  |  | خدمات عامة | No
2100073813 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 14971990.95 | 748599.5475 | 11084905.96 | 11084905.96 | 1010020305 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2007-11-13 | 2009-05-06 | 2018-08-17 | 2018-08-17 | 2009-05-06 |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | منجز | No
2100089025 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 3969591.9 | 198479.595 | 3429306.59 | 3429306.59 | 1116004478 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-11-09 | 2016-11-03 | 2022-08-10 | 2022-08-10 | 2016-11-03 |  | ضعف كفاءة المقاول الفنية |  | 46.8005 | 24.7884 | منجز | No
2100005913 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 22316052.15 | 1115802.6075 | 8953846.4 | 8953846.4 | 1010020305 | لا | 0 |  | مسحوب | التكلفة المفوترة | 38 | 100 | 2007-10-30 | 2009-04-22 | 2020-12-12 | 2020-12-12 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6096 | مسحوب | No
2100021604 | جامعة الإمام محمد بن سعود الاسلامية | دراسة الجدوى | ذات اولوية عالية | 10246500 | 512325 | 9079481.3673 | 6653792.4773 | 1010078921 | لا | 0 | 190909142090 | جاري | اخرى | 100 | 100 | 2012-11-17 | 2015-04-21 | 2020-09-19 | 2020-09-19 |  |  | تأخرصرف المستحقات المالية |  | 46.7061 | 24.8134 | خدمات عامة | No
2100041344 | جامعة الإمام محمد بن سعود الاسلامية | دراسة الجدوى | ذات اولوية متوسطة | 12039000 | 601950 | 12039000 | 11589000 | 1010462121 | لا | 0 | 180809038510 | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2010-05-17 | 2013-05-16 | 2016-05-31 | 2016-05-31 | 2013-05-16 |  | لا يوجد تأخير |  | 44.8306 | 26.3009 | منجز | No
2100072892 | أمانة / القصيم | تشييد | ذات اولوية متوسطة | 79000000 | 3950000 | 62984492.31 | 55984492.31 | 1010011560 | لا | 0 | 190509025503 | جاري | تكلفة العمل المنجز | 80 | 82 | 2018-12-16 | 2023-09-25 | 2023-09-25 | 2023-09-25 |  |  | تأخرصرف المستحقات المالية |  | 43.9818 | 26.3592 | منتظم | No
2100059861 | جامعة الإمام محمد بن سعود الاسلامية | تشييد | ذات اولوية عالية | 39935870.07 | 1996793.5035 | 35937909.33 | 35937909.33 | 1010081496 | لا | 0 | 180809038532 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-06-17 | 2016-05-17 | 2021-08-31 | 2021-08-31 | 2016-05-17 |  | لا يوجد تأخير |  | 45.3678 | 25.8939 | منجز | No
2300238420 | وزارة الصحة | ترميم | ذات اولوية متوسطة | 464690 | 23234.5 | 0 | 0 | 1132105948 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 37 | 45 | 2022-10-03 | 2023-03-29 | 2023-03-29 | 2023-03-29 |  |  |  |  | 43.4839 | 25.8827 | متأخر | No
2100047740 | وزارة الصحة / الحدود الشمالية | تشييد | ذات اولوية عالية | 19331562 | 966578.1 | 10335567.15 | 8466994.18 | 1010238171 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 100 | 100 | 2019-09-27 | 2021-09-26 | 2022-03-29 | 2022-03-29 |  |  |  |  | 38.6609 | 31.6685 | Failed | No
2100108695 | وزارة التعليم | تشييد | ذات اولوية عالية | 3196050 | 159802.5 | 2814999 | 2814999 | 1010018153 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-05-20 | 2017-05-19 | 2017-05-19 | 2017-05-19 | 2017-05-19 |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | منجز | No
2100041042 | وزارة التعليم | تشييد | ذات اولوية عالية | 10609229.77 | 530461.4885 | 9514845.92 | 9514845.92 | 1010081451 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2013-12-04 | 2015-11-24 | 2019-10-05 | 2019-10-05 | 2015-11-24 |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | منجز | No
2100016225 | جامعة الإمام محمد بن سعود الاسلامية | تشييد | ذات اولوية عالية | 605760721 | 30288036.05 | 244931957 | 234714033 | 1010053925 | لا | 0 | 181009216570 | جاري | اخرى | 46 | 100 | 2012-10-02 | 2020-01-10 | 2023-12-31 | 2023-12-31 |  |  | أوامر تغيير |  | 46.7098 | 24.6275 | Failed | No
2100058214 | جامعة الإمام محمد بن سعود الاسلامية | تشييد | ذات اولوية عالية | 23100000 | 1155000 | 14134000 | 12134000 | 1010081496 | لا | 0 | 180809038499 | جاري | اخرى | 80 | 100 | 2013-03-06 | 2020-02-13 | 2023-12-31 | 2023-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | Failed | No
2100032841 | المركز الوطني لتنمية الحياة الفطرية | تشييد | ذات اولوية منخفضة | 3820425 | 191021.25 | 3613975 | 130745 | 3450100938 | لا | 0 | 180809039733 | جاري | الكميات التي تم تركيبها | 55 | 100 | 2017-10-22 | 2019-10-12 | 2023-01-12 | 2023-01-12 |  |  | تأخرصرف المستحقات المالية |  | 38.9795 | 30.9399 | Failed | No
2100102664 | وزارة الصحة / الحدود الشمالية | تشييد | ذات اولوية متوسطة | 3923232 | 196161.6 | 3801422 | 1958816 | 3450008958 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-11-26 | 2020-11-19 | 2021-12-13 | 2021-12-13 | 2020-11-19 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.0511 | 30.9356 | منجز | No
2100078293 | وزارة الصحة / الحدود الشمالية | تشييد | ذات اولوية عالية | 78968192 | 3948409.6 | 78309809.81 | 71071373 | 1010008375 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2007-11-26 | 2017-08-19 | 2022-01-11 | 2022-01-11 | 2017-08-19 |  | التنسيق مع أصحاب المصلحه (خدمات |  | 43.5165 | 29.6394 | منجز | No
2100056066 | وزارة الصحة / الحدود الشمالية | تشييد | لم تعد تحتاجها الجهة | 7356850 | 367842.5 | 7356850 | 7356850 | 2050017521 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-01-17 | 2019-03-18 | 2021-11-29 | 2021-11-29 | 2019-03-18 |  | أوامر تغيير |  | 41.0457 | 30.9704 | منجز | No
2300238453 | وزارة الحرس الوطني / وكالة الشؤون الفنية | إشراف | ذات اولوية متوسطة | 5716650.47 | 285832.5235 | 0 | 0 | 1010322448 | لا | 0 |  | جاري | مدفوعات ساعات العمل | 0 | 0 | 2023-01-01 | 2025-06-30 | 2025-06-30 | 2025-06-30 | [6 empty] | خدمات عامة | No
2100055845 | وزارة الصحة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 20820075 | 1041003.75 | 6693962.2 | 6693962.2 | 2050017521 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 40 | 100 | 2020-02-20 | 2023-06-21 | 2023-06-21 | 2023-06-21 |  |  | سوء التخطيط الاولي للمشروع |  | 42.23 | 30.3612 | Failed | No
2100001982 | وزارة التعليم | تشييد | ذات اولوية عالية | 23134030 | 1156701.5 | 11744045 | 11744045 | 1010099661 | لا | 0 |  | مسحوب | التكلفة المفوترة | 68 | 87 | 2015-05-02 | 2017-10-18 | 2020-08-12 | 2020-08-12 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | مسحوب | No
2300238464 | وزارة الحرس الوطني / وكالة الشؤون الفنية | تحديث وتوريد | ذات اولوية متوسطة | 2363825 | 118191.25 | 0 | 0 | 1010432997 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 0 | 0 | 2022-11-30 | 2023-11-19 | 2023-11-19 | 2023-11-19 |  |  |  |  | 46.6655 | 24.7175 | منتظم | No
2100024076 | أمانة / عسير | تشييد | ذات اولوية عالية وعاجلة | 15572413 | 778620.65 | 11578818 | 4609090 | 5855007548 | لا | 0 | 181101256586 | جاري | تكلفة العمل المنجز | 92 | 100 | 2019-02-10 | 2020-02-05 | 2022-12-29 | 2022-12-29 |  |  | اخرى |  | 42.591 | 19.9786 | Failed | No
2100063755 | أمانة / عسير | تشييد | ذات اولوية عالية | 1492621 | 74631.05 | 240000 | 240000 | 5862003380 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 25 | 100 | 2016-08-30 | 2017-08-25 | 2022-07-06 | 2022-07-06 |  |  | ضعف كفاءة المقاول الفنية |  | 42.1825 | 18.9225 | مسحوب | No
2100046771 | أمانة / عسير | تشييد | ذات اولوية عالية | 380059 | 19002.95 | 380059 | 380059 | 5851004215 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 51 | 100 | 2014-11-19 | 2015-11-24 | 2018-12-31 | 2018-12-31 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | مسحوب | No
2100066290 | وزارة الصحة / الحدود الشمالية | تشييد | ذات اولوية عالية | 30436770 | 1521838.5 | 2359756.1 | 2359756.1 | 2511004129 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 8 | 100 | 2014-11-10 | 2016-11-10 | 2023-09-03 | 2023-09-03 |  |  | ضعف كفاءة المقاول الفنية |  | 41.0135 | 30.974 | مسحوب | No
2100095922 | وزارة الصحة / الحدود الشمالية | تشييد | لم تعد تحتاجها الجهة | 7683765.33 | 384188.2665 | 7683765.33 | 7683765.33 | 3450007134 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2017-10-21 | 2019-04-07 | 2019-12-14 | 2019-12-14 | 2019-04-07 |  | تأخرصرف المستحقات المالية |  | 42.2295 | 30.3595 | منجز | No
2100055974 | وزارة الصحة / الحدود الشمالية | تشييد | ذات اولوية متوسطة | 20476532 | 1023826.6 | 19553132.75 | 17199146 | 2511003703 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-11-03 | 2020-07-15 | 2021-11-28 | 2021-11-28 | 2020-07-15 |  | التنسيق مع أصحاب المصلحه (خدمات |  | 43.5252 | 29.6368 | منجز | No
2100044822 | أمانة / عسير | تشييد | ذات اولوية عالية | 4000000 | 200000 | 3600000 | 0 | 5852000047 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 74 | 100 | 2012-02-26 | 2013-08-27 | 2021-09-15 | 2021-09-15 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | مسحوب | Yes
2100029116 | أمانة / عسير | تشييد | ذات اولوية عالية | 5958409 | 297920.45 | 5165824 | 5165824 | 5852001934 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 86 | 100 | 2012-07-02 | 2013-12-24 | 2020-10-14 | 2020-10-14 |  |  | ضعف كفاءة المقاول الفنية |  | 42.2118 | 18.9085 | مسحوب | No
2100069274 | أمانة / عسير | تشييد | ذات اولوية عالية وعاجلة | 2455850 | 122792.5 | 1719095 | 1719095 | 5855012658 | لا | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 90 | 100 | 2015-02-03 | 2023-04-04 | 2023-04-04 | 2023-04-04 |  |  | تأخرصرف المستحقات المالية |  | 43.6594 | 18.7139 | Failed | No
2100075714 | أمانة / عسير | تشييد | ذات اولوية عالية | 1999565 | 99978.25 | 0 | 0 | 5855035278 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 3 | 100 | 2014-11-09 | 2015-11-06 | 2022-02-08 | 2022-02-08 |  |  | اخرى |  | 43.3276 | 17.5621 | مسحوب | No
2100048952 | أمانة / عسير | تشييد | ذات اولوية عالية | 3522960 | 176148 | 2044533.75 | 729750 | 5855002494 | لا | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 68 | 100 | 2019-08-22 | 2020-06-07 | 2023-03-15 | 2023-03-15 |  |  | اخرى |  | 43.2114 | 18.5529 | Failed | No
2100013123 | أمانة / عسير | تشييد | ذات اولوية عالية | 8298500 | 414925 | 5544929 | 5544929 | 5859002703 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 70 | 100 | 2015-09-04 | 2017-08-22 | 2021-12-11 | 2021-12-11 |  |  | تأخرصرف المستحقات المالية |  | 42.1351 | 19.1263 | مسحوب | No
2100052301 | أمانة / الحدود الشمالية | تشييد | ذات اولوية متوسطة | 2880000 | 144000 | 2720836 | 2720836 | 3450009879 | لا | 0 | 190301012276 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-11-27 | 2019-12-29 | 2019-12-29 | 2019-12-29 | 2019-12-29 |  | ضعف كفاءة المقاول الفنية |  | 41.596 | 30.6968 | منجز | No
2100025690 | أمانة / الحدود الشمالية | تشييد | ذات اولوية متوسطة | 512500 | 25625 | 512500 | 512500 | 5856009437 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2020-01-12 | 2020-09-12 | 2020-06-15 | 2020-06-15 | 2020-09-12 |  | ضعف كفاءة المقاول الفنية |  | 43.53 | 29.6174 | منجز | No
2100076344 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 1998925 | 99946.25 | 0 | 0 | 1010279929 | لا | 0 |  | فسخ العقد | منهجية القيمة المكتسبة | 0 | 0 | 2015-05-10 | 2015-05-11 | 2015-05-11 | 2015-05-11 |  |  | تأخرصرف المستحقات المالية |  | 44.3124 | 29.1489 | مسحوب | No
2100076565 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 16846000 | 842300 | 16637491.5 | 16637491.5 | 1010127437 | لا | 0 | 190409003162 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-11-20 | 2019-10-16 | 2021-12-01 | 2021-12-01 | 2019-10-16 |  |  |  | 40.9989 | 30.9844 | منجز | No
2100093332 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 1282300 | 64115 | 636635 | 636635 | 3450009680 | لا | 0 | 190309093508 | فسخ العقد | منهجية القيمة المكتسبة | 32 | 32 | 2015-01-28 | 2015-07-27 | 2021-11-11 | 2021-11-11 |  |  | اخرى |  | 41.0022 | 30.9757 | مسحوب | No
2100048296 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 3322810 | 166140.5 | 2658248 | 2658248 | 1010158252 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2020-02-17 | 2021-02-10 | 2022-12-31 | 2022-12-31 | 2021-02-10 |  | ضعف كفاءة المقاول الفنية |  | 43.3554 | 29.9504 | منجز | No
2100066323 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 3974145 | 198707.25 | 2340920.87 | 2340920.87 | 3450009993 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 61 | 100 | 2014-05-18 | 2015-11-09 | 2016-04-19 | 2016-04-19 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | مسحوب | No
2100092002 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 2699446 | 134972.3 | 2159554 | 2159554 | 1010181249 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 80 | 100 | 2018-09-05 | 2019-08-31 | 2020-09-10 | 2020-09-10 | 2019-08-31 |  | ضعف كفاءة المقاول الفنية |  | 42.2531 | 30.3481 | منجز | No
2100013823 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 895000 | 44750 | 895000 | 895000 | 1010127437 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-09-05 | 2019-06-01 | 2019-03-10 | 2019-03-10 | 2019-06-01 |  |  |  | 42.2471 | 30.3563 | منجز | No
2100065575 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 2960330 | 148016.5 | 977190 | 977190 | 1010056579 | لا | 0 |  | مسحوب | منهجية القيمة المكتسبة | 33 | 33 | 2014-03-03 | 2015-02-24 | 2020-09-15 | 2020-09-15 |  |  | تغيرات في نطاق المشروع |  | 42.2529 | 30.3494 | مسحوب | No
2100068423 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 2530190 | 126509.5 | 2421940 | 2421940 | 3450008799 | لا | 0 | 180801046552 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 96 | 100 | 2018-06-24 | 2019-06-19 | 2020-11-15 | 2020-11-15 | 2019-06-19 |  | ضعف كفاءة المقاول الفنية |  | 42.2584 | 30.3457 | منجز | No
2100092654 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 8194665 | 409733.25 | 7375191 | 7375191 | 1010127437 | لا | 0 | 180901073367 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-01-30 | 2020-07-21 | 2021-07-11 | 2021-07-11 | 2020-07-21 |  | ضعف كفاءة المقاول الفنية |  | 42.2528 | 30.3615 | منجز | No
2100036864 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 1355500 | 67775 | 1206392 | 1206392 | 1010181249 | لا | 0 | 181001143874 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-08-12 | 2019-04-14 | 2023-05-28 | 2023-05-28 |  |  | ضعف كفاءة المقاول الفنية |  | 43.3657 | 29.949 | منتظم | No
2100034134 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 1950110 | 97505.5 | 1950110 | 1950110 | 1131031254 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2015-08-02 | 2019-07-14 | 2019-03-30 | 2019-03-30 | 2019-07-14 |  | تأخرصرف المستحقات المالية |  | 44.7397 | 28.8899 | منجز | No
2100072822 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 8126980 | 406349 | 8126980 | 8126980 | 3450009076 | لا | 0 | 190501063546 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 97 | 100 | 2018-11-27 | 2019-10-23 | 2020-11-15 | 2020-11-15 | 2019-10-23 |  |  |  | 41.043 | 30.9623 | منجز | No
2100056626 | أمانة / الحدود الشمالية | إشراف | ذات اولوية متوسطة | 1960200 | 98010 | 1625400 | 1550150 | 3400014764 | لا | 0 | 181209470807 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-10-14 | 2020-10-14 | 2022-02-16 | 2022-02-16 | 2020-10-14 |  | اخرى |  | 41.0161 | 30.9843 | منجز | No
2100076230 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 9460000 | 473000 | 4135195 | 4135195 | 1010082460 | لا | 0 | 200209138920 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-09-15 | 2021-04-08 | 2021-07-22 | 2021-07-22 | 2021-04-08 |  |  |  | 38.653 | 31.6711 | منجز | No
2100034031 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 752200 | 37610 | 0 | 0 | 3357007585 | لا | 0 | 200209133178 | مسحوب | منهجية القيمة المكتسبة | 22 | 100 | 2019-11-04 | 2020-11-03 | 2020-12-02 | 2020-12-02 |  |  | ضعف كفاءة المقاول الفنية |  | 43.1374 | 29.8558 | مسحوب | No
2100071890 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 13717470 | 685873.5 | 12279755.21 | 12279755.21 | 1010133046 | لا | 0 | 190401078072 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2014-08-27 | 2016-02-18 | 2021-02-23 | 2021-02-23 | 2016-02-18 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 41.0041 | 30.9768 | منجز | No
2100048016 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 1575000 | 78750 | 798000 | 798000 | 1010101655 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 87 | 100 | 2019-11-14 | 2020-11-07 | 2023-03-27 | 2023-03-27 | 2020-11-07 |  | اخرى |  | 43.1336 | 29.8513 | منجز | No
2100032771 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | تشييد | ذات اولوية متوسطة | 16997748 | 849887.4 | 13401536.2 | 6355993.5 | 1010070634 | لا | 0 | 180809054189 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2017-07-20 | 2020-10-09 | 2020-10-09 | 2020-10-09 | 2020-10-09 |  | تأخرصرف المستحقات المالية |  | 40.4511 | 21.2747 | منجز | No
2100077210 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | تشييد | ذات اولوية عالية | 26768909.54 | 1338445.477 | 23386530.22 | 23386530.22 | 2055010409 | لا | 0 | 180709033794 | جاري | تكلفة العمل المنجز | 88 | 100 | 2018-04-01 | 2019-04-01 | 2023-05-31 | 2023-05-31 |  |  | تأخرصرف المستحقات المالية |  | 49.6626 | 27.0037 | Failed | No
2100024006 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | تشييد | ذات اولوية عالية وعاجلة | 61525418.08 | 3076270.904 | 22910314.18 | 22910314.18 | 2051027988 | نعم | 22910314.18 | 180709032450 | مسحوب | تكلفة العمل المنجز | 60 | 100 | 2015-09-17 | 2017-10-07 | 2022-12-31 | 2022-12-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 50.101 | 26.4494 | مسحوب | No
2100027053 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 630644.6 | 31532.23 | 452645 | 452645 | 1131015427 | لا | 0 | 190701135228 | جاري | منهجية القيمة المكتسبة | 80 | 90 | 2019-01-14 | 2020-01-08 | 2023-05-28 | 2023-05-28 |  |  | ضعف كفاءة المقاول الفنية | مخطط لسحبه وإعادة ترسيته | 43.1399 | 29.8535 | متأخر | No
2300238442 | وزارة الصحة | ترميم | ذات اولوية متوسطة | 2224040.2 | 111202.01 | 0 | 0 | 1131019831 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 1 | 10 | 2023-01-28 | 2023-08-27 | 2023-08-27 | 2023-08-27 |  |  |  |  | 44.2073 | 25.8462 | متأخر | No
2300238302 | وزارة الصحة | ترميم | ذات اولوية متوسطة | 1377318.2 | 68865.91 | 0 | 0 | 1131052191 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 1 | 10 | 2022-12-01 | 2023-06-01 | 2023-08-06 | 2023-08-06 |  |  |  |  | 43.4839 | 25.8827 | متأخر | No
2100043503 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 11659185.51 | 582959.2755 | 7864905.86 | 7864905.86 | 2050083217 | لا | 0 | 190601103874 | ايقاف كلي | تكلفة العمل المنجز | 72 | 82 | 2019-11-12 | 2022-04-15 | 2022-07-09 | 2022-07-09 |  |  |  | أخرى | 50.0076 | 26.5425 | Failed | No
2100029680 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 496800 | 24840 | 496800 | 496800 | 1010194071 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-12-15 | 2019-12-04 | 2019-12-05 | 2019-12-05 | 2019-12-04 |  |  |  | 49.4718 | 25.9952 | منجز | No
2300238593 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البحرية | تشييد | ذات اولوية عالية | 43923000 | 2196150 | 0 | 0 | 4031038849 | لا | 0 |  | لم يبدأ | الكميات التي تم تركيبها | 0 | 0 |  |  |  | 2024-06-17 |  |  |  |  | 48.6146 | 28.0964 | منتظم | No
2100044682 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 34886095 | 1744304.75 | 34541071.19 | 0 | 1116005202 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 98 | 100 | 2013-09-07 | 2015-08-28 | 2019-12-14 | 2019-12-14 | 2015-08-28 |  | ضعف كفاءة المقاول الفنية |  | 46.6891 | 24.7044 | منجز | Yes
2300238265 | وزارة الصحة | ترميم | ذات اولوية متوسطة | 2740982 | 137049.1 | 0 | 0 | 1132105948 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 15 | 50 | 2022-11-15 | 2023-05-10 | 2023-05-10 | 2023-05-10 |  |  |  |  | 43.9414 | 26.3707 | Failed | No
2300238291 | وزارة الصحة | ترميم | ذات اولوية متوسطة | 1386390 | 69319.5 | 0 | 0 | 1128008563 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 17 | 40 | 2022-10-28 | 2023-04-01 | 2023-09-03 | 2023-09-03 |  |  |  |  | 43.974 | 26.3489 | متأخر | No
2300238582 | وزارة الحرس الوطني / وكالة الشؤون الفنية | تحديث وتوريد | ذات اولوية متوسطة | 1799750 | 89987.5 | 0 | 0 | 1010282495 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 0 | 0 | 2023-01-04 | 2023-05-31 | 2023-05-31 | 2023-05-31 |  |  |  |  | 46.6806 | 24.705 | منتظم | No
2300238151 | وزارة الصحة | ترميم | ذات اولوية متوسطة | 1007342.5 | 50367.125 | 0 | 0 | 1131018576 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 1 | 10 | 2022-12-01 | 2023-06-01 | 2023-09-07 | 2023-09-07 |  |  |  |  | 43.9702 | 26.3487 | متأخر | No
2300238604 | وزارة الصحة | ترميم | ذات اولوية متوسطة | 4885228.85 | 244261.4425 | 0 | 0 | 1010162957 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 3 | 17 | 2022-12-22 | 2023-05-19 | 2024-08-08 | 2024-08-08 |  |  |  |  | 43.9702 | 26.3487 | متأخر | No
2300238405 | وزارة الصحة | ترميم | ذات اولوية متوسطة | 3366144.16 | 168307.208 | 0 | 0 | 1132103165 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 1 | 10 | 2023-01-15 | 2024-01-15 | 2024-01-15 | 2024-01-15 |  |  |  |  | 43.9702 | 26.3487 | متأخر | No
2100031231 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3564000 | 178200 | 41398 | 0 | 1010171813 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2013-11-06 | 2015-04-30 | 2019-10-05 | 2019-10-05 | 2015-04-30 |  | ضعف كفاءة المقاول الفنية |  | 46.7015 | 24.7119 | منجز | Yes
2100030995 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1697000 | 84850 | 0 | 0 | 1010242510 | لا | 0 |  | جاري | تكلفة العمل المنجز | 55 | 100 | 2018-04-15 | 2019-04-10 | 2019-05-10 | 2019-05-10 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6974 | 24.7181 | Failed | No
2300238416 | وزارة الصحة | ترميم | ذات اولوية متوسطة | 1508800 | 75440 | 0 | 0 | 1010217074 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 2 | 20 | 2023-01-24 | 2024-01-24 | 2024-01-24 | 2024-01-24 |  |  |  |  | 43.9702 | 26.3487 | متأخر | No
2300238394 | وزارة الصحة | ترميم | ذات اولوية متوسطة | 294678.88 | 14733.944 | 0 | 0 | 1010032384 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 40 | 80 | 2022-10-16 | 2023-04-12 | 2023-04-12 | 2023-04-12 |  |  |  |  | 42.9233 | 24.7239 | Failed | No
2100078901 | وزارة الحرس الوطني / وكالة الشؤون الفنية | تصميم وتشييد | ذات اولوية عالية | 14329386330 | 716469316.5 | 8106292199 | 8106292199 | 4030068284 | لا | 0 |  | جاري | تكلفة العمل المنجز | 73 | 100 | 2010-08-14 | 2014-08-14 | 2024-08-01 | 2024-08-01 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال | تم إنذار المقاول كتابيا |  |  | Failed | No
2100065306 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 31028480 | 1551424 | 23708563.034 | 0 | 1010056094 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-11-02 | 2016-10-22 | 2020-02-25 | 2020-02-25 | 2016-10-22 |  | ضعف كفاءة المقاول الفنية |  | 46.874 | 23.4933 | منجز | Yes
2100001934 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3309473.2 | 165473.66 | 0 | 0 | 1010276314 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-10-31 | 2016-01-24 | 2020-08-28 | 2020-08-28 | 2016-01-24 |  | تأخرصرف المستحقات المالية |  | 46.7216 | 24.7551 | منجز | No
2100193513 | وزارة الحرس الوطني / وكالة الشؤون الفنية | تشييد | ذات اولوية متوسطة | 10869879.72 | 543493.986 | 6617007.65 | 6617007.65 | 3400009021 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2021-01-24 | 2022-03-13 | 2022-11-04 | 2022-11-04 | 2022-03-13 |  |  |  | 41.0658 | 30.926 | منجز | No
2100063490 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3509803.5 | 175490.175 | 1874137.133 | 0 | 1010056094 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 91 | 100 | 2015-03-28 | 2016-06-20 | 2020-03-16 | 2020-03-16 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6775 | 24.705 | Failed | Yes
2100030704 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3122000 | 156100 | 1982125 | 0 | 1010301592 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-10-15 | 2017-01-07 | 2019-05-22 | 2019-05-22 | 2017-01-07 |  | ضعف كفاءة المقاول الفنية |  | 46.6672 | 24.7082 | منجز | Yes
2100047014 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 33177127 | 1658856.35 | 11018023.72 | 0 | 1010015152 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2011-09-06 | 2018-01-08 | 2018-01-08 | 2018-01-08 | 2018-01-08 |  |  |  | 46.6878 | 24.7181 | منجز | Yes
2100063560 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2775739.45 | 138786.9725 | 1271336 | 0 | 1010015152 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 97 | 100 | 2015-05-15 | 2016-11-05 | 2020-01-26 | 2020-01-26 | 2016-11-05 |  | ضعف كفاءة المقاول الفنية |  | 46.6672 | 24.7157 | منجز | Yes
2300238615 | المركز الوطني لتنمية الحياة الفطرية | تحديث وتوريد | ذات اولوية عالية | 15151287.38 | 757564.369 | 0 | 0 | 1010256498 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 5 | 5 | 2023-01-15 | 2023-05-29 | 2023-05-29 | 2023-05-29 |  |  |  |  | 46.7416 | 24.7024 | منتظم | No
2300238630 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 370300 | 18515 | 183137.5 | 107295 | 0 | لا | 0 |  | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 100 | 100 | 2022-06-28 | 2022-12-28 | 2022-12-26 | 2022-12-26 |  |  |  |  | 42.1709 | 18.2273 | منتظم | No
2300238626 | وزارة الحرس الوطني / الشؤون الصحية | توريد وتركيب | ذات اولوية عالية | 1117800 | 55890 | 0 | 0 | 4030147825 | لا | 0 | 220601103114 | جاري | الكميات التي تم تركيبها | 100 | 100 | 2022-08-03 | 2022-09-02 | 2022-11-30 | 2022-11-30 | [6 empty] | متأخر | No
2100193196 | وزارة الحرس الوطني / وكالة الشؤون الفنية | تشييد | ذات اولوية متوسطة | 5320041.72 | 266002.086 | 5302742.44 | 5302742.44 | 1010165175 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2020-05-31 | 2021-11-13 | 2022-05-09 | 2022-05-09 | 2021-11-13 |  |  |  | 46.6775 | 24.7038 | منجز | No
2100190175 | وزارة البيئة والمياة والزراعة | توريد وتركيب | ذات اولوية عالية وعاجلة | 20460480 | 1023024 | 16008250.15 | 16008250.15 | 5850008752 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 75 | 100 | 2019-01-13 | 2021-06-16 | 2022-09-06 | 2022-09-06 |  |  |  |  | 46.6952 | 24.7259 | Failed | No
2300238276 | وزارة الحرس الوطني / الشؤون الصحية | توريد وتركيب | ذات اولوية عالية وعاجلة | 2708678.68 | 135433.934 | 285518.69 | 0 | 1010134658 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 70 | 90 | 2022-07-17 | 2023-01-13 | 2023-01-31 | 2023-01-31 | [6 empty] | متأخر | Yes
2300238070 | وزارة الصحة | ترميم | ذات اولوية متوسطة | 3957702 | 197885.1 | 0 | 0 | 1131019831 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 4 | 8 | 2022-12-04 | 2023-04-01 | 2023-04-01 | 2023-04-01 |  |  |  |  | 43.9702 | 26.3487 | منتظم | No
2100049442 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 9892120 | 494606 | 1451229.74 | 1451229.74 | 4030023505 | لا | 0 | 190809096022 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-07-06 | 2020-12-27 | 2022-09-03 | 2022-09-03 | 2020-12-27 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 49.6028 | 25.3815 | منجز | No
2100064304 | أمانة / الجوف | تشييد | ذات اولوية عالية وعاجلة | 1441790 | 72089.5 | 1441790 | 1441790 | 3400111080 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-06-07 | 2019-06-01 | 2019-09-05 | 2019-09-05 | 2019-06-01 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.8755 | 29.79 | منجز | No
2100189932 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية عالية وعاجلة | 19977226.5 | 998861.325 | 1969939.65 | 1969939.65 | 1124000200 | لا | 0 | 190709164514 | جاري | الكميات التي تم تركيبها | 75 | 100 | 2018-05-11 | 2020-10-13 | 2021-06-07 | 2021-06-07 |  |  |  |  | 37.3547 | 31.3466 | Failed | No
2300238125 | وزارة الصحة | ترميم | ذات اولوية متوسطة | 1178175 | 58908.75 | 0 | 0 | 1131002183 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 2 | 10 | 2022-12-01 | 2023-02-28 | 2023-02-28 | 2023-02-28 |  |  |  |  | 43.9702 | 26.3487 | متأخر | No
2300238173 | وزارة الصحة | ترميم | ذات اولوية متوسطة | 2100000 | 105000 | 0 | 0 | 1131021347 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 2 | 13 | 2022-12-29 | 2023-08-22 | 2023-08-22 | 2023-08-22 |  |  |  |  | 43.9702 | 26.3487 | متأخر | No
2300238221 | وزارة الصحة | ترميم | ذات اولوية متوسطة | 1048512.5 | 52425.625 | 0 | 0 | 1131002183 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 90 | 100 | 2022-06-14 | 2023-01-12 | 2023-01-31 | 2023-01-31 |  |  |  |  | 43.9922 | 26.1046 | متأخر | No
2100190304 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية عالية وعاجلة | 105820102.59 | 5291005.1295 | 28588881.48 | 28588881.48 | 4030140655 | لا | 0 | 190609003523 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2017-02-25 | 2019-07-30 | 2021-10-06 | 2021-10-06 | 2019-07-30 |  |  |  | 37.2613 | 25.039 | منجز | No
2100003290 | وزارة الصحة / حائل | تشييد | ذات اولوية عالية وعاجلة | 7787760 | 389388 | 5475783 | 4335367.8 | 1010074061 | لا | 0 | 181109375877 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2017-09-13 | 2019-02-27 | 2022-09-13 | 2022-09-13 |  |  | أوامر تغيير |  | 41.6966 | 27.5075 | منتظم | No
2200231420 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 621155.25 | 31057.7625 | 621155.25 | 621155.25 | 2056005766 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2022-09-01 | 2022-11-30 | 2022-11-30 | 2022-11-30 | 2022-11-30 |  |  |  | 48.4855 | 27.4704 | منجز | No
2200231442 | أمانة / المنطقة الشرقية | أخرى | ذات اولوية متوسطة | 562212 | 28110.6 | 0 | 0 | 2056001462 | لا | 0 |  | جاري | تكلفة العمل المنجز | 2 | 62.92 | 2022-08-17 | 2023-04-14 | 2023-04-14 | 2023-04-14 |  |  |  |  | 48.4288 | 27.2669 | خدمات عامة | No
2300238663 | وزارة الصحة | ترميم | ذات اولوية متوسطة | 3957702 | 197885.1 | 0 | 0 | 1131028904 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 2 | 13 | 2022-11-20 | 2023-05-15 | 2023-05-15 | 2023-05-15 |  |  |  |  | 43.9702 | 26.3487 | متأخر | No
2100038231 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 20584700 | 1029235 | 19967700 | 19967700 | 1116000094 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2013-10-28 | 2015-12-23 | 2018-01-16 | 2018-01-16 | 2015-12-23 | 2019-07-27 |  |  | 39.1848 | 22.3467 | منجز | No
2100080570 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 755555 | 37777.75 | 755555 | 755555 | 2050069357 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-12-04 | 2020-11-22 | 2020-11-22 | 2020-11-22 | 2020-11-22 |  |  |  | 46.9781 | 27.2349 | منجز | No
2100031113 | أمانة / الجوف | تشييد | ذات اولوية عالية وعاجلة | 1488500 | 74425 | 1338900 | 1338900 | 3452004651 | لا | 0 | 190509075508 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-04-11 | 2021-03-30 | 2021-03-30 | 2021-03-30 | 2021-03-30 |  | اخرى |  | 37.1473 | 31.4806 | منجز | No
2100002015 | مدينة الملك فهد الطبية | تشييد | ذات اولوية عالية | 8618655 | 430932.75 | 7762733 | 7762733 | 2050038009 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-03-22 | 2020-03-22 | 2021-03-22 | 2021-03-22 | 2020-03-22 |  |  |  | 46.702 | 24.686 | منجز | No
2300238674 | مدينة الملك عبدالله الطبية بالعاصمة المقدسة | توريد وتركيب | ذات اولوية عالية | 1817037.95 | 90851.8975 | 0 | 0 | 4030045393 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 0 | 100 | 2022-11-14 | 2023-03-20 | 2023-03-10 | 2023-03-10 |  |  |  |  | 39.8811 | 21.3821 | Failed | No
2100080614 | أمانة / الجوف | تشييد | ذات اولوية عالية | 2798000 | 139900 | 2798000 | 2798000 | 3452003018 | لا | 0 | 181001119581 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-08-12 | 2019-08-08 | 2019-08-13 | 2019-08-13 | 2019-08-08 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.8888 | 29.8108 | منجز | No
2100087544 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | تشييد | ذات اولوية عالية | 105243070.8 | 5262153.54 | 83176080.7 | 83176080.7 | 1010147053 | لا | 0 | 181109274756 | جاري | تكلفة العمل المنجز | 94 | 100 | 2014-12-15 | 2017-05-31 | 2023-04-30 | 2023-04-30 |  |  | تأخرصرف المستحقات المالية |  | 50.101 | 26.4494 | Failed | No
2200234172 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | تشييد | ذات اولوية متوسطة | 7635920.01 | 381796.0005 | 0 | 0 | 4031038849 | لا | 0 | 191001040908 | جاري | تكلفة العمل المنجز | 3.8 | 14 | 2022-10-10 | 2024-01-03 | 2024-01-03 | 2024-01-03 |  |  |  |  | 47.3248 | 24.1576 | متأخر | No
2100013285 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 29948060 | 1497403 | 21862083.8 | 21862083.8 | 2050027937 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 73 | 93 | 2018-01-08 | 2022-12-26 | 2022-12-26 | 2022-12-26 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.5508 | 24.4754 | مسحوب | No
2200234216 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | تشييد | ذات اولوية متوسطة | 4014406.2 | 200720.31 | 0 | 0 | 1010218930 | لا | 0 | 220201203908 | جاري | تكلفة العمل المنجز | 0.9 | 4 | 2022-10-17 | 2024-09-14 | 2024-09-14 | 2024-09-14 |  |  |  |  | 42.7662 | 18.3093 | منتظم | No
2100061854 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | تشييد | ذات اولوية متوسطة | 91725750.6 | 4586287.53 | 65623856.4 | 65623856.4 | 1010093493 | لا | 0 | 181001160130 | جاري | تكلفة العمل المنجز | 88 | 100 | 2019-01-22 | 2021-10-17 | 2023-08-29 | 2023-08-29 |  |  | تأخرصرف المستحقات المالية |  | 50.101 | 26.4494 | Failed | No
2100065122 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 1686428 | 84321.4 | 1686428 | 1686428 | 2056001352 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-04-02 | 2020-01-05 | 2020-01-06 | 2020-01-06 | 2020-01-05 |  |  |  | 48.4772 | 27.4698 | منجز | No
2100058026 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 9569279 | 478463.95 | 3058812 | 3058812 | 1010187466 | لا | 0 |  | مسحوب | التكلفة المفوترة | 37 | 100 | 2014-10-19 | 2018-01-31 | 2020-12-31 | 2020-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 48.9541 | 28.4113 | مسحوب | No
2200234194 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | تشييد | ذات اولوية متوسطة | 13137370 | 656868.5 | 0 | 0 | 1010211349 | لا | 0 | 201101033665 | جاري | تكلفة العمل المنجز | 10 | 23.3 | 2022-10-09 | 2023-10-03 | 2023-10-03 | 2023-10-03 |  |  |  |  | 47.3248 | 24.1576 | متأخر | No
2100081502 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 58164000 | 2908200 | 58164000 | 58164000 | 3450000664 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-08-27 | 2022-02-28 | 2022-02-28 | 2022-02-28 | 2022-02-28 |  | ضعف كفاءة المقاول الفنية |  | 39.6022 | 24.4081 | منجز | No
2200222751 | وزارة الدفاع / الإدارة الهندسية والاشغال بقوة الصواريخ الإستراتيجية | تشييد | ذات اولوية عالية وعاجلة | 4588634.71 | 229431.7355 | 3694532.97 | 3694532.97 | 1010511546 | لا | 0 | 201201111386 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2020-12-15 | 2021-11-10 | 2022-04-10 | 2022-04-10 | 2021-11-10 |  |  | تم تمديد الجدول الزمني | 44.4182 | 24.5167 | منجز | No
2100064433 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 2557431.53 | 127871.5765 | 1004810.1 | 1004810.1 | 2055018225 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 41.36 | 100 | 2019-08-25 | 2021-05-08 | 2021-05-08 | 2021-05-08 |  |  |  |  | 49.5937 | 26.9976 | مسحوب | No
2300238696 | وزارة الدفاع / الإدارة الهندسية والاشغال بقوة الصواريخ الإستراتيجية | تصميم | ذات اولوية عالية وعاجلة | 103500 | 5175 | 0 | 0 | 1131056879 | لا | 0 |  | جاري | تكلفة العمل المنجز | 10 | 10 | 2022-12-27 | 2023-06-23 | 2023-06-23 | 2023-06-23 |  |  |  |  | 46.7396 | 24.7455 | منتظم | No
2100001750 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | تشييد | ذات اولوية عالية | 226987102.93 | 11349355.1465 | 207339742.85 | 181022993.35 | 1010074952 | لا | 0 | 180526033955 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-05-14 | 2018-11-29 | 2022-04-30 | 2022-04-30 | 2018-11-29 |  | تأخرصرف المستحقات المالية |  | 50.101 | 26.4494 | منجز | No
2100034425 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 2987152 | 149357.6 | 2987152 | 2987152 | 3357606131 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-01-29 | 2020-01-24 | 2020-02-06 | 2020-02-06 | 2020-01-24 |  | تأخرصرف المستحقات المالية |  | 40.9572 | 28.0218 | منجز | No
2100086133 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 12465498.79 | 623274.9395 | 7546983.81 | 0.01 | 2251003882 | لا | 0 |  | مسحوب | التكلفة المفوترة | 70 | 100 | 2014-08-12 | 2017-12-23 | 2019-12-01 | 2019-12-01 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5604 | 25.3897 | مسحوب | No
2100024345 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 108275.65 | 5413.7825 | 101489.16 | 101489.16 | 1010036045 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2012-04-17 | 2014-04-07 | 2019-01-31 | 2019-01-31 | 2014-04-07 |  | ضعف كفاءة المقاول الفنية |  | 45.975 | 28.4334 | منجز | No
2100012062 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 20796774 | 1039838.7 | 161403 | 15472.519 | 2050018834 | لا | 0 |  | مسحوب | التكلفة المفوترة | 85 | 100 | 2013-08-24 | 2015-11-12 | 2020-10-01 | 2020-10-01 |  |  | ضعف كفاءة المقاول الفنية |  | 50.5054 | 26.4769 | مسحوب | No
2100048381 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 6652637 | 332631.85 | 6652637 | 3568457.35 | 5950007223 | لا | 0 | 180909071249 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 96 | 100 | 2015-10-28 | 2019-01-05 | 2021-12-30 | 2021-12-30 | 2019-01-05 |  | ضعف كفاءة المقاول الفنية |  | 44.2368 | 17.6006 | منجز | No
2100051063 | أمانة / الجوف | تشييد | ذات اولوية عالية | 4178325 | 208916.25 | 3551696 | 3551696 | 3452003018 | لا | 0 | 181001119581 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 85 | 100 | 2018-12-08 | 2019-11-28 | 2020-04-25 | 2020-04-25 | 2019-11-28 |  | ضعف كفاءة المقاول الفنية |  | 37.3472 | 31.3238 | منجز | No
2200228314 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 768682.08 | 38434.104 | 668419 | 668419 | 2050018628 | لا | 0 |  | جاري | تكلفة العمل المنجز | 100 | 25.71 | 2022-05-16 | 2022-08-15 | 2022-08-15 | 2022-08-15 |  |  |  |  | 49.6481 | 25.9268 | Failed | No
2200216856 | وزارة المالية | إشراف | ذات اولوية متوسطة | 369600 | 18480 | 1056300 | 1056300 | 2050018622 | لا | 0 |  | ايقاف كلي | التكلفة المفوترة | 43 | 43 | 2018-07-22 | 2019-06-20 | 2023-11-30 | 2023-11-30 |  |  |  |  | 40.4248 | 21.2841 | Failed | No
2100099094 | وزارة المالية | تصميم | ذات اولوية عالية | 1575000 | 78750 | 472500 | 472500 | 1010076578 | لا | 0 | 181109326265 | ايقاف كلي | تكلفة العمل المنجز | 30 | 30 | 2017-12-08 | 2018-04-08 | 2023-12-31 | 2023-12-31 |  |  | أوامر سامية |  | 46.709 | 24.6938 | Failed | No
2100103014 | وزارة المالية | إشراف | ذات اولوية عالية | 13570200 | 678510 | 4830161.68 | 4830161.68 | 1010322156 | لا | 0 | 200801006659 | فسخ العقد | تكلفة العمل المنجز | 2 | 2 | 2020-06-29 | 2021-12-27 | 2021-12-27 | 2021-12-27 |  |  | لا يوجد تأخير |  | 46.7049 | 24.7094 | مسحوب | No
2100042685 | وزارة المالية | تشييد | ذات اولوية متوسطة | 22321716.91 | 1116085.8455 | 13994574.9 | 13994574.9 | 1010007606 | لا | 0 |  | مسحوب | التكلفة المفوترة | 64 | 64 | 2014-01-20 | 2023-11-30 | 2022-08-01 | 2022-08-01 |  |  | ضعف كفاءة المقاول الفنية |  | 42.0529 | 18.5228 | مسحوب | No
2300238744 | وزارة الدفاع / الإدارة الهندسية والاشغال بقوة الصواريخ الإستراتيجية | تصميم | ذات اولوية عالية وعاجلة | 297698.2 | 14884.91 | 0 | 0 | 1010468691 | لا | 0 | 220439537878 | جاري | تكلفة العمل المنجز | 5 | 5 | 2022-12-01 | 2023-06-03 | 2023-06-03 | 2023-06-03 |  |  |  |  | 46.7396 | 24.7455 | منتظم | No
2100035350 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية | 659654260.64 | 32982713.032 | 526211.47 | 526211.47 | 1010609431 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 0.14 | 59.88 | 2015-01-08 | 2018-12-17 | 2025-12-31 | 2025-12-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 43.9982 | 26.2091 | Failed | No
2100007162 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 17281039.62 | 864051.981 | 0.01 | 0.01 | 1010001374 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0 | 100 | 2007-11-10 | 2009-10-10 | 2021-01-10 | 2021-01-10 |  |  | ضعف كفاءة المقاول الفنية |  | 50.4882 | 26.5601 | مسحوب | No
2100031765 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 22031298.12 | 1101564.906 | 2190786.57 | 0 | 1010046644 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 10 | 100 | 2016-04-24 | 2018-07-12 | 2020-12-14 | 2020-12-14 |  |  | ضعف كفاءة المقاول الفنية |  | 50.4171 | 26.5891 | مسحوب | Yes
2100003603 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2801140 | 140057 | 1787025 | 816330 | 2057002826 | لا | 0 |  | مسحوب | التكلفة المفوترة | 83 | 88 | 2019-01-15 | 2020-01-10 | 2020-10-15 | 2020-10-15 |  |  | ضعف كفاءة المقاول الفنية |  | 47.6773 | 27.0109 | مسحوب | No
2100100903 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 4320872.05 | 216043.6025 | 4320872.05 | 4320872.05 | 2050041707 | لا | 0 | 191101075060 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-01-08 | 2020-12-20 | 2020-12-20 | 2020-12-20 | 2020-12-20 |  | ضعف كفاءة المقاول الفنية |  | 49.659 | 26.9997 | منجز | No
2100008993 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 34137687.76 | 1706884.388 | 21444777 | 21444777 | 1132002624 | لا | 0 |  | جاري | تكلفة العمل المنجز | 71 | 100 | 2013-06-23 | 2015-06-13 | 2022-05-10 | 2022-05-10 |  |  | ضعف كفاءة المقاول الفنية |  | 43.6565 | 26.1508 | Failed | No
2100038791 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 7570514.64 | 378525.732 | 829810.2 | 0.01 | 1010046644 | لا | 0 |  | مسحوب | التكلفة المفوترة | 15 | 100 | 2016-02-10 | 2017-11-01 | 2023-08-12 | 2023-08-12 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5604 | 25.3897 | مسحوب | No
2100103935 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 3389934.2 | 169496.71 | 2430042.76 | 2430042.76 | 2251027704 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-05-08 | 2015-10-29 | 2020-06-08 | 2020-06-08 | 2015-10-29 |  | ضعف كفاءة المقاول الفنية |  | 49.5604 | 25.3897 | منجز | No
2100192640 | الجامعة الاسلامية بالمدينة المنورة | دعم فني | ذات اولوية عالية | 3946800 | 197340 | 2805530.21 | 2805530.21 | 4650047424 | لا | 0 | 210301117704 | جاري | تكلفة العمل المنجز | 71 | 71 | 2021-05-05 | 2023-05-04 | 2023-05-04 | 2023-05-04 |  |  |  |  | 39.5654 | 24.4807 | خدمات عامة | No
2100060454 | وزارة الصحة / الحدود الشمالية | تشييد | لم تعد تحتاجها الجهة | 3250355 | 162517.75 | 3250355 | 3250355 | 3451003611 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2017-12-02 | 2019-04-23 | 2021-12-21 | 2021-12-21 | 2019-04-23 |  | أوامر تغيير |  | 38.6586 | 31.6699 | منجز | No
2100189582 | الهيئة الملكية للجبيل وينبع / مدينة جازان للصناعات الأساسية والتحويلية | تصميم | ذات اولوية منخفضة | 64142534 | 3207126.7 | 54780367.7 | 54780367.7 | 1010322156 | لا | 0 | 200509013501 | جاري | مدفوعات ساعات العمل | 86.46 | 86.55 | 2018-05-02 | 2023-02-04 | 2023-02-04 | 2023-02-04 |  |  |  | أخرى | 42.3625 | 17.352 | منتظم | No
2100086516 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 11640950 | 582047.5 | 1471867.36 | 1471867.36 | 1131022175 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 15 | 100 | 2014-01-20 | 2016-01-10 | 2017-12-14 | 2017-12-14 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 43.9875 | 26.0873 | مسحوب | No
2100096751 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 13153306.51 | 657665.3255 | 5970611.52 | 0 | 1010046644 | لا | 0 |  | مسحوب | التكلفة المفوترة | 69 | 100 | 2014-01-29 | 2016-05-17 | 2018-05-18 | 2018-05-18 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5604 | 25.3897 | مسحوب | Yes
2300238431 | وزارة الصحة | ترميم | ذات اولوية متوسطة | 662754 | 33137.7 | 0 | 0 | 1131002183 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 42 | 55 | 2022-10-13 | 2023-04-05 | 2023-04-05 | 2023-04-05 |  |  |  |  | 44.2055 | 26.7925 | متأخر | No
2100013882 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 21596388.1 | 1079819.405 | 7871231.69 | 4838244 | 5950013263 | لا | 0 | 180909073640 | جاري | الكميات التي تم تركيبها | 50.27 | 65 | 2015-08-02 | 2021-11-23 | 2023-03-31 | 2023-03-31 |  |  |  |  | 44.1907 | 17.5328 | متأخر | No
2300238361 | وزارة الصحة | ترميم | ذات اولوية متوسطة | 3064948 | 153247.4 | 0 | 0 | 4030151222 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 17 | 40 | 2022-12-01 | 2023-06-04 | 2023-08-06 | 2023-08-06 |  |  |  |  | 43.9702 | 26.3487 | متأخر | No
2100024544 | وزارة التعليم | تشييد | ذات اولوية عالية | 2656957.77 | 132847.8885 | 1629735.29 | 1629735.29 | 4030288443 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-05-20 | 2016-05-15 | 2021-12-23 | 2021-12-23 | 2016-05-15 |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | منجز | No
2100037181 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية | 252976514.58 | 12648825.729 | 0 | 0 | 1010609431 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 0 | 68.43 | 2015-01-08 | 2018-12-17 | 2026-12-31 | 2026-12-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.7288 | 27.5011 | Failed | No
2100195635 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 26205436.37 | 1310271.8185 | 15685032 | 15685032 | 1010194943 | لا | 0 | 201001222715 | جاري | الكميات التي تم تركيبها | 60 | 65 | 2021-01-18 | 2023-11-12 | 2023-11-12 | 2023-11-12 |  |  |  |  | 41.6995 | 27.4766 | منتظم | No
2100011303 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية | 366117190.35 | 18305859.5175 | 175321326.63 | 175321326.63 | 1010277276 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 53.95 | 56.3 | 2014-11-25 | 2018-11-03 | 2024-06-30 | 2024-06-30 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.5472 | 16.8945 | منتظم | No
2100098615 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 6584707.5 | 329235.375 | 1478774.27 | 1478774.27 | 4030023505 | لا | 0 | 190809095454 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 95.24 | 100 | 2019-07-06 | 2020-06-30 | 2021-03-19 | 2021-03-19 | 2020-06-30 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 49.5706 | 25.3706 | منجز | No
2100003500 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 12280363.12 | 614018.156 | 10956772.38 | 9700854.17 | 1010060469 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-12-13 | 2017-12-03 | 2019-03-06 | 2019-03-06 | 2017-12-03 |  |  |  | 39.6005 | 24.4595 | منجز | No
2100039966 | الهيئة الملكية للجبيل وينبع / مدينة جازان للصناعات الأساسية والتحويلية | تشييد | ذات اولوية متوسطة | 174866412.93 | 8743320.6465 | 40028941.35 | 40028941.35 | 2055014114 | لا | 0 | 190501147843 | جاري | الكميات التي تم تركيبها | 34.58 | 34.55 | 2020-03-11 | 2022-09-07 | 2024-07-16 | 2024-07-16 |  |  | اخرى |  | 42.3396 | 17.3519 | منتظم | No
2100094706 | الهيئة الملكية للجبيل وينبع / مدينة جازان للصناعات الأساسية والتحويلية | تشييد | ذات اولوية متوسطة | 61192698 | 3059634.9 | 55073427.73 | 55073427.73 | 4700004138 | لا | 0 | 190101009753 | جاري | تكلفة العمل المنجز | 93.7 | 93.57 | 2019-03-19 | 2021-03-18 | 2023-08-10 | 2023-08-10 |  |  | اخرى |  | 42.3396 | 17.3519 | منتظم | No
2200222725 | وزارة الدفاع / الإدارة الهندسية والاشغال بقوة الصواريخ الإستراتيجية | تصميم | ذات اولوية عالية وعاجلة | 1949595 | 97479.75 | 779836 | 779836 | 1010389317 | لا | 0 | 210439350011 | جاري | تكلفة العمل المنجز | 81 | 100 | 2021-11-01 | 2022-02-28 | 2023-03-02 | 2023-03-02 |  |  |  | تم تمديد الجدول الزمني | 40.3293 | 26.8578 | متأخر | No
2100001385 | وزارة التعليم | تشييد | ذات اولوية عالية | 21571420 | 1078571 | 8236265.41 | 7823146.22 | 4650020435 | لا | 0 |  | مسحوب | التكلفة المفوترة | 62 | 100 | 2014-11-15 | 2017-02-03 | 2023-06-15 | 2023-06-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | No
2100001912 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 18441724.7 | 922086.235 | 9617587.79 | 7496922.5 | 4650049177 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-02-28 | 2017-05-19 | 2021-04-02 | 2021-04-02 | 2017-05-19 |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | منجز | No
2100005585 | وزارة التعليم | تشييد | ذات اولوية عالية | 15612023.4 | 780601.17 | 11470044.4 | 10801849.22 | 1011008214 | لا | 0 |  | جاري | التكلفة المفوترة | 94 | 95 | 2016-03-14 | 2018-03-04 | 2022-11-17 | 2022-11-17 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6397 | 24.7487 | متأخر | No
2100008805 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 5432571.3 | 271628.565 | 5278121.98 | 5278121.98 | 1010211349 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2016-01-13 | 2017-06-13 | 2019-01-08 | 2019-01-08 | 2013-01-20 |  |  |  | 43.9544 | 26.3504 | منجز | No
2100089003 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 10855509 | 542775.45 | 3589344 | 3589344 | 1010095105 | لا | 0 |  | مسحوب | التكلفة المفوترة | 64 | 100 | 2015-08-31 | 2017-08-20 | 2022-08-16 | 2022-08-16 |  |  | ضعف كفاءة المقاول الفنية |  | 45.3525 | 25.8912 | مسحوب | No
2100096493 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 726463 | 36323.15 | 515600 | 515600 | 1118000760 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 92 | 90 | 2018-11-13 | 2019-05-12 | 2020-02-12 | 2020-02-12 | 2019-05-12 |  | اخرى |  | 42.9095 | 23.8972 | منجز | No
2100103165 | وزارة الداخلية / ديوان وزارة الداخلية | تصميم وتشييد | ذات اولوية عالية وعاجلة | 4371205569.05 | 218560278.4525 | 590512402 | 587257668 | 1010039386 | لا | 0 |  | مسحوب | التكلفة المفوترة | 6 | 68 | 2015-09-01 | 2019-12-04 | 2027-12-31 | 2027-12-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 46.7098 | 24.6275 | مسحوب | No
2100103434 | وزارة التعليم | تشييد | لم تعد تحتاجها الجهة | 40566383.45 | 2028319.1725 | 3772700 | 3772700 | 5855030665 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 9 | 42 | 2007-10-19 | 2010-04-07 | 2010-04-07 | 2010-04-07 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 46.7098 | 24.6275 | مسحوب | No
2300238766 | وزارة الدفاع / الإدارة الهندسية والاشغال بقوة الصواريخ الإستراتيجية | دراسات هندسية | ذات اولوية عالية وعاجلة | 780000 | 39000 | 0 | 0 | 4030235904 | لا | 0 | 211239467048 | جاري | تكلفة العمل المنجز | 2 | 8 | 2023-01-08 | 2023-04-06 | 2023-04-06 | 2023-04-06 |  |  |  |  | 43.068 | 25.8579 | خدمات عامة | No
2100009483 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 31411230 | 1570561.5 | 23977367.5 | 21667795 | 1010030949 | لا | 0 |  | مسحوب | التكلفة المفوترة | 66 | 88 | 2014-12-02 | 2016-11-21 | 2022-08-17 | 2022-08-17 |  |  | ضعف كفاءة المقاول الفنية |  | 45.3525 | 25.8912 | مسحوب | No
2100011911 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 6576804 | 328840.2 | 1429453 | 0 | 4650020435 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 30 | 100 | 2009-04-20 | 2010-12-13 | 2024-06-15 | 2024-06-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | مسحوب | Yes
2100016273 | الهيئة العامة للموانئ | تشييد | ذات اولوية عالية | 7996251 | 399812.55 | 5731592.84 | 5731592.84 | 2051023305 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 71 | 100 | 2012-08-22 | 2014-02-22 | 2022-12-31 | 2022-12-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 50.2151 | 26.4877 | مسحوب | No
2100016660 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 1995216 | 99760.8 | 1532215.88 | 1532215.88 | 1151000200 | لا | 0 |  | مسحوب | التكلفة المفوترة | 78 | 100 | 2009-12-09 | 2010-10-25 | 2023-11-11 | 2023-11-11 |  |  | ضعف كفاءة المقاول الفنية |  | 43.9544 | 26.3504 | مسحوب | No
2100016741 | وزارة التعليم | تشييد | ذات اولوية عالية | 15357533.93 | 767876.6965 | 11745857.1 | 11009974.55 | 1011008214 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 95 | 98 | 2016-03-14 | 2018-03-04 | 2022-08-04 | 2022-08-04 | 2018-03-04 |  | ضعف كفاءة المقاول الفنية |  | 46.6397 | 24.7487 | منجز | No
2100031916 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 11442164.7 | 572108.235 | 4426286.13 | 4426286.13 | 1010060469 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2018-09-19 | 2020-09-09 | 2021-01-31 | 2021-01-31 | 2020-09-09 |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | منجز | No
2100033121 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1892522 | 94626.1 | 1857231 | 1671397 | 2055004490 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2013-10-21 | 2018-10-01 | 2019-01-21 | 2019-01-21 | 2018-10-01 |  | ضعف كفاءة المقاول الفنية |  | 46.7271 | 22.2863 | منجز | No
2100042895 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1484910.67 | 74245.5335 | 511314.03 | 511314.03 | 1010261195 | لا | 0 |  | مسحوب | التكلفة المفوترة | 97 | 100 | 2013-10-20 | 2014-12-14 | 2024-07-29 | 2024-07-29 |  |  | ضعف كفاءة المقاول الفنية |  | 44.8241 | 26.3046 | مسحوب | No
2100058505 | وزارة التعليم | تشييد | ذات اولوية عالية | 10039304 | 501965.2 | 7955210 | 7955210 | 1010051817 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2012-11-16 | 2017-08-23 | 2017-08-23 | 2017-08-23 | 2017-08-23 |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | منجز | No
2100058796 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 981300 | 49065 | 250231.5 | 250231.5 | 5800003748 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 26 | 26 | 2015-06-23 | 2016-06-23 | 2019-10-27 | 2019-10-27 |  |  | ضعف كفاءة المقاول الفنية |  | 41.661 | 19.9966 | مسحوب | No
2100089725 | وزارة الداخلية / ديوان وزارة الداخلية | تصميم وتشييد | ذات اولوية عالية وعاجلة | 3225153628 | 161257681.4 | 654573978.87 | 651294989.14 | 1010039386 | لا | 0 |  | مسحوب | التكلفة المفوترة | 13 | 82 | 2014-10-23 | 2019-01-19 | 2027-12-31 | 2027-12-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 46.7098 | 24.6275 | مسحوب | No
2100100041 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2502453 | 125122.65 | 1251064.08 | 1251064.08 | 1010216996 | لا | 0 |  | مسحوب | التكلفة المفوترة | 65 | 100 | 2013-05-04 | 2014-09-04 | 2023-12-19 | 2023-12-19 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7271 | 22.2863 | مسحوب | No
2100034952 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 9203632 | 460181.6 | 540414.82 | 540414.82 | 4030023505 | لا | 0 | 190909006812 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-07-06 | 2020-12-27 | 2022-02-05 | 2022-02-05 | 2020-12-27 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 49.5865 | 25.3593 | منجز | No
2100015396 | الهيئة الملكية للجبيل وينبع / مدينة جازان للصناعات الأساسية والتحويلية | تشييد | ذات اولوية متوسطة | 66091938.03 | 3304596.9015 | 59450722.11 | 59450722.11 | 1010127437 | لا | 0 | 181201478866 | جاري | الكميات التي تم تركيبها | 98.82 | 98.01 | 2019-03-13 | 2022-03-12 | 2023-01-19 | 2023-01-19 |  |  | اخرى |  | 42.3208 | 17.3649 | منتظم | No
2300238840 | وزارة الصحة | توريد وتركيب | ذات اولوية عالية | 3174000 | 158700 | 0 | 0 | 4030109710 | لا | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 0 | 100 | 2022-05-27 | 2022-10-26 | 2023-03-01 | 2023-03-01 |  |  |  |  | 49.561 | 25.359 | Failed | No
2200213194 | الهيئة الملكية للجبيل وينبع / مدينة جازان للصناعات الأساسية والتحويلية | تشييد | ذات اولوية منخفضة | 120000000 | 6000000 | 27179835.38 | 27179835.38 | 2050004953 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 23.1 | 15.59 | 2021-10-13 | 2024-10-12 | 2024-10-12 | 2024-10-12 |  |  |  |  | 42.3606 | 17.3566 | منتظم | No
2100073662 | الهيئة الملكية للجبيل وينبع / مدينة جازان للصناعات الأساسية والتحويلية | تشييد | ذات اولوية عالية | 104556133.14 | 5227806.657 | 47070424.31 | 47070424.31 | 1010127437 | لا | 0 | 190501147843 | جاري | الكميات التي تم تركيبها | 36.24 | 25.89 | 2020-02-27 | 2022-08-28 | 2024-12-21 | 2024-12-21 |  |  | اخرى |  | 42.3366 | 17.3469 | منتظم | No
2300238755 | وزارة الدفاع / الإدارة الهندسية والاشغال بقوة الصواريخ الإستراتيجية | تصميم | ذات اولوية عالية وعاجلة | 2350000 | 117500 | 587500 | 587500 | 1010576526 | لا | 0 | 210539352709 | جاري | تكلفة العمل المنجز | 35 | 70 | 2022-08-23 | 2023-02-16 | 2023-02-16 | 2023-02-16 |  |  |  |  | 42.854 | 21.2627 | Failed | No
2100189615 | الهيئة الملكية للجبيل وينبع / مدينة جازان للصناعات الأساسية والتحويلية | تصميم وتشييد | ذات اولوية عالية وعاجلة | 94450018 | 4722500.9 | 23119818.18 | 23119818.18 | 2054000121 | لا | 0 | 191001219355 | جاري | الكميات التي تم تركيبها | 3.52 | 91.4 | 2020-07-15 | 2023-07-15 | 2025-10-01 | 2025-10-01 |  |  |  | تم تمديد الجدول الزمني | 42.4079 | 17.3224 | Failed | No
2300238884 | الهيئة الملكية للجبيل وينبع / مدينة جازان للصناعات الأساسية والتحويلية | تصميم وتشييد | ذات اولوية عالية وعاجلة | 1598888888.88 | 79944444.444 | 159888888.88 | 0 | 0 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 0 | 0 | 2022-12-19 | 2026-06-11 | 2026-06-11 | 2026-06-11 |  |  |  |  | 42.3684 | 17.3131 | منتظم | Yes
2100065505 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 84725500 | 4236275 | 82884793.45 | 82884793.45 | 4650033361 | لا | 0 |  | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-10-24 | 2023-10-23 | 2023-10-23 | 2023-10-23 |  |  | ضعف كفاءة المقاول الفنية |  | 39.5515 | 24.4418 | منتظم | No
2100108511 | وزارة الدفاع / الإدارة العامة للمرافق والشؤون الهندسية | تشييد | ذات اولوية متوسطة | 477025497.81 | 23851274.8905 | 392729583.86 | 311243043.07 | 1010070634 | لا | 0 | 180709035060 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-05-14 | 2017-10-21 | 2021-03-01 | 2021-03-01 | 2017-10-21 |  | تأخرصرف المستحقات المالية |  | 40.4511 | 21.2747 | منجز | No
2100025502 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 2826064.5 | 141303.225 | 1757948.1 | 1757948.1 | 4650032626 | لا | 0 | 200501038624 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 75 | 100 | 2019-04-06 | 2020-03-31 | 2021-05-26 | 2021-05-26 | 2020-03-31 |  | ضعف كفاءة المقاول الفنية |  | 42.4516 | 27.8599 | منجز | No
2100071503 | أمانة / الجوف | تشييد | ذات اولوية عالية | 4657953.63 | 232897.6815 | 4376240 | 3934585 | 3402001019 | لا | 0 | 181001119581 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-11-19 | 2019-07-15 | 2020-01-22 | 2020-01-22 | 2019-07-15 |  | أوامر تغيير |  | 37.3579 | 31.3167 | منجز | No
2100020926 | وزارة الحرس الوطني / الشؤون الفنية بالقطاع الشرقي | تشييد | ذات اولوية عالية | 15344476.29 | 767223.8145 | 15266806.29 | 12367059.66 | 2051027499 | لا | 0 | 190701095937 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-09-01 | 2020-11-30 | 2022-09-30 | 2022-09-30 | 2020-11-30 |  |  |  | 50.1669 | 26.3619 | منجز | No
2100071912 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 5998529.05 | 299926.4525 | 3174157.35 | 3174157.35 | 5950006647 | لا | 0 | 221009014884 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-05-08 | 2021-11-11 | 2021-11-12 | 2021-11-12 | 2021-11-11 |  | اخرى |  | 44.2298 | 17.5572 | منجز | No
2100058892 | وزارة الحرس الوطني / الشؤون الفنية بالقطاع الشرقي | تشييد | ذات اولوية عالية | 14696465.51 | 734823.2755 | 11529313.14 | 11529313.14 | 2050024197 | لا | 0 | 180501009333 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-08-13 | 2019-04-06 | 2022-04-30 | 2022-04-30 | 2019-04-06 |  | تأخرصرف المستحقات المالية |  | 49.5388 | 25.4406 | منجز | No
2100062333 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 4091750 | 204587.5 | 4091750 | 4091750 | 2060016250 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-04-15 | 2020-03-15 | 2020-02-25 | 2020-02-25 | 2020-03-15 |  |  |  | 49.4718 | 25.9952 | منجز | No
2100059614 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 1721077.5 | 86053.875 | 1415259 | 889902 | 3555000646 | لا | 0 | 190709075923 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2016-02-19 | 2017-11-18 | 2020-05-17 | 2020-05-17 | 2017-11-18 |  | اخرى |  | 36.5984 | 28.4096 | منجز | No
2100002354 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 978915 | 48945.75 | 800741 | 800741 | 4650060073 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 82 | 100 | 2020-01-11 | 2020-07-04 | 2021-08-29 | 2021-08-29 | 2020-07-04 |  |  |  | 36.5633 | 28.4607 | منجز | No
2100064960 | أمانة / تبوك | تشييد | لم تعد تحتاجها الجهة | 986385.75 | 49319.2875 | 986386 | 986386 | 4700010229 | لا | 0 | 190401068773 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-07-27 | 2020-07-21 | 2020-07-22 | 2020-07-22 | 2020-07-21 |  | ضعف كفاءة المقاول الفنية |  | 36.5641 | 28.364 | منجز | No
2100026445 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 1399965 | 69998.25 | 1000850 | 1000850 | 7012309774 | لا | 0 | 210601172735 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-09-01 | 2021-02-13 | 2021-02-13 | 2021-02-13 | 2021-02-13 |  | اخرى |  | 44.235 | 17.5502 | منجز | No
2100017146 | وزارة الحرس الوطني / الشؤون الفنية بالقطاع الشرقي | ترميم | ذات اولوية عالية | 12499732.52 | 624986.626 | 12499722 | 11219097.17 | 2060023127 | لا | 0 | 190801034125 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-10-07 | 2020-10-23 | 2021-11-29 | 2021-11-29 | 2020-10-23 |  |  |  | 50.1613 | 26.388 | منجز | No
2100046852 | أمانة / تبوك | تشييد | لم تعد تحتاجها الجهة | 106496.25 | 5324.8125 | 106496.25 | 106496.25 | 3550028240 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-05-20 | 2020-12-30 | 2019-03-17 | 2019-03-17 | 2020-12-30 |  | اخرى |  | 36.5249 | 28.4186 | منجز | No
2100012154 | أمانة / تبوك | تشييد | ذات اولوية عالية | 2867430 | 143371.5 | 700100 | 700100 | 1010346422 | لا | 0 | 181209447079 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 87 | 100 | 2015-02-28 | 2016-08-21 | 2021-04-21 | 2021-04-21 | 2016-08-21 |  | ضعف كفاءة المقاول الفنية |  | 36.5577 | 28.4727 | منجز | No
2100081992 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 3406842.5 | 170342.125 | 867750.9 | 867750.9 | 5950019273 | لا | 0 | 200309004991 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 65.1 | 70 | 2019-12-20 | 2022-01-03 | 2022-11-11 | 2022-11-11 | 2022-01-03 |  |  |  | 44.2177 | 17.5825 | منجز | No
2100054493 | أمانة / تبوك | تشييد | ذات اولوية عالية | 12834740 | 641737 | 9418927 | 9418927 | 4650032626 | لا | 0 | 180809045686 | مسحوب | الكميات التي تم تركيبها | 80.01 | 100 | 2014-07-20 | 2016-07-09 | 2021-05-30 | 2021-05-30 |  |  | تأخرصرف المستحقات المالية |  | 38.5165 | 27.6122 | مسحوب | No
2100035862 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 10966690 | 548334.5 | 10966690 | 10966690 | 4030201495 | لا | 0 | 181009144290 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-08-31 | 2019-09-11 | 2019-05-12 | 2019-05-12 | 2019-09-11 |  | اخرى |  | 38.5044 | 27.6278 | منجز | No
2300238895 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 806306.4 | 40315.32 | 0 | 0 | 0 | لا | 0 |  | جاري | تكلفة العمل المنجز | 60 | 52 | 2022-08-18 | 2023-06-09 | 2023-06-09 | 2023-06-09 |  |  |  |  | 49.5687 | 26.9598 | منتظم | No
2300238906 | الهيئة الملكية للجبيل وينبع / مدينة جازان للصناعات الأساسية والتحويلية | تصميم وتشييد | ذات اولوية عالية وعاجلة | 1598888888.88 | 79944444.444 | 159888888.88 | 0 | 2051035332 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 0 | 0 | 2022-12-19 | 2026-06-11 | 2026-06-11 | 2026-06-11 |  |  |  |  | 42.5363 | 17.374 | منتظم | Yes
2100045345 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 21844134 | 1092206.7 | 21844134 | 21844134 | 5950018186 | لا | 0 | 181209477572 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-07-17 | 2020-07-16 | 2020-07-07 | 2020-07-07 | 2020-07-16 |  | اخرى |  | 44.2159 | 17.5862 | منجز | No
2100039712 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 21312971.1 | 1065648.555 | 8209346.98 | 8209346.98 | 5950013363 | لا | 0 | 180909073640 | جاري | تكلفة العمل المنجز | 50.27 | 55 | 2015-08-30 | 2021-11-30 | 2023-03-31 | 2023-03-31 |  |  | نزع الملكيات |  | 44.2074 | 17.5474 | متأخر | No
2100004163 | مدينة الملك عبدالله الطبية بالعاصمة المقدسة | دراسة الجدوى | ذات اولوية عالية | 2099769 | 104988.45 | 0 | 0 | 1010358934 | لا | 0 | 190901190907 | ايقاف كلي | مدفوعات ساعات العمل | 0 | 0 | 2021-07-29 | 2022-07-29 | 2023-07-29 | 2023-07-29 |  |  | تغيرات في نطاق المشروع | لم يتم اتخاذ أي إجراء |  |  | Failed | No
2100194950 | الهيئة العامة للطيران المدني | توريد وتركيب | ذات اولوية عالية وعاجلة | 10763994.78 | 538199.739 | 7127448.66 | 5955112.79 | 1010437469 | لا | 0 | 190201008264 | لم يبدأ | تكلفة العمل المنجز | 92 | 96 | 2019-03-24 | 2021-11-30 | 2021-11-30 | 2021-11-30 |  |  |  |  | 46.7054 | 24.9405 | Failed | No
2100040235 | شركة المياه الوطنية / منطقة نجران | تشييد | ذات اولوية عالية | 47707908.41 | 2385395.4205 | 37640368.3 | 37640368.3 | 4030021112 | لا | 0 | 180709030339 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99 | 100 | 2012-07-08 | 2014-12-10 | 2020-01-28 | 2020-01-28 | 2014-12-10 |  | لا يوجد تأخير |  | 44.2341 | 17.5757 | منجز | No
2100073463 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 35110503.5 | 1755525.175 | 3349930 | 3349930 | 5950000060 | لا | 0 | 190801017385 | ايقاف جزئي | تكلفة العمل المنجز | 26.5 | 30 | 2019-08-24 | 2022-03-01 | 2022-09-11 | 2022-09-11 |  |  | التنسيق مع أصحاب المصلحه (خدمات |  | 44.2368 | 17.5566 | Failed | No
2100074130 | وزارة الداخلية / ديوان وزارة الداخلية | إشراف | ذات اولوية عالية وعاجلة | 1217418346.67 | 60870917.3335 | 1155594622.54 | 1155594622.54 | 1010330192 | لا | 0 |  | ايقاف كلي | منهجية القيمة المكتسبة | 94.47 | 100 | 2011-12-20 | 2015-04-20 | 2022-09-25 | 2022-09-25 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  |  |  | Failed | No
2100090856 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 1150000 | 57500 | 1147125 | 1147125 | 2050111809 | لا | 0 | 190709027090 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-03-18 | 2020-05-14 | 2020-05-14 | 2020-05-14 | 2020-05-14 |  | اخرى |  | 50.0039 | 26.5524 | منجز | No
2100032911 | شركة المياه الوطنية / منطقة نجران | تشييد | ذات اولوية عالية | 56037250 | 2801862.5 | 20764840 | 20764840 | 5950008379 | لا | 0 | 180709022515 | مسحوب | منهجية القيمة المكتسبة | 40 | 100 | 2015-06-21 | 2017-11-22 | 2024-04-17 | 2024-04-17 |  |  | ضعف كفاءة المقاول الفنية |  | 44.2341 | 17.5757 | مسحوب | No
2100097624 | شركة المياه الوطنية / منطقة نجران | تشييد | ذات اولوية عالية | 46412250 | 2320612.5 | 42112365.55 | 42112365.55 | 5950000060 | لا | 0 | 181009197930 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 84.2 | 100 | 2014-12-14 | 2017-11-11 | 2021-09-30 | 2021-09-30 | 2017-11-11 |  | لا يوجد تأخير |  | 44.2341 | 17.5757 | منجز | No
2100009995 | شركة المياه الوطنية / منطقة نجران | إشراف | ذات اولوية عالية | 14198400 | 709920 | 14198400 | 14198400 | 7001854525 | لا | 0 | 180301000911 | جاري | التكلفة المفوترة | 100 | 100 | 2018-06-07 | 2021-06-08 | 2022-06-08 | 2022-06-08 |  |  | لا يوجد تأخير |  | 44.2073 | 17.5284 | خدمات عامة | No
2100003986 | شركة المياه الوطنية / منطقة نجران | تشييد | ذات اولوية عالية | 53072818.5 | 2653640.925 | 51735643.44 | 51735643.44 | 5950002185 | لا | 0 | 180709025941 | منجز – استلام نهائي | منهجية القيمة المكتسبة | 99.98 | 100 | 2014-12-11 | 2017-05-15 | 2020-03-02 | 2020-03-02 | 2017-05-15 | 2021-02-22 | لا يوجد تأخير |  | 44.2341 | 17.5757 | منجز | No
2100205866 | وزارة الحرس الوطني / وكالة الشؤون الفنية | إشراف | ذات اولوية متوسطة | 12567360 | 628368 | 1751315.92 | 1333110.65 | 1010395124 | لا | 0 |  | جاري | التكلفة المفوترة | 11 | 14 | 2022-02-01 | 2025-12-18 | 2025-12-18 | 2025-12-18 |  |  |  |  | 46.8745 | 24.7361 | خدمات عامة | No
2100011760 | وزارة الدفاع / الإدارة الهندسية والاشغال بقوة الصواريخ الإستراتيجية | تشييد | ذات اولوية عالية | 218460415 | 10923020.75 | 158603594.8 | 158603594.8 | 2050011871 | لا | 0 | 181109344667 | جاري | الكميات التي تم تركيبها | 99 | 100 | 2014-12-04 | 2016-05-27 | 2023-01-31 | 2023-01-31 |  |  | نزع الملكيات | تم تمديد الجدول الزمني | 44.3945 | 24.5044 | Failed | No
2100098932 | وزارة الصحة / التجمع الاول | توريد وتركيب | ذات اولوية متوسطة | 4200000 | 210000 | 4200000 | 4200000 | 4030109710 | لا | 0 |  | لم يبدأ | الكميات التي تم تركيبها | 100 | 100 | 2019-12-04 | 2019-09-10 | 2021-08-30 | 2021-08-30 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 46.6893 | 24.6274 | Failed | No
2100013624 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 4945000 | 247250 | 2634016 | 2634016 | 5950007941 | لا | 0 | 181209477572 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 99 | 100 | 2019-04-20 | 2020-11-23 | 2022-10-09 | 2022-10-09 | 2020-11-23 |  | تأخرصرف المستحقات المالية |  | 44.2172 | 17.5515 | منجز | No
2100100936 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 14435166 | 721758.3 | 14435166 | 14435166 | 5950001999 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-01-20 | 2020-01-20 | 2020-01-20 | 2020-01-20 | 2020-01-20 |  | ضعف كفاءة المقاول الفنية |  | 44.2153 | 17.5591 | منجز | No
2100082106 | أمانة / نجران | تشييد | ذات اولوية عالية | 73503846.79 | 3675192.3395 | 62566009.98 | 46137663.69 | 5950002027 | لا | 0 | 180709017380 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 90.04 | 95 | 2015-07-29 | 2020-06-30 | 2022-09-11 | 2022-09-11 | 2020-06-30 |  | ضعف كفاءة المقاول الفنية |  | 44.2038 | 17.5498 | منجز | No
2100020020 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 12746150 | 637307.5 | 12746150 | 12746150 | 3552000023 | لا | 0 | 181009135186 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-10-06 | 2017-03-20 | 2018-11-04 | 2018-11-04 | 2017-03-20 |  | اخرى |  | 36.4689 | 26.2366 | منجز | No
2100020506 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 12935365 | 646768.25 | 12935565 | 12935565 | 4650032626 | لا | 0 | 190309006641 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-04-08 | 2015-09-21 | 2020-02-25 | 2020-02-25 | 2015-09-21 |  | ضعف كفاءة المقاول الفنية |  | 36.4689 | 26.2366 | منجز | No
2100053384 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 8537173 | 426858.65 | 4804858.97 | 4074210.25 | 5950007285 | لا | 0 | 180809042700 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 98.53 | 100 | 2014-03-23 | 2021-08-30 | 2022-12-13 | 2022-12-13 |  |  |  |  | 44.2261 | 17.5615 | متأخر | No
2100101216 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 45913026.3 | 2295651.315 | 39744499 | 39744499 | 3555000709 | لا | 0 | 180809056623 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 99.88 | 100 | 2017-09-28 | 2019-09-27 | 2023-02-04 | 2023-02-04 |  |  | أوامر تغيير |  | 38.3998 | 23.9235 | منتظم | No
2100027602 | وزارة العدل | تشييد | ذات اولوية عالية | 32734422 | 1636721.1 | 0 | 0 | 1131022493 | نعم | 18137729.8 | 180801061788 | مسحوب | تكلفة العمل المنجز | 0.28 | 0 | 2018-05-08 | 2020-05-07 | 2020-05-07 | 2020-05-07 |  |  | اخرى | أخرى | 45.9753 | 28.4253 | مسحوب | No
2100057525 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية | 1602946313.11 | 80147315.6555 | 2932711.27 | 2932711.27 | 1010609431 | لا | 0 |  | ايقاف كلي | منهجية القيمة المكتسبة | 0.2 | 0.2 | 2015-03-05 | 2019-02-11 | 2022-12-31 | 2022-12-31 |  |  | عدم وجود مبالغ في البنود تغطي الأعمال المرصودة |  | 39.8937 | 21.3571 | Failed | No
2100070836 | وزارة الداخلية / المديرية العامة للدفاع المدني | تشييد | ذات اولوية عالية | 16795104.77 | 839755.2385 | 16795104.77 | 16795104.76 | 1010219247 | لا | 0 | 190501000792 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-01-21 | 2019-12-12 | 2022-07-01 | 2022-07-01 | 2019-12-12 |  | تأخرصرف المستحقات المالية |  | 46.6614 | 24.541 | منجز | No
2100075622 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 4241861.25 | 212093.0625 | 3061940 | 3061940 | 2051043445 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-08-11 | 2020-01-07 | 2021-06-24 | 2021-06-24 | 2020-01-07 |  |  |  | 50.0085 | 26.555 | منجز | No
2200228362 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 269643.37 | 13482.1685 | 269643.37 | 269643.37 | 2251032226 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2022-05-09 | 2022-11-05 | 2022-11-05 | 2022-11-05 | 2022-11-05 |  |  |  | 48.2846 | 26.7644 | منجز | No
2100085750 | وزارة العدل | تشييد | ذات اولوية عالية وعاجلة | 727239686.95 | 36361984.3475 | 314814047 | 314814047 | 1010021034 | لا | 0 | 180809058141 | فسخ العقد | تكلفة العمل المنجز | 83.69 | 92.15 | 2014-12-21 | 2017-08-21 | 2023-04-30 | 2023-04-30 |  |  | تأخرصرف المستحقات المالية |  | 44.4489 | 24.546 | مسحوب | No
2200213371 | أمانة / الجوف | أخرى | ذات اولوية عالية وعاجلة | 8378600 | 418930 | 1427100 | 1427100 | 3400009825 | لا | 0 | 210901081726 | جاري | تكلفة العمل المنجز | 50 | 60 | 2020-12-03 | 2022-05-27 | 2023-05-29 | 2023-05-29 |  |  |  |  | 40.1043 | 29.878 | خدمات عامة | No
2100081233 | أمانة / الجوف | تشييد | ذات اولوية عالية وعاجلة | 2687200 | 134360 | 2687200 | 2687200 | 3404008078 | لا | 0 | 181109367229 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-10-28 | 2019-10-22 | 2019-10-22 | 2019-10-22 | 2019-10-22 |  |  |  | 39.8767 | 29.8117 | منجز | No
2100084534 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 43989777 | 2199488.85 | 41790278 | 41790278 | 5950011723 | لا | 0 | 180809057970 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 99.2 | 100 | 2017-09-12 | 2019-09-12 | 2023-01-19 | 2023-01-19 |  |  | ضعف كفاءة المقاول الفنية |  | 38.3319 | 23.9697 | Failed | No
2200219936 | وزارة الحرس الوطني / وكالة الشؤون الفنية | تشييد | ذات اولوية متوسطة | 23851550 | 1192577.5 | 641672.78 | 74822.27 | 1010032177 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 8 | 25 | 2022-03-09 | 2023-08-22 | 2023-08-22 | 2023-08-22 |  |  |  |  | 46.6828 | 24.7075 | متأخر | No
2100020344 | أمانة / تبوك | تصميم | ذات اولوية متوسطة | 45147 | 2257.35 | 43298 | 0 | 1010435343 | لا | 0 | 190909104488 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-04-07 | 2019-08-05 | 2019-12-08 | 2019-12-08 | 2019-08-05 |  | اخرى |  | 37.187 | 27.0479 | منجز | Yes
2100036385 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 3268335 | 163416.75 | 2086789.93 | 2086788 | 2051033934 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-12-25 | 2021-11-18 | 2022-05-13 | 2022-05-13 | 2021-11-18 |  | أوامر تغيير |  | 44.2098 | 17.5417 | منجز | No
2100085444 | أمانة / تبوك | تصميم | ذات اولوية متوسطة | 39375 | 1968.75 | 39375 | 39375 | 3550034877 | لا | 0 | 190909104488 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-05-02 | 2019-10-29 | 2019-10-29 | 2019-10-29 | 2019-10-29 |  | اخرى |  | 37.187 | 27.0479 | منجز | No
2100089994 | أمانة / تبوك | دراسة الجدوى | ذات اولوية متوسطة | 220500 | 11025 | 220500 | 220500 | 1010463231 | لا | 0 | 190609000000 | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2019-08-22 | 2020-08-16 | 2020-08-16 | 2020-08-16 | 2020-08-16 |  | اخرى |  | 37.187 | 27.0479 | منجز | No
2100201935 | الجمارك السعودية | تشييد | ذات اولوية عالية | 6309666.31 | 315483.3155 | 3945055.5 | 3945055.5 | 1010203140 | لا | 0 |  | جاري | تكلفة العمل المنجز | 98 | 100 | 2021-09-26 | 2024-01-22 | 2024-01-22 | 2024-01-22 |  |  |  |  | 41.4406 | 31.378 | منتظم | No
2100040106 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 49322530.62 | 2466126.531 | 34143478 | 34143478 | 1010135922 | لا | 0 | 181001128541 | جاري | منهجية القيمة المكتسبة | 97 | 100 | 2018-12-26 | 2020-12-25 | 2023-02-18 | 2023-02-18 |  |  | منازعات قائمة |  | 38.22 | 24.0285 | منتظم | No
2100064746 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 3074162 | 153708.1 | 1743049.8 | 1685508.3 | 5950017363 | لا | 0 | 210501030518 | مسحوب | تكلفة العمل المنجز | 59 | 100 | 2019-09-12 | 2021-07-04 | 2022-12-17 | 2022-12-17 |  |  |  |  | 47.108 | 17.4898 | مسحوب | No
2300238324 | وزارة الحرس الوطني / وكالة الشؤون الفنية | تشييد | ذات اولوية متوسطة | 326140 | 16307 | 0 | 0 | 5950025168 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 0 | 0 | 2022-11-06 | 2023-05-01 | 2023-05-01 | 2023-05-01 |  |  |  | لم يتم اتخاذ أي إجراء |  |  | منتظم | No
2100096316 | وزارة العدل | تشييد | ذات اولوية عالية وعاجلة | 322959490.26 | 16147974.513 | 63941065.62 | 63941065.62 | 1010154193 | لا | 0 | 180809060936 | مسحوب | تكلفة العمل المنجز | 39.35 | 0 | 2014-10-25 | 2017-05-26 | 2024-06-02 | 2024-06-02 |  |  | اخرى | مخطط لإعادة طرحه | 49.5585 | 25.6158 | مسحوب | No
2300238921 | أمانة / الجوف | تشييد | ذات اولوية عالية | 3786030 | 189301.5 | 517155 | 517155 | 7001398846 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 45 | 43 | 2022-09-18 | 2023-05-16 | 2023-05-16 | 2023-05-16 |  |  |  |  | 38.2216 | 30.5155 | منتظم | No
2200229530 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 84224438.45 | 4211221.9225 | 59799351.3 | 59799351.3 | 3555000709 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 71 | 75 | 2018-12-25 | 2024-01-08 | 2024-01-08 | 2024-01-08 |  |  |  |  | 39.5559 | 24.5008 | منتظم | No
2200220765 | المؤسسة العامة للتأمينات الاجتماعية | ترميم | ذات اولوية متوسطة | 1264881 | 63244.05 | 0 | 0 | 1010087837 | لا | 0 |  | ايقاف كلي | منهجية القيمة المكتسبة | 75 | 100 | 2021-10-30 | 2022-06-29 | 2022-08-31 | 2022-08-31 |  |  |  |  | 50.218 | 26.3812 | Failed | No
2100042044 | المؤسسة العامة للتأمينات الاجتماعية | إشراف | ذات اولوية عالية | 24500000 | 1225000 | 22832445.43 | 22832445.43 | 1010085518 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2017-01-15 | 2018-12-16 | 2021-02-28 | 2021-02-28 | 2018-12-16 |  | أوامر تغيير |  | 46.6753 | 24.7136 | منجز | No
2300238910 | أمانة / الجوف | تشييد | ذات اولوية عالية | 1035000 | 51750 | 0 | 0 | 7016239464 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 40 | 44 | 2022-11-21 | 2023-02-19 | 2023-02-19 | 2023-02-19 |  |  |  |  | 38.2216 | 30.5155 | منتظم | No
2100064293 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 18180999.9 | 909049.995 | 11999459.93 | 11999459.93 | 4650050716 | لا | 0 |  | ايقاف جزئي | تكلفة العمل المنجز | 66 | 77 | 2019-10-16 | 2023-04-11 | 2023-04-11 | 2023-04-11 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6154 | 24.4664 | متأخر | No
2100040714 | وزارة الصحة/ الاحساء | تشييد | ذات اولوية متوسطة | 16463262 | 823163.1 | 6462901.06 | 4087311.97 | 2051043740 | لا | 0 | 190401115712 | جاري | تكلفة العمل المنجز | 80 | 20 | 2019-10-26 | 2021-10-04 | 2023-03-01 | 2023-03-01 |  |  | اخرى |  | 49.5533 | 25.4569 | متأخر | No
2300238851 | وزارة الصحة | توريد وتركيب | ذات اولوية عالية | 2200000 | 110000 | 0 | 0 | 2051053469 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 25 | 75 | 2022-06-22 | 2022-12-21 | 2023-03-16 | 2023-03-16 |  |  |  |  | 49.5607 | 25.3583 | Failed | No
2300238932 | وزارة الصحة | إشراف | ذات اولوية متوسطة | 2652800 | 132640 | 2441020.92 | 2440369.31 | 0 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 0 | 2019-10-28 | 2021-10-27 | 2021-10-27 | 2021-10-27 | 2021-10-27 |  |  |  | 49.5523 | 25.4566 | منجز | No
2100020403 | مدينة الملك فهد الطبية | توريد وتركيب | ذات اولوية عالية | 114545781.53 | 5727289.0765 | 110248703.96 | 94100196.92 | 1010359384 | لا | 0 |  | جاري | اخرى | 58 | 100 | 2012-12-25 | 2022-10-22 | 2022-10-20 | 2022-10-20 |  |  | لا يوجد تأخير |  | 46.7038 | 24.6873 | Failed | No
2100034635 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 24281581 | 1214079.05 | 12741102.66 | 12741102.66 | 5950009827 | لا | 0 | 190201021530 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 62 | 100 | 2019-05-11 | 2020-11-10 | 2022-09-11 | 2022-09-11 | 2020-11-10 |  | ضعف كفاءة المقاول الفنية |  | 44.2384 | 17.5919 | منجز | No
2100064890 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 990642 | 49532.1 | 990642 | 990642 | 5950006099 | لا | 0 | 210501030518 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-12-08 | 2020-11-26 | 2020-11-26 | 2020-11-26 | 2020-11-26 |  | تأخرصرف المستحقات المالية |  | 44.0291 | 17.8508 | منجز | No
2100038006 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 70823374.7 | 3541168.735 | 64826273.93 | 64826273.93 | 1010184457 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2009-06-24 | 2012-05-21 | 2019-03-07 | 2019-03-07 | 2012-05-21 | 2021-09-02 |  |  | 39.8473 | 21.3546 | منجز | No
2300238943 | وزارة الصحة | توريد وتركيب | ذات اولوية عالية | 500825 | 25041.25 | 500825 | 500825 | 0 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 0 | 2021-08-23 | 2022-04-15 | 2022-04-15 | 2022-04-15 | 2022-04-15 |  |  |  | 49.5612 | 25.3575 | منجز | No
2100016424 | وزارة الحرس الوطني / جامعة الملك سعود بن عبدالعزيز للعلوم الصحية | تصميم وتشييد | ذات اولوية عالية | 18972552485 | 948627624.25 | 17583307937.23 | 17583307937.23 | 4030068284 | لا | 0 | 200309042512 | جاري | الكميات التي تم تركيبها | 95 | 100 | 2008-12-25 | 2011-12-24 | 2023-12-01 | 2023-12-01 |  |  | تأخرصرف المستحقات المالية |  | 46.8527 | 24.7543 | Failed | No
2100193325 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 4982610 | 249130.5 | 4982460.02 | 4982460.02 | 4030209372 | لا | 0 | 180301000483 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-03-05 | 2018-05-24 | 2021-12-31 | 2021-12-31 |  |  |  |  | 39.239 | 21.4933 | Failed | No
2100192614 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 20361475.9 | 1018073.795 | 19493356.84 | 17886801.97 | 5950006666 | لا | 0 | 180709015760 | جاري | تكلفة العمل المنجز | 100 | 100 | 2018-01-28 | 2019-01-17 | 2022-12-31 | 2022-12-31 |  |  |  |  | 39.2391 | 21.4933 | منتظم | No
2100014114 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 15809219.15 | 790460.9575 | 13083146.23 | 12668503.32 | 1010251358 | لا | 0 | 180709015890 | جاري | تكلفة العمل المنجز | 93.5 | 100 | 2017-05-03 | 2018-04-28 | 2022-12-31 | 2022-12-31 |  |  | تأخرصرف المستحقات المالية |  | 39.1677 | 21.5008 | متأخر | No
2100059231 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 18917012.79 | 945850.6395 | 16198514.62 | 16198514.62 | 4031069720 | لا | 0 | 180709016759 | جاري | تكلفة العمل المنجز | 97.28 | 100 | 2017-10-24 | 2018-10-13 | 2023-06-30 | 2023-06-30 |  |  | تأخرصرف المستحقات المالية |  | 39.1677 | 21.5008 | منتظم | No
2100032001 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 105448375.74 | 5272418.787 | 71081189.86 | 69609961.37 | 2051027134 | لا | 0 | 180709016774 | جاري | تكلفة العمل المنجز | 70 | 87 | 2017-08-06 | 2019-07-27 | 2023-12-31 | 2023-12-31 |  |  | تأخرصرف المستحقات المالية |  | 39.1677 | 21.5008 | متأخر | No
2100052065 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 26358109.32 | 1317905.466 | 26231568.23 | 26231568.23 | 1010196414 | لا | 0 | 180709016816 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-05-28 | 2019-05-18 | 2021-12-31 | 2021-12-31 |  |  | تأخرصرف المستحقات المالية |  | 39.1677 | 21.5008 | Failed | No
2100193233 | وزارة الحرس الوطني / وكالة الشؤون الفنية | هدم و ازالة | ذات اولوية متوسطة | 226837.5 | 11341.875 | 226837.5 | 226837.5 | 2511003200 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2021-03-14 | 2021-06-11 | 2021-06-11 | 2021-06-11 | 2021-06-11 | 2022-06-09 |  |  | 43.5409 | 29.6198 | منجز | No
2100096994 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 14709367.28 | 735468.364 | 3025708.75 | 3025708.75 | 4030123131 | لا | 0 | 180709016839 | جاري | تكلفة العمل المنجز | 38.7 | 64 | 2017-10-03 | 2018-07-23 | 2024-12-31 | 2024-12-31 |  |  | تأخرصرف المستحقات المالية |  | 39.1677 | 21.5008 | Failed | No
2100099680 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 48432600 | 2421630 | 28304461.59 | 28304461.59 | 5950006860 | لا | 0 | 190401021636 | جاري | تكلفة العمل المنجز | 70.49 | 75 | 2019-09-15 | 2023-03-23 | 2023-03-23 | 2023-03-23 |  |  | اخرى |  | 44.2251 | 17.5545 | منتظم | No
2100103456 | جامعة الباحة | تشييد | ذات اولوية عالية | 407717230 | 20385861.5 | 73555046 | 73555046 | 1010247052 | لا | 0 | 400820000474 | ايقاف كلي | الكميات التي تم تركيبها | 20 | 20 | 2012-03-31 | 2015-03-31 | 2022-05-01 | 2022-05-01 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 20.9517 | 42.0258 | Failed | No
2100092875 | أمانة / تبوك | تشييد | ذات اولوية عالية | 3409645 | 170482.25 | 1583000 | 1583000 | 3553000678 | لا | 0 | 181209444228 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 87 | 100 | 2015-10-21 | 2017-04-13 | 2021-09-29 | 2021-09-29 | 2017-04-13 |  | تأخرصرف المستحقات المالية |  | 34.9461 | 29.2798 | منجز | No
2100025815 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 224000 | 11200 | 194500 | 0 | 3553000678 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-03-29 | 2020-03-23 | 2021-05-05 | 2021-05-05 | 2020-03-23 |  |  |  | 34.9451 | 29.2864 | منجز | Yes
2100070302 | صندوق تنمية الموارد البشرية | تشييد | ذات اولوية منخفضة | 29685673.35 | 1484283.6675 | 12995243.21 | 12995243.21 | 1010145283 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 72.5 | 100 | 2015-02-03 | 2017-01-11 | 2021-09-09 | 2021-09-09 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.8565 | 21.389 | مسحوب | No
2100032012 | أمانة / نجران | تشييد | ذات اولوية عالية | 35367046.5 | 1768352.325 | 21771852.87 | 21771852.87 | 5950009685 | لا | 0 | 190401080025 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 97 | 100 | 2019-02-03 | 2020-07-18 | 2021-05-22 | 2021-05-22 | 2020-07-18 |  | ضعف كفاءة المقاول الفنية |  | 44.2439 | 17.5611 | منجز | No
2100060465 | جامعة الباحة | تشييد | ذات اولوية متوسطة | 1456000 | 72800 | 798000 | 798000 | 5810001890 | لا | 0 | 181001207295 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-12-16 | 2021-09-19 | 2022-05-17 | 2022-05-17 | 2021-09-19 |  |  |  | 25.3119 | 42.055 | منجز | No
2100110213 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية وعاجلة | 362553208.39 | 18127660.4195 | 42128736.62 | 42128736.62 | 1010014578 | لا | 0 | 180909089093 | جاري | مدفوعات ساعات العمل | 23.82 | 96.21 | 2010-06-28 | 2013-06-11 | 2024-12-31 | 2024-12-31 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | Failed | No
2100024286 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية وعاجلة | 1086234198 | 54311709.9 | 584273414.82 | 584273414.82 | 1010014578 | لا | 0 | 180909089093 | جاري | مدفوعات ساعات العمل | 86.23 | 93.83 | 2010-06-28 | 2013-06-11 | 2024-12-31 | 2024-12-31 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | متأخر | No
2100020775 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية وعاجلة | 479914858.49 | 23995742.9245 | 168784094.44 | 168784094.44 | 1010014578 | لا | 0 | 180909089093 | جاري | مدفوعات ساعات العمل | 58.56 | 98.92 | 2010-06-28 | 2013-06-11 | 2024-12-31 | 2024-12-31 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | Failed | No
2100110202 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية وعاجلة | 797632267.04 | 39881613.352 | 466759655.22 | 466759655.22 | 1010014578 | لا | 0 | 180909089093 | جاري | مدفوعات ساعات العمل | 81.14 | 99.44 | 2010-06-28 | 2013-06-11 | 2024-12-31 | 2024-12-31 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | متأخر | No
2100023682 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية وعاجلة | 783028095.61 | 39151404.7805 | 355557667.47 | 355557667.47 | 1010014578 | لا | 0 | 180909089093 | جاري | مدفوعات ساعات العمل | 75.76 | 92.15 | 2010-06-28 | 2013-06-11 | 2024-12-31 | 2024-12-31 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | متأخر | No
2100077033 | أمانة / تبوك | تشييد | ذات اولوية عالية | 2504000 | 125200 | 1005000 | 1005000 | 1010055791 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 66 | 100 | 2015-10-21 | 2016-10-21 | 2020-11-19 | 2020-11-19 | 2016-10-21 |  | تأخرصرف المستحقات المالية |  | 36.5389 | 28.4296 | منجز | No
2100005180 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية وعاجلة | 234461595.39 | 11723079.7695 | 165807995.25 | 165807995.25 | 1010014578 | لا | 0 | 180909089093 | جاري | مدفوعات ساعات العمل | 98.18 | 99.96 | 2010-06-28 | 2013-06-11 | 2024-12-31 | 2024-12-31 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | منتظم | No
2100024850 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية وعاجلة | 455210603.88 | 22760530.194 | 354723737.05 | 354723737.05 | 1010014578 | لا | 0 | 180909089093 | جاري | مدفوعات ساعات العمل | 83.06 | 87.56 | 2010-06-28 | 2013-06-11 | 2024-12-31 | 2024-12-31 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | منتظم | No
2300238980 | أمانة / المنطقة الشرقية | الخدمات الاستشارية | ذات اولوية متوسطة | 3157440 | 157872 | 394680 | 394680 | 0 | لا | 0 |  | جاري | التكلفة المفوترة | 12 | 19 | 2022-08-25 | 2024-08-24 | 2024-08-24 | 2024-08-24 |  |  |  |  | 50.0888 | 26.4207 | خدمات عامة | No
2300238976 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 1966500 | 98325 | 0 | 0 | 1010429275 | لا | 0 |  | جاري | تكلفة العمل المنجز | 25 | 34 | 2022-10-09 | 2023-08-05 | 2023-08-05 | 2023-08-05 |  |  |  |  | 46.9781 | 27.2349 | متأخر | No
2100101732 | أمانة / تبوك | دراسة الجدوى | ذات اولوية عالية | 6881089 | 344054.45 | 4929598.96 | 4929598.96 | 3350029142 | لا | 0 | 190901207366 | جاري | مدفوعات ساعات العمل | 93 | 77.06 | 2019-10-29 | 2021-10-28 | 2023-04-25 | 2023-04-25 |  |  | اخرى |  |  |  | خدمات عامة | No
2300239002 | جامعة الباحة | تشييد | ذات اولوية عالية وعاجلة | 6168124.9 | 308406.245 | 0 | 0 | 0 | لا | 0 |  | جاري | تكلفة العمل المنجز | 1 | 1 | 2022-12-24 | 2023-09-24 | 2023-10-08 | 2023-10-08 |  |  |  |  | 41.6334 | 20.1772 | منتظم | No
2100069532 | أمانة / نجران | تشييد | ذات اولوية عالية | 65419612 | 3270980.6 | 45358933.74 | 45358933.74 | 5950003965 | لا | 0 | 181009137273 | جاري | تكلفة العمل المنجز | 87 | 92 | 2013-06-01 | 2016-04-29 | 2023-09-10 | 2023-09-10 |  |  | اخرى |  | 44.1767 | 17.549 | منتظم | No
2300239024 | أمانة / المنطقة الشرقية | الخدمات الاستشارية | ذات اولوية متوسطة | 13932807 | 696640.35 | 0 | 0 | 0 | لا | 0 |  | جاري | التكلفة المفوترة | 0 | 17 | 2022-10-06 | 2024-04-06 | 2024-04-06 | 2024-04-06 |  |  |  |  | 50.1043 | 26.4254 | خدمات عامة | No
2300238991 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 9039000 | 451950 | 0 | 0 | 2057001166 | لا | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 20 | 11.02 | 2022-09-18 | 2023-09-07 | 2023-09-07 | 2023-09-07 |  |  |  | أخرى | 48.4887 | 28.4257 | Failed | No
2100034646 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 13789800 | 689490 | 13789800 | 12410822.4 | 3357004766 | لا | 0 | 200309112868 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2020-01-29 | 2020-11-29 | 2020-11-30 | 2020-11-30 | 2020-11-29 |  | ضعف كفاءة المقاول الفنية |  | 36.5194 | 28.4324 | منجز | No
2300239035 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 633937.5 | 31696.875 | 0 | 0 | 2065003779 | لا | 0 |  | جاري | تكلفة العمل المنجز | 10 | 27 | 2022-10-30 | 2023-08-21 | 2023-08-21 | 2023-08-21 |  |  |  |  | 46.9781 | 27.2349 | متأخر | No
2100067211 | أمانة / تبوك | تشييد | لم تعد تحتاجها الجهة | 428500 | 21425 | 428500 | 428500 | 3351010628 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-11-21 | 2020-05-16 | 2020-07-05 | 2020-07-05 | 2020-05-16 |  | اخرى |  | 37.7291 | 24.8079 | منجز | No
2100051752 | أمانة / تبوك | تشييد | ذات اولوية عالية وعاجلة | 71671740 | 3583587 | 71671740 | 51359968.9 | 4030140655 | لا | 0 | 190701132500 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-12-18 | 2022-12-17 | 2021-12-22 | 2021-12-22 | 2022-12-17 |  |  |  | 36.6 | 28.3684 | منجز | No
2300238954 | أمانة / المنطقة الشرقية | إشراف | ذات اولوية متوسطة | 2178882 | 108944.1 | 0 | 0 | 1010372072 | لا | 0 |  | جاري | تكلفة العمل المنجز | 8 | 13.15 | 2022-12-01 | 2023-12-01 | 2023-12-01 | 2023-12-01 |  |  |  |  | 49.5687 | 26.9598 | خدمات عامة | No
2300239013 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 416587.5 | 20829.375 | 234600 | 234600 | 2251032226 | لا | 0 |  | جاري | تكلفة العمل المنجز | 60 | 50 | 2022-08-21 | 2023-06-17 | 2023-06-17 | 2023-06-17 |  |  |  |  | 48.2692 | 26.7654 | منتظم | No
2300239061 | أمانة / المنطقة الشرقية | أخرى | ذات اولوية متوسطة | 13483189 | 674159.45 | 0 | 0 | 0 | لا | 0 |  | جاري | التكلفة المفوترة | 0 | 17 | 2022-10-10 | 2024-04-10 | 2024-04-10 | 2024-04-10 |  |  |  |  | 50.0888 | 26.4207 | خدمات عامة | No
2100102465 | أمانة / تبوك | تصميم | ذات اولوية عالية وعاجلة | 10950500 | 547525 | 10950500 | 9853250 | 1010323435 | لا | 0 | 180901083141 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-12-09 | 2020-06-01 | 2020-06-01 | 2020-06-01 | 2020-06-01 |  | تغيرات في نطاق المشروع |  |  |  | منجز | No
2100102690 | أمانة / تبوك | دراسة الجدوى | لم تعد تحتاجها الجهة | 23376000 | 1168800 | 23376000 | 13754000 | 1010323435 | لا | 0 | 180901083718 | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2018-11-05 | 2020-10-25 | 2021-04-06 | 2021-04-06 | 2020-10-25 |  | اخرى |  |  |  | منجز | No
2100024124 | أمانة / تبوك | دراسة الجدوى | ذات اولوية متوسطة | 2500000 | 125000 | 2500000 | 2500000 | 2051055115 | لا | 0 |  | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2018-07-04 | 2019-07-04 | 2019-07-04 | 2019-07-04 | 2019-07-04 |  | اخرى |  |  |  | منجز | No
2100064492 | أمانة / تبوك | تشييد | ذات اولوية عالية | 578800 | 28940 | 578800 | 0 | 4030243076 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-12-12 | 2019-12-12 | 2019-12-12 | 2019-12-12 | 2019-12-12 |  |  |  | 36.5514 | 28.38 | منجز | Yes
2300239094 | أمانة / المنطقة الشرقية | أخرى | ذات اولوية متوسطة | 3273947.59 | 163697.3795 | 636937.71 | 636937.71 | 2051060311 | لا | 0 |  | جاري | تكلفة العمل المنجز | 22 | 12.69 | 2022-09-01 | 2025-08-31 | 2025-08-31 | 2025-08-31 |  |  |  |  | 49.9982 | 26.5765 | خدمات عامة | No
2300239072 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 1325151.9 | 66257.595 | 0 | 0 | 2050134606 | لا | 0 |  | جاري | تكلفة العمل المنجز | 0 | 11.86 | 2022-12-14 | 2023-10-05 | 2023-10-05 | 2023-10-05 |  |  |  |  | 57.9784 | 23.2945 | متأخر | No
2300239046 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 21289806 | 1064490.3 | 7175483.49 | 7175483.49 | 2060024520 | لا | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 46.74 | 55.37 | 2020-12-07 | 2022-05-22 | 2022-05-22 | 2022-05-22 |  |  |  | أخرى | 49.9982 | 26.5765 | Failed | No
2100096191 | أمانة / تبوك | تصميم | ذات اولوية متوسطة | 990000 | 49500 | 990000 | 990000 | 1010326466 | لا | 0 | 190509012494 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-12-02 | 2019-12-02 | 2019-12-02 | 2019-12-02 | 2019-12-02 |  | اخرى |  |  |  | منجز | No
2100056405 | أمانة / تبوك | دراسة الجدوى | ذات اولوية متوسطة | 4889576 | 244478.8 | 4889576 | 4655284 | 1010326466 | لا | 0 |  | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2017-10-04 | 2019-10-04 | 2019-10-04 | 2019-10-04 | 2019-10-04 |  | اخرى |  |  |  | منجز | No
2300239050 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 847561.5 | 42378.075 | 324300 | 324300 | 1010203649 | لا | 0 |  | جاري | تكلفة العمل المنجز | 38 | 22.03 | 2022-11-14 | 2023-09-05 | 2023-09-05 | 2023-09-05 |  |  |  |  | 57.9784 | 23.2945 | منتظم | No
2300239105 | أمانة / المنطقة الشرقية | مساحة | ذات اولوية متوسطة | 1519380 | 75969 | 379845 | 379845 | 2051053755 | لا | 0 |  | جاري | تكلفة العمل المنجز | 91 | 89.55 | 2022-03-07 | 2023-02-24 | 2023-02-24 | 2023-02-24 |  |  |  |  | 49.9982 | 26.5765 | خدمات عامة | No
2200235863 | الهيئة العامة للموانئ | تصميم وإشراف | ذات اولوية متوسطة | 250000 | 12500 | 0 | 0 | 2050099301 | لا | 0 |  | جاري | تكلفة العمل المنجز | 50 | 75 | 2022-09-25 | 2023-01-22 | 2023-01-22 | 2023-01-22 |  |  |  |  | 49.6642 | 27.0178 | Failed | No
2100061165 | معهد الإدارة العامة | تشييد | ذات اولوية عالية | 189017993.2 | 9450899.66 | 187596438.9 | 187596438.9 | 1010078624 | لا | 0 | 180809043834 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-05-25 | 2018-04-22 | 2020-07-23 | 2020-07-23 | 2018-04-22 |  |  |  | 46.6886 | 24.8259 | منجز | No
2300239120 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 2441245.18 | 122062.259 | 0 | 0 | 2050018628 | لا | 0 |  | جاري | تكلفة العمل المنجز | 0 | 17 | 2022-11-28 | 2023-09-19 | 2023-09-19 | 2023-09-19 |  |  |  |  | 49.6707 | 25.9168 | متأخر | No
2100068913 | أمانة / تبوك | تشييد | ذات اولوية عالية وعاجلة | 13474200 | 673710 | 13474200 | 11939886 | 4030150094 | لا | 0 | 181009191989 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-05-01 | 2016-07-24 | 2021-01-15 | 2021-01-15 | 2016-07-24 |  | ضعف كفاءة المقاول الفنية |  | 36.5348 | 28.4 | منجز | No
2300239131 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 613258.2 | 30662.91 | 0 | 0 | 2060049307 | لا | 0 |  | جاري | تكلفة العمل المنجز | 1 | 100 | 2022-10-02 | 2022-12-31 | 2022-12-31 | 2022-12-31 |  |  |  | تم إنذار المقاول كتابيا | 47.6948 | 27.5548 | Failed | No
2300239116 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 1501065.23 | 75053.2615 | 0 | 0 | 2056101775 | لا | 0 |  | جاري | تكلفة العمل المنجز | 20 | 30.51 | 2022-10-02 | 2023-09-21 | 2023-09-21 | 2023-09-21 |  |  |  |  | 48.3789 | 26.9882 | متأخر | No
2300239153 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 1043280 | 52164 | 0 | 0 | 2056001352 | لا | 0 |  | جاري | تكلفة العمل المنجز | 0 | 2.82 | 2023-01-08 | 2023-12-28 | 2023-12-28 | 2023-12-28 |  |  |  |  | 48.4288 | 27.2669 | منتظم | No
2300239164 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 2245950 | 112297.5 | 1767480 | 1767480 | 2050018628 | لا | 0 |  | جاري | تكلفة العمل المنجز | 100 | 45.08 | 2022-09-07 | 2023-06-29 | 2023-06-29 | 2023-06-29 |  |  |  |  | 49.6707 | 25.9168 | منتظم | No
2300239175 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 1497357.5 | 74867.875 | 0 | 0 | 1010498848 | لا | 0 |  | جاري | تكلفة العمل المنجز | 5 | 10.41 | 2022-12-11 | 2023-12-11 | 2023-12-11 | 2023-12-11 |  |  |  |  | 48.3789 | 26.9882 | متأخر | No
2100008175 | وزارة الدفاع / الإدارة الهندسية والاشغال بالخدمات الصحية | تشييد | ذات اولوية متوسطة | 44132047 | 2206602.35 | 37366767.69 | 34840623.42 | 1010083138 | لا | 0 | 181009118302 | جاري | الكميات التي تم تركيبها | 82 | 99 | 2015-10-24 | 2016-08-12 | 2022-10-25 | 2022-10-25 |  |  | تغيرات في نطاق المشروع |  | 46.6635 | 24.6981 | متأخر | No
2100083790 | معهد الإدارة العامة | إشراف | ذات اولوية عالية | 12861288 | 643064.4 | 12777892.68 | 11748601.8 | 1010078624 | لا | 0 | 181109230114 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-07-09 | 2018-04-22 | 2020-12-15 | 2020-12-15 | 2018-04-22 |  |  |  | 46.6882 | 24.8254 | منجز | No
2300239186 | أمانة / المنطقة الشرقية | الخدمات الاستشارية | ذات اولوية منخفضة | 7493400 | 374670 | 2133250 | 1239700 | 1010419186 | لا | 0 |  | جاري | التكلفة المفوترة | 28 | 37 | 2022-04-20 | 2024-04-09 | 2024-04-09 | 2024-04-09 |  |  |  |  | 50.0888 | 26.4207 | خدمات عامة | No
2300239190 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 3259282.5 | 162964.125 | 1072950 | 1072950 | 2050018628 | لا | 0 |  | جاري | تكلفة العمل المنجز | 100 | 59.39 | 2022-07-06 | 2023-06-01 | 2023-06-01 | 2023-06-01 |  |  |  |  | 49.6707 | 25.9168 | منتظم | No
2300239142 | أمانة / الجوف | تشييد | ذات اولوية عالية | 4012925 | 200646.25 | 0 | 0 | 1134000444 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 18 | 26 | 2022-10-30 | 2023-10-29 | 2023-10-29 | 2023-10-29 |  |  |  |  | 39.8888 | 29.8108 | متأخر | No
2300239201 | أمانة / المنطقة الشرقية | مساحة | ذات اولوية متوسطة | 3149546.4 | 157477.32 | 2125522 | 2125522 | 1010611541 | لا | 0 |  | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 99 | 100 | 2021-12-30 | 2022-11-25 | 2022-11-25 | 2022-11-25 |  |  |  |  | 49.9982 | 26.5765 | متأخر | No
2100102631 | أمانة / تبوك | دراسات هندسية | ذات اولوية متوسطة | 2392740 | 119637 | 385911 | 385911 | 3550034877 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-12-22 | 2021-03-16 | 2021-03-16 | 2021-03-16 | 2021-03-16 |  | ضعف كفاءة المقاول الفنية |  |  |  | منجز | No
2300239212 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 486988.2 | 24349.41 | 278173.5 | 278173.5 | 2060049307 | لا | 0 |  | جاري | تكلفة العمل المنجز | 77 | 47.8 | 2022-08-30 | 2023-06-21 | 2023-06-21 | 2023-06-21 |  |  |  |  | 49.4797 | 25.9778 | منتظم | No
2100059430 | جامعة الإمام عبدالرحمن بن فيصل | تشييد | ذات اولوية عالية وعاجلة | 61683681.12 | 3084184.056 | 31953455.43 | 31953455.43 | 1010135922 | لا | 0 | 190101004915 | جاري | تكلفة العمل المنجز | 84 | 95.5 | 2019-08-01 | 2022-06-29 | 2022-06-29 | 2022-06-29 |  |  | اخرى |  | 50.193 | 26.399 | متأخر | No
2300239223 | أمانة / المنطقة الشرقية | إشراف | ذات اولوية متوسطة | 16617040 | 830852 | 1390695 | 1390695 | 1010308543 | لا | 0 |  | جاري | تكلفة العمل المنجز | 12 | 14.43 | 2022-08-13 | 2025-08-12 | 2025-08-12 | 2025-08-12 |  |  |  |  | 49.9982 | 26.5765 | خدمات عامة | No
2100008260 | جامعة الإمام عبدالرحمن بن فيصل | تشييد | ذات اولوية عالية وعاجلة | 52835099.19 | 2641754.9595 | 31131442.11 | 31131442.11 | 2055002293 | لا | 0 | 180709035892 | جاري | تكلفة العمل المنجز | 86 | 96.5 | 2014-01-20 | 2016-12-17 | 2022-05-19 | 2022-05-19 |  |  | لا يوجد تأخير |  | 50.1985 | 26.3989 | Failed | No
2100083020 | أمانة / تبوك | تشييد | ذات اولوية متوسطة | 11534100 | 576705 | 3071133 | 1604042 | 3357004766 | لا | 0 | 200309112868 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-05-18 | 2020-03-18 | 2020-08-01 | 2020-08-01 | 2020-03-18 |  | ضعف كفاءة المقاول الفنية |  | 36.5343 | 28.3335 | منجز | No
2100102443 | أمانة / تبوك | دراسة الجدوى | ذات اولوية عالية | 3513001 | 175650.05 | 264686 | 264686 | 3350029142 | لا | 0 | 19201125860 | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 100 | 100 | 2019-10-27 | 2021-10-26 | 2022-05-27 | 2022-05-27 | 2021-10-26 |  | اخرى |  |  |  | منجز | No
2300239234 | أمانة / المنطقة الشرقية | إشراف | ذات اولوية متوسطة | 8998080 | 449904 | 449904 | 0 | 1010419186 | لا | 0 |  | جاري | التكلفة المفوترة | 5 | 11 | 2022-10-24 | 2024-10-23 | 2024-10-23 | 2024-10-23 |  |  |  |  | 50.0888 | 26.4207 | خدمات عامة | Yes
2300239245 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 500000 | 25000 | 0 | 0 | 2051007339 | لا | 0 |  | جاري | تكلفة العمل المنجز | 49 | 62.78 | 2022-09-27 | 2023-03-26 | 2023-03-26 | 2023-03-26 |  |  |  |  | 49.9982 | 26.5765 | متأخر | No
2100009074 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 33041352 | 1652067.6 | 29678775 | 29678775 | 1010136405 | لا | 0 | 180809056621 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 98 | 98.18 | 2017-05-29 | 2019-05-29 | 2023-05-07 | 2023-05-07 |  |  | أوامر تغيير |  | 38.2979 | 23.9729 | منتظم | No
2200213065 | وزارة الحرس الوطني / وكالة الشؤون الفنية | مساحة | ذات اولوية عالية | 4945000 | 247250 | 4370000 | 2070000 | 1010322156 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2021-12-02 | 2022-12-01 | 2022-12-01 | 2022-12-01 | 2022-12-01 |  |  |  | 46.6571 | 24.7039 | منجز | No
2300239256 | أمانة / المنطقة الشرقية | دراسات هندسية | ذات اولوية متوسطة | 4607263 | 230363.15 | 1701417.4 | 1701417.4 | 2051224470 | لا | 0 |  | جاري | تكلفة العمل المنجز | 65 | 82.77 | 2022-03-31 | 2023-03-20 | 2023-03-20 | 2023-03-20 |  |  |  |  | 49.9982 | 26.5765 | خدمات عامة | No
2100015105 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 146209250 | 7310462.5 | 116532316 | 116532316 | 1010017123 | لا | 0 | 190301064718 | جاري | منهجية القيمة المكتسبة | 84 | 85.29 | 2019-07-09 | 2022-07-07 | 2023-09-06 | 2023-09-06 |  |  | عدم اكتمال أو ضعف أعمال التصميم والدراسات |  | 38.2288 | 23.9856 | منتظم | No
2100101345 | أمانة / تبوك | تشييد | ذات اولوية عالية | 39893350 | 1994667.5 | 28723212 | 28723212 | 1010009592 | لا | 0 | 180909106539 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 94 | 94 | 2015-07-07 | 2016-11-08 | 2021-03-10 | 2021-03-10 | 2016-11-08 |  | تأخرصرف المستحقات المالية |  | 36.5408 | 28.3996 | منجز | No
2100040014 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 341113171 | 17055658.55 | 285740689 | 285740689 | 1010011560 | لا | 0 | 181101337751 | جاري | منهجية القيمة المكتسبة | 88.58 | 92.02 | 2019-01-16 | 2022-01-14 | 2023-08-08 | 2023-08-08 |  |  | اخرى |  | 38.3081 | 23.934 | منتظم | No
2100205520 | المؤسسة العامة للري | تصميم | ذات اولوية عالية | 7115331.42 | 355766.571 | 4554635.47 | 4554635.47 | 2051011487 | لا | 0 | 201101455404 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 100 | 87.61 | 2021-02-18 | 2021-12-11 | 2022-11-26 | 2022-11-26 |  |  |  |  | 42.5706 | 16.8894 | منتظم | No
2300240704 | أمانة / الطائف | تشييد | ذات اولوية عالية | 1809812.5 | 90490.625 | 0 | 0 | 0 | لا | 0 |  | جاري | تكلفة العمل المنجز | 0 | 100 | 2022-07-25 | 2023-07-13 | 2023-07-13 | 2023-07-13 |  |  |  |  | 40.4109 | 22.4691 | منتظم | No
2100106643 | وزارة الحرس الوطني / وكالة الشؤون الفنية | تشييد | ذات اولوية عالية وعاجلة | 5639034309.83 | 281951715.4915 | 1842938506.49 | 1778509214.6 | 1010461955 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 41.1 | 52.28 | 2018-04-08 | 2023-04-08 | 2024-10-06 | 2024-10-06 |  |  | تأخرصرف المستحقات المالية | تم تمديد الجدول الزمني | 46.872 | 24.6943 | متأخر | No
2100193966 | وزارة الحرس الوطني / وكالة الشؤون الفنية | إشراف | ذات اولوية عالية | 50362849.28 | 2518142.464 | 26832065.86 | 25606006.09 | 4030276223 | لا | 0 |  | جاري | التكلفة المفوترة | 50.84 | 53.28 | 2019-01-20 | 2024-01-19 | 2025-01-19 | 2025-01-19 |  |  |  | تم تمديد الجدول الزمني |  |  | خدمات عامة | No
2300239271 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 1645236 | 82261.8 | 0 | 0 | 2050018628 | لا | 0 |  | جاري | تكلفة العمل المنجز | 10 | 17 | 2022-11-20 | 2023-11-09 | 2023-11-09 | 2023-11-09 |  |  |  |  | 49.4237 | 25.9492 | متأخر | No
2300239293 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 169912.5 | 8495.625 | 0 | 0 | 2056001462 | لا | 0 |  | جاري | تكلفة العمل المنجز | 0 | 11.67 | 2022-12-28 | 2023-06-26 | 2023-06-26 | 2023-06-26 |  |  |  |  | 48.4288 | 27.2669 | متأخر | No
2300239282 | أمانة / الجوف | تشييد | ذات اولوية عالية وعاجلة | 3971400 | 198570 | 3574000 | 3574000 | 3452147661 | لا | 0 |  | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 100 | 65 | 2022-05-18 | 2023-05-17 | 2023-05-17 | 2023-05-17 |  |  |  |  | 39.8888 | 29.8108 | منتظم | No
2300239315 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 562212 | 28110.6 | 0 | 0 | 2056001462 | لا | 0 |  | جاري | تكلفة العمل المنجز | 2 | 64.17 | 2022-08-17 | 2023-04-14 | 2023-04-14 | 2023-04-14 |  |  |  | تم إنذار المقاول كتابيا | 48.4288 | 27.2669 | Failed | No
2300238965 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 617377.5 | 30868.875 | 0 | 0 | 4030156456 | لا | 0 |  | جاري | تكلفة العمل المنجز | 12 | 44.11 | 2022-08-10 | 2023-08-10 | 2023-08-10 | 2023-08-10 |  |  |  | تم إنذار المقاول كتابيا | 49.5687 | 26.9598 | Failed | No
2300240236 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية عالية | 29363570.65 | 1468178.5325 | 0 | 0 | 0 | لا | 0 |  | جاري | تكلفة العمل المنجز | 4 | 13 | 2022-09-18 | 2022-09-19 | 2022-09-19 | 2022-09-19 |  |  |  |  | 42.8638 | 30.0799 | Failed | No
2100094990 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 19443460 | 972173 | 7136017.19 | 4416216.44 | 4030042874 | لا | 0 | 180709022988 | جاري | تكلفة العمل المنجز | 37.65 | 50 | 2017-07-30 | 2018-07-26 | 2024-12-31 | 2024-12-31 |  |  | تصاريح أعمال التنفيذ |  | 39.1677 | 21.5008 | متأخر | No
2100192511 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 11528737.07 | 576436.8535 | 9908917.51 | 8084523.01 | 4030019757 | لا | 0 | 180709026070 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 89 | 100 | 2017-09-24 | 2018-03-21 | 2022-12-31 | 2022-12-31 |  |  |  |  | 39.2391 | 21.4933 | متأخر | No
2200230123 | وزارة الخارجية | تصميم | ذات اولوية عالية | 1265000 | 63250 | 506000 | 506000 | 0 | لا | 0 | 211101195225 | جاري | تكلفة العمل المنجز | 90 | 100 | 2021-06-02 | 2022-11-30 | 2022-11-30 | 2022-11-30 |  |  |  |  | 7.4474 | 46.948 | متأخر | No
2100059835 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 17655670 | 882783.5 | 16888737.74 | 16888737.74 | 4032023055 | لا | 0 | 180709029164 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2017-09-10 | 2018-09-05 | 2021-12-31 | 2021-12-31 | 2018-09-05 |  | تأخرصرف المستحقات المالية |  | 39.1677 | 21.5008 | منجز | No
2100189851 | وزارة الحرس الوطني / الشؤون الصحية | تشييد | ذات اولوية عالية | 8277834835.05 | 413891741.7525 | 5695239704 | 5468530882.5 | 2051008235 | لا | 0 | 180909109682 | جاري | الكميات التي تم تركيبها | 96.78 | 100 | 2014-09-25 | 2020-01-20 | 2022-12-29 | 2022-12-29 |  |  |  |  | 46.8652 | 24.7509 | Failed | No
2100074572 | وزارة الحرس الوطني / الشؤون الصحية | تشييد | ذات اولوية عالية | 2439889 | 121994.45 | 995103.34 | 995103.34 | 1010323581 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 62 | 100 | 2015-05-24 | 2016-05-14 | 2022-06-30 | 2022-06-30 |  |  | عدم وجود مبالغ في البنود تغطي الأعمال المرصودة |  | 46.8643 | 24.7539 | مسحوب | No
2100023450 | وزارة الحرس الوطني / الشؤون الصحية | توريد وتركيب | ذات اولوية عالية | 525000 | 26250 | 273319 | 273319 | 1010007901 | لا | 0 | 181109274360 | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-01-07 | 2018-05-07 | 2022-12-31 | 2022-12-31 |  |  | أوامر تغيير |  | 46.8547 | 24.7479 | Failed | No
2100015293 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 58750000 | 2937500 | 45145617 | 45145617 | 2050004953 | لا | 0 | 181209542765 | جاري | منهجية القيمة المكتسبة | 92.41 | 97.26 | 2018-03-11 | 2020-03-10 | 2023-01-15 | 2023-01-15 |  |  |  |  | 38.2406 | 23.9888 | منتظم | No
2100064956 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 119750263 | 5987513.15 | 75597741 | 75597741 | 1010120626 | لا | 0 | 180201000199 | جاري | منهجية القيمة المكتسبة | 62.6 | 62.6 | 2020-07-05 | 2022-07-04 | 2023-12-16 | 2023-12-16 |  |  |  |  | 38.2522 | 23.9981 | منتظم | No
2100042593 | هيئة المدن الصناعية ومناطق التقنية | تشييد | ذات اولوية عالية | 6932023 | 346601.15 | 5040025 | 4345714 | 1010055791 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 91 | 100 | 2019-12-16 | 2020-12-15 | 2023-01-10 | 2023-01-10 |  |  | اخرى |  | 26.2487 | 44.0174 | متأخر | No
2100104355 | وزارة الحرس الوطني / الشؤون الصحية | ترميم | ذات اولوية عالية | 17030343 | 851517.15 | 2028039 | 1777126 | 1010065673 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 16 | 100 | 2015-04-05 | 2017-06-17 | 2017-09-28 | 2017-09-28 |  |  | ضعف كفاءة المقاول الفنية |  | 50.1773 | 26.3563 | مسحوب | No
2100086811 | وزارة الحرس الوطني / الشؤون الصحية | تشييد | ذات اولوية عالية | 122034358.35 | 6101717.9175 | 74497305.36 | 74497305.36 | 2050027608 | لا | 0 | 181009166755 | جاري | الكميات التي تم تركيبها | 84.8 | 100 | 2013-05-20 | 2015-04-27 | 2023-12-30 | 2023-12-30 |  |  | ضعف كفاءة المقاول الفنية |  | 50.1773 | 26.3563 | Failed | No
2300239341 | الهيئة العامة للموانئ | أخرى | ذات اولوية متوسطة | 766100 | 38305 | 0 | 0 | 5950004973 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 50 | 50 | 2022-08-01 | 2023-03-29 | 2023-03-29 | 2023-03-29 |  |  |  |  | 42.5355 | 16.8941 | خدمات عامة | No
2100039454 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 139986840 | 6999342 | 74766760 | 74766760 | 3555000709 | لا | 0 | 190301062641 | جاري | منهجية القيمة المكتسبة | 59.3 | 60.9 | 2019-07-11 | 2022-01-06 | 2023-12-07 | 2023-12-07 |  |  | عدم اكتمال أو ضعف أعمال التصميم والدراسات |  | 38.327 | 23.9414 | منتظم | No
2300239330 | أمانة / الجوف | تشييد | ذات اولوية عالية وعاجلة | 1430255 | 71512.75 | 0 | 0 | 3450009076 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 28 | 30 | 2022-10-03 | 2023-07-30 | 2023-07-30 | 2023-07-30 |  |  |  |  | 37.1473 | 31.4806 | منتظم | No
2100008890 | وزارة الحرس الوطني / الشؤون الصحية | تشييد | ذات اولوية عالية | 539120418 | 26956020.9 | 302232141.79 | 194564501.08 | 1010180118 | لا | 0 | 181209491495 | ايقاف كلي | الكميات التي تم تركيبها | 53 | 100 | 2012-10-06 | 2015-10-05 | 2023-12-14 | 2023-12-14 |  |  | اخرى |  | 49.5345 | 25.4601 | Failed | No
2100057083 | وزارة الحرس الوطني / الشؤون الصحية | تشييد | ذات اولوية عالية | 51953161 | 2597658.05 | 5336576 | 3081598 | 4030179603 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 22 | 100 | 2011-03-26 | 2012-09-15 | 2012-09-15 | 2012-09-15 |  |  | اخرى |  | 39.3615 | 21.4257 | مسحوب | No
2100095222 | وزارة الحرس الوطني / الشؤون الصحية | ترميم | ذات اولوية عالية | 41066120.09 | 2053306.0045 | 20082461.31 | 20082461.31 | 2052000357 | لا | 0 | 181109323297 | ايقاف كلي | الكميات التي تم تركيبها | 66 | 100 | 2018-07-01 | 2020-04-21 | 2023-06-29 | 2023-06-29 |  |  | اخرى |  | 46.8607 | 24.7524 | Failed | No
2100077044 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 43225842 | 2161292.1 | 38903257.8 | 38903257.8 | 1010152168 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2005-11-01 | 2010-01-01 | 2010-01-01 | 2010-01-01 | 2010-01-01 | 2021-11-16 |  |  | 42.5117 | 18.2465 | منجز | No
2100038043 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 30924570 | 1546228.5 | 30068812.8 | 30068812.8 | 5860007938 | لا | 0 | 181009162410 | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2017-11-23 | 2019-05-09 | 2020-02-19 | 2020-02-19 | 2019-05-09 | 2021-12-21 |  |  | 42.5582 | 17.9187 | منجز | No
2100090882 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 443500 | 22175 | 443500 | 443500 | 5950026666 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-01-22 | 2020-01-12 | 2020-01-12 | 2020-01-12 | 2020-01-12 |  | اخرى |  | 44.237 | 17.549 | منجز | No
2300238652 | وزارة الحرس الوطني / الشؤون الصحية | توريد وتركيب | ذات اولوية عالية وعاجلة | 52999000 | 2649950 | 0 | 0 | 1010161812 | لا | 0 | 220139477677 | جاري | الكميات التي تم تركيبها | 0 | 0 | 2022-12-14 | 2023-12-13 | 2023-12-13 | 2023-12-13 | [6 empty] | منتظم | No
2100199905 | رئاسة أمن الدولة / المديرية العامة للمباحث | ترميم | ذات اولوية متوسطة | 4298306.7 | 214915.335 | 1181142 | 613196 | 1010419886 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 90 | 100 | 2021-10-23 | 2022-04-18 | 2022-12-15 | 2022-12-15 |  |  |  |  | 46.6992 | 24.6718 | Failed | No
2100193292 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 61735671.75 | 3086783.5875 | 61678653.59 | 61678653.59 | 4030028078 | لا | 0 | 180709034678 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-06-16 | 2015-06-14 | 2022-12-31 | 2022-12-31 |  |  |  |  | 39.239 | 21.4933 | Failed | No
2100190330 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية عالية وعاجلة | 19079961.14 | 953998.057 | 8693172.79 | 8693172.79 | 4030140655 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 47 | 70 | 2020-01-12 | 2022-06-15 | 2022-06-16 | 2022-06-16 |  |  |  |  | 39.5794 | 24.4581 | متأخر | No
2100096784 | هيئة المدن الصناعية ومناطق التقنية | تشييد | ذات اولوية عالية | 41554993 | 2077749.65 | 17660570 | 16359396 | 1116001737 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 66 | 70 | 2019-12-30 | 2021-06-29 | 2023-03-31 | 2023-03-31 |  |  | اخرى |  | 24.7023 | 46.0656 | منتظم | No
2100059286 | هيئة المدن الصناعية ومناطق التقنية | تشييد | ذات اولوية متوسطة | 96309112 | 4815455.6 | 69808491 | 68244204 | 2051041139 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 77 | 100 | 2019-12-23 | 2021-06-15 | 2023-03-01 | 2023-03-01 |  |  | ضعف كفاءة المقاول الفنية |  | 26.2564 | 49.9733 | متأخر | No
2100055171 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 15831969 | 791598.45 | 15031205 | 15031205 | 4030023505 | لا | 0 | 181209546668 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2014-04-09 | 2016-04-08 | 2018-02-01 | 2018-02-01 | 2016-04-08 |  |  |  | 38.1853 | 24.006 | منجز | No
2100037656 | وزارة الداخلية / ديوان وزارة الداخلية | تشييد | ذات اولوية عالية وعاجلة | 408338974 | 20416948.7 | 375003979.08 | 375003979.08 | 1010004739 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2016-10-20 | 2018-10-30 | 2021-04-30 | 2021-04-30 | 2018-10-30 |  |  |  | 46.5367 | 24.8837 | منجز | No
2300240715 | أمانة / الطائف | تشييد | ذات اولوية عالية | 2803746 | 140187.3 | 0 | 0 | 0 | لا | 0 |  | جاري | تكلفة العمل المنجز | 0 | 100 | 2022-07-25 | 2023-07-13 | 2023-07-13 | 2023-07-13 |  |  |  |  | 40.4109 | 22.4691 | منتظم | No
2100194902 | هيئة المدن الصناعية ومناطق التقنية | تشييد | ذات اولوية عالية | 30200000 | 1510000 | 29945780 | 29945780 | 4030128442 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2020-09-02 | 2021-09-01 | 2022-04-28 | 2022-04-28 | 2021-09-01 |  |  |  | 39.2906 | 21.9045 | منجز | No
2100056593 | هيئة المدن الصناعية ومناطق التقنية | إشراف | ذات اولوية عالية | 61714833 | 3085741.65 | 56564476 | 56564476 | 7001444244 | لا | 0 |  | جاري | التكلفة المفوترة | 92 | 92 | 2018-01-01 | 2022-12-31 | 2023-05-29 | 2023-05-29 |  |  | لا يوجد تأخير |  | 49.9899 | 26.2454 | خدمات عامة | No
2100012633 | الهيئة العامة للموانئ | ترميم | ذات اولوية عالية | 2299000 | 114950 | 2116112.82 | 2116112.82 | 4030146000 | لا | 0 | 200901061306 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-09-26 | 2020-01-24 | 2021-11-18 | 2021-11-18 | 2020-01-24 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.5399 | 16.888 | منجز | No
2100103596 | هيئة المدن الصناعية ومناطق التقنية | تشييد | ذات اولوية عالية | 52055100 | 2602755 | 50191397 | 50191397 | 2051030141 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-04-03 | 2021-02-02 | 2022-06-05 | 2022-06-05 | 2021-02-02 |  | لا يوجد تأخير |  | 21.901 | 39.2881 | منجز | No
2100194880 | هيئة المدن الصناعية ومناطق التقنية | تشييد | ذات اولوية عالية | 282000000 | 14100000 | 209907529 | 209907529 | 2050005846 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 84 | 75 | 2020-07-15 | 2023-07-15 | 2024-01-14 | 2024-01-14 |  |  |  |  | 47.2711 | 23.9205 | منتظم | No
2100006952 | هيئة المدن الصناعية ومناطق التقنية | تشييد | ذات اولوية عالية | 44873747 | 2243687.35 | 38013362 | 38013362 | 4030034104 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-12-24 | 2022-06-23 | 2022-11-23 | 2022-11-23 | 2022-06-23 |  | لا يوجد تأخير |  | 24.5489 | 46.893 | منجز | No
2100194961 | هيئة المدن الصناعية ومناطق التقنية | تشييد | ذات اولوية عالية | 16977550 | 848877.5 | 7953892 | 7953892 | 2051030949 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 55 | 56 | 2021-03-28 | 2023-03-28 | 2023-03-28 | 2023-03-28 |  |  |  |  | 50.14 | 26.3984 | منتظم | No
2100192441 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 52423641.4 | 2621182.07 | 40356754.49 | 39571044.48 | 4030154608 | لا | 0 | 181109251650 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2012-09-05 | 2014-02-18 | 2020-08-17 | 2020-08-17 | 2014-02-18 |  |  |  | 39.2391 | 21.4933 | منجز | No
2200235303 | هيئة المدن الصناعية ومناطق التقنية | تشييد | ذات اولوية عالية | 63637726 | 3181886.3 | 813652 | 813652 | 1131013992 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 5 | 9 | 2022-08-25 | 2024-08-24 | 2024-08-24 | 2024-08-24 |  |  |  |  | 50.1395 | 26.398 | منتظم | No
2100192522 | جامعة الملك عبدالعزيز | ترميم | ذات اولوية متوسطة | 10252322.69 | 512616.1345 | 7339743.66 | 6471477.77 | 4032025725 | لا | 0 | 190409111004 | جاري | تكلفة العمل المنجز | 84.25 | 100 | 2019-02-19 | 2019-10-05 | 2022-12-31 | 2022-12-31 |  |  |  |  | 38.9603 | 22.789 | متأخر | No
2100192533 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 11048820.58 | 552441.029 | 4734851.35 | 4734851.35 | 1010251025 | لا | 0 | 190801093160 | جاري | تكلفة العمل المنجز | 54.4 | 68 | 2019-12-15 | 2020-10-16 | 2024-12-31 | 2024-12-31 |  |  |  |  | 39.2391 | 21.4933 | متأخر | No
2100060513 | وزارة الحرس الوطني / الشؤون الصحية | تشييد | ذات اولوية عالية | 1916140 | 95807 | 1854806.75 | 1854806.75 | 2051038453 | لا | 0 | 190501040770 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-02-24 | 2020-02-14 | 2021-04-11 | 2021-04-11 | 2020-02-14 |  | ضعف كفاءة المقاول الفنية |  | 49.5345 | 25.4601 | منجز | No
2100071050 | الهيئة العامة للموانئ | دراسات هندسية | ذات اولوية عالية | 6500000 | 325000 | 4800000 | 4800000 | 1010348048 | لا | 0 | 180401001625 | جاري | تكلفة العمل المنجز | 95 | 100 | 2018-05-03 | 2019-02-27 | 2022-12-01 | 2022-12-01 |  |  | اخرى |  | 42.1856 | 16.7086 | خدمات عامة | No
2100097134 | وزارة المالية | ترميم | ذات اولوية عالية | 178506777.38 | 8925338.869 | 0 | 0 | 1010154193 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 5 | 17 | 2020-06-29 | 2021-12-27 | 2021-12-27 | 2021-12-27 |  |  | لا يوجد تأخير |  | 39.1693 | 21.6858 | مسحوب | No
2100102653 | وزارة المالية | إشراف | ذات اولوية متوسطة | 7398000 | 369900 | 14982120.24 | 14982120.24 | 1010440889 | لا | 0 | 180809065102 | جاري | تكلفة العمل المنجز | 93.48 | 100 | 2015-08-12 | 2022-12-30 | 2022-12-30 | 2022-12-30 |  |  | تغيرات في نطاق المشروع |  | 39.2338 | 21.4587 | خدمات عامة | No
2100059824 | وزارة المالية | تشييد | ذات اولوية متوسطة | 6552907.63 | 327645.3815 | 4086771.57 | 4086771.57 | 1010099661 | لا | 0 |  | جاري | التكلفة المفوترة | 79.35 | 100 | 2020-01-28 | 2021-12-09 | 2023-06-30 | 2023-06-30 |  |  | التنسيق مع أصحاب المصلحه (خدمات |  | 18.823 | 24.7066 | Failed | No
2100149052 | وزارة المالية | ترميم | ذات اولوية متوسطة | 1557090 | 77854.5 | 736901.47 | 736901.47 | 1010351129 | لا | 0 | 200909152541 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-10-10 | 2020-08-01 | 2022-09-15 | 2022-09-15 | 2020-08-01 |  |  |  | 46.6691 | 24.7273 | منجز | No
2100039056 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 18637431 | 931871.55 | 17445224 | 16585130 | 4030023505 | لا | 0 | 180809040143 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2014-09-08 | 2016-03-09 | 2022-05-27 | 2022-05-27 | 2016-03-09 |  | أوامر تغيير |  | 38.3614 | 23.9486 | منجز | No
2100192356 | جامعة المجمعة | تشييد | ذات اولوية عالية وعاجلة | 33002726.52 | 1650136.326 | 28557765.22 | 28557765.22 | 1010005046 | لا | 0 | 180909072756 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-09-03 | 2021-08-14 | 2021-08-14 | 2021-08-14 | 2021-08-14 |  |  |  | 45.4194 | 25.8782 | منجز | No
2100052942 | أمانة / الجوف | تشييد | ذات اولوية عالية وعاجلة | 6893500 | 344675 | 6199926 | 6199926 | 3350013518 | لا | 0 | 190701014372 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-04-02 | 2020-03-20 | 2020-03-20 | 2020-03-20 | 2020-03-20 |  | ضعف كفاءة المقاول الفنية |  | 38.233 | 30.5084 | منجز | No
2100026014 | أمانة / الجوف | دراسات هندسية | ذات اولوية عالية | 3245000 | 162250 | 2729548 | 2729548 | 7001336770 | لا | 0 | 190301096796 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 90 | 100 | 2019-04-23 | 2021-04-22 | 2021-04-22 | 2021-04-22 |  |  | اخرى |  | 40.1043 | 29.878 | Failed | No
2100036046 | أمانة / الجوف | تشييد | ذات اولوية عالية | 17200000 | 860000 | 17200000 | 17200000 | 3400011750 | لا | 0 | 180901069702 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-11-01 | 2020-10-21 | 2022-09-15 | 2022-09-15 | 2020-10-21 |  |  |  | 40.1263 | 29.8759 | منجز | No
2300239352 | أمانة / الجوف | تشييد | ذات اولوية عالية وعاجلة | 1600800 | 80040 | 1072536 | 0 | 1134000444 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 67 | 29 | 2022-10-16 | 2023-07-13 | 2023-07-13 | 2023-07-13 |  |  |  |  | 39.3051 | 29.888 | منتظم | Yes
2100192566 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 1538172.56 | 76908.628 | 1531224.3 | 1531224.3 | 4030185851 | لا | 0 | 190801131509 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-11-24 | 2019-12-27 | 2021-06-08 | 2021-06-08 |  |  |  |  | 38.9603 | 22.7892 | Failed | No
2200235126 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 18314966 | 915748.3 | 15550687 | 15550687 | 1017000028 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 95.82 | 95.6 | 2019-09-08 | 2021-09-06 | 2023-05-01 | 2023-05-01 |  |  |  |  | 38.19 | 24.0232 | منتظم | No
2100192603 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 3384352.93 | 169217.6465 | 3355893.7 | 3355893.7 | 4030023917 | لا | 0 | 191001157212 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-05-15 | 2019-09-20 | 2022-12-31 | 2022-12-31 |  |  |  |  | 39.2563 | 21.4981 | Failed | No
2100192570 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 5477622.3 | 273881.115 | 3067721.93 | 2996761.99 | 4030099922 | لا | 0 | 191001166636 | جاري | تكلفة العمل المنجز | 65.75 | 89 | 2019-08-21 | 2020-03-03 | 2023-12-31 | 2023-12-31 |  |  |  |  | 38.9603 | 22.7892 | Failed | No
2100192463 | جامعة الملك عبدالعزيز | توريد وتركيب | ذات اولوية متوسطة | 5240306.2 | 262015.31 | 2849084 | 2849084 | 4030114926 | لا | 0 | 191001192006 | جاري | تكلفة العمل المنجز | 90 | 100 | 2019-08-15 | 2020-12-03 | 2022-12-31 | 2022-12-31 |  |  |  |  | 39.2391 | 21.4933 | متأخر | No
2100192673 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 19975738.55 | 998786.9275 | 0 | 0 | 4030123131 | لا | 0 | 200709175078 | لم يبدأ | تكلفة العمل المنجز | 0 | 0 | 2019-03-11 | 2020-01-09 | 2023-12-31 | 2023-12-31 |  |  |  |  | 39.239 | 21.4933 | منتظم | No
2100193303 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 22753460 | 1137673 | 18201738 | 18201738 | 4030114926 | لا | 0 | 200709175190 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2013-07-15 | 2014-01-05 | 2021-12-31 | 2021-12-31 |  |  |  |  | 39.2391 | 21.4933 | Failed | No
2100192102 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 339639647.43 | 16981982.3715 | 122749056.6 | 122749056.6 | 1010034600 | لا | 0 | 210509069484 | جاري | تكلفة العمل المنجز | 46.3 | 100 | 2013-03-23 | 2021-03-27 | 2023-12-31 | 2023-12-31 |  |  |  |  | 38.9603 | 22.7892 | Failed | No
2100192146 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 96114599 | 4805729.95 | 83660190.9 | 83660190.9 | 1010152417 | لا | 0 | 210709145327 | جاري | تكلفة العمل المنجز | 99 | 100 | 2012-09-03 | 2015-08-01 | 2021-12-31 | 2021-12-31 |  |  |  |  | 39.2577 | 21.4891 | Failed | No
2100192113 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 771223310 | 38561165.5 | 549132230.23 | 549132230.23 | 1010152417 | لا | 0 | 210709145696 | جاري | تكلفة العمل المنجز | 99 | 100 | 2010-11-06 | 2013-09-21 | 2021-12-31 | 2021-12-31 |  |  |  |  | 39.2577 | 21.4891 | Failed | No
2100085886 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 64999943.92 | 3249997.196 | 0 | 0 | 4030114926 | نعم | 41624154.78 |  | مسحوب | تكلفة العمل المنجز | 0 | 0 | 2014-02-25 | 2021-10-14 | 2021-11-30 | 2021-11-30 |  |  | موافقات |  | 39.1677 | 21.5008 | مسحوب | No
2100092912 | وزارة الموارد البشرية والتنمية الإجتماعية | إشراف | ذات اولوية منخفضة | 4893925.93 | 244696.2965 | 6400277.44 | 6400277.44 | 1010322156 | لا | 0 | 181109297038 | فسخ العقد | الكميات التي تم تركيبها | 76 | 100 | 2012-06-11 | 2015-05-09 | 2021-09-09 | 2021-09-09 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.2355 | 21.5461 | مسحوب | No
2100078956 | جامعة الملك عبدالعزيز | تصميم | ذات اولوية متوسطة | 1180000 | 59000 | 1180000 | 1180000 | 4030231228 | لا | 0 | 180809043861 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-10-13 | 2016-01-11 | 2016-01-11 | 2016-01-11 | 2016-01-11 |  | لا يوجد تأخير |  | 39.243 | 21.4872 | منجز | No
2100078551 | وزارة الموارد البشرية والتنمية الإجتماعية | إشراف | ذات اولوية منخفضة | 1263300 | 63165 | 3013309 | 3013309 | 1010429789 | لا | 0 | 190501072467 | مسحوب | الكميات التي تم تركيبها | 84 | 100 | 2015-12-27 | 2017-12-26 | 2022-04-05 | 2022-04-05 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 47.2786 | 24.137 | مسحوب | No
2100004653 | وزارة الموارد البشرية والتنمية الإجتماعية | تشييد | ذات اولوية منخفضة | 21687716.74 | 1084385.837 | 21687716.74 | 21687716.74 | 1010224427 | لا | 0 | 180709022294 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-07-06 | 2017-06-02 | 2019-02-24 | 2019-02-24 | 2017-06-02 |  | ضعف كفاءة المقاول الفنية |  | 46.6988 | 24.6577 | منجز | No
2100062086 | وزارة الموارد البشرية والتنمية الإجتماعية | تشييد | ذات اولوية منخفضة | 17163482 | 858174.1 | 10756748.22 | 10756748.22 | 1010219247 | لا | 0 | 190209042608 | مسحوب | الكميات التي تم تركيبها | 86 | 100 | 2015-02-17 | 2017-01-25 | 2022-05-18 | 2022-05-18 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 46.7352 | 22.3179 | مسحوب | No
2100091685 | وزارة الموارد البشرية والتنمية الإجتماعية | تشييد | ذات اولوية منخفضة | 43901811.77 | 2195090.5885 | 43901811.77 | 43901811.77 | 3350012618 | لا | 0 | 181109271424 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2013-04-23 | 2016-03-21 | 2018-02-20 | 2018-02-20 | 2016-03-21 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 37.3845 | 31.2895 | منجز | No
2100040600 | وزارة الموارد البشرية والتنمية الإجتماعية | تشييد | ذات اولوية منخفضة | 10455332.21 | 522766.6105 | 10438172.77 | 10438172.77 | 4030140863 | لا | 0 | 180909091178 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-09-16 | 2017-02-17 | 2022-02-01 | 2022-02-01 | 2017-02-17 |  | ضعف كفاءة المقاول الفنية |  | 43.511 | 17.6564 | منجز | No
2100106094 | وزارة الموارد البشرية والتنمية الإجتماعية | تشييد | ذات اولوية منخفضة | 5162261 | 258113.05 | 1236711.5 | 1236711.5 | 1128004938 | نعم | 2965488.91 | 190501087051 | فسخ العقد | الكميات التي تم تركيبها | 39 | 100 | 2019-01-10 | 2020-07-03 | 2023-05-10 | 2023-05-10 |  |  | ضعف كفاءة المقاول الفنية |  | 44.0248 | 26.1082 | مسحوب | No
2100042066 | وزارة الموارد البشرية والتنمية الإجتماعية | تشييد | ذات اولوية منخفضة | 37461982.5 | 1873099.125 | 10650428.74 | 10650428.74 | 4030150126 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 44 | 100 | 2015-04-08 | 2018-03-05 | 2020-01-01 | 2020-01-01 |  |  | ضعف كفاءة المقاول الفنية |  | 39.8752 | 21.3606 | مسحوب | No
2100039406 | شركة الكهرباء | تشييد | ذات اولوية متوسطة | 50475934 | 2523796.7 | 44530849 | 44530849 | 1010157290 | لا | 0 |  | جاري الاستلام الإبتدائي | اخرى | 100 | 100 | 2015-11-01 | 2017-06-18 | 2022-11-30 | 2022-11-30 |  |  | لا يوجد تأخير |  | 39.633 | 24.4578 | Failed | No
2100040051 | شركة الكهرباء | تشييد | ذات اولوية متوسطة | 90923850 | 4546192.5 | 80987250 | 80987250 | 4030019266 | لا | 0 |  | جاري الاستلام الإبتدائي | اخرى | 100 | 100 | 2015-12-20 | 2018-01-20 | 2021-05-28 | 2021-05-28 |  |  | اخرى |  | 39.2538 | 21.487 | متأخر | No
2100101021 | شركة الكهرباء | تشييد | ذات اولوية متوسطة | 91164629 | 4558231.45 | 74467518 | 74467518 | 1010154437 | لا | 0 |  | جاري | اخرى | 96 | 100 | 2016-02-07 | 2018-05-06 | 2023-07-29 | 2023-07-29 |  |  | لا يوجد تأخير |  | 43.947 | 26.1203 | منتظم | No
2100019563 | أمانة / حائل | تشييد | ذات اولوية عالية | 791910 | 39595.5 | 558794 | 558794 | 3350127297 | لا | 0 | 190509029585 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 100 | 2018-12-22 | 2019-12-17 | 2019-03-28 | 2019-03-28 | 2019-12-17 |  | ضعف كفاءة المقاول الفنية |  | 42.4135 | 27.8869 | منجز | No
2100013602 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 6000000 | 300000 | 5434993.81 | 5434993.81 | 1011010795 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-08-29 | 2019-08-30 | 2021-02-18 | 2021-02-18 | 2019-08-30 |  | ضعف كفاءة المقاول الفنية |  | 41.0453 | 30.9716 | منجز | No
2100082843 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 21999850 | 1099992.5 | 14264013.85 | 14264013.85 | 3450009076 | لا | 0 | 181001143450 | جاري | منهجية القيمة المكتسبة | 71 | 80 | 2019-02-25 | 2021-02-24 | 2023-05-28 | 2023-05-28 |  |  | ضعف كفاءة المقاول الفنية |  | 38.6865 | 31.6692 | متأخر | No
2100066570 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 2333800 | 116690 | 456800 | 456800 | 3450008816 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2015-11-05 | 2019-07-30 | 2020-02-29 | 2020-02-29 | 2019-07-30 |  | ضعف كفاءة المقاول الفنية |  | 38.6314 | 31.6848 | منجز | No
2100048230 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 1300000 | 65000 | 1106711 | 1106711 | 3453002636 | لا | 0 | 190309074120 | جاري | منهجية القيمة المكتسبة | 92 | 100 | 2018-09-06 | 2019-08-31 | 2023-05-31 | 2023-05-31 |  |  | ضعف كفاءة المقاول الفنية | مخطط لسحبه وإعادة ترسيته | 42.2398 | 30.3531 | متأخر | No
2100058870 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 726000 | 36300 | 506785.12 | 506785.12 | 3453003284 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-05-27 | 2020-05-21 | 2021-03-05 | 2021-03-05 | 2020-05-21 |  | ضعف كفاءة المقاول الفنية |  | 40.9622 | 30.9334 | منجز | No
2100072074 | أمانة / الحدود الشمالية | تشييد | ذات اولوية متوسطة | 273000 | 13650 | 260000 | 260000 | 3453003284 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-09-15 | 2019-09-11 | 2019-09-11 | 2019-09-11 | 2019-09-11 |  |  |  | 41.0898 | 30.9517 | منجز | No
2100051052 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية وعاجلة | 1940000 | 97000 | 1216824 | 1216824 | 3453003328 | نعم | 713908 | 200201078754 | جاري | منهجية القيمة المكتسبة | 63 | 75 | 2019-10-27 | 2020-09-17 | 2023-05-28 | 2023-05-28 |  |  |  | تم إشعار المقاول كتابيا بالتأخير | 43.5511 | 29.6254 | متأخر | No
2100072026 | أمانة / الحدود الشمالية | تشييد | ذات اولوية عالية | 1228029 | 61401.45 | 688683.38 | 688683.38 | 3453102469 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 54 | 70 | 2019-12-09 | 2021-07-08 | 2023-05-31 | 2023-05-31 |  |  |  | مخطط لسحبه وإعادة ترسيته | 43.5157 | 29.6227 | متأخر | No
2100102082 | وزارة الصحة / عسير | تشييد | لم تعد تحتاجها الجهة | 32329505.98 | 1616475.299 | 17935624.38 | 11742567.38 | 4030052981 | لا | 0 | 181009123280 | مسحوب | تكلفة العمل المنجز | 90 | 100 | 2013-05-01 | 2014-11-01 | 2021-07-11 | 2021-07-11 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال | تم إعادة ترسيته | 42.5238 | 18.2024 | مسحوب | No
2100102071 | وزارة الصحة / عسير | تشييد | لم تعد تحتاجها الجهة | 43117435.88 | 2155871.794 | 29412056 | 21530519.6 | 4030052981 | لا | 0 | 181009122850 | مسحوب | تكلفة العمل المنجز | 90 | 100 | 2013-05-18 | 2014-11-18 | 2021-07-11 | 2021-07-11 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.5228 | 18.2017 | مسحوب | No
2100013156 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 64175000 | 3208750 | 57757500 | 57757500 | 1010052246 | لا | 0 |  | جاري | تكلفة العمل المنجز | 90 | 100 | 2017-12-03 | 2021-04-24 | 2022-04-03 | 2022-04-03 |  |  | ضعف كفاءة المقاول الفنية |  | 39.542 | 24.4834 | متأخر | No
2100095782 | وزارة الصحة / عسير | تشييد | ذات اولوية عالية وعاجلة | 38114035.65 | 1905701.7825 | 24226429.95 | 24226429.95 | 1010159118 | لا | 0 | 181009119577 | جاري | تكلفة العمل المنجز | 86 | 100 | 2012-10-05 | 2014-04-05 | 2023-04-21 | 2023-04-21 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال | تم تمديد الجدول الزمني | 42.5238 | 18.2024 | Failed | No
2100202193 | وزارة الصحة / عسير | ترميم | لم تعد تحتاجها الجهة | 4199000 | 209950 | 0 | 0 | 1010087837 | لا | 0 | 181009118303 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 90 | 100 | 2017-10-02 | 2018-08-02 | 2022-06-02 | 2022-06-02 |  |  |  | العقد يسير حسب الخطة | 42.5249 | 18.199 | متأخر | No
2200235115 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 45510533 | 2275526.65 | 7743087.2 | 7743087.2 | 2051002267 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 38 | 38.52 | 2022-02-06 | 2024-02-05 | 2024-02-05 | 2024-02-05 |  |  |  |  | 38.19 | 24.0232 | منتظم | No
2100055031 | مدينة الملك عبدالعزيز للعلوم والتقنية | تشييد | ذات اولوية عالية وعاجلة | 511416511.87 | 25570825.5935 | 361850363.54 | 361850363.54 | 1010254468 | لا | 0 | 180909066474 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 98 | 100 | 2014-01-01 | 2016-03-20 | 2022-12-31 | 2022-12-31 | 2016-03-20 |  |  |  | 46.6433 | 24.717 | منجز | No
2300240726 | أمانة / الطائف | تشييد | ذات اولوية عالية | 1500175 | 75008.75 | 0 | 0 | 0 | لا | 0 |  | جاري | تكلفة العمل المنجز | 0 | 100 | 2022-07-25 | 2023-07-13 | 2023-07-13 | 2023-07-13 |  |  |  |  | 40.4109 | 22.4691 | منتظم | No
2200235911 | أمانة / الأحساء | دراسة الجدوى | ذات اولوية متوسطة | 4243000 | 212150 | 0 | 0 | 1010597257 | لا | 0 |  | جاري | تكلفة العمل المنجز | 3.5 | 5 | 2022-09-18 | 2023-09-13 | 2023-09-13 | 2023-09-13 |  |  |  |  | 49.5604 | 25.3897 | خدمات عامة | No
2100084851 | شركة الكهرباء | تشييد | ذات اولوية متوسطة | 412429553 | 20621477.65 | 411936142 | 411936142 | 1010086434 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2015-10-29 | 2018-04-08 | 2021-02-03 | 2021-02-03 | 2018-04-08 |  | لا يوجد تأخير |  | 39.271 | 21.483 | منجز | No
2200235933 | أمانة / الأحساء | توريد وتركيب | ذات اولوية متوسطة | 12706925 | 635346.25 | 700850 | 700850 | 2050018628 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 5 | 7 | 2022-10-16 | 2025-09-30 | 2025-09-30 | 2025-09-30 |  |  |  |  | 49.576 | 25.3657 | منتظم | No
2100073161 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 121640472.59 | 6082023.6295 | 109475970 | 109475970 | 5950005891 | لا | 0 | 180801058166 | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2015-02-25 | 2017-02-03 | 2020-05-09 | 2020-05-09 | 2017-02-03 | 2021-05-05 |  |  | 41.9101 | 18.3453 | منجز | No
2100038452 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 85680998 | 4284049.9 | 76979152 | 76979152 | 5950005891 | لا | 0 | 190609059012 | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2015-03-26 | 2018-10-15 | 2019-11-15 | 2019-11-15 | 2018-10-15 | 2021-01-31 |  |  | 43.3839 | 17.8913 | منجز | No
2100039642 | شركة الكهرباء | تشييد | ذات اولوية متوسطة | 140702260 | 7035113 | 82776314 | 82776314 | 2050004063 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 73.95 | 76 | 2012-05-29 | 2014-11-11 | 2024-12-30 | 2024-12-30 |  |  | اخرى |  | 39.8979 | 21.4165 | Failed | No
2100002855 | شركة الكهرباء | تشييد | ذات اولوية متوسطة | 21474657 | 1073732.85 | 1102780 | 1102780 | 1010157290 | لا | 0 |  | جاري | اخرى | 5 | 100 | 2015-09-17 | 2017-09-28 | 2022-08-31 | 2022-08-31 |  |  | اخرى |  | 39.1882 | 21.5105 | Failed | No
2100036061 | أمانة / الأحساء | تشييد | ذات اولوية عالية وعاجلة | 20392413 | 1019620.65 | 20392412 | 20392412 | 2252008753 | لا | 0 | 191001115222 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-07-14 | 2020-01-10 | 2021-12-31 | 2021-12-31 | 2020-01-10 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 49.5911 | 25.3889 | منجز | No
2100038334 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 18079653 | 903982.65 | 17232392.65 | 17232392.65 | 4031049008 | لا | 0 | 200209134693 | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2014-07-20 | 2016-12-21 | 2017-08-14 | 2017-08-14 | 2016-12-21 | 2020-02-11 |  |  | 39.8912 | 21.3593 | منجز | No
2100028022 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 420000 | 21000 | 0 | 0 | 2066002549 | لا | 0 | 191101089689 | فسخ العقد | تكلفة العمل المنجز | 1 | 100 | 2019-09-14 | 2020-03-12 | 2020-03-13 | 2020-03-13 |  |  | ضعف كفاءة المقاول الفنية |  | 49.7094 | 25.4103 | مسحوب | No
2100081141 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 999450 | 49972.5 | 279596 | 279596 | 1117002145 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 28 | 100 | 2016-06-10 | 2016-06-11 | 2021-04-06 | 2021-04-06 |  |  | تأخرصرف المستحقات المالية |  | 51.5755 | 24.1309 | مسحوب | No
2100067351 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 399000 | 19950 | 0 | 0 | 2066002549 | لا | 0 | 191101101569 | فسخ العقد | تكلفة العمل المنجز | 1 | 100 | 2019-09-14 | 2020-12-21 | 2020-03-13 | 2020-03-13 |  |  | ضعف كفاءة المقاول الفنية |  | 49.7217 | 25.3759 | مسحوب | No
2100041086 | أمانة / حائل | دراسة الجدوى | ذات اولوية متوسطة | 700000 | 35000 | 400000 | 400000 | 3350022433 | لا | 0 | 200501037425 | جاري | الكميات التي تم تركيبها | 100 | 100 | 2019-07-28 | 2020-01-25 | 2020-09-09 | 2020-09-09 |  |  | اخرى |  | 42.4079 | 27.9048 | خدمات عامة | No
2100004535 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 64389843.12 | 3219492.156 | 65828381.64 | 65828381.64 | 2050018628 | لا | 0 | 190509106781 | جاري | منهجية القيمة المكتسبة | 98 | 100 | 2018-03-18 | 2020-01-19 | 2023-09-28 | 2023-09-28 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5648 | 27.1019 | منتظم | No
2100021232 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 6375504.45 | 318775.2225 | 6375504.45 | 6375504.45 | 5801009694 | لا | 0 | 181001116833 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-11-11 | 2020-10-20 | 2021-11-09 | 2021-11-09 | 2020-10-20 |  |  |  | 41.4802 | 19.995 | منجز | No
2100076554 | أمانة / الأحساء | تشييد | ذات اولوية عالية وعاجلة | 8499765.75 | 424988.2875 | 7550228 | 6942769 | 2050041707 | لا | 0 | 190909036960 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-04-30 | 2019-10-27 | 2022-09-30 | 2022-09-30 | 2019-10-27 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 49.6787 | 25.4071 | منجز | No
2100039222 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 9641105.4 | 482055.27 | 9641105 | 9641105 | 1010039430 | لا | 0 | 200209109141 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-06-10 | 2020-06-04 | 2021-12-31 | 2021-12-31 | 2020-06-04 |  | ضعف كفاءة المقاول الفنية |  | 49.6019 | 25.3569 | منجز | No
2100061036 | وزارة التعليم | تشييد | ذات اولوية عالية | 5180137.09 | 259006.8545 | 375343.87 | 0 | 4030065868 | لا | 0 |  | جاري | التكلفة المفوترة | 8 | 100 | 2012-06-11 | 2014-02-03 | 2024-01-15 | 2024-01-15 |  |  | ضعف كفاءة المقاول الفنية |  | 39.6005 | 24.4595 | Failed | Yes
2100040246 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 79484157.36 | 3974207.868 | 59757069.36 | 59757069.36 | 2060002548 | لا | 0 | 180809058480 | جاري | منهجية القيمة المكتسبة | 79 | 100 | 2011-09-28 | 2014-05-28 | 2023-09-20 | 2023-09-20 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 49.5648 | 27.1019 | متأخر | No
2100057120 | أمانة / الباحة | دراسة الجدوى | ذات اولوية متوسطة | 10764000 | 538200 | 10764000 | 10749900 | 4650047424 | لا | 0 | 180401003878 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-09-25 | 2021-07-12 | 2021-09-09 | 2021-09-09 | 2021-07-12 |  | اخرى |  |  |  | منجز | No
2100192684 | جامعة الملك عبدالعزيز | تشييد | ذات اولوية متوسطة | 2965903 | 148295.15 | 2870930.49 | 2870930.49 | 4030152097 | لا | 0 | 181101274708 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-11-14 | 2019-05-11 | 2022-12-31 | 2022-12-31 |  |  |  |  | 39.2391 | 21.4933 | Failed | No
2200234636 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | دراسات هندسية | ذات اولوية عالية وعاجلة | 5999999.65 | 299999.9825 | 0 | 0 | 2050087924 | لا | 0 |  | جاري | تكلفة العمل المنجز | 4 | 7 | 2022-08-02 | 2027-03-16 | 2027-08-01 | 2027-08-01 |  |  |  |  | 49.1911 | 27.4973 | خدمات عامة | No
2100046281 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 2684160 | 134208 | 2004900 | 2004900 | 5802010434 | لا | 0 | 190201019982 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-11-10 | 2020-10-31 | 2022-05-01 | 2022-05-01 | 2020-10-31 |  | تأخرصرف المستحقات المالية |  | 49.5922 | 25.377 | منجز | No
2100070663 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 20779000 | 1038950 | 18689578 | 18689578 | 5860007938 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2013-12-19 | 2016-09-20 | 2020-01-09 | 2020-01-09 | 2016-09-20 | 2020-01-19 |  |  | 42.5333 | 18.214 | منجز | No
2100084873 | جامعة القصيم | تشييد | ذات اولوية عالية وعاجلة | 104413766 | 5220688.3 | 89388065.97 | 89388065.97 | 1131013992 | لا | 0 | 210509132838 | جاري | تكلفة العمل المنجز | 77 | 100 | 2013-08-31 | 2016-02-17 | 2023-12-25 | 2023-12-25 |  |  | ضعف كفاءة المقاول الفنية |  | 43.7482 | 26.361 | Failed | No
2100066371 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 10404600 | 520230 | 7348837.4 | 6866204.4 | 1010152168 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 69 | 100 | 2012-12-02 | 2014-11-11 | 2016-07-12 | 2016-07-12 |  |  | ضعف كفاءة المقاول الفنية |  | 41.469 | 19.9675 | مسحوب | No
2100095944 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 182281983.82 | 9114099.191 | 136680874 | 136680874 | 1010166751 | لا | 0 | 180809049364 | جاري | منهجية القيمة المكتسبة | 79 | 100 | 2015-02-26 | 2017-08-24 | 2023-10-17 | 2023-10-17 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 49.5648 | 27.1019 | متأخر | No
2100083171 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 9570487.5 | 478524.375 | 0 | 0 | 2050027937 | لا | 0 | 190909071387 | مسحوب | تكلفة العمل المنجز | 6 | 100 | 2019-06-10 | 2020-12-01 | 2021-02-01 | 2021-02-01 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 49.5547 | 25.3993 | مسحوب | No
2100058240 | جامعة القصيم | تشييد | ذات اولوية متوسطة | 14938000 | 746900 | 12087495.94 | 11822330 | 4031053163 | لا | 0 | 190709132644 | مسحوب | تكلفة العمل المنجز | 80 | 100 | 2012-10-31 | 2013-12-25 | 2020-12-31 | 2020-12-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 43.6077 | 26.1531 | مسحوب | No
2100202462 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 268034981.85 | 13401749.0925 | 99445655.55 | 99445655.55 | 1010135922 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 49 | 46 | 2021-09-13 | 2024-08-26 | 2024-09-09 | 2024-09-09 |  |  |  |  | 49.1722 | 27.5011 | منتظم | No
2100073846 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 213537918.44 | 10676895.922 | 171304069.1 | 171304069.1 | 1123000085 | لا | 0 | 180101000034 | جاري | منهجية القيمة المكتسبة | 77 | 98 | 2018-11-04 | 2021-05-02 | 2024-05-21 | 2024-05-21 |  |  | اخرى |  | 49.5648 | 27.1019 | متأخر | No
2100091361 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تصميم وتشييد | ذات اولوية عالية وعاجلة | 85744999 | 4287249.95 | 68082014.95 | 68082014.95 | 2050022550 | لا | 0 | 180809058517 | جاري | منهجية القيمة المكتسبة | 96 | 96 | 2014-07-14 | 2016-10-24 | 2023-08-03 | 2023-08-03 |  |  | اخرى |  | 49.5648 | 27.1019 | متأخر | No
2100084976 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 159037000 | 7951850 | 101819231.4 | 101819231.4 | 2050004953 | لا | 0 | 180901069107 | جاري | منهجية القيمة المكتسبة | 69 | 100 | 2018-11-19 | 2019-12-16 | 2023-04-01 | 2023-04-01 |  |  | التنسيق مع أصحاب المصلحه (خدمات |  | 49.5648 | 27.1019 | Failed | No
2100101964 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تصميم وتشييد | ذات اولوية عالية وعاجلة | 587361257.31 | 29368062.8655 | 435944994.97 | 435944994.97 | 1010011560 | لا | 0 | 180809058391 | جاري | منهجية القيمة المكتسبة | 95 | 100 | 2013-04-15 | 2016-04-11 | 2023-07-03 | 2023-07-03 |  |  | اخرى |  | 49.5648 | 27.1019 | متأخر | No
2100019773 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 186179426.29 | 9308971.3145 | 189013207.36 | 189013207.36 | 2051035332 | لا | 0 | 180809049262 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2015-01-13 | 2017-07-11 | 2022-08-30 | 2022-08-30 | 2017-07-11 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 49.6626 | 27.0037 | منجز | No
2100050912 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 14822571 | 741128.55 | 14822571 | 14822571 | 2251029920 | لا | 0 | 190201040446 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-05-14 | 2020-11-05 | 2021-12-31 | 2021-12-31 | 2020-11-05 |  |  |  | 49.5823 | 25.3697 | منجز | No
2100026806 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 56564292.75 | 2828214.6375 | 53834355 | 53834355 | 2050003475 | لا | 0 | 191001272691 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-09-14 | 2020-09-08 | 2021-09-23 | 2021-09-23 | 2020-09-08 |  | اخرى |  | 50.1519 | 26.3891 | منجز | No
2100099831 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 99076584.16 | 4953829.208 | 87055661.47 | 87055661.47 | 1010071283 | لا | 0 | 211001032007 | مسحوب | منهجية القيمة المكتسبة | 92 | 100 | 2013-12-17 | 2017-04-04 | 2023-04-04 | 2023-04-04 |  |  | ضعف كفاءة المقاول الفنية |  | 49.6626 | 27.0037 | مسحوب | No
2100015223 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تصميم | ذات اولوية عالية وعاجلة | 80922969.99 | 4046148.4995 | 73566955.74 | 73566955.74 | 1010322156 | لا | 0 | 180201000354 | جاري | تكلفة العمل المنجز | 90 | 91 | 2018-10-18 | 2023-10-17 | 2023-10-17 | 2023-10-17 |  |  |  |  | 49.1725 | 27.494 | منتظم | No
2100084501 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تصميم | ذات اولوية عالية وعاجلة | 94514541 | 4725727.05 | 90713413 | 90713413 | 1010322156 | لا | 0 | 180709026143 | منجز – استلام ابتدائي | اخرى | 97.51 | 100 | 2016-10-09 | 2021-10-08 | 2022-09-28 | 2022-09-28 | 2021-10-08 |  |  |  | 38.1953 | 23.9876 | منجز | No
2100048893 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 26145278 | 1307263.9 | 23759479 | 23759479 | 4030023505 | لا | 0 | 180901098106 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-01-06 | 2020-12-26 | 2022-09-30 | 2022-09-30 | 2020-12-26 |  | ضعف كفاءة المقاول الفنية |  | 49.5828 | 25.3772 | منجز | No
2100108684 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 282837395.47 | 14141869.7735 | 232145268.6 | 232145268.6 | 1010011560 | لا | 0 | 180809049323 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2014-10-19 | 2018-04-15 | 2022-07-31 | 2022-07-31 | 2018-04-15 |  | لا يوجد تأخير |  | 49.6626 | 27.0037 | منجز | No
2200214185 | أمانة / الأحساء | أخرى | ذات اولوية عالية وعاجلة | 5210244 | 260512.2 | 5210244 | 5210244 | 2050018628 | نعم | 3079259 | 180909103090 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2021-11-07 | 2022-11-02 | 2022-10-23 | 2022-10-23 | 2022-11-02 |  |  |  | 49.6144 | 25.3415 | منجز | No
2100107494 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 257091535.52 | 12854576.776 | 197023685.57 | 197023685.57 | 1010158635 | لا | 0 | 180809057541 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2013-06-17 | 2015-12-14 | 2020-12-31 | 2020-12-31 | 2015-12-14 |  | لا يوجد تأخير |  | 49.6626 | 27.0037 | منجز | No
2200214163 | أمانة / الأحساء | أخرى | ذات اولوية متوسطة | 6434296 | 321714.8 | 5790086 | 5790086 | 2050018628 | نعم | 1391267 | 220209078889 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2021-11-07 | 2022-11-02 | 2022-11-02 | 2022-11-02 | 2022-11-02 |  |  |  | 49.6118 | 25.3466 | منجز | No
2100048613 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية | 366838919.77 | 18341945.9885 | 285243293.48 | 285243293.48 | 1010066115 | لا | 0 | 180709034023 | جاري | منهجية القيمة المكتسبة | 96 | 100 | 2014-09-10 | 2017-09-06 | 2023-01-30 | 2023-01-30 |  |  | لا يوجد تأخير |  | 49.6626 | 27.0037 | منتظم | No
2100023752 | جامعة الملك خالد | تشييد | ذات اولوية عالية وعاجلة | 98661925.24 | 4933096.262 | 88567181.15 | 88567181.15 | 5855000147 | لا | 0 | 180809042795 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-04-09 | 2019-03-29 | 2021-12-26 | 2021-12-26 |  |  | تأخرصرف المستحقات المالية |  | 42.8114 | 18.0836 | Failed | No
2100014895 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | دراسات هندسية | ذات اولوية عالية وعاجلة | 44630355 | 2231517.75 | 45609460.36 | 45609460.36 | 2051060068 | لا | 0 | 180809058994 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 95 | 100 | 2017-07-17 | 2022-07-16 | 2023-07-16 | 2023-07-16 | 2022-07-16 |  |  | أخرى | 49.5894 | 26.9867 | منجز | No
2100089773 | وزارة الدفاع / الإدارة الهندسية والاشغال بقوة الصواريخ الإستراتيجية | تشييد | ذات اولوية عالية | 132978845 | 6648942.25 | 95759669.36 | 95759669.36 | 1010154193 | لا | 0 | 181009184300 | جاري | الكميات التي تم تركيبها | 99 | 100 | 2015-04-01 | 2015-09-28 | 2023-04-30 | 2023-04-30 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال | تم إشعار المقاول كتابيا بالتأخير | 44.4351 | 24.5242 | Failed | No
2100063696 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 66728527.7 | 3336426.385 | 16920366.44 | 16920366.44 | 4650052854 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 25 | 100 | 2014-08-06 | 2016-07-14 | 2021-09-08 | 2021-09-08 |  |  | ضعف كفاءة المقاول الفنية |  | 39.5757 | 24.5371 | مسحوب | No
2100057046 | وزارة الموارد البشرية والتنمية الإجتماعية | إشراف | ذات اولوية منخفضة | 1182000 | 59100 | 2445051.32 | 2445051.32 | 1010332416 | لا | 0 | 190209047199 | جاري | مدفوعات ساعات العمل | 88 | 100 | 2016-02-01 | 2018-07-04 | 2021-12-31 | 2021-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5711 | 16.8693 | خدمات عامة | No
2200231630 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | دراسات هندسية | ذات اولوية عالية وعاجلة | 18780650 | 939032.5 | 3869288.69 | 3869288.69 | 2051047662 | لا | 0 |  | جاري | تكلفة العمل المنجز | 21 | 12 | 2022-04-11 | 2027-04-11 | 2027-05-25 | 2027-05-25 |  |  |  |  | 49.5533 | 27.039 | خدمات عامة | No
2100042302 | جامعة الملك خالد | تشييد | ذات اولوية عالية وعاجلة | 54340000 | 2717000 | 44918465.81 | 35012129.81 | 5855000147 | لا | 0 | 181109265794 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-09-26 | 2019-07-23 | 2022-05-23 | 2022-05-23 |  |  | تأخرصرف المستحقات المالية |  | 42.8114 | 18.0836 | متأخر | No
2200222331 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 18112500 | 905625 | 15863562.47 | 15863562.47 | 2051002267 | نعم | 87055661.47 | 211001032007 | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2021-11-16 | 2022-11-15 | 2023-03-15 | 2023-03-15 |  |  |  |  | 49.5335 | 27.1676 | متأخر | No
2100097650 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | توريد وتركيب | ذات اولوية عالية وعاجلة | 16790000 | 839500 | 12319912.25 | 12319912.25 | 2051010241 | لا | 0 | 180701018796 | جاري | تكلفة العمل المنجز | 75 | 100 | 2018-08-29 | 2021-02-24 | 2023-10-27 | 2023-10-27 |  |  | لا يوجد تأخير | تم إشعار المقاول كتابيا بالتأخير | 49.6626 | 27.0037 | Failed | No
2100039885 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | دراسة بيئية | ذات اولوية عالية وعاجلة | 21168850 | 1058442.5 | 17994843.92 | 17994843.92 | 1010412691 | لا | 0 | 180809059326 | ايقاف جزئي | تكلفة العمل المنجز | 85 | 100 | 2016-06-27 | 2021-06-26 | 2023-06-26 | 2023-06-26 |  |  |  | أخرى | 49.575 | 26.9795 | Failed | No
2100005983 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | دراسات هندسية | ذات اولوية عالية وعاجلة | 65410400 | 3270520 | 59443920.57 | 59443920.57 | 2050100852 | لا | 0 | 180809059416 | ايقاف جزئي | تكلفة العمل المنجز | 85 | 100 | 2015-02-28 | 2020-02-27 | 2023-02-28 | 2023-02-28 |  |  |  | أخرى | 49.5668 | 27.0016 | متأخر | No
2100055344 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | دراسات هندسية | ذات اولوية عالية وعاجلة | 44943000 | 2247150 | 33330340.34 | 33330340.34 | 1010281596 | لا | 0 | 180809059279 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 72 | 100 | 2014-11-26 | 2019-11-25 | 2023-07-26 | 2023-07-26 | 2019-11-25 |  |  | أخرى | 49.5835 | 26.9704 | منجز | No
2100073566 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تصميم | ذات اولوية عالية وعاجلة | 80000000 | 4000000 | 57908495.38 | 57908495.38 | 1010902667 | لا | 0 | 190709040900 | جاري | تكلفة العمل المنجز | 68 | 90 | 2018-11-12 | 2023-11-11 | 2023-11-11 | 2023-11-11 |  |  |  | أخرى | 49.5646 | 26.9617 | متأخر | No
2100195952 | وزارة النقل والخدمات اللوجستية/ منطقة عسير | تشييد | ذات اولوية متوسطة | 32360580 | 1618029 | 31433421.09 | 31433421.09 | 5855001146 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2013-10-24 | 2019-07-27 | 2018-06-23 | 2018-06-23 | 2019-07-27 | 2020-10-25 |  |  | 43.6039 | 19.0756 | منجز | No
2300239470 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | دراسات هندسية | ذات اولوية عالية وعاجلة | 68842532.5 | 3442126.625 | 0 | 0 | 1010359384 | لا | 0 |  | لم يبدأ | تكلفة العمل المنجز | 0 | 0 |  |  |  | 2027-11-01 |  |  |  |  | 49.5433 | 27.0722 | منتظم | No
2100064805 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تصميم | ذات اولوية عالية وعاجلة | 36432950 | 1821647.5 | 24302981.29 | 24302981.29 | 2051060090 | لا | 0 | 180809059281 | جاري | منهجية القيمة المكتسبة | 63 | 99 | 2018-02-04 | 2023-02-03 | 2023-02-03 | 2023-02-03 |  |  |  | أخرى | 49.5773 | 26.9864 | Failed | No
2300239481 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 507459209.7 | 25372960.485 | 0 | 0 | 2055014114 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 0 | 0 | 2022-12-05 | 2026-08-31 | 2026-08-31 | 2026-08-31 |  |  |  |  | 49.168 | 27.4978 | منتظم | No
2100103445 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 84858799.4 | 4242939.97 | 9792006.744 | 9682712.36 | 4030172446 | لا | 0 |  | فسخ العقد | تكلفة العمل المنجز | 15 | 100 | 2014-11-03 | 2017-04-21 | 2026-12-31 | 2026-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 41.8878 | 19.1367 | مسحوب | No
2200235266 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 109244971 | 5462248.55 | 10924497 | 10924497 | 2051001976 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 8.72 | 12.3 | 2022-08-31 | 2025-08-01 | 2025-08-01 | 2025-08-01 |  |  |  |  | 38.19 | 24.0232 | منتظم | No
2300239466 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 109375443.73 | 5468772.1865 | 0 | 0 | 2051013824 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 0 | 0 | 2022-12-13 | 2025-10-22 | 2025-12-16 | 2025-12-16 |  |  |  |  | 49.5551 | 27.1763 | منتظم | No
2100073636 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | دراسات هندسية | ذات اولوية عالية وعاجلة | 77770066 | 3888503.3 | 71533849.84 | 71533849.84 | 2051047662 | لا | 0 | 180809059387 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 98 | 100 | 2015-01-29 | 2020-01-28 | 2023-01-29 | 2023-01-29 | 2020-01-28 |  |  | أخرى | 49.5681 | 26.9923 | منجز | No
2300239503 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تصميم | ذات اولوية عالية وعاجلة | 63552680 | 3177634 | 0 | 0 | 2051047662 | لا | 0 |  | جاري | تكلفة العمل المنجز | 0 | 0 | 2022-11-30 | 2027-11-11 | 2027-11-11 | 2027-11-11 |  |  |  |  | 49.112 | 27.4922 | منتظم | No
2200229364 | أمانة / جدة | دراسات هندسية | ذات اولوية عالية | 3434314 | 171715.7 | 0 | 0 | 4030282813 | لا | 0 | 220501009830 | جاري | اخرى | 6 | 6 | 2022-08-01 | 2025-07-31 | 2025-07-31 | 2025-07-31 |  |  |  |  | 39.1677 | 21.5007 | خدمات عامة | No
2100092901 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 9570487.5 | 478524.375 | 3079259 | 3079259 | 2050027937 | لا | 0 | 190909071219 | مسحوب | تكلفة العمل المنجز | 38 | 100 | 2019-06-09 | 2021-02-01 | 2021-01-17 | 2021-01-17 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 49.5527 | 25.3989 | مسحوب | No
2100071886 | أمانة / تبوك | تشييد | ذات اولوية عالية | 1351118 | 67555.9 | 1351118 | 1351118 | 3551000039 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2016-01-03 | 2019-12-13 | 2019-12-12 | 2019-12-12 | 2019-12-13 |  | تأخرصرف المستحقات المالية |  | 36.2522 | 28.8737 | منجز | No
2200235782 | أمانة / جدة | تشييد | ذات اولوية عالية | 24461822 | 1223091.1 | 12219128.39 | 12219128.39 | 2050018628 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 86 | 92.05 | 2021-10-24 | 2022-06-26 | 2022-05-24 | 2022-05-24 | 2022-06-26 |  |  |  | 39.1676 | 21.5008 | منجز | No
2100023623 | جامعة الطائف | تشييد | ذات اولوية متوسطة | 12983725 | 649186.25 | 7319367.8 | 7319367.8 | 4031041927 | لا | 0 | 180809041032 | جاري | تكلفة العمل المنجز | 60 | 100 | 2017-11-12 | 2018-05-12 | 2022-09-29 | 2022-09-29 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.8469 | 21.2514 | Failed | No
2100036492 | أمانة / جدة | تشييد | ذات اولوية عالية وعاجلة | 12410050 | 620502.5 | 12106765 | 12106765 | 4030032259 | لا | 0 | 181209459740 | منجز – استلام نهائي | الكميات التي تم تركيبها | 98 | 100 | 2015-06-15 | 2017-05-22 | 2020-11-15 | 2020-11-15 | 2017-05-22 | 2020-11-15 | اخرى |  | 39.2166 | 21.4619 | منجز | No
2100016321 | أمانة / جدة | تشييد | ذات اولوية عالية وعاجلة | 12106765 | 605338.25 | 10100496 | 9488255 | 4030183716 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 82 | 100 | 2015-06-16 | 2017-04-13 | 2020-11-15 | 2020-11-15 | 2017-04-13 | 2020-11-15 | اخرى |  | 39.1978 | 21.512 | منجز | No
2100084335 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 59733594.15 | 2986679.7075 | 58439766.52 | 58439766.52 | 4031046036 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2012-07-04 | 2016-05-20 | 2019-11-24 | 2019-11-24 | 2016-05-20 | 2021-07-14 |  |  | 39.8582 | 21.4473 | منجز | No
2100043363 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 1918695 | 95934.75 | 0 | 0 | 3550010361 | لا | 0 |  | جاري | التكلفة المفوترة | 0.5 | 100 | 2007-06-26 | 2008-06-14 | 2023-06-15 | 2023-06-15 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5638 | 28.4092 | Failed | No
2100085945 | جامعة الملك سعود | تشييد | ذات اولوية عالية | 213743699 | 10687184.95 | 138212566.05 | 135796682 | 1010062464 | نعم | 1 | 181209509507 | جاري | تكلفة العمل المنجز | 91 | 100 | 2007-01-29 | 2010-06-27 | 2023-03-31 | 2023-03-31 |  |  | ضعف كفاءة المقاول الفنية |  | 46.7098 | 24.6275 | متأخر | No
2100079682 | جامعة القصيم | تشييد | ذات اولوية عالية | 89804258 | 4490212.9 | 897705 | 897705 | 1010172403 | لا | 0 |  | ايقاف كلي | تكلفة العمل المنجز | 1 | 1 | 2015-11-01 | 2018-10-16 | 2018-10-16 | 2018-10-16 |  |  | عدم وجود مبالغ في البنود تغطي الأعمال المرصودة |  | 44.2014 | 25.8831 | Failed | No
2200235966 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 28301488.8 | 1415074.44 | 24587190 | 24587190 | 2251007668 | نعم | 42935074 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 89 | 93 | 2020-08-30 | 2022-11-12 | 2022-11-12 | 2022-11-12 | 2022-11-12 |  |  |  | 49.5659 | 25.3834 | منجز | No
2200226586 | جامعة الملك سعود | إشراف | ذات اولوية متوسطة | 3778560 | 188928 | 663040 | 0 | 1010440712 | لا | 0 |  | جاري | مدفوعات ساعات العمل | 17.55 | 18 | 2022-06-14 | 2025-06-13 | 2025-06-13 | 2025-06-13 |  |  |  |  | 46.2595 | 24.4731 | خدمات عامة | Yes
2100087006 | جامعة القصيم | تشييد | ذات اولوية عالية | 12524127.65 | 626206.3825 | 11245079.06 | 11245079.06 | 1010187466 | لا | 0 | 181009207727 | جاري | تكلفة العمل المنجز | 94 | 100 | 2014-12-04 | 2016-01-28 | 2022-12-25 | 2022-12-25 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 43.489 | 25.869 | Failed | No
2100011340 | جامعة الطائف | تشييد | ذات اولوية متوسطة | 12197886.1 | 609894.305 | 12145957.4 | 10855116.8 | 4032014152 | لا | 0 | 181109293448 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2013-04-23 | 2014-04-22 | 2017-11-22 | 2017-11-22 | 2014-04-22 |  | اخرى |  | 41.6382 | 21.2199 | منجز | No
2200233376 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 9080800 | 454040 | 354382 | 0 | 2251007095 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 4 | 5 |  | 2024-03-04 | 2024-03-05 | 2024-03-04 |  |  |  |  | 49.5342 | 25.3975 | منتظم | Yes
2100009192 | جامعة الطائف | تشييد | ذات اولوية عالية | 474977371 | 23748868.55 | 33056846.34 | 33056846.34 | 1010247052 | لا | 0 | 190909020020 | جاري | تكلفة العمل المنجز | 12 | 100 | 2012-05-27 | 2015-10-10 | 2023-01-01 | 2023-01-01 |  |  | أوامر تغيير |  | 40.5097 | 21.3191 | Failed | No
2100004395 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 73377261.73 | 3668863.0865 | 65094566.03 | 65094566.03 | 1128000011 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-04-09 | 2020-11-14 | 2020-11-14 | 2020-11-14 | 2020-11-14 |  | أوامر تغيير |  |  |  | منجز | No
2100065446 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 29776470 | 1488823.5 | 29776470 | 29776470 | 4030115476 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-11-06 | 2022-02-22 | 2021-10-04 | 2021-10-04 | 2022-02-22 |  |  |  | 39.579 | 24.5418 | منجز | No
2100049265 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 16314953 | 815747.65 | 16314953 | 14651907 | 2251029920 | لا | 0 | 180701033527 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-11-20 | 2020-11-09 | 2021-04-18 | 2021-04-18 | 2020-11-09 |  | ضعف كفاءة المقاول الفنية |  | 49.5995 | 25.3617 | منجز | No
2100082552 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 5987257.5 | 299362.875 | 0 | 0 | 2050027937 | لا | 0 | 190909073568 | مسحوب | تكلفة العمل المنجز | 6 | 100 | 2019-06-09 | 2021-02-01 | 2021-01-17 | 2021-01-17 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 49.5904 | 25.3699 | مسحوب | No
2200214174 | أمانة / الأحساء | أخرى | ذات اولوية متوسطة | 9403205 | 470160.25 | 4621885 | 4621885 | 2050018628 | نعم | 0.1 | 220209078804 | جاري | الكميات التي تم تركيبها | 40 | 52 | 2021-11-07 | 2023-05-01 | 2023-05-01 | 2023-05-01 |  |  |  |  | 49.5752 | 25.3984 | خدمات عامة | No
2200235874 | أمانة / الأحساء | تشييد | ذات اولوية متوسطة | 17905500 | 895275 | 777000 | 0 | 4030148791 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 5 | 5 | 2022-09-25 | 2024-03-18 | 2024-03-18 | 2024-03-18 |  |  |  |  | 49.5826 | 25.3665 | منتظم | Yes
2300239584 | أمانة / الباحة | توريد وتركيب | ذات اولوية متوسطة | 1162784.7 | 58139.235 | 363000 | 363000 | 4603004089 | لا | 0 |  | جاري | تكلفة العمل المنجز | 45 | 100 | 2020-12-03 | 2023-11-15 | 2023-11-15 | 2023-11-15 |  |  |  |  | 41.661 | 19.9966 | Failed | No
2300239595 | أمانة / الباحة | توريد وتركيب | ذات اولوية متوسطة | 998987.75 | 49949.3875 | 289435.29 | 289435.29 | 5810001890 | لا | 0 |  | جاري | تكلفة العمل المنجز | 50 | 100 | 2022-08-09 | 2023-08-09 | 2023-08-09 | 2023-08-09 |  |  |  |  | 41.661 | 19.9966 | Failed | No
2100104462 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 60227285.09 | 3011364.2545 | 25928464.96 | 25928464.96 | 1010085001 | لا | 0 | 180709018762 | جاري | تكلفة العمل المنجز | 48 | 100 | 2014-06-08 | 2016-05-08 | 2025-12-31 | 2025-12-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.608 | 16.8448 | Failed | No
2100097974 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 76365145.98 | 3818257.299 | 20555082.79 | 20555082.79 | 1010219308 | لا | 0 | 180709021898 | ايقاف كلي | تكلفة العمل المنجز | 42 | 100 | 2014-11-26 | 2017-05-14 | 2026-12-31 | 2026-12-31 |  |  | تأخرصرف المستحقات المالية |  | 39.9912 | 21.5488 | Failed | No
2100057212 | شركة المياه الوطنية / منطقة الجوف | إشراف | ذات اولوية عالية | 4932000 | 246600 | 4555416.07 | 4459416.07 | 1131052029 | لا | 0 | 180701035509 | منجز – استلام نهائي | التكلفة المفوترة | 100 | 100 | 2018-10-09 | 2021-10-10 | 2021-11-25 | 2021-11-25 | 2021-10-10 | 2022-02-28 | لا يوجد تأخير |  | 40.1786 | 29.9713 | منجز | No
2100014243 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 48984171.02 | 2449208.551 | 32015323.75 | 31804409.75 | 1010200533 | لا | 0 | 180709035731 | ايقاف كلي | تكلفة العمل المنجز | 80 | 100 | 2014-05-06 | 2016-04-05 | 2024-12-31 | 2024-12-31 |  |  | تأخرصرف المستحقات المالية |  | 43.8246 | 25.0283 | Failed | No
2300240262 | الجمارك السعودية | تشييد | ذات اولوية عالية وعاجلة | 19130434.78 | 956521.739 | 11466270 | 11466270 | 1010433444 | لا | 0 |  | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 98 | 100 | 2022-06-30 | 2022-10-14 | 2022-11-16 | 2022-11-16 |  |  |  |  | 50.7572 | 24.7209 | Failed | No
2100001061 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 103606262.67 | 5180313.1335 | 40615744.02 | 39223944.14 | 1010034808 | لا | 0 | 180709020868 | ايقاف كلي | تكلفة العمل المنجز | 65 | 100 | 2014-07-14 | 2016-12-30 | 2025-12-31 | 2025-12-31 |  |  | تأخرصرف المستحقات المالية |  | 47.375 | 24.1974 | Failed | No
2100073091 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 201987657.72 | 10099382.886 | 195847790.95 | 195847790.95 | 1010008118 | لا | 0 |  | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2013-03-04 | 2014-08-17 | 2019-03-09 | 2019-03-09 | 2014-08-17 | 2021-02-14 |  |  | 39.1288 | 21.7203 | منجز | No
2100070932 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية متوسطة | 86799071.29 | 4339953.5645 | 83162391.44 | 83162391.44 | 1116001737 | لا | 0 | 181109327798 | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2011-06-28 | 2013-11-29 | 2019-11-24 | 2019-11-24 | 2013-11-29 | 2021-04-18 |  |  | 42.2715 | 21.1538 | منجز | No
2100051811 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 9722650 | 486132.5 | 9722650 | 9722650 | 4030007950 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-10-06 | 2021-02-19 | 2022-08-01 | 2022-08-01 | 2021-02-19 |  |  |  | 41.4429 | 20.022 | منجز | No
2100041904 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 50621654.26 | 2531082.713 | 15322951.24 | 15322951.24 | 1010336347 | لا | 0 | 180709021295 | ايقاف كلي | تكلفة العمل المنجز | 41 | 100 | 2013-06-07 | 2015-05-28 | 2025-12-31 | 2025-12-31 |  |  | تأخرصرف المستحقات المالية |  | 39.0086 | 22.8459 | Failed | No
2100190713 | شركة المياه الوطنية / منطقة الجوف | تشييد | ذات اولوية عالية وعاجلة | 114343226.45 | 5717161.3225 | 24175144.53 | 24175144.53 | 4030021112 | لا | 0 | 191101094031 | جاري | الكميات التي تم تركيبها | 36.33 | 100 | 2020-11-24 | 2022-11-03 | 2022-11-13 | 2022-11-13 |  |  |  |  | 40.2398 | 29.9635 | Failed | No
2100051973 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 17741795 | 887089.75 | 17741795 | 15967615.5 | 5810001890 | لا | 0 | 180901089876 | جاري | تكلفة العمل المنجز | 100 | 95 | 2018-11-25 | 2022-10-24 | 2022-09-25 | 2022-09-25 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 41.4754 | 19.9956 | متأخر | No
2100194924 | الهيئة العامة للطيران المدني | تصميم وتشييد | ذات اولوية عالية وعاجلة | 50692418 | 2534620.9 | 50692418 | 50692418 | 2511005931 | لا | 0 | 200101003508 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2021-04-29 | 2022-12-01 | 2022-12-01 | 2022-12-01 | 2022-12-01 |  |  |  | 46.125 | 28.3376 | منجز | No
2100085153 | وزارة الصحة / حفر الباطن | تشييد | ذات اولوية متوسطة | 8755018 | 437750.9 | 8755018 | 8755018 | 2511006133 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-02-19 | 2015-08-04 | 2017-05-03 | 2017-05-03 | 2015-08-04 |  | تأخرصرف المستحقات المالية |  | 45.9571 | 28.3167 | منجز | No
2100048521 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | تشييد | ذات اولوية عالية وعاجلة | 73749804 | 3687490.2 | 55477882.01 | 55477882.01 | 2055006347 | لا | 0 | 180809049182 | مسحوب | منهجية القيمة المكتسبة | 79 | 100 | 2017-10-12 | 2020-11-28 | 2024-11-16 | 2024-11-16 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 49.6626 | 27.0037 | مسحوب | No
2100051310 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 42000000 | 2100000 | 32684601.89 | 31002780.8 | 4030148791 | لا | 0 | 181101274927 | جاري | تكلفة العمل المنجز | 75 | 100 | 2019-01-24 | 2022-01-24 | 2022-04-23 | 2022-04-23 |  |  | اخرى |  | 39.2024 | 21.5259 | Failed | No
2100097296 | المؤسسة العامة لتحلية المياه المالحة | تشييد | ذات اولوية عالية | 154280000 | 7714000 | 131686549.38 | 131686549.38 | 1010012911 | لا | 0 | 200809124424 | جاري | منهجية القيمة المكتسبة | 95.8 | 100 | 2020-01-21 | 2021-12-31 | 2023-03-31 | 2023-03-31 |  |  | لا يوجد تأخير |  | 49.7715 | 26.8945 | منتظم | No
2100084486 | أمانة / جدة | تشييد | ذات اولوية عالية | 46992470 | 2349623.5 | 23895271 | 23895271 | 4030141919 | لا | 0 | 181101276191 | جاري | تكلفة العمل المنجز | 47 | 100 | 2019-01-14 | 2021-12-24 | 2022-06-11 | 2022-06-11 |  |  | اخرى |  | 39.2011 | 21.5554 | Failed | No
2300239606 | وزارة الحرس الوطني / الشؤون الصحية | تصميم | ذات اولوية عالية وعاجلة | 563500 | 28175 | 354441.5 | 354441.5 | 4030232311 | لا | 0 | 201239291172 | جاري | تكلفة العمل المنجز | 80 | 100 | 2022-03-27 | 2022-10-05 | 2023-01-31 | 2023-01-31 |  |  |  |  | 39.3616 | 21.4254 | Failed | No
2100007744 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 130173973.74 | 6508698.687 | 106053307.28 | 106053307.28 | 1010090968 | لا | 0 |  | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-01-01 | 2019-01-01 | 2021-07-25 | 2021-07-25 |  |  | منازعات قائمة | أخرى |  |  | Failed | No
2200226973 | المؤسسة العامة لتحلية المياه المالحة | تشييد | ذات اولوية عالية | 283000000 | 14150000 | 77006367.13 | 77006367.13 | 1010012911 | لا | 0 | 210501061182 | جاري | تكلفة العمل المنجز | 49.1 | 62.8 | 2021-08-23 | 2023-07-03 | 2023-07-03 | 2023-07-03 |  |  |  |  | 39.1925 | 21.4858 | متأخر | No
2200235745 | أمانة / جدة | تشييد | ذات اولوية عالية | 20368445 | 1018422.25 | 0 | 0 | 4030129949 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 1 | 1 | 2022-09-21 | 2024-08-29 | 2024-08-29 | 2024-08-29 |  |  |  |  | 39.1678 | 21.5005 | منتظم | No
2100087511 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 21428398 | 1071419.9 | 20904389.61 | 20879369.61 | 4031046036 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2020-02-17 | 2021-02-16 | 2021-02-16 | 2021-02-16 | 2021-02-16 |  | أوامر تغيير |  |  |  | منجز | No
2100002310 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 28890650.7 | 1444532.535 | 20072346.16 | 20072346.16 | 1010185409 | لا | 0 |  | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-12-25 | 2019-10-21 | 2021-09-21 | 2021-09-21 |  |  | منازعات قائمة | أخرى |  |  | Failed | No
2100060583 | أمانة / حفر الباطن | تشييد | ذات اولوية عالية وعاجلة | 47493921 | 2374696.05 | 47453186 | 42301351 | 1010136405 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-08-11 | 2018-01-13 | 2021-12-31 | 2021-12-31 | 2018-01-13 |  | تأخرصرف المستحقات المالية |  | 45.9986 | 28.2911 | منجز | No
2200226726 | أمانة / حفر الباطن | تشييد | ذات اولوية عالية | 11945395 | 597269.75 | 6306239.64 | 6306239.64 | 1010008188 | لا | 0 |  | جاري | تكلفة العمل المنجز | 56 | 73 | 2022-04-03 | 2023-03-29 | 2023-03-29 | 2023-03-29 |  |  |  |  | 45.9627 | 28.3784 | متأخر | No
2200226730 | أمانة / حفر الباطن | تشييد | ذات اولوية عالية | 3655713.15 | 182785.6575 | 3130300 | 3130300 | 1010019983 | لا | 0 |  | جاري | تكلفة العمل المنجز | 90 | 93 | 2022-02-22 | 2023-02-17 | 2023-02-01 | 2023-02-01 |  |  |  |  | 45.9627 | 28.3784 | منتظم | No
2100082633 | أمانة / حفر الباطن | تشييد | ذات اولوية متوسطة | 18080058.5 | 904002.925 | 18080058.5 | 15976370.93 | 2511006133 | لا | 0 | 181001160404 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-12-22 | 2021-06-15 | 2020-12-24 | 2020-12-24 | 2021-06-15 |  | ضعف كفاءة المقاول الفنية |  | 45.9966 | 28.3659 | منجز | No
2200227695 | أمانة / حفر الباطن | تشييد | ذات اولوية عالية | 1627250 | 81362.5 | 162750 | 162750 | 1010350726 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 77 | 82 | 2021-11-16 | 2022-11-11 | 2022-11-11 | 2022-11-11 | 2021-11-11 |  |  |  | 45.9627 | 28.3784 | منجز | No
2100072704 | أمانة / حفر الباطن | تشييد | ذات اولوية متوسطة | 18850730 | 942536.5 | 18850730 | 18450201 | 1010136405 | لا | 0 | 0 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2015-06-09 | 2019-11-01 | 2019-12-30 | 2019-12-30 | 2019-11-01 |  | تأخرصرف المستحقات المالية |  | 45.9656 | 28.4187 | منجز | No
2200236342 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 59131495 | 2956574.75 | 59126072 | 59126072 | 4030043565 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 92.59 | 92.59 | 2020-01-26 | 2022-01-03 | 2022-01-03 | 2022-01-03 | 2022-01-03 |  |  |  | 39.8579 | 21.3891 | منجز | No
2200236364 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 98590857.75 | 4929542.8875 | 90478027.85 | 90478027.85 | 4030043565 | لا | 0 |  | منجز – استلام ابتدائي | مدفوعات ساعات العمل | 91.77 | 91.77 | 2020-09-04 | 2022-03-18 | 2022-03-18 | 2022-03-18 | 2022-03-18 |  |  |  | 39.8579 | 21.3891 | منجز | No
2100066393 | أمانة / العاصمة المقدسة | أخرى | ذات اولوية متوسطة | 47968250 | 2398412.5 | 42744825.1 | 42744825.1 | 4031041927 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 99.01 | 100 | 2013-05-01 | 2015-10-30 | 2017-02-09 | 2017-02-09 | 2015-10-30 |  |  |  | 39.8665 | 21.3943 | منجز | No
2200233730 | أمانة / الرياض | الخدمات الاستشارية | ذات اولوية متوسطة | 18381600 | 919080 | 8125696.2 | 8125696.2 | 1010322156 | لا | 0 |  | جاري | اخرى | 18 | 20 | 2022-02-20 | 2023-12-29 | 2023-12-29 | 2023-12-29 |  |  |  |  | 46.6736 | 24.6258 | خدمات عامة | No
2100054412 | وزارة النقل والخدمات اللوجستية / منطقة مكة المكرمة | تشييد | ذات اولوية منخفضة | 54999999.45 | 2749999.9725 | 53123133.46 | 53123133.46 | 4031032312 | لا | 0 | 181109339076 | منجز – استلام نهائي | الكميات التي تم تركيبها | 100 | 100 | 2011-07-09 | 2017-07-01 | 2017-12-31 | 2017-12-31 | 2017-07-01 | 2020-01-26 |  |  | 39.8262 | 21.4066 | منجز | No
2300239676 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 23711107.1 | 1185555.355 | 0 | 0 | 4031042604 | لا | 0 |  | جاري | اخرى | 0 | 0 | 2021-12-03 | 2023-12-03 | 2023-12-03 | 2023-12-03 |  |  |  |  | 46.6736 | 24.6258 | منتظم | No
2300239680 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 161705242.1 | 8085262.105 | 19788708.2 | 19788707 | 0 | لا | 0 |  | جاري | اخرى | 2.24 | 8.89 | 2022-07-18 | 2023-11-03 | 2023-11-03 | 2023-11-03 |  |  |  |  | 46.6736 | 24.6258 | متأخر | No
2200229983 | وزارة الدفاع / الإدارة الهندسية والاشغال بقوة الصواريخ الإستراتيجية | تشييد | ذات اولوية عالية | 1999544.1 | 99977.205 | 398588.22 | 398588.22 | 1010495829 | لا | 0 | 200939238162 | جاري | الكميات التي تم تركيبها | 38 | 81 | 2022-02-24 | 2023-02-19 | 2023-07-18 | 2023-07-18 |  |  |  | تم إشعار المقاول كتابيا بالتأخير | 45.5629 | 20.4669 | Failed | No
2100048941 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية وعاجلة | 84808302.24 | 4240415.112 | 33181373.52 | 33181373.52 | 2051003203 | لا | 0 | 180709022022 | مسحوب | تكلفة العمل المنجز | 65 | 100 | 2014-06-22 | 2016-12-08 | 2025-12-31 | 2025-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 49.5586 | 25.2605 | مسحوب | No
2300239691 | جامعة الملك سعود | هدم و ازالة | ذات اولوية عالية | 740000 | 37000 | 0 | 0 | 0 | لا | 0 |  | جاري | اخرى | 0 | 3 | 2023-01-17 | 2023-06-16 | 2023-06-16 | 2023-06-16 |  |  |  |  | 46.6244 | 24.7124 | منتظم | No
2100043551 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 54543500 | 2727175 | 54543500 | 46907410 | 1010052246 | لا | 0 |  | جاري | تكلفة العمل المنجز | 86 | 97 | 2017-11-28 | 2022-10-11 | 2022-10-11 | 2022-10-11 |  |  | ضعف كفاءة المقاول الفنية |  | 39.5644 | 24.4929 | متأخر | No
2300239702 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 10091250.5 | 504562.525 | 323921.39 | 323921.39 | 1010321365 | لا | 0 |  | جاري | اخرى | 3.21 | 3.97 | 2022-08-14 | 2024-11-02 | 2024-11-02 | 2024-11-02 |  |  |  |  | 46.6736 | 24.6258 | منتظم | No
2100076160 | أمانة / حفر الباطن | تشييد | ذات اولوية متوسطة | 89977650 | 4498882.5 | 64796089 | 64796089 | 1011010795 | لا | 0 | 190701200641 | جاري | تكلفة العمل المنجز | 72 | 86 | 2019-12-02 | 2023-03-15 | 2023-05-13 | 2023-05-13 |  |  |  |  | 46.0046 | 28.3807 | متأخر | No
2100034226 | أمانة / حفر الباطن | تشييد | ذات اولوية متوسطة | 18951820 | 947591 | 6895656 | 0 | 2511005876 | لا | 0 | 0 | مسحوب | تكلفة العمل المنجز | 1 | 100 | 2015-05-10 | 2017-10-18 | 2021-06-17 | 2021-06-17 |  |  | ضعف كفاءة المقاول الفنية |  | 45.985 | 28.3739 | مسحوب | Yes
2100046572 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 18350575 | 917528.75 | 18350575 | 16714442 | 4650007032 | لا | 0 |  | جاري | تكلفة العمل المنجز | 91 | 100 | 2019-10-26 | 2021-10-25 | 2023-01-25 | 2023-01-25 |  |  | ضعف كفاءة المقاول الفنية |  | 39.5904 | 24.4445 | متأخر | No
2100057551 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية منخفضة | 2698718.4 | 134935.92 | 1404120 | 1404120 | 4031058260 | لا | 0 |  | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 90 | 100 | 2019-08-31 | 2021-09-15 | 2021-09-15 | 2021-09-15 |  |  |  | أخرى | 48.4796 | 27.4685 | Failed | No
2100108371 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 49764737 | 2488236.85 | 46808920.33 | 46808920.33 | 1010031532 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-03-12 | 2020-12-02 | 2020-12-02 | 2020-12-02 | 2020-12-02 |  | أوامر تغيير | أخرى |  |  | منجز | No
2100048834 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 3815375 | 190768.75 | 3997059.5 | 3997059.5 | 4030198598 | لا | 0 | 200309018057 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-08-20 | 2020-08-10 | 2021-01-07 | 2021-01-07 | 2020-08-10 |  | ضعف كفاءة المقاول الفنية |  | 41.6677 | 19.5812 | منجز | No
2100048160 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 884460 | 44223 | 914577.13 | 242000 | 5802010434 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-10-31 | 2020-04-25 | 2020-08-10 | 2020-08-10 | 2020-04-25 |  | ضعف كفاءة المقاول الفنية |  | 41.31 | 18.9762 | منجز | No
2100009424 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 265245717.07 | 13262285.8535 | 177465881.44 | 177465881.44 | 1010329341 | لا | 0 |  | ايقاف جزئي | منهجية القيمة المكتسبة | 72 | 100 | 2019-12-18 | 2021-06-10 | 2023-04-30 | 2023-04-30 |  |  | منازعات قائمة | أخرى |  |  | Failed | No
2100018675 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 43699563 | 2184978.15 | 43699563 | 43699563 | 4650049563 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2016-03-08 | 2022-02-17 | 2022-02-17 | 2022-02-17 | 2022-02-17 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.5581 | 24.517 | منجز | No
2100048226 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 845480 | 42274 | 871380 | 543900 | 5802010434 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-11-05 | 2020-04-30 | 2020-08-10 | 2020-08-10 | 2020-04-30 |  | اخرى |  | 41.3087 | 18.9762 | منجز | No
2100023435 | شركة المياه الوطنية / منطقة الجوف | تشييد | ذات اولوية عالية | 7074221 | 353711.05 | 1674253.27 | 1674253.27 | 5950004981 | لا | 0 |  | مسحوب | منهجية القيمة المكتسبة | 41.48 | 100 | 2011-01-12 | 2012-06-28 | 2023-03-23 | 2023-03-23 |  |  | ضعف كفاءة المقاول الفنية |  | 37.8679 | 30.8353 | مسحوب | No
2100005176 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 176071437 | 8803571.85 | 165926416.38 | 165780419.17 | 1010185409 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-08-10 | 2018-08-10 | 2019-10-24 | 2019-10-24 | 2018-08-10 |  | منازعات قائمة | أخرى |  |  | منجز | No
2100052570 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 778601 | 38930.05 | 778601.25 | 778601.25 | 4602001616 | لا | 0 | 180709025521 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-07-23 | 2020-07-11 | 2020-06-29 | 2020-06-29 | 2020-07-11 |  | ضعف كفاءة المقاول الفنية |  | 39.7378 | 23.0048 | منجز | No
2100042372 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 10584000 | 529200 | 10584000 | 10478160 | 1010185409 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-07-28 | 2020-01-24 | 2020-01-24 | 2020-01-24 | 2020-01-24 |  | عدم اكتمال أو ضعف أعمال التصميم والدراسات | أخرى |  |  | منجز | No
2100000184 | شركة المياه الوطنية / منطقة الجوف | تشييد | ذات اولوية عالية | 49264387.5 | 2463219.375 | 35258775.04 | 35258775.04 | 1116002219 | لا | 0 | 180201000159 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 98 | 100 | 2018-10-07 | 2021-09-04 | 2022-08-17 | 2022-08-17 | 2021-09-04 |  | لا يوجد تأخير |  | 40.2103 | 29.9425 | منجز | No
2100018222 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 5534467 | 276723.35 | 4443951.26 | 4368984.48 | 1128000011 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-11-06 | 2020-08-02 | 2020-08-02 | 2020-08-02 | 2020-08-02 |  | أوامر تغيير | أخرى |  |  | منجز | No
2200226785 | أمانة / حفر الباطن | تشييد | ذات اولوية عالية | 1819310.93 | 90965.5465 | 1819310.93 | 1819310.93 | 7001653174 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2022-02-24 | 2023-02-19 | 2023-02-01 | 2023-02-01 | 2023-02-19 |  |  |  | 45.9627 | 28.3784 | منجز | No
2300239724 | رئاسة أمن الدولة / المديرية العامة للمباحث | ترميم | ذات اولوية متوسطة | 270250 | 13512.5 | 0 | 0 | 3550025468 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 30 | 50 | 2022-10-18 | 2023-02-13 | 2023-02-13 | 2023-02-13 |  |  |  |  | 46.6992 | 24.6718 | متأخر | No
2100108430 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 76929721.25 | 3846486.0625 | 57736435.8 | 57736435.8 | 1010136405 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 97 | 100 | 2018-12-31 | 2020-06-23 | 2023-03-13 | 2023-03-13 |  |  | أوامر تغيير | أخرى |  |  | متأخر | No
2100098103 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 63836255.21 | 3191812.7605 | 46402851.98 | 46402851.98 | 1010039430 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 95 | 98 | 2018-12-30 | 2019-12-30 | 2023-03-15 | 2023-03-15 |  |  | أوامر تغيير | أخرى |  |  | منتظم | No
2100026622 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 3994200 | 199710 | 3994200 | 3994200 | 4605000749 | لا | 0 | 200101004376 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-12-21 | 2020-12-10 | 2020-12-09 | 2020-12-09 | 2020-12-10 |  | اخرى |  | 39.7874 | 22.2686 | منجز | No
2300239735 | رئاسة أمن الدولة / المديرية العامة للمباحث | تشييد | ذات اولوية متوسطة | 4965401 | 248270.05 | 0 | 0 | 1010242486 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 35 | 60 | 2022-10-02 | 2023-02-26 | 2023-02-26 | 2023-02-26 |  |  |  |  | 46.6992 | 24.6719 | Failed | No
2100091792 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 143862526 | 7193126.3 | 79983601.81 | 79983601.81 | 5855000147 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 93 | 100 | 2019-10-30 | 2021-01-22 | 2023-05-31 | 2023-05-31 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ | أخرى |  |  | Failed | No
2300239746 | وزارة الصحة | ترميم | ذات اولوية عالية | 4909666 | 245483.3 | 2245689.32 | 1028156.63 | 4030185377 | لا | 0 |  | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 90 | 100 | 2022-04-03 | 2022-11-26 | 2023-01-31 | 2023-01-31 |  |  |  |  | 41.4713 | 20.0217 | متأخر | No
2100088642 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 104874703 | 5243735.15 | 102609820.02 | 101933553.11 | 1010329341 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-12-30 | 2019-12-30 | 2020-03-29 | 2020-03-29 | 2019-12-30 |  | منازعات قائمة | أخرى |  |  | منجز | No
2300239750 | رئاسة أمن الدولة / المديرية العامة للمباحث | تشييد | ذات اولوية متوسطة | 6942918 | 347145.9 | 0 | 0 | 4031042604 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 5 | 10 | 2022-10-30 | 2024-04-14 | 2024-04-14 | 2024-04-14 |  |  |  |  | 46.6992 | 24.6718 | منتظم | No
2100051295 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 797311 | 39865.55 | 835278.16 | 835278.16 | 4603001574 | لا | 0 | 200309117637 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 90 | 100 | 2019-04-18 | 2021-03-25 | 2021-06-01 | 2021-06-01 | 2021-03-25 |  | ضعف كفاءة المقاول الفنية |  | 41.3607 | 18.7165 | منجز | No
2100061051 | شركة المياه الوطنية / منطقة الجوف | تشييد | ذات اولوية عالية | 79865460 | 3993273 | 79865460 | 61039741.75 | 5950014087 | لا | 0 | 180201000160 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-04-30 | 2021-03-27 | 2022-11-30 | 2022-11-30 | 2021-03-27 |  | لا يوجد تأخير |  | 40.2405 | 29.971 | منجز | No
2100075821 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 21289806 | 1064490.3 | 7175483.49 | 0 | 2051007339 | لا | 0 | 181001117920 | ايقاف كلي | تكلفة العمل المنجز | 47 | 100 | 2019-03-09 | 2020-08-21 | 2020-03-01 | 2020-03-01 |  |  | ضعف كفاءة المقاول الفنية | أخرى | 50.0054 | 26.5534 | Failed | Yes
2100028276 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 1081748.75 | 54087.4375 | 1081749 | 1081748.75 | 4603002630 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 80.4 | 80.4 | 2018-08-27 | 2020-10-22 | 2020-10-22 | 2020-10-22 | 2020-10-22 |  | ضعف كفاءة المقاول الفنية |  | 39.2042 | 21.519 | منجز | No
2100085864 | شركة المياه الوطنية / منطقة الجوف | إشراف | ذات اولوية عالية | 2052000 | 102600 | 4577983.5 | 4553015.76 | 1010421976 | لا | 0 | 180709030288 | منجز – استلام نهائي | مدفوعات ساعات العمل | 100 | 100 | 2014-08-17 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2016-02-16 | 2020-01-18 | لا يوجد تأخير |  | 37.3857 | 31.3163 | منجز | No
2300239805 | رئاسة أمن الدولة / المديرية العامة للمباحث | توريد وتركيب | ذات اولوية متوسطة | 45281.25 | 2264.0625 | 0 | 0 | 1010190575 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 80 | 100 | 2023-01-03 | 2023-03-02 | 2023-03-02 | 2023-03-02 |  |  |  |  | 46.6992 | 24.6718 | متأخر | No
2300239713 | وزارة الصحة | تشطيب | ذات اولوية متوسطة | 254249.16 | 12712.458 | 254249.16 | 0 | 4603001885 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2022-06-23 | 2022-09-19 | 2022-09-19 | 2022-09-19 | 2022-09-19 |  |  |  | 41.5068 | 19.975 | منجز | Yes
2100007770 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 66668888.16 | 3333444.408 | 56548489.46 | 56548489.46 | 1010090968 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2018-01-01 | 2019-01-01 | 2020-10-13 | 2020-10-13 | 2019-01-01 |  | منازعات قائمة | أخرى |  |  | منجز | No
2300239816 | وزارة الصحة | تشييد | ذات اولوية عالية | 5299173.6 | 264958.68 | 5299173.6 | 4796689.08 | 5907024458 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-12-08 | 2022-05-04 | 2022-05-04 | 2022-05-04 | 2022-05-04 |  |  |  | 41.4535 | 20.0565 | منجز | No
2100003356 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية متوسطة | 57180015.34 | 2859000.767 | 13635372.47 | 8827146.5 | 2050020357 | لا | 0 | 181109323692 | ايقاف كلي | تكلفة العمل المنجز | 25 | 94 | 2015-05-16 | 2017-11-01 | 2025-12-31 | 2025-12-31 |  |  | تأخرصرف المستحقات المالية |  | 49.9885 | 26.2655 | Failed | No
2300239794 | أمانة / الباحة | تشييد | ذات اولوية عالية وعاجلة | 1690020.45 | 84501.0225 | 0 | 0 | 5810001890 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 40 | 100 | 2022-08-28 | 2023-02-21 | 2023-02-21 | 2023-02-21 |  |  |  |  | 41.678 | 20.2381 | Failed | No
2100006635 | وكالة / الإسكان | تشييد | ذات اولوية متوسطة | 31022846.28 | 1551142.314 | 24106786.25 | 24106786.25 | 5855000147 | لا | 0 |  | جاري الاستلام الإبتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-11-05 | 2021-01-28 | 2022-12-31 | 2022-12-31 |  |  | أوامر تغيير | أخرى |  |  | Failed | No
2300239820 | رئاسة أمن الدولة / المديرية العامة للمباحث | تشييد | ذات اولوية متوسطة | 122425.55 | 6121.2775 | 0 | 0 | 2050160330 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 50 | 100 | 2022-11-14 | 2023-01-18 | 2023-02-28 | 2023-02-28 |  |  |  |  | 46.6992 | 24.6719 | Failed | No
2300239853 | وزارة الصحة | تشييد | ذات اولوية عالية | 3347429 | 167371.45 | 0 | 0 | 1010240529 | نعم | 0.0001 |  | مسحوب | الكميات التي تم تركيبها | 22 | 100 | 2016-05-01 | 2017-10-13 | 2017-10-14 | 2017-10-14 |  |  |  | مخطط لإعادة طرحه | 41.5778 | 19.8793 | مسحوب | No
2300239831 | وزارة الصحة | تشييد | ذات اولوية عالية | 3919449 | 195972.45 | 874323.54 | 874323.54 | 4030190342 | نعم | 874323.54 |  | مسحوب | الكميات التي تم تركيبها | 32 | 100 | 2015-08-09 | 2017-09-20 | 2020-09-21 | 2020-09-21 |  |  |  |  | 41.9078 | 20.2978 | مسحوب | No
2100106002 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية | 110554972.8 | 5527748.64 | 86662851.12 | 86605561.88 | 1010152370 | لا | 0 | 180709019992 | جاري | تكلفة العمل المنجز | 97 | 97 | 2014-11-26 | 2017-02-03 | 2023-12-31 | 2023-12-31 |  |  | تأخرصرف المستحقات المالية |  | 39.8147 | 21.2842 | منتظم | No
2300239864 | أمانة / الجوف | تشييد | ذات اولوية عالية وعاجلة | 1542150 | 77107.5 | 622916 | 622916 | 3450009076 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 100 | 100 | 2022-06-05 | 2023-02-04 | 2023-02-04 | 2023-02-04 |  |  |  |  | 37.6333 | 31.0752 | منتظم | No
2300239842 | أمانة / الجوف | تشييد | ذات اولوية عالية وعاجلة | 1542150 | 77107.5 | 622916 | 622916 | 3450009076 | لا | 0 |  | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 100 | 100 | 2022-06-05 | 2023-02-04 | 2023-02-04 | 2023-02-04 |  |  |  |  | 37.6333 | 31.0752 | منتظم | No
2100001374 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية | 63298801.28 | 3164940.064 | 53567120.1 | 52984162.98 | 1010069654 | لا | 0 | 180709020192 | جاري | تكلفة العمل المنجز | 98 | 100 | 2014-12-07 | 2017-02-14 | 2023-12-31 | 2023-12-31 |  |  | تأخرصرف المستحقات المالية |  | 46.7385 | 22.3313 | متأخر | No
2300239875 | وزارة الصحة | تحديث وتوريد | ذات اولوية عالية وعاجلة | 661319 | 33065.95 | 209596 | 209596 | 0 | لا | 0 |  | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 85 | 100 | 2021-09-29 | 2022-03-25 | 2023-01-31 | 2023-01-31 |  |  |  |  | 41.5671 | 19.8629 | متأخر | No
2300241382 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 399708015 | 19985400.75 | 4058399.45 | 4058399.45 | 1116005202 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 89 | 100 | 2020-12-30 | 2022-11-24 | 2022-11-25 | 2022-11-25 |  |  |  |  | 43.6756 | 24.6756 | متأخر | No
2100001956 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 11872083 | 593604.15 | 6849857.6 | 0 | 1116004627 | لا | 0 | 190309005162 | جاري | التكلفة المفوترة | 90 | 100 | 2012-12-23 | 2014-12-13 | 2022-05-11 | 2022-05-11 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5429 | 16.8808 | Failed | Yes
2300239886 | الهيئة العامة للطيران المدني | أخرى | ذات اولوية عالية | 22148225 | 1107411.25 | 0 | 0 | 0 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 0 | 0 | 2022-09-04 | 2025-02-20 | 2025-02-20 | 2025-02-20 |  |  |  |  | 49.7972 | 26.4683 | خدمات عامة | No
2300239890 | الهيئة العامة للطيران المدني | تصميم وتشييد | ذات اولوية متوسطة | 3696900 | 184845 | 2289448 | 0 | 0 | لا | 0 |  | جاري | تكلفة العمل المنجز | 80 | 50 | 2022-04-04 | 2023-04-04 | 2023-03-31 | 2023-03-31 |  |  |  |  | 49.7972 | 26.4683 | منتظم | Yes
2200229585 | أمانة / جدة | أخرى | ذات اولوية عالية | 18700000 | 935000 | 18206993.35 | 13541083.37 | 1010216421 | لا | 0 | 180401001723 | منجز – استلام ابتدائي | اخرى | 97 | 100 | 2018-09-09 | 2021-09-08 | 2022-06-04 | 2022-06-04 | 2021-09-08 |  |  |  | 39.1677 | 21.5007 | منجز | No
2300239901 | هيئة المدن الصناعية ومناطق التقنية | تشييد | ذات اولوية عالية | 168555197 | 8427759.85 | 0 | 0 | 1010039430 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 0 | 0 | 2023-01-08 | 2025-12-08 | 2025-12-08 | 2025-12-08 |  |  |  |  | 42.6649 | 18.3407 | منتظم | No
2300239912 | هيئة المدن الصناعية ومناطق التقنية | تشييد | ذات اولوية عالية | 150942392 | 7547119.6 | 0 | 0 | 1010039430 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 0 | 2 | 2022-10-26 | 2025-09-25 | 2025-09-25 | 2025-09-25 |  |  |  |  | 39.3362 | 21.1242 | منتظم | No
2300239960 | أمانة / الرياض | الخدمات الاستشارية | ذات اولوية متوسطة | 14938500 | 746925 | 0 | 0 | 1010281596 | لا | 0 |  | جاري | اخرى | 0 | 0 | 2022-09-15 | 2024-09-15 | 2024-09-15 | 2024-09-15 |  |  |  |  | 46.6736 | 24.6258 | خدمات عامة | No
2300239923 | هيئة المدن الصناعية ومناطق التقنية | تشييد | ذات اولوية متوسطة | 7158462 | 357923.1 | 4329756 | 4147322 | 4030199041 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 64 | 48 | 2021-12-28 | 2023-06-27 | 2023-06-27 | 2023-06-27 |  |  |  |  | 42.6649 | 18.3407 | منتظم | No
2300239971 | هيئة المدن الصناعية ومناطق التقنية | تشييد | ذات اولوية عالية | 11942605 | 597130.25 | 0 | 0 | 1010010305 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 0 | 0 | 2022-03-20 | 2023-09-11 | 2023-09-11 | 2023-09-11 |  |  |  |  | 46.8743 | 24.4077 | منتظم | No
2100001120 | المؤسسة العامة للتدريب التقني والمهني | تشييد | ذات اولوية عالية | 5356876.54 | 267843.827 | 3221247.39 | 2858833.07 | 2057002282 | نعم | 1461892.18 | 180709022519 | جاري | تكلفة العمل المنجز | 91 | 100 | 2017-07-14 | 2018-04-09 | 2025-12-31 | 2025-12-31 |  |  | اخرى |  | 49.8968 | 26.7751 | متأخر | No
2100208003 | الهيئة العامة للطيران المدني | تصميم | ذات اولوية عالية | 25061599.2 | 1253079.96 | 20324127.12 | 20324127.12 | 4030276223 | لا | 0 | 190409032705 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2017-02-13 | 2018-11-10 | 2018-11-10 | 2018-11-10 |  |  |  |  | 46.1255 | 28.3308 | Failed | No
2100208036 | الهيئة العامة للطيران المدني | توريد وتركيب | ذات اولوية عالية وعاجلة | 13804280 | 690214 | 11698751 | 11698751 | 4032016864 | لا | 0 | 200809128763 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-03-22 | 2017-08-26 | 2017-08-26 | 2017-08-26 | 2017-08-26 |  |  |  | 46.7007 | 24.9637 | منجز | No
2100002203 | الهيئة العامة للطيران المدني | تشييد | ذات اولوية عالية | 49442371.35 | 2472118.5675 | 44442371.35 | 44442371.35 | 1010020305 | لا | 0 | 181009138991 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2013-01-30 | 2015-01-19 | 2020-12-18 | 2020-12-18 | 2015-01-19 |  | لا يوجد تأخير |  | 39.5462 | 24.4947 | منجز | No
2300239934 | هيئة المدن الصناعية ومناطق التقنية | تشييد | ذات اولوية عالية | 10854210 | 542710.5 | 0 | 0 | 1010206690 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 0 | 0 | 2022-12-20 | 2024-12-09 | 2024-12-09 | 2024-12-09 |  |  |  |  | 46.8835 | 24.5478 | منتظم | No
2100034790 | وزارة الصحة / الرياض | تشييد | ذات اولوية متوسطة | 24106437 | 1205321.85 | 19441665 | 19441665 | 1010191039 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 95 | 95 | 2014-04-27 | 2016-04-26 | 2018-11-13 | 2018-11-13 | 2016-04-26 |  | تأخرصرف المستحقات المالية |  | 46.7098 | 24.6275 | منجز | No
2300239945 | هيئة المدن الصناعية ومناطق التقنية | تشييد | ذات اولوية عالية | 8282785 | 414139.25 | 0 | 0 | 1131013992 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 0 | 0 | 2022-11-06 | 2024-10-26 | 2024-10-26 | 2024-10-26 |  |  |  |  | 45.701 | 25.7227 | منتظم | No
2100085282 | وزارة الصحة / الرياض | تشييد | ذات اولوية متوسطة | 23389601 | 1169480.05 | 21934110 | 21102442 | 1010191039 | لا | 0 |  | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 95 | 92 | 2014-04-27 | 2016-04-26 | 2020-04-19 | 2020-04-19 |  |  | تأخرصرف المستحقات المالية |  | 46.6692 | 24.7025 | Failed | No
2300239956 | هيئة المدن الصناعية ومناطق التقنية | تشييد | ذات اولوية عالية | 17344609 | 867230.45 | 0 | 0 | 1010135922 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 0 | 0 | 2022-11-24 | 2024-11-13 | 2024-11-13 | 2024-11-13 |  |  |  |  | 45.701 | 25.7227 | منتظم | No
2100040611 | وزارة الصحة / حفر الباطن | تشييد | ذات اولوية متوسطة | 10789515 | 539475.75 | 4194124.8 | 4194124.8 | 2511006797 | لا | 0 | 190301084214 | جاري | الكميات التي تم تركيبها | 65 | 100 | 2019-04-01 | 2021-03-19 | 2021-08-09 | 2021-08-09 |  |  | تأخرصرف المستحقات المالية | تم تمديد الجدول الزمني | 45.9764 | 28.4132 | Failed | No
2100085120 | وزارة الصحة / حفر الباطن | تشييد | ذات اولوية عالية وعاجلة | 46646758.04 | 2332337.902 | 40107499.74 | 40107499.74 | 2055002421 | لا | 0 | 181009159316 | جاري | الكميات التي تم تركيبها | 95 | 100 | 2013-05-11 | 2015-05-10 | 2023-07-01 | 2023-07-01 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال | مخطط لسحبه وإعادة ترسيته | 45.9536 | 28.311 | Failed | No
2300239982 | أمانة / الرياض | أخرى | ذات اولوية متوسطة | 46403074.08 | 2320153.704 | 0 | 0 | 4031042604 | لا | 0 |  | جاري | اخرى | 0 | 0 | 2022-03-17 | 2024-03-17 | 2024-03-17 | 2024-03-17 |  |  |  |  | 46.6736 | 24.6258 | خدمات عامة | No
2300239993 | هيئة المدن الصناعية ومناطق التقنية | تشييد | ذات اولوية عالية | 13121525 | 656076.25 | 1625882 | 1055695 | 1011009116 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 17 | 17 | 2021-12-29 | 2023-09-28 | 2023-09-28 | 2023-09-28 |  |  |  |  | 49.9858 | 26.2502 | منتظم | No
2300240004 | هيئة المدن الصناعية ومناطق التقنية | تشييد | ذات اولوية عالية | 7694610 | 384730.5 | 0 | 0 | 1010199022 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 0 | 0 | 2023-01-10 | 2024-07-09 | 2024-07-09 | 2024-07-09 |  |  |  |  | 45.9627 | 28.3784 | منتظم | No
2100059194 | أمانة / جدة | تشييد | ذات اولوية عالية وعاجلة | 108942448 | 5447122.4 | 82160000 | 79764725.88 | 4030017054 | لا | 0 | 190509128348 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 99.9 | 100 | 2019-02-17 | 2020-02-05 | 2021-12-30 | 2021-12-30 |  |  | أوامر سامية | أخرى | 39.1671 | 21.5393 | Failed | No
2300240015 | هيئة المدن الصناعية ومناطق التقنية | تشييد | ذات اولوية عالية | 14625500 | 731275 | 3488535 | 3488535 | 1010206690 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 30 | 23 | 2021-12-23 | 2023-06-22 | 2023-06-22 | 2023-06-22 |  |  |  |  | 39.3362 | 21.1242 | منتظم | No
2100066010 | أمانة / جدة | تشييد | ذات اولوية متوسطة | 28311000 | 1415550 | 0 | 0 | 1010242626 | لا | 0 |  | فسخ العقد | الكميات التي تم تركيبها | 8 | 58 | 2015-05-19 | 2018-03-13 | 2017-04-26 | 2017-04-26 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.0251 | 22.7885 | مسحوب | No
2100000420 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 70863307.77 | 3543165.3885 | 57831925.02 | 57831925.02 | 1010185409 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2020-01-29 | 2021-07-22 | 2022-09-30 | 2022-09-30 | 2021-07-22 |  | أوامر تغيير | أخرى |  |  | منجز | No
2100194541 | أمانة / جدة | تشييد | ذات اولوية عالية وعاجلة | 93478944 | 4673947.2 | 56957601.68 | 56957601.68 | 4030017054 | لا | 0 | 200701137888 | جاري | تكلفة العمل المنجز | 86 | 94 | 2020-10-10 | 2022-09-22 | 2023-03-19 | 2023-03-19 |  |  |  |  | 39.2537 | 21.5296 | متأخر | No
2200223193 | أمانة / جدة | تشييد | ذات اولوية عالية | 85830437 | 4291521.85 | 5157323 | 5157323 | 2050001536 | لا | 0 | 211201076500 | جاري | الكميات التي تم تركيبها | 45 | 47 | 2022-03-13 | 2024-03-12 | 2024-03-12 | 2024-03-12 |  |  |  |  | 39.1153 | 21.7507 | منتظم | No
2100088200 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 184630726 | 9231536.3 | 162697781.36 | 162697781.36 | 1123000085 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-03-13 | 2020-10-18 | 2020-10-18 | 2020-10-18 | 2020-10-18 |  | أوامر تغيير | أخرى |  |  | منجز | No
2100088620 | جامعة طيبة | تشييد | ذات اولوية عالية | 355374909 | 17768745.45 | 292507646 | 287523856.32 | 4030068284 | لا | 0 | 180809038835 | جاري | تكلفة العمل المنجز | 81.82 | 87.14 | 2009-12-12 | 2011-04-15 | 2023-04-10 | 2023-04-10 |  |  | عدم وجود مبالغ في البنود تغطي الأعمال المرصودة | تم تمديد الجدول الزمني | 39.6005 | 24.4595 | متأخر | No
2100016870 | وكالة / الإسكان | تشييد | ذات اولوية متوسطة | 250655984.69 | 12532799.2345 | 191473971.42 | 191473971.42 | 1010329341 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 90 | 100 | 2018-10-24 | 2020-10-23 | 2023-07-31 | 2023-07-31 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ | أخرى |  |  | متأخر | No
2100002940 | جامعة طيبة | تشييد | ذات اولوية عالية | 135741834.9 | 6787091.745 | 24629209.41 | 23748723.05 | 1010306708 | لا | 0 | 181109377277 | جاري | تكلفة العمل المنجز | 18.5 | 88 | 2015-02-26 | 2017-08-13 | 2024-02-13 | 2024-02-13 |  |  | تأخرصرف المستحقات المالية | تم إشعار المقاول كتابيا بالتأخير | 39.6005 | 24.4595 | Failed | No
2300240026 | أمانة / الرياض | الخدمات الاستشارية | ذات اولوية متوسطة | 10091250.5 | 504562.525 | 0 | 0 | 1010321365 | لا | 0 |  | جاري | اخرى | 3.21 | 3.97 | 2022-08-14 | 2024-08-14 | 2024-08-14 | 2024-08-14 |  |  |  |  | 46.6736 | 24.6258 | خدمات عامة | No
2100091501 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | دراسات هندسية | ذات اولوية عالية وعاجلة | 15000000 | 750000 | 1468680 | 1468680 | 1010320728 | لا | 0 | 180809058624 | جاري | تكلفة العمل المنجز | 10 | 100 | 2016-06-29 | 2021-06-28 | 2022-10-30 | 2022-10-30 |  |  |  |  | 49.1542 | 27.4924 | خدمات عامة | No
2100019821 | الهيئة الملكية للجبيل وينبع / مدينتي الجبيل ورأس الخير الصناعية | دراسة بيئية | ذات اولوية عالية وعاجلة | 12202300 | 610115 | 11256341.49 | 11256341.49 | 1010187400 | لا | 0 | 181009156999 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 85 | 100 | 2016-06-29 | 2021-06-28 | 2022-06-28 | 2022-06-28 | 2021-06-28 |  |  |  | 49.1757 | 27.4945 | منجز | No
2300240030 | أمانة / الأحساء | تشييد | ذات اولوية عالية | 9080800 | 454040 | 354382 | 0 | 2251007095 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 4 | 5 | 2022-09-11 | 2024-03-04 | 2024-03-05 | 2024-03-05 |  |  |  |  | 49.5432 | 25.2898 | منتظم | Yes
2100087975 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 9811881.68 | 490594.084 | 8995570.46 | 7252287.31 | 1010060469 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2016-02-09 | 2018-01-29 | 2019-11-05 | 2019-11-05 | 2018-01-29 |  | اخرى |  | 42.5429 | 16.8808 | منجز | No
2100074421 | الهيئة العامة للموانئ | تشييد | ذات اولوية عالية | 19001308 | 950065.4 | 15728768 | 15728768 | 4031028157 | نعم | 500000 |  | جاري | تكلفة العمل المنجز | 83 | 100 | 2015-01-18 | 2016-07-11 | 2019-03-22 | 2019-03-22 |  |  | اخرى |  | 39.173 | 21.4648 | Failed | No
2100021394 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 14729627.64 | 736481.382 | 12738538 | 11776801.5 | 4031041927 | لا | 0 | 200609130074 | جاري | التكلفة المفوترة | 100 | 100 | 2012-09-07 | 2014-08-28 | 2022-04-10 | 2022-04-10 |  |  | ضعف كفاءة المقاول الفنية |  | 39.836 | 21.4408 | Failed | No
2300240052 | أمانة / الأحساء | تصميم وإشراف | ذات اولوية عالية | 19712700 | 985635 | 14998549 | 14998549 | 1010322156 | لا | 0 |  | جاري | تكلفة العمل المنجز | 88 | 90 | 2020-07-01 | 2022-06-21 | 2023-03-31 | 2023-03-31 |  |  |  |  | 49.5604 | 25.3897 | منتظم | No
2100108743 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 8200000 | 410000 | 8125714.85 | 0 | 1010225334 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2012-04-13 | 2013-12-13 | 2016-02-06 | 2016-02-06 | 2013-12-13 |  | اخرى |  | 42.5429 | 16.8808 | منجز | Yes
2100000770 | وزارة الدفاع / الإدارة الهندسية والاشغال بالخدمات الصحية | تشييد | ذات اولوية متوسطة | 42717292.21 | 2135864.6105 | 39609172.1 | 39609172.1 | 1010262187 | لا | 0 | 180909090297 | جاري | الكميات التي تم تركيبها | 86.4 | 100 | 2012-02-23 | 2014-01-30 | 2021-12-31 | 2021-12-31 |  |  | ضعف كفاءة المقاول الفنية |  | 36.6196 | 28.4123 | Failed | No
2100024150 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2351008 | 117550.4 | 0 | 0 | 5855014881 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 10 | 100 | 2016-03-13 | 2018-03-03 | 2023-02-11 | 2023-02-11 |  |  | ضعف كفاءة المقاول الفنية |  | 42.4987 | 18.2178 | مسحوب | No
2100035501 | أمانة / حفر الباطن | تشييد | ذات اولوية متوسطة | 17919550 | 895977.5 | 15885134.91 | 15885134.91 | 1011010795 | لا | 0 | 190409031178 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-11-05 | 2021-01-12 | 2022-12-30 | 2022-12-30 | 2021-01-12 |  | ضعف كفاءة المقاول الفنية |  | 45.9818 | 28.3644 | منجز | No
2100047611 | أمانة / حفر الباطن | تشييد | ذات اولوية متوسطة | 11683601.6 | 584180.08 | 10005671 | 10005671 | 1010008188 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-09-25 | 2021-09-22 | 2022-04-20 | 2022-04-20 | 2021-09-22 |  | ضعف كفاءة المقاول الفنية |  | 45.9973 | 28.3808 | منجز | No
2100055392 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 17754999.15 | 887749.9575 | 492344 | 492344 | 2051001976 | لا | 0 | 191001131489 | ايقاف جزئي | منهجية القيمة المكتسبة | 38.44 | 100 | 2019-11-25 | 2020-11-23 | 2023-11-06 | 2023-11-06 |  |  | عدم اكتمال أو ضعف أعمال التصميم والدراسات |  | 38.2527 | 23.9984 | Failed | No
2100074771 | المؤسسة العامة للحبوب | تشييد | ذات اولوية عالية | 3097500 | 154875 | 3097500 | 3097500 | 4030327596 | لا | 0 | 200201120872 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-12-03 | 2019-11-22 | 2019-11-22 | 2019-11-22 | 2019-11-22 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 41.7216 | 27.647 | منجز | No
2200228771 | وزارة المالية | تصميم وتشييد | ذات اولوية عالية | 6209316493 | 310465824.65 | 3931727084.1 | 3931727084.1 | 1010054406 | لا | 0 |  | جاري | تكلفة العمل المنجز | 73.83 | 75 | 2014-08-17 | 2015-05-17 | 2024-04-30 | 2024-04-30 |  |  |  |  | 39.7443 | 24.435 | منتظم | No
2200229375 | أمانة / جدة | تشييد | ذات اولوية عالية وعاجلة | 16884307 | 844215.35 | 2400896.46 | 1541610 | 4030151328 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 63 | 100 | 2021-08-01 | 2023-01-14 | 2023-01-14 | 2023-01-14 |  |  |  | تم إنذار المقاول كتابيا | 39.1925 | 21.4858 | Failed | No
2100073651 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 117405924 | 5870296.2 | 68630835 | 57796595 | 4700004138 | لا | 0 | 181209543120 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 99.99 | 100 | 2013-10-20 | 2015-10-20 | 2022-10-16 | 2022-10-16 | 2015-10-20 |  | أوامر تغيير |  | 38.3011 | 23.9647 | منجز | No
2300240085 | المؤسسة العامة لتحلية المياه المالحة | تشييد | ذات اولوية عالية | 747000000 | 37350000 | 50210305.62 | 50210305.62 | 7001555890 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 31.9 | 42.8 | 2022-04-10 | 2023-10-10 | 2023-10-10 | 2023-10-10 |  |  |  |  | 50.1971 | 26.2172 | متأخر | No
2300240096 | المؤسسة العامة لتحلية المياه المالحة | تشييد | ذات اولوية عالية | 1082132989 | 54106649.45 | 0 | 0 | 7018053871 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 15.2 | 15.8 | 2022-05-23 | 2024-02-21 | 2024-02-21 | 2024-02-21 |  |  |  |  | 49.5687 | 26.9598 | منتظم | No
2300240100 | المؤسسة العامة للري | تشييد | ذات اولوية متوسطة | 12615000 | 630750 | 0 | 0 | 2050003475 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 12 | 13 | 2022-11-01 | 2023-10-31 | 2023-12-31 | 2023-12-31 |  |  |  |  | 49.3653 | 21.9113 | منتظم | No
2300240111 | رئاسة أمن الدولة / المديرية العامة للمباحث | ترميم | ذات اولوية متوسطة | 372467.75 | 18623.3875 | 0 | 0 | 3550025468 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 20 | 100 | 2022-10-11 | 2022-11-24 | 2023-02-28 | 2023-02-28 |  |  |  |  | 46.6992 | 24.6718 | Failed | No
2300240122 | المؤسسة العامة لتحلية المياه المالحة | تشييد | ذات اولوية عالية | 1216198860 | 60809943 | 441514167.35 | 441514167.35 | 7001555890 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 56.9 | 42.1 | 2022-06-07 | 2024-06-06 | 2024-06-06 | 2024-06-06 |  |  |  |  | 39.8579 | 21.3891 | منتظم | No
2300240133 | المؤسسة العامة لتحلية المياه المالحة | تشييد | ذات اولوية عالية | 562386320 | 28119316 | 0 | 0 | 7006784990 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 23 | 31.2 | 2022-06-07 | 2024-06-06 | 2024-06-06 | 2024-06-06 |  |  |  |  | 39.8579 | 21.3891 | متأخر | No
2100103246 | وزارة المالية - الحرمين | إشراف | ذات اولوية عالية وعاجلة | 718491662 | 30000000 | 646017177 | 646017177 | 1010076578 | لا | 0 |  | جاري | مدفوعات ساعات العمل | 89 | 89 | 2012-12-15 | 2015-12-14 | 2024-03-31 | 2024-03-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.8216 | 21.4272 | خدمات عامة | No
2100084615 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 31459355 | 1572967.75 | 18246388 | 18246388 | 1010185409 | لا | 0 | 200209141391 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2009-06-21 | 2011-06-21 | 2021-09-30 | 2021-09-30 | 2011-06-21 |  | اخرى |  | 38.1922 | 23.9855 | منجز | No
2100079004 | وزارة المالية - الحرمين | تشييد | ذات اولوية عالية وعاجلة | 136696000000 | 21900000000 | 45458311327 | 43962598902 | 4030068284 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 85.87 | 86.27 | 2010-06-16 | 2012-06-15 | 2025-08-31 | 2025-08-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.8257 | 21.4229 | منتظم | No
2100036256 | أمانة / جدة | تشييد | ذات اولوية عالية | 44469856 | 2223492.8 | 42108367.38 | 41102894.57 | 4030151328 | لا | 0 | 190301051486 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 99 | 100 | 2019-09-06 | 2020-11-20 | 2021-07-26 | 2021-07-26 | 2020-11-20 |  | تأخرصرف المستحقات المالية |  | 39.2277 | 21.5435 | منجز | No
2100194283 | أمانة / جدة | دراسات هندسية | ذات اولوية متوسطة | 40506723 | 2025336.15 | 28486325.01 | 28486325.01 | 1010183478 | لا | 0 | 190801091077 | جاري | تكلفة العمل المنجز | 76 | 76 | 2020-09-13 | 2023-08-11 | 2023-08-11 | 2023-08-11 |  |  |  |  | 39.1677 | 21.5008 | خدمات عامة | No
2100040703 | وزارة الصحة / القريات | ترميم | ذات اولوية عالية وعاجلة | 33829743 | 1691487.15 | 21515891.09 | 21515891.09 | 1010220966 | لا | 0 | 180101000030 | جاري | الكميات التي تم تركيبها | 100 | 100 | 2018-08-08 | 2021-09-06 | 2022-10-18 | 2022-10-18 |  |  | التنسيق مع أصحاب المصلحه (خدمات |  | 37.3627 | 31.3279 | Failed | No
2100036945 | أمانة / الباحة | تشييد | ذات اولوية عالية | 5490224.63 | 274511.2315 | 5490224.63 | 5490224.63 | 5810001890 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-11-21 | 2020-12-19 | 2022-09-01 | 2022-09-01 | 2020-12-19 |  | ضعف كفاءة المقاول الفنية |  | 41.661 | 19.9966 | منجز | No
2100093413 | أمانة / جدة | إشراف | ذات اولوية عالية | 142433150 | 7121657.5 | 94192539 | 76864239 | 1010403954 | لا | 0 | 180401004299 | جاري | اخرى | 68 | 68 | 2018-09-09 | 2021-09-09 | 2024-04-15 | 2024-04-15 |  |  | اخرى |  | 39.1925 | 21.4858 | خدمات عامة | No
2100074104 | وزارة المالية - الحرمين | إشراف | ذات اولوية عالية وعاجلة | 6902241863 | 135000000 | 6087135058 | 6087135058 | 1010076578 | لا | 0 |  | جاري | مدفوعات ساعات العمل | 77 | 77 | 2010-06-16 | 2012-06-15 | 2026-08-31 | 2026-08-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.8257 | 21.4229 | خدمات عامة | No
2100095325 | الهيئة الملكية للجبيل وينبع / مدينة ينبع الصناعية | تشييد | ذات اولوية عالية وعاجلة | 212239158 | 10611957.9 | 182485938 | 176371216.05 | 4700004138 | لا | 0 | 181209476223 | جاري | منهجية القيمة المكتسبة | 92.55 | 99.75 | 2017-08-09 | 2019-08-09 | 2023-01-04 | 2023-01-04 |  |  | أوامر تغيير | تم تمديد الجدول الزمني | 38.4001 | 23.8863 | متأخر | No
2300240155 | المؤسسة العامة لتحلية المياه المالحة | تشييد | ذات اولوية عالية | 1237715662 | 61885783.1 | 603784318 | 492238999 | 1010004739 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 84.5 | 94.2 | 2020-12-31 | 2023-06-30 | 2023-06-30 | 2023-06-30 |  |  |  |  | 42.0287 | 17.7199 | متأخر | No
2100014350 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية عالية | 3385588.5 | 169279.425 | 1730271 | 1730271 | 4031071448 | لا | 0 | 200209133380 | جاري | تكلفة العمل المنجز | 51.11 | 51.11 | 2020-01-01 | 2021-12-09 | 2023-01-25 | 2023-01-25 |  |  |  | أخرى | 39.8855 | 21.347 | Failed | No
2100085234 | أمانة / العاصمة المقدسة | ادارة مشاريع | ذات اولوية متوسطة | 34010000 | 1700500 | 33461000 | 33461000 | 1010348048 | لا | 0 | 181009118739 | جاري الاستلام الإبتدائي | التكلفة المفوترة | 100 | 100 | 2012-02-27 | 2015-01-24 | 2015-06-03 | 2015-06-03 |  |  | اخرى |  | 39.8327 | 21.3869 | Failed | No
2200233612 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 17588639.25 | 879431.9625 | 15239840.22 | 15239840.22 | 1010063483 | لا | 0 |  | جاري | تكلفة العمل المنجز | 92.81 | 92.81 | 2019-04-15 | 2021-03-23 | 2021-08-15 | 2021-08-15 |  |  |  |  | 39.8579 | 21.3891 | Failed | No
2100014335 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية عالية | 5317750 | 265887.5 | 2823589.29 | 2823589.29 | 4030013052 | لا | 0 |  | جاري | تكلفة العمل المنجز | 60 | 60 | 2015-11-22 | 2018-05-22 | 2020-07-26 | 2020-07-26 |  |  |  | أخرى | 39.8879 | 21.3714 | Failed | No
2100101135 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 2895291 | 144764.55 | 2543525.09 | 2543525.09 | 4030044382 | لا | 0 | 200309112855 | جاري | التكلفة المفوترة | 89.44 | 89.44 | 2020-01-01 | 2022-03-09 | 2022-03-09 | 2022-03-09 |  |  |  |  | 39.8995 | 21.3738 | Failed | No
2100019180 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 1500000 | 75000 | 1271034.3 | 1271034.3 | 4030138666 | لا | 0 | 1046354 | جاري الاستلام الإبتدائي | التكلفة المفوترة | 99 | 99 | 2014-03-11 | 2016-10-12 | 2016-10-12 | 2016-10-12 |  |  | ضعف كفاءة المقاول الفنية |  | 40.0105 | 21.991 | Failed | No
2200236051 | أمانة / العاصمة المقدسة | الخدمات الاستشارية | ذات اولوية متوسطة | 7365600 | 368280 | 1400000 | 1400000 | 4031089686 | لا | 0 |  | جاري | تكلفة العمل المنجز | 19.01 | 19.01 | 2015-08-31 | 2017-09-29 | 2017-09-29 | 2017-09-29 |  |  |  |  | 39.8579 | 21.3891 | خدمات عامة | No
2100106831 | وزارة التعليم | تشييد | ذات اولوية عالية | 23214860.93 | 1160743.0465 | 16969561 | 14237284 | 4030140863 | لا | 0 | 190409005047 | جاري | التكلفة المفوترة | 85 | 100 | 2015-07-01 | 2017-09-18 | 2022-05-11 | 2022-05-11 |  |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | Failed | No
2200236106 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 3950081 | 197504.05 | 2808161 | 2808161 | 4031027455 | لا | 0 |  | جاري | تكلفة العمل المنجز | 71.09 | 71.09 | 2020-03-11 | 2022-03-11 | 2024-12-03 | 2024-12-03 |  |  |  | أخرى | 39.8579 | 21.3891 | Failed | No
2100094846 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية عالية | 426719840.3 | 21335992.015 | 225400944 | 225400944 | 1116000094 | لا | 0 |  | جاري | التكلفة المفوترة | 50.13 | 50.13 | 2012-06-30 | 2014-12-29 | 2024-04-09 | 2024-04-09 |  |  | ضعف كفاءة المقاول الفنية | أخرى | 39.8579 | 21.3544 | Failed | No
2100077744 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 683128815.35 | 34156440.7675 | 540292657.89 | 540292657.89 | 1010090968 | لا | 0 |  | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2012-06-30 | 2014-11-23 | 2020-11-16 | 2020-11-16 |  |  |  |  | 39.8586 | 21.3766 | Failed | No
2100110224 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 2315246.44 | 115762.322 | 1721827 | 1721827 | 4030140863 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2014-12-27 | 2015-12-19 | 2019-09-09 | 2019-09-09 | 2015-12-19 |  | اخرى |  | 39.1677 | 21.5008 | منجز | No
2100005073 | وزارة التعليم | تشييد | ذات اولوية عالية | 8938172.36 | 446908.618 | 4501187.14 | 4501187.14 | 1010187466 | لا | 0 | 190209015510 | مسحوب | التكلفة المفوترة | 62 | 100 | 2014-01-08 | 2015-12-29 | 2023-08-23 | 2023-08-23 |  |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | مسحوب | No
2100008072 | وزارة التعليم | تشييد | ذات اولوية عالية | 2434397.98 | 121719.899 | 931419 | 931419 | 4030140863 | لا | 0 | 190409042140 | منجز – استلام ابتدائي | التكلفة المفوترة | 75 | 100 | 2015-07-29 | 2016-07-23 | 2021-12-31 | 2021-12-31 | 2016-07-23 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.1677 | 21.5008 | منجز | No
2100000151 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 12486011.35 | 624300.5675 | 8972525.21 | 8972525.21 | 5950000316 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-11-29 | 2017-11-18 | 2020-03-03 | 2020-03-03 | 2017-11-18 |  | ضعف كفاءة المقاول الفنية |  | 42.4987 | 18.2178 | منجز | No
2100037026 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 1071105.74 | 53555.287 | 583367.65 | 0 | 3350018913 | لا | 0 | 190401024379 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 99 | 100 | 2018-12-31 | 2019-12-26 | 2020-08-11 | 2020-08-11 | 2019-12-26 |  | تأخرصرف المستحقات المالية |  | 42.4141 | 27.8867 | منجز | Yes
2300240181 | رئاسة أمن الدولة / المديرية العامة للمباحث | ترميم | ذات اولوية متوسطة | 526157.08 | 26307.854 | 0 | 0 | 1010238249 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 95 | 100 | 2022-06-04 | 2022-09-19 | 2023-02-24 | 2023-02-24 |  |  |  |  | 46.6992 | 24.6719 | منتظم | No
2300239761 | رئاسة أمن الدولة / المديرية العامة للمباحث | ترميم | ذات اولوية متوسطة | 169855 | 8492.75 | 0 | 0 | 5950028000 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 10 | 50 | 2022-12-25 | 2023-02-22 | 2023-02-22 | 2023-02-22 |  |  |  |  | 46.6992 | 24.6718 | Failed | No
2200210840 | المؤسسة العامة للحبوب | تصميم وتشييد | ذات اولوية عالية | 2413765 | 120688.25 | 154246.95 | 154246.95 | 1010211349 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 60 | 60 | 2022-10-04 | 2023-09-23 | 2023-09-23 | 2023-09-23 |  |  |  |  | 41.7339 | 27.496 | منتظم | No
2100029864 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 18155345.89 | 907767.2945 | 16173875.26 | 15233813.67 | 5810001890 | لا | 0 |  | جاري | تكلفة العمل المنجز | 90 | 98.12 | 2019-05-15 | 2021-04-22 | 2023-02-04 | 2023-02-04 |  |  | ضعف كفاءة المقاول الفنية |  | 41.5812 | 19.8649 | متأخر | No
2100192216 | وزارة الصحة / القنفذة | ترميم | ذات اولوية عالية وعاجلة | 2282800 | 114140 | 0.01 | 0.01 | 4603004089 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 12 | 100 | 2020-11-09 | 2021-04-08 | 2021-04-08 | 2021-04-08 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.3278 | 18.8706 | مسحوب | No
2300240214 | وزارة البيئة والمياة والزراعة | ترميم | ذات اولوية متوسطة | 875035 | 43751.75 | 0 | 0 | 0 | لا | 0 |  | جاري | تكلفة العمل المنجز | 97 | 100 | 2022-07-25 | 2022-11-24 | 2023-01-20 | 2023-01-20 |  |  |  |  | 42.5706 | 16.8894 | Failed | No
2200226144 | المؤسسة العامة للحبوب | تصميم وتشييد | ذات اولوية عالية وعاجلة | 21407250 | 1070362.5 | 0 | 0 | 4601000417 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 5 | 5 | 2022-11-29 | 2023-11-18 | 2023-11-18 | 2023-11-18 |  |  |  |  | 42.5675 | 16.8887 | منتظم | No
2300240225 | وزارة التعليم | ترميم | ذات اولوية متوسطة | 469085 | 23454.25 | 0 | 0 | 0 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 1 | 100 | 2022-07-26 | 2023-01-24 | 2023-01-24 | 2023-01-24 |  |  |  |  | 42.1573 | 18.1522 | Failed | No
2300240402 | أمانة / الباحة | تشييد | ذات اولوية عالية | 892732.35 | 44636.6175 | 892732.35 | 714083.88 | 7002908940 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2022-04-03 | 2022-07-02 | 2022-07-02 | 2022-07-02 | 2022-07-02 |  |  |  | 41.5302 | 19.598 | منجز | No
2300240391 | أمانة / الباحة | توريد | ذات اولوية متوسطة | 2357385 | 117869.25 | 2357385 | 2357385 | 4030005320 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2021-10-20 | 2021-12-04 | 2022-12-15 | 2022-12-15 | 2021-12-04 |  |  |  | 41.5286 | 19.5988 | منجز | No
2300240203 | أمانة / الباحة | تصميم وتشييد | ذات اولوية عالية | 5183133.01 | 259156.6505 | 4108246.64 | 2678564.4 | 5800004732 | لا | 0 | 210601190317 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2020-05-31 | 2021-05-20 | 2022-10-06 | 2022-10-06 | 2021-05-20 |  |  |  | 41.5692 | 19.8805 | منجز | No
2300240251 | وزارة التعليم | ترميم | ذات اولوية متوسطة | 513015 | 25650.75 | 0 | 0 | 0 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 100 | 100 | 2022-07-25 | 2023-01-23 | 2023-01-23 | 2023-01-23 |  |  |  |  | 42.251 | 18.265 | منتظم | No
2100084416 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 449257288.25 | 22462864.4125 | 449083043.84 | 405477140.62 | 1010043654 | لا | 0 | 180909110215 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 99.82 | 100 | 2013-07-31 | 2016-07-30 | 2023-02-28 | 2023-02-28 |  |  |  |  | 46.6727 | 24.7082 | Failed | No
2300240284 | الجمارك السعودية | تشييد | ذات اولوية عالية | 16217391.3 | 810869.565 | 0 | 0 | 1010149050 | لا | 0 |  | جاري | تكلفة العمل المنجز | 82 | 100 | 2022-08-25 | 2022-11-10 | 2023-01-10 | 2023-01-10 |  |  |  |  | 51.5731 | 24.1283 | Failed | No
2100101253 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 71102347.12 | 3555117.356 | 62066356.05 | 47752848.83 | 2050022550 | نعم | 4775284883 |  | مسحوب | الكميات التي تم تركيبها | 90.4 | 100 | 2013-02-01 | 2015-01-10 | 2016-04-20 | 2016-04-20 |  |  | ضعف كفاءة المقاول الفنية |  | 46.6814 | 24.7044 | مسحوب | No
2100017614 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2440826.62 | 122041.331 | 0 | 0 | 4030140863 | لا | 0 |  | ايقاف كلي | التكلفة المفوترة | 0 | 100 | 2015-07-28 | 2016-07-22 | 2023-01-01 | 2023-01-01 |  |  | ضعف كفاءة المقاول الفنية |  | 39.1677 | 21.5008 | Failed | No
2100003102 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 4865586.52 | 243279.326 | 445921.11 | 445921.11 | 1010045486 | لا | 0 |  | جاري | التكلفة المفوترة | 14 | 100 | 2015-07-29 | 2017-04-19 | 2023-05-10 | 2023-05-10 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.1677 | 21.5008 | Failed | No
2300240413 | أمانة / الباحة | تشييد | ذات اولوية عالية | 97307.25 | 4865.3625 | 97307.25 | 97307.25 | 7002908940 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2022-06-29 | 2022-08-27 | 2022-08-27 | 2022-08-27 | 2022-08-27 |  |  |  | 41.5253 | 19.596 | منجز | No
2300240240 | الجمارك السعودية | تشييد | ذات اولوية عالية | 9914131.5 | 495706.575 | 0 | 0 | 1010344765 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 94 | 100 | 2022-05-22 | 2022-10-15 | 2022-10-15 | 2022-10-15 | 2022-10-15 |  |  |  | 48.412 | 28.52 | منجز | No
2200223683 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 55836512.61 | 2791825.6305 | 49209477 | 44113588.962 | 1010082898 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 87.5 | 100 | 2012-03-13 | 2014-03-13 | 2023-03-31 | 2023-03-31 |  |  |  | تم إنذار المقاول كتابيا | 44.19 | 25.8588 | متأخر | No
2100070022 | وزارة الصحة / مستشفى الملك خالد للعيون | تشييد | ذات اولوية عالية وعاجلة | 2665950 | 133297.5 | 2159419 | 2151765 | 1010109325 | لا | 0 | 190809094244 | جاري | الكميات التي تم تركيبها | 90 | 100 | 2019-01-07 | 2020-02-23 | 2021-12-31 | 2021-12-31 |  |  | موافقات | أخرى | 46.636 | 24.6945 | Failed | No
2300240306 | أمانة / الباحة | تشييد | ذات اولوية عالية | 5317733.23 | 265886.6615 | 3076424.4 | 677687 | 5800004732 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 58.36 | 100 | 2020-05-31 | 2021-05-20 | 2021-08-17 | 2021-08-17 |  |  |  | أخرى | 41.5684 | 19.8803 | Failed | No
2100102476 | أمانة / جدة | ترميم | ذات اولوية متوسطة | 4339200 | 216960 | 4555623 | 4555623 | 4030282813 | لا | 0 | 190509009590 | منجز – استلام نهائي | مدفوعات ساعات العمل | 100 | 100 | 2019-02-17 | 2021-02-16 | 2021-02-16 | 2021-02-16 | 2021-02-16 | 2021-02-17 | اخرى |  | 39.2128 | 21.4663 | منجز | No
2300240310 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 1397121.5 | 69856.075 | 1397121.5 | 1226847 | 5800009796 | نعم | 553194.5 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2020-05-31 | 2021-05-20 | 2023-03-30 | 2023-03-30 | 2021-05-20 |  |  | تم إعادة ترسيته | 41.5693 | 19.8808 | منجز | No
2300240321 | أمانة / الباحة | تشييد | ذات اولوية عالية | 3666749.5 | 183337.475 | 2779571.42 | 0 | 5800004732 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 76.44 | 100 | 2020-05-31 | 2021-05-20 | 2021-08-17 | 2021-08-17 |  |  |  | أخرى | 41.5688 | 19.8803 | Failed | Yes
2100073570 | أمانة / جدة | تشييد | ذات اولوية عالية | 92767500 | 4638375 | 92493990.43 | 92493990.43 | 4030140655 | لا | 0 | 181101249937 | منجز – استلام نهائي | الكميات التي تم تركيبها | 99 | 100 | 2019-01-09 | 2020-06-23 | 2022-07-02 | 2022-07-02 | 2020-06-23 | 2021-03-29 | اخرى |  | 39.1653 | 21.581 | منجز | No
2200229541 | أمانة / جدة | دراسات هندسية | ذات اولوية عالية | 1470000 | 73500 | 1556792 | 1556792 | 1010461905 | لا | 0 |  | منجز – استلام نهائي | اخرى | 100 | 100 | 2020-11-22 | 2021-11-11 | 2021-11-11 | 2021-11-11 | 2021-11-11 | 2021-11-12 |  |  | 39.1677 | 21.5007 | منجز | No
2300240295 | الجمارك السعودية | تشييد | ذات اولوية عالية | 1030390 | 51519.5 | 0 | 0 | 1010155869 | نعم | 2762270.5 | 180901097732 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 97 | 100 | 2022-06-01 | 2022-07-16 | 2023-01-03 | 2023-01-03 |  |  |  |  | 51.5654 | 24.1378 | Failed | No
2300240343 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 4631741.46 | 231587.073 | 2238556.96 | 1400346.97 | 0 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 70 | 100 | 2020-05-31 | 2021-05-20 | 2021-08-17 | 2021-08-17 |  |  |  |  | 41.5812 | 19.8649 | مسحوب | No
2100101006 | مدينة الملك عبدالعزيز للعلوم والتقنية | تشييد | ذات اولوية عالية | 7885465 | 394273.25 | 7718354 | 7718354 | 1010026854 | لا | 0 | 190801118415 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2014-03-02 | 2014-06-14 | 2015-12-09 | 2015-12-09 | 2014-06-14 |  |  |  | 46.6433 | 24.717 | منجز | No
2300240365 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 2416794.5 | 120839.725 | 2416794.5 | 2416794.5 | 5805014373 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 93.779 | 93.779 | 2020-06-03 | 2021-05-23 | 2022-06-30 | 2022-06-30 | 2021-05-23 |  |  |  | 41.7692 | 19.7806 | منجز | No
2100201880 | وزارة الصحة / عسير | ترميم | لم تعد تحتاجها الجهة | 2153046.5 | 107652.325 | 2113069.9 | 1980247.5 | 5860019265 | لا | 0 | 200201045660 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-12-04 | 2022-04-01 | 2022-04-01 | 2022-04-01 |  |  |  |  | 42.8638 | 19.0969 | Failed | No
2300240380 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 3878439.66 | 193921.983 | 1997595.57 | 0 | 0 | لا | 0 |  | ايقاف جزئي | تكلفة العمل المنجز | 70 | 100 | 2020-05-31 | 2021-05-20 | 2021-08-17 | 2021-08-17 |  |  |  |  | 41.5812 | 19.8649 | Failed | Yes
2200223650 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 86057406.64 | 4302870.332 | 1708309.64 | 634682.47 | 1010082898 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 31 | 100 | 2020-12-23 | 2021-12-03 | 2022-12-31 | 2022-12-31 |  |  |  | أخرى | 45.401 | 25.9265 | Failed | No
2200223753 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 25382951.28 | 1269147.564 | 24441000.92 | 24441000.92 | 1010154193 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2017-08-09 | 2018-06-05 | 2019-08-26 | 2019-08-26 | 2018-06-05 |  |  |  | 46.7188 | 22.2899 | منجز | No
2100071315 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 3187100 | 159355 | 2537740 | 2537740 | 4035000994 | لا | 0 | 200209133463 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-09-11 | 2020-09-05 | 2022-01-01 | 2022-01-01 | 2020-09-05 |  | ضعف كفاءة المقاول الفنية |  | 42.8401 | 21.2499 | منجز | No
2100050411 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 382650 | 19132.5 | 314582.5 | 314582.5 | 4034000979 | لا | 0 | 180709015817 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2017-11-28 | 2018-11-23 | 2018-11-23 | 2018-11-23 | 2018-11-23 |  | اخرى |  | 41.6266 | 21.2081 | منجز | No
2300240446 | أمانة / الباحة | تشييد | ذات اولوية عالية | 1387401 | 69370.05 | 1374566.55 | 0 | 5806008614 | لا | 0 | 210209141832 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2021-01-17 | 2022-01-17 | 2022-01-17 | 2022-01-17 | 2022-01-17 |  |  |  | 41.4362 | 19.756 | منجز | Yes
2300237683 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 1950990 | 97549.5 | 1755891 | 0 | 5806008614 | لا | 0 | 210209141918 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2021-01-26 | 2022-01-16 | 2022-01-16 | 2022-01-16 | 2022-01-16 |  |  |  | 41.4362 | 19.756 | منجز | Yes
2100047250 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 5997320 | 299866 | 5322797.66 | 5322797.66 | 1118001565 | لا | 0 | 190909008794 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-06-19 | 2021-06-08 | 2022-06-30 | 2022-06-30 | 2021-06-08 |  |  |  | 40.4165 | 21.2594 | منجز | No
2100016586 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 10045600 | 502280 | 4018225.5 | 3116993.656 | 3350000614 | نعم | 6227279 | 181101263148 | جاري | الكميات التي تم تركيبها | 67 | 100 | 2019-01-02 | 2021-10-16 | 2023-10-23 | 2023-10-23 |  |  |  | تم إنذار المقاول كتابيا | 41.7207 | 27.5467 | Failed | No
2100077066 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1296277.5 | 64813.875 | 1296277.5 | 1296277.5 | 1118100724 | لا | 0 | 191001276365 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-09-15 | 2021-03-08 | 2021-06-06 | 2021-06-06 | 2021-03-08 |  |  |  | 41.7527 | 22.427 | منجز | No
2100091350 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1487500 | 74375 | 1275124.27 | 1275124.27 | 4035000994 | لا | 0 | 200401107281 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 98 | 100 | 2020-04-01 | 2021-03-27 | 2022-06-30 | 2022-06-30 | 2021-03-27 |  | تأخرصرف المستحقات المالية |  | 40.8314 | 20.7294 | منجز | No
2100014814 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 6498611.11 | 324930.5555 | 6407946.73 | 6407946.73 | 4032027295 | لا | 0 | 181001201433 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-03-24 | 2020-03-23 | 2020-03-23 | 2020-03-23 | 2020-03-23 |  |  |  | 40.4135 | 21.2664 | منجز | No
2100031710 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 983835 | 49191.75 | 0.01 | 0.01 | 1017001023 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 1 | 100 | 2013-02-18 | 2014-02-13 | 2022-01-01 | 2022-01-01 |  |  | ضعف كفاءة المقاول الفنية |  | 42.8421 | 21.257 | مسحوب | No
2100043831 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 6600000 | 330000 | 0 | 0 | 2050001536 | لا | 0 | 191101329201 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-09-18 | 2020-03-16 | 2021-10-31 | 2021-10-31 | 2020-03-16 |  | اخرى |  | 40.4215 | 21.2734 | منجز | No
2100060185 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 2996642 | 149832.1 | 2996642 | 2996642 | 4030006066 | لا | 0 | 191101208129 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-07-23 | 2020-07-17 | 2020-07-17 | 2020-07-17 | 2020-07-17 |  |  |  | 41.6255 | 21.2052 | منجز | No
2300240450 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 2094150 | 104707.5 | 1032626 | 1032626 | 4046001026 | لا | 0 |  | جاري | تكلفة العمل المنجز | 55 | 100 | 2022-08-02 | 2023-08-03 | 2023-08-03 | 2023-08-03 |  |  |  |  | 42.1721 | 22.7241 | Failed | No
2300240461 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 2094150 | 104707.5 | 1032626 | 1032626 | 4046001026 | لا | 0 |  | جاري | تكلفة العمل المنجز | 55 | 100 | 2022-08-02 | 2023-08-03 | 2023-08-03 | 2023-08-03 |  |  |  |  | 42.1721 | 22.7241 | Failed | No
2300240472 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1028424.07 | 51421.2035 | 0 | 0 | 4031046917 | لا | 0 |  | جاري | تكلفة العمل المنجز | 10 | 100 | 2023-09-27 | 2024-03-27 | 2024-03-27 | 2024-03-27 |  |  |  |  | 40.4212 | 21.2732 | Failed | No
2300240483 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 2412918.5 | 120645.925 | 1520138 | 0 | 4031045075 | لا | 0 |  | جاري | تكلفة العمل المنجز | 63 | 100 | 2023-09-27 | 2024-09-26 | 2024-09-26 | 2024-09-26 |  |  |  |  | 40.4023 | 21.6458 | Failed | Yes
2100004082 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 11426693 | 571334.65 | 0 | 0 | 1010051817 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0 | 100 | 2015-02-15 | 2019-02-04 | 2023-02-01 | 2023-02-01 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.5429 | 16.8808 | مسحوب | No
2100108496 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 14145592.31 | 707279.6155 | 7435752.11 | 7196298.32 | 7001681225 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 55 | 100 | 2012-03-21 | 2014-03-11 | 2023-03-31 | 2023-03-31 |  |  | ضعف كفاءة المقاول الفنية |  | 42.4987 | 18.2178 | مسحوب | No
2100057945 | وزارة التعليم | تشييد | ذات اولوية عالية | 9690513.95 | 484525.6975 | 1099979.64 | 0 | 5950007285 | لا | 0 | 190309000831 | مسحوب | التكلفة المفوترة | 20 | 100 | 2014-09-03 | 2016-05-26 | 2022-11-26 | 2022-11-26 |  |  | ضعف كفاءة المقاول الفنية |  | 42.6509 | 17.1567 | مسحوب | Yes
2100079284 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 13190604.48 | 659530.224 | 3306098.79 | 3306098.79 | 1010223860 | لا | 0 | 190209018363 | مسحوب | التكلفة المفوترة | 48 | 100 | 2012-09-29 | 2014-10-19 | 2022-08-17 | 2022-08-17 |  |  | ضعف كفاءة المقاول الفنية |  | 42.4987 | 18.2178 | مسحوب | No
2300240645 | أمانة / الطائف | تشييد | ذات اولوية عالية | 1982255 | 99112.75 | 0 | 0 | 0 | لا | 0 |  | جاري | تكلفة العمل المنجز | 10 | 100 | 2022-10-13 | 2023-10-23 | 2023-10-25 | 2023-10-25 |  |  |  |  | 41.0457 | 20.5988 | منتظم | No
2300240494 | جامعة القصيم | توريد وتركيب | ذات اولوية عالية وعاجلة | 2499999 | 124999.95 | 2010098.8 | 0 | 1010274108 | لا | 0 |  | جاري | تكلفة العمل المنجز | 60 | 60 | 2022-09-05 | 2025-08-20 | 2025-08-20 | 2025-08-20 |  |  |  |  | 43.7737 | 26.3511 | منتظم | Yes
2300240505 | جامعة القصيم | تشييد | ذات اولوية عالية وعاجلة | 695738.5 | 34786.925 | 0 | 0 | 1128001366 | لا | 0 |  | جاري | تكلفة العمل المنجز | 35 | 35 | 2022-11-07 | 2023-02-05 | 2023-02-05 | 2023-02-05 |  |  |  |  | 44.0727 | 26.1127 | منتظم | No
2100019132 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2213456 | 110672.8 | 1727618 | 1727618 | 5857031865 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2017-01-28 | 2019-01-18 | 2019-11-14 | 2019-11-14 | 2019-01-18 |  | ضعف كفاءة المقاول الفنية |  | 42.4987 | 18.2178 | منجز | No
2100009181 | وزارة الشـؤون الاسلامية والدعوة والارشاد | تشييد | ذات اولوية عالية | 1153110 | 57655.5 | 1131272.16 | 154717.5 | 5950008566 | لا | 0 | 180909070275 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-03-25 | 2019-09-25 | 2020-04-25 | 2020-04-25 | 2019-09-25 |  | تأخرصرف المستحقات المالية |  | 44.266 | 17.5673 | منجز | No
2300240516 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية عالية | 6989648.25 | 349482.4125 | 0 | 0 | 0 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 2 | 100 | 2022-10-16 | 2024-04-15 | 2024-04-15 | 2024-04-15 |  |  |  |  | 39.3206 | 29.8874 | Failed | No
2300240520 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية عالية | 36800000 | 1840000 | 0 | 0 | 0 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 7 | 12 | 2022-09-26 | 2024-09-24 | 2024-09-25 | 2024-09-25 |  |  |  |  | 43.4837 | 26.2078 | منتظم | No
2300240531 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية عالية | 28028064.5 | 1401403.225 | 0 | 0 | 0 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 3 | 12 | 2022-09-22 | 2024-09-26 | 2024-09-26 | 2024-09-26 |  |  |  |  | 39.8579 | 21.3891 | متأخر | No
2100066404 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 88112000 | 4405600 | 88061232.82 | 88061232.82 | 1010061463 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-04-22 | 2015-10-05 | 2017-06-10 | 2017-06-10 | 2015-10-05 |  |  |  | 46.6814 | 24.7044 | منجز | No
2100087566 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية عالية | 12057750 | 602887.5 | 10207552.6 | 10207552.6 | 1132002308 | لا | 0 | 180709025931 | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 89 | 100 | 2015-02-15 | 2018-01-13 | 2018-06-11 | 2018-06-11 |  |  | ضعف كفاءة المقاول الفنية |  | 44.8906 | 26.2514 | Failed | No
2100079343 | وزارة التعليم | تشييد | ذات اولوية عالية | 2396774 | 119838.7 | 0 | 0 | 5859000660 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 45 | 100 | 2014-04-15 | 2015-07-09 | 2025-08-20 | 2025-08-20 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 42.1351 | 19.1255 | مسحوب | No
2100032292 | وزارة التعليم | تشييد | ذات اولوية منخفضة | 2452474 | 122623.7 | 1402776 | 724351 | 4030140863 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2016-05-08 | 2017-05-03 | 2021-11-25 | 2021-11-25 | 2017-05-03 |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 39.1677 | 21.5008 | منجز | No
2300240542 | جامعة القصيم | تشييد | ذات اولوية عالية وعاجلة | 281493.55 | 14074.6775 | 0 | 0 | 1010278646 | لا | 0 |  | جاري | تكلفة العمل المنجز | 20 | 20 | 2022-10-03 | 2023-09-28 | 2023-09-23 | 2023-09-23 |  |  |  |  | 43.5394 | 25.8869 | منتظم | No
2100077862 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 117639071.34 | 5881953.567 | 106308346.94 | 82597365.24 | 1116000094 | نعم | 82597365 |  | مسحوب | الكميات التي تم تركيبها | 94.11 | 100 | 2012-04-03 | 2014-04-03 | 2021-06-21 | 2021-06-21 |  |  | ضعف كفاءة المقاول الفنية |  | 46.8343 | 24.6728 | مسحوب | No
2300240553 | أمانة / الرياض | تشييد | ذات اولوية عالية | 53961338.3 | 2698066.915 | 22649994.38 | 22649994.38 | 0 | لا | 0 |  | جاري | التكلفة المفوترة | 53.9 | 100 | 2019-08-19 | 2023-02-19 | 2023-08-19 | 2023-08-19 |  |  |  |  | 46.7378 | 24.6728 | Failed | No
2300240730 | الجمارك السعودية | تشييد | ذات اولوية عالية | 17146820.75 | 857341.0375 | 8624094.3 | 0 | 1010790557 | لا | 0 |  | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 95 | 100 | 2022-09-12 | 2022-10-27 | 2022-11-20 | 2022-11-20 |  |  |  |  | 50.7572 | 24.7209 | Failed | Yes
2100190293 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية عالية وعاجلة | 1322433 | 66121.65 | 228699.45 | 228699.45 | 4650028053 | لا | 0 | 200601109017 | مسحوب | الكميات التي تم تركيبها | 60 | 100 | 2020-11-02 | 2021-07-25 | 2021-07-26 | 2021-07-26 |  |  | ضعف كفاءة المقاول الفنية |  | 42.5895 | 16.8785 | مسحوب | No
2100190411 | وزارة البيئة والمياة والزراعة | تشييد | ذات اولوية عالية وعاجلة | 56432994.51 | 2821649.7255 | 0 | 0 | 4030140655 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 2 | 69 | 2020-01-12 | 2022-06-15 | 2022-06-15 | 2022-06-15 |  |  | موافقات |  | 36.6048 | 28.4238 | Failed | No
2100106945 | وزارة التعليم | تشييد | ذات اولوية عالية | 11372396.92 | 568619.846 | 10230729.16 | 0 | 1010060469 | لا | 0 |  | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2015-03-07 | 2016-11-26 | 2020-03-03 | 2020-03-03 | 2016-11-26 |  | ضعف كفاءة المقاول الفنية |  | 42.6509 | 17.1567 | منجز | Yes
2100040666 | وزارة الصحة / ديوان الوزارة | تشييد | لم تعد تحتاجها الجهة | 115375913 | 5768795.65 | 58286050 | 40578452 | 1010151889 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 68 | 23.55 | 2014-06-14 | 2023-01-30 | 2023-01-16 | 2023-01-16 |  |  | ضعف كفاءة المقاول الفنية |  | 39.2115 | 21.3364 | Failed | No
2300240693 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1910756.55 | 95537.8275 | 1910756.55 | 1910756.55 | 0 | لا | 0 |  | جاري | تكلفة العمل المنجز | 50 | 100 | 2022-12-19 | 2023-07-28 | 2023-07-28 | 2023-07-28 |  |  |  |  | 40.8298 | 20.727 | منتظم | No
2100016494 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 7862293.98 | 393114.699 | 4737636.25 | 3254326.45 | 5855020529 | لا | 0 | 190509122749 | منجز – استلام ابتدائي | التكلفة المفوترة | 100 | 100 | 2018-09-16 | 2020-01-04 | 2021-06-16 | 2021-06-16 | 2020-01-04 |  | ضعف كفاءة المقاول الفنية |  | 41.4779 | 20.0185 | منجز | No
2300238033 | أمانة / المنطقة الشرقية | تشييد | ذات اولوية متوسطة | 2346000 | 117300 | 0 | 0 | 2050050111 | لا | 0 |  | جاري | التكلفة المفوترة | 0 | 25 | 2022-10-11 | 2023-10-11 | 2023-10-11 | 2023-10-11 |  |  |  |  | 50.0888 | 26.4207 | Failed | No
2100099422 | وزارة الحرس الوطني / الشؤون الصحية | توريد وتركيب | ذات اولوية عالية | 25784567.61 | 1289228.3805 | 22991511.16 | 21101506.37 | 1010090071 | لا | 0 |  | مسحوب | الكميات التي تم تركيبها | 90 | 100 | 2015-12-31 | 2016-09-26 | 2022-06-30 | 2022-06-30 |  |  | ضعف كفاءة المقاول الفنية |  | 39.3625 | 21.4223 | مسحوب | No
2100012353 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 6999000 | 349950 | 2712000 | 2712000 | 4653000202 | لا | 0 |  | مسحوب | تكلفة العمل المنجز | 51 | 100 | 2015-09-02 | 2017-09-11 | 2017-09-11 | 2017-09-11 |  |  | ضعف كفاءة المقاول الفنية |  | 39.5624 | 24.5515 | مسحوب | No
2300240273 | الجمارك السعودية | تشييد | ذات اولوية عالية | 18260869.565 | 913043.4783 | 6873174 | 6873174 | 1010433444 | لا | 0 |  | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 95 | 100 | 2022-06-30 | 2022-10-14 | 2023-02-15 | 2023-02-15 |  |  |  |  | 50.7572 | 24.7208 | Failed | No
2300240564 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 2094150 | 104707.5 | 1032626 | 1032626 | 0 | لا | 0 |  | جاري | تكلفة العمل المنجز | 55 | 100 | 2022-08-02 | 2023-08-02 | 2023-08-02 | 2023-08-02 |  |  |  |  | 42.1721 | 22.7241 | منتظم | No
2300240575 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 2094150 | 104707.5 | 1032626 | 1032626 | 0 | لا | 0 |  | جاري | تكلفة العمل المنجز | 55 | 100 | 2022-08-02 | 2023-08-02 | 2023-08-02 | 2023-08-02 |  |  |  |  | 42.1721 | 22.7241 | منتظم | No
2300240586 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 2495988.75 | 124799.4375 | 631519.05 | 631519.05 | 0 | لا | 0 |  | جاري | تكلفة العمل المنجز | 18 | 35 | 2022-08-14 | 2023-08-14 | 2023-08-14 | 2023-08-14 |  |  |  |  | 41.7457 | 22.4343 | منتظم | No
2300240590 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 2495988.75 | 124799.4375 | 0 | 0 | 0 | لا | 0 |  | جاري | تكلفة العمل المنجز | 18 | 35 | 2022-08-14 | 2023-08-14 | 2023-08-14 | 2023-08-14 |  |  |  |  | 41.7457 | 22.4343 | منتظم | No
2300240601 | أمانة / الطائف | تشييد | ذات اولوية عالية | 2200525 | 110026.25 | 0 | 0 | 0 | لا | 0 |  | جاري | تكلفة العمل المنجز | 0 | 0 | 2023-01-29 | 2024-01-29 | 2024-01-29 | 2024-01-29 |  |  |  |  | 41.3511 | 22.6212 | منتظم | No
2300240612 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 3000000 | 150000 | 1154279.15 | 178167 | 0 | لا | 0 |  | جاري | تكلفة العمل المنجز | 42 | 46 | 2022-08-10 | 2023-08-04 | 2023-08-04 | 2023-08-04 |  |  |  |  | 40.989 | 21.0542 | منتظم | No
2200236412 | أمانة / العاصمة المقدسة | توريد وتركيب | ذات اولوية متوسطة | 2299700 | 114985 | 1855110.04 | 1855110.04 | 4031040424 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 80.67 | 80.67 | 2015-10-14 | 2016-10-13 | 2016-10-13 | 2016-10-13 | 2016-10-13 |  |  |  | 39.8579 | 21.3891 | منجز | No
2300240623 | أمانة / الطائف | تشييد | ذات اولوية عالية | 2943685 | 147184.25 | 1144353.5 | 396152 | 0 | لا | 0 |  | جاري | تكلفة العمل المنجز | 44 | 46 | 2022-08-10 | 2023-08-04 | 2023-08-04 | 2023-08-04 |  |  |  |  | 40.989 | 21.0542 | منتظم | No
2300240634 | أمانة / الطائف | تشييد | ذات اولوية عالية | 1805845 | 90292.25 | 0 | 0 | 0 | لا | 0 |  | جاري | تكلفة العمل المنجز | 0 | 30 | 2022-10-09 | 2023-10-03 | 2023-10-03 | 2023-10-03 |  |  |  | أخرى | 40.989 | 21.0542 | منتظم | No
2100099956 | أمانة / العاصمة المقدسة | دراسة الجدوى | ذات اولوية متوسطة | 9717870.55 | 485893.5275 | 8603511 | 8603511 | 2050100852 | لا | 0 | 200209133231 | منجز – استلام نهائي | مدفوعات ساعات العمل | 88.53 | 88.53 | 2019-10-01 | 2021-09-30 | 2021-12-31 | 2021-12-31 | 2021-09-30 | 2022-02-15 | اخرى |  | 39.8663 | 21.3785 | منجز | No
2100042744 | جامعة الحدود الشمالية | تشييد | ذات اولوية متوسطة | 129083790.48 | 6454189.524 | 42955602.4 | 39448700.6 | 1010069654 | لا | 0 |  | جاري | تكلفة العمل المنجز | 33 | 52 | 2015-08-02 | 2018-07-16 | 2025-01-12 | 2025-01-12 |  |  | تأخرصرف المستحقات المالية |  | 41.0346 | 30.951 | متأخر | No
2300240656 | أمانة / الطائف | تشييد | ذات اولوية عالية | 1145112.5 | 57255.625 | 443325 | 443325 | 0 | لا | 0 |  | جاري | تكلفة العمل المنجز | 70 | 100 | 2022-07-27 | 2022-07-28 | 2023-07-28 | 2023-07-28 |  |  |  |  | 41.0722 | 20.4628 | منتظم | No
2100088270 | جامعة الحدود الشمالية | تشييد | ذات اولوية عالية | 233616845.88 | 11680842.294 | 108192021.92 | 108192021.92 | 1010034600 | لا | 0 | 211009189955 | ايقاف جزئي | تكلفة العمل المنجز | 43 | 100 | 2012-11-17 | 2015-10-15 | 2024-10-30 | 2024-10-30 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.0346 | 30.951 | Failed | No
2100099396 | جامعة الحدود الشمالية | تشييد | ذات اولوية عالية | 107589877.98 | 5379493.899 | 79258980.98 | 79258980.98 | 1010034600 | لا | 0 | 181009185167 | جاري | تكلفة العمل المنجز | 79 | 98 | 2012-11-17 | 2015-10-15 | 2023-07-01 | 2023-07-01 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.0346 | 30.951 | متأخر | No
2300240660 | أمانة / الطائف | تشييد | ذات اولوية عالية | 29536945 | 1476847.25 | 1201027.81 | 0 | 0 | لا | 0 |  | جاري | تكلفة العمل المنجز | 50 | 100 | 2022-08-22 | 2023-08-11 | 2023-08-11 | 2023-08-11 |  |  |  |  | 40.8298 | 20.727 | منتظم | Yes
2200236445 | أمانة / العاصمة المقدسة | أخرى | ذات اولوية متوسطة | 6667000 | 333350 | 2434614.82 | 2434614.82 | 4031019772 | لا | 0 |  | جاري | تكلفة العمل المنجز | 36.52 | 36.52 | 2020-04-26 | 2022-04-04 | 2022-04-04 | 2022-04-04 |  |  |  |  | 39.8579 | 21.3891 | خدمات عامة | No
2300240671 | أمانة / الطائف | تشييد | ذات اولوية عالية | 197103675 | 9855183.75 | 0 | 0 | 0 | لا | 0 |  | جاري | تكلفة العمل المنجز | 40 | 100 | 2022-08-22 | 2023-08-11 | 2023-08-11 | 2023-08-11 |  |  |  |  | 40.8298 | 20.727 | منتظم | No
2100018406 | جامعة الحدود الشمالية | تشييد | ذات اولوية عالية | 387304843.04 | 19365242.152 | 156117692 | 156117692 | 1010034600 | لا | 0 | 210909000632 | ايقاف جزئي | تكلفة العمل المنجز | 44 | 100 | 2012-06-11 | 2015-05-23 | 2024-12-30 | 2024-12-30 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال |  | 41.0346 | 30.951 | Failed | No
2100072483 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 5964000 | 298200 | 5804360.44 | 5804360.44 | 1010063483 | لا | 0 | 190501028178 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 97.21 | 97.21 | 2019-09-29 | 2021-07-09 | 2021-12-06 | 2021-12-06 | 2021-07-09 |  | أوامر سامية |  | 39.8523 | 21.3299 | منجز | No
2300240682 | أمانة / الطائف | تشييد | ذات اولوية متوسطة | 1393639 | 69681.95 | 0 | 0 | 0 | لا | 0 |  | جاري | تكلفة العمل المنجز | 5 | 100 | 2022-12-19 | 2023-05-25 | 2023-05-25 | 2023-05-25 |  |  |  |  | 40.8298 | 20.727 | منتظم | No
2100076683 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 5358040.8 | 267902.04 | 369705 | 369705 | 4031045724 | لا | 0 | 180909105548 | مسحوب | تكلفة العمل المنجز | 33 | 100 | 2015-08-20 | 2017-02-17 | 2018-04-09 | 2018-04-09 |  |  | ضعف كفاءة المقاول الفنية |  | 39.89 | 21.3815 | مسحوب | No
2100091254 | وزارة التعليم | تشييد | ذات اولوية متوسطة | 3254770.52 | 162738.526 | 0 | 0 | 4030204423 | لا | 0 |  | فسخ العقد | التكلفة المفوترة | 0 | 100 | 2015-03-15 | 2017-03-15 | 2023-06-06 | 2023-06-06 |  |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 42.5429 | 16.8808 | مسحوب | No
2100075515 | أمانة / نجران | تشييد | ذات اولوية متوسطة | 1392857.5 | 69642.875 | 13928.57 | 0 | 5950012645 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 22 | 33 | 2019-06-20 | 2020-06-19 | 2022-09-11 | 2022-09-11 | 2020-06-19 |  | اخرى |  | 44.1567 | 17.6045 | منجز | Yes
2100007781 | هيئة تطوير منطقة المدينة المنورة | تشييد | ذات اولوية عالية | 54497745 | 2724887.25 | 54497745 | 54497745 | 4650050716 | لا | 0 | 190309071612 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-08-30 | 2020-08-29 | 2021-04-28 | 2021-04-28 | 2020-08-29 |  | ضعف كفاءة المقاول الفنية |  | 39.5473 | 24.4593 | منجز | No
2100046336 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 667700 | 33385 | 484310.2 | 484310.2 | 3357606103 | لا | 0 | 180909103716 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-06-21 | 2019-10-14 | 2020-07-15 | 2020-07-15 | 2019-10-14 |  |  |  | 42.443 | 27.1781 | منجز | No
2100178404 | وزارة الثقافة | تشييد | ذات اولوية عالية | 46075832.59 | 2303791.6295 | 4705754.29 | 3790124.75 | 3350012131 | لا | 0 | 201009164354 | مسحوب | منهجية القيمة المكتسبة | 100 | 100 | 2018-03-21 | 2020-01-31 | 2020-01-30 | 2020-01-30 |  |  | اخرى |  | 49.5824 | 25.3792 | مسحوب | No
2100099326 | الديوان العام للمحاسبة | تشييد | ذات اولوية عالية | 84359542 | 4217977.1 | 75633670.2 | 75633670.2 | 1010046693 | لا | 0 | 181001146050 | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2019-02-25 | 2022-12-29 | 2022-12-29 | 2022-12-29 | 2022-12-29 |  | تأخرصرف المستحقات المالية |  | 46.7239 | 24.6578 | منجز | No
2200234301 | الديوان العام للمحاسبة | إشراف | ذات اولوية متوسطة | 1273740 | 63687 | 1056479.03 | 1056479.03 | 1010046693 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2021-11-14 | 2022-12-29 | 2022-12-29 | 2022-12-29 | 2022-12-29 |  |  |  | 46.7238 | 24.6576 | منجز | No
2200223742 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 31262714.58 | 1563135.729 | 3900709.03 | 3900709.03 | 1010082898 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 41.25 | 100 | 2020-10-26 | 2021-10-25 | 2023-03-31 | 2023-03-31 |  |  |  | تم إنذار المقاول كتابيا | 42.9591 | 16.8675 | Failed | No
2100064794 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 33497415 | 1674870.75 | 27935093.6 | 27935093.6 | 4030010851 | لا | 0 | 180809063858 | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 85 | 100 | 2018-04-01 | 2020-03-31 | 2023-03-08 | 2023-03-08 |  |  |  | أخرى | 41.7243 | 27.537 | متأخر | No
2100008050 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 176642181 | 8832109.05 | 85403051.83 | 85403051.83 | 2050022550 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 88 | 100 | 2013-05-21 | 2015-05-11 | 2023-03-31 | 2023-03-31 |  |  | ضعف كفاءة المقاول الفنية | أخرى | 42.4409 | 27.1923 | Failed | No
2100005095 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 40000664.2 | 2000033.21 | 22644482.53 | 10627646.57 | 2050022550 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2013-05-19 | 2015-05-09 | 2022-12-31 | 2022-12-31 | 2015-05-09 |  | ضعف كفاءة المقاول الفنية | أخرى | 43.4919 | 25.8758 | منجز | No
2100004373 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 396416038 | 19820801.9 | 186510287.29 | 186510287.29 | 2050022550 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 89 | 100 | 2013-05-21 | 2015-05-11 | 2023-03-31 | 2023-03-31 |  |  | تأخرصرف المستحقات المالية | أخرى | 41.6968 | 27.506 | Failed | No
2100102944 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 104012325 | 5200616.25 | 47171859.58 | 47171859.58 | 1010054406 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 80 | 100 | 2013-08-19 | 2015-08-09 | 2023-03-31 | 2023-03-31 |  |  | ضعف كفاءة المقاول الفنية | أخرى | 40.197 | 29.9622 | Failed | No
2100045312 | أمانة / حائل | تشييد | ذات اولوية متوسطة | 691777.8 | 34588.89 | 569420.65 | 569420.65 | 3360005382 | لا | 0 | 200801025238 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 82 | 82 | 2019-06-13 | 2020-06-06 | 2022-05-15 | 2022-05-15 | 2020-06-06 |  |  |  | 40.6059 | 27.1238 | منجز | No
2100003043 | أمانة / العاصمة المقدسة | دراسة بيئية | ذات اولوية متوسطة | 39743975 | 1987198.75 | 38711995 | 38711995 | 1010325725 | لا | 0 | 190601032388 | منجز – استلام نهائي | التكلفة المفوترة | 88.77 | 88.77 | 2019-09-24 | 2021-09-23 | 2022-03-22 | 2022-03-22 | 2021-09-23 | 2022-04-28 | اخرى |  | 39.8513 | 21.3748 | منجز | No
2100019434 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 40787335.4 | 2039366.77 | 38268441 | 38268441 | 4031025550 | لا | 0 | 180301000710 | جاري | التكلفة المفوترة | 89.33 | 89.33 | 2018-06-28 | 2021-06-27 | 2022-07-02 | 2022-07-02 |  |  |  |  | 39.8777 | 21.3667 | متأخر | No
2100066754 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 36834815 | 1841740.75 | 33700959.41 | 33700959.41 | 4031041927 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 98.67 | 98.67 | 2014-11-18 | 2017-10-15 | 2019-03-15 | 2019-03-15 | 2017-10-15 |  | أحداث غير متوقعة : الطقس/ إجازات / مشاكل حفر... الخ |  | 39.8621 | 21.3697 | منجز | No
2100091184 | أمانة / العاصمة المقدسة | دراسة الجدوى | ذات اولوية متوسطة | 3996000 | 199800 | 3348996 | 3348996 | 4031089686 | لا | 0 | 181009120048 | جاري الاستلام الإبتدائي | التكلفة المفوترة | 89.5 | 89.5 | 2018-11-02 | 2020-11-02 | 2020-02-11 | 2020-02-11 |  |  | اخرى |  |  |  | Failed | No
2100096386 | أمانة / العاصمة المقدسة | دراسة بيئية | ذات اولوية متوسطة | 6640000 | 332000 | 6319714 | 6319714 | 4031008077 | لا | 0 | 190909043078 | جاري الاستلام الإبتدائي | التكلفة المفوترة | 81.78 | 81.78 | 2019-08-20 | 2022-08-04 | 2022-08-04 | 2022-08-04 |  |  | اخرى |  |  |  | متأخر | No
2100073415 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 65374760 | 3268738 | 65374760 | 65374760 | 1010066115 | لا | 0 |  | منجز – استلام نهائي | التكلفة المفوترة | 100 | 100 | 2013-06-10 | 2014-06-10 | 2016-10-22 | 2016-10-22 | 2014-06-10 | 2020-09-20 |  |  | 39.9325 | 21.3625 | منجز | No
2100052905 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 73392035 | 3669601.75 | 58181734 | 58181734 | 4031024970 | لا | 0 | 4046203 | جاري | التكلفة المفوترة | 75.51 | 75.51 | 2018-06-24 | 2021-10-22 | 2023-03-12 | 2023-03-12 |  |  |  |  | 39.8753 | 21.3899 | منتظم | No
2300240741 | جامعة القصيم | تشييد | ذات اولوية عالية وعاجلة | 366299 | 18314.95 | 0 | 0 | 1128001788 | لا | 0 |  | جاري | تكلفة العمل المنجز | 10 | 10 | 2022-12-06 | 2023-08-13 | 2023-08-13 | 2023-08-13 |  |  |  |  | 43.7668 | 26.349 | منتظم | No
2100002026 | وكالة / الإسكان | تشييد | ذات اولوية متوسطة | 90631472.3 | 4531573.615 | 38674634.4 | 37589494.51 | 1010166750 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2014-11-24 | 2016-05-17 | 2019-11-09 | 2019-11-09 | 2016-05-17 |  | ضعف كفاءة المقاول الفنية | أخرى | 38.4276 | 24.3262 | منجز | No
2200221826 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 92421883.5 | 4621094.175 | 37307735.53 | 37307735.53 | 2051017029 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 92 | 95 | 2020-11-15 | 2022-02-08 | 2023-09-30 | 2023-09-30 |  |  |  |  | 50.0888 | 26.4207 | منتظم | No
2300240752 | جامعة القصيم | تشييد | ذات اولوية عالية وعاجلة | 4174500 | 208725 | 0 | 0 | 1010196594 | لا | 0 |  | جاري | تكلفة العمل المنجز | 50 | 50 | 2022-12-01 | 2023-01-30 | 2023-01-30 | 2023-01-30 |  |  |  |  | 43.7613 | 26.3522 | منتظم | No
2100095970 | أمانة / العاصمة المقدسة | تحديث وتوريد | ذات اولوية متوسطة | 2992500 | 149625 | 327750 | 327750 | 1010326466 | لا | 0 | 200209131703 | منجز – استلام نهائي | مدفوعات ساعات العمل | 100 | 100 | 2019-10-06 | 2021-08-09 | 2021-03-28 | 2021-03-28 | 2021-08-09 | 2021-08-09 | اخرى |  |  |  | منجز | No
2100070781 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 118109111.48 | 5905455.574 | 45802629.4 | 45802629.4 | 1128000011 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 78 | 78 | 2019-12-03 | 2021-05-26 | 2023-09-02 | 2023-09-02 |  |  | التنسيق مع أصحاب المصلحه (خدمات | أخرى |  |  | منتظم | No
2100193115 | وزارة الحرس الوطني / جامعة الملك سعود بن عبدالعزيز للعلوم الصحية | توريد وتركيب | ذات اولوية عالية | 4447774.5 | 222388.725 | 1891485.5 | 1891485.5 | 1010219886 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 85 | 100 | 2021-01-17 | 2021-07-17 | 2023-02-28 | 2023-02-28 | 2021-07-17 | 2022-01-11 |  |  | 46.8599 | 24.7553 | Failed | No
2100103121 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 114351752 | 5717587.6 | 81715525.13 | 81715525.13 | 1010006362 | لا | 0 |  | منجز – استلام ابتدائي | منهجية القيمة المكتسبة | 100 | 100 | 2014-11-09 | 2016-02-02 | 2022-12-31 | 2022-12-31 | 2016-02-02 |  | تأخرصرف المستحقات المالية | أخرى | 45.3525 | 25.8912 | منجز | No
2200218013 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 42872591.2 | 2143629.56 | 27964398.04 | 27964398.04 | 1010185409 | لا | 0 |  | ايقاف جزئي | منهجية القيمة المكتسبة | 99 | 100 | 2019-12-30 | 2021-07-27 | 2022-12-31 | 2022-12-31 |  |  |  | أخرى | 42.8614 | 18.1862 | Failed | No
2100054526 | وكالة / الإسكان | تشييد | ذات اولوية متوسطة | 23933668.08 | 1196683.404 | 8683629.76 | 8683629.76 | 1128000011 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 74 | 83 | 2019-09-02 | 2020-09-01 | 2023-03-31 | 2023-03-31 |  |  | التنسيق مع أصحاب المصلحه (خدمات | أخرى |  |  | متأخر | No
2100002575 | وكالة / الإسكان | تشييد | ذات اولوية عالية وعاجلة | 304540964.78 | 15227048.239 | 140678168.09 | 117460427.24 | 1010008118 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 84 | 100 | 2015-02-02 | 2016-07-31 | 2023-03-31 | 2023-03-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال | أخرى | 38.7932 | 23.7799 | Failed | No
2300240800 | وزارة التعليم | توريد وتركيب | ذات اولوية متوسطة | 2093000 | 104650 | 732607.5 | 206195 | 0 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 50 | 100 | 2022-04-21 | 2023-04-21 | 2023-04-21 | 2023-04-21 |  |  |  |  | 42.2313 | 18.099 | Failed | No
2100011406 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 2689357.5 | 134467.875 | 1599335 | 1599335 | 2511104587 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2019-03-11 | 2020-07-03 | 2020-09-05 | 2020-09-05 | 2020-07-03 |  | اخرى |  | 46.8595 | 24.7664 | منجز | No
2100020156 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 4199920 | 209996 | 4184410 | 4184410 | 2511104587 | لا | 0 |  | جاري | اخرى | 100 | 100 | 2019-06-30 | 2020-06-29 | 2021-10-05 | 2021-10-05 |  |  |  |  | 46.8595 | 24.7664 | Failed | No
2100205505 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية وعاجلة | 4173325 | 208666.25 | 0 | 0 | 1010581759 | لا | 0 | 210901202769 | جاري | تكلفة العمل المنجز | 0 | 10 | 2021-11-24 | 2023-05-24 | 2023-05-24 | 2023-05-24 |  |  |  |  | 49.9982 | 26.5765 | متأخر | No
2100178500 | وزارة الثقافة | إشراف | ذات اولوية عالية | 4602675 | 230133.75 | 2833720.99 | 0 | 1010433597 | لا | 0 | 201009164378 | منجز – استلام نهائي | مدفوعات ساعات العمل | 100 | 100 | 2019-11-17 | 2021-02-16 | 2021-06-30 | 2021-06-30 | 2021-02-16 | 2021-06-06 |  |  | 36.526 | 28.3874 | منجز | Yes
2100040596 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 3488823 | 174441.15 | 3488823 | 3488823 | 1010259143 | لا | 0 |  | منجز – استلام ابتدائي | اخرى | 100 | 100 | 2019-05-02 | 2020-02-05 | 2020-02-05 | 2020-02-05 | 2020-02-05 |  | لا يوجد تأخير |  | 21.3355 | 39.9652 | منجز | No
2100004701 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 2297435 | 114871.75 | 1505900 | 1505900 | 3400017056 | لا | 0 |  | جاري | اخرى | 52 | 100 | 2018-09-13 | 2019-08-13 | 2019-08-13 | 2019-08-13 |  |  | ضعف كفاءة المقاول الفنية |  |  |  | Failed | No
2100020521 | رئاسة أمن الدولة / قوات الطوارئ الخاصة | تشييد | ذات اولوية عالية | 7293578.25 | 364678.9125 | 6390255.8 | 6390255.8 | 1010259143 | لا | 0 |  | جاري | اخرى | 99 | 100 | 2020-03-29 | 2021-08-19 | 2021-08-19 | 2021-08-19 |  |  | لا يوجد تأخير |  |  |  | Failed | No
2100082320 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 29999105.5 | 1499955.275 | 15559798 | 15559798 | 1010156720 | لا | 0 | 181009117228 | منجز – استلام نهائي | التكلفة المفوترة | 91.04 | 91.04 | 2014-10-19 | 2016-10-18 | 2020-05-15 | 2020-05-15 | 2016-10-18 | 2022-02-20 | أوامر سامية |  | 39.8891 | 21.3304 | منجز | No
2300240811 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1152782 | 57639.1 | 676999.47 | 676999.47 | 1015000676 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 97 | 100 | 2014-12-18 | 2019-12-11 | 2021-08-18 | 2021-08-18 | 2019-12-11 |  |  |  | 46.1805 | 22.4329 | منجز | No
2300240833 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 119680155 | 5984007.75 | 57446474.4 | 57446474.4 | 3555000709 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 48 | 55 | 2019-11-18 | 2025-10-21 | 2025-10-21 | 2025-10-21 |  |  |  |  | 39.6005 | 24.4595 | متأخر | No
2300240822 | الإدارة العامة للشؤون الإدارية والمالية | توريد وتركيب | ذات اولوية متوسطة | 4967425 | 248371.25 | 1316175 | 1316175 | 1010199999 | لا | 0 |  | جاري | اخرى | 26.5 | 33 | 2022-09-27 | 2023-09-16 | 2023-09-16 | 2023-09-16 |  |  |  |  | 46.7109 | 24.6286 | متأخر | No
2200233660 | أمانة / العاصمة المقدسة | تشييد | ذات اولوية متوسطة | 19033062.58 | 951653.129 | 6222597 | 6222597 | 4031019772 | لا | 0 |  | جاري | تكلفة العمل المنجز | 35.34 | 35.34 | 2021-02-18 | 2023-01-23 | 2023-01-23 | 2023-01-23 |  |  |  |  | 39.8579 | 21.3891 | منتظم | No
2300240866 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1105845 | 55292.25 | 0 | 0 | 1010056094 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 90 | 100 | 2015-08-06 | 2018-12-14 | 2018-12-14 | 2018-12-14 |  |  |  |  | 46.1805 | 22.4329 | Failed | No
2300240855 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 499900 | 24995 | 0 | 0 | 1010324989 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 100 | 100 | 2015-05-26 | 2016-09-17 | 2016-09-17 | 2016-09-17 |  |  |  |  | 46.1805 | 22.4329 | Failed | No
2100101080 | جامعة الجوف | تشييد | ذات اولوية عالية | 4961400 | 248070 | 3903322.3 | 3903322.3 | 3400006337 | لا | 0 | 181009144366 | جاري | تكلفة العمل المنجز | 80 | 100 | 2019-03-24 | 2020-08-30 | 2023-02-01 | 2023-02-01 |  |  | تأخرصرف المستحقات المالية |  | 40.0636 | 29.7981 | متأخر | No
2100098954 | أمانة / العاصمة المقدسة | دراسة الجدوى | ذات اولوية متوسطة | 4356000 | 217800 | 4343455 | 4343455 | 4030228046 | لا | 0 | 181109339754 | منجز – استلام نهائي | تكلفة العمل المنجز | 93.24 | 93.24 | 2018-06-12 | 2020-12-09 | 2020-12-09 | 2020-12-09 | 2020-12-09 | 2020-12-21 | اخرى |  |  |  | منجز | No
2300240870 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 425646 | 21282.3 | 0 | 0 | 4030149405 | لا | 0 |  | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 87 | 100 | 2020-02-05 | 2021-04-16 | 2021-04-16 | 2021-04-16 |  |  |  |  | 46.1805 | 22.4329 | Failed | No
2100092606 | أمانة / تبوك | تشييد | ذات اولوية عالية وعاجلة | 14416500 | 720825 | 5791108.05 | 5791108.05 | 1010188619 | لا | 0 | 181201398029 | جاري | الكميات التي تم تركيبها | 75 | 98 | 2019-03-30 | 2022-12-22 | 2023-08-07 | 2023-08-07 |  |  | ضعف كفاءة المقاول الفنية |  | 36.5213 | 28.3814 | متأخر | No
2100034930 | الهيئة الملكية لمدينة الرياض | تشييد | ذات اولوية عالية | 79083298 | 3954164.9 | 70604598 | 70604598 | 1010085518 | لا | 0 | 190909135969 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2015-11-01 | 2017-04-15 | 2020-12-12 | 2020-12-12 | 2017-04-15 |  |  |  | 46.7093 | 24.6283 | منجز | No
2100101695 | وزارة الصحة / الرياض | تشييد | ذات اولوية متوسطة | 20999150 | 1049957.5 | 16049348 | 16049348 | 1018000245 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 85 | 100 | 2013-12-03 | 2015-12-02 | 2017-12-27 | 2017-12-27 |  |  | اخرى | أخرى | 46.7098 | 24.6275 | Failed | No
2100102270 | أمانة / العاصمة المقدسة | تشطيب | ذات اولوية متوسطة | 1447200 | 72360 | 1423321 | 1423321 | 1010348048 | لا | 0 |  | منجز – استلام نهائي | مدفوعات ساعات العمل | 100 | 100 | 2018-07-16 | 2019-07-17 | 2019-07-17 | 2019-07-17 | 2019-07-17 | 2022-04-10 | اخرى |  | 39.8828 | 21.3494 | منجز | No
2100099186 | أمانة / العاصمة المقدسة | إشراف | ذات اولوية متوسطة | 12204000 | 610200 | 11220965 | 11220965 | 2051060068 | لا | 0 | 190509033555 | منجز – استلام نهائي | مدفوعات ساعات العمل | 94.91 | 94.91 | 2018-01-07 | 2020-12-29 | 2021-05-20 | 2021-05-20 | 2020-12-29 | 2021-06-06 | اخرى |  |  |  | منجز | No
2300240881 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 811725 | 40586.25 | 361875 | 0 | 1010085648 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 44 | 65 | 2019-05-14 | 2021-01-05 | 2021-01-05 | 2021-01-05 |  |  |  |  | 46.1805 | 22.4329 | Failed | Yes
2200234393 | أمانة / العاصمة المقدسة | إشراف | ذات اولوية متوسطة | 1890105 | 94505.25 | 1842013.07 | 1842013.07 | 1010320728 | لا | 0 |  | جاري | تكلفة العمل المنجز | 97.46 | 97.46 | 2021-03-10 | 2023-03-10 | 2023-03-10 | 2023-03-10 |  |  |  |  | 39.8579 | 21.3891 | خدمات عامة | No
2100102583 | أمانة / العاصمة المقدسة | تصميم وإشراف | ذات اولوية متوسطة | 8118000 | 405900 | 5975193 | 5975193 | 4031063513 | لا | 0 |  | منجز – استلام نهائي | مدفوعات ساعات العمل | 96.77 | 96.77 | 2018-11-20 | 2021-11-19 | 2021-07-05 | 2021-07-05 | 2021-11-19 | 2021-11-19 | اخرى |  | 39.8778 | 21.3768 | منجز | No
2300240914 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 78073140.51 | 3903657.0255 | 66362169.43 | 66362157 | 1010095089 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 85 | 90 | 2019-01-14 | 2019-07-15 | 2025-12-28 | 2025-12-28 |  |  |  |  | 39.6005 | 24.4595 | منتظم | No
2300240925 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 5865500 | 293275 | 4047195 | 4047195 | 4030007950 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 69 | 76 | 2022-10-18 | 2023-06-18 | 2023-03-06 | 2023-03-06 |  |  |  |  | 39.6005 | 24.4595 | متأخر | No
2300240892 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 69934800 | 3496740 | 15385656 | 15385656 | 1010595703 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 22 | 26 | 2021-12-19 | 2022-12-19 | 2023-12-19 | 2023-12-19 |  |  |  |  | 39.6005 | 24.4595 | منتظم | No
2300240995 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 16797376.25 | 839868.8125 | 12766005.95 | 12766005.95 | 1010219886 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 76 | 80 | 2019-10-29 | 2023-08-05 | 2024-08-05 | 2024-08-05 |  |  |  |  | 39.6005 | 24.4595 | منتظم | No
2300240973 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 64175000 | 3208750 | 64175000 | 64175000 | 1010052246 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2017-12-04 | 2022-08-22 | 2023-08-22 | 2023-08-22 | 2022-08-22 |  |  |  | 39.6005 | 24.4595 | منجز | No
2300240940 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 14626843.49 | 731342.1745 | 13164159.14 | 13164159.14 | 1131009849 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 90 | 95 | 2022-05-30 | 2022-11-30 | 2023-11-30 | 2023-11-30 |  |  |  |  | 39.6005 | 24.4595 | منتظم | No
2300241006 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 14172375 | 708618.75 | 12613413.75 | 12613413.75 | 1010267848 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 89 | 95 | 2020-06-15 | 2022-11-29 | 2023-11-29 | 2023-11-29 |  |  |  |  | 39.6005 | 24.4595 | متأخر | No
2300241010 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 14728350 | 736417.5 | 13108231.5 | 13108231.5 | 0 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 89 | 95 | 2020-06-15 | 2022-11-05 | 2023-11-05 | 2023-11-05 |  |  |  |  | 39.6005 | 24.4595 | متأخر | No
2300241054 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 64984920 | 3249246 | 58486428 | 58486428 | 1010052246 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 90 | 95 | 2018-01-29 | 2022-10-30 | 2023-10-30 | 2023-10-30 |  |  |  |  | 39.6005 | 24.4595 | منتظم | No
2300240962 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 19997736.68 | 999886.834 | 10798777.81 | 10798777.81 | 1010052246 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 54 | 60 | 2020-10-21 | 2022-10-10 | 2023-12-01 | 2023-12-01 |  |  |  |  | 39.6005 | 24.4595 | متأخر | No
2300240951 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 21168257 | 1058412.85 | 3175238.55 | 3175238.55 | 1010052246 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 15 | 20 | 2022-03-06 | 2023-03-06 | 2024-02-12 | 2024-02-12 |  |  |  |  | 39.6005 | 24.4595 | منتظم | No
2300241102 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 19638504 | 981925.2 | 2945775.6 | 2945775.6 | 4650032795 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 15 | 20 | 2022-11-06 | 2024-11-05 | 2025-11-05 | 2025-11-05 |  |  |  |  | 39.6005 | 24.4595 | منتظم | No
2300241113 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 19846251.5 | 992312.575 | 3175400.24 | 3175400.24 | 4650032795 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 16 | 20 | 2022-11-06 | 2023-11-05 | 2024-11-06 | 2024-11-06 |  |  |  |  | 39.6005 | 24.4595 | منتظم | No
2300241124 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 19932731.5 | 996636.575 | 996636.575 | 996636.575 | 4650032795 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 5 | 15 | 2022-11-06 | 2023-11-05 | 2024-11-05 | 2024-11-05 |  |  |  |  | 39.6005 | 24.4595 | متأخر | No
2300241135 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 4841500 | 242075 | 3389050 | 3389050 | 4650047424 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 70 | 75 | 2022-04-04 | 2023-03-24 | 2024-04-24 | 2024-04-24 |  |  |  |  | 39.6005 | 24.4595 | منتظم | No
2300241146 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 966000 | 48300 | 869400 | 869400 | 4650047424 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 90 | 100 | 2021-02-21 | 2022-02-22 | 2023-02-21 | 2023-02-21 | 2022-02-22 |  |  |  | 39.6005 | 24.4595 | منجز | No
2300241161 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 42499947 | 2124997.35 | 28049965.02 | 28049965.02 | 4030140655 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 66 | 70 | 2020-07-13 | 2023-06-10 | 2024-06-10 | 2024-06-10 |  |  |  |  | 39.6005 | 24.4595 | منتظم | No
2300241172 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 6198500 | 309925 | 2479400 | 2479400 | 1010425494 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 40 | 45 | 2022-06-01 | 2023-12-01 | 2024-12-01 | 2024-12-01 |  |  |  |  | 39.6005 | 24.4595 | منتظم | No
2300241065 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 77652185.16 | 3882609.258 | 69886966.64 | 69886966.64 | 1010052246 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 90 | 95 | 2019-01-29 | 2023-07-31 | 2024-07-31 | 2024-07-31 |  |  |  |  | 39.6005 | 24.4595 | منتظم | No
2300240984 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 17760600 | 888030 | 15629328 | 15629328 | 1010220868 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 88 | 92 | 2019-10-02 | 2020-10-02 | 2023-08-08 | 2023-08-08 |  |  |  |  | 39.6005 | 24.4595 | منتظم | No
2300241194 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 15949400 | 797470 | 13716484 | 13716484 | 4650007032 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 86 | 100 | 2018-10-07 | 2023-05-17 | 2023-05-17 | 2023-05-17 |  |  |  |  | 39.6005 | 24.4595 | متأخر | No
2300241216 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 19657076.5 | 982853.825 | 4127986.065 | 4127986.065 | 4650049563 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 21 | 40 | 2022-03-08 | 2024-02-14 | 2024-02-14 | 2024-02-14 |  |  |  |  | 39.6005 | 24.4595 | متأخر | No
2300241242 | أمانة / المدينة المنورة | دراسات هندسية | ذات اولوية متوسطة | 4991000 | 249550 | 1247750 | 1247750 | 2050111273 | لا | 0 |  | جاري | تكلفة العمل المنجز | 25 | 40 | 2022-03-23 | 2024-02-29 | 2024-02-29 | 2024-02-29 |  |  |  |  | 39.6005 | 24.4595 | خدمات عامة | No
2300241231 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 3724297.5 | 186214.875 | 3351867.75 | 3351867.75 | 4650030480 | لا | 0 |  | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 90 | 100 | 2020-05-06 | 2023-01-07 | 2023-01-07 | 2023-01-07 |  |  |  |  | 39.6005 | 24.4595 | متأخر | No
2300241264 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 29379576 | 1468978.8 | 1149392.59 | 1149392.59 | 1017000207 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 65 | 100 | 2019-04-29 | 2021-07-03 | 2021-07-03 | 2021-07-03 |  |  |  |  | 46.1805 | 22.4329 | Failed | No
2300241275 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 6442800 | 322140 | 2609358.6 | 2609358.6 | 1113000219 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 65 | 100 | 2019-06-13 | 2021-05-05 | 2022-02-09 | 2022-02-09 |  |  |  |  | 45.3463 | 26.5018 | Failed | No
2300241286 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3557640 | 177882 | 981650 | 981650 | 1010197183 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 28 | 50 | 2014-09-22 | 2016-09-11 | 2016-09-11 | 2016-09-11 |  |  |  |  | 45.3463 | 26.5018 | Failed | No
2100005703 | جامعة طيبة | تشييد | ذات اولوية عالية | 152385742 | 7619287.1 | 121691070.82 | 121691070.82 | 4650002884 | لا | 0 | 180709033708 | جاري | تكلفة العمل المنجز | 80 | 96 | 2013-09-19 | 2022-01-03 | 2022-12-30 | 2022-12-30 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال | تم إنذار المقاول كتابيا | 39.6005 | 24.4595 | متأخر | No
2300241205 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 4500000 | 225000 | 3780000 | 3780000 | 1010425494 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 84 | 94 | 2022-11-09 | 2024-11-08 | 2024-11-08 | 2024-11-08 |  |  |  |  | 39.6005 | 24.4595 | متأخر | No
2100060992 | رئاسة أمن الدولة / ديوان رئاسة أمن الدولة | تشييد | ذات اولوية عالية وعاجلة | 5891823.5 | 294591.175 | 5694338.85 | 5694338.85 | 2252032121 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-10-14 | 2021-12-01 | 2022-11-17 | 2022-11-17 | 2021-12-01 |  | تغيرات في نطاق المشروع |  |  |  | منجز | No
2300241334 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 166418900 | 8320945 | 108452019.3 | 108452019.3 | 1010017123 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 86 | 100 | 2019-09-05 | 2023-02-02 | 2023-02-02 | 2023-02-02 |  |  |  |  | 46.8243 | 22.6917 | متأخر | No
2300241312 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2075832 | 103791.6 | 0 | 0 | 1010263223 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 100 | 100 | 2019-06-10 | 2020-11-17 | 2020-11-17 | 2020-11-17 |  |  |  |  | 46.6753 | 24.7136 | Failed | No
2300241301 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 7164341 | 358217.05 | 1234107.75 | 1234107.75 | 1010056094 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 41 | 100 | 2015-08-06 | 2018-12-14 | 2018-12-14 | 2018-12-14 |  |  |  |  | 46.6753 | 24.7136 | Failed | No
2300241290 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 333748684 | 16687434.2 | 1704430.69 | 1704430.69 | 1010234015 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 84 | 100 | 2015-03-29 | 2017-09-16 | 2017-09-16 | 2017-09-16 |  |  |  |  | 47.0001 | 22.7323 | Failed | No
2300241323 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1455650 | 72782.5 | 174132.21 | 174132.21 | 1017000955 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 11 | 100 | 2019-09-09 | 2021-09-12 | 2021-09-12 | 2021-09-12 |  |  |  |  | 46.2702 | 21.6234 | Failed | No
2300241345 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 794400 | 39720 | 0 | 0 | 1015000676 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 0 | 100 | 2020-02-05 | 2021-01-31 | 2021-01-30 | 2021-01-30 |  |  |  |  | 46.9055 | 22.6148 | Failed | No
2300241356 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2069020 | 103451 | 1733889.55 | 1733889.55 | 1010393520 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 90 | 100 | 2019-09-01 | 2022-10-17 | 2022-10-17 | 2022-10-17 |  |  |  |  | 45.3941 | 23.6212 | متأخر | No
2300241360 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2634250 | 131712.5 | 463937.25 | 463937.25 | 1010188984 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 27 | 100 | 2018-09-30 | 2020-12-04 | 2023-01-23 | 2023-01-23 |  |  |  |  | 45.898 | 24.384 | Failed | No
2300241371 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1225500 | 61275 | 185783.5196 | 185783.5196 | 1010265792 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 15 | 100 | 2020-08-24 | 2021-11-17 | 2021-11-18 | 2021-11-18 |  |  |  |  | 45.898 | 24.384 | Failed | No
2100044645 | أمانة / الرياض | تشييد | ذات اولوية عالية | 293721619.8 | 14686080.99 | 196958.74 | 0.01 | 1010092796 | لا | 0 | 190701144035 | جاري | الكميات التي تم تركيبها | 75.76 | 67.26 | 2019-12-05 | 2023-11-23 | 2021-11-23 | 2021-11-23 |  |  |  |  | 46.8374 | 24.7959 | منتظم | No
2300241393 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 5647320 | 282366 | 0 | 0 | 1010328456 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 0 | 70 | 2021-01-03 | 2023-12-19 | 2023-12-19 | 2023-12-19 |  |  |  |  | 43.6791 | 24.6769 | Failed | No
2100062031 | الهيئة الملكية لمدينة الرياض | تشييد | ذات اولوية عالية | 805213766.06 | 40260688.303 | 805213766.06 | 805213766.06 | 1010146766 | لا | 0 | 190209014172 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-11-29 | 2017-10-26 | 2021-04-29 | 2021-04-29 | 2017-10-26 |  |  |  | 46.6536 | 24.8425 | منجز | No
2100005924 | جامعة طيبة | تشييد | ذات اولوية عالية | 38370047.83 | 1918502.3915 | 5973961.13 | 5973961.13 | 2050022550 | لا | 0 | 181109376888 | ايقاف كلي | تكلفة العمل المنجز | 16 | 100 | 2014-09-21 | 2015-08-06 | 2017-03-24 | 2017-03-24 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال | مخطط لسحبه وإعادة ترسيته | 39.6005 | 24.4595 | Failed | No
2100022013 | جامعة طيبة | تشييد | ذات اولوية عالية | 118648772.73 | 5932438.6365 | 96105506.72 | 96105506.72 | 2050022550 | لا | 0 | 181109376888 | ايقاف كلي | تكلفة العمل المنجز | 81 | 100 | 2012-01-07 | 2017-01-30 | 2017-01-30 | 2017-01-30 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال | مخطط لسحبه وإعادة ترسيته | 39.6005 | 24.4595 | Failed | No
2300241404 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 8512945 | 425647.25 | 749494 | 749494 | 7010924525 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 89 | 100 | 2019-10-29 | 2021-07-21 | 2021-07-21 | 2021-07-21 |  |  |  |  | 43.6756 | 24.6756 | Failed | No
2300241415 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 8512945 | 425647.25 | 749494 | 749494 | 7010924525 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 89 | 100 | 2019-10-29 | 2021-07-21 | 2021-07-21 | 2021-07-21 |  |  |  |  | 43.6756 | 24.6756 | Failed | No
2300241426 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 47506094 | 2375304.7 | 0 | 0 | 1116001737 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 71 | 100 | 2019-12-01 | 2021-05-24 | 2021-05-24 | 2021-05-24 |  |  |  |  | 43.6756 | 24.6756 | Failed | No
2300241430 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1998435 | 99921.75 | 1082125 | 1082125 | 7010924525 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 91 | 100 | 2020-02-16 | 2021-06-26 | 2021-06-26 | 2021-06-26 |  |  |  |  | 43.6756 | 24.6756 | Failed | No
2300241441 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1532050 | 76602.5 | 0 | 0 | 4030192494 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 100 | 100 | 2009-07-04 | 2011-06-24 | 2021-08-25 | 2021-08-25 |  |  |  |  | 43.6831 | 24.6795 | متأخر | No
2300241452 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2595825 | 129791.25 | 0 | 0 | 1010407036 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 0 | 100 | 2020-08-13 | 2021-11-06 | 2023-01-23 | 2023-01-23 |  |  |  |  | 45.898 | 24.384 | Failed | No
2300241463 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 17281688 | 864084.4 | 0 | 0 | 1010407036 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 0 | 100 | 2019-11-13 | 2021-02-05 | 2023-01-23 | 2023-01-23 |  |  |  |  | 45.898 | 24.384 | Failed | No
2300241474 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 198005 | 9900.25 | 0 | 0 | 1010407036 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 0 | 100 | 2019-11-13 | 2021-02-05 | 2023-02-21 | 2023-02-21 |  |  |  |  | 45.898 | 24.384 | Failed | No
2100055414 | جامعة جدة | تشييد | ذات اولوية متوسطة | 43000000 | 2150000 | 43000000 | 43000000 | 4031052995 | لا | 0 | 180409003124 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2016-04-11 | 2018-03-21 | 2018-03-21 | 2018-03-21 | 2018-03-21 |  | لا يوجد تأخير |  | 21.8911 | 39.2563 | منجز | No
2300240903 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 50096193 | 2504809.65 | 8516352.81 | 8516335 | 1010267848 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 17 | 25 | 2022-01-12 | 2024-05-19 | 2024-12-19 | 2024-12-19 |  |  |  |  | 39.6005 | 24.4595 | متأخر | No
2300241485 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 10056150 | 502807.5 | 0 | 0 | 1010149483 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 61 | 100 | 2014-10-13 | 2017-02-15 | 2022-08-01 | 2022-08-01 |  |  |  |  | 44.888 | 22.8622 | Failed | No
2300240936 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 11795844.5 | 589792.225 | 4600379.355 | 4600379.355 | 1131009849 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 39 | 46 | 2023-03-21 | 2023-07-21 | 2024-01-21 | 2024-01-21 |  |  |  |  | 39.6005 | 24.4595 | متأخر | No
2300241496 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1958360 | 97918 | 0 | 0 | 1010149483 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 2 | 100 | 2018-10-08 | 2020-10-04 | 2023-03-23 | 2023-03-23 |  |  |  |  | 44.888 | 22.8622 | Failed | No
2300241500 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 626220 | 31311 | 0 | 0 | 1010324989 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 95 | 100 | 2020-01-22 | 2022-01-11 | 2022-01-11 | 2022-01-11 |  |  |  |  | 44.888 | 22.8622 | Failed | No
2300241511 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 315300 | 15765 | 0 | 0 | 1117002589 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 0 | 100 | 2020-02-16 | 2021-04-17 | 2022-01-17 | 2022-01-17 |  |  |  |  | 45.3898 | 23.6574 | Failed | No
2300241522 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1044317 | 52215.85 | 94812.9 | 94812.9 | 1013001518 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 21 | 100 | 2019-08-25 | 2021-04-18 | 2022-01-17 | 2022-01-17 |  |  |  |  | 45.3898 | 23.6574 | Failed | No
2300241533 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 997500 | 49875 | 0 | 0 | 1013001518 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 0 | 77 | 2015-08-12 | 2016-06-13 | 2016-06-13 | 2016-06-13 |  |  |  |  | 45.3898 | 23.6574 | Failed | No
2300241544 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1907690 | 95384.5 | 849165.0575 | 849165.0575 | 1010056094 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 50 | 100 | 2015-08-06 | 2019-10-12 | 2022-01-17 | 2022-01-17 |  |  |  |  | 45.3898 | 23.6574 | Failed | No
2300241555 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3850150 | 192507.5 | 0 | 0 | 1010056094 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 60 | 100 | 2015-10-15 | 2020-03-06 | 2020-03-06 | 2020-03-06 |  |  |  |  | 46.0993 | 22.9877 | Failed | No
2300241566 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 94994220 | 4749711 | 0 | 0 | 1010202928 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 92 | 100 | 2014-11-11 | 2017-09-09 | 2022-05-15 | 2022-05-15 |  |  |  |  | 47.3248 | 24.1576 | متأخر | No
2300241570 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 14802650 | 740132.5 | 0 | 0 | 1010209661 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 0 | 100 | 2019-09-24 | 2024-09-22 | 2024-09-22 | 2024-09-22 |  |  |  |  | 47.2957 | 24.1357 | Failed | No
2300241581 | الهيئة الملكية لمحافظة العلا | تصميم وتشييد | ذات اولوية متوسطة | 33018900.05 | 1650945.0025 | 15500212.6 | 15500212.6 | 1010010521 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 62 | 78 | 2022-07-14 | 2023-04-10 | 2023-05-18 | 2023-05-18 |  |  |  |  | 37.8648 | 26.7432 | متأخر | No
2300241076 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 74976890.1 | 3748844.505 | 74976890.1 | 74976890.1 | 1010052246 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-05-29 | 2022-06-14 | 2024-03-14 | 2024-03-14 | 2022-06-14 |  |  |  | 39.6005 | 24.4595 | منجز | No
2300241592 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 6990000 | 349500 | 3108000 | 3108000 | 1010101252 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 70 | 100 | 2019-07-04 | 2021-11-22 | 2022-05-31 | 2022-05-31 |  |  |  |  | 47.3233 | 24.1903 | Failed | No
2300241603 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 28995100 | 1449755 | 8152529.7 | 8152529.7 | 1011012161 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 88 | 100 | 2019-01-03 | 2022-05-21 | 2022-07-19 | 2022-07-19 |  |  |  |  | 47.341 | 24.1733 | متأخر | No
2300241614 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 15208050 | 760402.5 | 4547918.84 | 4547918.84 | 1011012161 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 66 | 100 | 2019-05-19 | 2023-01-29 | 2023-01-29 | 2023-01-29 |  |  |  |  | 47.3248 | 24.1576 | Failed | No
2300241706 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1116810 | 55840.5 | 211346.4 | 211346.4 | 1011012750 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 40 | 100 | 2020-02-19 | 2024-03-23 | 2024-03-23 | 2024-03-23 |  |  |  |  | 47.1557 | 23.9766 | Failed | No
2300241625 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 6334000 | 316700 | 2135175 | 2135175 | 1010101252 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 37 | 100 | 2019-11-04 | 2022-01-08 | 2024-01-13 | 2024-01-13 |  |  |  |  | 47.2998 | 24.1657 | Failed | No
2300241636 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 29229500 | 1461475 | 2524619.52 | 2524619.52 | 1010234015 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 17 | 100 | 2019-02-11 | 2021-04-17 | 2023-02-21 | 2023-02-21 |  |  |  |  | 47.3248 | 24.1576 | Failed | No
2300241640 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 69962737 | 3498136.85 | 4219425 | 4219425 | 1011012750 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 11 | 100 | 2019-09-03 | 2023-11-17 | 2023-11-17 | 2023-11-17 |  |  |  |  | 47.3248 | 24.1576 | Failed | No
2300241150 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 55084983.8 | 2754249.19 | 49025635.58 | 49025635.58 | 4030140655 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 89 | 95 | 2020-07-13 | 2024-03-25 | 2025-03-24 | 2025-03-24 |  |  |  |  | 39.6005 | 24.4595 | متأخر | No
2300241651 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 983740 | 49187 | 0 | 0 | 1115001965 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 80 | 100 | 2018-10-23 | 2020-04-17 | 2020-04-17 | 2020-04-17 |  |  |  |  | 46.5363 | 24.7481 | Failed | No
2300241662 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4387551 | 219377.55 | 0 | 0 | 1010231660 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 81 | 100 | 2014-09-22 | 2016-05-30 | 2023-02-01 | 2023-02-01 |  |  |  |  | 46.5388 | 24.7507 | Failed | No
2300241183 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 4500000 | 225000 | 3780000 | 3780000 | 1010425494 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 84 | 90 | 2022-01-26 | 2023-07-28 | 2024-07-28 | 2024-07-28 |  |  |  |  | 39.6005 | 24.4595 | متأخر | No
2300241673 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 12441625 | 622081.25 | 0 | 0 | 1011000444 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 6 | 11 | 2014-09-30 | 2016-09-19 | 2016-09-16 | 2016-09-16 |  |  |  |  | 47.1557 | 23.9766 | Failed | No
2300241684 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3924784 | 196239.2 | 0 | 0 | 1010279126 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 83 | 100 | 2015-06-23 | 2016-09-01 | 2016-09-01 | 2016-09-01 |  |  |  |  | 47.1557 | 23.9766 | Failed | No
2300241695 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 10559725 | 527986.25 | 0 | 0 | 1011000444 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 19 | 100 | 2019-12-18 | 2022-02-21 | 2022-02-21 | 2022-02-21 |  |  |  |  | 47.1557 | 23.9766 | Failed | No
2300241253 | أمانة / المدينة المنورة | تشييد | ذات اولوية متوسطة | 3836400 | 191820 | 3414396 | 3414396 | 4650030480 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 89 | 90 | 2022-02-28 | 2023-02-28 | 2023-02-28 | 2023-02-28 |  |  |  |  | 39.6005 | 24.4595 | منتظم | No
2300241710 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 12832000 | 641600 | 0 | 0 | 1010101252 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 53 | 100 | 2020-03-15 | 2022-08-03 | 2022-08-03 | 2022-08-03 |  |  |  |  | 47.1557 | 23.9766 | Failed | No
2200236073 | وزارة الرياضة | تصميم وإشراف | ذات اولوية عالية | 16730200 | 836510 | 635950 | 635950 | 1010425026 | لا | 0 |  | جاري | التكلفة المفوترة | 8.33 | 8.33 | 2022-06-21 | 2025-12-04 | 2025-12-04 | 2025-12-04 |  |  |  |  | 46.7264 | 24.6598 | منتظم | No
2300241721 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1715000 | 85750 | 714745.2 | 714745.2 | 1010381102 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 39 | 39 | 2020-09-21 | 2022-03-21 | 2022-03-21 | 2022-03-21 |  |  |  |  | 44.4182 | 24.5167 | Failed | No
2300241732 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 547700 | 27385 | 0 | 0 | 1116001509 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 87 | 100 | 2021-01-19 | 2021-06-18 | 2022-04-04 | 2022-04-04 |  |  |  |  | 44.4302 | 24.5311 | Failed | No
2300241743 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1197000 | 59850 | 125400 | 125400 | 1010315853 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 50 | 100 | 2020-07-08 | 2020-12-05 | 2022-04-11 | 2022-04-11 |  |  |  |  | 44.4182 | 24.5167 | Failed | No
2300241754 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 13693832 | 684691.6 | 0 | 0 | 1116001737 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 0 | 100 | 2019-06-20 | 2021-08-24 | 2024-04-24 | 2024-04-24 |  |  |  |  | 44.4182 | 24.5167 | Failed | No
2300241765 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 8037765 | 401888.25 | 3489357.27 | 3489357.27 | 1116001737 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 77 | 100 | 2019-11-11 | 2021-04-06 | 2022-04-19 | 2022-04-19 |  |  |  |  | 44.3877 | 24.5211 | Failed | No
2300241776 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2959240 | 147962 | 0 | 0 | 1116001737 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 40 | 100 | 2019-06-13 | 2020-08-06 | 2022-05-19 | 2022-05-19 |  |  |  |  | 44.3877 | 24.5223 | Failed | No
2100196103 | وزارة الرياضة | ترميم | ذات اولوية متوسطة | 4199409 | 209970.45 | 2505958.1 | 2505958.1 | 1010144692 | لا | 0 | 210601142814 | ايقاف جزئي | التكلفة المفوترة | 80 | 80 | 2021-06-02 | 2021-12-01 | 2023-05-01 | 2023-05-01 |  |  |  |  | 50.0017 | 26.5652 | منتظم | No
2100065516 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 74955000 | 3747750 | 67406143.6 | 67406143.6 | 1010171813 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 100 | 100 | 2017-11-16 | 2019-10-25 | 2020-08-18 | 2020-08-18 |  |  |  |  | 46.6786 | 24.7057 | Failed | No
2300241780 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 245700 | 12285 | 0 | 0 | 1116010350 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 80 | 100 | 2020-12-31 | 2022-06-24 | 2022-06-24 | 2022-06-24 |  |  |  |  | 44.3945 | 24.5173 | Failed | No
2300241791 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 655300 | 32765 | 257565 | 257565 | 4031044308 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 77 | 100 | 2019-10-20 | 2021-03-15 | 2021-03-15 | 2021-03-15 |  |  |  |  | 44.4182 | 24.5167 | Failed | No
2100033014 | الرئاسة العامة لهيئة الأمر بالمعروف والنهي عن المنكر | تشييد | ذات اولوية متوسطة | 7127013 | 356350.65 | 3170576 | 2861583.24 | 1010180774 | نعم | 6158563.46 | 180501008471 | مسحوب | الكميات التي تم تركيبها | 70 | 80 | 2018-09-04 | 2019-11-28 | 2022-12-31 | 2022-12-31 |  |  | تأخرصرف المستحقات المالية | مخطط لسحبه وإعادة ترسيته | 49.5493 | 25.6021 | مسحوب | No
2100096681 | الرئاسة العامة لهيئة الأمر بالمعروف والنهي عن المنكر | تشييد | ذات اولوية متوسطة | 15394694 | 769734.7 | 4514025 | 4446615.21 | 2251029920 | نعم | 1977173.52 | 180501008471 | جاري | الكميات التي تم تركيبها | 74 | 100 | 2018-09-04 | 2020-01-27 | 2022-12-31 | 2022-12-31 |  |  | تأخرصرف المستحقات المالية | تم تمديد الجدول الزمني | 50.0314 | 26.5228 | Failed | No
2300241802 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4999050 | 249952.5 | 0 | 0 | 1116004922 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 0 | 100 | 2015-07-30 | 2016-10-22 | 2016-10-22 | 2016-10-22 |  |  |  |  | 44.4182 | 24.5167 | Failed | No
2200235804 | جامعة الجوف | أخرى | ذات اولوية عالية | 3446550 | 172327.5 | 800000 | 0 | 7001586028 | لا | 0 |  | جاري | تكلفة العمل المنجز | 50 | 50 | 2022-10-10 | 2023-03-10 | 2023-03-10 | 2023-03-10 |  |  |  |  | 40.045 | 29.7907 | خدمات عامة | Yes
2100003183 | الرئاسة العامة لهيئة الأمر بالمعروف والنهي عن المنكر | تشييد | ذات اولوية متوسطة | 13745395.51 | 687269.7755 | 2535199.89 | 2535199.89 | 1010183010 | نعم | 4420138.3 | 180301000546 | مسحوب | الكميات التي تم تركيبها | 54 | 81 | 2018-09-24 | 2020-01-17 | 2022-06-30 | 2022-06-30 |  |  | تأخرصرف المستحقات المالية | مخطط لسحبه وإعادة ترسيته | 44.2103 | 26.7906 | مسحوب | No
2300241813 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2133700 | 106685 | 0 | 0 | 1116010334 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 7 | 100 | 2019-05-29 | 2023-02-11 | 2021-10-17 | 2021-10-17 |  |  |  |  | 44.4182 | 24.5167 | Failed | No
2100057794 | الرئاسة العامة لهيئة الأمر بالمعروف والنهي عن المنكر | تشييد | ذات اولوية متوسطة | 18365934.4 | 918296.72 | 12138355 | 11891077.77 | 1010223501 | لا | 0 | 180709021987 | جاري | الكميات التي تم تركيبها | 68 | 100 | 2015-07-31 | 2018-08-11 | 2022-02-28 | 2022-02-28 |  |  | تأخرصرف المستحقات المالية | تم تمديد الجدول الزمني | 45.878 | 25.7016 | Failed | No
2300241824 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2251139 | 112556.95 | 0 | 0 | 1010209661 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 81 | 100 | 2020-12-06 | 2023-01-31 | 2023-01-31 | 2023-01-31 |  |  |  |  | 44.4182 | 24.5167 | متأخر | No
2100070066 | الرئاسة العامة لهيئة الأمر بالمعروف والنهي عن المنكر | تشييد | ذات اولوية متوسطة | 25299254 | 1264962.7 | 12536627.5 | 12536627.5 | 1010005046 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 75 | 100 | 2015-03-10 | 2023-03-06 | 2024-05-01 | 2024-05-01 |  |  | تأخرصرف المستحقات المالية | تم تمديد الجدول الزمني | 42.1659 | 22.7262 | Failed | No
2300241835 | الهيئة العامة للطيران المدني | توريد وتركيب | ذات اولوية عالية | 33516369 | 1675818.45 | 5055661 | 4455391 | 0 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 44 | 32 | 2023-05-09 | 2023-08-09 | 2023-08-09 | 2023-08-09 |  |  |  |  | 49.7972 | 26.4683 | منتظم | No
2100008315 | الرئاسة العامة لهيئة الأمر بالمعروف والنهي عن المنكر | تشييد | ذات اولوية متوسطة | 8334186 | 416709.3 | 6428364.18 | 6428364.18 | 1010110645 | لا | 0 | 180609013130 | مسحوب | الكميات التي تم تركيبها | 86 | 100 | 2013-02-19 | 2014-10-12 | 2022-01-31 | 2022-01-31 |  |  | ضعف كفاءة المقاول المالية لتسيير الأعمال | تم إعادة ترسيته | 46.566 | 24.7529 | مسحوب | No
2300241846 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 14485000 | 724250 | 0 | 0 | 1010197183 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 32 | 87 | 2019-09-19 | 2022-11-27 | 2022-11-27 | 2022-11-27 |  |  |  |  | 44.4182 | 24.5167 | Failed | No
2300241861 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 798000 | 39900 | 0 | 0 | 1010315853 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 35 | 100 | 2020-03-18 | 2022-04-11 | 2020-08-31 | 2020-08-31 |  |  |  |  | 44.4182 | 24.5167 | Failed | No
2300241872 | الرئاسة العامة لهيئة الأمر بالمعروف والنهي عن المنكر | ترميم | ذات اولوية عالية | 849798 | 42489.9 | 0 | 0 | 0 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 5 | 100 | 2023-01-04 | 2023-10-26 | 2023-10-26 | 2023-10-26 |  |  |  |  | 45.3731 | 25.8759 | Failed | No
2300241905 | جامعة جدة | تصميم وإشراف | ذات اولوية منخفضة | 4987830 | 249391.5 | 824457.61 | 0 | 4030276223 | لا | 0 | 220739608793 | جاري | التكلفة المفوترة | 20 | 20 | 2022-09-15 | 2023-09-15 | 2023-09-15 | 2023-09-15 |  |  |  |  | 39.2579 | 21.8921 | منتظم | Yes
2100031776 | مستشفى الملك فيصل التخصصي ومركز الأبحاث | تشييد | ذات اولوية عالية | 226840000 | 11342000 | 105562806.65 | 103224638.88 | 1010005046 | لا | 0 | 180701023263 | ايقاف جزئي | منهجية القيمة المكتسبة | 71.99 | 88.93 | 2019-01-15 | 2021-01-13 | 2023-04-30 | 2023-04-30 |  |  | تغيرات في نطاق المشروع |  | 46.6699 | 24.6688 | متأخر | No
2100097366 | مستشفى الملك فيصل التخصصي ومركز الأبحاث | تشييد | ذات اولوية عالية | 26330726 | 1316536.3 | 21608742.09 | 21547742.09 | 1131020873 | لا | 0 | 190309099319 | ايقاف كلي | منهجية القيمة المكتسبة | 90 | 100 | 2018-02-05 | 2018-10-02 | 2023-04-30 | 2023-04-30 |  |  | تأخرصرف المستحقات المالية |  | 46.6701 | 24.6709 | Failed | No
2100089784 | الهيئة الملكية لمدينة الرياض | تشييد | ذات اولوية عالية | 2095170646.69 | 104758532.3345 | 2095170646.69 | 2095170646.69 | 1010079853 | لا | 0 | 190109010576 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2017-03-01 | 2019-02-06 | 2021-02-26 | 2021-02-26 | 2019-02-06 |  |  |  | 46.7626 | 24.7631 | منجز | No
2100095804 | وزارة الصحة / الرياض | تشييد | ذات اولوية متوسطة | 39204641 | 1960232.05 | 31770377 | 31770377 | 1010305737 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 90 | 100 | 2014-11-30 | 2016-11-30 | 2021-03-07 | 2021-03-07 |  |  | تأخرصرف المستحقات المالية |  | 46.7098 | 24.6275 | Failed | No
2100000836 | الهيئة الملكية لمدينة الرياض | تشييد | ذات اولوية عالية | 58471396.45 | 2923569.8225 | 14908065.61 | 14908065.61 | 1010085982 | لا | 0 | 190209009503 | فسخ العقد | اخرى | 21.17 | 69 | 2018-09-20 | 2021-08-17 | 2021-05-23 | 2021-05-23 |  |  | التنسيق مع أصحاب المصلحه (خدمات |  | 46.6184 | 24.8715 | مسحوب | No
2300241920 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 1245832 | 62291.6 | 829207.5 | 224227 | 5806004553 | لا | 0 | 211001271515 | جاري | الكميات التي تم تركيبها | 75 | 90 | 2021-08-29 | 2022-02-22 | 2023-03-01 | 2023-03-01 |  |  |  |  | 41.4362 | 19.756 | متأخر | No
2300241931 | أمانة / الباحة | تشييد | ذات اولوية متوسطة | 1245832 | 62291.6 | 829207.5 | 224227 | 5806004553 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 75 | 90 | 2021-08-29 | 2022-02-22 | 2023-03-01 | 2023-03-01 |  |  |  |  | 41.4362 | 19.756 | متأخر | No
2300241850 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2680875 | 134043.75 | 1557697.63 | 1557697.63 | 1116010334 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 82 | 100 | 2019-05-29 | 2022-08-16 | 2022-08-16 | 2022-08-16 |  |  |  |  | 44.4182 | 24.5167 | متأخر | No
2300241942 | أمانة / الرياض | تشييد | ذات اولوية عالية وعاجلة | 8297200 | 414860 | 977992.8 | 977992.8 | 1010015152 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 11 | 100 | 2014-08-21 | 2020-07-25 | 2020-07-25 | 2020-07-25 |  |  |  |  | 44.4182 | 24.5167 | Failed | No
2300241953 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4960630 | 248031.5 | 0 | 0 | 1116004922 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 14 | 100 | 2014-09-15 | 2017-03-06 | 2017-03-06 | 2017-03-06 |  |  |  |  | 44.4182 | 24.5167 | Failed | No
2300241964 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1769885 | 88494.25 | 445412 | 445412 | 1111000637 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 91 | 100 | 2020-01-23 | 2021-07-02 | 2022-04-11 | 2022-04-11 |  |  |  |  | 45.5158 | 23.5419 | Failed | No
2300241975 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 75785205 | 3789260.25 | 11048606.905 | 11048606.905 | 1010149483 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 36 | 100 | 2019-10-22 | 2022-06-09 | 2022-06-09 | 2022-06-09 |  |  |  |  | 45.5158 | 23.5419 | Failed | No
2300241986 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 17449761 | 872488.05 | 1528538 | 1528538 | 1010256208 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 33 | 100 | 2022-04-16 | 2023-01-19 | 2023-01-19 | 2023-01-19 |  |  |  |  | 44.8318 | 26.3099 | Failed | No
2300241990 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 19999536 | 999976.8 | 0 | 0 | 1010263223 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 0 | 100 | 2015-07-26 | 2017-01-16 | 2017-01-16 | 2017-01-16 |  |  |  |  | 45.5629 | 20.4669 | Failed | No
2300242001 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1315145 | 65757.25 | 0 | 0 | 1017000207 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 21 | 100 | 2020-09-22 | 2022-09-12 | 2022-09-12 | 2022-09-12 |  |  |  |  | 45.5629 | 20.4669 | Failed | No
2300242012 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3950520 | 197526 | 0 | 0 | 1017000207 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 19 | 100 | 2020-08-09 | 2024-08-31 | 2024-08-31 | 2024-08-31 |  |  |  |  | 45.5629 | 20.4669 | Failed | No
2300242023 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 599199 | 29959.95 | 235839 | 235839 | 1010242510 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 92 | 100 | 2020-02-25 | 2021-05-06 | 2022-03-31 | 2022-03-31 |  |  |  |  | 46.3193 | 24.804 | Failed | No
2300242034 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 18856474 | 942823.7 | 7619297.98 | 7619297.98 | 1010041430 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 85 | 100 | 2019-07-07 | 2023-07-17 | 2023-07-17 | 2023-07-17 |  |  |  |  | 46.3972 | 24.8987 | متأخر | No
2300242130 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 28560000 | 1428000 | 946699.38 | 946699.38 | 1010101252 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 3 | 68 | 2020-08-25 | 2024-03-30 | 2024-03-30 | 2024-03-30 |  |  |  |  | 45.3731 | 25.8759 | Failed | No
2300242045 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1732142 | 86607.1 | 0 | 0 | 1114000037 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 37 | 100 | 2014-08-30 | 2016-05-07 | 2020-04-03 | 2020-04-03 |  |  |  |  | 46.3906 | 24.9018 | Failed | No
2300242056 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2769942 | 138497.1 | 0 | 0 | 1010318603 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 50 | 100 | 2020-09-09 | 2021-12-03 | 2022-08-17 | 2022-08-17 |  |  |  |  | 45.2806 | 24.0671 | Failed | No
2300242060 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 29950368 | 1497518.4 | 0 | 0 | 1010373330 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 0 | 52 | 2020-02-15 | 2021-05-10 | 2021-05-21 | 2021-05-21 |  |  |  |  | 45.2806 | 24.0671 | Failed | No
2300242071 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 253171825 | 12658591.25 | 16270464.813 | 16270464.813 | 1010177200 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 88 | 100 | 2014-08-03 | 2017-09-04 | 2022-05-01 | 2022-05-01 |  |  |  |  | 45.2927 | 24.0752 | متأخر | No
2300242082 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 723348546 | 36167427.3 | 3721741.65 | 3721741.65 | 1010177200 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 80 | 100 | 2015-04-16 | 2017-09-02 | 2022-05-01 | 2022-05-01 |  |  |  |  | 45.2806 | 24.0671 | متأخر | No
2300242093 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 6708640 | 335432 | 1924991.25 | 1924991.25 | 1117001926 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 48 | 100 | 2019-06-26 | 2021-06-03 | 2022-01-26 | 2022-01-26 |  |  |  |  | 45.2806 | 24.0671 | Failed | No
2100083963 | جامعة نجران | تشييد | ذات اولوية عالية | 22012000 | 1100600 | 5973208 | 5973208 | 2066001761 | لا | 0 | 181209511458 | جاري | الكميات التي تم تركيبها | 84 | 100 | 2017-10-02 | 2018-06-25 | 2022-05-07 | 2022-05-07 |  |  | تأخرصرف المستحقات المالية |  | 44.2341 | 17.5757 | Failed | No
2300242104 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 743479901 | 37173995.05 | 11077919.51 | 11077919.51 | 1010149483 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 25 | 100 | 2019-11-13 | 2022-01-17 | 2022-01-26 | 2022-01-26 |  |  |  |  | 45.2806 | 24.0671 | Failed | No
2300242115 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 35503560 | 1775178 | 6049220.7 | 6049220.7 | 1010149483 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 22 | 100 | 2019-08-25 | 2022-02-18 | 2022-02-18 | 2022-02-18 |  |  |  |  | 45.2806 | 24.0671 | Failed | No
2100054202 | مستشفى الملك فيصل التخصصي ومركز الأبحاث | تصميم | ذات اولوية عالية | 20184000 | 1009200 | 15675198 | 14949998 | 4030216250 | لا | 0 |  | جاري | تكلفة العمل المنجز | 80 | 80 | 2015-05-17 | 2015-11-16 | 2024-09-01 | 2024-09-01 |  |  | تأخرصرف المستحقات المالية |  | 39.1737 | 21.7414 | منتظم | No
2300242126 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4926600 | 246330 | 0 | 0 | 1010943550 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 11 | 70 | 2021-01-05 | 2023-12-21 | 2023-12-21 | 2023-12-21 |  |  |  |  | 45.3577 | 25.8889 | Failed | No
2300242141 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2433850 | 121692.5 | 276000 | 276000 | 1122001367 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 25 | 30 | 2020-01-26 | 2021-07-05 | 2022-06-19 | 2022-06-19 |  |  |  |  | 46.2732 | 24.4714 | Failed | No
2100104705 | مستشفى الملك فيصل التخصصي ومركز الأبحاث | تشييد | ذات اولوية عالية | 3783576880 | 189178844 | 2053106262.61 | 1904438053.85 | 4030068284 | لا | 0 | 180709019455 | جاري | منهجية القيمة المكتسبة | 46 | 67 | 2013-06-01 | 2016-05-30 | 2024-04-30 | 2024-04-30 |  |  | تأخرصرف المستحقات المالية |  | 39.1723 | 21.7432 | متأخر | No
2300242152 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3013160 | 150658 | 120506 | 120506 | 1122001367 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 25 | 27 | 2020-02-09 | 2021-07-19 | 2022-07-18 | 2022-07-18 |  |  |  |  | 46.2732 | 24.4714 | Failed | No
2300242163 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1975400 | 98770 | 303000 | 303000 | 1122001367 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 30 | 39 | 2019-12-08 | 2021-05-17 | 2022-07-25 | 2022-07-25 |  |  |  |  | 46.2732 | 24.4714 | Failed | No
2300242174 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3600000 | 180000 | 0 | 0 | 1010265792 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 19 | 100 | 2019-06-17 | 2021-02-22 | 2022-03-20 | 2022-03-20 |  |  |  |  | 46.2732 | 24.4714 | Failed | No
2300242185 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1569570 | 78478.5 | 0 | 0 | 1010015152 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 51 | 58 | 2019-09-24 | 2021-06-01 | 2022-07-18 | 2022-07-18 |  |  |  |  | 46.2732 | 24.4714 | Failed | No
2300242196 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1583100 | 79155 | 0 | 0 | 1010242510 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 0 | 93 | 2019-06-23 | 2021-02-28 | 2022-06-20 | 2022-06-20 |  |  |  |  | 46.2732 | 24.4714 | Failed | No
2300242200 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1739200 | 86960 | 0 | 0 | 1114000037 | لا | 0 |  | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 54 | 100 | 2013-12-16 | 2016-06-20 | 2016-06-20 | 2016-06-20 |  |  |  |  | 45.9658 | 21.9868 | Failed | No
2300242211 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 375420 | 18771 | 0 | 0 | 1015000676 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 1 | 100 | 2020-02-18 | 2020-10-31 | 2022-01-18 | 2022-01-18 |  |  |  |  | 45.9658 | 21.9868 | Failed | No
2300239304 | أمانة / الجوف | تشييد | ذات اولوية عالية وعاجلة | 8676556 | 433827.8 | 3400000 | 3400000 | 3450009076 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 62 | 66 | 2022-05-22 | 2023-05-21 | 2023-05-21 | 2023-05-21 |  |  |  |  | 39.8888 | 29.8108 | منتظم | No
2300242550 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 930050 | 46502.5 | 0 | 0 | 1118001032 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 88 | 100 | 2013-05-07 | 2014-10-05 | 2014-10-05 | 2014-10-05 |  |  |  |  | 43.8176 | 25.0131 | Failed | No
2300242222 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 179000 | 8950 | 0 | 0 | 1015000676 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 0 | 100 | 2020-02-18 | 2020-08-16 | 2022-01-18 | 2022-01-18 |  |  |  |  | 45.9658 | 21.9868 | Failed | No
2300242233 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 6324385 | 316219.25 | 0 | 0 | 1011012750 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 29 | 99 | 2019-12-30 | 2023-07-23 | 2023-07-23 | 2023-07-23 |  |  |  |  | 47.2298 | 24.1639 | Failed | No
2300242244 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3981290 | 199064.5 | 0 | 0 | 1011007483 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 25 | 100 | 2020-02-04 | 2021-04-15 | 2021-04-15 | 2021-04-15 |  |  |  |  | 47.2298 | 24.1639 | Failed | No
2300242255 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4473657 | 223682.85 | 1068135.6 | 1068135.6 | 1011012161 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 68 | 100 | 2019-04-10 | 2022-04-26 | 2022-04-26 | 2022-04-26 |  |  |  |  | 45.8707 | 25.2794 | Failed | No
2300242266 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1795500 | 89775 | 0 | 0 | 1010393520 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 38 | 100 | 2020-12-15 | 2024-05-30 | 2024-05-30 | 2024-05-30 |  |  |  |  | 45.4592 | 25.6834 | Failed | No
2300242270 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3188300 | 159415 | 0 | 0 | 1010223571 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 11 | 100 | 2020-03-04 | 2022-07-24 | 2022-07-24 | 2022-07-24 |  |  |  |  | 46.104 | 25.1158 | Failed | No
2300242281 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1904750 | 95237.5 | 340410 | 340410 | 1116622477 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 20 | 81 | 2019-07-04 | 2020-12-11 | 2022-06-30 | 2022-06-30 |  |  |  |  | 46.104 | 25.1158 | Failed | No
2300242292 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1234535 | 61726.75 | 0 | 0 | 4038000474 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 40 | 100 | 2020-05-04 | 2021-07-04 | 2023-01-30 | 2023-01-30 |  |  |  |  | 44.3891 | 23.489 | Failed | No
2300242303 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3178000 | 158900 | 0 | 0 | 1011000444 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 5 | 100 | 2020-07-15 | 2022-12-07 | 2022-12-07 | 2022-12-07 |  |  |  |  | 46.8447 | 23.5252 | Failed | No
2300242314 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1667800 | 83390 | 706080 | 706080 | 1011000444 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 70 | 87 | 2020-07-23 | 2021-12-31 | 2021-12-31 | 2021-12-31 |  |  |  |  | 46.8447 | 23.5252 | Failed | No
2300242325 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1900514 | 95025.7 | 290220 | 290220 | 1010258205 | لا | 0 |  | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 100 | 90 | 2020-10-18 | 2023-05-10 | 2023-05-10 | 2023-05-10 |  |  |  |  | 46.8447 | 23.5252 | منتظم | No
2300242336 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 7639550 | 381977.5 | 2986875.119 | 2986875.119 | 1010056094 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 39 | 100 | 2015-08-06 | 2019-10-12 | 2022-03-03 | 2022-03-03 |  |  |  |  | 46.8447 | 23.5252 | Failed | No
2300242340 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3863620 | 193181 | 0 | 0 | 1010245790 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 0 | 0 | 2020-12-20 | 2022-06-13 | 2022-06-13 | 2022-06-13 |  |  |  |  | 45.3787 | 25.3557 | Failed | No
2300242351 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 999400 | 49970 | 546285.2 | 546285.2 | 1120100222 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 53 | 62 | 2019-06-26 | 2020-12-05 | 2020-12-05 | 2020-12-05 |  |  |  |  | 47.1606 | 25.5637 | Failed | No
2300242362 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1798500 | 89925 | 957900 | 957900 | 1115001965 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 72 | 77 | 2019-12-23 | 2021-06-01 | 2021-06-01 | 2021-06-01 |  |  |  |  | 44.602 | 25.1859 | Failed | No
2300242373 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 684300 | 34215 | 0 | 0 | 2050063248 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 0 | 100 | 2019-11-07 | 2021-01-16 | 2021-01-16 | 2021-01-16 |  |  |  |  | 44.602 | 25.1859 | Failed | No
2300242384 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 548790 | 27439.5 | 0 | 0 | 1186100355 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 68 | 100 | 2019-07-04 | 2022-02-19 | 2022-02-19 | 2022-02-19 |  |  |  |  | 44.602 | 25.1859 | Failed | No
2300242395 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1716340 | 85817 | 0 | 0 | 1115001965 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 53 | 95 | 2020-11-12 | 2023-03-21 | 2023-03-21 | 2023-03-21 |  |  |  |  | 44.602 | 25.1859 | Failed | No
2300242406 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1100000 | 55000 | 0 | 0 | 1115001965 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 87 | 100 | 2020-11-12 | 2022-07-25 | 2022-07-08 | 2022-07-08 |  |  |  |  | 44.602 | 25.1859 | Failed | No
2300242410 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 22683931 | 1134196.55 | 0 | 0 | 1010188861 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 17 | 80 | 2020-09-17 | 2023-09-02 | 2023-09-02 | 2023-09-02 |  |  |  |  | 44.602 | 25.1859 | Failed | No
2300242421 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3237187.5 | 161859.375 | 0 | 0 | 1010290069 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 0 | 100 | 2020-07-10 | 2021-10-03 | 2021-10-03 | 2021-10-03 |  |  |  |  | 44.602 | 25.1859 | Failed | No
2300242432 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1900000 | 95000 | 621759.9045 | 621759.9045 | 1113000448 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 33 | 100 | 2019-04-08 | 2023-08-27 | 2023-08-27 | 2023-08-27 |  |  |  |  | 45.2525 | 25.2476 | Failed | No
2300242443 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 319571826 | 15978591.3 | 4335796.51 | 4335796.51 | 1010197183 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 49 | 88 | 2019-07-08 | 2023-08-08 | 2023-08-08 | 2023-08-08 |  |  |  |  | 45.2525 | 25.2476 | Failed | No
2300242454 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 3284420 | 164221 | 1299401.78 | 1299401.78 | 1113000601 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 38 | 87 | 2019-03-07 | 2020-11-12 | 2020-11-12 | 2020-11-12 |  |  |  |  | 45.2525 | 25.2476 | Failed | No
2300242465 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2041825 | 102091.25 | 0 | 0 | 1010158786 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 42 | 91 | 2022-10-16 | 2023-02-13 | 2023-02-13 | 2023-02-13 |  |  |  |  | 46.1518 | 24.6124 | Failed | No
2300242476 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2484680 | 124234 | 0 | 0 | 1116000436 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 41 | 74 | 2019-09-01 | 2021-11-05 | 2022-10-25 | 2022-10-25 |  |  |  |  | 44.6302 | 23.9073 | Failed | No
2300242480 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 11935900 | 596795 | 7129719.77 | 7129719.77 | 1118001565 | لا | 0 |  | ايقاف كلي | الكميات التي تم تركيبها | 63 | 98 | 2018-10-31 | 2021-10-16 | 2021-10-16 | 2021-10-16 |  |  |  |  | 42.9125 | 23.9052 | Failed | No
2300242491 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 371611491 | 18580574.55 | 20971057.042 | 20971057.042 | 1010203405 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 98 | 100 | 2014-09-16 | 2017-02-15 | 2022-04-02 | 2022-04-02 |  |  |  |  | 42.9125 | 23.9052 | متأخر | No
2300242502 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 37855006 | 1892750.3 | 30001966.0365 | 30001966.0365 | 1116001737 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 96 | 100 | 2013-10-20 | 2016-01-15 | 2022-04-02 | 2022-04-02 |  |  |  |  | 42.9125 | 23.9052 | متأخر | No
2300242513 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 4289709 | 214485.45 | 3526346.41 | 3526346.41 | 1113000601 | لا | 0 |  | جاري الاستلام الإبتدائي | الكميات التي تم تركيبها | 95 | 100 | 2014-09-23 | 2016-03-02 | 2022-03-18 | 2022-03-18 |  |  |  |  | 47.5446 | 23.5641 | متأخر | No
2300242524 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 116793735 | 5839686.75 | 3972419.0096 | 3972419.0096 | 1116005033 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 49 | 100 | 2019-05-28 | 2022-04-17 | 2022-04-17 | 2022-04-17 |  |  |  |  | 43.8176 | 25.0131 | Failed | No
2300242535 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 2967900 | 148395 | 0 | 0 | 1116005202 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 52 | 100 | 2019-03-17 | 2020-08-24 | 2020-08-24 | 2020-08-24 |  |  |  |  | 43.8176 | 25.0131 | Failed | No
2300242546 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 5640398 | 282019.9 | 1048000 | 1048000 | 1115001965 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 70 | 100 | 2015-01-17 | 2019-06-09 | 2016-06-09 | 2016-06-09 |  |  |  |  | 43.8176 | 25.0131 | Failed | No
2300242561 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1299470 | 64973.5 | 0 | 0 | 1017000955 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 25 | 100 | 2020-01-09 | 2022-11-19 | 2022-11-19 | 2022-11-19 |  |  |  |  | 44.8501 | 20.4493 | Failed | No
2100193955 | مستشفى الملك فيصل التخصصي ومركز الأبحاث | تصميم وإشراف | ذات اولوية عالية وعاجلة | 499220873.05 | 24961043.6525 | 437087985.18 | 415170225.9 | 1010056779 | لا | 0 | 190409033064 | جاري الاستلام الإبتدائي | تكلفة العمل المنجز | 96 | 100 | 2019-02-28 | 2022-09-30 | 2022-04-20 | 2022-04-20 |  |  |  |  | 39.524 | 24.3524 | Failed | No
2300242572 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1413237000 | 70661850 | 1401223.72 | 1401223.72 | 1185000614 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 21 | 100 | 2014-09-21 | 2017-05-24 | 2022-01-30 | 2022-01-30 |  |  |  |  | 44.8501 | 20.4493 | Failed | No
2300242583 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 5408138 | 270406.9 | 0 | 0 | 4030170053 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 0 | 100 | 2020-07-01 | 2022-06-21 | 2022-06-21 | 2022-06-21 |  |  |  |  | 46.6753 | 24.7136 | Failed | No
2300242594 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 1944000 | 97200 | 162000 | 162000 | 1010462629 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 79 | 100 | 2020-09-22 | 2022-09-12 | 2022-09-12 | 2022-09-12 |  |  |  |  | 46.6928 | 24.6568 | متأخر | No
2300242605 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 6628480 | 331424 | 1043985.5999 | 1043985.5999 | 1010348048 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 85 | 100 | 2018-02-21 | 2019-08-15 | 2019-08-15 | 2019-08-15 |  |  |  |  | 46.6753 | 24.7136 | Failed | No
2100195215 | رئاسة أمن الدولة / ديوان رئاسة أمن الدولة | تشييد | ذات اولوية عالية وعاجلة | 6043917.8 | 302195.89 | 6043917.8 | 6043917.8 | 1010235877 | لا | 0 | 190301082478 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2019-02-28 | 2019-10-28 | 2021-12-31 | 2021-12-31 | 2019-10-28 |  |  |  | 46.6679 | 24.7188 | منجز | No
2300242616 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 43974000 | 2198700 | 20390200.3632 | 20390200.3632 | 1010348048 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 67 | 100 | 2019-04-01 | 2025-01-14 | 2025-01-14 | 2025-01-14 |  |  |  |  | 46.7093 | 24.6618 | Failed | No
2300242620 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 49932000 | 2496600 | 18977900.7325 | 18977900.7325 | 1010363372 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 52 | 100 | 2019-02-03 | 2024-03-24 | 2024-03-24 | 2024-03-24 |  |  |  |  | 46.7121 | 24.6967 | Failed | No
2300242631 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 47973600 | 2398680 | 19253787.1205 | 19253787.1205 | 1010327067 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 53 | 100 | 2019-05-22 | 2025-05-21 | 2025-05-21 | 2025-05-21 |  |  |  |  | 46.7079 | 24.6805 | Failed | No
2300242642 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 7446000 | 372300 | 5007857.13 | 5007857.13 | 1010363448 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 97 | 100 | 2019-05-01 | 2022-04-15 | 2022-04-15 | 2022-04-15 |  |  |  |  | 46.6753 | 24.7136 | متأخر | No
2300242653 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 32979099 | 1648954.95 | 23245107.9898 | 23245107.9898 | 1010433483 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 100 | 100 | 2019-07-04 | 2022-06-18 | 2022-06-18 | 2022-06-18 |  |  |  |  | 46.6753 | 24.7136 | متأخر | No
2300242664 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 12816008 | 640800.4 | 3260602.8 | 3260602.8 | 1010348048 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 62 | 89 | 2020-06-01 | 2023-05-21 | 2023-05-21 | 2023-05-21 |  |  |  |  | 46.7052 | 24.6318 | Failed | No
2300242675 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 13795200 | 689760 | 0 | 0 | 1010363372 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 44 | 96 | 2020-12-01 | 2023-07-31 | 2023-07-31 | 2023-07-31 |  |  |  |  | 46.6942 | 24.6505 | Failed | No
2300242686 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 15615075 | 780753.75 | 0 | 0 | 1010435343 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 0 | 100 | 2022-01-10 | 2023-01-05 | 2023-01-05 | 2023-01-05 |  |  |  |  | 46.6753 | 24.7136 | Failed | No
2300241032 | أمانة / المدينة المنورة | تشييد | ذات اولوية عالية | 24023865.47 | 1201193.2735 | 17056944.48 | 17056944.48 | 2051058157 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 71 | 80 | 2019-11-18 | 2023-06-03 | 2023-06-03 | 2023-06-03 |  |  |  |  | 39.6005 | 24.4595 | متأخر | No
2100006882 | وزارة الدفاع / الإدارة الهندسية والاشغال بالقوات البرية | تشييد | ذات اولوية عالية | 5497965.91 | 274898.2955 | 5412375.16 | 3286752.53 | 3550024705 | لا | 0 |  | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2019-01-20 | 2020-01-08 | 2021-09-19 | 2021-09-19 | 2020-01-08 |  | تأخرصرف المستحقات المالية |  | 36.6108 | 28.4099 | منجز | No
2300242690 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 5113584 | 255679.2 | 0 | 0 | 1010183478 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 0 | 100 | 2020-11-22 | 2023-07-22 | 2023-07-22 | 2023-07-22 |  |  |  |  | 46.6753 | 24.7136 | Failed | No
2300242701 | أمانة / الرياض | دراسات هندسية | ذات اولوية عالية | 12000000 | 600000 | 0 | 0 | 0 | لا | 0 |  | جاري | اخرى | 5 | 2.52 | 2022-11-21 | 2024-11-20 | 2024-11-20 | 2024-11-20 |  |  |  |  | 46.693 | 24.6413 | منتظم | No
2100030273 | أمانة / الجوف | تشييد | ذات اولوية عالية | 775750 | 38787.5 | 775750 | 775750 | 3409006577 | لا | 0 | 181209507686 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2018-11-11 | 2019-11-10 | 2021-06-14 | 2021-06-14 | 2019-11-10 |  |  |  | 40.3803 | 30.1147 | منجز | No
2100020311 | أمانة / الجوف | دراسة الجدوى | ذات اولوية متوسطة | 675000 | 33750 | 661500 | 645187.5 | 1010250667 | لا | 0 | 181209522064 | منجز – استلام ابتدائي | تكلفة العمل المنجز | 100 | 100 | 2018-12-19 | 2019-12-18 | 2019-12-18 | 2019-12-18 | 2019-12-18 |  | اخرى |  | 39.8888 | 29.8108 | منجز | No
2300240041 | أمانة / الأحساء | توريد وتركيب | ذات اولوية متوسطة | 306360 | 15318 | 306360 | 239040 | 2050032600 | لا | 0 |  | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2022-10-23 | 2023-01-23 | 2023-03-23 | 2023-03-23 | 2023-01-23 |  |  |  | 49.5902 | 25.3709 | منجز | No
2100091011 | أمانة / الرياض | تشييد | ذات اولوية متوسطة | 219310002.16 | 10965500.108 | 197379001.94 | 197379001.94 | 1010253433 | لا | 0 | 180809042599 | منجز – استلام ابتدائي | الكميات التي تم تركيبها | 100 | 100 | 2014-08-13 | 2021-03-09 | 2019-12-17 | 2019-12-17 | 2021-03-09 |  |  |  | 46.6773 | 24.7057 | منجز | No
2100087916 | الهيئة الملكية لمدينة الرياض | تشييد | ذات اولوية عالية | 33132056.35 | 1656602.8175 | 26671206 | 26671206 | 4030034104 | لا | 0 | 190209009460 | منجز – استلام نهائي | اخرى | 100 | 100 | 2018-07-08 | 2021-06-04 | 2021-06-25 | 2021-06-25 | 2021-06-04 | 2022-05-25 | لا يوجد تأخير |  | 46.676 | 24.5708 | منجز | No
2300242723 | الرئاسة العامة لهيئة الأمر بالمعروف والنهي عن المنكر | تشييد | ذات اولوية متوسطة | 499599.17 | 24979.9585 | 0 | 0 | 1011009562 | نعم | 3565427.85 |  | جاري | الكميات التي تم تركيبها | 30 | 100 | 2022-08-11 | 2023-04-16 | 2023-04-16 | 2023-04-16 |  |  |  | أخرى | 46.5363 | 24.7481 | Failed | No
2300242734 | أمانة / حائل | تشييد | ذات اولوية عالية | 897368 | 44868.4 | 556320 | 556320 | 0 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 93 | 100 | 2022-06-01 | 2023-05-26 | 2023-05-26 | 2023-05-26 |  |  |  |  | 40.9611 | 28.0267 | منتظم | No
2300242712 | الرئاسة العامة لهيئة الأمر بالمعروف والنهي عن المنكر | تشييد | ذات اولوية متوسطة | 1420020 | 71001 | 308943.89 | 0 | 1011009562 | نعم | 2932850.6 |  | جاري | الكميات التي تم تركيبها | 40 | 100 | 2022-08-18 | 2023-04-14 | 2023-04-14 | 2023-04-14 |  |  |  | أخرى | 46.2732 | 24.4714 | Failed | Yes
2200226940 | المؤسسة العامة لتحلية المياه المالحة | تشييد | ذات اولوية عالية | 334000000 | 16700000 | 168639850.92 | 168639850.92 | 1010011560 | لا | 0 | 200301067834 | جاري | منهجية القيمة المكتسبة | 64.4 | 64.4 | 2020-11-03 | 2022-10-30 | 2023-06-30 | 2023-06-30 |  |  |  |  | 39.5355 | 20.6903 | منتظم | No
2300240063 | المؤسسة العامة لتحلية المياه المالحة | تشييد | ذات اولوية عالية | 390011420 | 19500571 | 117370220.06 | 117370220.06 | 7018061536 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 70.9 | 70.9 | 2021-06-27 | 2022-12-27 | 2023-10-02 | 2023-10-02 |  |  |  |  | 38.19 | 24.0232 | منتظم | No
2300240144 | المؤسسة العامة لتحلية المياه المالحة | تشييد | ذات اولوية عالية | 2686000000 | 134300000 | 139600144.03 | 99274404.55 | 1010011560 | لا | 0 |  | جاري | منهجية القيمة المكتسبة | 17.51 | 20.56 | 2021-08-25 | 2024-08-24 | 2024-08-24 | 2024-08-24 |  |  |  |  | 49.5687 | 26.9598 | منتظم | No
2300242745 | الإدارة العامة للشؤون الإدارية والمالية | أخرى | ذات اولوية متوسطة | 1988695 | 99434.75 | 0 | 0 | 7001760086 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 50 | 65 | 2022-11-13 | 2023-03-13 | 2023-03-13 | 2023-03-13 |  |  |  |  | 46.7109 | 24.6286 | خدمات عامة | No
2300242760 | الإدارة العامة للشؤون الإدارية والمالية | ترميم | ذات اولوية متوسطة | 936718.7 | 46835.935 | 230152.58 | 0 | 1010199999 | لا | 0 |  | جاري | تكلفة العمل المنجز | 38 | 43 | 2022-11-27 | 2023-04-27 | 2023-04-27 | 2023-04-27 |  |  |  |  | 46.7109 | 24.6286 | منتظم | Yes
2300242756 | الإدارة العامة للشؤون الإدارية والمالية | تشييد | ذات اولوية عالية | 122981264.39 | 6149063.2195 | 1232000 | 0 | 1010176525 | لا | 0 |  | جاري | تكلفة العمل المنجز | 1 | 13.8 | 2022-09-18 | 2025-09-15 | 2025-09-15 | 2025-09-15 |  |  |  |  | 39.1758 | 21.5427 | متأخر | Yes
2100000033 | الهيئة الملكية لمدينة مكة المكرمة و المشاعر المقدسة | تشييد | ذات اولوية عالية وعاجلة | 161875900 | 8093795 | 88331572.582 | 86831316.507 | 4031008077 | لا | 0 | 190209005394 | جاري | منهجية القيمة المكتسبة | 61.17 | 70.52 | 2019-07-02 | 2021-07-01 | 2023-10-30 | 2023-10-30 |  |  | تأخرصرف المستحقات المالية | العقد يسير حسب الخطة | 39.814 | 21.4339 | متأخر | No
2100060546 | الهيئة الملكية لمدينة مكة المكرمة و المشاعر المقدسة | تشييد | ذات اولوية عالية وعاجلة | 237493734.474 | 11874686.7237 | 213744361.0266 | 213744361.0266 | 1010090968 | لا | 0 | 190409052109 | جاري | منهجية القيمة المكتسبة | 96.4 | 95.95 | 2018-10-16 | 2020-10-15 | 2023-02-28 | 2023-02-28 |  |  | تأخرصرف المستحقات المالية | العقد يسير حسب الخطة | 39.8261 | 21.466 | منتظم | No
2300242771 | الإدارة العامة للشؤون الإدارية والمالية | ترميم | ذات اولوية متوسطة | 13484578 | 674228.9 | 0 | 0 | 1010199999 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 3 | 9.73 | 2022-11-27 | 2024-11-27 | 2024-11-27 | 2024-11-27 |  |  |  |  | 46.7109 | 24.6286 | متأخر | No
2300242804 | الإدارة العامة للشؤون الإدارية والمالية | ترميم | ذات اولوية متوسطة | 2298447.5 | 114922.375 | 703581.5 | 703581.5 | 1116003807 | لا | 0 |  | ايقاف جزئي | اخرى | 45 | 62 | 2022-02-08 | 2023-06-08 | 2023-09-08 | 2023-09-08 |  |  |  | تم تمديد الجدول الزمني | 46.7109 | 24.6286 | متأخر | No
2300242782 | الإدارة العامة للشؤون الإدارية والمالية | توريد وتركيب | ذات اولوية عالية | 3974952 | 198747.6 | 0 | 0 | 7006947076 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 5 | 62.5 | 2022-09-04 | 2023-04-28 | 2023-04-28 | 2023-04-28 |  |  |  | تم إشعار المقاول كتابيا بالتأخير | 46.7109 | 24.6286 | Failed | No
2300242793 | الإدارة العامة للشؤون الإدارية والمالية | أخرى | ذات اولوية متوسطة | 2325730.1 | 116286.505 | 0 | 0 | 1010287690 | لا | 0 |  | جاري | الكميات التي تم تركيبها | 40 | 58 | 2022-09-25 | 2023-04-25 | 2023-04-25 | 2023-04-25 |  |  |  |  | 46.7109 | 24.6286 | خدمات عامة | No